DFID Annual Review

Title: Urban Water for Darfur (UW4D)
Programme Value: £12m		Review Date: 15 September 2017
Programme Code: 204045	Start Date: 6 August 2015	End Date: 30 June 2019

Summary of Programme Performance
Year	2015/16	2016/17	2017/18	2018/19	2019/20
Programme Score	C	B	A
Risk Rating	Moderate	Major	Major

Summary of progress and lessons learnt since last review
This was a light touch interim Annual Review, building on the review carried out in February 2017. It specifically assessed achievements against the logframe outcome and output indicator milestones and the plans for the remainder of the project. A field visit was undertaken in late July and the Project Steering Committee held in mid-September 2017.

The review confirmed that the Urban Water for Darfur project is unique, necessary, and timely in the operational context of protracted crisis in Darfur. The Master Planning process has succeeded in driving a new shift in focus, away from ad hoc emergency response for the delivery of services to strategic planning and decision-making based on data and evidence. This is acknowledged and welcomed by the State Government. In addition, the project’s focus on the whole town is recognised as essential because it integrates service provision in the now virtually permanent IDP (Internally Displaced Person) settlements which for 13 years have been treated separately by the international community. The project is delivering a fundamental shift of approach to service delivery by the State Government for relatively neglected peri-urban communities, and for the long term aid dependent IDPs. This is bringing greater sustainability and greater equity.

The annual review was based on assessment of the context, performance of partners, and of DFID in delivering the project.
Context. Over the last six months substantial progress has been made to complete the Master Plans for water and sanitation in El Fasher, with secondary attention, as agreed, to Zalingei. The State Government of North Darfur has been fully involved in the development of the Master Plans, is fully committed to their implementation including contributing financing, and is keen to see results on the ground to benefit people in the town. The Governor and Minister were well aware of the findings such as the assessment of the wellfield and the plan to incorporate a partially completed water distribution network funded several years ago from federal budgets. Communities have been engaged in planning for expansion of the water supply network including identification of sites for new tap-stands and agreements for management. In addition, officials and communities are aware of the ongoing outbreaks of Acute Watery Diarrhoea in the state which put a spotlight on the need to improve sanitation and hygiene. Mobilisation for community action to drive sanitation and hygiene behaviour change has started. Overall there continues to be substantial support as well as substantial expectations from State Government and communities to implement the Master Plans.

Partners. The implementing partners have worked hard collecting, analysing and refining a substantial amount of data and information to develop the Master Plans. UNOPS have completed an assessment of the main water sources, completed topographical and network mapping, and completed the infrastructure assessment including plans for water network expansion for both El Fasher and Zalingei. Priorities have been identified, bills of quantities drafted, and pre-qualification of national contractors started in preparation for the tender process for works in El Fasher. To bolster capacity to complete the delayed institutional and financial assessments, UNOPS hired a well-known international consulting firm who unfortunately was unable to fulfil the terms of reference, resulting in cancellation of the contract. This has caused further delays with this essential work. UNOPS has brought in an independent consultant who will finalise the assessments in the next three months, utilising a capacity building approach with greater participation by the authorities as a basis for building trust and ensuring understanding and agreement for the necessary changes. UNICEF have completed assessments of sanitation and hygiene in households, schools, health centres and public places, and drawing on the KAP survey findings, have developed a community-led behaviour change approach encompassing the entire town of El Fasher. This will link to sanitation marketing to ensure households have access to information and products to implement their improved behaviours. The assessment of the water infrastructure and management situation in the two IDP settlements is being finalised, ensuring similar service levels to the other areas of the town.

Overall, good work has been achieved in many areas but sometimes it has not been brought together or communicated effectively. Both UNICEF and UNOPS need to more clearly present and communicate their work and successes, with more clearly written briefs of key information, for state government, DFID and other interested parties. This situation still implies a continued need for greater strategic leadership to support the technical team to combine the work done and to distil and communicate the key messages. This is being resolved; UNICEF have recently changed the project manager, and have increased support from the new head of Water, Sanitation and Hygiene (WASH) and WASH manager in Khartoum; and UNOPS have engaged a strategic technical adviser to support the field based team.

Performance. DFID has continued to be proactive in providing guidance and advice to the project team. This has often been challenging to the team but has been acknowledged as constructive.

Overall the project has completed the majority of the milestones and is back on track, scoring an A. The hardest part of the project - that of developing the Master Plans - has largely been completed successfully although some consolidation is still required. This is a new approach to planning both for the State Government and largely for the UN implementing partners in the context of moving away from emergency response. By comparison, the next steps for the project with the implementation of the Master Plans is relatively straight forward and implementation is expected to proceed without delays. UNOPS are extremely experienced in water infrastructure provision and now have good expertise in institutional issues, and UNICEF are extremely experienced in implementation of water provision in IDP settlements and community-led action to achieve sanitation and hygiene behaviour change.

Over the coming year, the Master Plans for El Fasher with their related work plans and budgets for the short term (this project) form the basis for implementation, with preparations already well underway. Clear plans for implementation are required, ensuring appropriate sequencing of the capacity building aspects (such as for community management) with infrastructure provision. The Governor of North Darfur requested improvements by the next dry season in March 2018. The experience gained for El Fasher will be used to finalise the Master Plans for Zalingei and start implementation in 2018.

The project’s scope is recommended to remain the same; supporting water and sanitation master plans and implementation of the short term priorities in two towns (El Fasher and Zalingei) period, and continued management support for water service delivery in two further towns (Geneina and Nyala). A no cost extension of six months was discussed with DFID and requested by UNICEF in order to ensure adequate follow up of infrastructure and institutional issues. This will be agreed as part of the internal DFID Sudan restructuring of the water portfolio as briefly explained below.

The overall risk has been retained as major but is expected to reduce during the next year as implementation proceeds. The number of implementation uncertainties has reduced substantially since February, with a key remaining issue the condition of the TDRA pipe network[1]. Uncertainty over the status and future of the IDPs is expected to continue in the medium term although it is highly likely that many will continue to require sustainable services in the existing IDP settlements.
[1] Belonging to the Transitional Darfur Regional Authority (TDRA).
Lessons learnt
The lessons learnt are:
- Shifting well embedded approaches takes longer than expected, such as moving from service delivery as an emergency response to longer term strategic planning for service delivery, both for State Government and for implementing partners.
- The importance of sticking with a change process despite the challenges of insufficient pace and uncertainty, recognising it is a learning process and acknowledging growing commitment to the new approaches.
- The need to assess value for money over the full duration of a project, recognising that initial activities can be time and resource consuming, but are essential to embed a new approach and deliver sustainable outcomes.

Summary of recommendations for the next year
Programme delivery
1. Strengthen presentation of information and communication of key messages within the Master Plans for El Fasher. Key messages include the role of the state as service provider and the role of customers to pay for services. The Water Master Plan should integrate the assessment and plans for the two IDP settlement areas. (UNICEF/UNOPS by April 2018)
2. Finalise implementation plans for El Fasher with clear deliverables and milestones linked to the project’s logframe. Include state commitments in the implementation plans – this will increase coherency of plans and ensure all required works are completed at the right times and increase state partnership in, and ownership of, the process (UNICEF and UNOPS by April 2018).
3. Confirm final version of Knowledge, Attitude, Practice (KAP) survey for El Fasher and Zalingei, addressing concerns about inconsistency of information and clearly stating the baselines for measurement of behaviour change in the interim and final KAP surveys. (UNICEF by April 2018)
4. Consider an expert review of the Shagra wellfield water resources assessment given the importance of the study for the sustainability of the water source for the town supply as well as other uses in the catchment area. (UNOPS by April 2018)
5. Follow-up North Darfur state government commitment to fund improvements to the power supply to the El Shagra wellfield’s and to complete construction of the two storage tanks. (UNOPS, by April 2018)
6. Finalise review of tariffs for water supply in El Fasher and present clearly argued case with evidence to state government. Interim measures for financing the current budget shortfall for operations and maintenance need to be agreed, with clear budget commitments. (UNOPS by April 2018)
7. Confirm approach for community management of water kiosks and develop training package, for implementation prior to start of works. (UNOPS by April 2018)
Programme management
1. Agree a 6 month no cost extension to end December 2019 with an amendment to the Standard Administrative Arrangement (SAA). (DFID, as part of water portfolio restructuring by April 2018)
2. Continue to strengthen strategic leadership and close oversight to ensure timely project delivery. (UNICEF/UNOPS immediate and ongoing)

Carry out a fraud risk assessment of the delivery chain to identify the potential fraud and corruption risks. (DFID, UNICEF and UNOPS, during the next Annual Review)

## A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204045/documents
DevTracker Link to Log frame:	Updated logframe Quest No: 5720479

Context
Darfur suffers from multiple linked factors driving conflict, fragility, and poverty. It is a region in the west of Sudan, approximately the size of France with about 8 million people. It has suffered from 13 years of sporadic intense and low level conflict and widespread lawlessness, forcing over 2.5 million people to flee their homes and live in temporary camps, often on the outskirts of towns. An average size camp hosts about 60,000 people. There may be several camps adjacent to a town, often doubling the usual population.

The Internally Displaced Persons (IDP) camps have been managed separately to the urban areas, with separate services largely provided for free by humanitarian agencies. Over time however the IDP camps have become more permanent, and some are effectively peri-urban settlements with people integrating into the livelihood activities of the town. Due to improved security, some IDPs are returning to their homes for seasonal farming as well as maintaining a household in the urban area. Many people have grown up in the camp or become used to living in an urban area with the benefits that it provides. The availability of largely free services has created some disparity between IDPs and peri-urban residents, and in some areas IDPs have sold water to the peri-urban residents of the town as a livelihood opportunity. The Government of Sudan and the International Community is keen to encourage more sustainable approaches to basic service delivery. This includes integrated management of IDP settlements and tackling provision of services in a more sustainable way which builds systems and capacity for the longer term.

Most towns have inadequate infrastructure and what does exist has suffered from decades of insufficient investment and lack of appropriate maintenance and management. The urban water supply network often serves less than 25% of the population requiring the majority of people to rely on private sector donkey cart vendors and tankers. The vendors are charged a higher tariff by the Urban Water Authority than for households and after they add a mark-up, the price can be over eight times higher per cubic meter. The poorest people who largely live in the peri-urban areas pay the most for water.

In recognition of the water crisis in the urban areas in Darfur, DFID initiated the Darfur Urban Water Supply Project[2] from 2009-2013 with a budget of £6.6m, implemented by UNOPS. This project rehabilitated infrastructure for water supply and started to strengthen the UWA’s capacity for management in the then 3 State capitals[3] of Nyala, El Fasher, and Geneina, plus at the request of the State Government, Zalingei. Access to water was improved for 244,600 people but the project was criticised for benefiting those people already on the network. However, any expansion of the network to unserved people needed to be underpinned by rehabilitation and better management of the existing network. This project set the foundation for the current Urban Water for Darfur programme. In addition, DFID funded the Sudan Integrated Environment Programme from 2009-2014 which included a component to mitigate the impacts of drought in Darfur[4] with a budget of £3.9m implemented by UNOPS. A number of dams and water harvesting structures were rehabilitated, contributing to improving the availability of water supply to some of the key towns, including Golo dam which supplies El Fasher.
[2] Darfur Urban Water Supply Project Completion Report, DFID, December 2014, https://devtracker.dfid.gov.uk/projects/GB-1-201622/documents
[3] Darfur’s three States were subsequently divided into five States with Zalingie becoming the capital of Central Darfur. The project retained its focus on the four state capitals and did not expand to include Ed Dein.
[4] Sudan Integrated Environment Project Completion Report, DFID, June 2014, https://devtracker.dfid.gov.uk/projects/GB-1-200627/documents

The resolution of conflict, peace building, and sustainable development in Darfur is a key objective for the UK. DFID Sudan is leading the drive for new ways of working in the Darfur context of protracted crisis, working closely with key UN agencies. The Urban Water for Darfur programme contributes to this drive, implementing longer term more sustainable approaches to water supply provision in urban areas, integrating long term IDP settlements where possible, and building the capacity of State Government and communities to manage and maintain services.

The programme contributes to delivering DFID Sudan’s Business Plan for the period 2016-2020, with the vision by 2020 that Sudan’s most vulnerable and excluded people are increasingly able to meet their basic needs, sustain their livelihoods, build their resilience to crises, and engage in laying the foundations for a more democratic, inclusive and peaceful future.

Outline of the programme
The Urban Water for Darfur programme aims to improve sustainable and more equitable access to water in urban communities in Darfur, and to improve sanitation and hygiene behaviour. The integrated benefits of improved water, sanitation and hygiene are expected to contribute to improving the health of the targeted population. This along with improving security and stability will support people to build more productive livelihoods, possibly enabling them to remain in Darfur rather than to migrate.

The programme will deliver:
- Improved availability and reliability of water supply, developing a new approach to provision of services in a protracted crisis where there are large, stable IDP settlements on the outskirts of urban areas as well as unserved poor peri-urban areas. Activities include a water resources assessment, strategic planning for the whole town, prioritised rehabilitation of source and network infrastructure, management & maintenance.
- Improved equity of service provision, benefiting the most vulnerable people with explicit focus on gender equality and Leave No One Behind. Activities include expansion of the urban network to the unserved peri-urban areas (introducing water kiosks) and expansion to connect IDP settlements to a more sustainable water supply.
- Improved sustainability with full cost recovery for operations and maintenance based on a review of tariffs.
- Improved governance with strengthened accountability between the State and citizens for service delivery. The poorest people are able and willing to pay for services, currently paying more than people with a household connection.
- Strengthened capacity of the State Government at senior and technical levels to plan and develop reliable and sustainable service delivery. This focuses on a holistic approach to water supply, ensuring sustainable, climate resilient solutions with greater attention to water resources management, appropriate maintenance, and sustainability through cost recovery.
- Improved sanitation and hygiene behaviour. This includes awareness and behaviour change communication, sanitation marketing with local private sector, and hygiene promotion.

The programme will expand the urban water supply network to areas which are currently unserved in the towns of El Fasher in North Darfur and Zalingei in Central Darfur. The target areas are:
- peri-urban areas where people currently buy water from private sector donkey cart vendors and tanker trucks. By expanding the urban network with community stand-posts (water kiosks), an average household’s monthly expenditure on water is expected to decrease. The communities themselves will be supported to manage the stand-posts, paying the Urban Water Authority for the volume of water consumed. Community management will help to ensure better accountability and transparency of the funds gained from the payment of water by the consumers.
- the long term Internally Displaced Persons (IDP) settlements which are adjacent to the town where people have gained water largely for free, often selling it on to people in the peri-urban areas. Some settlements already have a connection to the town’s supply but lack a clear management and payment agreement and as a result, the supply is unreliable or non-functional. A more sustainable approach for water service delivery will be developed including community management with payment for water.

In addition, households already connected to the urban network will benefit from more reliable and sustainable water supplies. For these people, the cost of water is likely to increase because the current tariffs do not cover the full costs of supply. Illegal connections and multiple household connections will be stopped, ensuring each household pays for water. Demand management will still be a concern given the flat rate tariffs, rather than consumption based tariffs. Widespread household metering is not a viable option in the short term due to the frequent zero/low pressure in the network and the need to prioritise available funds to rehabilitation and expansion to achieve the biggest impact.

A prerequisite for expansion of the network is the availability and effective management of a reliable and sustainable water supply. The programme will build the institutional capacity of the State Government to better understand, manage, operate and maintain water service delivery. Reliability of supply and sustainability of services will be underpinned by greater attention to water resources management, increased maintenance of the water supply infrastructure, reduced leakage and non-revenue water, and appropriately priced tariffs with full revenue collection. Clear performance parameters for water service delivery will be developed and monitored, contributing to building better accountability and transparency between the State Government and Urban Water Authority, and with customers.

The expected number of beneficiaries is 400,000. Beneficiaries will be disaggregated by sex as far as practicable as part of identification of the specific needs of women and girls. This contributes to the UK Manifesto commitment and the DFID Departmental Results Framework indicator for water and sanitation. The expected results are:

At least 400,000 people with sustainable access to clean drinking water sources and/or sanitation. For water, this includes new or rehabilitated water facilities which are improved. i.e. protected from outside contamination such as piped connection or public stand-post. For sanitation, this includes people eliminating open defecation where an entire community has been certified as open defecation free. Improved facilities include pit latrines with a slab or platform of any material which covers the pit entirely. The result does not include beneficiaries of communal water or sanitation facilities such as in schools and health centres.

At least 400,000 people with improved hygiene behaviour. This is defined as hand washing at critical times, observing the safe drinking water chain from source to mouth, ensuring a safe, clean environment, and safe storage of food and utensils.

The programme budget is £12 million (CDEL[5]) over 5 financial years from 2015/16 to 2019/20. The implementing partners are UNICEF (lead agency) and UNOPS.
[5] CDEL = Capital Delivery or implementation that generates an asset, such as building a latrine.

Portfolio restructuring
As well as this programme, DFID Sudan has two other water programmes – Water for Three States and Sustain Darfur. As part of the 2017 Ministerial Portfolio Quality Review process, DFID Sudan has de-risked its portfolio and is in the process of restructuring it from three water programmes to two. As shown in the figure below, this programme will be combined with the urban component of the existing Water for Three States (W4TS) project that is doing very similar work in Port Sudan.

While there are no changes in funding, outcomes, scope or scale compared with the original approved Business Cases, or changes to the Standard Administrative Arrangement signed with UNICEF, the combined programme will improve cross-programme learning, maximise impact and value for money, reduce risk and streamline management. This is further outlined in the new business case. This process is expected to be completed in the second quarter of 2018, i.e. before the next UW4D annual review, and partners will be kept informed.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The outcome of the Urban Water for Darfur project is ‘Sustainable and more equitable access to water, and improved sanitation and hygiene in targeted State capitals in Darfur’.

There continues to be substantial commitment to this project from the state government and also substantial expectations. His Excellency the Governor of North Darfur stated his clear expectations for delivery before the next dry season in April 2018 and followed up our July 2017 visit with a meeting with the UK Ambassador to request quicker action. The Governor committed to resolving the power supply problems at the wellfields which will enable more continuous pumping of water to the town and committed to completing two water storage tanks at the wellfields.

As noted for the February review, the project concept remains valid and is a priority for DFID Sudan and for the International Community as a platform for testing and learning about durable solutions for IDPs in urban areas. It contributes to influencing the transition from short term humanitarian focused programming to longer term more sustainable approaches in the context of protracted crisis, and importantly brings greater equity between urban residents and IDPs.

The key underlying assumptions in the Business Case remain valid and are areas for continued attention to mitigate delivery risks.

Indicators	Milestone / June 2017	Progress at September 2017
Number of people with sustainable access to safe drinking water sources (total, plus disaggregated by town and sex)	Target areas for expansion of water supply services identified in the Master Plan for 2 towns	Achieved. Areas for expansion of services have been identified in El Fasher and Zalingei. This includes assessment of the available water from the source, calculation of the water balance, completion of topographical studies, and network mapping of existing supply lines. / About 206,000 people (28,000 households) in the four towns have benefited from essential maintenance work to date which enabled their part of the network to be re-supplied with water, some for the first time in three years. In addition, about 13,000 people (1817 households) have benefited from new connections due to improved services.
Percentage reduction in the average cost of a month’s supply of water for an average household which gained access to a networked tap stand and was previously served by a vendor (disaggregated by town).	Water market information mapped for each town showing source of water, household status, consumption, and monthly cost	Achieved. The water market assessment has been completed in both towns and contributes to the Master Plan. The new households connected to the network have benefited from a 70-80% reduction in the cost of a month’s water supply.
Number of people with improved hygiene behaviour (disaggregated by sex, and by 2 towns, cumulative)	Prioritisation of sanitation and hygiene Master Plan actions and priorities discussed with stakeholders.	Achieved. Extensive consultations have been held with State Government and communities in El Fasher and Zalingei. Critical areas for behaviour change communication have been identified, linked to a review of the KAP survey.

Good progress has been achieved over the last six months since the Annual Review in February. The bulk of the work has targeted completion of the Master Plans for water and for sanitation. The status of the Master Plans in El-Fasher and Zalingei are outlined in the table below. Given that the El Fasher Master Plan is virtually complete, with priorities identified and agreed with the state government, preparation for implementation has started for both water and sanitation including engagement of targeted communities and identification of contractors. This will enable swift progress and results. Master Plans in Zalingei are about half completed and are drawing on the experience of El Fasher as agreed by DFID.

Master Plan	Status / Completion Date	Notes
El-Fasher
I: Water Supply System Technical Appraisal	All drafts completed and sent to DFID for review. / Final versions to be completed prior to the Master Plan launch scheduled for October including the Master Plan Summary, which will also be translated into Arabic.	If there is further learning during implementation, the Master Plans will be updated at key intervals as appropriate.
II: Water Market Assessment
III: Institutional Assessment
IV: Financial Sustainability and Water Tariff Study
Zalingei
I: Water Supply System Technical Appraisal	Draft report completed. / Finalised by end March 2018.	Further review is being made towards including the short, medium and long term recommendations.
II: Water Market Assessment	Complete (May 2017).	The results have been used in the different volumes of the Water Master Plan.
III: Institutional Assessment	Draft report is expected by end of Jan 2018, while final report is expected by end of March 2018.	Data collection has been conducted in a participatory way during the reporting quarter. Data analysis and compiling the draft report is ongoing by the consultant.
IV: Financial Sustainability and Water Tariff Study	Draft report is expected by end of Dec 2017, while final report is expected by end of March 2018.	Data collection in the field followed by data analysis and compilation of the draft report will all be completed in the final quarter of 2017.

DFID considers that whilst there is much improvement, there still needs to be continued focus on overall strategic leadership to drive and bring this complex and challenging project together. UNICEF and UNOPS continue to need to ensure clear strategic direction and maintain close oversight.

The assessment of progress against the milestones demonstrates that the project is on track to achieve its outcome. The extended planning phase was essential and has resulted in a thorough understanding of the status and issues for improved service delivery and of the short and medium term priorities. The focus is now on implementation of the Master Plans in El Fasher and finalisation of the plans for Zalingei. Implementation will be more straight-forward with each agency well experienced in delivery.

A six month no cost extension was discussed, weighing up the benefits of additional time with the cost of extension particularly with exchange rate losses. The primary rationale is to ensure follow up and monitor the effective functioning and sustainability of the water network and management arrangements, and to follow up and monitor sanitation and hygiene behaviour change. Additional time was agreed to be necessary and it is recommended that an amendment is made to the project end date from June 2019 to December 2019. This will be agreed as part of DFID Sudan’s internal restructuring of the water portfolio.

Overall output score and description
The overall output score is A – outputs met expectation. The outputs were assessed as follows:

Output	Weighting	Score	Risk
Planning, management and maintenance of water supply service delivery	30%	A	Major
Expansion of networked water supply to unserved areas	40%	A	Moderate
Behaviour change for improved sanitation and hygiene practices	20%	A	Moderate
Stronger knowledge base on effective approaches	10%	B	Minor

Key lessons
- Shifting well embedded approaches takes longer than expected, such as moving from service delivery as an emergency response to longer term strategic planning for service delivery, both for State Government and for implementing partners.
- The importance of sticking with a change process despite the challenges of insufficient pace and uncertainty, recognising it is a learning process and acknowledging growing commitment to the new approaches.
- The need to assess value for money over the full duration of a project, recognising that initial activities can be time and resource consuming, but are essential to embed a new approach and deliver sustainable outcomes.

Recommendations
Continue to strengthen strategic leadership and ensure close oversight to ensure timely project delivery. (UNICEF/UNOPS immediate and ongoing)

Agree a 6 month no cost extension to end December 2019 with an amendment to the SAA. (DFID, as part of water portfolio restructuring by April 2018)

Has the logframe been updated since the last review? No.

## C: DETAILED OUTPUT SCORING

Output Title	Planning, management and maintenance of water supply service delivery
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone June 2017	Progress at September 2017
1.1 % cost recovery (KPI 2 revenue/costs) (disaggregated by 4 towns)	Revision of methodology accepted by Urban Water Authorities (UWAs), with improved accuracy & transparency of data collection and monthly reporting	Achieved. / The methodology for KPI 2 has been fully revised with the State Water Corporation (SWC) and UWA, and the figures are now more realistic, between 50-75%. The UWAs do not cover their O&M costs, indicating a tariff increase will be required to ensure sustainable water supply service delivery. When appropriate, an evidence based case for a tariff increase will be made to the specific state government. The North Darfur State Governor has stated his willingness to consider raising the tariffs based on a well evidenced case.
1.2 Change in level of service (KPI 5 water availability hours/days per week (disaggregated by 2 towns)	Master Plans define expected level of service increase for different areas in two towns.	Achieved. / The pilot sectors[6] are not representative of all areas (baseline level of service in the pilot sectors in 2016; El Fasher 6 hours/day, 5 days/week; Zalingei 12 hours/day, 7 days/week). Service levels in other areas need to be assessed from network operating schedules and verified with a household sample. The potential change in service level due to the prioritised works in a given area can then be estimated. Some good examples already exist where due to essential maintenance, service levels changed from zero to a regular supply. These should be documented.
1.3 Percentage of deployable water source output being delivered to the distribution areas (KPI 1) (disaggregated by 4 towns)	Areas to install bulk water meters are identified.	Achieved. / Locations have been identified as part of the Master Plans for El Fasher and Zalingei.
1.4 Status of Master Plan for water (in 2 towns)	Comprehensive assessment completed, plan for both towns developed and shared with SWC.	Largely achieved. / In El Fasher, the Master Plan for water is 90% complete with full participation of the SWC in its development. The remaining tasks are finalisation of institutional and financial assessment which were delayed due to contractual problems with a supplier – now rectified with a new supplier. In Zalingei, the Master Plan is 70% complete.
[6] Pilot sectors were identified in each town by the previous Darfur Urban Water Supply project, as a defined area for data and information gathering. The pilot sectors are relatively small (2-5% of the network) and are only considered to be largely representative of the system as a whole for some KPIs. Data gathering for KPIs needs to be expanded to more representative areas.

Key Points
The majority of work to develop the Master Plans for water has been completed in both towns. Some additional work and refinements are ongoing particularly for the institutional and financial assessments by UNOPS and for water supply in the IDP settlements by UNICEF. The project team need to ensure the four volumes of the Master Plan are brought together in a summary with clear explanations of the expected changes in service delivery and how this will be achieved, as well as maps and diagrams to show the proposed work.

The assessment of the wellfield supplying El Fasher has confirmed the safe yields of boreholes and assuming operation at full capacity, there is sufficient water to meet the current demands of El Fasher town. An expert review of the assessment is recommended given the importance of the study for the sustainability of the water source for the town supply as well as other uses in the catchment area.

Works are planned at the wellfields, on the transmission pipes and on the distribution network. These should be clearly presented in the Master Plan, along with the complementary works planned to be funded by the state for the wellfield power supply and storage tanks.

In El Fasher, the launch of the Master Plan and the start of implementation of the short term priorities is scheduled for October. Although the Master Plan may not be 100% completed, it is recommended that the launch goes ahead and implementation proceeds. The Master Plan is ‘good enough’ at the present time with clear priorities and a costed plan for implementation. Further delays risk losing the commitment and goodwill of the state government which would jeopardise the outcome of the project.

Summary of responses to issues raised in previous annual reviews (February 2017)
- Focus on El Fasher, concentrating capacity in one town to complete the Master Plan and learn the lessons, prior to completing the Master Plan process in Zalingei. Ongoing.
- Ensure the process of development and prioritisation of the Master Plan fully involves the state government, particularly SWC, UWA and WES (Water and Environmental Sanitation), and also the Ministry of Physical Planning and Public Utilities (MoPPPU) and Ministry of Finance (MoF), drawing on the commitment for full support including funding. Effective consultation with community representatives in the planning process should also be ensured as a basis for building ownership and accountability. Successfully completed. Good engagement with state government and with targeted communities who show substantial commitment, and expectation.
- Further review the KPIs, their suitability, methodology and use by UWA for decision making, recommending revisions, including for expansion beyond the pilot areas. Completed as part of the Master Plan.
- Determine a realistic routine and periodic maintenance schedule for the urban water supply system (assuming it is in a functioning/rehabilitated state), and the related annual and monthly budget requirements. Request the UWA Board to cover the shortfall in the maintenance budget starting from the next budget year as part of negotiations on the Master Plan. Ongoing negotiations – to follow up.
- Ensure the final draft Master Plan clearly identifies the outcome of negotiations and commitments of the state government on issues such as state financing for infrastructure replacement, the maintenance budget, and tariff reform. Ongoing as Master Plans are finalised.
- Schedule a formal signing and launch of the Master Plan with HE State Governor, the UK Ambassador, and DFID, UNICEF and UNOPS Representatives, timed to also sign the Master Plan for sanitation. Ongoing.
Recommendations
1. Strengthen presentation of information and communication of key messages within the Master Plans for El Fasher. This includes the role of the state as service provider and the role of customers to pay for services. The Water Master Plan should integrate the assessment and plans for the two IDP settlement areas. (UNICEF/UNOPS by April 2018)
2. Finalise implementation plans for El Fasher with clear deliverables and milestones linked to the project’s logframe. (UNICEF and UNOPS by April 2018)
3. Follow-up North Darfur state government commitment to fund improvements to the power supply to the El Shagra wellfield’s and to complete construction of the two storage tanks. (UNOPS, by April 2018)
4. Consider an expert review of the Shagra wellfield water resources assessment given the importance of the study for the sustainability of the water source for the town supply as well as other uses in the catchment area. (UNOPS by April 2018)

Output Title	Expansion of networked water supply to unserved areas
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones / June 2017	Progress at September 2017
2.1 Percentage of households served by the urban network from either household connections or community taps stands (disaggregated by 2 towns)	Master Plan defines the current coverage and the feasibility of expansion to target areas in peri-urban and IDP settlements.	Achieved. / Population estimates confirmed, network mapping completed and areas for expansion identified within the Master Plan.
2.2 Number of new, functioning, well managed and maintained community tap stands in peri-urban areas and IDP settlements, assessed against defined criteria (disaggregated by 2 towns)	Community based management models for tap stands assessed and agreed with SWC/UWA and sample of targeted communities.	Achieved. / The management model for community managed tap stands in Geneina has been explored and documented as a basis for other towns. Key issues are the tariff level, regular payment by the community to the UWA, clear responsibilities for maintenance, and transparency of use of funds by the community.
2.3 Number of formal agreements to supply bulk water to peri-urban areas and IDP settlements operating successfully with payment based on full cost recovery (disaggregated for the 2 towns)	Standard agreement between UWA and peri-urban/IDP communities for a defined level of service and with an agreed tariff drafted and agreed by the UWA/state.	Achieved. / A formal agreement between the UWA and community representatives for a defined level of service for supply (hours/day and days/week) has been drafted for Abu Shouk pipeline and for peri-urban areas.
2.4 Water quality at point of delivery (disaggregated for the 2 towns).	Upgrading of chlorination unit included in Master Plan	Achieved. / An automatic chlorination unit has been installed in El Fasher water treatment plant funded by Japan.

Key Points
The Master Plan forms the basis for output 2 implementation. Priorities and plans are complete for El Fasher with preparation for implementation already underway. Communities have been engaged in preparatory activities and identification of contractors is progressing.

Targeted areas within El Fasher have been identified for expansion of the network with water kiosks. Some communities have already signed agreements with the UWA for bulk water supply. The tariff needs to be confirmed, with either the same tariff as household connections or preferably a reduced tariff to account for the lower level of service delivery. This would reverse the current situation where the poorest pay the most and would provide an immediate and substantial beneficial impact. .

The arrangements for community management of the water kiosks need to be further specified, with appropriate training planned and undertaken in advance of works. The committee should have representative membership and a full understanding of their responsibilities. Training should include discussion of the state-citizen ‘contract’ where the state provides reliable and affordable services to an agreed schedule and the community pays for those services.

An agreement between the IDPs and UWA for the Abu Shouk pipeline has also been signed. However during the visit, it was reported that no water was being provided. This needs urgent attention. The remaining issues around management and payment by WES need to be resolved.

Summary of responses to issues raised in previous annual reviews
Ensure greater consideration of equity as a primary objective of this project for water supply service levels and tariffs for all residents in an urban area. Ongoing as part of Master Plan negotiation.

Ensure coordination with the other agencies working on urban displacement, particularly regarding Abu Shouk, including sharing documentation about plans. Continues to need attention.

Recommendations
1. Confirm approach for community management of water kiosks and develop training package for implementation prior to start of works. Ensure community engagement is inclusive, with proactive steps taken to include the voices of women and girls as well as minority groups and those with disabilities. (UNOPS by April 2018)
2. Ensure construction of all community infrastructure considers accessible design. For example, in areas where there may be wheel chair users, ensure ramps are used instead of steps. (UNOPS, ongoing)
3. Finalise review of tariffs for water supply in El Fasher and present clearly argued case with evidence to state government. Interim measures for financing the current budget shortfall for operations and maintenance need to be agreed, with clear budget commitments. (UNOPS by April 2018)

Output Title	Behaviour change for improved sanitation and hygiene practices
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones / June 2017	Progress at September 2017
3.1 Number of people using an improved sanitation facility (sex disaggregated and by 2 towns, cumulative)	Sanitation and hygiene Master Plans completed in two towns	Largely achieved. / Master Plan completed for El Fasher following DFID recommendation for attention to one town first and then the second town. Master Plan for Zalingei under preparation.
3.2 Number of communities achieving open defecation free status (cumulative)	Urban Community Led Total Sanitation (UCLTS) defined for each town’s context.	Achieved. / A town wide campaign to stop open defecation will be undertaken, linked to sanitation marketing.
3.3 Number of households with soap and water together at a handwashing place used by family members (proxy for improved hygiene behaviour).	Approaches for accelerating improved hygiene behaviour change selected.	Achieved. / Approaches defined in Master Plan and agreed with state MoH and municipality (with roles clearly defined).

Key Points
The Master Plan includes an Open Defecation Free (ODF) campaign for the entire population. This may require additional resources beyond the current budget allocation, possibly utilising UNICEFs own resources which is welcomed.

The Knowledge, Attitude, Practice (KAP) study has been reviewed and revised to improve analysis and findings. Some concerns were raised about inconsistency between the KAP and the UNOPS water market assessment. These need to be explored and resolved. The KAP needs to provide a clear baseline for assessment of behaviour change.

Summary of responses to issues raised in previous annual reviews
- Caution on expanding the scope of the sanitation and hygiene component beyond the original expectations and the available budget. Prioritisation has been challenging given the needs. UNICEF will integrate the activities in to their own programming with additional budget.
- Ensure the final draft Master Plan clearly identifies the outcome of negotiations and commitments of the state government. To be confirmed in final draft plan.

Recommendations
Confirm final version of Knowledge, Attitude, Practice survey for El Fasher and Zalingei, addressing concerns about inconsistency of information and clearly stating the baselines for measurement of behaviour change in the interim and final KAP surveys. (UNICEF by April 2018)

Output Title	Stronger knowledge base on effective approaches
Output number per LF		4	Output Score	B
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones / June 2017	Progress as at September 2017
4.1 Number of field notes and technical briefs on urban water and sanitation, to be disseminated within Sudan and regionally (cumulative)	1 technical brief	Largely achieved. / Many technical briefs have been written on a range of subjects to inform the development of the Master Plans. Greater clarity is needed on which subjects to prioritise as a technical paper for peer review and dissemination.
4.2 Consolidated packages of lessons learnt on urban water and sanitation for dissemination	Documentation of issues in IDP settlements	Partially achieved. / Documentation of water and sanitation issues in the camps has been partially completed but not as a paper to inform debate on future service delivery.

Key Points
As noted in February, the partners have generated a lot of information and learning but they have not been systematically managed, quality assured, or disseminated. Documents need to be well structured, covering the issue, context, approach, result and evidence, drawing out the key points and learning.

There is a lot of interest within the International Community about how to manage urban displacement in more sustainable ways, and this project has much to contribute in relation to service delivery and community management. The project team should engage with the Durable Solutions working group to contribute experience of durable solutions.

Communications and visibility still needs to improve, with partners being much more proactive in gathering and communicating the objectives and key messages, case studies and people impact stories.

Summary of responses to issues raised in previous annual reviews
Strengthen structured documentation and learning as the basis for guidance for this and similar programmes in future. This should include learning about disability and the specific requirements for water, sanitation and hygiene in the urban context. Ongoing, needs attention.

Improve communications and visibility, implementing a clear strategy targeted for different stakeholder groups with case studies and people impact stories. Ongoing, needs attention.

Recommendations

Improve communications and visibility, agreeing a clear plan and regular communication products. (UNICEF, UNOPS by April 2018)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The Business Case identified key cost drivers as skilled personnel inputs, management and overheads, and capital infrastructure unit costs. This still remains the case.
The main expenditure to date has been staff inputs and operational expenses, with a small amount of capital expenditure on maintenance. Expenditure will increase sharply once the project moves into full implementation in year 2.
Exchange rate differences compared with the original US dollar budget on project approval are substantial, estimated to be US$ 3.5m. Partners need to carefully prioritise activities to ensure the projects targets are achieved.

VfM performance compared to the original VfM proposition in the business case
VfM is currently debatable given the extended timeframe and hence cost to complete the Master Plans. It is now essential to move forward with implementation to underpin the VfM of the project overall.
The VfM indicators for this project are clear (as noted in the February annual review report). The impact of improved water supply from the network rather than from vendors will provide substantial benefits for poor households. In addition, changes in tariff will have a substantial benefit – with the average monthly cost of water expected to decrease for the poorest people. These benefits will become clearer over the next year.
Assessment of whether the programme continues to represent value for money
The project overall represents value for money. It will enable poor households to reduce their expenditure on water substantially. It will enable the State authorities to better plan use of funds, avoid ‘fire-fighting’ annual repairs, and increase service delivery, thereby increasing revenues through payment for services. In addition, it will reduce the need for continued humanitarian intervention for water supply in the IDP settlements.

Quality of financial management
Financial management needs strong improvement. Expenditure has been slower than expected due to implementation delays in finalising the Master Plans and hence moving forward with implementation. Forecasting has involved inaccuracies due to over-optimism and a lack of focus on risks affecting planned spend. Communication between field teams, finance officers and between the agencies themselves and DFID needs to be clearer, more frequent and more targeted.

DFID have requested that the UN team take a much more risk-based approach to identify where delays are likely to occur and what mitigating actions are therefore required to make sure they do not. Further, clearer monthly profiling of operation and contract spend is required to ensure DFID does not pay more in advance of need than is necessary. UN partners have begun to take steps to fulfil these expectations and DFID will be monitoring the situation carefully, at least on a quarterly basis.

The project team has updated the budget for the remainder of the project, including the 6 month no cost extension by six months from June 2019 to December 2019 and adjusting the US$ budget for the lower exchange rate. This has required some tough prioritisation.

Date of last narrative financial report	02/09/2017
Date of last audited annual statement	31/12/2016

## E: RISK

Overall risk rating
The overall risk is major. This reflects the ongoing challenge of finalisation of credible master plans which requires strong leadership to underpin the technical work, decision making, and negotiations. This risk is being addressed, with additional support and surge capacity brought in.
Overview of programme risk
The main risks and mitigation measures as set out in the Business Case still apply. The risk matrix is reviewed at least quarterly during Steering Committee meetings. The risks that are most important at this time, and their current status, are:
State Government and/or IDP camp management do not agree to integrate the urban water supply with the camp. Indications in El Fasher positive from both the State Government and from IDP community leadership but not in Zalingei where further assessment is required and a transitional solution. Given the ongoing discussions on urban displacement with the government and the international community, the project team will need to actively coordinate the plans for service delivery.

State Government does not commit to full cost recovery for water supply. Early indications from senior State officials are positive. The work to define cost recovery enables clear identification of the realistic cost to supply 1m3 of water and the corresponding revenue generated. This provides a sound evidence base for tariff review, as requested by the state government.

Lack of UWAs capacity to effectively manage reliable service delivery. All four UWAs are supported by the project team to improve performance based on the set of Key Performance Indicators. Capacity is variable but improving, as shown by the increasing reliability of KPI data. The Master Plans for water includes an institutional assessment and capacity building for the two targeted UWAs.

Inequity of service levels and tariffs impact most on the poorest people. This is the current situation but there are positive indications that the state government is willing to amend tariffs, based on evidence. Tariffs have been reviewed to ensure full cost recovery of water service delivery as part of the Master Plans for water. This information will be used to recommend a change in tariffs to the state government.

Insufficient leadership and strategic technical capacity within implementing partners. Partner capacity has increased, with greater oversight by UNICEF and UNOPS head-quarters, and additional technical support in UNOPS. This needs to be maintained.

The risk of programme funds not being used as intended is low. The majority of funds are directly managed by the implementing partners, with some small scale funding to downstream partners. As implementation proceeds, the risk is likely to be higher because additional downstream partners will be contracted for infrastructure works. UNOPS have substantial experience of local contracting in Darfur as well as sound procurement and contract management procedures, with past experience demonstrating full compliance. In line with DFID Sudan’s requirements for full transparency of downstream partners and flow of funds, the implementing partners update DFID quarterly as part of regular reporting.

As recommended by DFID Internal Audit Department (IAD) in December 2016, a fraud risk assessment of the delivery chain should be undertaken to identify the potential fraud and corruption risks that could occur. This will help the project team to strengthen the risk identification and mitigating controls. This is particularly relevant now partners are starting to engage local contractors with larger contracts. Initiation of this process will be prioritised as part of an upcoming DFID field visit to El-Fasher in March 2018 and will be completed by the end of April 2018. In addition, IAD recommended DFID Sudan should discuss its expectations of fraud reporting with the partners. This was completed for all partners in May 2017.

Outstanding actions from risk assessment
There are no actions outstanding.

## F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The timeline for delivery of the project was revised as part of DFID Sudan’s portfolio review and de-risking. This took account of the delays to date which resulted from greater time required to complete the Master Plan process than expected. The project is on track with the revised timeframe.

Performance of partnership(s)
The partnership between UNICEF, UNOPS, and DFID is positive with open communications, working together to tackle the challenges and develop solutions. There have been some changes in key staff since February including; in UNICEF a new Head of WASH arrived in May, the UW4D Project Manager left in May and was replaced in June, and in UNOPS a new Infrastructure Team Leader, and a new Head of Office in mid Sept 2017. In DFID, the SRO/Lead Adviser is changing, with the replacement already engaged and inducted.

UNICEF and UNOPS are performing well as a partnership, with greater interaction between the field teams and headquarters. Senior managers are committed, are promoting the project’s vision, and have acted quickly to ensure the project improves performance. The project team has positive relationships and collaborative ways of working, although there have been some gaps (e.g. population data, IDP camp water supply) which have been addressed. UNOPS continue to have good relationships with the SWC and UWAs, built over many years and with the knowledge and experience of national staff. This helps to ensure cooperation, with openness and willingness to explore issues and challenges together. UNICEF also have good relationships at State level, especially the State Ministry of Health (SMoH) and localities.

DFID has performed well, actively engaging to provide technical and project management guidance to the project team. The extent of inputs is in excess of DFIDs expectations and will reduce as the leadership, capacity and experience of the project team continues to strengthen. UNICEF and UNOPS acknowledged DFIDs proactive support.

Asset monitoring and control
There have been no purchases of assets by UNICEF or UNOPS so far. If assets are purchased, UNICEF and UNOPS will update the asset register for all assets procured with programme funds and will submit on a quarterly basis. DFID will undertake periodic checks.

## G: CONDITIONALITY

Update on partnership principles (if relevant)
No funding is provided directly to the Government of Sudan for implementation of activities. Indirect funding via the UN agencies will be notified to DFID in advance. This includes funds to the State Water Corporation for borehole pumping tests and to the Ground Water and Wadi’s Department (GWWD) for water resources assessments (including basic equipment such as groundwater monitoring meters and related software with training).

The programme contributes to encouraging positive action in relation to the DFID Partnership Principles by:
- Strengthening commitment to poverty reduction at State level, focusing on greater equity of service delivery for all the town’s residents.
- Strengthening financial management and accountability at State level for water service delivery. This includes increased transparency of revenue collection using a computerised billing system, increased monitoring of performance with a range of key indicators including customer feedback, as well as increased communication of tariffs and use of revenues for maintenance.
- Strengthening commitment to domestic accountability by building relationships between the State Government and citizens for improved service delivery. This includes greater community engagement in the management of service delivery, including payment for water supplies to the Urban Water Authority.

## H: MONITORING & EVALUATION

Evidence and evaluation
There have been no changes in evidence. The project concept remains valid, a priority for DFID, and very relevant in the Darfur context of protracted crisis and the need for durable solutions for long term urban displacement.

Monitoring progress throughout the review period
Over the last six months since the annual review in February 2017, the DFID SRO and other team members visited Darfur twice, in April and in July, to review progress. This included meetings with state officials, beneficiaries, and the project team, as well as visits to project areas.

Regular correspondence was maintained with senior management in UNICEF and UNOPS, and with the project teams throughout the review period.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.
## The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.
The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process