Annual Review - Summary Sheet

Title: Financial Sector Deepening Zambia (FSDZ)
Programme Value: £15.0m		Review Date: June 2017
Programme Code: 203000	Start Date: May 2013	End Date: June 2018

Summary of Programme Performance
Year	28/02/2014	28/11/2014	27/11/2015	30/11/2016	20/07/2017
Programme Score	B	A	A	A	A
Risk Rating	Medium	Low	Medium	Minor	Minor

Summary of progress and lessons learned since last review

Progress
There has been continued progress on financial inclusion, with all three outcome targets again being exceeded in the past year. This means that since 2013, 271,000 rural poor, 48,500 smallholder farmers, and 16,000 small businesses now have access to a financial service (such as a form of saving, or insurance) as a direct result of FSDZ’s activities. Most output targets have also been met or exceeded in the past year, including ‘behind the scenes’ progress on policy and financial regulation. Since the start of the programme in 2013, FSDZ has made a real difference to the lives of poor men and women in Zambia: more people and businesses are accessing quality financial services that will help to make sustainable improvements to their livelihoods.

Since April 2016, the Financial Sector Deepening Zambia (FSDZ) has been running as a Zambian not-for-profit company limited by guarantee, following the move to a Special Purpose Vehicle. A new CEO and a Board of Directors were recruited, and co-funding from Sweden came on stream in June 2016.
Under this new leadership, policy influencing has improved: for example, a new MoU with the Bank of Zambia was signed, and FSDZ was invited to work with the Ministry of Finance in drafting the new National Financial Inclusion Strategy. FSDZ has also embarked on several exciting and innovative new projects in the past year, such as working with traditional leadership in Luapula province to improve financial access and education.

Staff recruitment and development has been a priority, and there have been a number of very good new appointments, making FSDZ well placed to further its reputation as a source of knowledge and driver of change on financial inclusion. There are encouraging signs of new funders coming on board, and FSDZ is currently in discussions with major donors and funding partners. DFID will work to support and facilitate efforts to bring in new financial support, as well as looking to extend its own support to the programme for a further three years.

Alongside this progress, there were some challenges associated with moving to the new structure, including uncertainty on governance arrangements (the roles of the Board, FSDZ, and DFID) and high spending on overhead costs. FSDZ also needs to step up its efforts to ensure more women benefit from financial inclusion. The recommendations in this Annual Review have sought to address these challenges. FSDZ should use the findings from this Annual Review, as well as learnings from the programme since 2013, to focus its activities as it enters the next phase of funding.

Lessons learned since last review
- The move to a Special Purpose Vehicle has had a positive impact in its first year: it has become a more local, innovative organisation, with improved ability to attract new funding
- Policy influencing has emerged as one of FSDZ’s real strengths
- The transition and post-transition period has taken longer than expected for new systems and processes to bed down, including corporate governance arrangements and IT

Summary of recommendations for the next year
A number of recommendations are made throughout this review, and are intended to guide the programme in its final year of the current funding phase as well as into a further phase of funding, if a business case extension is approved. Progress towards these recommendations will be monitored as part of FSDZ’s quarterly reporting. The main recommendations are set out below:

Informal and digital finance
1. FSDZ to assess options for linking savings groups to formal financial institutions and mobile money - lessons from other DFID-supported financial inclusion programmes, such as those in Tanzania and Uganda, are likely to be useful here (ongoing; by March 2018).
2. FSDZ and partners to build on the successful microinsurance pilots by scaling up coverage and bundling with other forms of insurance (by end 2017).
3. FSDZ and DFID to assess the scope for expanding FSDZ’s work on digital financial services, given the transformational potential seen in East Africa (by Q3, 2017).

Funding and sustainability
1. DFID SRO and FSDZ to work closely to secure DFID funding beyond 2018 to support FSDZ’s Strategic Plan, and to agree new targets and indicators as part of the business case extension (by March 2018).
2. FSDZ to continue efforts to attract new sources of finance to broaden the funding base and ensure longer term sustainability (ongoing).

Corporate governance
Board, funders and management to review the current governance model, including a review of Board and Investment Committee terms of reference (to be discussed at August 2017 Board and Investment Committee meetings).

Communications
1. FSDZ should continue its good work on communications while recognising DFID’s low risk appetite for activities that could have a reputational risk. FSDZ will sign a new visibility statement with DFID on branding and communications (by September 2017).
2. FSDZ to consider the balance between promoting FSDZ and using communications as part of programme activities, and look at measuring the impact its communications activities (by end March 2018).

Value for Money
1. FSDZ to provide more detail on expenditure as part of quarterly and annual reporting to ensure more transparency on the use of DFID funds. FSDZ should think critically about where value for money can be improved as well as telling a positive story (by September 2017).
2. FSDZ management to discuss key decisions that have value for money implications with DFID at an early stage (ongoing).
3. FSDZ to ensure a successful handover of the SME Executive Diploma course to the Zambian Institute of Banking and Financial Services (ZIBFS) and assess if the results justify continued support (by end of 2017).

Inclusion
1. FSDZ to fully implement its new Gender, Disability, and Diversity policy, linking to the theory of change (by end 2017).
2. FSDZ to work with the Sweden-funded women’s financial inclusion component to learn lessons on how increase the number of women benefiting from financial inclusion (ongoing).
3. DFID and FSDZ to assess the current programme’s geographical spread and consider how to target provinces where needs are highest (ahead of any new DFID funding - by March 2018).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3549927.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4380062.xlsx

Introduction
FSDZ is a five year programme to support inclusive financial sector development in Zambia. This means working to increase the number of poor Zambians who have access to one or more financial services to enable them to save, borrow, receive insurance coverage, make payments or use mobile money. To achieve this, the programme takes a ‘making markets work for the poor’ (MM4P) approach which involves a range of interventions, including advising policymakers, setting up informal savings groups in rural areas, and piloting micro insurance schemes for smallholder farmers.

The programme started in September 2013 and was initially was managed by a supplier, DAI. In accordance with a clause in the contract, DFID took the decision to end the contract with DAI at the 3 year point and set up a special purpose vehicle (SPV) to deliver the programme from 1 April 2016. This approach has given FSDZ more independence as a stand-alone Zambian organisation and allows it to more easily diversify its funding sources, reducing dependence on the UK. This change in delivery mechanism has not altered the goals of the organisation or the DFID logframe targets.

The impact of the programme is to make sustainable improvements in the livelihoods of poor people by supporting 138,750 people with increased incomes or a reduction in vulnerability.

The outcome of the programme is a financial sector capable of delivering a wide range of financial services to more people and businesses in Zambia. By end March 2018, it aims to provide:

- 300,000 additional people with access to finance (of which 65% to be women)
- 50,000 smallholder farmers with access to agricultural finance (of which 50% to be women)
- 12,000 additional MSMEs with finance from banks and financial service providers (FSPs)

FSDZ has focused on developing several thematic areas: rural and household finance (including savings groups and micro insurance); MSME finance; policy and digital financial services; and research and information. These thematic areas do not directly map onto a logframe output or outcome; rather, they interact with one another and each contributes towards various elements of the six programmatic logframe outputs and the three outcome targets. This is reflective of the ‘market systems’ approach that underlies FSDZ’s design, which seeks to achieve an outcome that is greater than the sum of its parts. So although FSDZ reporting is disaggregated to show the contribution of each thematic area to each output and outcome, we would expect over time to see an acceleration in progress towards the ultimate impact as systemic change takes place. Further information can be found at: www.fsdzambia.org

Since the start of DFID’s funding of the programme in 2013, a number of lessons have been learned. These are summarised below, and will be particularly relevant should DFID support continue beyond March 2018:

Market change and policy influencing can take time to deliver results - the ‘J-curve’ effect: on some areas of the programme, there was slow initial progress followed by an acceleration in results. This effect was observed with the expansion of informal savings groups, which required a hands-on approach at first but are now being replicated by communities themselves in many areas of Zambia.

Policymakers’ support and political will is critical: FSDZ has made a considerable investment in relationships, and has built up contacts in policy and industry. These have been used to good effect, for example in supporting the Ministry of Finance in its new National Financial Inclusion Strategy, and this year FSDZ signed a detailed MoU to support the Bank of Zambia on financial inclusion. Financial inclusion has emerged as a policy priority in for the government in the last 18 months, in part due to FSDZ’s work to build the evidence base (through research such as Finscope, geospatial mapping and Financial Diaries) and its influencing work with policymakers.

Piloting and demonstrations can be used to scale up progress: FSDZ has piloted innovative approaches to financial inclusion, such as the use of weather index-based insurance, and has then used the evidence and results to demonstrate viability to insurance companies and policy makers.[1] The government has now committed to rolling out weather index-based insurance to the 1m recipients of its agricultural subsidy scheme.
[1] FSDA/ Ledgerwood (2017)

FSDZ’s new structure and local ownership have been beneficial: since May 2016, FSD Zambia has been operating as a local non-profit company limited by guarantee. This has made the organisation more Zambian than the previous contractor-led model, and made it easier for other funders to support FSDZ. Learnings from the transition period include the need to have more clarity over the role and scope of Board, members, and management; and the need to limit transition-related administrative costs where possible.

Context
Zambia experienced significant growth in the last decade (averaging 7% GDP growth per annum until 2015) but with little change in poverty, especially in rural areas. Poverty levels now stand at 54.4% nationally and 76.6% in rural areas and have been relatively static for a number of years (Living Conditions Monitoring Survey, 2015). Economic growth is narrowly focused around the mining, services and construction sectors, while most Zambians rely on subsistence agriculture for a living.

Evidence points to the development of the financial sector as an important driver of the rural economy and a critical means for poor people, small businesses and smallholder farmers to smooth their income and consumption, manage risks, and invest in productive capacity.

Financial exclusion in Zambia remains high. Nationally, it has reduced from 62% in 2009 to 41% in 2016, (FinScope 2015) but this masks a number of variations. In rural areas 50% of adults have no access to any financial service, whether formal or informal. Financial exclusion is higher for women (43%) than men (39%), and for those working in the informal sector than formal wage earners.

The Government of Zambia has shown commitment to expanding financial inclusion and has established a new Financial Inclusion Unit in the Ministry of Finance to lead the development of a National Financial Inclusion Strategy, building on the Financial Sector Development Plan (2010 to 2015).

While the latest FinScope (2015) research showed good progress on financial inclusion, there is still a long way to go on formal services for Zambia when compared to its peers. While some issues have been identified at the policy level (such regulation of the microinsurance sector), many of the constraints to financial sector development arise from significant market failures and the focus and strategies of individual banks and other non-bank financial institutions (NBFIs) in the formal sector. Most do not provide accessible financial services to the rural population in any significant way. Thus, without catalytic interventions in the formal sector alongside support to develop the informal sector, many Zambians will continue to be financially excluded.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Progress against the March 2017 Outcome milestones is shown below.

Indicator(s)	Target for March 2017	Results achieved	Progress against milestone
Impact Indicator 1 Number of people experiencing an expansion in income opportunities or a decrease in vulnerability	99,500 / (64,675 women or 65%)	105,471 (84,687 women)	106% (progress on reaching women: 131% of milestone target; women beneficiaries comprise 80% of total)
Outcome indicator 1 Number of poor people and microenterprises accessing a new financial service	240,000 / (156,000 women or 65%)	271,091 (137,180 women)	113% (progress on reaching women: 88% of milestone target; women beneficiaries comprise 51% of total)
Outcome indicator 2 Number of smallholder farmers accessing a new financial service	30,000 (15,000 women or 50%)	48,582 (12,097 women)	162% (progress on reaching women: 80% of milestone r=target; women beneficiariescomprise 25% of total)
Outcome indicator 3 Number of MSMEs accessing a new financial service	7,500	16,413	219%

Results for all three outcomes have again achieved their milestone targets, with progress against targets for Outcome 2 (smallholder farmers accessing a new financial service) and Outcome 3 (MSMEs accessing a new financial service) being particularly impressive and exceeding their targets by 62% and 119% respectively. All three outcome targets are on track to exceed the final targets in the logframe by the end of the current phase of funding in March 2018. The overall impact target milestone has been met and exceeded by 3% – 105,471 poor people (against a target of 99,500) have experienced an expansion in income opportunities or a reduction in vulnerability directly or indirectly due to FSDZ – a large increase from last year’s 63,166 people. We expect FSDZ to achieve the outcomes envisaged by the end of the programme in 2018. FSDZ is currently projecting to reach 333,500 poor people (Outcome 1) by March 2018, exceeding the final target of 300,000.

Gender balance has improved on last year – with women now making up just over half of the number of poor people and microenterprises accessing a new financial service under Outcome 1 (up from 45% last year) though still below the target level of 65%). This is mainly due to the expansion of Savings Groups which tend to be comprised mostly of women. However, the number of women smallholder farmers reached under Outcome 2 (mainly farmers accessing weather index-based insurance) remains a particular challenge, with levels of women still at only 25%. Of those reached under the Impact target, 80% (84,687) were women, which exceeds both the target level (65%) and number (64,675).

The last annual review recommended working closely with the Women’s Financial Inclusion (WIN) component of FSDZ (funded by the Sweden International Development Cooperation Agency, SIDA) to learn lessons on improving the gender focus. This is still the intention, though as there was a delay in the start of the WIN component due to recruitment this is yet to happen. An FSDZ Gender, Diversity and Disability policy has been launched, and when implemented will be an important part of increasing the reach on gender as well as other groups.

By the end of 2017, DFID will seek to secure extended funding for FSDZ beyond 2018 through a Business Case extension, and if this is forthcoming will agree a new set of targets for FSDZ from 2018-2021. These should include indicators to measure the quality and sustainability of the financial services being accessed as well as the level of external funding.

Overall output scores and description
The overall output score is ‘A’ (outputs met expectations). Detailed output scoring follows in section C. The first five outcomes, for which FSDZ is directly responsible, performed above expectation at A+ or A level, whereas the final one – on the transition from a DAI contract to a local not-for-profit company – performed at B level.

Key lessons
The transition to a Zambian Special Purpose Vehicle has brought many benefits, such as further establishing FSDZ’s credibility as a local, Zambian organisation, and an experienced Board of directors. Policy influencing has emerged as one of FSDZ’s real strengths under the new management, and there has been strong delivery against results in most output areas. However, the new governance arrangements and processes such as IT systems have taken time to bed down. There has been some progress on these issues, and the recommendations in this review should help to ensure this continues.

Key actions
In addition to the recommendations made in this Annual Review, there are two main actions for the final year of the current funding period:
- Future funding and sustainability – FSDZ should work closely with DFID on the business case extension, and continue efforts to target new funders
- Governance - the management, Board, and DFID will need to work on getting the balance right on oversight, managing reputational risks, and following good corporate governance. This will include in the first instance a review of the Board and Programme Investment Committee terms of reference at the next Board meeting

DFID’s current funding of FSDZ will end on 31 March 2018, by which time the special purpose vehicle will have been running for two years. As this is a short timeframe for FSDZ to secure full funding from other sources to continue beyond this date, it was agreed that during 2017 DFID Zambia will seek ministerial approval for 3 years of additional funding i.e. to ensure there is DFID funding for the first five years of operating as an SPV. This will be structured in such a way as to incentivise FSDZ to raise funding from other sources – so DFID would cover a given amount of core costs and programme funding, and would offer additional funding provided it is matched from other sources, up to a certain level. This should incentivise FSDZ to attract new funding and ensure a smooth and sustainable exit from DFID funding in 2021.

Has the logframe been updated since the last review?
No, although if new funding is approved beyond 2018, a full review of all logframe indicators would be carried out.

## C: DETAILED OUTPUT SCORING

Output Title	More and better industry data and public information on the financial sector is available and used by stakeholders
Output number per LF		1	Output Score	A+
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 1.1 Number of financial sector stakeholders using new and industry data and public information products	20	36 (180%): target exceeded
Output indicator 1.2 Number of target beneficiaries receiving financial education	120,000 / 60,000 women	160,046 (133%): target exceeded / 108,530 women: target exceeded

Key Points
FSDZ is doing valuable work to build the evidence base in Zambia on financial inclusion, using a mixture of in-house expertise and consultancy support, including from the South Africa based Centre for Financial Regulation and Inclusion (CENFRI).

Output indicator 1.1 was exceeded by 80%, with an additional 16 organisations using FSDZ’s information products. The most used products were FinScope and Financial Diaries, and organisations benefiting included commercial banks, Bank of Zambia, Ministry of Finance and mobile money firms. These products are highly valued by market users - feedback from a range of market users of these knowledge products collected during the review period has been very positive. Most users that were met noted the FinScope research as well as other products such as the Making Access Possible (MAP) work led by CENFRI. The leading mobile money transfer company in Zambia has used the geospatial mapping outputs to guide their operations and targeting.

Output indicator 1.2 was exceeded by 33%, with over 160,000 people receiving some form of financial education. As with last year, this was primarily delivered through savings groups, education to farmers receiving life insurance, and large scale campaigns through Insurance Week and Financial Literacy week.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
FSDZ and DFID should consider raising the 2018 targets for 1.1 and 1.2, pending the impact of the proposed wording changes to better capture quality.	Not yet implemented. The targets have not yet been raised – FSDZ and DFID will firstly need to look at ways to measure the quality dimension. This should be done as a priority since the programme is now into its final year.
FSDZ should consider how to reach women with financial education beyond the savings groups.	This is ongoing, though a set of actions has not yet been agreed. The SIDA-funded WIN component is reaching women and girls through the development of financial education modules to be included on tablets alongside the school curriculum and through extracurricular groups. / Financial Literacy Week, on the theme of ‘Know and Plan Your Finances for a Better Life’, included financial education to women through events such as school debates, radio and workshops.

Recommendations
FSDZ should consider revising the targets upwards for the final year, and start assessing the quality of both research and financial education outputs for future assessments – the British Council/ DFID supported Zambia Accountability Programme (ZAP) is likely to have some lessons on how to measure this (by Q3 of 2017).

Output Title	Improved policy and regulatory environment for the delivery of financial services
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 2.1 Number of organisations demonstrating improved effectiveness in advocating for financial sector reform	4 organisations / Target of 25% improvement in effectiveness measured by the use of new advocacy toolkit	4 organisations (100%): target met / Benefiting organisations: Insurance Association of Zambia (IAZ), Technical Advisory Group (TAG), Bankers Association of Zambia, Zambia Credit Ratings Bureau. / IAZ: 35% improvement using the Advocacy Toolkit: target met but other organisations not yet measured
Output indicator 2.2 Improved capacity of policy makers to formulate and implement effective financial sector policies and regulations.	2 organisations / Target of 15% improvement, measured by the use of new Policy and Regulatory Toolkit	2 organisations (100%): target met / Benefiting organisations: Bank of Zambia, Pensions and Insurance Authority (PIA) / PIA: 16% improvement (target met); Bank of Zambia not yet assessed

Key Points
FSDZ is using its expertise to build capacity in key organisations to improve their delivery on financial inclusion. Following the development of advocacy and policy and regulatory assessment toolkits, it is now able to measure the impacts of its activities quantitatively. These toolkits measure advocacy capacity as well as policy making and regulatory capacity. They are also being considered for use in other DFID Zambia programmes.

Output indicator 2.1 Four organisations received support from FSDZ on improving advocacy, meeting the target. This including working with the Technical Advisory Group on a set of microinsurance principles to guide the development of the sector. The advocacy toolkit has measured progress in one organisation, so far - a 35% increase in advocacy capacity in the Insurance Association of Zambia (IAZ) was recorded.

Output indicator 2.2 FSDZ provided policy and regulatory assistance to two organisations, again meeting the milestone target. This included a workshop on microinsurance regulations with the Pensions and Insurance Authority (PIA); and four days of field trips and workshops on MSME lending with managers from the Bank of Zambia. The Policy and Regulatory Assessment Toolkit found a 16% improvement in the capacity of the PIA.

This supports the positive feedback from partners interviewed during the review period - both the PIA and Bank of Zambia remarked that they had valued working with FSDZ and had benefited from their advice and assistance. The toolkits should now be applied to assess advocacy and policy capacity improvements in the other organisations. The assessment questions and analysis used in the advocacy toolkit are shown below. The Policy and Regulatory toolkit uses a similar approach.

Questions used in the advocacy toolkit to assess impacts of capacity building:

Template for analysis based on the toolkit questions:

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
Continued emphasis on phasing out of FSDZ (financial) support on Insurance Week and the TAG.	This has partly been done. FSDZ is planning to support Insurance Week in September 2017 but it will be joined with Financial Literacy week from 2018.
Ensure the Regulatory Assessment Toolkit is utilised in time for the next Annual Review to formally measure progress on improving the capacity of policy makers.	This has been developed and are being used to track progress, though it needs to be applied to all organisations that have received support from FSDZ under this output. Other DFID Zambia programmes (ZAP and governance programmes) are also looking at using the toolkit or adapting them.
There seems to be no specific attention to women in microinsurance product development or consumer education, although microinsurance does get sold through women’s market groups. FSDZ and IAZ should ensure this is aligned to mitigate risks of selling products to potentially vulnerable or non-financially literate consumers.	Some progress: education on insurance has been provided to those in the microinsurance pilots (weather index-based insurance), through the use of aggregators. FSDZ has also been engaging on the new insurance bill with IAZ.

Recommendations
FSDZ should apply the toolkits to measure advocacy capacity and policy/ regulatory capacity in all organisations supported by FSDZ (ongoing; by end 2017).

Output Title	Adequate infrastructure and support services in place to support financial sector development
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 3.1 Number of new or improved support service offerings to stakeholders	10	10 (100%): target met
Output indicator 3.2 Number of financial infrastructure functions recording progress during the year	4	4 (100%): target met / ZIBFS (Level 3) / Credit Reference Bureau (Level 3) / Collateral Registry (Level 4) / National Switch (Level 1)

Key Points
An important component of a market systems approach to financial sector development is ensuring sufficient market infrastructure and support services are in place (for example a credit reference bureau or collateral registry). This is a ‘behind the scenes’ component, but a critical one nonetheless.

Output indicator 3.1 The target of providing support services to 10financial service providers (FSPs) was met. This included the Catholic Diocese of Ndola advising two other service providers on savings groups; MSME relationship banking training being provided by the Zambia Institute of Banking and Financial Services (ZIBFS) to one commercial bank; and support on inclusive insurance from the Technical Advisory Group (TAG) and the Microinsurance Acceleration Facility (MAF) to insurers such as African Life and Madison.

Output indicator 3.2 40 professional bankers graduated on the SME Executive Diploma course this year, including an in-house session for Cavmont Bank staff. Plans are underway for a full handover of the curriculum to the Zambia Institute of Banking and Financial Services (ZIBFS). Elsewhere, support was provided to the Zambian Credit Bureau on a new workplan, and research was funded to produce a business case for the National Switch (on banking and ATM interoperability).

Last year FSDZ developed a scoring system to benchmark and assess the scale of improvements to financial infrastructure across 8 levels – a Financial Infrastructure Assessment Matrix, shown below. Four organisations have made progress against this scale, meeting the target amount. However, the highest level reached was Level 4 (out of 8) so there is scope for further progress with the four organisations.

FSDZ ‘Financial Infrastructure Status Assessment matrix’:

Level 0	Nothing in place
Level 1	Stakeholders in broad agreement on need and functionality of the infrastructure
Level 2	Operational plan developed
Level 3	Enabling regulations / legislation in place
Level 4	Funding secured and contract awarded for development of the infrastructure
Level 5	Infrastructure in place and fully operational
Level 6	Infrastructure in use by < 10% of organisations receiving support
Level 7	Infrastructure in use by < 50% of organisations receiving support
Level 8	Infrastructure in use by > 50% of organisations receiving support

In each infrastructure area FSDZ measures progress annually. This year the National Switch has been added as a new area of infrastructure being supported by FSDZ (currently at Level 1). The three organisations supported last year have all reported progress in the past year as shown below. The relatively low levels reached on these infrastructure scores suggests a need for further FSDZ involvement in these areas.

Infrastructure	Achievement Level 2017
Zambia Institute of Banking and Financial Services (ZIBFS)	Level 3 (2016: Level 2)
Credit Reference Bureau	Level 3 (2016: Level 1)
Collateral Registry	Level 4 (2016: Level 3)
National Switch	Level 1 (New this past year)

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
FSDZ could do more to understand the impact of the SME diploma training – for example through interviews with bank managers, participants or considering evidence from participating banks’ MSME portfolios. This would also help in promoting the course in future.	This has been done. FSDZ carried out an assessment of the SME Executive Diploma in March 2017 - this looked at the extent to which the course had induced changes in lending practices, including through interviews and questionnaires. The assessment found that the course has changed perceptions of MSME finance and had improved capacity. However, trainees indicated that the greatest challenge they faced was influencing management in their respective institutions, implying the targeting of the course needed adjusting. As a result, the course is now focusedon more senior staff.

Recommendations

1. Review the progress of the Zambia Institute of Banking and Financial Services (ZIBFS) in delivering the SME Executive Diploma course once handed over from the current team of international consultants (ongoing; by end of 2017).
2. Carry out a detailed assessment of the course’s impacts and value for money, including whether it leads to changes in banks’ lending practices (ongoing; by end of 2017).

Output Title	Increased capacity of financial service providers to deliver products that are accessible, affordable and appropriate to poor people
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 4.1 Number of financial service providers (FSPs) with increased capacity to reach poor women, men and microenterprises with financial services	14	20 (143%): target exceeded
Output indicator 4.2 Number of sustainable community based financial institutions providing financial services to poor men and women	5000	4867 (97%): target not met

Key Points
The awareness raising activities of FSDZ together with the Technical Advisory Group (TAG) for microinsurance is resulting in an increased interest in provision of insurance for low-income households.
Improving the policy and regulatory environment remains a work in progress - the new Insurance bill will cover microinsurance for the first time, and will therefore encourage market entrants - but has yet to be passed. FSDZ has been providing technical inputs to the regulator. There has been a significant increase in savings groups, and good progress in trialling sustainable support through village agents and private service providers.

Output indicator 4.1
The number of financial service providers with increased capacity to reach beneficiaries has increased from 2 to 16. 13 of these provide inclusive insurance products (including Madison, Hollard, Prudential, and Barclays Life), 2 provide digital financial services (Zoona, AB Bank) and 1 provides microfinance (MFinance).

FSDZ launched a new Inclusive Insurance Upscaling Challenge Fund in December, attracting 8 proposals and aiming to reach 200,000 low-income consumers with innovative insurance products. FSDZ also provided training in product development and pricing to insurance firms which was well received and attracted 12 participants. Participants paid a fee to cover venue and accommodation costs (an indication of value and quality), collected through the Insurers Association of Zambia, and FSDZ covered trainer costs.

Output indicator 4.2
The rollout of savings groups has significantly accelerated this year, and results are just shy of the target. The ability to both use it as a savings tool and a way to earn interest income is valued by members. The social fund also acts as an informal insurance scheme against economic shock. As set out in the impact survey from last year, members use the loans and interest earned for commercial purposes predominantly which should lead to further increases in income. Savings groups have also proven to be sustainable[2] and replicable, with interesting models for support being tested, including a voluntary payment for support from village agents to more formal support and payment structures for private service providers. It will be useful to continue to track these groups’ progress following the end of the last grant. Interestingly the savings group methodology has also been independently replicated far beyond the target groups, including the police force, teachers, and office workers. FSDZ should push on the potential for linking saving groups to banks, using mobile money to make transfers, and opportunities for micro insurance.
[2] FSDZ will conduct an assessment of the different savings group models and sustainability in Quarter 2, 2017. In addition qualitative feedback from PSPs will be documented and records reviewed to estimate sustainability.

Potential challenges with savings groups include the safety of cash deposits, unscrupulous village/ private sector agents, and group power dynamics. Also, vulnerable members benefit from the social fund but there are some emerging concerns that high interest rates may be making some members more vulnerable.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
Ensure that reporting on indicator 4.1 captures evidence that the Financial Service Providers (FSPs) are growing in their capacity to reach poor women, men and microenterprises.	Not yet done. There is some anecdotal evidence of capacity development, however the monitoring system should allow for this information to be better captured.
Use a bigger sample to measure whether savings group members are below $2.50 per day, and report on the percentage of PPI level 1.	This has been done. The report was submitted as part of the 2017 Annual Report - see the value for money section for more details. A larger sample was drawn (600 compared to 150 sampled in 2015).
Provide some form of continued monitoring (beyond the grant end) to ensure new savings groups are well-supported by the Private Service Providers (PSPs).	This has been done - a preliminary case study was conducted by MRM and a report was also submitted as part of 2017 Annual Report. A deeper study is planned in 2017 Quarter 2 to consolidate the preliminary findings.
Undertake further research on linkages to the formal financial sector for savings group members.	This is underway and is due to report by end 2017.
The monitoring of the different savings groups is a very valuable source of information. It is recommended to: / Add an indicator relating to quality or impact of the savings groups rather than just the numbers reached. / Pay particular attention in the CARE MIS to discern impacts of savings groups in areas with social cash transfer beneficiaries.	An indicator has been added in the savings groups intervention measurement plan to capture qualitative feedback and other descriptive variables of quality and impacts of savings groups. / Partially done. FSDZ have monitored CARE during the MIS verification process, monthly meetings with partners and report reviews but this does not specifically look at impacts in areas with social cash transfer beneficiaries.

Recommendations

1. The large amount of cash held, particularly towards the end of the savings period, increases the risk and impact of theft. FSDZ should continue to work with FSPs to assess whether solutions can be developed to address this risk. It will be interesting to hear from FINCA (a microfinance company) and others including on the potential for making deposits via mobile money. As set out in the last review, the FSD Uganda research into linkages between savings groups and financial service providers/digital financial services providers will be very valuable (by end 2017).
2. Linked to this, banks’ reputation of being unfriendly and untrustworthy will need to be overcome – the Catholic Diocese of Ndola (CDN) in Copperbelt are looking at linking a commercial bank with savings groups to improve understanding on both sides, and if successful this could be followed in other areas (ongoing; by March 2018).
3. The knowledge of financial product availability is low - FSDZ should do an assessment of the various low cost savings accounts and disseminate this, both to share the information and stimulate competition (by March 2018).
4. Consider trialling the mobile phone app for savings group record keeping in Zambia, depending on experience in Kenya. DFID Zambia should also establish a link with digital team in London on this (by end 2017).
5. FSDZ to look at the implications for members who have more than one savings group, as this seems to be fairly common (Q3 2017).
6. Most members the review met are involved in trading and small scale agriculture, with low returns. How these returns stack up against the high interest rates should be assessed in due course (by end 2017).

Output Title	Increased capacity of financial service providers (FSPs) to deliver products that are accessible, affordable and appropriate to MSMEs and smallholder farmers
Output number per LF		5	Output Score	A
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 5.1 Number of FSPs with increased capacity to reach MSMEs with financial services	10	13 (130%) – target exceeded
Output indicator 5.2 Number of financial service providers with increased capacity to reach smallholder farmers with financial services	6	6 (100%) – target met

Key Points
Turbulent economic conditions created challenges for some FSPs in targeting MSMEs. However, there has been good progress within a subset of the 13. There are some exciting pilot initiatives in weather index-based insurance which are showing early promise and there is potential in livestock insurance.

Output indicator 5.1
FSDZ continues to support 7 of the 13 FSPs reached, to better serve the MSME sector. With each of these, FSDZ has agreed action plans of support. FSDZ’s support for the Executive Diploma in SME Relationship Management is valued and a number of frontline staff have passed through the programme. In terms of sustainability, the capacity of national trainers has been increased, though it has taken longer than planned to do so.

Direct support by FSDZ to improve FSPs’ MSME strategies has been mixed, due to economic conditions and uncertainty created by changing ownership within a number of targeted FSPs. The ‘Livelabs’ pilot project (where MSMEs are partnered with FSPs to better understand each other’s requirements) is progressing and is linking with DFID Zambia’s Private Enterprise Programme. A concern was raised by one of the FSPs that the financing modality (where MSMEs are required to part fund their involvement) is discouraging MSMEs from taking part as it is a pilot project with uncertain results at this stage.

Output indicator 5.2
The target of reaching 6 financial service providers was achieved. The partnership with Musika to support two insurance companies in providing well designed weather index-based insurance products has led to good results. The DFID Annual Review team met with beneficiaries of Mayfair insurance’s weather index-based insurance product (cotton farmers) and feedback was positive. The capacity of Mayfair has been well supported by FSDZ and its partners, and its product will be rolled out further. Other types of insurance that would benefit farmers are in design.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
It would be helpful to better understand the impact on beneficiaries of services delivered under both these outputs: / What types of MSMEs are benefiting (e.g. location, size, sector)? / What is the experience of farmers enrolled in the weather index-based insurance?	a.The MSMEs benefiting are mainly tier 1 and tier 2 (annual turnover of between ZMW500k to ZM20m) and between 2 to 100 employees. These are mainly located along the ‘line of rail’ (where the main railway runs through Zambia). Most of FSDZ’s partners do not have a rural presence and so very few rural MSMEs are benefiting from their products and services. FSDZ’s new rural and agricultural finance component should help to increase the rural outreach. MSMEs reached are typically from the mining, agro-processing, construction, manufacturing, trading and trading value chains. / b. The review team heard very positive feedback from farmers who had taken out weather index-based insurance, with demand for additional insurance products. To address this, FSDZ is looking to pilot bundling of wider risk coverage. FSDZ is also looking at scale up strategies for weather index-based insurance, including discussions with the Ministry of Agriculture on linking to the FISP (agriculture subsidy scheme).
FSDZ should ensure continued close collaboration with PEPZ in joint initiatives such as Live Labs	The Live Labs project has continued, however it has been slightly delayed due to staff turnover and the approach has been adjusted.

Recommendations
1. The Livelabs pilot has been scaled up and MSMEs are now required to part fund this pilot. This should be reassessed given the novelty and uncertainty of impact (by Q3 2017).
2. Assess if the apppropriate level of seniority is attending Executive Diploma in SME Relationship Management, and ensure a successful handover for ZIBFS to take over the running of the course (by Q3 2017).

Output Title	Establishment and operation of SPV
Output number per LF		6	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Output indicator 6.1 Strategic plan and business plan completed	Annual workplans and budget submitted, approved and implemented	Annual workplans and budget submitted, approved, and implemented. Delay to the budget for the 5 year Strategic Plan but now completed. Some operating manuals not yet finalised.
Output indicator 6.2 Special purpose vehicle established and operational	Programme managed effectively and efficiently	Completed successful first year as a company limited by guarantee. Some operational transition related issues.

Key Points
FSD Zambia is a fully functional, trusted and independent Zambian organisation. Positive feedback was received from a range of stakeholders, including the Bank of Zambia and the Ministry of Finance. The quarterly and annual reports are of a high quality, though more transparency and improved reporting on expenditure is needed. As the SPV was established during last year’s review period, this year’s assessment of the output relates to operations during the first year – on progress in completing key documents and on working arrangements. Output 2 will be replaced by an indicator relating to new funding.

Output indicator 6.1
The five year Strategic plan and annual workplan were prepared to a high standard, though cost estimates for the Strategic Plan are still awaited. This year’s budget was submitted later than expected, meaning that there was not sufficient time for the Board and members to properly scrutinise and discuss - steps have been taken to provide this earlier next year. Some key operating manuals, including a finance and procurement manual, are still awaited.

Output indicator 6.2
The SPV is fully operational and has had a successful first year, bringing together a strong team, new innovations, and continued achievement of results. Good working relationships have been developed between Board, management and funders, though there have been instances where DFID have not been sighted on significant funding decisions. Quarterly forecasting has sometimes been very inaccurate, and the quarterly expenditure reporting has not been sufficiently detailed.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
Closely monitor admin costs and overall financial forecasts – ensure these are on track by March 2017.	Administrative costs have fallen since the transition period, though there has been limited reporting on both admin and programme costs so it has been difficult to fully assess the cost drivers. Admin costs are slightly higher than desired mainly due to higher one off costs associated with the creation of the SPV.
A new indicator for output 6.2 should be agreed now that the SPV has been established, potentially focusing on external fundraising.	This has not been changed yet, though FSDZ and DFID are working on draft text on a new indicator to support the focus on bringing in new (non-DFID) funding.

Recommendations
1. The Board and DFID should discuss and agree on how to improve the current governance model. This would ideally be done through a working agreement, or a review of terms of reference. Or it may warrant a formal change in the governance structure, whereby the funders sit on or above the Board to provide a no objection to key decisions (to be discussed at August 2017 Board and Investment Committee meetings).
2. FSDZ and DFID should consider adjusting or removing the Output 6 indicators to take into account the stage of development of the SPV, including a focus on seeking out new funders (by Q3 2017).
3. The members of the company (DFID and SIDA) should strengthen their roles to ensure they provide timely input into key decisions regarding governance, finances and changes in strategy (ongoing; from Q3 2017).
4. FSDZ’s CEO and finance team should ensure that outstanding operating manuals are finalised, and take steps to improve their quarterly forecasting and reporting, with urgency (from Q3 2017). .

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

FSDZ has developed a good value for money strategy with key indicators, aligned with DFID’s 4Es approach. There is generally good quality reporting on value for money, and FSDZ has a strong monitoring and results measurement team in place.

Key cost drivers and performance

The tables below set out the main cost drivers, at a high level, under administrative and programme expenditures.

Programme expenditure
Rural and Household Finance	896,308
MSME finance	380,784
Policy and Digital financial services	385,091
Research and information	435,768
Monitoring and results	182,063
Communications and knowledge management	179,705
Luapula Chiefs financial inclusion project	27,598
Total programme costs	2,487,317

Administration expenditure
Human resource	323,666
Governance	75,802
Operational Costs	382,983
Vehicle expenses	18,526
Travel	13,092
Guest house expenses	53,368
Fiduciary and financial management	90,964
Capital expenditure	64,041
Total administrative costs	1,022,442

Total DFID funding, 2016-17:	£3,509,759

Of the programme component (£2.5m), the main component was rural and household finance (£0.9m), which includes the formation of informal savings groups and inclusive insurance activities. £0.4m was spent on research and information, with similar amounts supporting MSME finance and policy and digital financial services. Of the administrative costs, the largest driver was operational costs (£0.4m) which includes the new IT system, followed by human resources (£0.3m). FSDZ are improving their financial reporting on expenditure in order to provide greater transparency and more ‘Economy’ value for money analysis.

Economy
Ratio of national to international STTA consultants
This shows a positive trend which should lead to savings, assuming local consultants are lower cost than international consultants (a comparison of local and international consultant rates has been requested for the final review period).

Technical Assistance	March 2015	March 2016	March 2017
National Technical Assistance	5	10	26
International Technical Assistance	20	12	23
Ratio	1/5	1/1.2	1.1/1

Cost savings
FSDZ has generated savings from using their guest house for consultants (£6,222) and their own office space for training (£19,862). Other savings will be captured from the transition from international to local consultants in activities such as the SME Executive Diploma training. (Banks taking part in the training pay a participation fee to cover venue, meals and national trainer fees, and FSDZ has been covering the costs for international trainers). While the Guest House does generate some savings this may not be enough to justify the time and effort in maintaining it – we suggest reconsidering the value for money of this.

Programme management costs to total costs
The target for this new indicator is 18%. FSDZ overshot this at 23%, in part due to a number of one-off expenses incurred in the setup of the new institution. These included set-up of the guest house, IT handover and setup, vehicle purchase, and office equipment. FSDZ needed to build its process systems and create administrative budgets without prior data from DAI. It is likely that the target will be met in this next period as we move beyond the transition.

Efficiency
Average cost per beneficiary
This indicator measures the efficiency of FSDZ’s support to savings groups. The Rural and Household component comprised 36% of FSDZ’s programme spend over the reporting period, with savings groups accounting for the majority of this. Across the three implementing partners, the costs have continued to decrease, and compare favourably to the regional average of £14 per beneficiary, and to the forecasted cost/beneficiary (CDN - £12, CARE - £7, Plan - £16). It is interesting to note that the cost per beneficiary for Zoona, a third party mobile service provider is significantly lower than the savings groups model, though FSDZ has not funded Zoona during the last year.

Smallholder Farmers and Households	CDN	CARE	PLAN
Cost as at March 2015	£221,042	£69,671	£138,726
Number of beneficiaries reached as at March 2015	15,930	2,410	0
Cost per beneficiary	£13.88	£28.91	N/A
Cost as at March 2016	£319,381	£96,249	£176,053
Number of beneficiaries reached as at June 2016	40,075	10,057	12,148
Cost per beneficiary	£7.97	£9.57	£14.49
Cost as at March 2017	£434,997	£156,638	£251,144
Number of beneficiaries reached as at June 2017	55,047	24,152	25,386
Cost per beneficiary	£7.90	£6.49	£9.89

Partner leverage ratio
This ratio is a good indication of whether FSDZ’s private sector partners are convinced by the business case of the proposed activities and are willing to ‘buy-in’ with their own finances. For support to NGOs, this indicator assesses the crowding in of other support for initiatives. Last year 4 out of 16 partners contributed 50 percent to total project costs. This year, two of the four new private sector partners contributed over 50 percent.. In some cases it may still be justified for FSDZ to contribute more than 50 percent - for example, the MSME Livelabs pilot is an unproven initiative and may require more funding from FSDZ. Once this model has established a track record, MSMEs may be more willing to pay for the training. It may be worth relooking at the proposed package for this initiative – it could perhaps use a sliding scale of funding from FSDZ to encourage MSMEs to take part.

Percentage of partnerships resulting in sustainable practice change
To assist FSDZ assess whether this is happening, four studies were conducted: i) FSP capacity to deliver, ii) Use of FSDZ research products and information, iii) Private services case study, and iv) Policy change. This is a useful indicator to measure efficiency (it could arguably be seen as an effectiveness indicator), but so far uses qualitative evidence rather than estimating a percentage. In all four studies, some evidence of sustainable change was provided.

Effectiveness
Number of actual people utilizing financial services vs planned
This indicator measures the actual results of the programme against the expected milestones across impact and outcomes indicators. Across the board FSDZ has achieved higher results than expected.

FSDZ’s mandate is not only to reach direct beneficiaries, but also to have wider market system change and impact. It could also set a goal for the level of financial inclusion in the country (measured by Finscope surveys) and use progress towards that goal as an indicator of the effectiveness of the organisation’s activities including direct interventions and wider policy and regulatory changes and the impact those can have on financial inclusion.

Estimated economic returns on specific project activities
This is a new indicator that is currently in development –it will be reported on in March 2018.

Equity
Percentage of beneficiaries that are female
FSDZ has a target of 65% of beneficiaries being female. With 51% achieved (25% of farmers) the target has not yet been met, but the trend is positive and with the new Swedish funded WIN programme actively seeking to support this, progress is expected next year.

Percentage of beneficiaries that are below $2.5/day as measured by PPI
Following the first small survey which concluded all beneficiaries were on less than $2.5/day, further studies were conducted to assess poverty levels of the beneficiaries of savings group support. This larger study concluded that 21% were very poor, 49% poor and 20% near poor. No target was set but results are encouraging.

Percentage of beneficiaries in least connected/ poorest states
Assuming that results reported at the national level (e.g. those from DFS) cover the whole country in the same ratio as population, beneficiaries from both national and direct beneficiaries from the programme are more or less aligned with population density. The biggest discrepancies can be seen in Western Province, Luapula, and Lusaka (the assumption above may under report results for Lusaka). Poverty levels are highest in Luapula and Western Province, so the upcoming workstream with traditional leaders (Council of Chiefs) in Luapula province is a welcome addition to the portfolio. FSDZ should also assess whether there are any opportunities to work in Western province, for example through existing partners who have a presence there.

Gender, diversity and disability
FSDZ’s new Gender, Diversity and Disability Action Plan aims to mainstream gender, diversity and disability into all FSDZ’s activities. This is a welcome approach, going further than in other DFID Zambia programmes. FSDZ should ensure this links into their overall objectives e.g. via the Theory of Change, look at what is being monitored beyond process, and add a timeframe for these activities. FSDZ could consider linking to disability organisations that could help in the institutional assessment to understand where some of the inclusion challenges lie (following the principle of ‘nothing about us without us’). The Zambia Accountability Programme (ZAP) may also have some useful lessons on mainstreaming gender and disability.

Value for money performance compared to the original value for money proposition in the business case
The original business case proposed three value for money measures:
1. The ratio of programme management to total costs (<20%; later changed to <18%)
2. Estimated economic returns for specific project activities (>15%), and
3. The cost of financial inclusion for each additional person (<£24)

FSDZ’s value for money strategy has expanded these, identifying a number of indicators across the ‘4Es’. Using the original indicators, the programme is above the level set for administrative costs (23% vs 20%) – FSDZ will need to address this in the second year, and there should be fewer transition related administrative costs. The second indicator (on economic returns) is still being developed and will be reported on for the final review of this phase of funding. For the third indicator, the total number of direct beneficiaries is 271,091 and the total programme cost to date is £12,088,688, resulting in cost of financial inclusion per person of £44.60. However, this does not capture the many indirect beneficiaries who benefit from the policy and regulatory work of FSDZ.

Assessment of whether the programme continues to represent value for money
Based on the above analysis of progress against value for money indicators, the programme overall does continue to represent value for money – it has performed well against the impact, outcome and output milestones, has achieved an ‘A’’ score overall, and is assessed as minor risk. However, there is scope for further efficiency and economy savings – for example the level of administrative costs should decrease in the second year under the SPV structure and require continued monitoring. If further funding is approved, the range of value for money indicators and targets will be reviewed, taking into learnings to date from the programme as well as from other DFID Zambia programmes.

Quality of financial management
DFID makes funds available to FSDZ at quarterly intervals in advance, against a forecast of expenditure for the period covered and a statement of actual expenditure for the previous quarter.

Table 1 shows a comparison of planned to actual total expenditure for FSDZ for financial year 2016. The programme spent 103% against initial forecast representing an over spend of 3% which is within acceptable limits. This was due to some additional administrative costs during and after the transition from DAI to FSDZ.

Forecast 2016/7	Actual Spend / 2016/7	Variance / 2016/7
£3,409,757	£3,509,758	103%

During this review period, the forecasting and expenditure reporting have been problematic. For example, quarter one and two recorded underspend of 51% and 11% against forecasts respectively. The quarterly expenditure reports lack sufficient information to give DFID an insight into what was spent on each thematic area, and on administrative costs. This is partly because FSDZ has been using a manual system to capture expenses which has proved to be challenging. A new automated IT system has faced a long delay but when up and running should give a more accurate expenditure for both financial and procurement operations. We do not envisage that the programme will incur costs above the overall approved budget.

Date of last narrative financial report	05/07/2017
Date of last audited annual statement	First audit under SPV to be carried out w/c 16/07/2017

Recommendations
1. More detailed quarterly and annual financial reporting on expenditure is needed (ongoing; from Q3 2017).
2. FSDZ’s finance team to set out plans to improve the accuracy of their forecasting to avoid large variances (ongoing; from Q3 2017).

E: RISK (½ page)

Overall risk rating: Minor

Overview of programme risk
The overall assessment of programme risk is minor. The SRO reviews the risk matrix for the programme each quarter, consulting with others in DFID and FSDZ. This focuses on what are considered the top 5 risks at a given point in time, and tracks their status and trend.

The top five risks currently include:
1. Transition and operating risks: The new FSDZ structure continues to incur additional transition related costs and delays.
2. Misuse of funds (fraud, corruption and reputational damage): Risk of funds not being used as intended (a proportion of the programme funds will be subcontracted and granted to other organisations).
3. Policy environment and partner support: Deterioration in the Zambian policy/regulatory environment (e.g. reserve requirements further crowd out lending to MSMEs; Financial Inclusion Policy not finalised). Key policy partners such as Bank of Zambia, Ministry of Finance, and the Pensions and Insurance Authority cease to be supportive of financial inclusion.
4. Macroeconomy: Significant deterioration in the global environment or the Zambian macroeconomy (e.g. a combination of low copper prices, fiscal deficits, and a weakened kwacha raise interest rates and further crowd out MSME and other lending). Low GBP exchange rate impacts on programme purchasing power as well as international staff and contractor remuneration.
5. Financial sustainability – DFID funding is expected to move to a matched fund model for the following three years, so there is a risk that sufficient additional funding from other sources is not forthcoming.

Most macroeconomic indicators have stabilised or improved in recent months, though risks remain for private sector lending and access to finance. The interest rate caps on lending have been removed and the Ministry of Finance is developing a National Financial Inclusion Strategy, so there have been some encouraging signals in the policy environment. On balance, this programme remains minor risk. While the move to an SPV has now been made, transition-related issues could still negatively affect FSDZ's programme delivery, though at this stage it is a low risk.

Likelihood and impact of risks:

		Impact
		Insignificant	Minor	Moderate	Major	Severe
Likelihood	Almost Certain
	Likely
	Possible		1.Transition and operating risks / 4.Macroeconomy: significant deterioration in the global or Zambian economy	5. Financial sustainability: new funding sources are not sufficient
	Unlikely			2.Misuse of funds (fraud and corruption / 3. Policy environment and partner support
	Rare

While some of the risks in the table above could have moderate impacts, given that the programme is now in its final year with performance on track to exceed final outcome targets, it is judged to be minor risk overall. This is also in line with most of the output risk assessments.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme is delivering as planned against the envisaged timeframe and is expected to achieve or exceed the end-of programme targets. Outputs in some areas are taking longer than expected to achieve, but given the market systems approach employed by FSDZ this is manageable with a high degree of confidence that these outputs will be delivered by the end of the current funding period (March 2018).

Performance of partnership
Since the transition to an SPV there were several changes in the DFID programme management team, but the new programme CEO and DFID SRO have developed a good working relationship. FSDZ has also taken part in the DFID Partner Voice pilot in which our office gathered feedback from the FSDZ team on the working relationship with DFID. Overall, feedback was positive, commending on flexibility to learn, but requested more proactive support on complying with DFID procedures.

Asset monitoring and control
FSDZ has maintained a well-documented asset register which is updated regularly with clear description of assets and the date of purchase. A spot check was carried out in January 2016 and all assets were found in good condition. During the transition from DAI contract to a special purpose vehicle, an updated asset register was compiled and all assets were transferred to FSDZ. A spot check has been scheduled for the second half of 2017.

Communication and visibility
FSDZ has a dynamic comms team who have raised FSDZ’s profile on social and traditional media. Increasing awareness of financial services is an important part of FSDZ’s mission, and having a comms presence helps to disseminate research to a wide audience. Events, such as financial literacy week, research launches, and workshops, are professionally organised and run, and receive good feedback from attendees. However, FSDZ needs to be cognisant of DFID’s risk appetite for activities that are not in line with programme objectives or that could be misrepresented, and should sign and follow the visibility statement. FSDZ should also consider the balance between promoting FSDZ, and using communications as part of programme activities, and could look at measuring the impact of its communications activities.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
An assessment of the Partnership Principles is not relevant as this programme does not directly engage with the Government of the Republic of Zambia, nor does it use government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
No external evaluation is currently planned for FSDZ, though one should be considered as part of any further DFID funding beyond 2018 as a means of assessing change at the market systems level. DFID’s results adviser has previously found that FSDZ has an adaptive and strong theory-based approach to monitoring and evaluation (M&E). The project has placed the theory of change at the heart of its M&E function, and reviews and adapts the theory of change on a regular basis, changing it as new evidence and monitoring data is produced, creating a valuable feedback loop.

As noted in section C, FSDZ is doing excellent work to build the evidence and statistical base in Zambia on financial inclusion, including Fin Scope, financial diaries and geo-spatial mapping. FinScope is an impressive survey, especially because it is representative to the district level across Zambia. The data and findings from the 2015 FinScope have been used to produce a series of analytical papers (FinScope FOCUS Series) in the period until the next planned FinScope, in 2018.

There is very good networking on M&E across the FSD Africa offices, and this has increased since the move to an SPV. FSD offices across Africa (with good support from FSD Africa, the centrally funded regional programme) are sharing evidence and M&E approaches in a very constructive way. This can range from using evidence generated in another office or collaboration on a research topic to the discussion of indicators and methodology tools - the M&E system developed in Zambia is being promoted as an exemplar across other FSD offices.

Monitoring progress throughout the review period
The DFID team has attended a number of external FSDZ events since the last review period, such as the launch of the Cenfri Making Access Possible work and financial literacy week events. All have been very high quality and well attended. The annual review process involved meetings with a range of stakeholders including the Bank of Zambia, Ministry of Finance, commercial banks, regulators, and a mobile money agent.

The Annual Review visits and meetings were carried out in June 2017 by DFID Zambia’s Economist and Programme Manager and DFID Tanzania’s Inclusive Growth Team Leader. These included field visits to savings groups in Kabwe and Copperbelt (run by different implementing partners), weather index-based insurance projects near Manze in Southern Province, and financial education projects in Kabwe. In the coming year, additional field visits should be arranged to meet beneficiaries and provide additional monitoring opportunities – in particular, to see the progress being made at the new project with Luapula Chiefs.