Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2018

Title: Knowledge Partnership Programme (KPP)
Programme Code: 202765	Start Date: October 2012	End Date: December 2017

Summary of Programme Performance

Year	2012 – 13	2013 - 14	2014 - 15	2015-16	2018
Programme Score	A	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium	Moderate.

Financial Position

Original Programme Value	£9 million
Extensions/ amendments	No-cost extension from June 2016 to June 2017 / No cost extension from June to December 2017.
Log-frame revisions (with dates)	September 2014 / June 2016 / April 2017
Total programme spend	£ 8,814,679

Follow up actions required following closure

We have carefully analysed the lessons and ensured they are integrated into the design of the new Global Partnership Programme on Development. We will continue to ensure KPP lessons are informing programming delivery in the next phase.

We will remain engaged with leading Think Tanks, senior officials from Ministry of External Affairs, (MEA) Government of India, EXIM Bank, CII (Confederation of Indian Industries) on global development. The team will continue to reach out to stakeholders across a range of organisations at multiple levels.

DFID team shall continue to contribute to X –HMG priorities.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202765/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202765/documents/

Outline of programme and what it has achieved

DFID India launched Knowledge Partnership Programme (KPP) in 2012. KPP sought to enhance collaboration on ideas, technology and innovation to expedite learning between India and developing countries for improved development outcomes. The primary focus of KPP was to work with India on impacting the delivery of global public goods and services and leverage Indian experience to reduce poverty in third world countries. It worked by supporting partner institutions with evidence-based studies that (a) gathered and promoted uptake of evidence on issues central to India’s impact on global poverty and (b) shared Indian evidence, best practice and expertise with Developing Countries. KPP thus directly relates to DFID India’s objective (as stated in DFID India’s Operational Plan 2011-15) to deepen the engagement with India on global issues.

KPP has delivered many knowledge products in six areas: Health, Nutrition and Disease Control; Women and Girls; Food Security, Resource Scarcity & Climate Change; Trade and Investment and Development Effectiveness. Knowledge products in these six areas have helped establish a novel partnership between the UK, India and selected developing countries.

Engaging with India on global development was a new area of work for DFID in India. KPP helped the team to learn and test different approaches. KPP proved to be an innovative initiative that generated both knowledge and practical action to strengthen India’s engagement with the developing world, and promoted better development outcomes.

Until June 2016, the consultancy IPE Global managed the implementation and management of KPP. Thereafter, DFID India took over direct management. In April 2016 the HoO (Head of Office) approved a no-cost extension and extended the programme by one year to June 2017. Subsequently another extension was approved until December 2017.The rationale for this was to allow the Global Team to remain responsive to key stakeholders and develop new areas of work quickly and effectively; better align the portfolio to the three focus areas of our Global strategy refresh (Development Diplomacy; Trade and Investment; Affordable Innovations); and demonstrate concrete actions to respond to commitments for development cooperation in third countries, agreed in the Joint Statement by the two Prime Ministers in November 2015. The time extension to the programme enabled the team to deliver using the remaining approved financial resources.

Context: The ToC (Theory of Change) was developed in the Business Case and still stands. The ToC is that relevant and high quality analysis (‘knowledge products’), and communicating findings persuasively to key decision makers and policymakers, through briefs, meetings, events and media campaigns, will lead to uptake in terms of more evidence-based policy choices and programming. Over time, these choices will support improved development outcomes for poor people. KPP has performed well, with evidence of delivery of expected outputs and outcome. The key success factor in the ToC is the quality of the DFID relationship with GoI.

In effect, two Theories of change have been tested: the first, where partnership was not under direct DFID control; and the second, where partnership is under direct DFID control. The direct management of partnerships has enabled DFID to strengthen relationships with Government of India /MEA.

Results: KPP initiated multiple and varied projects / assignments in its five years tenure, across the six work streams. Not all studies / assignments had the same level of success, but several initiatives did manage to inform policy change in India and in other countries, even though direct attribution to policy influence has been inherently difficult. KPP filled a critical gap in learning for development across countries. The programme has been able to demonstrate the need for sharing and the appetite for learning among developing countries.
DFID has built strong relationships with the senior Indian officials and influencers who are instrumental in delivering the ‘UK-India Joint Statement of Intent’ of November 2015.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Outcome Indicator	Milestone (2017)	Achievement (2017)	Description
Number of development programmes / schemes / practices in LICs informed by KPP	4	4	Bangladesh, Nepal, Malawi and Kenya
Number of development programmes / schemes / practices of India informed by KPP	4	6	Informing NFTP, DFTP and TPP. (National Foreign Trade Policy, Duty Free Trade Preference, Trans Pacific Partnership) Strengthening Agricultural Forecasts and pharma quality testing processes
Number of newer Indian institutions significantly involved in global development policy / processes	4	7	RIS (Research and Information Systems -Think-Tank); ORF (Observer Research Foundation), EXIM (Export Import Bank), FICCI (Federation of Indian Chamber of Commerce and Industry); CIIE (Centre for Innovation, Incubation and Entrepreneurship - Private Organisation); WNTA (Wada Na Todo Abhiyan – Civil Society Organisation) and NCAER (National Council for Applied Economic Research)

Number of development programmes / schemes / practices in Developing Countries informed by KPP
Malawi, Bangladesh, Kenya and Nepal are LICs which have engaged in Indian practices and initiatives under the KPP and are willing to adopt or test similar programmes / initiatives in their countries. This includes: transferring Low Carbon Building Technology (Malawi); promoting resource efficiency along the supply chain of key sectors (Bangladesh); learning from the debates in Indian civil society that led to its Right to Food legislation (Bangladesh); learning from India’s tea sector Trust Tea Code and Plant Protection Code – (Nepal), Safetipin (Kenya).

Number of development programmes / schemes / practices of India informed by KPP

KPP has especially contributed to the Indian trade policy landscape with research based evidence and policy level interactions. This includes – (i) Informing the National Foreign Trade Policy; (ii) informing India’s Duty Free Tariff Preference (DFTP) scheme and making more tariff lines duty free for LIC’s; (iii) Government recognising the importance of mega-FTAs like TPP and the importance of the upcoming plurilaterals being included in the new foreign trade policy and the economic survey document of the Government of India; (iv) credible and improved Agricultural Forecasts; and (v) strengthening the quality of Indian Pharmaceuticals (on drug testing facilities).

Number of newer Indian institutions significantly involved in global development policy / processes.
KPP has strengthened the engagement of a number of Indian institutions in various global development processes. Research and Information Systems (RIS -a Delhi based think tank supported by the Ministry of External Affairs, Govt of India) has built capacity among research institutes and government officials in Myanmar in international and regional trade agreement and facilitation. RIS is committed to continue supporting this initiative. ORF has been instrumental in engaging constructively with policy makers. The DFID-ORF partnership will increase our ability to liaise constructively with GoI on the effectiveness of Indian engagement in global development processes. DFID and EXIM are jointly working to establish EXIM’s monitoring systems.

Output Score and Description

KPP’s Overall Score is A, indicating that outputs taken as a whole have met expectations.

Description	Score	Impact weight
KPP produces and disseminates High quality Knowledge Products (KPs) on climate smart development, low carbon growth, resource scarcity and food security.	A+	25%
KPP produces and disseminates High quality Knowledge Products (KPs) on Health, Nutrition & Disease Control.	A	10%
KPP produces and disseminates High quality Knowledge Products (KPs) on Trade & Investment	A	20%
KPP produces and disseminates High quality Knowledge Products (KPs) on transforming the lives of women and girls (Focal areas: VAWG, Women Empowerment & Education)	A+	20%
KPP Responsive window responds effectively to demands for emergent, non-priority workstreams and cross-sectoral studies to promote development effectiveness.	A	15%
Demonstrate concrete actions towards commitments under the UK-India Joint Statement of Intent.	B	10%

The first 4 outputs focused on producing and disseminating Knowledge products. KPP has had significant success against these outputs.
Output 5 responded to the workstream on development effectiveness. This was led by Think Tanks and preparation of policy papers eg Post 2015 Millennium Development Goals Agenda Consultation, carried out by UNDP and CSO.
Output 6 was designed to take forward initiatives that would respond to the UK –India Joint Statement.
Working with leading Think Tanks, who can be instrumental in policy engagement and building on existing relationships with the senior DPA (Development Partnership Administration) officials. This workstream is a combination of different initiatives to achieve this objective.

Lessons and how these have been shared

Building relationships and networks:

- Direct implementation by DFID enabled the team to build a stronger and strategic relationship with GoI /MEA and other stakeholders. We have learnt this is an incremental process and it takes time. India’s bandwidth to engage on global development is not limitless and understandably therefore they prioritise.
- The other lesson is that working with India on global issues requires us to engage across the full spectrum of India’s diplomacy (Europe West) and development divisions (Development Partnership Authority,(DPA, 1,2 and 3) UN and multilateral. To do this, it is helpful to work with other HMG departments; especially the High Commissioner and senior members who can help develop a holistic understanding of the India-UK global partnership. We were able to use this lesson in preparation for the Commonwealth Summit.
- We learnt that India is keen to learn from all sources and not just UK. We need to have mechanisms to facilitate such knowledge exchange quickly to enhance our cooperation with GoI on India’s development practices.
- Building engagement with policy makers should be done from the initial stage onwards. This is essential for knowledge sharing programmes to bring in policy changes. Work of the Think Tanks needs to be actively taken to the policy makers for making an impact.
- Engagement with civil society groups in the recipient country is imperative to build support base for transferring knowledge.
- The outsourcing model was successful in creating networks. However it was limited in its ability to catalyse change at the policy level as partners had inadequate knowledge about global best practices.

This programme highlighted the need for DFIDI to manage senior stakeholder relationships more directly and enabled technical leads to engage in first-hand interactions with partners to work jointly to achieve the desired outcomes. Based on these, DFID India is now developing a strategic, high value programme to work with Government of India to deliver joint priorities in development.

Sustaining relationships and networks
- Future programme should sustain engagement with DPA, MEA, Ministry of Commerce, EXIM Bank, CII, FICCI and other institutions to ensure we are able to demonstrate the value of this partnership to the Indian government.
- Identify key areas of common interest with DPA/MEA, where DFID engagement will add value.

Choosing the right partners
- Partner credibility and strength is a significant factor in generating effective policy engagement. Some of KPP’s partners have strong networks and are associated with high-level policy makers, enabling direct access to policy development.
- KPP’s experience shows that self-driven, credible partners, whose early initiatives were seed funded by KPP not only continued the initiative beyond the project but also leveraged other funds for its upscaling.
Opportunities for lateral programmatic expansion
- Interventions in one sector can have impact on other sectors, providing opportunities for lateral programmatic expansion. For instance, there was a rise in women’s livelihood opportunities due to the demonstration of more environment friendly brick-making VSBK (Vertical Shaft Brick Kilns) technology in Malawi. Employment increased around 30% in the pilot initiative and the new technology also raised demand for eco-friendly building materials.
- KPP-like programmes should support inter/ intra-regional, thematic conferences and workshops to share knowledge and to conduct cross-country issue-based studies to facilitate adaption/ replication of models/ programmes and policies.
- KPP type projects should fund an idea / initiative; not just a study or a partner.

Enhanced trade and investment focus to strengthen relationships with key stakeholders: Develop a tighter and more focused portfolio of trade and investment interventions to support the development of more impactful partnerships with the key trade and investment stakeholders (MEA, DPA, EXIM Bank, ORF, RIS, CII).

Dissemination and knowledge sharing
- Capture concrete examples of our impact and disseminate widely within DFID and across HMG.
- Effective communication on the benefits and opportunities of inter-government partnerships.

Working with DFID country offices
- Meaningful engagement requires regular contact and is strengthened by support at the senior management level.
- Engaging with country offices at an early stage of the programme is better to generate interest and engagement – than starting at later stages of implementation – though early engagement needs to be followed up on a systematic basis.
- Different country offices respond differently based on their areas of interest and availability.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	KPP produces and disseminates High quality Knowledge Products (KPs) on climate smart development, low carbon growth, resource scarcity and food security.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Percentage of KPP studies / initiatives completed within schedule	75%		80%
Number of Knowledge Products (KPs) appropriately documented and available in public domain	5		8
Achievement against communication outreach Plan (no. of people reached, key stakeholder meetings)	75%		Achieved
No. of people reached for dissemination of Knowledge Products and study reports on climate smart development, low carbon growth, resource scarcity and food security	Around 22 events were organised under this workstream (workshops / meetings/ round tables / conferences / exchange visits etc.) and 745 key stakeholders from more than 20 countries participated in these events, in various capacities

Key Points
Through this workstream, KPP engaged effectively on key policy outcomes in India and globally, in the areas of agriculture and food security, climate change adaptation and mitigation and protection and conservation of resources. Highlights include:
Global Dialogues: Three Global Dialogues were held in Bangladesh, Mali, and Kenya involving representatives from 18 countries on national food security polices and legal frameworks. These dialogues were based around the FAO publication on ‘State food provisioning as social protection: Debating India’s national food security law’ prepared under KPP and launched in FAO (Food and Agriculture Organisation), Rome. The document has been subsequently translated into French and Spanish by FAO and the cost of publication and future dissemination is being borne by FAO. The ‘Global Dialogues’ led to further demand from 5 Developing Countries for the food security law. Further, a delegation led by the Chairperson of Bangladesh Law Commission visited India to learn about the Right to Food and requested for inputs into Bangladesh’s draft Right to Food Legislation;
Green Bricks: KPP supported technology transfer (high quality, energy-saving, deforestation-avoiding brick technology) to Malawi complemented with capacity building (new VSBK brick kiln and trained operators) has created additional employment (including for women) and elevated brick industry worker incomes by 300%. The Government of Malawi has sought policy advice to manage a national transition to VSBK approaches and GIZ/DFID Malawi are positioned to support its scale up.
- Energy efficiency: Based on learning from a KPP project, IRENA (International Renewable Energy agency) dedicated $461,000 for capacity building of Renewable Energy (RE) entrepreneurs in South Asia using a business incubator approach.
- AMIS: The Government of India agreed to continue funding of the KPP initiated Agricultural Market Information System (AMIS), until 2017. BMGF is supporting the consolidation of similar systems for Nigeria and Bangladesh by FAO, and improving data compilation for India.
- Fly Ash: A complementary series of cross-visits, technology transfer, capacity building and policy dialogue helped secure commitment by Bangladesh government and industry to promote India’s model of unfired fly-ash (FAL-G) brick technology, which will save valuable energy, topsoil and manage fly-ash waste. DFID continued to support this project under Output 6.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A
Recommendations for future programmes
- This Output closed in June 2016, in the future if DFID India has another similar programme, we shall factor in these recommendations.
- Deepen the search of quality and credible partners and building their capacity.
- Build a vibrant portal for accessing and sourcing requirements for cross-country learning and knowledge sharing.

Output Title	KPP produces and disseminates High quality Knowledge Products (KPs) on Health, Nutrition & Disease Control.
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Percentage of KPP studies / initiatives completed within schedule on health, nutrition and disease control	75%	More than 70%
Number of Knowledge Products (KPs) appropriately documented and available in public domain on health, nutrition and disease control	5	7
Achievement against communication outreach Plan (no. of people reached, key stakeholder meetings)	75%	Achieved
	larger events were organised under this workstream – an outreach to 2,330 participants was achieved through 5 conferences

Key Points
This work stream connected Indian health sector successes to global health outcomes, especially in Developing Countries. Areas included access to quality pharmaceuticals, reducing cost of care through technology and reducing anti-microbial resistance. Highlights include the following:
KPP supported initial market scoping in Africa for an affordable phototherapy device ‘Brilliance[1]’ (especially for neonatal jaundice) which is gaining acceptance in Ethiopia, Ghana and Kenya. 1,168 units have been installed and after a competitive tender process the Government of Kenya has plans to install the device in every public hospital in the country.
[1] http://ipekpp.com/admin/upload_files/Knowledge_2_39_D-Revrsquos_8123332691.pdf http://ipekpp.com/admin/upload_files/informaticdoc_2491187114_C:fakepathAffordable_World_class_Phototherapy_for_Neonatal_Jaundice.pdf
Two policy oriented studies[2] based on secondary data and depth stakeholder consultations were conducted on (a) Active Pharmaceutical Ingredient (API) manufacture in India, and (b) Impact of Mergers and Acquisitions (M&As) in the pharma industry on drug prices. The studies were even more contextual in the light of ‘Make in India’ initiative of the Indian Government. The first study highlighted the promising field of API manufacture in India and a high- level (Katoch) Committee has been set up by Government of India to promote API manufacture in India. The findings of the second study on mergers and acquisitions countered popular arguments that an increase in prices of essential medicines in India is attributable to sectoral M&As.
[2] http://ipekpp.com/admin/upload_files/Knowledge_2_39_Promoting_8334133657.pdf http://ipekpp.com/admin/upload_files/Knowledge_2_39_Impact_2575324832.pdf
ORF organised, Health is Wealth – Indian Private Sector Investments in African Healthcare[3], June 2016 this paper examines the nature of Indian private sector investments in African healthcare. It analyses their effectiveness in dealing with the issues around equity of access, the establishment of comprehensive ‘prevention based’ health systems, and the creation of mutual benefit.
[3] http://cf.orfonline.org/wp-content/uploads/2016/06/ORF_IssueBrief_145_NgangomAneja_Final.pdf
- Primary and secondary medical care at affordable prices is a focus for African countries, good and evidence-based documentation (key innovations, service delivery arrangements, reforms, or complementary community level participation) of Indian experience can facilitate better uptake.
- The Indian public health delivery story is under-researched and thus requires focused attention and investment in conducting systematic documentation and its dissemination.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations for future programmes
- Considering that India is emerging as a hub in offering primary and secondary medical care at affordable price and competitive quality, there is scope for exchange of knowledge and technology with developing nations in Africa.
- This Output closed in June 2016.

Output Title	KPP produces and disseminates High quality Knowledge Products (KPs) on Trade & Investment.
Output number per LF	3	Output Score	A
Risk:	Medium	Impact weighting (%):	20%
Risk revised since last AR?	No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Percentage of KPP studies / initiatives completed within schedule on Trade & Investment	75%	More than 75%
Number of Knowledge Products (KPs) appropriately documented and available in public domain on Trade & Investment	5	15
Achievement against communication outreach Plan (no. of people reached, key stakeholder meetings)	75%	Achieved
No. of people reached for dissemination of Knowledge Products and study reports on Trade & Investment	11 Key events (Conferences, Seminars, Training, Meetings etc.) were organised under this work stream and an outreach to 1075 high-level stakeholders was achieved

Key Points

The studies under this stream have focused on strengthening India’s engagement in Africa and Asia, through Asian and African LDC’s on improved trade relations and technological collaboration under structural and economic growth transformation programmes. Evidence based research projects have analysed the developmental impact of various Indian trade, investment and aid policies in other developing countries in an effort to assess and identify optimal policies and best practices that contribute to global development. Capacity building, especially for Myanmar Government officials and Confidence Building Measures with Afghanistan have been a key and significant contribution of the KPP under the T&I work stream. The demand and response from Myanmar has been particularly encouraging. Highlights include:
- There has been a major shift in India’s approach towards the emerging Mega Free Trade Agreements (FTAs) / plurilateral agreements and their role in the global trade architecture. KPP supported analysis has informed this process significantly.
- As a direct result of KPP efforts[4], a MoU has been signed between the Quality Council of India and the African Standards Organisation to share key elements of improving standards in both the continents in the context of the upcoming mega FTAs. This has increased awareness about adapting higher standards to be adopted across sectors for India to be a part of TPP (mega FTAs).
  [4] http://ipekpp.com/pdf/Achievements/Report_1_17_Building_7876964610.pdf
- A KPP supported study [5]contributed to changes in the DFTP scheme and facilitate exports from Africa to India. Liberalisation was extended to cover nearly 98 percent of the tariff lines under the ‘duty free’ regime.
  [5] http://ipekpp.com/pdf/Achievements/Report_1_17_Building_7876964610.pdf
- A KPP supported study[6] on ‘Making Indian Development Assistance more effective by building better synergies between India’s South-South Cooperation and the Indian Private Sector’ by CII was disseminated in a seminar and shared both with Ministry of External Affairs and the Ministry of Commerce and Industry to help India further analyse the impact of development cooperation initiatives of India’s private sector in Africa as well as the impact of India’s Lines of Credit.
  [6] http://ipekpp.com/admin/upload_files/Report_3_25_Indiarsquos_2431529605.pdf
- The findings of the KPP study[7] – ‘Removing Barriers to Trade and Investment between India and Ethiopia’ have been shared with the Ethiopian Trade Minister and Ethiopian Ambassador to India. The report includes a comparison of Ethiopian trade practices with that of other East African countries such as Kenya and is thus useful to the entire region.
  [7] http://ipekpp.com/admin/upload_files/Report_3_52_Prospects_2523493963.pdf
- The KPP supported trade capacity building training programme for the Myanmar government officials being carried out by RIS has helped officials to understand India’s trade policy, as well as international trade related issues and the art of negotiations. Myanmar’s counterparts have requested for a continuation of the effort.

Summary of responses to issues raised in previous annual reviews (where relevant) – N/A

Recommendations for future programmes
- Develop a tighter and more focused portfolio of trade and investment interventions to support the development of more impactful partnerships with the key trade and investment stakeholders (MEA, DPA, EXIM Bank, ORF, RIS, CII).
- The programme team established contact with the counterparts in the respective DFID country offices, however the interaction was limited. Going forward we need to engage with colleagues in DFID country offices at an early stage of programming and then sustain communication in a systematic and regular way.
- This Output closed in June 2016.

Output Title	KPP produces and disseminates High quality Knowledge Products (KPs) on transforming the lives of women and girls (Focal areas: VAWG, Women Empowerment & Education)
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone (2016)	Achievement (2016)
Percentage of KPP studies / initiatives completed within schedule	75%	80%
Number of Knowledge Products (KPs) appropriately documented and available in public domain	5	11
Achievement against communication outreach Plan (no. of people reached, key stakeholder meetings)	75%	Achieved
No. of people reached for dissemination of Knowledge Products	24 events (Knowledge Exchange, Scoping Visits, Workshops etc.) were organised under this workstream achieving an outreach among over 1600 key stakeholders.

Key Points

Though there remains much scope for improving its gender indicators, India has seen substantial progress in this area that can be documented and shared as lessons / solutions with other developing countries. Examples include:
- ‘Safetipin[8]’, an application for crowdsourcing women-safety information, demonstrated the utility of community-based, safety audits in developing countries. There has been interest among policy makers in India, Nepal, Bangladesh and Kenya to use the application and the data. An agreement has been signed with ‘Uber’ to collect city night data. Safetipin has been able leverage funds from other sources to continue and scale up the initiative, for e.g. in Nairobi with support from UN Habitat.
  [8] http://ipekpp.com/admin/upload_files/informatic_2100023249_C:fakepathSafetiPin_Technology_for_safe_public_spaces.pdf
- A scoping exercise to pilot the Kudumbashree model[9] in Ethiopia was conducted in two regions of Ethiopia in November-December 2015 following which an Intervention plan and Budget have been formulated. Further support to implement this pilot was planned for the extended phase, however the project was postponed due local conditions.
  [9] http://ipekpp.com/admin/upload_files/Report_4_44_Ethiopia_1639660404.pdf
- A two-day Regional Workshop was held in Nairobi (March, 2016), with representatives from India and five East African countries to share good practices in economic empowerment of women and to build a knowledge and peer learning platform “Mitreeki”[10] The network is now being managed by ITC (International Trade Centre) under the SITA (Supporting Indian Trade & Investment in Africa)[11] programme.
  [10] http://www.intracen.org/SITA/Mitreeki-East-Africa---India-Partnership/
  [11] http://www.intracen.org/sita/
- This work stream has undertaken several knowledge exposure visits, scoping visits, International and National level consultations on themes of maintaining women’s safety (in public and private spaces) and women’s economic empowerment.
- A Panel on Digital Empowerment held in September 2016; part of ORF deliverables, featured over 100 experts from 33 countries. The panel consisted of both Indian and African participants from academia, the private sector, and relevant policy communities. It examined how internet access can facilitate inclusive development, particularly for women.
- ORF organised a ‘Panel on Gender Empowerment’ at the Raisina Dialogue | March 2016
The session ‘DiplomaShe: Gender, Policy and Politics’ explored the issue of women in the workplace, particularly in the fields of politics, development and foreign policy.

All the initiatives above will benefit from a combination of policy and programme expertise bringing in experience both from India and other geographies.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations for future programmes

- Engagement with policy makers in India and recipient country from the initial stage is essential for knowledge sharing programmes to bring in policy changes.
- Engagement with civil society groups in the recipient country is imperative to build support base for transferring knowledge.
- Capacity building and technology transfer that help in transforming the lives of women, based on evidence of successful implementation at home with a road map for knowledge transfer, would have more takers.
- Engagement with DFID country offices can strengthen in-country support for the programme and help deliver synergies. The success of such engagement depends on regular and consistent contact, engagement by senior management and the interest and availability of the country office.
- KPP-like programmes should support inter/ intra-regional, thematic conferences and workshops to share knowledge and to conduct cross-country issue-based studies to facilitate adaption/ replication of models/ programmes and policies.
- This Output closed in June 2016, in the future if DFID India has another similar programme, we shall factor in these recommendations.

Output Title	KPP Responsive window responds effectively to demands for emergent, non-priority workstreams and cross-sectoral studies to promote development effectiveness.
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Percentage of KPP Responsive Window studies / initiatives completed within schedule	75%	Achieved
Number of Responsive Window Knowledge Products (KPs) appropriately documented and available in public domain	8	13+ achieved
Number of assignments / analysis with potential to inform international agreements	3	Achieved.
Achievement against communication outreach Plan (no. of people reached, key stakeholder meetings)	75%	5 workshops were held with 755 key stakeholders. Apart from these, KPP supported various dialogues to engage with a wide range of stakeholders to discuss and develop positions around the evolving development agenda and contribute to the global discourse. This has been one of the largest social engagements for a global agenda, in India. An estimated 15,000 people across thousands of organizations, with representative membership of 400 million Indians, were involved in the process.

Key Points

This stream has had the largest and widest variety and highest budget among assignments under KPP. All issues of multi-sectoral development that are not covered under specific streams have been placed here. Over the lifetime of KPP, this work stream has covered issues such as Post-2015 debates and discussions, Transparent Governance, Fiscal Analysis and promoting Entrepreneurship Eco-systems.
Two core areas have been taken forward by the management agent under this work stream:
 i) Post 2015 MDG Agenda Consultations – carried out by UNDP and Wada Na Todo Abhiyan (WNTA)[12], and ii) the India Human Development Survey (IHDS)[13] – India’s largest developmental effectiveness panel survey covering urban and rural areas to monitor progress of national/state led programmes, carried out by NCAER.
[12] http://ipekpp.com/admin/upload_files/Report_5_33_Overview_7877492221.pdf
[13] https://ihds.umd.edu/
- A third work stream has been directly managed by DFID. This has involved support to the ORF to take forward analytical and convening activities focused on India’s global development impact at the level of individual developing countries and at an international level.
- The support to the Observer Research Foundation helped to strengthen DFID’s profile in the run up to the India-Africa Summit, and stimulated debate on the outcomes of the Addis Financing for Development conference – through a de-briefing meeting with the Minister of State for Finance.
- Monitoring the performance of the Sustainable Development Goals among developing nations provides an opportunity to collate learning and together steer development outcomes in the right direction.

Summary of responses to issues raised in previous annual reviews (where relevant) N/A

Recommendations for future programmes
- The flexibility of this work stream was appreciated, important to maintain an overarching theme (like governance etc.), as it is difficult to oversee a widely varying portfolio.
- This Output was closed in June 2016.

Output Title	Demonstrate concrete actions towards commitments under the UK-India Joint Statement of Intent.
Output number per LF		6	Output Score	B
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Milestones	Progress
Projects implemented that show: / (a) clear demand from third countries and / (b) alignment with UK-India strategic priorities.	10 new projects	6 completed , 2 not pursued, / 2 good progress, though not completed.

Key Points

This programme highlighted the need for DFIDI to manage stakeholder relationships more directly and enabled technical leads to engage in first-hand interactions with partners to work jointly to achieve the desired outcomes. Based on these, DFID India is now developing a strategic, high value programme to work with Government of India to deliver joint priorities in development.

Engaging with Ministry of External Affairs.

Engaging constructively with India (DPA) on adopting global good practice on development management: In a two-day workshop in December 2016, senior Indian officials and DFID India staff shared their experiences on designing and delivering development projects. India is keen to institutionalise an arrangement for knowledge partnership on development good practice between the two countries with a shared pool of global expertise. We have discussed such knowledge partnership could include exchange programmes, workshops on specialised areas, sharing of global experts and consultants and we are ambitious, development of joint strategies for development in select countries / and or sectors in Africa and Asia.

In late 2017, we worked on a pilot design work for joint detailed project report development in Ghana demonstrating our capacity in procurement The Ghana pilot project could not be completed due to the fact that KPP was ending and preparation of DPRs needed more time than the available five months. The project in Ghana also required clearances from borrowing government and Indian government. Personnel changes in the Ministry also affected the progress within the short time frame. India and UK were doing such joint work for the first time and we underestimated the steps required to arrive at joint decisions on procurement.

Engagement with EXIM: DFID and EXIM signed a Memorandum of Understanding (MoU) in March 2016 to develop a partnership on shared goals of global poverty reduction and developing more effective investment instruments that deliver impact for the poor in developing countries.

Consultants procured by DFID have provided EXIM bank staff training and support on understanding and assessing the development impact of the Bank’s financial instruments and projects, with a view to enhancing the development impact of Bank operations. Our engagement with EXIM has been deepest on their Lines of Credit (LoC) work where support has been provided on streamlining existing monitoring processes, standardizing tools and developing templates with the long term objective of switching to an integrated IT system on the lines of DFID’s own Aid Management Programme (AMP).

DFID organised a training of the AMP system for EXIM in early 2017 and have been working with DFID’s Business Innovation team (London) to enable this technology transfer.

DFID has also discussed linking EXIM’s OIF (Overseas Investment Finance)-loans to Indian companies to invest abroad-with the work being done under DFID’s programme SITA (Supporting Indian Trade & Investment for Africa).

Partnership with Think Tanks

RIS and ORF are both influential think tanks , while RIS is affiliated to the Ministry of External Affairs ORF is well recognised and leads on forums eg Raisina Dialogue ; ( MEA’s flagship event on international issues)
- This association has provided a unique platform to discuss India’s development cooperation programme and policies. We have prepared a number of papers and used these to engage with India’ thinking on Africa, Development Assistance; regional and global development challenges.
- The Accountable grant with ORF delivered high quality analysis and targeted engagement and events with GoI, including on Indian aid architecture, LOC, FDI, BRICS, women empowerment, G20 and Raisina Dialogue.
- DFID India Global Team leader and Senior Governance Adviser were key speakers at the South-South conference held in New Delhi, August 2017.

Preparing for the Commonwealth Summit

We have used our relationships with think tanks and senior GoI officials to support early engagement, jointly with the FCO, with India on the Commonwealth Summit. This has included joint calls on senior Indian officials, organising ‘roundtables’ on the future of the Commonwealth and India’s role in revitalising it, and commissioning analytical work on Commonwealth trade, India’s role and India’s interests. These activities have contributed to a positive engagement with India on the Commonwealth.

FAL –G Brick Technology for Bangladesh: Completion of clean brick technology transfer to Bangladesh.

DFID continued to support IIP on this initiative to conclude this technology transfer with the Government of Bangladesh.

The project has made considerable progress towards achieving its intended outcomes, in
particular:
Policy Changes catalysed Two policy amendments initiated viz.
1. Inclusion of fly ash in Bangladesh Environment Conservation Policy; and
2. Inclusion of Fly ash Bricks in existing Brick gazette (Brick Manufacturing and Kiln Set up (Control) Act, 2013) that will help in promotion of fly ash brick technology) . Convincing DoE and BBMOA about the technical and economic viability of FaL technology (Brick price, quality and market acceptability);
- Creating understanding about the key success factors and failure issues to establish and scale up FaL-G technology, in particular the importance of taking together diverse stakeholders (need to work closely with industry associations, entrepreneurs, technology suppliers) and working on both the supply side (policy reforms, market based incentive mechanism etc.) as well as demand side (working with construction companies and government agencies on creating awareness and reviewing their procurement policies etc.);
- Establishing a spirit of cooperation and collaboration between policy makers, industry associations and industry members of the two countries to share learnings, experiences, technologies and practices;
- Identifying knowledge partners like Housing Building Research Institute to act as repository of information on the technology and provide hand holding support to industry;
- Sector assessment and Development of specific policy recommendations (Policy Briefs) that can be adopted by the policy makers, industry and other stakeholders
- Apart from the plant for pilot demo, two more brick entrepreneurs have ordered FaL-G plants from India, which should reach Bangladesh by April 2018.The project has demonstrated scaling up the technology. This new technology would help in replacing the existing outdated technologies with low efficiency and poor social & environmental performance.

DFID TA to support CDC to catalyse Indian investors to frontier markets;

DFID procured services of a consultant to map the healthcare demand and supply situation in select countries in Africa (Nigeria & Ethiopia). This was to enable Indian medical operators to invest in hospitals/support establishment of affordable hospitals/ healthcare ventures in Africa. The purpose of the study was to identify a specific number of investment targets in the selected countries. The study highlights the gaps in skills, infrastructure, regulations, pricing and other local conditions. CDC has the opportunity to pursue these opportunities jointly with CDC’s existing healthcare portfolio companies. This is work in progress.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations for future programmes

- Future programme should sustain engagement with DPA and MEA to ensure we are able to demonstrate the value of this partnership to the Indian government.
- Identify key areas of common interest with DPA/MEA, where DFID engagement will add value.
- Capture concrete examples of our impact and disseminate these more widely within DFID and across HMG.
- Communicate more effectively the benefits and opportunities of such a partnership.
- In KPP’s engagement with CDC, CDC was found to be receptive and open to joint work. Specifically, there exists potential and interest (in CDC) around DFID adding on TA support to CDC’s investment focused work. The initiative on this kind of work may need to be taken by DFID.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The overall approved allocation for KPP was £ 9 million, against which a total expenditure of £ 8,814,619 was incurred till December 2017. £7.9 million were contracted out to the Management Agency (IPE Global). Of this, core fees constituted £1.95 million. £5.7 million was for subcontracting towards programme projects (inclusive of management fees and service tax). Annual proposals with detailed budgets were prepared and agreed with DFID. These were regularly reviewed to ensure allocation to priority areas. The detailed budget enabled DFID to monitor progress of activities and verify payments against agreed milestones.

Since July 2016, DFID directly engaged with partners and procurement was managed internally. DFID procurement procedures were followed to procure services of Consultants. The budget was managed with scrutiny and payments were linked to deliverables.

VfM performance compared to the original VfM proposition in the business case

KPP was a source of flexible funds used by DFID to partner with key stakeholders and decision makers to further the agenda on transfer of knowledge, policies and development effectiveness.

The KPP Business Case had undertaken a cost effectiveness assessment which made the case for the option of outsourcing the management of the programme. The analysis had suggested that this would be more cost-effective than the option of in-house management.

On implementation, the chosen option demonstrated the following benefits and costs.
Benefits: the implementing partner performed well in delivering programme outputs and outcomes.
Costs: Two costs, or drawbacks, emerged during the implementation.

1. It was found that DFID spent more time than anticipated managing the implementing partner.
2. It was found that not managing relationships with programme stakeholders directly did not advance sufficiently the development of deeper partnerships.

Following this assessment, the programme was brought under DFID management during the no-cost extension phase of one year (June 2017).This was subsequently increased to a year and a half (up to December 2017)

The one and a half year no-cost extension with a new focused and highly strategic output 6 was approved by the Head of Office in June 2016.

Programme Evaluation: The Business Case had envisaged that the programme VfM would be assessed through an external evaluation. In 2016, the Global team re-considered the case and value for such an external evaluation. It was decided that given the extensive lessons already learned internally regarding what had worked well and not so well with KPP, an external evaluation would in fact represent low VfM itself. Instead, it was decided that bringing the programme under direct DFID management and using the remaining funds during a one-year extension would likely represent much better VfM than a lengthy and transaction-cost heavy evaluation.

During the one and a half year extension to the programme, all funding arrangements were scrutinised. Due Diligence on think tanks was carried out. Consultants were procured directly through a bidding process to ensure competition. Costs were linked to programme deliverables, (management cost, fees, and skills) to drive performance.

Assessment of whether the programme represented value for money

This programme does not lend itself to a quantitative VfM assessment. However, an informed qualitative judgement of its outputs 1-5 and 6 can be presented to understand its VfM. On the benefit side: 5 of the programme outputs met expectations (2 exceeded). 1 did not meet expectation. The evidence presented in this PCR shows that outputs contributed to the good progress of the programme outcome (i.e. uptake of KPP knowledge products and their use in decision making of public service and welfare schemes in India and developing countries).

All outputs were quality assured. Risk mitigation measures were built-into the programme and assessed on a regular basis.

This programme has also created enormous value through the lessons and experiences that DFID has gained in its implementation. This was DFID’s first programme to partner with an emerging economy like India for poverty reduction in third countries. This extensive and deep learning was applied for the delivery of output 6 during the extension phase.

For outputs 1-5, the management of the programme was outsourced to a management agency. The contracting process was led by PCD. For output 6 (in the extension phase), DFID India directly managed and implemented the programme.

Under output 6, the programme delivered 6 projects. These projects were highly strategic in value deepening our partnership with the MEA/DPA and meeting our objectives of diplomatic diplomacy.
On the cost side, a cost saving of £ 600, 000 was realised during the extension phase. This money was invested in the one year extension under a tighter and more focused portfolio of projects, under direct DFID management these funds enabled us to partner with leading Indian think tanks, MEA and the EXIM Bank, and procure consultant services to catalyse Indian investment in the affordable health sector

The programme was and continues to be well recognised by various partners, including MEA, donor partners, EXIM Bank and CSOs. DFID support has been recognised as an important step in bridging the gap to establish systems, standardise operations that can be scaled and implemented including policy changes.

Quality of financial management during programme

During the design phase of the programme, a procurement guideline was developed to detail out the procurement process for contracting of services, and monitoring of resources. Due diligence was carried out on ‘Not for profit organisations’. Amendments to contracts were made after due approvals. IPE shared monthly financial reports. The contract with IPE concluded in June 2016.

Throughout the entirety of the programme all partners were systematically monitored, all disbursements were made after completion of deliverables. Timely updates were sought through quarterly partner meetings and agreeing upon a work plan which in turn resulted in high quality output-based Quarterly Progress Reports.

DFIDI team has directly managed the financial outlay of the programme since July 2016.

Financial accounting and reporting requirements were strictly adhered to. DFID ensured that reports were approved before disbursing payments to ensure cost effectiveness and adherence.

Date of last narrative financial report	July 2016, Vault No 7628454
Date of last audited annual statement	October 2015 Vault no 7675008( Conducted by External Auditors)

E: RISK (½ page)

Quality of risk management over the life of the programme

The overall risk continued to be moderate during the life of the programme. The primary risks relate to the challenge of engaging with external partners who may not be open to new thinking or willing to act on it. The financial risks were low.

Overview of programme risk

Outstanding actions from risk assessment: N.A.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme has essentially been efficient in delivering outputs against the timeframe, with very little or negligible delays in delivery. Regular quarterly meetings with the partners ensured timely delivery of outputs maintaining pillars of quality, timeliness, analysis and dissemination.

The Head of Office approved a no - cost time extension on KPP till December 2017. The projects planned for this extension focused on ‘Development Diplomacy’.

Performance of partnership(s)

KPP has been associated with a wide range of partners from, Ministry of External Affairs (Development Partnership Authority) , EXIM Bank , leading Think Tanks , UN organisations, CDC, Chambers of Commerce, Research Organisations and Academic Institutions, International and National NGOs and others. For most of the partners, KPP was an additional pool of funds with a balance of flexibility and rigour. This was catalytic and enabled partners to complement the existing activities.

The timeliness of the reporting varied across the partners as did the quality. Constant engagement with the partners, in-depth discussion helped improve the quality of the deliverables. The research organisations and think tanks not only understood the objectives but also took lead in dissemination efforts. Some of the think tanks are most likely to carry forward the work beyond KPP. Industry associations have been helpful in taking forward the project findings to a larger audience and stakeholders.

Asset disposal and value obtained by DFID

An approval from the HoO (Vault no. 7629050 & 7531241) provides details regarding the assets. Most assets (e.g. laptops) were handed over to the DFID India IT team. A few assets (five laptops) were transferred to NCAER. No new assets have been procured since June 2016.

 CONDITIONALITY (½ page)

There is no conditionality attached to this project.

Partnership principles assessment.

N/A No financial aid provided to Government of India.
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
KPP has been following a well-grounded M&E system with quarterly and half-yearly MIS formats which were regularly shared by the KPP Management Team. Quarterly Progress Reports were submitted on a regular basis.
Since July 2016, KPP was monitored through monthly meetings of the DFID Global Team. Technical leads also undertake regular meetings with their stakeholder counterparts. A number of field visits were conducted by technical leads to monitor progress on the ground. The Delivery Plan was reviewed every quarter.
DFID decided that no formal evaluation of this project would be undertaken. Feedback from partners endorses partners appreciation of the support provided by KPP and recognised the importance of such a work stream.

Key feedback includes:
- Value –addition of the UK Government’s involvement
- DFID Advisers, Management team and the Programme Management team (IPE Global), worked cohesively to deal with contract issues and technical assistance.
- KPP partners validate the significance of KPP being ‘flexible and responsive’ to emerging issues and changes. KPP engaged with multiple policy issues across varying sectors and with range of stakeholders with limited resources.
- KPP established that knowledge sharing and partnership are processes crucial to development cooperation.
- KPP promoted formation of networks, to take forward similar issues across countries, organisations and partners creating a path for sharing knowledge.
- Establishment of a distinctive place for DFID as a facilitator of India’s international cooperation engagement.

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, and lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process