ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Financial Sector Deepening Zambia (FSDZ)
Country or region targeted	Zambia
Type of cost extension (if applicable)	Accountable grant with matched funding
Original project budget	£15m
Original project start and end dates	(2013-2018)
Cost extension value (if applicable)	£8.5m[1]
New project end date (if applicable)	2021
Business Case Vault Document No.	21243240
[1] The total proposed extension over the next three years is £8.5m: this would include £7.95m of new funding plus £550,000 of remaining funds from the current phase of the programme

INFORMATION
What is the project’s purpose?
The Financial Sector Deepening Zambia (FSDZ) programme aims to expand financial inclusion in Zambia. This means increasing the number of poor Zambians who have access to one or more financial services to enable them to save, borrow, receive insurance coverage, make payments, or use mobile money. To achieve this, the programme takes a “whole system” approach and seeks to tackle constraints at different levels, from advising policymakers on financial sector reforms to partnering with local insurance firms to provide weather index-based insurance for smallholder farmers. / Lack of access to finance is a major constraint to inclusive growth in Zambia. DFID Zambia’s inclusive growth diagnostic found that limited access to financial services and the high cost of credit are constraints across several sectors, particularly for MSMEs (micro, small, and medium enterprises), 80% of whom are agri-businesses[2]. The IMF (International Monetary Fund) Financial System Stability Assessment (2017)[3] also found significant barriers facing Zambian MSMEs in accessing finance, such as high collateral requirements, poor bank lending tools, high commercial interest rates (26.5% on average in Q3 2017), and the crowding out of private credit markets by government debt. / FSDZ addresses constraints in the financial sector across five main thematic areas: informal and agricultural finance; inclusive insurance; finance for MSMEs; policy influencing; and digital finance and technology (including mobile money). It also conducts high quality research and analysis on the state of financial inclusion in Zambia in order to help stimulate market development and the creation of new products to reach the poor and financially excluded. We estimate that FSDZ has directly supported around 20% of the national increase in financial inclusion each year, as well as contributing indirectly through its policy and market infrastructure support. / In 2015, 41% of Zambians did not have access to any financial service (50% in rural areas[4]), with more women than men being excluded. Financial inclusion is improving in Zambia (increasing from 37% in 2009 to 59% in 2015), driven by greater access to both formal and informal[5] financial services. However, this is below levels of financial inclusion in other countries in the region such as Tanzania (73%), Kenya (75%), Uganda (85%), and South Africa (86%), based on latest available data[6]. Zambia has improved its global ranking on ‘access to credit’ in the World Bank’s 2018 Doing Business survey[7], although this reflects technical improvements (such as a new moveable collateral registry) rather than outcomes – the cost of credit for much of the private sector remains prohibitive. / Having access to finance increases individuals’ resilience, and reduces dependence on support from government or donors. Evidence suggests that countries with better developed financial systems tend to grow faster[8], and that having access to financial services increases income generating opportunities, raises the productivity of MSMEs, and helps poor people to manage risks and have more control over their lives.[9] Developing the financial sector will therefore support an exit from development assistance towards a path where Zambia self-finances its development. It will also promote a more conducive environment for firms to invest in Zambia’s financial sector, including UK firms. / The UK has provided almost £15m to FSDZ (2013-2018), enabling 330,000 Zambians to gain access to a new financial service. This figure is expected to reach over 380,000 by March 2018, exceeding the target of 350,000.[10] The current results include 117,000 rural Zambians who have joined a savings group, 48,600 smallholder farmers who have weather index-based insurance, and 125,000 rural Zambians using mobile money. 17,200 MSMEs have also benefited from accessing a new financial product. In addition, financial education has been provided to 178,000 Zambians via savings groups, micro-insurance pilot schemes, and events such as financial literacy week. At the Impact level, 119,000 Zambians have directly benefited from improved income opportunities or a reduction in their vulnerability due to gaining access to finance. Overall, the programme has been a success story, and is on track to exceed its outcome and impact targets by the end of the current DFID funding period (31 March 2018). / The programme is also helping to shape important policy and industry changes to make the financial sector more inclusive. Over the next few years, FSDZ will be advising the government on its policy to scale up weather index-based insurance to 1m farmers, assisting with the implementation of the new National Financial Inclusion Policy and Strategy, and continuing its technical support to the Bank of Zambia. This has been achieved by building a ‘trusted partner’ reputation with policymakers and industry bodies, and by demonstrating evidence from pilot projects and research. / FSDZ is one of ten entities in an Africa-wide network of financial inclusion programmes established by DFID[11]. This network includes the regional FSD (Financial Sector Deepening) Africa programme, which performs a coordination, secretariat and research function for the network, as well as investing in the financial sector in cross-cutting areas that are not covered by local FSD programmes. FSDA does not have a day to day presence in Zambia or the relationships with the private sector and policymakers needed for reforming and expanding financial inclusion on the ground. / FSDZ has scored highly in DFID annual reviews and partner feedback. The programme scored an A in DFID’s last Annual Review (covering 2016-17), exceeding many of its output targets and is performing reasonably well on value for money in most areas. It also scored an A in the previous two annual reviews, and independent partner feedback commissioned by DFID Zambia has been highly positive, demonstrating confidence in the partnership with DFID.
What is the objective of the cost extension or other changes?
The objectives of the proposed cost extension are to: / Expand financial inclusion in Zambia and drive policy change and innovation in the financial sector so that more Zambians have access to financial services; and / Put in place a sustainable and responsible transition of FSDZ from DFID funding by 2021, contributing funds while incentivising the programme to attract funds from other sources / Objective 1 / The cost extension will contribute to FSDZ’s strategy, directly providing over 145,000 poor Zambians with financial access by 2022[12]. Overall, implementing the strategy should directly provide access to finance for at least an additional 340,000 people, a 7% increase in the number of Zambian adults financially included (with many more indirectly benefiting from access). Interventions will include an expansion of informal savings groups, micro insurance, and MSME support, as well as a greater focus on digital finance and policy influencing. In addition, it will include an innovative new project working through traditional leadership structures (Chiefdoms) in one of Zambia’s poorest provinces to provide financial education and new financial services. / Improving financial inclusion directly supports the delivery of DFID’s new Economic Development Strategy. This identified financial services as one of the focus sectors for the economic development portfolio due to its role in unlocking growth.[13] The policy and regulatory work that FSDZ does will also help improve the environment for the private sector, including UK firms, to invest and do business in Zambia. A sign of the sector’s improving attractiveness is the recent arrival of the UK insurance firm Prudential in 2016. / FSDZ’s activities are aligned with the UK Aid Strategy. The programme will: / Promote Global Prosperity: by building the financial sector in Zambia and making it more inclusive; and by supporting economic transformation, growth and job creation; / Tackle Extreme Poverty and Help the World’s Most Vulnerable: by increasing financial inclusion to improve income opportunities for poor Zambians; and by promoting women’s economic empowerment; and / Strengthen Resilience and Response to Crisis: by expanding access to weather index-based insurance and savings products to build individual economic resilience, allowing households to withstand shocks such as poor rainfall or ill health. / Objective 2 / DFID support for a further 3 years would allow FSDZ to put in place a responsible exit strategy from DFID funding. This would be a transition period, setting the organisation up so that it can continue with the support of other funding partners after DFID funding ends. This is consistent with the actions agreed in the DFID Zambia Portfolio Quality Review, as well as the Bilateral Development Review and DFID Zambia’s Business Plan. DFID Zambia is looking to gradually reduce and end its support, in line with a move to fewer, larger programmes so that the office can focus more on policy influencing, strengthening local institutions, and assisting government to utilise its own resources more effectively. / FSD Zambia is well placed to attract funding from non-DFID sources. In 2016, DFID registered FSDZ as a Zambian not-for-profit company, to create a local entity that is able to secure funding from other sources and a first step to a transition from DFID funding. Currently, the new organisation has been operating for 1.5 years, and by the end of the proposed new funding period it will have been running for five years. We expect this to be sufficient time for the organisation to have fully established itself as a credible, Zambian entity and to have sourced and secured new funding to enable it to continue. / The programme is already attracting support from other funding partners. The UK is the largest funding partner, providing approximately £4m per year, with the Swedish International Development Cooperation Agency (SIDA) adding approximately £800,000 per year. A minimum of £355,000 over the next three years has just been signed with the International Fund for Agricultural Development (IFAD). FSDZ’s management and Board have taken a proactive approach towards attracting new sources of income, and there are encouraging signs of interest from other funders (discussions have recently taken place with the Bill and Melinda Gates Foundation and the MasterCard Foundation). This gives us confidence that the organisation can continue without DFID’s support after three years, from 2021. We will also explore with FSDZ the possibility of bringing in private funds through consulting services, following the example of the EFinA (Enhancing Financial Innovation and Access) programme in Nigeria.
What is the additional and total support the UK will provide?
We recommend that the UK continues to support FSD Zambia by providing a total of £8.5m over 3 years, including matched funding of up to £2.5m. The additional support would be £7.95m, utilising £550,000 of unspent funds from the current phase that would be carried over. This would bring the total investment in FSDZ (from 2013-2021) to £23.5m. / DFID funding would be tapered, declining from years 1 to 3, and would use matched funding to incentivise FSDZ to attract funding from other sources. In year 1, for example, £0.5m of DFID funds would be conditional on FSDZ bringing in new funding from other donors of an equivalent amount. So if only £0.25m of new funds were sourced, DFID would only provide £0.25m from the matched funding component. We propose to raise the matched funding component to £1m in years 2 and 3. Overall, matched funding would account for £2.5m out of the proposed total of £8.5m (29%). / Three options have been considered: / End support for financial inclusion in Zambia after March 2018 (i.e. do nothing) / Continue funding for 5 further years at current levels (i.e. £4m per year) / Continue funding for 3 years with tapered and matched funding (preferred option) / Table 1: Comparison of Options: / Option 1: End support for financial inclusion in Zambia after March 2018 / Description: The current phase of DFID funding (2013-2018) is due to end on 31 March 2018. FSDZ would still have funding from SIDA and IFAD but would have very limited time to find additional sources. / Strengths: This would mean a rapid exit, allowing DFID Zambia to reallocate its resources (staff and funding) into other areas. DFID would still have funded an impressive programme for five years and will have set up a credible local organisation. / Weaknesses: Cutting funding at this early stage would be premature and would create a very high risk that the organisation ceases to operate as there would not be sufficient time to bring other partners on board. While there are encouraging signs of new funding being mobilised from major donors, the majority of new funds are only likely to come on stream during or after the next financial year. This option would therefore affect FSDZ’s ability to deliver systemic change and achieve its results and policy influencing objectives at a critical time just as it established itself as a credible facilitator. It could also affect DFID Zambia’s reputation as a trusted and reliable partner. / Funding: No further funding beyond March 2018 / Option 2: Continue funding FSDZ at a similar level for a further 5 years / Description: This would represent a continuation of current levels of spend (£4m per year) on the organisation for the duration of the new strategy and beyond / Strengths: DFID would be able to claim ownership of a larger share of results achieved as it would likely be the majority funding partner for this period. This option provides greater financial security for the programme. / Weaknesses: The incentive for the organisation to attract new sources of funding would be weakened if DFID continues to fund FSDZ’s activities at this level for a five year period. Five further years of funding mean that an exit strategy is some way off, and would be less credible. DFID resources would be committed to the project, reducing flexibility to support other programmes in Zambia as recommended in the DFID Zambia Business Plan. / Funding: £20m over 5 years (£4m per year) / Option 3 (preferred): Continue for a further 3 years, with tapered and matched funding / Description: DFID funding would continue for three further years, but would decline each year and involve a component of capped matched funding (where DFID agrees to further funds up to a given level, subject to an equal amount being provided from new partners) / Strengths: This combines with a clearly defined exit strategy. This would allow DFID to exit responsibly and oversee a managed transition to new funders who can support the organisation. / Weaknesses: There is some risk that the funds are not sufficient to achieve significant results in the absence of other funders; or, alternatively, do not provide sufficient incentives to diversify funding. However, we see this as a reasonable balance between the two objectives. / Funding: £8.5m over 3 years, including £2.5m matched funding: / Year 1, 2018-19: £3.5m (£3.0m + £0.5m matched) / Year 2, 2019-20: £3.0m (£2.0m + £1m matched) / Year 3, 2020-21: £2.0m (£1.0m + £1m matched) / Option 3, to fund FSDZ for three further years with matched and tapered funding, is the preferred Option. Our view is that this option would offer the right mix between funding results and putting in place a responsible transition away from DFID support. Further options could involve elements of the above three options. However, we feel that funding for a longer period of time than three years would indicate a lack of confidence in FSDZ’s management to attract other funders; similarly, providing higher levels of funding would weaken the incentive to diversify sources of funding beyond DFID. / If DFID were to exit after the end of the current phase in March 2018, there would be a very high risk that FSDZ would cease to continue. This would slow the pace of financial inclusion in Zambia. Similarly, funding for less than three years would make it significantly more difficult for FSDZ to leverage other funding partners: discussions with potential partners have indicated that DFID’s support is critical in crowding in others. There would also be a potential reputational risk to DFID if funding was to cease at this point, and it would raise questions about FSDZ among other likely donors. The unanticipated exit of DFID funding from FSD Kenya has been difficult for the organisation to manage, even though it is also funded by others. By contrast, the EFinA (Enhancing Financial Innovation and Access) programme in Nigeria has recently put in place a sustainable exit strategy, involving a final extension (no-cost) over two years. / The proposed amount (£8.5m in total over three years) should be sufficient to achieve results and leverage new funding. This level of support, together with funds from SIDA, IFAD, and others, would allow FSDZ to meet the ‘base’ scenario set out in FSDZ’s strategy, and would mean the programme continues to operate at a similar scale. Although FSDZ has ambitions over time to increase the scale of some elements of its work (such as savings groups, the traditional leadership project, and research), we feel that it may struggle to efficiently absorb and utilise additional funds to the amounts proposed, thereby affecting value for money. Likewise, we believe that if new funds were much below the proposed amounts, the organisation would compromise on its results and objectives, which would in turn weaken the leadership’s ability to bring in new funding and deliver value for money. / An indicative breakdown of the allocation of DFID support over the next three years is provided below. Although we expect funds to be broadly allocated in these amounts, an element of flexibility is required since the programme will need to be responsive to demands from the market, policymakers and regulators: / Table 2: Summary of proposed budget / Budget Summary (£) / 2018-2019 2019-2020 2020-2021 Total % of total / Informal Finance 500,000 300,000 100,000 900,000 14% / MSME support 200,000 100,000 100,000 400,000 7% / Inclusive insurance 450,000 300,000 100,000 850,000 14% / Traditional leadership 200,000 200,000 100,000 500,000 8% / Digital finance 400,000 250,000 100,000 750,000 13% / Policy support 250,000 200,000 100,000 550,000 9% / Research 250,000 150,000 100,000 500,000 8% / M&E and comms 250,000 200,000 100,000 550,000 9% / Operations & Governance 500,000 300,000 200,000 1,000,000 16% / Total (no matching) 3,000,000 2,000,000 1,000,000 6,000,000 / Matched funds 500,000 1,000,000 1,000,000 2,500,000 29% / Total 3,500,000 3,000,000 2,000,000 8,500,000 / DFID’s proportionate contribution is expected to decline over the next three years as more funders come on board. The table below sets out the current and expected funds provided to FSDZ: / Table 3: DFID and others’ contributions to FSDZ, 2017-2021 / Partner support (£) Current year Year 1 (new funds) Year 2 Year 3 / (2017-18) (2018-2019) (2019-2020) (2020-2021) / DFID (with matched funding) 4,000,000 3,500,000 3,000,000 2,000,000 / SIDA 800,000 800,000 800,000 800,000 / IFAD 0 200,000 200,000 200,000 / Others (projected) 0 500,000 1,000,000 2,000,000 / Total 4,800,000 5,000,000 5,000,000 5,000,000 / DFID % 83% 70% 60% 40% / Proposed DFID share of FSDZ funding, 2018-21:57% / New DFID funding to FSDZ would be aligned to support the main components in FSDZ’s Five Year Strategy[14] which sets out the challenges facing financial inclusion in Zambia and how these will be addressed through a mixture of project, research and policy influencing interventions. The main activities that new DFID support would contribute to are: / Informal Finance: (approx. £900,000 over three years) / Proposed activities: this would include an expansion of the number of savings groups; and piloting formal links between savings groups, insurance and mobile money. / Progress to date: the current programme has reached 118,400 beneficiaries through the creation of 5,341 savings groups at a cost of £8.05 per beneficiary. Assessments have found savings groups supported by FSDZ to be effective at targeting the poor (90% of members below US$2.5/ day using the Progress out of Poverty Index[15]) and in providing income opportunities and reduced vulnerability. / Inclusive Insurance (approx. £850,000 over three years) / Proposed activities: increasing the uptake of micro insurance products among low-income households and individuals, increasing the range of products available (such as health and transport/ accident insurance); and supporting government expansion of coverage to farmers receiving agricultural subsidies. / Progress to date: 48,500 smallholder farmers are now covered by weather index-based insurance; insurance companies have developed new, commercially viable, products; and government interest in the concept led to a new policy to provide weather index-based insurance to recipients of the main agricultural subsidy scheme. / MSMEs (approx. £400,000 over three years) / Proposed activities: providing financial education for MSMEs; working with regulators to encourage lending to MSMEs; and market studies on MSME access to finance. DFID funding would no longer support capacity building for banks, but would instead work directly with MSMEs and regulators. / Progress to date: 17,200 MSMEs now have access to a new financial service; there have been measured improvements in the capacity of financial service providers, MSMEs, and regulators. / Traditional leadership project (£500,000 over three years) / Proposed activities: working with traditional leaders to expand financial education across Luapula province; creating privately-driven savings groups; and increasing the use of micro insurance and digital financial services. / Progress to date: FSDZ has not worked directly with traditional leadership previously, but the proposed interventions have been successful when FSDZ has worked directly with villagers and farmers. / Digital financial services and infrastructure (approx. £750,000 over three years) / Proposed activities: supporting new digital finance applications (including social cash transfers, paying school fees, and digital savings accounts); advising regulators to improving the digital finance legal and regulatory environment; and providing financial literacy and consumer protection systems for users of digital finance. / Progress to date: 125,000 Zambians have access to a new digital financial service, such as mobile money. / Policy support (approx. £550,000 over three years) / Proposed activities: influencing government on policy areas which promote the use of technology for financial inclusion (universal biometric identity cards, mobile phone ownership, and cell tower area coverage); providing technical support to the government on its plans to expand weather index-based insurance; and advising on the new insurance bill. / Progress to date: a MoU has been signed with the central bank; FSDZ advised the Ministry of Finance on the new National Financial Inclusion Strategy; there have been measured improvements in regulator capacity. / Research (approx. £500,000 over three years) / Proposed activities: FSDZ will contribute to a Finscope study which will assess levels of financial inclusion in Zambia and market developments (to be co-funded by the Bank of Zambia); and will carry out a longitudinal study of savings group operations and a new study on MSMEs. / Progress to date: the Finscope 2015 study was conducted and has been widely used; geospatial mapping and ‘Making Access Possible’ studies have informed FSDZ’s interventions and have been used by policymakers and mobile money companies. / M&E and communications (approx. £550,000 over three years) / Proposed activities: informing the market of new findings and research; running financial inclusion week; and collecting robust evidence on the impacts of FSDZ’s activities and reporting findings to DFID. FSDZ has signed a visibility statement and will continue to use appropriate UK branding as part of its activities. / Progress to date: FSDZ runs professional events and presentations on financial inclusion; improved awareness and reach; robust M&E in place. / Operations and governance (approx. £1,000,000 over three years) / Proposed activities: the Board and Investment Committee will meet three times per year; rental costs for FSDZ’s office, IT and vehicle costs will be funded, as well as back office and administrative staff salaries. / Progress to date: an experienced Board of Directors and Investment Committee are in place; a new third party fiduciary service provider (Deloitte) handles FSDZ’s finances. / Matched funding (up to £2,500,000 over three years) / Proposed activities: this would not be earmarked, but would be expected to primarily support FSDZ’s Traditional Leadership project working with Chiefs in Luapula province, as well as funding additional reach on savings groups and insurance. The matched funding would offer flexibility for FSDZ to do more in priority areas and to respond to requests from government and regulators. / Progress to date: the use of matched funding is new to the programme, but is expected to incentivise new funding
What are the expected results?
The expected results due to further DFID funding from 2018-2021 at the outcome level are listed below. These are based on DFID attributing a share of 43% of the total expected results, equal to DFID’s estimated share of total costs. We believe that these results are sufficiently ambitious, based on trend analysis and previous performance. FSDZ also sees these as conservative estimates which would be exceeded if further progress is made on expanding weather index-based insurance, using digital finance for school fees, and on the project in Luapula province with local Chiefs. / 80,000 poor people accessing a new financial service (of which at least 65% will be women) – to include over 60,000 additional members of savings groups / 65,000 smallholder farmers with access to weather index-based insurance (of which at least 50% will be women) [16] / 8,000 additional MSMEs with access to finance / 120,000 Zambians receive effective financial education / At the impact level, a further 90,000 people are estimated to experience an expansion in income opportunities or reduced vulnerability due to DFID funding. This indicator recognises that financial access is often a necessary but not sufficient condition for improved livelihoods. It is measured using surveys of beneficiaries from FSDZ activities (e.g. savings group members) and the use of the Progress out of Poverty Index to assess changes in incomes. / Wider economic benefits of FSDZ’s interventions are expected to include: / Decrease in post-harvest losses due to weather index-based insurance / Increase in MSME turnover and value added due to greater access to finance / Reduced risk of loss of savings due to greater formalisation; / Lower transaction costs of transferring money through new mobile money mechanisms and expansion of bank and non-bank outlets / Reduced costs to government and donors from dealing with the costs of poverty directly / The original business case’s appraisal found that FSDZ would increase the level of financial inclusion above the baseline trend, and we estimate that this would continue. Directly, FSDZ activities should account for a 7% increase above trend, and indirectly significantly more. FSDZ is conducting ongoing studies to better understand the wider economic impacts of its activities, including analysis of the economic returns from financial inclusion (due to report in early 2018).
What is the approach to implementation?
Overall approach / The programme would continue to use the successful ‘market systems’ approach to address constraints to financial inclusion. This approach, also known as Making Markets Work for the Poor (M4P), is also used by other FSD programmes, and involves interventions targeted at different levels of the market, from setting up informal rural savings groups; to providing weather index-based agricultural insurance; to advising senior policymakers (for example on Zambia’s new National Financial Inclusion Strategy). / This approach recognises that economic poverty is the result of the structure of market systems in which poor people participate.[17] When markets work efficiently and produce equitable outcomes for the poor, they can deliver balanced growth and reduce poverty. Using the M4P approach, FSDZ will continue to work to identify the underlying causes (market failures) which mean that financial markets do not work for the poor; and then facilitate change to address the identified constraints. / Governance and DFID controls / The funding modality would be a new Accountable Grant to FSD Zambia, overseen by the Board of Directors and its members (including DFID). FSD Zambia is a company limited by guarantee (a not-for-profit entity) accountable to a Board of Directors, who provide scrutiny and strategic oversight. These are appointed by the members of the company and bring significant private sector and senior leadership experience. Current Directors include a former Governor of the Bank of Zambia, a High Court Judge, and a prominent Zambian businesswoman. As a member of the company (with the power to appoint or dismiss Board members), DFID’s SRO attends the Board as an observer, and has a veto over key financial decisions such as executive pay. / Technical oversight and monitoring / Technical and financial oversight is provided by FSDZ’s Programme Investment Committee (PIC) who add value through their detailed knowledge of financial markets. Current PIC members include a financial sector development specialist; a Director of Genesis Analytics, a South African consultancy; and a Zambian businessman. DFID chairs the Investment Committee, ensuring it has a voice at the technical level as well as the strategic level of the organisation. / The programme is monitored through regular reporting and field visits. FSDZ provides detailed quarterly reports (technical and financial) to DFID, as well as an Annual Report. There are regular discussions between DFID and FSDZ management and M&E staff, and DFID carries out its own Annual Reviews and makes quarterly field visits to see project sites and hear feedback from beneficiaries and partners. / Financial and commercial management / FSDZ has a third party financial management contract to bring fiduciary assurance. The involvement of an internationally recognised accounting company (Deloitte) provides credibility and reassures new funders. An external audit is carried out annually, with findings presented to the Board and members. The most recent (July 2017) was conducted by KPMG and was unqualified. FSDZ’s CEO and management will implement future funding in accordance with the new Supplier Code of Conduct (Compliance Level 1), and will attend a briefing at DFID Zambia in November to ensure the six responsibilities are well understood. DFID Zambia also conducts spot check audits every 1-2 years. / Management and leadership / FSDZ’s CEO provides leadership and direct accountability to the Board and members (DFID), supported by a senior management team. The current CEO has significant public and private financial sector experience (including most recently as a Senior Director at the Asian Development Bank), has good contacts with senior policy makers and is highly regarded. The CEO and Board are supportive of making the organisation more Zambian, and there is a good commitment to staff development. The CEO has signed a visibility statement on branding, and FSDZ uses the UK Aid logo and references DFID funding where appropriate. / Risk management / The programme risk is assessed as minor. Key risks are monitored and regularly updated in the DFID SRO delivery plan, alongside mitigating actions. The five main risks at present are set out in the table and include: / High administrative costs (related to FSDZ’s transition to a not-for-profit company)[18] / Misuse of funds (fraud, corruption and reputational damage) / Deterioration in the Zambian policy/regulatory environment / Significant deterioration in the global or Zambian economy / Financial sustainability (donor funding) / FSDZ attended a session run by DFID Zambia on what constitutes a risk to DFID, including reputational risk, with examples provided of activities which are not acceptable. FSDZ has previously funded work with commercial banks, however it is reducing its work in this area and DFID funds would no longer support this activity over the proposed extension period. We do not judge that any planned activities constitute a reputational risk to DFID. If in doubt, the CEO approaches the DFID SRO in the first instance. DFID reviews and approves FSDZ’s annual workplan and ensures that the proposed activities are within our risk threshold. / Table 4: current risk matrix / Impact / Insignificant Minor Moderate Major Severe / Likelihood Almost Certain / Likely / Possible 1.Transition and operating risks / 4.Macroeconomy: significant deterioration in the global or Zambian economy 5. Financial sustainability: new funding sources are not sufficient / Unlikely 2.Misuse of funds (fraud and corruption / 3. Policy environment and partner support / Rare / Value for Money / The move to become a Special Purpose Vehicle (a Zambian not-for-profit company) was informed by an independent FSD Africa value for money assessment and a detailed, independent study for FSDZ which compared the risk profiles and cost implications of various FSD structures. These found that setting up FSDZ as a not-for-profit company would offer better value for money and would carry lower risks than alternatives, such as the contractor-led model used at the time.[19] Given the strong evidence base provided by these studies in favour of the Special Purpose Vehicle model, we have not re-assessed alternative modalities of delivery for this extension. The new structure also allows for additional funders to come on board, so value for money will also be achieved by using DFID funds to leverage funding pledges from new partners. / This year’s DFID Annual Review found that FSDZ is generally good value for money, though there is room for improvement. It performed well against its impact, outcome and output milestones, achieved an ‘A’ score overall, and is assessed as minor risk. However, the review also found scope for further efficiency and economy savings. For example, the level of administrative costs (operations and governance) should move back to the target level now that transition-related costs to the not-for-profit company (new IT systems for example) have been incurred. Consultations with other DFID-supported FSD programmes have found that FSDZ’s approach on executive remuneration, consultant costs, and oversight was generally consistent. However we want to improve this further. A number of steps to drive value for money in both administrative and programme (delivery) components, have been agreed, and where possible these will be specified in a new Accountable Grant. These include: / Administrative: / Reducing overhead costs to 16% of total expenditure by the second year of new funding – FSDZ will set out plans to do this, including reducing governance costs. / A benchmarking exercise is being conducted by Grant Thornton, an independent advisory firm, on comparable local salaries to ensure pay is in line with market rates DFID will look at freezes or reductions where pay is in excess of market values. / FSDZ will revise its HR manual to more clearly define its approach to salary bands and annual rises (in the first year under the new structure, there were some inconsistencies) to be agreed by Board and DFID. / Programme: / Using lessons from the first phase to set up and support savings groups more efficiently, such as through increased use of local private sector agents. / Supporting large scale government programmes (such as the main farmer subsidy scheme) and the use of digital finance (e.g. for school fees and cash transfers) to increase the overall effectiveness of the programme. / On equity, carry out an analysis of FSDZ’s geographical reach, and adjust as necessary to ensure poorer provinces with higher levels of financial exclusion are targeted. / Table 5: Value for Money indicators / Value for Money category Current target Performance June 2017 Annual Review Target for new funding phase / Economy / Administrative costs 18% of total 23% 18% (Year 1) 16% (Years 2 and 3) / Consultancy day rates and salaries Rates capped at £950/ day Rate cap followed £800/ day cap[20] / Efficiency / Average cost per savings group beneficiary £14/ person (based on average of other FSD programmes) £8/ person < £8 person / Project leverage ratio (% of costs for individual projects that are co-funded by FSDZ’s partners) 50% co-funding by NGOs, government, and private sector 34% on average (8 projects) 50% on average / Programme leverage ratio (% of FSDZ total costs funded by non-DFID sources) N/A (this will be a new target) 18% (SIDA) 40% funding by other partners / Effectiveness / Number of people using a new financial service 350,000 by March 2018 327,700 (on track) 145,000 (2018-21) / Cost per person financially included (direct beneficiaries) N/A (this will be a new target) £38 £35 / Financial inclusion % in Zambia 70% (2022) 2015: 59% 70% (2022) / Equity / % of beneficiaries that are female Impact: 65% / Outcome 1: 65% / Outcome 2: 50% Impact: 80% / Outcome 1: 51% / Outcome 2: 25% Impact: 65% / Outcome 1: 65% / Outcome 2: 50% / % of beneficiaries that are below $2.5/day as measured by Progress out of Poverty Index (PPI) 90% 91% 90% / Links with other DFID programmes and HMG Departments / The next phase of funding will require FSDZ to work more closely with other DFID Zambia programmes, given the cross-cutting nature of financial inclusion. This will mean developing links with areas such as education support (facilitating school fees payments) and adolescence (financial education, insurance and savings groups). It also will build on and learn from our existing relationships with traditional leaders for the new project working with Chiefs in Luapula province. There may be opportunities to use UK expertise to support FSDZ, for example by providing capacity building on financial regulation – these will be explored if requests are made to FSDZ (this support to the government is demand led). / Gender Equality and Disability / The programme will continue to give strong regard to reducing gender inequality, and further enhance its work on disability, in accordance with the 2014 Gender Equality Act. This will be done by continuing the programme’s ambitious gender targets. At the impact level, at least 65% of those benefiting from increased income opportunities should be women (the programme is currently over-achieving at 80%). At the outcome level, at least 65% of those benefiting from new formal and informal access to finance and at least 50% of smallholder farmers benefiting should be women. Currently, the programme is on track to meet these in terms of absolute numbers (as it is likely to over-achieve on the overall targets), but not in percentage terms: women comprise 51% and 25% of beneficiaries respectively. / The programme will increase its efforts to meet these targets and ensure more women benefit from access to finance. This will include more focus on women smallholder farmers and women-led MSMEs, and ensuring that lessons from the Sweden funded FSDZ component targeting women’s financial inclusion are applied across all programme activities. FSDZ will also fund new savings groups (of which membership has tended to be mainly women). FSDZ’s new Gender, Diversity and Disability Action Plan will improve the FSDZ team’s awareness of disability issues both within the organisation and across its activities. FSDZ is reaching beneficiaries with disabilities (for example a savings group in the Copperbelt province has members who are all blind), and the programme will now monitor numbers of disabled beneficiaries, and identify positive stories to tell, in order to better understand and communicate its impact.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The theory of change and its underlying assumptions still hold, though there have been a number of lessons learned on the process of achieving financial inclusion. Some key learnings are as follows: / Market change and policy influencing take time: the ‘J-curve’ effect: this refers to the trajectory of slow initial progress followed by acceleration in results. This effect has been observed with a number of FSDZ’s interventions, notably with the expansion of informal savings groups, which required a hands-on approach at first but are now being initiated by communities themselves in many areas of Zambia. Policy influencing is another example, which has required continued patience and perseverance: it took four years to achieve a detailed MoU with the Bank of Zambia on financial inclusion (signed this year). / Policymakers’ support and political will is critical: FSDZ has made a considerable investment in relationships, and has built up contacts in policy and industry. FSDZ’s CEO has extensive connections, having worked in Zambia previously, and these have been used to good effect, for example in supporting the Ministry of Finance in its new National Financial Inclusion Strategy. Financial inclusion has emerged as a policy priority in for the government in the last 18 months, in part due to FSDZ’s work to build the evidence base (through research such as Finscope, geospatial mapping and Financial Diaries) and its influencing work with policymakers. / Piloting and demonstrations can be used to scale up progress: FSDZ has piloted innovative approaches to financial inclusion, such as the use of weather index-based insurance. In this case it used the evidence and results to demonstrate viability to insurance companies and policy makers.[21] The government has now committed to rolling out weather index-based insurance to the 1m recipients of its agricultural subsidy scheme. / FSDZ’s new structure and local ownership have been beneficial: as set out earlier, since May 2016 FSD Zambia has been operating as a local non-profit company limited by guarantee, with an independent Board of Directors. This has made the organisation more Zambian than the previous contractor-led model, and has enabled other funders to support FSDZ. Learnings from the transition period include the need to have more clarity over the role and scope of Board, members, and management; and the need to limit transition-related costs where possible. / References / Cenfri/ FSD Africa (2015) Analysis of options for programme completion for DFID Zambia / CGAP (2015) A Market Systems Approach to Financial Inclusion: Guidelines for Funders / DFID Zambia (2016) Inclusive Growth Diagnostic / DFID Zambia (2016) Business Plan / DFID (2017) Economic Development Strategy: Prosperity, Poverty, and Meeting Global Challenges / Finscope survey (2015) / FSD Zambia (2017) 5 Year Strategy, 2017-2022 / FSD Africa/ Bester (2014) Risks, costs and incentives across FSD programmes / JPAL / IPA/ Karlan (2016) Impact of Savings Groups on the Lives of The Poor / Ledgerwood/ FSD Africa (2017) The Art of Market Facilitation: Learning from the Financial Deepening Network / Nathan Associates (2016) Political Economy Analysis of Financial Sector in Zambia / Springfield Centre Gibson/ (2016) FSD Kenya: 10 Years of a Market Systems Approach in the Kenyan Finance Market / World Bank (2017) Doing Business 2018
[2] DFID Zambia (2015) Inclusive Growth Diagnostic
[3] IMF (2017) Zambia Financial System Stability Assessment
[4] Finscope (2015)
[5] Informal financial services include savings, borrowing, money transfers, and risk management that are outside a country’s formal financial sector and regulations. A good example is the informal savings groups that FSDZ supports
[6] Finscope (2015)
[7] World Bank (2018) Doing Business
[8] Commission on Growth and Development (2008) Working Paper No. 11: Finance, Financial Sector Policies and Long-Run Growth
[9] See, for example, JPAL/ IPA (2016) Impact of Savings Groups on the Lives of The Poor; Springfield Centre/ Gibson (2016) FSD Kenya: Ten Years of a Market Systems Approach in the Kenyan Finance Market
[10] FSDZ (2017) 2nd Quarterly report
[11] FSD programmes operate in: Tanzania, Kenya, Mozambique, Nigeria, Uganda, Rwanda, South Africa, DRC, Ethiopia, and Zambia
[12] DFID’s share of the estimated total outcome results, based on its expected funding contribution, would be 43%: DFID funds would provide access to finance for 145,000 beneficiaries out of a total of 340,000 from 2018 until 2022. This is based on FSDZ’s conservative estimate of results and funding – the higher scenario assumes more funding from non-DFID sources and therefore more beneficiaries (495,000) over the period
[13] DFID (2017) Economic Development Strategy: prosperity, poverty and meeting global challenges
[14] FSDZ (2017) Five Year Strategy 2017-2022
[15] The Progress out of Poverty Index is a measure of household poverty. It uses a survey of 10 questions on household characteristics and asset ownership to estimate the likelihood that a household is living below the poverty line
[16] N.B. the number of beneficiaries could be much higher if the government’s plans to scale up weather index-based insurance to 1m recipients of the main agricultural subsidy scheme, supported by FSDZ, are realized. FSDZ is also supporting a government drive to increase the use of digital finance for school payments which could benefit a further 500,000.
[17] See, for example: FSD Africa/ Ledgerwood (2017) The Art of Market Facilitation: Learning from the Financial Sector Deepening Network
[18] These costs arose following the transition from a supplier-led contract to a local company limited by guarantee, and have included purchasing new IT systems for example
[19] Cenfri/ FSD Africa (2015) Analysis of options for programme completion for DFID Zambia and FSD Africa/ Bester (2014) Risks, costs and incentives across FSD programmes
[20] This is following new DFID FCPD guidance. In line with FCPD advice, any exceptions to this will need to be approved by the SRO on a case by case basis, and would need to show strong justification on value for money
[21] FSDA/ Ledgerwood (2017)