## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 114334
ARIES Project Description | Migrating out of Poverty
A1: Goal, Purpose, Risk
Goal
Goal statement | Poverty reduction and development impacts of migration maximized; costs and risks of migration for the poor minimized: Development of pro-poor migration policies by target governments; Migrant access to government services and welfare programmes improved; Barriers to internal mobility reduced.
Indicator 1 | Discussions on policy reform initiated in at least two countries by EOP
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Despite not having commissioned research yet (as it is still the inception phase), the RPC has got off to strong start in engaging in policy reform discussions. The governments of Uganda and Rwanda expressed interest in harnessing the development potential of diasporas from their countries and invited the RPC to work with them. AMADPOC (The African Migration and Development Policy Centre) is already involved in Uganda’s process of formulating a National Migration Policy in which diaspora issues will feature prominently. See Output 4 for more information.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Migration mainstreamed in at least two donor strategy documents by 2016
Milestone for this review (if any)
What progress has been made in the period covered by this review? | None - too early to assess. This target is for 2016.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | After a year into the inception phase, the RPC has paved the way for undertaking research where knowledge is most needed and relevant to development outcomes from migration. It will focus largely on internal and regional migration, where the evidence base is weakest. It has developed a research agenda which responds to key Ministerial priorities and poverty reduction outcomes. In particular it is concerned to establish whether and how migration enables people to move out of poverty (including through moving into uban areas). It is also particularly concerned with the way in which migration affects women and girls (both those who remain behind and those who migrate within their own countries and regionally).
Goal Recommendation 1
Goal Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | New understandings of the migration-development nexus based on fresh analysis of existing data and targeted new studies mainstreamed in policy and programming, research and donor assistance in select countries in Sub-Saharan Africa and Asia
Indicator 1 | Understanding of the relationship between migration, poverty and development clearly articulated in documents of at least two ministries in at least 2 countries
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Too early to assess - Ghana's national migration policy is likely to be the first ministerial document to reflect a stronger evidence based response to migration and poverty outcomes. The RPC has been coordinating with the government team working on this.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | At least 5 regional and global research and/or policy institutes utilize concepts andfindingsfrom the RPC by EOP
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Too early to assess - Given the early entry points it is already using to engaging with policy makers and other boundary partners on areas of need and interest to them, it is anticipated that the RPC will reach this target by EOP.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Assumptions will be developed in a final log frame and theory of change as key inception phase outputs
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree?
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | The RPC will use Outcome Mapping and Theory of Change approaches to explain how and why the work will contribute to achieving a desired change. As long as these are properly developed and monitored, there should be evidence of the achievement of purpose that can be attributed to the programme.
Purpose Recommendation 1 | Demonstrate Consortium-wide understanding of boundary partners, needs and interests by end of the inception phase.
Purpose Action Point 1 | A clear theory of change and outcome mapping with progress markers by August 201. Develop a strategy to work with Boundary Partners and identify anticipated outcomes at different levels and at different points in time
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 3 | 2.25
Purpose Justification | The beginning of the RPC has its strengths (e.g. a solid research strategy) but it needs to carefully monitor and address the delivery of outputs by consortium theme leaders. It will be critical that the CEO and Research Director can build strong systems that manage the performance of partners and ensure effective quality control of research outputs. The draft outputs received suggest that this is an area that requires significant attention; and the Management Team have promised to move quickly to strengthen
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | A draft logframe was prepared for the programme submission and approval. Final log frame is an output of the inception phase ending Sept 2011.
Logframe Recommendation 1 | Develop a harmonised M&E framework guided by an overarching log frame.
Logframe Action Point 1 | Ensure that Log frame is well aligned with Theory of Change and Outcome Mapping
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | A robust and up-to-date database on migration that can be sustained in the future and is open and compatible with other databases
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium |  | 2
0.5
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  |  | 1
Original or Revised DFID Share |  |  | 2
3
Indicator 1 | New data on internal, south-south and other kinds of international migration (indicator being refined during year 1) |  | 4
Is this a Standard Indicator? | No |  | 5
Milestone for this review (if any) |  |  | 0
What progress has been made in the period covered by this review? | In the first year of the programme, preliminary evidence based on internal migration data for Ghana and India has been produced so far. This is new data generated by the programme which focuses on inter-state migrants and state-to-state migrants under 1 year and 5 years in India. Data on sending and receiving regions in Ghana showing different patterns of migration across Ghana is also analysed. Tentative explanations are presented and discussed in a presentation on Internal Migration to DFID, UK partners and country offices. Internal Migration data for 6 or more countries will eventually be compiled by the RPC. Coordination with national and international partners initiated in the first year to promote more coherent development of migration data, and identification of areas where there is data and research scarcity.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Data disaggregated by gender
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Data generated so far is work in progress, and there are plans to construct more refined migration measures by specifying other characteristics of the movement or of the migrant him/herself, for example: gender, age, level of skills; reasons for migration (conflict, economic, education, family); legal/illegal status.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 1 | 2 |  | 0.75
Impact Weighted Score | 18.75 |  | 0.1875
Justification for the Score | The programme is still in its inception phase, and internal migration data already being generated and disseminated. Arrangements are already being put in place to coordinate support for improved migration data through the GMOD (Global Migrant Origin Database) and MiNS (Migration in National Surveys) which provide a global view of patterns of migration between countries and regions. Data on internal migration is still sparse, and the programme has made this area of migration data the main focus. There is a clear work plan in place for data related tasks to improve the analysis of secondary datasets to tease out findings related to migration impacts, remittances and gender.
Output 1 Recommendation 1 | Policy questions emerging from the preliminary evidence need to be strengthened.
Output 1 Action Point 1 | Develop and discuss a range of relevant policy and research questions with other consortium theme leaders and key boundary partners.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | DFID should push for the RPC to involve international partners especially DESA Population Division as well as others on the next phase of data updates. This will ensure sustainability and more immediately avoid duplications with work underway in DESA.
Output 1 Recommendation 3
Output 1 Action Point 2 | Coordinate a data roundtable with UN and other key partners in the first quarter of year 2, to encourage shared responsibility in the expansion and updating of data.
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | A coherent body of high quality, policy relevant new knowledge that makes a significant contribution to the understanding of migration impacts on poverty reduction, drivers of migration, the role of policies in shaping migration flows, and of how partners can maximise the benefits of migration for development, and minimise the costs and risks
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium |  | 2
0.5
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Model on migration driver sensitivity to global change
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review? | No progress made in year 1
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Data and analysis on migration drivers; Factors mediating impacts identified; Economic contribution of migrants measured
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review? | The RPC will produce peer reviewed evidence products on drivers and impacts of migration by the end of the inception phase (Sept 2011). So far, draft evidence papers on impacts and drivers are now being reviewed for improved final products. A number of problems have been identified with the drafts, and a non-cost extension has been granted to enable the team to address these. Statistical measurements of impact will be conducted.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Migration gaps in PRSPs (Poverty Reduction Strategy Papers) and NAPAs (National Adaptation Programme of Action) identified; Best practice in policy reform; Map/chart of policy barriers and stakeholders by location
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review? | During the first year, areas of national migration policy frameworks and policies affecting migration's poverty outcomes were examined with policy makers and practitioners in different regions in Africa and Asia. This has informed the prioritisation of research activities looking at PRSPs, housing, education, access to basic services, and other areas. The mapping and analysing of key actors in the shaping of national migration policies has commenced. The team has developed "policy matrices" for each of the RPC regions. These seek to map out policies affecting migration (e.g. policies of containment, labour market policies, redistributive and developmental policies). These are important tools for research.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 2 | 3 |  | 0.5
Impact Weighted Score | 12.5 |  | 0.125
Justification for the Score | It is too early to assess the quality of the data and analysis of the 3 core themes (policy, drivers, impact) after the first of the 6 year duration. To date, a research framework describing the work that will be carried out by the consortium over the next five years is almost completed as an inception phase output. Some progress markers for justifying the particular research strategy to follow have slipped and there is need for greater discipline by consortium partners in meeting deadlines and producing quality outputs.
Output 2 Recommendation 1 | Finalised research strategy should present a strong case for undertaking particular research activities based on rigorous review of the evidence.
Output 2 Action Point 1 | Coordinate an evidence paper virtual discussion involving the core partners, to communicate the results of the final peer review process and help ensure improved quality.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Strategic capacity of developing country partners strengthened resulting in a 'critical mass' of research expertise in southern research institutions.
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High |  | 1
0.25
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Training and capacity building course material
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review? | A capacity building programme has been developed as an inception phase output. Apart from formal placements and training, an approach to enable full participation of a range of partners in research processes is being followed. During the inception phase theme leadership has been drawn from both northern and southern partners and all the partners are members of the management team. Course and other material is still being developed based on a baseline questionnaire which identified RPC partners’ needs in relation to material resources and non-research focused training. The responses and subsequent discussions have also identified ICT, financial management and project management skills gaps.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | High quality publications from southern partners
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review? | It is too early to assess publications as none have been completed one year into the inception phase. Southern consortium partners have so far produced draft evidence papers (migration impacts and policy). Standard needs to be improved and efforts are being made to address these so that final papers are publishable. Associate partners and other southern-based researchers will undertake research over the course of the next 5 years after the research strategy is finalised and approved by Sept 2011.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Public pronouncements by migrant organizations on websites, in the press, campaign literature
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Too early to assess - none of these were progress markers for the first year inception phase. Each consortium partner has mapped stakeholders and developed a detailed engagement strategy which targets national and regional media in the areas where the research will take place, including the UK media.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 3 | 2 |  | 0.75
Impact Weighted Score | 18.75 |  | 0.1875
Justification for the Score | The capacity building and uptake managers, including regional communication focal points, have been actively involved in the research strategy development process to ensure an integrated approach.
Output 3 Recommendation 1
Output 3 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Proven evidence of uptake of new knowledge by developing country policy makers, international organisations and other research institutions
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High |  | 1
0.25
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Developing country government publications use new knowledge
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review? | The RPC is already involved in supporting development of national migration policies despite not having generated new knowledge in the first year. The work done on the evidence papers and the regional consultations have produced information helping to respond to the needs and interests of policy makers and other boundary partners. AMADPOC (The African Migration and Development Policy Centre) works closely with both the Intergovernmental Authority on Development (IGAD) and the East African Community (EAC). IGAD member states include Djibouti, Ethiopia, Kenya, Somalia, Sudan and Uganda. IGAD is currently working with the AU Commission and IOM on developing ways of cooperating on several issues relevant to the RPC including migration and development, labour migration, social protection and migration data. The Centre for Migration Studies, University of Ghana, a core partner, is playing a key role in shaping Ghana’s new migration policy by working closely with the Inter-Ministerial Steering Committee on Migration (IMSCM) which has been established at the Ministry of Interior. | What evidence do we have that the work on the evidence papers has been useful to decision makers. It is not clear here whehter the RPC funds have enabled AMADPOC to maintain its existing links to IGAD and EAC or has significantly. In other words can we specify the contribution of this programme more tightly?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | International organization and research institution documents use new knowledge
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Public pronouncements by civil society organizations on websites, in the press or in literature
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Too early to assess - this was not a progress marker for the first year inception phase. Each consortium partner has mapped stakeholders and developed a detailed engagement strategy which targets migrant groups such as the Consortium for Refugees and Migrants in South Africa, among other civil society organisations.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 4 | 2 |  | 0.75
Impact Weighted Score | 18.75 |  | 0.1875
Justification for the Score | Too early to assess - A number ofentry points have already emerged for research uptake opportunities. The RPC core partners are well known and network with a number of boundary partners who are in stronger positions to apply research findings in decision-making. E.g. The Institute for Human Rights and Business has expressed an interest in working with the RPC on the issue of migrants going to East Asia and the Middle East, and is planning a roundtable dialogue on the issue in Dhaka.
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 5 |  |  | 0
Impact Weighted Score | 0 |  | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy)
Impact Weighting (must = 100) | 100%
Total Impact Score | 68.75 | 0.6875
Output Risk | High | 1.5
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study
Government assessment
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners
DFID staff
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility. | Staff managing the programme are responsible for this first scoring after 12 months into the programme. Assessments are based on several face to face and telephone discussions with the RPC management team, and core partners. A draft research strategy and evidence papers, along with capacity building and uptake strategies were the key documents reviewed.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Consortium partners bring different degrees of capacity, and some need closer supervision and guidance than others. The slipping of deadlines by some partners can have ripple affect on the entire performance of the consortium.
Working with Partners Recommendation 1 | Closer management of consortium partners; introduce stronger accountability systems.
Working with Partners Action Point 1 | Address the above as part of the agreement for a possible continuation of the programme at the end of the inception phase in September 2011.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation
Best Practice / Innovation Recommendation 1
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | A 50% CEO based overseas has its challenges when there are consortium partners spread across the globe.
Project Management Recommendation 1 | Revisit governance structure to strengthen arrangements and structure to efficiently and effectively carry out the consortium management functions.
Project Management Action Point 1 | Agree on revised management structure proposed by RPC and University of Sussex
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
3048677 | Draft Evidence papers
3058935 | Draft inception report (research strategy, capacity building and uptake strategies)
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions?
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | The RPC is likely to leave behind a legacy of new data on internal migration, remittance flows, etc. which are useful to future analysis and planning. Major contributions of the RPC are envisaged in this area. It will improve the availability of data on internal remittances and bilateral matrices of international remittances. It will set in motion a culture of data updating and management.
Sustainability Recommendation 1
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | 0
R2 | 0
R3 | 0
A1: Purpose
R1 | Demonstrate Consortium-wide understanding of boundary partners, needs and interests by end of the inception phase. | Research Director, CEO and RED
R2 | 0
R3 | 0
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | Develop a harmonised M&E framework guided by an overarching log frame. | Research Director and CEO
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Policy questions emerging from the preliminary evidence need to be strengthened. | University of Sussex and RED/Stats
R1.2 | DFID should push for the RPC to involve international partners especially DESA Population Division as well as others on the next phase of data updates. This will ensure sustainability and more immediately avoid duplications with work underway in DESA. | RED
R1.3 | 0
R2.1 | Finalised research strategy should present a strong case for undertaking particular research activities based on rigorous review of the evidence. | Research Director and CEO
R2.2 | 0
R2.3 | 0
R3.1 | 0
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Closer management of consortium partners; introduce stronger accountability systems. | CEO
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | 0
R2 | 0
R3 | 0
Project Management
R1 | Revisit governance structure to strengthen arrangements and structure to efficiently and effectively carry out the consortium management functions. | CEO, Richard Black and RED
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | A clear theory of change and outcome mapping with progress markers by August 201. Develop a strategy to work with Boundary Partners and identify anticipated outcomes at different levels and at different points in time | CEO and Research Director
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | Ensure that Log frame is well aligned with Theory of Change and Outcome Mapping | CEO and Research Director and RED
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Develop and discuss a range of relevant policy and research questions with other consortium theme leaders and key boundary partners. | Research Director and Consortium theme leads
AP1.2 | Coordinate a data roundtable with UN and other key partners in the first quarter of year 2, to encourage shared responsibility in the expansion and updating of data. | University of Sussex
AP1.3 | 0
AP2.1 | Coordinate an evidence paper virtual discussion involving the core partners, to communicate the results of the final peer review process and help ensure improved quality. | Research Director and Consortium theme leads
AP2.2 | 0
AP2.3 | 0
AP3.1 | 0
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Address the above as part of the agreement for a possible continuation of the programme at the end of the inception phase in September 2011.
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | Agree on revised management structure proposed by RPC and University of Sussex
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3