## A1 Goal, Purpose, Risk
Annual Review (reviewed August 2011)
ARIES Project Code | 113580
ARIES Project Description | Improving Institutions for Pro-Poor Growth, University of Oxford (iiG Oxford)
A1: Goal, Purpose, Risk
Goal
Goal statement | The production and uptake of technologies and policies that will contribute to poverty reduction and the achievement of the MDGs.
Indicator 1 | Proportion of people living in poverty in Africa.
Milestone for this review (if any) | None
What progress has been made in the period covered by this review? | N/A
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Proportion of people living in poverty in South Asia.
Milestone for this review (if any) | None
What progress has been made in the period covered by this review? | N/A
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Last DFID annual report shows poverty rates declining in both Africa and South Asia although the MDG is off/track in Africa. Global downturn has increased headwinds facing Africa.
Goal Recommendation 1 | None
Goal Action Point 1 | None
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | To provide governments and civil society in Africa and Asia, and development agencies, with usable and useful knowledge as to how institutions can be redesigned so as to be more conducive to growth and empowerment.
Indicator 1 | Number of major policy changes related to institutional design in the context of growth and poverty reduction.
Milestone for this review (if any) | 2 major policy changes in the areas of the programme: - governance and accountability; - firm development and exports; - institutions for inclusive growth in poor settings. [milestone July 2009]. Cumulative target (Dec. 2011): At least 3 major policy changes in the areas of the programme: - governance and accountability; - firm development and exports; - institutions for inclusive growth in poor settings.
What progress has been made in the period covered by this review? | In addition to the two reported policy shifts on EPA rules of origin and economic liberalisation in India IIG have seen considerable traction as a result of work on the institutional mechanisms of delivering the RSBY health insurance scheme in India. There has been considerable press coverage and engagement with senior policy makers including the Chief Secretary in Bangalore who has requested IIG to undertake further research. This work places IIG favourably to have a significant policy impact over the coming year.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | iiG's level of influence on debates on institutional design in the context of growth and poverty reduction.
Milestone for this review (if any) | 2 cases of significant impact on institutional design debates in the areas of the programme: - governance and accountability; - firm development and exports; institutions for inclusive growth in poor settings. [milestone July 2009]. Cumulative target (Dec. 2011): At least 5 cases of significant impact on current debates in the areas of the programme: - governance and accountability; - firm development and exports; - institutions for inclusive growth in poor settings.
What progress has been made in the period covered by this review? | In addition to the RSBY work detailed above IIG continues to have significant impact in Kenya and Ethiopia. Research in Kenya (involving both local and international researchers) has been influential in debates on reforms in the education sector and the benefits or not of the Constituency Development Fund. DFID hosted senior Kenyan education officials to discuss the research during the year highlighted that although the large scale introduction of contract teachers may not in itself have been influenced by the research, the way it is occurring and the monitoring of the results has definitely been influenced by the research presence within the Ministry. Furthermore work in Ethiopia by Dercon building on iiG work (‘Rural Poverty: Old Challenges in New Contexts’), is contributing to substantive policy debate on the role of agriculture in growth, including via high level policy meetings in the PM office and led to further work on agriculture first sponsored by the country office and now taken up by IGC. The work has been clearly reflected in the new 5 year plan, the GTP
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Purpose assumptions being realised. IIG makes considerable effort to ensure that the research work feeds into and is linked with policy processes. Sometimes this has slowed the research progress but in the end ensures greater impact. The example of the education work in Kenya is an example of this where the research was tailored to (and delayed by) by the political processes.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | Better policies will contribute toward improved macroeconomic and growth environment although the quantification of this would be very difficult and is beyond the scope of this review.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | The achievement of the outputs will contribute to the delivery of the purpose. IIG is undertaking quality research linked into the policy environment. There is a strong likelihood that the research will impact policy in developing countries as evidenced by the RSBY, Kenyan, Ethiopian and Trade preference work. Moreover, during the coming year IIG have agreed to cohere and synthesise the research programme across their guiding intellectual framework in 5 or 6 of the key areas. Depending on the area, IIG will develop synthesis and policy products drawing on the research work and wider academic literature.
Purpose Recommendation 1
Purpose Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 2 | 2
Purpose Justification | Some high quality and influential research work has been done by IIG. Care is taken to ensure the research is linked into key policy networks. The programme is on course to deliver its objectives by the end of the programme and efforts will be taken over the remaining year to cohere and synthesise across the research portfolio. The main weakness of the programme is in the firm development area where there is scope for more research work to be undertaken.
Risk
Project Risk Rating or latest Overall Risk Score. | Low
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1 | None
Risk Action Point 1 | None
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | No
If Yes, why was/is this?
Logframe Recommendation 1
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design.
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 50%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Low | 3
1.5
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 (leave blank if standard indicator) | Number of papers in peer-reviewed journals. | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 15 journal papers. [milestone July 2009]. Cumulative target (Dec. 2011): 30 journal papers accepted in journals, 10 more submitted. | 0
Progress made in the period covered by this review, including numbers. | IIG are on track to deliver this output. So far 27 journal articles have been accepted (25 in print). It is anticipated that a number of new articles will be developed over the coming year. The list of papers are 1. 2007 Paul Collier and Benedikt Goderis, "Prospects for Commodity Exporters: Hunky Dory or Humpty Dumpty?" in World Economics, 8(2), 2007 2. 2008 Paul Collier and Tony Venables, "Rethinking trade preferences: How Africa can diversify its exports", in 'The World Economy, Global Trade Policy 2007' Ed. David Greenaway. Wiley-Blackwell, Feb 2008. 3. 2008 Philippe Aghion, Robin Burgess, Stephen Redding, and Fabrizio Zilibotti, 2008. "The Unequal Effects of Liberalization: Evidence from Dismantling the License Raj in India." American Economic Review, 98(4): 1397–1412. 4. 2008 Michael Bratton and Mwangi Kimenyi, 2008 " Voting in Kenya:Putting Ethnicity in Perspective", Journal of Eastern African Studies, 2 (2): 272-82. 5. 2008 Paul Collier and Tony Venables, " Trade and economic performance: does Africa's fragmentation matter?" in Lin and Pleskovic (eds) Annual World Bank conference on Development Economics 2009, Global: People, Politics, and Globalization. (Conference held in June 2008.) 6. 2008 Chauvet L. and P. Collier. 2008. What are the preconditions for turnarounds in failing states? Conflict Management and Peace Science 25(4):332 – 348. 7. 2009 Christopher Adam and Stefan Dercon, " The Assessment: the Political Economy of Economic Development " Introduction to Special issue Oxford Review of Economic Policy, on the Political Economy of Economic Development. May 2009, Oxford University Press. 8. 2009 Toke S. Aidt, "Corruption, Institutions and Economic Development" in Special issue of the Oxford Review of Economic Policy, on the Political Economy of Economic Development. May 2009, Oxford University Press. 9. 2009 Gani Aldashev, "Legal Institutions, Political Economy and Development" in Special issue of the Oxford Review of Economic Policy, on the Political Economy of Economic Development. May 2009, Oxford University Press. 10. 2009 Paul Collier, "The Political Economy of State Failure" in Special issue of the Oxford Review of Economic Policy, on the Political Economy of Economic Development. May 2009, Oxford University Press. 11. 2009 Indermit Gill and Homi Kharas, "Gravity and Friction in Growing East Asia" in Special issue of the Oxford Review of Economic Policy, on the Political Economy of Economic Development. May 2009, Oxford University Press. 12. 2009 Ragnar Torvik, "Why do some resource abundant countries succeed while others do not?" in Special issue of the Oxford Review of Economic Policy, on the Political Economy of Economic Development. May 2009, Oxford University Press. 13. 2009 Pedro C. Vicente and Leonard Wantchekon, "Clientelism and Vote Buying: Lessons from Field Experiments in African Elections" Special issue of the Oxford Review of Economic Policy, on the Political Economy of Economic Development. May 2009, Oxford University Press. 14. 2009 Paul Collier and Benedikt Goderis, "Does Aid Mitigate External Shocks", Review of Development Economics, 13 (2009), s1 (08), 429-451 15. 2009 Paul Collier and Anke Hoeffler, "Testing the Neocon Agenda: Democracy in Resource-Rich Societies", European Economic Review, Volume 53, Issue 3, April 2009, Pages 293-308. 16. 2009 Tim Besley and Torsten Persson, "The Origins of State Capacity: Property Rights, Taxation and Politics", American Economic Review, 99(4): 1218–44. Sep 2009. 17. 2009 Besley, Timothy, and Torsten Persson, "Repression or Civil War?" American Economic Review, 99(2): 292–97. May 2009. 18. 2009 Paul Collier, "Wars, Guns and Votes: Democracy in Dangerous Places". The Bodley Head, 2009. 19. 2009 Paul Collier and Lisa Chauvet, "Elections and Economic Policy in Developing Countries", Economic Policy, 24 (59):509-50. July 2009 20 2009 Paul Collier and Benedikt Goderis. 2009 "Structural Policies for Shock-Prone Developing Countries", Oxford Economic Papers , 61 (4): 703-26 21 2009 Stefan Dercon "Rural Poverty: Old Challenges in new Contexts", The World Bank Research Observer 2009 24(1):1-28; doi:10.1093/wbro/lkp003 22 2010 Oriana Bandiera, Robin Burgess, Markus Goldstein, Selim Gulesci, Imran Rasul and Munshi Sulaiman "Intentions to participate in adolescent training programs: Evidence from Uganda" Journal of the European Economic Association April/May 2010, Vol. 8, No. 2-3 23 2010 Timothy Besley & Torsten Persson, 2010. "State Capacity, Conflict, and Development," Econometrica, Econometric Society, vol. 78(1), pages 1-34, 01. Jan 2010. 24 2010 Robin Burgess and Dave Donaldson, "Can openness mitigate the effects of weather shocks? Evidence from India's Famine Era", American Economic Review: Papers & Proceedings 100 (May 2010): 449–453. 25 2010 Paul Collier, Anthony J. Venables, Illusory revenues: Import tariffs in resource-rich and aid-rich economies, Journal of Development Economics, In Press, Corrected Proof, Available online 12 February 2010, ISSN 0304-3878, DOI: 10.1016/j.jdeveco.2010.01.015. 26 Forthcoming 2011 Anke Hoeffler and Verity Outram, Need, Merit or Self-Interest – What Determines the Allocation of Aid? Accepted for publication in the Review of Development Economics. Additional Material for Anke Hoeffler and Verity Outram, Need, Merit or Self-Interest – What Determines the Allocation of Aid? 27 Forthcoming 2011 Ali, D. A., Dercon, S. and Gautam, M. (2011), Property rights in a very poor country: tenure insecurity and investment in Ethiopia. Agricultural Economics, 42: 75–86. doi: 10.1111/j.1574-0862.2010.00482.x
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of working papers, book chapters and research reports.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 12 papers. [ milestone July 2009]. Cumulative target (Dec. 2011) 25 papers.
Progress made in the period covered by this review, including numbers | IIG has already more than achieved the target. To date they have 27 working papers (in defined series, unpublished in journals or books) plus 3 published book chapters. New additions in 2010 were the 3 book chapters and 11 papers. See below for list Books 1. 2010 Stefan Dercon and Pramila Krishnan, “Land Rights Revisited”, in The Microeconomics of Institutions, Tim Besley and Raji Jayaraman (eds.), MIT Press (2010) 2. 2010 Gutiérrez Romero, R., Kimenyi, M,. Collier, P. (2010) ‘Elections and Institutions in Kenya’, in Adam, C. Collier, P. N’dungu (Eds.) Kenya Policies for Prosperity, Oxford University Press, 2010. 3. 2010 Tessa Bold, Mwangi Kimenyi, Germano Mwabu, and Justin Sandefur. “Determinants of Educational Achievement in Kenya since the Introduction of FPE.” . in Adam, C. Collier, P. (Eds.) Kenya Policies for Prosperity, Oxford University Press, 2010. Working papers 1 2007 Stefan Dercon and Daniel Ayalew, Land Rights, Power and Trees in Rural Ethiopia, CSAE WPS/2007-07, 2007 2 2008 Mwangi S. Kimenyi & Roxana Gutierrez Romero, Tribalism as a Minimax-Regret Strategy: Evidence from Voting in the 2007 Kenyan Elections, University of Connecticut, Department of Economics Working paper 2008-35, 2008 3 2008 Michael Bratton and Mwangi Kimenyi, Voting in Kenya: Putting Ethnicity in Perspective, Afrobarometer Working Paper No.95, 2008 4 2008 Paul Collier and Pedro C. Vicente, Votes and Violence: Evidence from a Field Experiment in Nigeria, CSAE WPS/2008-16, 2008 5 2008 Paul Collier and Benedikt Goderis, Commodity Prices, Growth, and the Natural Resource Curse: Reconciling a Conundrum, CSAE WPS/2007-15, 2007 6 2008 Sylvain Chassang and Gerard Padró i Miquel, "Mutual Fear and Civil War", BREAD working paper # 165, February 2008 7 2008 Tim Besley with Torsten Persson, "The Incidence of Civil War: Theory and Evidence", NBER Working Paper No. 14585, Dec 2008. 8 2009 Christopher Ksoll, Rocco Macchiavello and Ameet Morjaria. Guns and Roses: The Impact of the Kenyan Post-Election Violence on Flower Exporting Firms. CSAE WPS/2009-06, 2009 9 2009 Mwangi S. Kimenyi & Roxana Gutierrez Romero, Identity, Grievances, and Economic Determinants of Voting in the 2007 Kenyan Elections, University of Connecticut, Department of Economics Working paper 2008-38, 2008 10 2009 Marcel Fafchamps and Pedro C. Vicente. Political Violence and Social Networks: Experimental Evidence from a Nigerian Election CSAE WPS/2009-14 11 2009 Tessa Bold and Stefan Dercon, Contract Design in Insurance Groups. CSAE WPS/2009-04, 2009 12 2009 Oriana Bandiera, Robin Burgess, Selim Gulesci and Imran Rasul, "Community Networks and Poverty Reduction Programmes: Evidence from Bangladesh." Paper No' EOPP 015, December 2009 13 2009 Timothy Besley and Torsten Persson, "The Logic of Political Violence" Nov 2009 14 2009 Oriana Bandiera, Robin Burgess, Selim Gulesci and Imran Rasul "Community Networks and Poverty Reduction Programmes: Evidence from Bangladesh". STICERD Economic Organisation and Public Policy Discussion Papers, EOPP/2009/15 15 2009 Paul Collier and Anke Hoeffler. Democracy’s Achilles Heel or, How to Win an Election without Really Trying. CSAE WPS/2009-08 16 2010 Roxana Gutiérrez-Romero. Decentralization, Accountability and the 2007 MPs Elections in Kenya. CSAE WPS/2010-09 17 2010 Abigail Barr and Andrew Zeitlin. Dictator games in the lab and in nature: External validity tested and investigated in Ugandan primary schools. CSAE WPS/2010-11 18 2010 Stefan Dercon and Roxana Gutiérrez-Romero. Triggers and Characteristics of the 2007 Kenyan Electoral Violence. CSAE WPS/2010-12 19 2010 Roxana Gutiérrez-Romero. The Role of Ethnic Identity and Economic Issues in the 2007 Kenyan Elections. CSAE WPS/2010-06 20 2010 Roxana Gutiérrez-Romero. The Dynamics of the Informal Economy. CSAE WPS/2010-07 21 2010 Roxana Gutiérrez-Romero. Occupational Choice and Inequality Traps. CSAE WPS/2010-08 22 2010 Pramila Krishnan and Sofya Krutikova (2010), “Skill formation in Bombay's Slums", CWPE 1010 23 2010 Justin Sandefur. On the Evolution of the Firm Size Distribution in an African Economy. CSAE WPS/2010-05 24 2010 Sanchari Roy, "Empowering Women: Inheritance Rights and Female Education in India", May 9, 2010 25 2010 Paul Collier and Anke Hoeffler. Do Elections Matter for Economic Performance? CSAE WPS/2010-35 26 2010 Madina Guloba, James Wokadala and Lawrence Bategeka, 2010. Teaching Resource Availability and Methods on Pupils Performance: Evidence from For Districts in Uganda, EPRC Research Series Paper, October 2010 27 2011 Tanguay Bernard, Stefan Dercon and Alemayehu Seyoum Tafesse, Beyond fatalism: an empirical exploration of self-efficacy and aspirations failure in Ethiopia.WPS/2011-03
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Number of data sets.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Kenya dataset released on web. [milestone end 2010] Target 2011 - 3 datasets from Bangladesh, Kenya, and Ethiopia on web within 24 months of completion of survey work.
Progress made in the period covered by this review, including numbers | Kenya dataset is on the web and available upon request. Work underway to deliver other data sets and will be achieved by the target date.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 2 | 0.75
Impact Weighted Score | 37.5 | 0.375
Justification for the Score | Overall the programme is on track to deliver the indicators and has already exceeded the target in one case. There is a good underlying research programme in the area of accountability and governance and institutions for pro-poor growth which will deliver the desired journal articles, working papers and data sets. The main weakness however is in the area of firm development where the quantity of research has been weakest and where possibly more work is needed.
Output 1 Recommendation 1 | Consider the scope for more work on firm development
Output 1 Action Point 1 | Explore with IIG the scope for further work on firm development
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Strengthened capacity of partner institutions in RPC in analysing the role of institutions and their reform for growth and poverty.
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Low | 3
0.45
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | Number of papers per year with co-authors from partner institutions published in peer reviewed journals, book chapters and in working paper series.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 6 papers of which 2 in peer-reviewed journals. [milestone July 2009]. Cumulative target (Dec. 2011): 10 papers of which at least 4 in peer reviewed journals.
Progress made in the period covered by this review, including numbers | IIG is on track to deliver against this indicator. Currently 8 papers have been co-authored of which 2 are in peer review journals. 2 papers were added in 2010 and 1 is forthcoming in 2011. See the full list below Peer reviewed journals 4. 2008 Michael Bratton and Mwangi Kimenyi, 2008 " Voting in Kenya: Putting Ethnicity in Perspective", Journal of Eastern African Studies, 2 (2): 272-82. 22 2010 Oriana Bandiera, Robin Burgess, Markus Goldstein, Selim Gulesci, Imran Rasul and Munshi Sulaiman "Intentions to participate in adolescent training programs: Evidence from Uganda" Journal of the European Economic Association April/May 2010, Vol. 8, No. 2-3 Book Chapters 2. 2010 Gutiérrez Romero, R., Kimenyi, M,. Collier, P. (2010) ‘Elections and Institutions in Kenya’, in Adam, C. Collier, P. N’dungu (Eds.) Kenya Policies for Prosperity, Oxford University Press, 2010. 3. 2010 Tessa Bold, Mwangi Kimenyi, Germano Mwabu, and Justin Sandefur. “Determinants of Educational Achievement in Kenya since the Introduction of FPE.” . in Adam, C. Collier, P. (Eds.) Kenya Policies for Prosperity, Oxford University Press, 2010. WORKING PAPERS 2 2008 Mwangi S. Kimenyi & Roxana Gutierrez Romero, Tribalism as a Minimax-Regret Strategy: Evidence from Voting in the 2007 Kenyan Elections, University of Connecticut, Department of Economics Working paper 2008-35, 2008 3 2008 Michael Bratton and Mwangi Kimenyi, Voting in Kenya: Putting Ethnicity in Perspective, Afrobarometer Working Paper No.95, 2008 9 2009 Mwangi S. Kimenyi & Roxana Gutierrez Romero, Identity, Grievances, and Economic Determinants of Voting in the 2007 Kenyan Elections, University of Connecticut, Department of Economics Working paper 2008-38, 2008 27 2011 Tanguay Bernard, Stefan Dercon and Alemayehu Seyoum Tafesse, Beyond fatalism: an empirical exploration of self-efficacy and aspirations failure in Ethiopia.WPS/2011-03
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Spend in developing countries.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Cumulative at Dec. 2009: £408,885; Cumulative at Dec. 2010: £574,057; Cumulative Target Dec. 2011: £899,636.
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 2 | 0.75
Impact Weighted Score | 11.25 | 0.1125
Justification for the Score | IIG is on track to deliver against this Output. Through its networks with southern researchers IIG has developed effective working relationships and supported southern capacity. A significant number of papers are co-authored with southern researchers
Output 2 Recommendation 1 | None
Output 2 Action Point 1 | None
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Effective communication of research outcomes.
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 35%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Low | 3
1.05
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | Number of briefing papers on research outcomes.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 10 briefing papers. [milestone end of 2009]. Cumulative total (Dec. 2011): 20 briefiing papers.
Progress made in the period covered by this review, including numbers | IIG is on track to deliver against this indicator. 17 briefing papers are on the website of which 7 were added in 2010. IIG have also committed to produce sythesis and brieifng products across 5 or 6 of their research areas during the coming year. The current list of brieifng papers are 2008 C1 Roxana Gutiérrez Romero, Mwangi S. Kimenyi and Stefan Dercon, "The 2007 Elections, Post-Conflict Recovery and Coalition Government in Kenya", iiG Briefing Paper 01, September 2008 2009 C2 Roxana Gutiérrez Romero, 'Decentralization, Accountability and the MPs Elections: The Case of the Constituency Development Fund in Kenya' iiG Briefing Paper 02, May 2009 2009 C3 Stefan Dercon, Michael Bratton, Mwangi Kimenyi, Roxana Gutierrez-Romero, and Tessa Bold, "Ethnicity, Violence and the 2007 Elections in Kenya", Afrobarometer Briefing Paper No.48, 2008 2007 C4 Paul Collier, "Survival of the Fattest", in The American Interest, 2007 2007 C5 Paul Collier and Anthony J. Venables, “Rethinking Trade Preferences to Help Diversify African Exports”, CEPR Policy Research Insight No. 2, June 2007. 2009 C6 "Lessons from Kenya’s introduction of free primary education", iiG Briefing Paper 03, August 2009 2009 C7 "Teacher Interns and Community Monitoring in Kenyan Schools", iiG Briefing Paper 04, August 2009 2009 C8 "The Impact of the Kenyan Post-election Violence on the Kenyan Flower Export Industry", iiG Briefing Paper 05, August 2009 2009 C9 "Votes and Violence in Nigeria", iiG Briefing Paper 06, August 2009 2009 C10 Campaign finance distorts Nigerian elections, iiG Briefing Paper 07, November 2009 2010 C11 "India's poor rely mainly on private health care" iiG Briefing Paper 08 March 2010 2010 C12 "Supporting Democratic Institutions and Clean and Peaceful Elections" iiG Briefing Paper 09 March 2010 2010 C13 "How economic growth and politics interact" iiG Briefing paper 10 March 2010 2010 C14 "The Informal Economy and Growth", iiG Briefing Paper 11, June 2010 2010 C15 "To feed or to educate: Hard choices for the extremely poor", iiG Briefing Paper 12, June 2010 2010 C16 "Hospitalisation means India’s poor go hungry", iiG Briefing Paper 13, July 2010 2010 C17 "Can you successfully teach people how to run small businesses?" iiG Briefing Paper 14, January 2011
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of workshops with at least 5 relevant stakeholders.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2. [milestone end 2010]. Cumulative target (Dec. 2011): 6.
Progress made in the period covered by this review, including numbers | IIG has already exceeded the target and plans to hold at least another 2 workshops before the end of the programme, one in Kenya which has a direct capacity building aim and one linked to the CSAE event in March 2012 Jun 2007 iiG workshop CSAE Mar 2008 iiG workshop CSAE Mar 2008 CSAE Conference (special iiG session) CSAE Sep 2008 iiG Workshop: Elections and Post-Conflict Recovery in Kenya Nairobi, Kenya Mar 2009 iiG workshop CSAE Mar 2009 CSAE Conference (special iiG session) CSAE Oct 2009 iiG Workshop: Improving Management and Accountability in Primary Schools Kampala, Uganda Dec 2009 iiG Workshop: Institutional Aspects of Pro-Poor Policy: Revising the Indian Poverty Line ISEC, Bangalore Mar 2010 iiG workshop CSAE Mar 2010 CSAE Conference (specific iiG papers presented) CSAE Jun 2010 iiG Workshop: Researching Nigeria CSAE Sep 2010 iiG Workshop: Policies for Inclusion in India and Beyond Bangalore, India
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Project website, kept up to date.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | All briefing papers, data and research papers available on webiste in structured form. [milestone end 2009]. Cumulative target (Dec. 2011): All briefing papers, data and research papers available on website in structured form.
Progress made in the period covered by this review, including numbers | The webiste is constantly updated throughout the year with new articles and briefing notes added as and when completed.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 2 | 0.75
Impact Weighted Score | 26.25 | 0.2625
Justification for the Score | IIG has developed a good set of brieifng notes over the year which are a useful source of quick reference notes on key research issues. Each partner has received at least one in country training event with a further event planned for Nigeria this coming year
Output 3 Recommendation 1 | IIG will focus on cohering the programme and developing appropriate synthesis/other communication documents over the coming year and explore options for further work on firm development
Output 3 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-06-14
Impact Weighting (must = 100) | 100%
Total Impact Score | 75 | 0.75
Output Risk | Low | 3
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners
DFID staff | X
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility. | Scoring undertaken and agreed by project team (John Piper, Tim Hatton and Tony Zachariades).
Scoring Recommendation 1 | None
Scoring Action Point 1 | None
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | IIG have continued to be proactive in working with its partners. For example, this year a new partner has emerged in Nigeria - a country where IIG had had problems previously. As a result of this new partnership interesting research is likely to result.
Working with Partners Recommendation 1 | Continue to develop relationships with partner researchers and institutions
Working with Partners Action Point 1 | None
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | None
Best Practice / Innovation Recommendation 1 | N/A
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Management of this project has been satisfactory. IIG does however need to tighten up on its financial forecasting. Throughout the year under review, the amounts invoiced to DFID have differed significantly from the forecasts of expenditure provided. This has caused difficulties for us in our financial management of our programme portfolio as well as in our financial reporting.
Project Management Recommendation 1 | IIG to make efforts to be more accurate with financial forecasting liaising more regularly with the DFID programme management team.
Project Management Action Point 1 | As in recommendation above.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | N/A
Key issues, points of information or additional comments that may be useful for this or other project teams. | IIG has a number of activities where it is working on gender-related issues. DFID is currently conducting an exercise to draw together the work done on gender in the field of growth research and IIG is likely to be a potentially good source of data for this work.
Other Recommendation 1 | IIG to collaborate with DFID on gender data gathering.
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
IIG annual report 2010
IIG website www.iig.ox.ac.uk
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause? | n/a
Date Suspended (dd/mm/yyyy)? | n/a
What were the consequences? | n/a
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | The programme produces research outputs that will continue to be used beyond the lifetime of the project
Sustainability Recommendation 1
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | None
R2 | 0
R3 | 0
A1: Purpose
R1 | 0
R2 | 0
R3 | 0
A1: Risk
R1 | None
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Consider the scope for more work on firm development
R1.2 | 0
R1.3 | 0
R2.1 | None
R2.2 | 0
R2.3 | 0
R3.1 | IIG will focus on cohering the programme and developing appropriate synthesis/other communication documents over the coming year and explore options for further work on firm development
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | None
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Continue to develop relationships with partner researchers and institutions
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | N/A
R2 | 0
R3 | 0
Project Management
R1 | IIG to make efforts to be more accurate with financial forecasting liaising more regularly with the DFID programme management team.
R2 | 0
R3 | 0
C: Other Comments
R1 | IIG to collaborate with DFID on gender data gathering.
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | None
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | None
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Explore with IIG the scope for further work on firm development
AP1.2 | 0
AP1.3 | 0
AP2.1 | None
AP2.2 | 0
AP2.3 | 0
AP3.1 | 0
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | None
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | None
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | As in recommendation above.
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3