## A1 Goal, Purpose, Risk
Project Completion Report (reviewed August 2010)
ARIES Project Code | 109153
ARIES Project Description | Basic Education Development Project (BEDP)
A1: Goal, Purpose, Risk
Goal
Goal statement | Basic Education in Yemen improves
Indicator 1 | Gross enrolment ratio in basic education for Grades 1-9 nationally (To note: This indicator has been dropped from the jointly agreed project Results Framework as this is a national level indicator and does not represent targeted project governorates).
Target (if any) | 90% (2010 target taken from Ministry of Education Mid Term Framework)
What progress was made? | Largely achieved. The initial results from the 2010 Comprehensive School Survey (CSS) suggests an increase in gross enrolment rates from 77% in academic year 2005/06 to 85% in 2010/11 (95% boys, 75% girls). The CSS field data collection was finalised in March 2011. However, the final results of the CSS will not be published until September 2011 due to difficulties in data entry and verification of data as a result of ongoing political unrest.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Gender Parity Index for Grade 1-9 enrolment nationally
Target (if any) | 0.8 (The target was changed from 0.90 to 0.80 in 2010/11)
What progress was made? | Largely achieved. While it is not possible to accurately report progress against this target in the absence of the Comprehensive School Survey (CSS) 2010/11, it is evident that good progress has been made. The Gender Parity Index (GPI) improved from the base line of 0.70 in 2005/06 to 0.77 in 2009/10. The CSS is due to be published in September 2011 and will enable this data to be updated.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Female retention rate to Grade 6 nationally
Target (if any) | 0.63 (2010 target)
What progress was made? | It is not possible to measure progress against this target in the absence of the Comprehensive School Survey (CSS) 2010/11. The results of the CSS are due to be published in September 2011 and will enable updating and/or verification of the 2005 baseline figure (0.59).
Goal Recommendation 1 | There is weak evidence to determine whether the national increase in male and female enrolment and retention can be attributed to BEDP. The Comprehensive School Survey (CSS) is essential for measuring progress against Goal and Purpose level targets. DFID has decided to undertake this Project Completion Report (PCR), despite the absence of this data, as we have disbursed over 90% of our overall commitment to BEDP and there is sufficient evidence to evaluate the performance of the project. DFID should continue to push for timely completion of the CSS, now planned for September 2011. The London based Deputy Programme Manager will produce an information note confirming progress against Goal and Purpose level data following publication of the CSS.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Purpose
Project Purpose | Increased participation, especially of girls, in better quality basic education in ten Governorates, with the foundations of Ministry of Education (MoE) capacity to deliver core functions established.
Indicator 1 | Number of female students enrolled in Grades 1-9 in 10 Governorates
Target (if any) | 925,000 (2010 target)
What progress was made? | Largely achieved. 875,275 female students were enrolled in Grades 1-9 in 2009/10 (data taken from 2009/10 Annual Education Survey (AES)). This is a notable improvement on the 2005/06 baseline of 780,000. The Comprehensive School Survey (CSS) 2010/11 will enable the updating of this progress against this target. We expect to see an increase in the number of female students to approximately 900,000 (over 90% of the original target).
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Percentage of Grade 4 students in schools where few (25% or less) teachers had professional development in improving teaching skills
Target (if any) | 25% (2012 target)
What progress was made? | Partially achieved. It is not possible to accurately assess progress against this indicator in the absence of the 2011 International Assessment of Trends in Maths and Science Subjects (TIMSS). However, TIMSS is progressing well. Preparatory work and field analysis have been completed and informal results of TIMSS will be available in late October 2011. The official results will be available in the second quarter of 2012.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Implementation of reform policies based on the Basic Education Development Strategy
Target (if any) | Revised MoE structure completed and adopted (2012 target)
What progress was made? | Partially achieved. Some progress has been made against this output. The Ministry of Education produced an Organisational Structural Reform and Modernisation Vision across central and local levels with the technical assistance from international consultants. A Modernisation Task Force (MTF) and the Centre for Measurement and Evaluation (Come) were established to drive forward restructuring and reform in the Ministry. However, despite commitment at Ministerial level, high level resistance remains problematic. The current political unrest has resulted in suspension of much of the MoE reform and modernisation agenda.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Target (if any)
What progress was made?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Target (if any)
What progress was made?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Target (if any)
What progress was made?
Were Purpose Assumptions realised? If so, to what degree, and what was the effect on the project? | Insecurity and conflict continue to pose a real challenge for project implementation and the safety and security of implementing partners. The increasing political unrest and localised violence, as well as the resulting food and fuel shortages, have put considerable stress on implementing partners' financial and human resources. This has resulted in suspension of activities in the Governorates most affected by fighting, including Sana'a and Marib. The purpose assumptions were realised to some degree. Societal barriers to girls' education remains problematic, however, some good progress has been made in female enrolment and retention. Substantial progress has been made against 'teacher training' targets. However, it is not clear to what extent a country wide approach to teacher training has been adopted, nor is it possible to measure the extent to which teacher training impacts on the quality of teaching.
Despite the major challenges, the Ministry of Education (MoE) remains committed to BEDP and to the special initiatives aimed at increasing girls participation. While commitment to reform at Ministerial level remains intact, high level resistance across the organisation to wider reforms and restructuring has impeded progress. The current political unrest has resulted in suspension of much of the MoE reform and modernisation agenda.
What evidence is there that achievement of the Purpose contributed or continues to contribute to the realisation of the Goal? If it has done so or is doing so, to what degree? | While achievement of the purpose would contribute to improved Basic Education in Yemen, there is not enough evidence to determine whether the national increase in male and female enrolment and retention can be attributed to BEDP. Evidence from the October 2010 Joint Review Mission suggests that BEDP has made a positive contribution in target Governorates. The Comprehensive School Survey (CSS) will improve our ability to measure the impact of BEDP on the wider Education Sector in Yemen. The publication of the CSS has been subject to a number of delays, the most recent of which is due to political instability in Yemen. Data collection took place in March 2011. Data entry was subsequently delayed due to violence in Sana'a, which has impaired the Ministry of Education's (MoE) ability to operate - continued power cuts, staffing constraints due to civil unrest, fuel shortages and rioting in the vicinity of the MoE office. The final report should now be published in September 2011. Good progress has been made in increasing the capacity of MoE staff. However, while commitment to reform at Ministerial level remains intact, high level resistance across the organisation to wider reforms and restructuring has delayed significant progress. The current political unrest has resulted in suspension of much of the MoE reform and modernisation agenda.
Good progress has been made in increasing the capacity of MoE staff. However, while commitment to reform at Ministerial level remains intact, high level resistance across the organisation to wider reforms and restructuring has impeded progress. The current political unrest has resulted in suspension of much of the MoE reform and modernisation agenda.
What is the evidence that the achievement of the Purpose can be attributed to progress made in delivering the Outputs? | There is strong evidence to suggest that achievement of the purpose can be directly attributed to the delivery of the outputs. The results of the Comprehensive School Survey (CSS) 2010/11 will make it possible to better measure the extent of progress at all levels. Following the revision of the World Bank's Results Framework in 2010, the indicators are now better aligned to programme delivery and are more realistic than previous ambitious targets. However, the BEDP logframe/Results Framework remains input focused rather than measuring outcomes and impact. While the project has made substantial progress in achieving targets at output level, it is important to recognise the impact of the current situation and the effect this may have on final achievement of the project.
Purpose Recommendation 1 | The Yemen-based Project Officer should continue to review the status of implementation, producing quarterly information notes to update progress and flag issues to senior management.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Project Purpose Score | 2 | 2
Purpose Justification | This project has been assessed as "Largely Achieved". While BEDP will continue to implement activities until mid-late 2012, the final year of implementation will face a number of new risks and challenges related to the ongoing political unrest. Despite these challenges, the project is on track to meet the majority of its qualitative and quantative targets at outcome and output level. The Donor Partners remain commited to Basic Education in Yemen, and will continue to support the sector, thereby improving the likelihood of the benefits of this project continuing. The initial findings from the Comprehensive School Survey (CSS) 2010/11 suggests that substantial progress has been made in increasing enrolment rates and improving gender parity at the national level over the last 5 years. This Project Completion Report (PCR) has been completed as DFID has disbursed over 90% of its committed £15 million.BEDP is likely to score a 1 once the final activities have been completed in 2012.
Risk
Project Risk Rating or latest Overall Risk Score. | High
Was the Project Risk Rating revised since the last review? | Yes
If Yes, why was this? | Given the deteriorating political, economic and security situation in Yemen, the risk rating needs to be revised to "High". New and emerging risks include increasing costs of implementation due to shortages of fuel and commodities; lack of financial resources to meet contractual obligations; and restrictions on access due to insecurity. Implementing partners need to ensure sufficient risk management strategies are in place to deal with the evolving context. This revision is necessary as project implementation will continue until mid-late 2012.
If new risks have emerged since the last review, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What was done to manage or monitor these new Risks? How successful was the action taken?
Risk Recommendation 1 | The London based Deputy Programme Manager will work with donor and implementing partners to be better prepared to mitigate emerging risks.
If more Recommendations need to be made click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised since the last review? | No
If Yes, why was this? | The logframe was revised prior to the last annual review. This review is based on the revision of February 2010.
Logframe Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
DSOs revised since the last review? | No
If Yes, why was this?
DSO Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
Cross-Cutting Markers revised since the last review? | No
If Yes, why was this?
CCM Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Opportunities for participation of children, especially girls, in Grades 1-9 are increased
Has the Impact Weight been revised since the last review? | No
If Yes, why was this?
Current Impact Weight (%) | 40%
Has the Risk been revised since the last review? | No
If Yes, why was this?
Current Risk | Medium
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share | 16% (This is DFID's share of the overall contribution to BEDP)
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator? | Yes
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated
Target (with numbers, where appropriate) | 3,442 (Cumulative)
What progress was made, including numbers | Achieved. To date 1,850 newly constructed or extended classrooms and 1,739 rehabilitated classrooms have been handed over to the Ministry of Education. This is a cumulative total of 3,589. An additional 98 classrooms are currently under construction or rehabilitation. As of June 2011, 196 new and rehabilitated schools were handed over to MoE.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator | Number of girls in grades 4-9 receiving Conditional Cash Transfers in 2 Governorates
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | 33,784 (2012 target)
What progress was made, including numbers | Achieved. The Conditional Cash Transfers (CCT) component was completed in 2010. This innovative project benefitted 38,379 female students in 2 pilot Governorates. Anecdotal evidence suggests that CCT has led to an increase in the number of females attending school. An independent evaluation of CCT is currently being designed and technical proposals for the impact evaluation in Hodeidah Governorate are being assessed. The selection process and awarding of contracts may take up to 6 months and it is hoped that results of the evaluation will be published in April 2012.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator | Gender Parity Index (GPI) for Grades 1-9 enrolment in 10 Governorates
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | 0.8 (2010 target))
What progress was made, including numbers | Largely achieved. While it is not possible to accurately report progress against this target in the absence of the Comprehensive School Survey (CSS) 2010/11, it is evident that good progress has been made. The Gender Parity Index (GPI) improved from the base line of 0.70 in 2005/06 to 0.77 in 2009/2010. The CSS is due to be published in September 2011 and will enable this data to be updated.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 1 | 2
Impact Weighted Score | 30
Justification for the Score | Largely achieved. The construction/rehabilitation of the additional 98 classrooms is currently suspended due to the deteriorating political and security situation. Construction works are also being delayed due to lack of financial resources in the Project Administration Unit (PAU) and Public Works Programme (PWP) to meet contractual commitments. Resolving this issue is largely dependent on the World Bank's ability to disburse much-needed funds to continue public works.
Output 1 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Nationwide quality of teaching improved
Has the Impact Weight been revised since the last review? | No
If Yes, why was this?
Current Impact Weight (%) | 30%
Has the Risk been revised since the last review? | No
If Yes, why was this?
Current Risk | Medium
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share | 16% (This is DFID's share of the overall contribution to BEDP)
Indicator 1 (leave blank if standard indicator | Number of teachers trained in Part 1,2 and 3 of In-service Teacher Training (INSET)
Is this a Standard Indicator? | Yes
Select standard indicator from drop down list | 1. Number of teachers trained
Target (with numbers, where appropriate) | 90,274 (Cumulative - Parts I and II) of which 56,000 also completed Part III
What progress was made, including numbers | Largely achieved. This indicator captures a three part training programme. Overall the project targeted 90,274 teachers. Part I - 90,274, (100%) teachers have completed training; Part II - 74,407 ( 80%) teachers have complete training to date. An additional 9,900 teachers are due to receive training this year. This will bring the total for Part II to 83,000 (90%). Part III - 43,524 (50%) teachers have received training on Part 3 to date. The target number of teachers receiving training on Part III has been reduced to 56, 000 due to lack of funding.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator | Number of Headmasters and Deputy Headmasters trained in Parts 1, 2 and 3 of school management training
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | 16,471 (cumulative) of which 15,262 complete Parts I ,II, and III (2012 target)
What progress was made, including numbers | Achieved. This component was completed in 2010. Over 100% of the target number of Head teachers received training in Parts 1 and 2 in 2007/08. Over 16,180 Heads and Deputy Heads received training in Part 3 in 2009/10.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator | Number of schools nationally receiving more than 3 inspection visits per year
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | 10,000 per year
What progress was made, including numbers | Largely achieved. 7,684 schools of the target 10,000 received at least 3 supervision visits during the school year 2009/10. This represents 76% achievement. Almost 100% of target schools received inspection visits in the first 3 years of implementation (2006/07 - 2008/09). Results for school year 2010/2011 will be made available in September 2011.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 2 | 2
Impact Weighted Score | 22.5
Justification for the Score | Largely achieved. Excellent progress has been made against this output. It is worth noting that these indicators do not capture the full extent of the school-related training supported through BEDP. Other activities include training for laboratory specialists and social workers, and on sign language. While good progress has been made, these indicators are quantative and do not capture the effectiveness or impact of training. More work is needed to monitor and evaluate the impact of training on quality of teaching.
Output 2 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Foundations established for improved MoE capacity to carry out its core functions
Has the Impact Weight been revised since the last review? | No
If Yes, why was this?
Current Impact Weight (%) | 30%
Has the Risk been revised since the last review? | No
If Yes, why was this?
Current Risk | High
Has the DFID Share been revised since the last review? | No
If Yes, why was this?
Current DFID Share | 16% (This is DFID's share of the overall contribution to BEDP)
Indicator 1 (leave blank if standard indicator | Job descriptions and profiles for administration positions (Central MoE, District Education Office and Governorate Education Office) are available and used.
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Descriptions and profiles being used (2012 target)
What progress was made, including numbers | Partially achieved. Job descriptions and profiles were made available in 2009/10. However, there is no evidence to verify whether these are being used by MoE.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator | Number of MoE staff trained in core skills
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | 5,436 (cumulative) (2012 target)
What progress was made, including numbers | Largely achieved. To date 3,287 (cumulative) MoE staff from centre, governorate and district levels received training in core skills [1,836 in 2007/2008; 609 in 2008/2009; 299 in 2009/2010; 543 in 2010/2011]. 490 staff are currently receiving training in computer and basic management skills. In addition, a training programme in basic management and reporting targeting 1,200 staff is also being contracted. This will bring the total number of beneficiaries to approximately 5,000.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator | Education Management Information System (EMIS) established and functioning.
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Target (with numbers, where appropriate) | Fully functioning EMIS with comprehensive up-to-date information being regularly used
What progress was made, including numbers | Largely achieved. The HR and Payroll software has now been completed and installed. Over 90% of the examination system has been completed and is undergoing testing. 14 technical flaws/defects have now been addressed and the modified EMIS has been handed over to the Ministry of Education (MoE) team for testing. The consultants will hand over the modified version to MoE in July 2011 once testing has been completed. MIS training for staff at central and governorate levels will commence in the coming months.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 3 | 2
Impact Weighted Score | 22.5
Justification for the Score | Largely achieved. The ongoing political crisis, and resulting violence, power and fuel shortages, has severally constrained progress against this output. The MoE is currently operating reduced hours due to the lack of electricity. However, the Minister remains very supportive of BEDP. While the current Ministerial leadership remains committed to reform, it is unclear whether institutional reform will be a priority for a new or transitional government.
Output 3 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 4
Impact Weighted Score
Justification for the Score
Output 4 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5 | 0
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 5
Impact Weighted Score
Justification for the Score
Output 5 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk |  | 0
0
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk | Low | 3
0
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk |  | 0
0
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk |  | 0
0
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Has the Impact Weight been revised since the last review?
If Yes, why was this?
Current Impact Weight (%)
Has the Risk been revised since the last review?
If Yes, why was this?
Current Risk |  | 0
0
Has the DFID Share been revised since the last review?
If Yes, why was this?
Current DFID Share
Indicator 1 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator
Is this a Standard Indicator?
Select standard indicator from drop down list
Target (with numbers, where appropriate)
What progress was made, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-07-01
Impact Weighting (must = 100) | 100%
Total Impact Score | 67.5 | #VALUE!
Output Risk | Medium | #VALUE!
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review *
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners
DFID staff | X
Donor partners | KFW
Netherlands
World Bank
GTZ
Comment here on the Method of Scoring and Scoring Responsibility. | We had originally planned to carry out a Joint Donor Mission in May/June to assess progress to date and evaluate DFID’s contribution to the Education Sector in Yemen as part of the Project Completion Report (PCR) process. However, due to the deteriorating political and security situation in Yemen a mission was not possible. This desk-based Project Completion Report was completed by the London-based Deputy Programme Manager, with input from the Education and Skills Team Leader and an Education Adviser. The data from this review is based on a) a review of key progress reports, including Previous Annual Reviews 2009/2010 and 2010/11; the Aide Memoire from the last Joint Donor Assessment (October 2010); MoE Narrative and Financial Reports; b) telephone interviews with implementing partners, including the Project Administration Unit (PAU); and c) telephone interviews with donor partners including the World Bank, KfW and the Netherlands.
Scoring Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Donor coordination has been an increasing challenge, particularly over the last year. This has been exacerbated by the withdrawal of many international donor staff from Yemen in recent months. The last Joint Donor review took place in October 2010. Since then, Ministry of Education (MoE) reporting has been infrequent and there has been very little agreed assessment of progress to date. While the donor community has continued to meet virtually to discuss BEDP, these meetings have been ad hoc and have not included key stakeholders in Yemen, such as the Project Administration Unit (PAU) or Ministry of Education (MoE). Remote management severely limits donors' ability to effectively understand the operating environment, make decisions related to project implementation, and to monitor and evaluate programme delivery.
There have been different donor responses to the political unrest in Yemen. While the Netherlands has suspended much of its support to Yemen, including its contribution to BEDP, others such as the World Bank are continuing to monitor the situation and are assessing their options. The World Bank manages a Multi Donor Trust Fund, which includes DFID's contribution to BEDP. While KfW operates independently from the Trust Fund, their disbursement cycle is linked to that of the World Bank and, therefore, no funds have been disbursed to implementing partners since March 2011. The MoE has a role to play in ensuring donor coordination and driving forward progress in the education sector during this period of change.
Working with Partners Recommendation 1 | Donor Partners should agree a coordination mechanism, such as monthly donor meetings to maintain some overview of progress and challenges, and to ensure issues are followed up and resolved. These meetings should include implementing partners and an informal assessment of progress to date.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Working with Partners Recommendation 2 | The PAU should be more proactive in updating donor partners on progress, challenges, and issues which require donor attention. This could take the form of bi-weekly/monthly informal email updates and could include photographs/videos for information.
Working with Partners Recommendation 3 | The MoE should play a greater role in donor coordination, setting a clear framework for donor engagement, and lobbying on issues to drive forward programme delivery.
2. Best Practice / Innovation | The Rural Female Teacher Pilot Project has been a real achievement and innovation from BEDP. 500 female teachers in rural areas have received training and have subsequently been contracted by the Ministry of Civil Service in permanent teaching roles. Prior to this programme there were very few female teachers in rural areas, and those that were employed were largely graduates from large cities. The female teachers were selected from rural communities and had a minimum of a high school diploma. Anecdotal evidence suggests that the presence of female teachers has increased girls' participation in basic education and has provided wider benefits for women’s empowerment and their role in the communities. This project has now been replicated as part of the centrally funded Fast Track Initiative (FTI) and continues to produce impressive results. Previous reviews have highlighted a number of other successful innovations, including the Conditional Cash Transfers Pilot Project and the establishment of a Modernisation Task Force to carry forward key reforms, including restructuring of the MoE.
In order to evaluate DFID’s wider contribution to the education sector in Yemen, and learn lessons which can be shared across DFID's Education cadre, we have received input from an Education Adviser and the Education Policy Team.
Best Practice / Innovation Recommendation 1 | The London-based Deputy Programme Manager will ensure the timely production of a supplementary narrative report by September 2011. This will be circulated to implementing partners and donors for information, as well as informing wider DFID education policy.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
3. Project Management | Staff turnover and lack of expertise have been a consistent project management challenge for DFID and the wider BEDP project team. The lack of internal education expertise available to DFID Yemen weakened DFID Yemen’s ability to engage at a policy level and to drive forward necessary reforms in the Ministry of Education. The PAU has also suffered a number of staff changes in the last year, including specialist staff such as their Procurement Specialist and Technical Coordinator. The loss of these business critical roles, as well as PAU's inability to find suitable qualified replacements, has hampered PAU's ability to undertake core business functions, leading to delays and putting additional stress on incumbent staff.
DFID has disbursed over 90% of its committed £15 million. The project is due to be completed in June 2012, though this is likely to be extended to December 2012 due to delays as a result of the current political situation and financing difficulties. It is anticipated that all outstanding activities will be completed within the remaining 12-18 months. There is, however, a risk to this should the situation become significantly worse.
Project Management Recommendation 1 | The Sana'a-based Project Officer should continue to keep abreast of progress and issues related to the implementation of BEDP despite our formal project management coming to an end. DFID will produce quarterly information notes to update on progress and highlight issues.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Evidence: Key documents
Quest No.
2982416 | BEDP Progress Report - March 2011
2982329 | World Bank Aide Memoire, October 2010
2972145 | BEDP Narrative Reports, October 2010
2601497 | DFID Annual Review 2010 - March 2010
2517491 | Submission - No Cost Extension - January 2010
2517500 | Revised DFID Logframe - January 2010
2517505 | Revised Result Framework - January 2010
Evidence Recommendation 1 | This project completion report is based on a) narrative reports including the October 2010 World Bank Aide Memoire and implementing partner reports; b) telephone interviews with implementing partners including the Project Administration Unit (PAU); and c) telephone interviews with donor partners including the World Bank, KfW and the Netherlands.
If more Recommendations need to be made, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions were attached to this project, was disbursement suspended at any point because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)? | n/a
What were the consequences? | n/a
Conditionality Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Sustainability
Comment on the likelihood of the benefits arising from this project being sustained beyond the end of project, and any challenges to sustainability. | The evolving political situation in Yemen will inevitably have an impact on the sustainability of benefits arising from BEDP. However, the uncertainty over Yemen’s future makes it difficult to assess the likely extent of any impact. Since the beginning of the current civil unrest in early 2011 implementation in a number of areas has slowed or been suspended. As such, it is likely that the project end date will postponed until December 2012 or early 2013. Donors with a history in the sector, including the World Bank and KfW, are keen to continue their support to education in Yemen. Indeed, the World Bank are planning to launch a new Basic Education programme following the conclusion of BEDP. The key factor for sustainability in both the short and long term, however, will be the commitment and will of the Government of Yemen (GoY).
Sustainability Recommendation 1
If more Recommendations need to be made, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3

## E Recommendations
E: Recommendations
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | There is weak evidence to determine whether the national increase in male and female enrolment and retention can be attributed to BEDP. The Comprehensive School Survey (CSS) is essential for measuring progress against Goal and Purpose level targets. DFID has decided to undertake this Project Completion Report (PCR), despite the absence of this data, as we have disbursed over 90% of our overall commitment to BEDP and there is sufficient evidence to evaluate the performance of the project. DFID should continue to push for timely completion of the CSS, now planned for September 2011. The London based Deputy Programme Manager will produce an information note confirming progress against Goal and Purpose level data following publication of the CSS. | Claire Fitzroy
R2 | 0
R3 | 0
A1: Purpose
R1 | The Yemen-based Project Officer should continue to review the status of implementation, producing quarterly information notes to update progress and flag issues to senior management. | Sheikha Bazarah
R2 | 0
R3 | 0
A1: Risk
R1 | Given the deteriorating political, economic and security situation in Yemen, the risk rating needs to be revised to "High". New and emerging risks include increasing costs of implementation due to shortages of fuel and commodities; lack of financial resources to meet contractual obligations; and restrictions on assess due to insecurity. Implementing partners need to ensure sufficient risk management strategies are in place to deal with the evolving context. The London based Deputy Programme Manager will work with donor and implementing partners to be better prepared to mitigate emerging risks. | Claire Fitzroy
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | 0
R1.2 | 0
R1.3 | 0
R2.1 | 0
R2.2 | 0
R2.3 | 0
R3.1 | 0
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Donor Partners should agree a coordination mechanism, such as monthly donor meetings to maintain some overview of progress and challenges, and to ensure issues are followed up and resolved. These meetings should include implementing partners and an informal assessment of progress to date. | Claire Fitzroy
R2 | The PAU should be more proactive in updating donor partners on progress, challenges, and issues which require donor attention. This could take the form of bi-weekly/monthly informal email updates and could include photographs/videos for information. | Claire Fitzroy
R3 | The MoE should play a greater role in donor coordination, setting a clear framework for donor engagement, and lobbying on issues to drive forward programme delivery. | Claire Fitzroy
Best Practice / Innovation
R1 | The London-based Deputy Programme Manager will ensure the timely production of a supplementary narrative report by September 2011. This will be circulated to implementing partners and donors for information, as well as informing wider DFID education policy. | Claire Fitzroy
R2 | 0
R3 | 0
Project Management
R1 | The Sana'a-based Project Officer should continue to keep abreast of progress and issues related to the implementation of BEDP despite our formal project management coming to an end. DFID will produce quarterly information notes to update on progress and highlight issues. | Shiekha Bazarah
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | This project completion report is based on a) narrative reports including the October 2010 World Bank Aide Memoire and implementing partner reports; b) telephone interviews with implementing partners including the Project Administration Unit (PAU); and c) telephone interviews with donor partners including the World Bank, KfW and the Netherlands. | Claire Fitzroy
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3