### Logframe
PROJECT TITLE (max. 50 characters)		Refugees and Internally Displaced People 2009-11
GOAL	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target Dec 2011
Improve the quality of life and reduce the vulnerability of refugees and displaced persons along Burma’s border.	Under 5 mortality rate in Burmese refugee camps in Thailand. / (DFID standard outcome indicator)	5.8 per 1000.	Annual target: / < 8 / 1000	Annual target: / < 8 / 1000	Annual target: / < 8 / 1000
		Source
		CCSDPT Health Information System data for Mortality rates (reported annually). / Annual targets are based on mortality rates for East Asia & Pacific region. An increase to twice the target (16 per 1000) would indicate a significant public health emergency.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target Dec 2011
	Refugee camp residents’ awareness of their rights and satisfaction with the actions taken to protect them.	Knowledge: / Existing camps: 39% know Thai laws apply.		Knowledge: / Existing camps: 44% know Thai laws apply.	Knowledge: / Existing camps: 49% know Thai laws apply.
		Satisfaction: / Existing camps: / 42% Camp Justice / 47% Section Leaders / 29% Thai System / (39% average)	Satisfaction: / Will not be re-measured in 2009. / New camps: NA	Satisfaction: / Existing camps: / Increase average by 5% by 2010 / Baseline established in new camps by Mar 2010	Satisfaction: / Existing camps: / Increase average by 10% / New camps: Increase average by 5%
		Source
		Baseline: IRC Assessment on Protection, Access to Justice and the Rule of Law in camps. Y2: random sampling Y3: Repeat Assessment and Project Evaluation. Collected by IRC Legal Assistance Centre Staff and External Evaluator. / Note: Sex disaggregated targets will be developed in the first 3 months of the project.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target Dec 2011
	Women as a % of refugee camp management. / (Camp Committees, security and other stipend positions).	20% of Refugee Camp Management.	30% of Camp Management.	40% of Camp Management.	50% of Camp Management.

		Source
		Membership records of camp committees. / Project reports from community organisations.

PURPOSE (max. 250 characters)	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011	Assumptions
	Crude mortality rate (CMR) in refugee camps.	3.3 per 1,000 (2008)	Annual target: / < 7 / 1,000.	Annual target: / < 7 / 1,000.	Annual target: / < 7 / 1,000.	RTG Ministry of Interior continues to grant NGO partners access to refugee camps. / Security situation in camps remains stable. / Data on support to IDPs is reliable. / Dramatic reductions in other donors’ contributions to TBBC do not undermine its ability to meet the basic needs of refugees. / Other donors contribute extra support to community-based organisations providing assistance to IDPs. / Refugees and IDPs remain largely isolated from the effects of the global economic downturn.
Meet more of the basic humanitarian needs of Burmese refugees and displaced persons in conflict-affected border areas in Burma.		Source
		CCSDPT Health Information System data for Mortality rates (reported annually). / Annual targets are based on mortality rates for East Asia & Pacific region. An increase to twice the target (14 per 1000) would indicate a significant public health emergency.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
	Children under 5 in refugee camps with wasting malnutrition, as a percentage of the Under 5 camp population.	2.7% (2008)	Annual target: < 5%	Annual target:< 5%	Less than 5%
		Source
		Annual Nutrition Surveys: children 6 months to <5 weight/ height measurements (World Health Organisation (WHO) / NCHS z scores). / CCSDPT Health Information System data: children identified as malnourished from clinic visits or nutrition surveys conducted by the medical agencies.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
	Number of people in communities affected by conflict and displacement benefiting from needs-based humanitarian relief.	14,012 through 6-month village-based community support (2008) / 80,420 people in 343 villages through cash support (2007).	30,000 through village-based community support by 2009 / (DFID share 100%) / 80,000 per year through cash support. / (DFID share 10%)	70,000 through village-based community support by 2010. / (DFID share 80%) / 70,000 per year through cash support. / (DFID share 10%)	125,000 through village-based community mechanisms. / (DFID share 70%) / 70,000 per year through cash support. / (DFID share 10%)
		Source
		Project reports from community organisations. / DFID is working with partners on the detail of this reporting and will investigate new data collection mechanisms within the first six months of the programme.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
	% of cases known to LAC where the justice process and/or outcome observed are in line with internationally recognised human rights, refugee and Thai legal standards.	Existing camps: 16% / New camps – baseline to be measured in 2010.	By end 2009: Existing camps: 20% / New camps: n/a	By end 2010: / Existing camps: 40% / New camps: 10%	Existing camps: 60% / New camps: 30%
		Source
		LAC Database, Hearing monitoring checklists, Detention monitoring checklists, Camp justice reports, UNHCR records. Collected by legal assistance centre staff.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£7,450,000		£76,000,000		9%
INPUTS (HR)	DFID (FTEs)
	0.2 FTE Political Officer (Bangkok). / 0.05 FTE Service Delivery Adviser (Rangoon). / 0.2 FTE Bangkok Liaison Officer.

OUTPUT 1	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011	Assumptions
Delivery of food and relief items to enable refugees to sustain a basic livelihood.	Nutrition: Average no. of kCal per person per day.	2,102 kCal	Annual target / 2,100 kCal	Annual target / 2,100 kCal	Annual target / 2,100 kCal	Other services provided to camp residents (e.g. NGO health services) are sufficient to maintain basic health levels. / No major new policy restrictions on refugee camps or NGO access to them. / Security situation in camps remains stable. / No sudden increases in numbers of refugees eligible for feeding and other support. / No dramatic reductions in other donors’ support to TBBC.
		Source
		Nutritional analysis of standard TBBC ration. / Ration item calculations are based on data from the Institute of Nutrition at Mahidol University, ASEAN Food Composition Tables (2000), and have been updated to accommodate recent changes in commodities. The actual ration may vary slightly between camps, but all variations meet the minimum recommendation. / Target is based on the World Food Programme (WFP)/ UNHCR recommendation for planning rations.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
	Supply & Distribution – Percentage of registered population receiving all components of the food basket as planned. / (Supply & Distribution reconciliation %)	135,623 people receiving rations at end of 2008. / 98.4% received rations as planned (Jul-Dec 08).	132,000 people receiving rations. / Annual target: / 95% receive rations as planned.	132,000 people receiving rations. / Annual target: / 95% receive rations as planned.	132,000 people receiving rations. / Annual target: / 95% receive rations as planned.
		Source
		Monthly monitoring reports, independent inspectors’ reports, acceptance by Camp Committees. The measure takes into account ration calculation, measurement and delivery; use of ration books; and the presence of ration posters, monitoring feedback information and comments post-boxes.
IMPACT WEIGHTING	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
40%	Shelter - Covered space per person (m2).	Average 5.2 m2.	Annual target / 3.5 m2	Annual target / 3.5 m2	Annual target / 3.5 m2
		Source				RISK RATING
		Survey of Households (annual). / Target is the standard set by TBBC for all camps.				Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£2,500,000		£68,000,000	£70,500,000	4%
INPUTS (HR)	DFID (FTEs)
	Not disaggregated

OUTPUT 2	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011	Assumptions
Deliver needs-based humanitarian assistance to people in communities in Burma affected by displacement and conflict.	Number of people directly assisted by food security programmes: / (Standard Indicator #13) / a) Village-based community mechanisms (e.g. rice banks) (cumulative) / b) Cash support (cumulative figures to be developed)	a) Village-based community mechs: 14,012 / (6 month project in 2008).	Village-based: / 30,000 by end of 2009. / (DFID share 100%)	Village-based: / 70,000 by end 2010. / (DFID share 80%)	Village-based: / 125,000 by end of 2011. / (DFID share 70%)	No major changes in the political situation affecting border areas. / Partners continue to be able to access IDP communities. / Activities are carried out with meaningful community involvement in identifying priorities. / Women are given a meaningful role in implementation. / Reliable data can be collected on support to IDPs. / Collection of new baseline data on vulnerable populations. / Other donors contribute extra support to community-based organisations providing assistance to IDPs.
		b) Cash support: / 80,000 in 2008.	80,000 per year / (DFID share 10%)	70,000 per year / (DFID share 10%)	70,000 per year / (DFID share 10%)
		Source
		Project reports from community organisations.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
	Number of new/improved sanitation facilities provided. / (Standard Indicator #9)	1,982 households received materials for flyproof latrine (6 month project in 2008).	4,000 by end of 2009. / (DFID share 100%)	4,000 by end of 2010. / (DFID share 80%)	7,000 by end of 2011. / (DFID share 70%)
		Source
		Project reports from community organisations.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
	Number of households provided with new/improved drinking water sources. / (Standard Indicator #8)	800 in an initial 6 month project.	1,700 by end of 2009. / (DFID share 100%)	6,500 by end of 2010 (cumulative) / (DFID share 80%)	10,000 by end of 2011 (cumulative) / (DFID share 70%)
		Source
		Project reports from community organisations.
IMPACT WEIGHTING	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
35%	Number of families assisted to overcome financial obstacles to primary schooling for their children.	1,926 families in an initial 6 month project.	4,000 families by end of 2009. / (DFID share 100%)	6,000 families by end of 2010. / (DFID share 80%)	10,000 families. / (DFID share 70%)
		Source				RISK RATING
		Project reports from community organisations.				High
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£3,150,000		£7,100,000	£10,250,000	31%
INPUTS (HR)	DFID (FTEs)	Note – further work is planned on the indicators for this output in the first six months of the programme. Existing baselines and projections come from project reports from existing partners.
	Not disaggregated.

OUTPUT 3	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011	Assumptions
Improved access to justice and protection services for refugees living in camps.	% of all appropriate serious crimes reported to the camp justice committee or LAC that are successfully referred (with client consent) to the Thai justice system.	All camps: 12%	By end 2009. / Existing camps: 60% / New camps: NA	By end 2010 / Existing camps: 80% / New camps: 40%	Existing camps: 90% / New camps: 60%	RTG Ministry of Interior continues to grant IRC access to refugee camps along the Thai-Burma border. / Continued willingness of Thai government justice system to take on cases from refugee camps. / Security situation in camps remains stable. / Significant numbers of trained paralegals do not apply for resettlement to third countries (these are currently selected from individuals with no resettlement plans). / Continued engagement of the Ministry of Interior and Ministry of Justice in the development of guidelines. / Camp justice guidelines are produced within six months of the start of the project.
		Source
		LAC Database, Client Satisfaction surveys, Random sampling of camp residents, Focus groups (collected by LAC staff). / External Evaluation (outside evaluator).
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
	Quality guidelines on in-camp administration of justice (reflective of international and Thai legal standards) are understood and implemented in % of cases by camp leadership (e.g. Committee, Security, Justice, Zone and Section) and Thai justice officials.	Guidelines do not exist at project outset.	By end of 2009, LAC / community leadership / Ministry of Interior have developed guidelines ratified by all key justice stakeholders.	By end of 2010, 90% of key justice stakeholders in all sites have attended and passed at least one workshop on Guidelines.	In 80% of observed cases, guidelines are understood and implemented by Camp leadership and Thai justice officials.
		Source
		LAC case management database, Training records, Hearing observation and detention monitoring checklists, Camp justice records / External evaluation/ survey (at least annual). Client satisfaction surveys.
	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
	% of survey respondents indicate that they would report three prominent legal problems (murder, child rape and theft) in a way that reflects camp justice guidelines. / Note – Baseline is based on the presumed outcomes of the guidelines, which are still under development.	Existing camps: / Murder: 10% / Child rape: 9% / Theft: 59% / Average: 26%	Existing camps: / Justice guidelines disseminated to population; milestone not to be measured.	By end of 2010: / Existing camps: / 20% increase on baseline.	Existing camps: / 30% increase from baseline
		New camps: to be established Y2.	New camps: work will start in late 2009. Baseline survey to be done within 6 months.	New camps: Guidelines disseminated; no milestone measure.	New camps: 20% increase on baseline.
		Source
		Baseline survey (to be repeated in new camps within six months of work starting in each camp). External evaluation and repeat survey. Annual random sampling of target population. / IRC Legal Assistance Centre Staff Community survey teams. External evaluator.
IMPACT WEIGHTING	Indicator	Baseline 2008	Milestone 1: 2009	Milestone 2: 2010	Target 2011
25%	% of legal assistance centre functions (training, monitoring, legal service provision and community liaison) assumed by Community paralegals under minimal external supervision, accessible to all camp residents.	Existing camps: 22 Paralegals trained as trainers.	By end of 2009: / Existing camps: Role extended to incorporate detention and hearing monitoring.	By end of 2010: / Existing camps: Paralegal teams are trained in and begin to provide basic legal advice as well as case management in camps.	Existing camps: Paralegals carrying out 70% of LAC functions under minimal external supervision.
		New camps: 0 paralegals operational.	New camps: work will only start in late 2009.	New camps: Paralegal teams recruited, trained and operational as trainers in all sites.	New camps: Role extended to incorporate detention and hearing monitoring, and basic legal advice.
		Source				RISK RATING
		LAC case management database. Training records and pre/ post tests. / Client satisfaction surveys (at least annual).				Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£1,800,000	0	£900,000	£2,700,000	67%
INPUTS (HR)	DFID (FTEs)
	Not disaggregated at output level.