## A1 Goal, Purpose, Risk
Summary Review (reviewed June 2011)
ARIES Project Code | 200274
ARIES Project Description | Deepening Democracy in Nigeria
A1: Purpose, Risk
Purpose
Project Purpose | Advance key political governance processes and structures
Indicator 1 | Quality of elections
Milestone for this review (if any) | "mediocre"
What progress has been made in the period covered by this review? | "Satisfactory". An over-achievement. Elections were better than expected. Generally, the elections reflected the will of the people, which represents a marked improvement over earlier elections in Nigeria. International observers, the "Swift Vote Count" and other civil society monitors support this view. Reasons: Political leadership by the President, an exceptional head of the election management body and strong international support/pressure.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | %satisfaction with democracy (fairly or very satisfied)
Milestone for this review (if any) | 34%
What progress has been made in the period covered by this review? | Very likely to have been met; surpasses in some parts of the country and not fully met in parts of the North. Data will be out around November 2011. The postive conduct of elections will likely lead to an improvement in "Satisfaction with Democracy" (milestone 34%).Election violence changed in nature from culminating during primaries to being very much a post-election issue. Political campaigning moved gradually towards issue/policy based campaigns - although from a low base. Nigeria is at a critical point where elections are more competitive, but potentially also more violent. There were positive indications in the South West and South East parts of the country.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | % women in Parliament
Milestone for this review (if any) | 9%
What progress has been made in the period covered by this review? | Not met. % women in NASS fell to just under 6%. Cultural norms and the brutal and highly monetarised nature of Nigerian party primaries puts women at a disadvantage. The women's lobby and advocacy groups remain weak and driven by elite and personal interests, which are not very effective. International support is still too aligned with standard advocacy and has not found effective ways of encouraging wider groups of women candidates to run an effective campaign.
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Overall, the purpose level assumptions still hold. There has been relatively little real threat to the assumption on constitutional democracy and with the April 2011 elections, this assumption remain fair and realistic. The stability assumption was tested, especially during the days immediately after the presidential elections and in some parts of the country, stability and security remains a challenge. Overall, the magnitude is not a major threat to democracy, but state-level violence can still disrupt participation and engagement in democratic processes. In many cases, violence is supported by politicians; an indication that not all politicians subcribe to acceptable democratic means of campaigning.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | There is significant evidence globally as well as in Africa and Nigeria that better elections, satisfaction with democracy and improved political participation by women play strong roles in terms of improving democratic governance (DDIN's goal). The April 2011 elections are one important milestone towards better governance. Although better elections will not automatically lead to improved democratic governance they are a crucial and necessary condition.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | There is mixed evidence in terms of correlation between outputs and purpose achievements. For some outputs, such as output 1 (INEC), output 4 (Civil Society) and output 5 (international support) there is very strong support. For outputs 2 (National Assembly) and output 3 (political parties) there are some elements with strong correlation (passing the election act and signing the political parties' "code of conduct"). This is not surprising as progress related to elections and some parts of outputs 2 and 3 are less related to elections and more to longer term deepning democracy.
Purpose Recommendation 1 | Overall, the purpose level milestones remain relevant and provide sound strategic focus for DDIN. With the main elections completed, a measured shift would be appropriate - towards addressing deepening democracy challenges (% satisfaction with democracy) and underlying drivers of gender imbalances in politics.
Purpose Action Point 1 | Undertake analysis on issues, drivers and obstacles to democratic transition in Nigeria. Complete the main work by end-2011. The analysis will guide focus and help identify the best partners for future DDIN implementation.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 1 | 1.2
Purpose Justification | Overall, the purpose milestones have been achieved or surpassed, even if women representation remains a major challenge.
Risk
Project Risk Rating or latest Overall Risk Score | High
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability | The elections pose a risk to the project. Strong political will is essential for pushing through tax administration reform and increasing revenue collection
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks? | The Secretary of State has sought assurance from President Karzai that a strong economic team will remain in place after the elections. The office will monitor closely any changes in the Cabinet post-election
Risk Recommendation 1 | On balance risks have decreased although still firmly in the "high" category. Election related violence and no further progress on electoral reform remain the highest risk-factors. If the next 12 months see progress in these areas, the 2013 review should consider lowering the risk rating.
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Strengthen the capacity and independence of INEC
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | There is a mistake in the logframe - the total adds up to more than 100%. The weight for output 1 should be 25%
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
|  | 0.25 | 1. Number of teachers trained
DFID Share revised/needs revision? | No |  | 2. Number of classrooms constructed or rehabilitated
If Yes, why was/is this? |  | 1 | 3. Number of health professionals trained
Original or Revised DFID Share | 28% | 2 | 4. Number of one year olds vaccinated against measles
|  | 3 | 5. Number of insecticide treated bed nets distributed
Indicator 1 (leave blank if standard indicator) | % commissioners and %senior management in INEC substantively appointed | 4 | 6. Number of people with advanced HIV infection receiving ARVs
Is this a Standard Indicator? | No | 5 | 7. Number of condoms distributed
Select standard indicator from drop down list |  | 0 | 8. Number households provided with new/improved drinking water sources
Milestone for this review (including number, if any) | 50% (commissioners) and 60% (senior management). |  | 9. Number of new/improved sanitation facilities provided
Progress made in the period covered by this review, including numbers | Over-achieved. All 13 commissioner are in place. Two are up for replacement in August and no names have been formally put forward yet. Of 15 INEC core senior management (director) positions 14 are in place, although a number are on temporary promotion. Overall, This milestone has been surpassed.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet |  |  | 12. Number of households provided with new/improved access to basic electricity supply
Indicator 2 (leave blank if standard indicator) | % Implementation of recommendations from UK/US independent mission report |  | 13. Number of people directly assisted by food security programmes
Is this a Standard Indicator? | No |  | 14. Number of people directly assisted by social assistance programmes
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 30% of recommendations implemented.
Progress made in the period covered by this review, including numbers | Over-achieved. Around 70% of the recommendations have been taken on-board and all major election-related recommendations were addressed (parallel vote tabulation, voter register, new INEC chair, election policing).
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Quality and effectiveness of relationship between INEC and political parties and CSOs (proxi, scale 1-5 where 1 is poor and 5 is excellent)
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 1
Progress made in the period covered by this review, including numbers | Over-achieved. INEC worked closely and effectively with CSOs. The work political parties got better as election approached, but that relationship remains complicated. The signing of the political parties code of conduct was however an indication of progress.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 1 | 1
Impact Weighted Score | 25 | 0.25
Justification for the Score | INEC's capacity to deliver increased massively once prof. Jega was appointed. In turn this enabled donor support to be much more effective and constructive. As DFID, we can take credit for much; we supported and pushed Jega in innovative ways at crucial moments.
Output 1 Recommendation 1 | Based on INEC's upcoming review, support to INEC should be further deepened. Future support should be carefully targetted strategic areas where DFID has a comparative advantage (either directly or through intermediaries such as IFES)
Output 1 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Better functioning National Assembly
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | There is a mistake in the logframe - the total adds up to more than 100%. The weight for output 2 should be 20%
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 32%
Indicator 1 (leave blank if standard indicator) | Number of Parliamentary Committees with approved strategic plans
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 4
Progress made in the period covered by this review, including numbers | Over-achieved. 5 committees in the House of Reps and another 5 have basic strategic plans in place. The Speaker of the House has a strategic plan and another 10 committees have scetchy plans (which do not qualify as real plans)
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of substantive legislation passed by the NASS (same bill, both Chambers)
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 2
Progress made in the period covered by this review, including numbers | 5, over-achieved. Partly due to last-minute incentives within the NASS, but good progress nevertheless.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Quality and effectiveness of interactions between NASS and CSOs/public/Media
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 2 (qualitatative assessment on a scale of 1-5)
Progress made in the period covered by this review, including numbers | Score 3. Over-achieved. Civil society engagement with NASS has improved (although from a low base). Engagement around the election act revision and the Constitutional amendments were particularly good.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 1 | 1
Impact Weighted Score | 20 | 0.2
Justification for the Score
Output 2 Recommendation 1 | Carefully explore new opportunities in working with the NASS. It is still too early to tell if the NASS will be a genuine driver of reform, but the potential is much higher than during the 2007-11 NASS.
Output 2 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Better functioning Political Parties, incl. women representation
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | There is a mistake in the logframe - the total adds up to more than 100%. The weight for output 3 should be 20%
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 40%
Indicator 1 (leave blank if standard indicator) | Number of political parties with approved manifestos, code of conduct and audited accounts
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | No milestone. The baseline was 0.
Progress made in the period covered by this review, including numbers | The main 5 parties all have manifestoes and codes of conduct. That better than expected and reflect the nascent Only 1 party has submitted audited accounts.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of IPAC/ PPRRC sessions undertaken (with participation from at least 80% of the 5 major parties)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 5
Progress made in the period covered by this review, including numbers | 8, i.e. an overachievement. 3 of the meetings were directly related to the "code of conduct" for political parties during elections.
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 2 | 0.75
Impact Weighted Score | 15 | 0.15
Justification for the Score
Output 3 Recommendation 1 | Political parties showed early signs of responding to a more demanding electorate. Going ahead, DDIN should explore possibilities to influence and accelerate this trend.
Output 3 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Strengthen the role of civil society organisations and Media in promoting and protecting democratic processes
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 43%
Indicator 1 (leave blank if standard indicator) | Number of professionally executed opinion surveys published
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 6
Progress made in the period covered by this review, including numbers | 6 sound surveys, + another 4-5, where actual methodology/professionalism was hard to assess (and survey results differed significantly from the eventual election result).
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of community radio stations licensed and operational
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 2
Progress made in the period covered by this review, including numbers | 3. The main progress in this area is less about a third community radio station being operational, but rather that the broadcasting act has been revised such that community radio stations are now much easier to setup.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Number of people trained/sensitised on elections, rights and responsibilities
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any) | No milestone.
Progress made in the period covered by this review, including numbers | Good progress has been made in this area - better than expected in terms of the electorate protecting their vote (in the South) and still ground to cover in the North (where better voter education would likely have prevented some of the violence. The swift count (where we training 8000 observers) lay the foundation for a more credible results transmission process.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | Quality and effectiveness of CSO work to promote democratic processes (scale 1-5, 1=bad, 5=excellent)
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 2
Progress made in the period covered by this review, including numbers | Score 3. Over-achieved. Key parts of civil society played a crucial role before and during the 2011 elections. The situation room was key and the social media tracking centre helped prevent violence and improve communication from INEC.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 1 | 1
Impact Weighted Score | 25 | 0.25
Justification for the Score | Overall, civil society performed better than expected and achieved better results during the review period.
Output 4 Recommendation 1 | DFID need to work with CSOs to build on the successes achieved during the elections while not undermining credibility. Secondly, more work is required on voter education in northern Nigeria.
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5 | Policy support and coordination maximised
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 10%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.2
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 100%
Indicator 1 (leave blank if standard indicator) | Quality and effectiveness of international community and donor messages on elections and deepening democracy issues (score 1=bad, 5=excellent).
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 3
Progress made in the period covered by this review, including numbers | 3. Overall coordination between the UK, US and EC was excellent. Wider coordination on messaging was also good (incl. Canada, Germany and France). Development aid was well-coordinated within the US/UK work and partly within the UN-led basket, although the lack of sound leadership within the UN basket at times impacted on coordination of technical aid.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Debate on international and African perspectives on best elections and deepening democracy practices
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 2 high-level engagements.
Progress made in the period covered by this review, including numbers | 4 (2 with NDI, Joe Clark, and 2 with UNDP, Afari-Gyan). This was backed up by other bilateral visits (not paid for by DFID), such as Johnnie Carson (US) and Ron Gould (Canada)
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 5 | 1 | 1
Impact Weighted Score | 10 | 0.1
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision? |  |  | 1. Number of teachers trained
If Yes, why was/is this? |  |  | 2. Number of classrooms constructed or rehabilitated
Original or Revised DFID Share |  |  | 3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
Indicator 1 (leave blank if standard indicator) |  |  | 5. Number of insecticide treated bed nets distributed
Is this a Standard Indicator? |  |  | 6. Number of people with advanced HIV infection receiving ARVs
Select standard indicator from drop down list |  |  | 7. Number of condoms distributed
Milestone for this review (including number, if any) |  |  | 8. Number households provided with new/improved drinking water sources
Progress made in the period covered by this review, including numbers |  |  | 9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet |  |  | 11. Total length of roads maintained or rehabilitated
Indicator 2 (leave blank if standard indicator) |  |  | 12. Number of households provided with new/improved access to basic electricity supply
Is this a Standard Indicator? |  |  | 13. Number of people directly assisted by food security programmes
Select standard indicator from drop down list |  |  | 14. Number of people directly assisted by social assistance programmes
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-06-26
Impact Weighting (must = 100) | 100%
Total Impact Score | 95 | 0.95
Output Risk | High | 1.75
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner | X
National non-Government partner | X
Independent consultant
Donor partners | X
DFID staff | X
Donor partners | USAID (incl. IFES, NDI, IRI)
EU
Comment here on the Method of Scoring and Scoring Responsibility | Scoring responsibility: DDIN lead adviser (Jens-Peter Dyrbak), in consultation with the DDIN programme officer (Odumu Ebegonye). Method: Assessment of progress against milestones back up by qualitative assessments of outputs status.
Scoring Recommendation 1 | 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Working with the US and Nigerian partners worked well. Mutual respect was easily built and positions were understood. Working with UNDP was time-consuming and often not strategic. Roles and comparative advantages were not easily identified and understood.
Working with Partners Recommendation 1 | Be (brutally) honest when deciding on partners and think carefully about capacity and areas of mutual interests.
Working with Partners Action Point 1 | Consider not working through the UN basket.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | The DDIN board added real value, both to the programme as such, but also in terms of identifying and capitalising on political opportunities (identified at the technical level). The strategic component helped to make crucial events happen such as the "Election Situation Room" and the Wangonet/social media centre even if transaction costs were high. On balance, the strategic fund enabled us to test potential "gamechangers" without running major fiduciary risks.
Best Practice / Innovation Recommendation 1
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | USAID provided strong and detailed information on interventions. The UN basket less so. Both were lacking in terms of systematic, relevant strategic information, which had to be identified by the lead adviser. DFID/HMG is clearly unique in terms of links between technical and political interventions and ability to identify and implement crucial strategic opportunities. This should be kept in mind when designing the next phase of DDIN.
Project Management Recommendation 1 | Looking ahead, project management should cover three areas: 1) Sound, flexible, management. 2) provide updates on strategic opportunities/issues, 3) provide an avenue to explore strategic opportunity at minimum transaction costs (to DFID and partners)
Project Management Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
Key issues, points of information or additional comments that may be useful for this or other project teams
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
Evidence Recommendation 1 | The logframe needs minor revision in terms of correcting weights and establishing milestones for the 2 indicators where these are missing. DFID should also explore the possibility of establishing an indicator on wider democratic transition (possibly using randomised control tests etc).
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality
D: Conditionality
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Purpose
R1 | Overall, the purpose level milestones remain relevant and provide sound strategic focus for DDIN. With the main elections completed, a measured shift would be appropriate - towards addressing deepening democracy challenges (% satisfaction with democracy) and underlying drivers of gender imbalances in politics. | JPD, Odumu (Julius, Richard, FCO backup)
R2 | 0
R3 | 0
A1: Risk
R1 | On balance risks have decreased although still firmly in the "high" category. Election related violence and no further progress on electoral reform remain the highest risk-factors. If the next 12 months see progress in these areas, the 2013 review should consider lowering the risk rating. | JPD, Odumu
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Based on INEC's upcoming review, support to INEC should be further deepened. Future support should be carefully targetted strategic areas where DFID has a comparative advantage (either directly or through intermediaries such as IFES) | JPD
R1.2 | 0 | JPD
R1.3 | 0
R2.1 | Carefully explore new opportunities in working with the NASS. It is still too early to tell if the NASS will be a genuine driver of reform, but the potential is much higher than during the 2007-11 NASS. | JPD
R2.2 | 0
R2.3 | 0
R3.1 | Political parties showed early signs of responding to a more demanding electorate. Going ahead, DDIN should explore possibilities to influence and accelerate this trend. | JPD
R3.2 | 0
R3.3 | 0
R4.1 | DFID need to work with CSOs to build on the successes achieved during the elections while not undermining credibility. Secondly, more work is required on voter education in northern Nigeria. | JPD
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 1
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Be (brutally) honest when deciding on partners and think carefully about capacity and areas of mutual interests. | JPD, DDIN board
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | 0
R2 | 0
R3 | 0
Project Management
R1 | Looking ahead, project management should cover three areas: 1) Sound, flexible, management. 2) provide updates on strategic opportunities/issues, 3) provide an avenue to explore strategic opportunity at minimum transaction costs (to DFID and partners) | JPD, Odumu
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | The logframe needs minor revision in terms of correcting weights and establishing milestones for the 2 indicators where these are missing. DFID should also explore the possibility of establishing an indicator on wider democratic transition (possibly using randomised control tests etc). | JPD
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Purpose
AP1.1 | Undertake analysis on issues, drivers and obstacles to democratic transition in Nigeria. Complete the main work by end-2011. The analysis will guide focus and help identify the best partners for future DDIN implementation. | JPD
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
AP2.1 | 0
AP2.2 | 0
AP2.3 | 0
AP3.1 | 0
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Consider not working through the UN basket.
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3