Annual Review – post April 2018
Title: Multisector Humanitarian Response Programme (MHRP)
Programme Value £ (full life): £90 million		Review Date: 18/05/2018
Programme Code: 300046	Start Date: 01/04/2017	End Date: 31/03/2020

Summary of Programme Performance
Year	2017/18	2018/19	2019/20
Programme Score	B
Risk Rating	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300046/documents

A. Summary and Overview (1-2 pages)
Description of programme
Yemen is the world’s largest humanitarian crisis. Currently, 17.8 million people are food-insecure or malnourished, with 8.4 million severely food insecure and at risk of starvation. The year 2017 has seen a significant scale up of World Food Programme (WFP) global food assistance, reaching millions of beneficiaries. In its extended Emergency Operation Plan (EMOP), WFP aims to reach 7.6m beneficiaries with food assistance every month, out of the 8.4m who were identified in need of food assistance by the Humanitarian Needs Overview of December 2017. This leaves 800,000 beneficiaries who remain to be assisted every month by other members of the food security cluster, such as MHRP partners.
In spite of this large food assistance programme, the Humanitarian Needs Overview of December 2017 showed that if the number of people in need of food assistance had marginally increased from the previous year, the number of people in acute need of food assistance has increased by 24% from March 2017. In late 2017, the Food Security, Nutrition, Health, and Water, Sanitation and Hygiene (WASH) clusters came up with a list of 107 priority districts where famine risk is the highest and where integration of the four cluster activities is highly recommended in order to avert famine. The MHRP pursues the same goal to assist beneficiaries in hard to reach areas with a mix of integrated WASH/Health/Nutrition and Food Security assistance. This programme is innovative in its attempt to implement cash transfers in remote and sensitive parts of Yemen. At the time of reporting, WFP had not yet launched its cash transfer programme and social protection activities are far from adequately covering needs both in terms of beneficiaries and in terms of cash amounts transferred. MHRP therefore remains a key funding instrument, allowing DFID Yemen to lower the risk of famine in pockets of extreme food security. It does this through two components:
1. Improving access to food for the most vulnerable, through conditional (e.g. cash for work) and unconditional cash and voucher assistance.
2. Treating and addressing the underlying causes of acute malnutrition through an integrated multi-sectoral approach[1] covering: Nutrition; Water, Sanitation and Hygiene (WASH); and Health activities.
  [1] The term multisector refers to beneficiaries receiving assistance in more than one sector (e.g WASH and Health). The term integrated means that the each multisector activity is working towards the same overarching objective
The programme is delivered directly through International and National Non-Governmental Organisations (INGOs and NNGOs) and is designed to complement large-scale UN programmes by providing quality programming to some of the most vulnerable conflict-affected groups in hard to reach areas of Yemen.
Partners comprise: Oxfam; Save the Children; CARE International in consortium with Action Against Hunger (ACF), Mercy Corps (MC) and Norwegian Refugee Council (NRC); and ACTED in consortium with ADRA, Yemen Family Care Association (YFCA), and Humanity and Inclusion[2] (HI).
[2] Formerly Handicap International, as referred to in the business case and all reports prior to December 2017.
Summary supporting narrative for the overall score in this review
This Annual Review assesses performance over the first three quarters of the programme. Progress in the final quarter of year one is referred to, and significant results anticipated, but only officially reported after completion of this review. As such, the scoring reflects the evidence provided for April 2017 to December 2017.
The programme faced multiple setbacks at its inception. The resulting delay in delivering activities has meant results up to quarter three were off track. The snap UK 2017 elections delayed approval for the full business case and instead four months pre approval was awarded, allowing partners to proceed with delivering lifesaving assistance, whilst the business case was going through full approval. Unfortunately the ensuing temporary accountable grants agreements were deemed insufficient by local authorities to grant implementing partners access. In July the full grant agreements were awarded, however, partners spent a further 3-6 months negotiating access, delaying the expected implementation timeframe considerably. At the time of writing, a couple of locations still face access constraints and multiple changes to location have been approved. Internal constraints such as high staff turnover may have contributed to these external factors, for example seven out of the ten partners have seen new Country Directors arrive within the last year. Established Country Director relationships with authorities facilitate more timely local authority agreements, which are time consuming and hard to negotiate. The more complex multisector consortia have suffered the most severe delays. In a consortium one partner’s access constraints can undermine the additional benefits of an integrated response, and the basis on which the programme is designed. Staff capacity and experience has affected partners’ ability to deliver their targets. The three multisector components (45% of the programme) have scored Cs. As a result additional oversight measures will be introduced as detailed below. By the end of quarter three both consortia were in stronger positions regarding access, and progress will be monitored closely over the first two quarters of year two.
Within these operating constraints, this programme has had some notable successes in the cash transfer component, which scored a B (50% of the programme). In recent communications, both Oxfam and Save the Children have confirmed they were able to deliver and exceed their full cash programmes by the end of the full year. This has demonstrated their adaptability and ability to scale up to reach more beneficiaries as set out in the programme’s objectives. However, they too experienced delays at the start which is reflected in the quarter three score. In order to maximise the amount of cash received by the beneficiaries, DFID engaged with all partners to negotiate a Yemeni Rial (YER) exchange rate resulting in savings of over 33%. This was reinvested into the programme, either through additional rounds to existing beneficiaries, or by adding new beneficiaries, significantly improving the value for money.
Recommendations for the year ahead
- The biggest challenge to this programme has been local authority permissions.
  - Partners should coordinate as a team and with the UN to support each other in strengthening local partnerships and securing permissions. Where one partner has good local relationships, they should support the negotiations of other partners where possible. They can also seek support from the relevant cluster lead.
  - DFID Yemen must continue to work with consortium members to understand the cause of access constraints and work with counterparts such as the United Nations Office for the Coordination of Humanitarian Affairs (UN OCHA) and UN agencies to try and unlock some of the barriers. DFID should use its relationships with larger UN implementers to support other partners to secure access.
  - Partners should draw up shared/joint contingency plans / scenario plans for access issues. This would allow partners to move more quickly from one scenario to another, based on the access constraints faced, with clear timeframes for negotiations, with partners moving locations if access is not achieved, or other such issues persist. DFID’s flexibility in this should be maintained.
- Moreover consortia are struggling to deliver the integrated multi-sector responses as initially planned. If by the end of September 2018 this is still failing to deliver, DFID will reassess the design of this programme. Options include:
  - Individual MHRP partners providing the full package of WASH, Health, Nutrition activities altogether (and Food Security where relevant / plausible), rather than as a consortium.
  - DFID explore new partnerships, with those with a recent record of success in delivery.
  - In the worst case scenario, DFID terminates the implementation of Component 2 (Health, WASH and Nutrition) of this programme and scales up conditional and unconditional cash and voucher transfer programmes (Component 1), for which access has been more forthcoming.
To monitor this, additional oversight measures will be introduced for the ACTED and CARE Consortia. Performance targets will be agreed over the next month with progress assessed at monthly meetings with DFID. Monthly progress meetings will include updates on access constraints and actions taken; detailed scrutiny of forecasts and budgets; evidence of regular coordination meetings within consortia as well as all MHRP partners in Sana’a.
- All partners’ reporting must be strengthened. Inconsistencies between the logframe and reports and financial discrepancies have consistently been seen. Any changes proposed to the logframe, must be discussed and approved in writing by DFID, and sufficient consideration of potential impacts on value for money, theory of change and risk demonstrated. Payment schedules will return to dispersal in the quarter activities are delivered, based on three month forecasts, until improved financial reporting is seen.
- Partners need to approach programming with greater realism in planning - factoring in realistic inception periods at the start of the programme and ensuring optimism bias is factored throughout. This programme focusses on hard to reach areas, and as such we recommend building in a level of tolerance to allow the bureaucratic impediments restraining delivery to be negotiated. This should be factored in to future geographic changes or new activity streams. In addition DFID and partners need to work more closely to ensure information from DFID, including grants, are presented in a format that will aid and not hinder local authority permit granting.
- Staffing has remained a key area for concern. Organisations have suffered high levels of staff turnover and vacancy rates, in particular with 7 new Country Directors within the last year. Both CARE and ACTED have had significant issues in hiring staff, including key positions dedicated for this programme. Whilst some have now been filled it is critical that staffing gaps are addressed urgently including forward resource planning.
- Partners need stronger dialogue amongst each other; within the consortia; between partner country teams and headquarters; as well as with DFID. DFID expect to see evidence of improved coordination by partners, including through meetings outside of the DFID roundtables at least quarterly over the coming year. Consortia, especially, need to be more cohesive to enable successful delivery of combined objectives. This should be helped by recent appointments of consortium managers. In order to capture the success of integration, partners should develop a single outcome indicator on multi-sector assistance.
- Partners should remain aware of critical economic issues. They should continue to engage with the Cash and Market Working Group and the Liquidity and Currency Sub Working Group to monitor the market exchange rate, and utilise savings to maximise impact and value for money of the programme.
- Gender, disability, protection and conflict sensitivity remain patchy across partners. Greater consistency and meaningful consideration of these areas within programme design, implementation and monitoring is needed, as well as sharing of analysis and best practice. It is recommended that there is more direct interaction between partners and DFID Yemen cross-cutting advisers and that these issues are considered in depth at the next quarterly meeting.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)
All outputs are assessed against targets up to quarter three (31 December 2017). Annual targets have been pro-rated to two thirds of the full target, recognising that the first quarter would involve additional preparations, rather than delivery. Pro-rated targets are marked with a *.

Output Title	Men, women, girls and boys access basic food requirements in the form of unconditional cash transfers (UCT), vouchers, or cash for work
Output number per LF	1	Output Score	B
Impact weighting (%):	50	Impact weighting % revised since last AR?	No

Indicators	Partner	Milestones for Q1-Q3	Progress for Q1-Q3	Comments
Number of unconditional cash transfers of / minimum food basket	Oxfam	29,626	27,022	Slippage met in Q4.
	Save the Children	26,886	26,886	Met
	CARE Consortium	29,972*	4,943	Not met - significant increase in Q4 confirmed
	ACTED Consortium	12,970	0	No Year one delivery.
	TOTAL	99,454	58,851	Not Met
Number of cash for work / of minimum food basket	Oxfam	1,950	1,300	Slippage met in Q4.
	CARE Consortium	2,226*	125	Not met - increase in Q4 confirmed
	ACTED Consortium	N/A	N/A	In agreement with DFID, This activity was cancelled for Year I of the project. It will be resumed in Year 2.
	TOTAL	4,176	1,425	Not Met

Provide supporting narrative for the score
This output aims to improve access to food for the most vulnerable, through conditional and unconditional cash and voucher assistance. Overall this output has scored a B. As detailed in the summary, since the outset partners have found it hard to get activities up and running. Two partners (Oxfam and Save the Children) have performed well from quarter two and by quarter four will have overachieved on their original targets. The two consortia have struggled to catch up from inception delays and although significant increases are anticipated from CARE in quarter four, quarter three is significantly below target.
Following import restrictions imposed from November 2017, and subsequent severe spikes in food costs, DFID reached out to all partners offering flexibility to their response. Oxfam, Save the Children, and the CARE Consortium (NRC) were able to deliver a double round of cash transfers in December. These ensured partners were both able to meet the increased costs of the staple foods, as well as provide a small safety net anticipating access could deteriorate further into the new year and limit or delay access for January transfers. In addition, both Save the Children and Oxfam were awarded top-ups in year one to deliver a combined additional 26,362 Unconditional Cash Transfers (UCT), by the end of year one. These were all planned to be delivered in quarter four. This flexibility was welcomed by all partners.
Unconditional cash transfers remain feasible and beneficiary feedback continues to demonstrate that this is the preferred transfer modality when compared to in-kind food distributions or food commodity vouchers. Recommendations from the 2016 third party monitoring report (Tazeez) were taken on board, and implemented throughout this programme, further strengthening accountability to affected populations, beneficiary selection criteria, and accuracy of data collection.
Oxfam delivers both UCTs and a small number of Cash for Work (CFW) interventions. Oxfam experienced initial delays including access constraints in the districts of Al-Taizia; Mawiyah; and Sharab ar Rawnah. As a result it expanded to two new districts in Taiz. From July, Oxfam has performed well delivering UCTs, and secured a top up to reach 11,681 households with two additional rounds of UCTs (to be delivered in the fourth quarter). Of these beneficiaries, 2,100 were new households in Amran. The remaining additional rounds were existing beneficiaries. This top up was designed as bridge funding whilst Oxfam looked to secure additional funding from other donors to maintain the intervention, and continue their support to these beneficiaries. Whilst the outreach and support to these beneficiaries is critical in itself, securing this additional funding will be an important metric for the success of this top up (to be discussed in the next quarterly meeting). 40% of unconditional cash transfers targeted female headed households.
Through cash for work (CFW) Oxfam has supported 650 people with short term income generation and employment opportunities on selected community projects. CFW beneficiaries targeted both women and men, with 30% of workers being women. The interventions made contributions towards rehabilitating and improving community assets and infrastructure to support the recovery process. This included: latrine construction for IDPs; rehabilitation of open dug wells; road rehabilitation; construction and maintenance of houses; trenching for water pipes; amongst other activities.
Save the Children has successfully delivered UCTs since August 2017. Despite the escalation of the Yemen conflict and the operational challenges all the planned activities to date were successfully completed. In quarter four, Save the Children was awarded a top-up to reach additional 3,000 households with 6 rounds (first round took place in March 2018).
Alongside the traditional delivery mechanism of cash transfers, Save the Children used funds to pilot innovative mobile transfers (Mfloos). During the first three months of the pilot, 151 recipients had enrolled in this service. High satisfaction levels and the many advantages of using the mobile money transfer has attracted more beneficiaries to enrol for the mobile money transfer service, enabling beneficiaries to access cash assistance on the move. By the end of quarter three an additional 738 households enrolled on the Mfloos service, bringing the total to 889 households using the service to receive their cash transfers. The lessons learned and advantages of this approach have been shared with all MHRP partners, and Save the Children has offered to continue to share these lessons in country, with others possibly looking to replicate where appropriate and viable.
Save the Children have also implemented effective measures to drive forward gender sensitive programming: 33% of households were female headed and a total of 51% of beneficiaries were women. Effective reporting on disability has also made Save the Children’s programming stand out (see output 5 for more detail).
The CARE Consortium, working through CARE, Mercy Corps and NRC has struggled to deliver cash transfers. At the very end of quarter three CARE and NRC launched their cash activities in Ash Shamaytayn and Al Mawasit Districts of Taiz. NRC reached 1,548 households with two rounds of UCTs, about 50% of their intended quarter three target. They are expected to meet their target by the end of year one. CARE reached 1,972 households with one round, though this accounted for just 13% of their intended target. Cash for Work activities also started at the end of the third quarter, with 125 recipients receiving cash for rehabilitation of rural to market roads. 43.74% of conditional and unconditional cash transfer beneficiaries are female-headed households.
Mercy Corps and CARE had planned to deliver some in-kind food baskets, but in agreement with DFID, these were changed to UCTs to be delivered in quarter four. This change follows practicalities in procurement with a lack of eligible vendors within the targeted areas in Taiz. DFID agreed this approach and preferences cash as the modality of intervention where viable, in line with our humanitarian strategy, and globally recognised best practice.
Within the ACTED Consortium only ACTED provide cash support. By the end of the third quarter no activities had been delivered under this output. Whilst they are working in some of the hard to access areas, and this remains the principle constraint, this is also is in part due to the staff capacity and recruitment challenges. The lack of cash delivery undermines the consortium’s approach to integrate both component 1 and 2 of this programme. Access has continued to play a constraining factor in quarter four and ACTED are not expected to deliver against this output by the end of the year.
One success regarding this output is around the exchange rate and increasing value for money (see value for money (VFM) section for more detail). At the start of the programme the official rate of 250 Yemeni Rial (YER) to the USD was in use. Through close work between DFID’s Economic Adviser, the Cash and Market Working Group (CMWG), and the banking sector, partners were able to gradually negotiate significantly better rates, within 10% of the market rate eg 370 YER to the USD (Sept 2017). This led to an instant savings of up to 33% on all cash related activities. These savings were channelled directly back to the communities, through additional rounds of transfers, increased amounts, and/or reaching additional beneficiaries.
Whilst the YER has continued to devalue, partners have responded and adjusted their exchange rates. At the time of writing this report the exchange rate was around 485 YER to the USD. Any direct effect of the depreciation (or other factors) on beneficiaries such as spikes in food prices and their ability to afford the minimum food basked are monitored through the CMWG. All partners use the rates recommended by this group. Food availability and food prices are monitored by WFP across the 22 governorates with monthly updates shared with donors (Yemen Market Situation Reports). This monitoring includes a system of Alert for Price Spikes (ALPS) and allows regular updates by the Food Security and Agriculture Cluster (FSAC) of the estimated value of the household minimum food consumption basket. Since the start of the programme, MHRP partners have aligned their cash transfer assistance to FSAC guidance, as a key lesson learnt from the predecessor programme.
Lessons identified this year, and recommendations for the year ahead linked to this output
- There remains significant optimism bias regarding what can be achieved and how quickly, especially evident in the consortia. This programme focusses on hard to reach areas as such building in more time to manage the bureaucratic impediments causing the access constraints would be prudent. This should be factored in to future geographic changes or new activity streams.
- Joint/shared contingency plans around access constraints should be built into the planning to improve efficiency of the programme delivery; alternative districts identified and timeframes set out for decision points. Where partners have had district changes approved, a plan for revisiting access potential to original districts should be addressed. This may include assessments that other implementers have preferential access arrangements and feed into gap analysis. There is the risk that hardest to reach districts, and potentially most in need, never receive the support they require, taking away from this programmes objectives: to support hard to reach populations and the most vulnerable.
- Partners need to do more on gap analysis and stronger coordination internally and within the food security cluster. Reporting against this to DFID should also be strengthened in the quarterly reports. Whilst coordination amongst MHRP partners is reported against, more should be developed regarding how well partners are working with other cash programmes including: WFP; UNICEF (SWF); other NGOs; and World Bank funding.
- DFID is currently supporting OCHA to strengthen the Cash and Market Working Group (CMWG). It is essential that cash based programmes, either multi-purpose (e.g. ACTED) or specific to the minimum food basket (e.g. Oxfam and Save the Children), implemented under MHRP are closely coordinated through this revamped CMWG with coverage data and beneficiary lists shared as appropriate. Whilst Oxfam co-chairs the working group, it is essential that others maintain their active engagement. It is equally important that partners work with both the CMWG and the FSAC to ensure their recommendations align.
- Post distribution monitoring conducted by Oxfam and Save the Children has demonstrated that delivering cash to vulnerable households is attaining its objective with immediate positive outcomes. This is encouraging and cash transfer programming must be further supported. Save the Children monitoring has shown however that positive food security outcomes are short-lived and that where cash transfers had to be postponed due to access constraints (e.g. Taiz governorate) gains were rapidly lost. It is therefore essential that partners look at medium term solutions building the resilience of targeted vulnerable households, avoiding creating dependence on regular humanitarian assistance. Therefore, in line with the Humanitarian Response Plan 2018, where applicable we will support a progressive switch from UCT to more conditional cash transfer programmes such as CFW, primarily related to the protection of community livelihood assets and strengthening community resilience. Moreover, partners should commit to identify exit strategies, where possible, in the course of this 3-year programme.
- Mobile transfers are a viable and increasingly popular model for cash distribution, with the potential for further improved VFM, as well as safeguarding benefits. In other contexts where mobile transfer technology has been developed (e.g. Horn of Africa) it has been demonstrated that this transfer modality contributes to the protection of beneficiaries in the sense that no-one in a given community (e.g. IDP camp) would know who received a cash transfer, when and for which amount. Whilst the lessons and results of the pilot need further analysis and consideration, this should be further encouraged and developed, including by other partners where viable and sustainable.
Programme flexibility – DFID’s flexibility in supporting partners has been key to resolving issues, and should be maintained where possible. This has included the support for double distributions, increases, changes to locations; and modality changes.

Output Title	Pregnant or lactating women and children are screened and treated for acute malnutrition in targeted areas.
Output number per LF	2	Output Score	C
Impact weighting (%):	15	Impact weighting % revised since last AR?	No

Indicator(s)	Partner	Milestone(s) for this review (Q1-Q3)	Progress (Q1 – Q3)	Comments
# of malnourished U5 children (girls & boys) treated for severe acute malnutrition (SAM)[3].	CARE Consortium	1,220*	273	Off Track
	ACTED Consortium	1,980	205	Off track
	TOTAL	3,200	478	Not met
# of U5 children (girls and boys) treated for moderate acute malnutrition. (MAM)[4]	CARE Consortium	3,708	523	Off track
	ACTED Consortium	10,100	460	Off track
	TOTAL	13,808	983	Not met
# of pregnant and lactating women treated for acute malnutrition.	CARE Consortium	940	356	On track
	ACTED Consortium	2,475	234	Off track
	TOTAL	3,415	590	Not met
[3] Severe acute malnutrition (SAM) is the most extreme form of malnutrition, where cases fall below 70% of the national median weight for the height. It poses the greatest risk to life.
[4] Moderate acute malnutrition (MAM) is where cases fall between 71% and 79% of the national median weight for the height. Without treatment, cases can quickly fall from MAM to SAM.

Provide supporting narrative for the score
As part of the integrated approach this output screens and treats pregnant or lactating women and children for acute malnutrition in targeted areas. This output has scored a C. By the end of quarter three it had failed to meet even 25% of its targets. This poor result is a consequence of the consortia activities only starting at the end of quarter three.
The CARE Consortium delivers this output through ACF and Mercy Corps. Due to staff turnover on top of local authority access constraints, Mercy Corps had failed to deliver any results by the end of quarter three. By the end of December 2017, ACF had rehabilitated 5 health facilities out of 11 targeted in Al Thuhayta and Al Garahj districts of Hudaydah governorate. Four were made functional allowing ACF to reach a total of 2,787 cases with health/nutrition interventions, including the treatment of 273 Severe Acute Malnutrition (SAM) children <5 years. One stabilisation centre set up by ACF in Al Thuhayta town treated 273 severe acute malnourished children with medical complications. The cure rate was 95%, with a low defaulter rate of 3.72%, and only 1.06% deaths, all well within international standards[5].
[5] Internationally recognised SPHERE guidance sets out the minimum standards in humanitarian responses. SPHERE recommends a cure rate of >75%, default rate of <15%, and a death rate of <10%)
Where local authority access issues were resolved, the number of beneficiaries remained low as patients and staff struggled to reach the health facilities, and medical supplies could not be brought in. Much of this was linked directly to the deteriorating security and access constraints following the increased import restrictions from November onwards. No ACF staff were able to access health facilities in December, but some activities continued through Ministry of Health staff. No funds were ever transferred to the Ministry of Health, however local staff received direct cash incentives, and amounts were agreed at the cluster level and with the Ministry and apply to all agencies. Significant activity has taken place in quarter four, and although a year one shortfall is still expected, we anticipate substantial improvements against targets for the full 12 month period.
The ACTED Consortium delivers this output through ADRA and YFCA. After a very late start, ADRA and YFCA were able to establish 10 treatment centres for malnutrition between October and December 2017; 3 in Al Dhale’e, 4 in Sa’ada, and 3 in Al Jawf governorates. Additionally, one centre for children suffering severe acute malnutrition was established in Juban hospital, in Juban district of Al Dhale’e governorate. Treatment centres were selected in close coordination with the respective health authorities.
As such a limited number of beneficiaries could be provided with screening and treated for malnutrition. Children identified as acutely malnourished through the screening were all enrolled in the treatment programme and provided with specialist food supplements. Information on infant and young child feeding was provided through pamphlets and information sessions to pregnant or lactating women and mothers of under-five children suffering from malnutrition. Weekly follow-up for the cases was also undertaken by the community mobilisers to ensure a low default rate. By the end of the third quarter the SAM treatment results showed: 77% (cured); 0 (dead); and 26% (default). While the cure rate matches recommended international standards, the default rate seems abnormally high and needs to be looked at with ADRA and YFCA in Year 2.
It is expected that by the end of the year, ADRA and YFCA will have made good progress against these outputs, though there will still be a shortfall from the original targets.
Lessons identified this year, and recommendations for the year ahead linked to this output
- The consortia approach to an integrated multi-sector response to address the root causes of acute malnutrition still remains to be proven effective. While the approach looks right on paper and partners have the technical capacity to deliver the programme as planned, bureaucratic impediments - affecting the wider humanitarian community in Yemen, NGO and UN alike – were probably underestimated by the two consortium lead agencies and have resulted in serious delays. As in output one – but to a greater degree with the more complex components of the programme – partners need to be much more realistic about factoring in set-up time into work plans and budgets.
- The consortia should operate as a coordinated and complementary group to benefit from the capabilities that each brings. Consortia still struggling to deliver the integrated responses as initially planned should consider:
  - Switching approach so that, where feasible, each consortium member commits to cover all sectors: WASH, health and nutrition in the priority districts in which they have secured access (i.e. currently multiple partners aim to operate in each district for different sectors). This would not need to, but could include the food security component.
  - Terminating the implementation of the multi-sector component and scale up the cash component.
- Coordination within and between consortia/partners should also be enhanced with best practices shared, and lessons learned. The quarterly round tables hosted by DFID have helped this, but more is needed on a regular basis and independent of DFID. The hiring of consortia managers should assist in this.
- Partners have claimed that due to increased demand on supplies, stemming from the prioritisation of malnutrition treatment carried out through the World Food Programme, some of the districts targeted by the ACTED programme suffered a shortage of the therapeutic food required to treat the large number of enrolled cases. Whilst the severity of the issue is disputed, it is clear better coordination is required through the nutrition cluster to ensure buffer stocks or alternative sources exist to reduce the risk of such constraints happening again.
- Due to the low number of SAM and Moderate Acute Malnutrition (MAM) referrals in Al Dhale’e and Sa’ada governorates, ACTED foresees that the majority of the cash transfer beneficiaries will be selected through local beneficiary selection committees. This is largely due to the late start of nutrition activities as well as the need to clarify referral procedures adapted to each context so as to avoid additional burden on nutrition teams, as well as remove any incentive to have malnourished children (in the hope of being selected as a cash beneficiary). YFCA and ACTED will need to work closely together to determine the best selection processes that can be developed for year 2.
- Where patients and staff are struggling to reach the health facilities, and medical supplies cannot be brought in partners should be exploring other options, e.g. transport vouchers, mobile clinics, and should coordinate closely with UNICEF on these.

Output Title	Women, men, girls and boys access primary health services in targeted areas.
Output number per LF		3	Output Score	C
Impact weighting (%):		15	Impact weighting % revised since last AR?	No

Provide supporting narrative for the score
Indicator(s)	Partner	Milestone(s) for this review (Q1-Q3)	Progress (Q1 – Q3)	Comments
# of children under 5 received Primary Health Care Services	CARE Consortium	3,112	1,155
	ACTED Consortium	12,979	3,238
	TOTAL	16,091	4,393	Not Met
# of women provided with Ante and/or postnatal care	CARE Consortium	1,026	480
	ACTED Consortium	1,160	785
	TOTAL	2,186	1,265	Not Met
# of consultation provided with medical teams and outreach services	ACTED Consortium	38,591*	12,720
	TOTAL	38,591*	12,720	Not Met

This output aims to increase access to primary health services in targeted areas. Overall this output has been scored a C. Achievement has also been lower than targeted due to the same reasons presented throughout this annual review and specifically in output 2.
The CARE Consortium delivers this output through ACF and Mercy Corps. Both partners aimed to provide access to medical support for under-fives, focusing on common childhood illnesses, and antenatal and post-natal care consultations for pregnant and lactating women. By the end of quarter three, Mercy Corps had not started any activities.
Out of the 11 health centres targeted for rehabilitation by ACF in Hudaydah district, five health facilities were rehabilitated, of which 4 (1 in Al Thuhayta and 3 in Al Garahj) had started delivering Mother and Child Healthcare services in quarter three, including 480 antenatal and postnatal consultations as well as 1,155 child consultations applying Integrated Management of Childhood Illness (IMCI) protocols[6]. Local staff based at district level was hired in close proximity to the health facilities to minimise movements in the area, and to avoid further access issues.
[6] Integrated Management of Childhood Illness (IMCI) is an integrated approach to child health that focuses on the well-being of the whole child. IMCI aims to reduce death, illness and disability, and to promote improved growth and development among children under five years of age. IMCI includes both preventive and curative elements that are implemented by families and communities as well as by health facilities.
The ACTED Consortium delivers this output through ADRA and YFCA. During the reporting period YFCA established seven mobile medical teams in Al Dhale’e and four in Sa’ada governorate. By the end of December, YFCA mobile teams had provided childhood illness support to 2,812 children in these governorates. Services provided included antimalarial treatment, deworming, diarrheal treatment, vitamin supplements, pneumonia treatment and Vaccination. Moreover, preventive care services were provided to 2,966 women during the reporting period.
Regarding Al Jawf governorate, ADRA established two outreach teams in the health facilities in Al Hazm and in Barat Alanan districts. By the end of December, ADRA medical teams had provided integrated health and nutrition assistance to 4,108 cases in Al Hazm and 3,811 in Barat Alanan.
Lessons identified this year, and recommendations for the year ahead linked to this output
See output 2 – the consortium approach to integrated multi-sector response to root causes of acute malnutrition still remains to be proven effective. If there are no visible improvements in the way the integrated approach is delivered, it will need to be reconsidered.

Output Title	Women, men, girls and boys access safe drinking water as well as improved hygiene and sanitation environment in targeted areas.
Output number per LF		4	Output Score	C
Impact weighting (%):		15	Impact weighting % revised since last AR?	No

Indicators	Partner	Milestones for this review (Q1-Q3)	Progress (Q1 – Q3)	Comments
Water provision, where the unit delivered is 15L per person per day or 1,350L per person per quarter.	ACTED Consortium	2,333*	0
	TOTAL	2,333*	0	Not Met
Number of beneficiaries with access to safe water	CARE Consortium	22,251*	8,001
	TOTAL	22,251*	8,001	Not Met
# of individuals (including women, elderly & persons with disability) receiving hygiene kits	CARE Consortium	37,567*	0
	ACTED Consortium	4,500	0
	TOTAL	42,067	0	Not Met
% of beneficiaries (including women, elderly & persons with disability) that demonstrate awareness of safe hygiene practices (i.e can state at least three key hygiene & sanitation messages retained from their training.)	CARE Consortium	60%	N/A	To be measured in Q4
	ACTED Consortium	80%	N/A	To be measured in Q4
	TOTAL	70%	N/A

# Provide supporting narrative for the score
This output aims to provide access to safe drinking water through water provision as well as an improved hygiene and sanitation environment in targeted areas. This output has scored a C. Very little had been delivered against indicators 4.1 and 4.2 by the end of December 2017. 4.3 will only be measured at quarter four although awareness sessions have taken place.
The CARE Consortium delivers this output through CARE, ACF, NRC and Mercy Corps. Water provision through water-trucking was carried out in in Al-Hali and provided water to 8,100 persons. This activity is a continuation from a previous programme where water tanks had already been installed. DFID agreed to carry over the activity as part of the cholera response under this programme. Procurement processes for 3 well rehabilitation schemes are also ongoing to provide safe drinking water for 1,500 persons.
Safe hygiene practices have been promoted by 83 community volunteers (52 females and 31 males) in Ash Shamayateen district. Three training sessions were organized for community volunteers on nutrition/hygiene messaging so that they conduct the nutrition/hygiene promotion sessions effectively. Topics included: hygiene promotion (water purification methods, personal hygiene, prevention of diarrhoea causes, solid and liquid garbage disposal); planning and reporting. The community volunteers conducted 396 awareness sessions through house-to-house visits, school based sessions and community campaigns.
The ACTED Consortium delivers this output through ACTED. Whilst the project was accepted at the national level, major delays occurred in approval and signing of the Memorandum of Understanding (MoU) at the governorate level which hindered progress on this output. Without the MoU, field teams were unable to start community assessments, or implementation. Given the shortened period available for the implementation of activities as well as the guidance from the WASH Cluster encouraging unconditional cash for water in this period of limited access to fuel, ACTED removed water trucking and tank construction from year one of the project. Instead, ACTED asked DFID to switch from the FSAC value of the minimum food basket for cash transfer to the value of the minimum expenditure basket (MEB), as recommended by the Cash and Market Monitoring working group. MEB includes the coverage of household needs in trucked safe water. The scaled down WASH interventions for year one aimed to focus on completion of the most needed rehabilitation work. Despite DFID’s flexibility in responding to these constraints, ACTED still failed to deliver against both the revised and original targets.
Lessons identified this year, and recommendations for the year ahead linked to this output:
- Where one consortium partner is unable to deliver a particular activity they should look to see if there is another partner in the consortium who could successfully implement it. For example: ACTED should have looked to other partners in the consortium to see if they were able to successfully implement the WASH activities in districts where they were already delivering health and nutrition. ADRA, potentially, could have undertaken these activities as they are implementing multisector programmes (including WASH) in the same governorate (different districts) with other donor funding. Failing that they could have looked into other organisations delivering WASH activities in the same districts to support the overall programme objectives
- The indicators, whilst agreed and selected by partners, need to be revisited in terms of how they are reported against, due to inconsistency from partner to partner.

Output Title	Effective delivery of programme: delivering VFM, Protection mainstreaming and an inclusive response.
Output number per LF		5	Output Score	B
Impact weighting (%):		5	Impact weighting % revised since last AR?	No

Indicator(s)	Partner	Milestone(s) for this review (Q1-Q3)	Progress
% of beneficiaries (disaggregated by sex, age and disability) reporting that humanitarian assistance is delivered in a safe manner.	Oxfam	100%	100%
	Save the Children	100%	98%
	CARE Consortium	75%	To be measured in Q4
	ACTED Consortium	80%	To be measured in Q4
% of beneficiaries (disaggregated by sex, age and disability) reporting that humanitarian assistance is delivered in an accessible manner.	Oxfam	100%	100%
	Save the Children	100%	98%
	CARE Consortium	75%	To be measured in Q4
	ACTED Consortium	80%	To be measured in Q4
% of beneficiaries (disaggregated by sex, age and disability) reporting that humanitarian assistance is delivered in a participatory manner	Oxfam	100%	100%
	Save the Children	100%	62%
	CARE Consortium	75%	To be measured in Q4
	ACTED Consortium	80%	To be measured in Q4
# of feedback/complaints received (disaggregated by sex and age)	Oxfam	N/A	1565
	Save the Children	N/A	952
	CARE Consortium	N/A	To be measured in Q4
	ACTED Consortium	0	To be measured in Q4
% of feedback/complaints received which have been timely* acted upon (disaggregated by sex and age) / ^timely - to be justified in the narrative report	Oxfam	100%	100%
	Save the Children	100%	Data missing
	CARE Consortium	100%	To be measured in Q4
	ACTED Consortium	85%	To be measured in Q4
Ratio: Value of cash delivered / total operational cost of UCT delivery	Oxfam	Data missing	To be measured in Q4
	Save the Children	4:5	To be measured in Q4
	CARE Consortium	4:5	To be measured in Q4
	ACTED Consortium	Data missing	To be measured in Q4

Provide supporting narrative for the score
This output measures the overall effective delivery of the programme including consideration of value for money (VFM), protection mainstreaming and an inclusive response. Overall this output has scored a B. Where data is available targets have largely been met. However, a significant amount of data will only be available with quarter four reporting. For Output 5.3, the percentage of beneficiaries reporting that humanitarian assistance is delivered in a participatory manner, the outlier is Save reporting only 62%. More work is needed to understand this low performing score and will be analysed at the next quarterly meeting. 5.6, the VFM indicator, will be assessed on receiving quarter four reports.
MHRP partners are committed to mainstreaming cross cutting issues (gender sensitivity, conflict sensitivity, protection mainstreaming and disability) within the programme activities. Regular interaction with DFID has ensured that these issues are maintained and strengthened throughout the programme. Partners have continued to report against these core issues through their quarterly reports.
The recent conflict escalation in 2017 has complicated humanitarian access, and working in these areas without exacerbating conflict and, in turn, mitigating the negative impact of conflict dynamics on programmes has been challenging. Below summarises partners’ approaches to cross-cutting issues during the first year of the programme.
Gender sensitivity
Partners’ quarterly reports and the discussions held with the programme team show that the differing needs of men, women, boys and girls, have been adequately considered in the programme response. Beneficiaries/households were selected through robust vulnerability criteria, including some targeting of female headed households. Beneficiary verification mechanisms showed that this was working well. Community projects were designed by all partners to meet needs of the vulnerable groups, particularly the women and children.
Save the Children used their new Gender Equality Marker Score Card to review how gender sensitive the DFID project is. The final score was C - some gender equality components had been integrated, and a good foundation to build from, but not currently enough to meet Save the Children’s essential standard of gender sensitivity. This shows that more can be done.
This programme is taking steps to advance from gender inclusion, to shifting gender norms and improving women’s participation in society. For example, partners have ensured meaningful representation of women in the community committees (CARE: 48%, Oxfam: 43%, Save the Children: 36%). Partners conducted community mobilisation and sensitisation sessions, and training for men and women. These sessions aimed to ensure communities understood project interventions, beneficiary selection criteria and project modalities, feedback and complaints processes, and to promote female decision making at community level. Cash for work activities have also been designed to encourage female participation. For example, Oxfam set the daily wage at four hours allowing time for women to undertake work alongside their other responsibilities. Their activities included rehabilitation of house fencing for poor families, which improved the protection and privacy for female household members.
Conflict Sensitivity[7]
[7] Conflict sensitivity means understanding the context in which one is operating, understanding the interaction between ones engagement and the context, and taking action to avoid negative impacts and maximise positive impacts on conflict and stability.
Conflict sensitivity has continued to be considered, as demonstrated in the quarterly reporting by all partners. ACTED and Save the Children have both conducted a conflict analyses. The CARE consortium are contracting the peacebuilding INGO, Search for Common Ground (SFCG), for specialist conflict sensitivity technical support. This reflects a welcome prioritisation of the issue. The technical support comprises: conflict assessments; advice on programme adaptation; and building the CARE consortium staff capacity for conflict-sensitive programming and implementation. This support has been delayed and currently expected to be undertaken during the first half of year two. The findings are to be shared not only across the consortium, but also with the wider partners across this programme, maximising VFM, strengthening coordination, and ensuring the maximum impact on conflict sensitive programming.
Most partners have focussed their analyses on the conflict dynamics in their targeted locations. A greater focus on the interaction of partners’ projects with the conflict should be taken forward in year two followed by a demonstration of how programmes have adapted as a consequence. It is also recommended Oxfam undertake a conflict analysis.
Protection mainstreaming[8]
[8] Protection mainstreaming is the process of incorporating protection principles and promoting meaningful access, safety and dignity in humanitarian aid.
Each partner has their own approach to ensuring the needs of the most vulnerable are considered throughout the programme. Save the Children, Oxfam, and the CARE consortium all have in-house expertise dedicated to this, whilst the ACTED consortium have brought on board Humanity and Inclusion (HI), formerly Handicap International, to take the lead on providing technical support to partners to ensure the integration of inclusion principles and protection mainstreaming throughout the project cycle.
All partners have sought to ensure that protection is mainstreamed at all project stages. This has included (though is not limited to): prioritisation of the most vulnerable people and marginalized groups in the targeting process, selection of safe sites for cash distribution, nutrition and WASH activities designed to ensure safety and privacy, risk assessments and mitigation measures during the implementation including the mitigation of harassment or sexual exploitation; and sharing project information with the community.
Oxfam was also able during 2017 to train members’ committees on protection mainstreaming and community self-protection. Its aim was to enhance the understanding of the community through its representatives on the key protection issues. In the reporting period, a protection officer was engaged in the targeting process of UCT, identification and implementation of CFW schemes and cash distribution.
Disability
Disability is one of the key cross cutting areas where partners are behind where DFID would like to see more progress. It is recommended as a focus area with partners next year. One of the good practices by all partners is ensuring elderly and disabled beneficiaries can fast-track queues. Partners also have people living with disabilities as one of the beneficiary selection criteria. Save the Children have also updated their post distribution monitoring questionnaires to capture disability status of beneficiaries, and ACTED already capture this. Neither CARE nor Oxfam capture this, and will need to do so in year two.
Lessons identified this year, and recommendations for the year ahead linked to this output
- Logframe indicators under this output should be reviewed and refined and agreed by the next quarterly meeting, with clearer parameters, and more standardised targets, as well as reporting requirements.
- Protection mainstreaming by Humanity and Inclusion is mostly on track but serves a programme which was still not delivering by the end of quarter three. The next phase will be key and effective implementation will need to be closely monitored with lessons learnt ideally transposed to the other consortium (CARE), and partners.
- CARE has contracted Search for Common Ground (SFCG) - an international organisation based in Yemen - to provide technical support on conflict sensitivity programming. The consortium will partner with SFCG for conflict assessments and conflict sensitivity mainstreaming and build capacity for conflict sensitive programming and implementation. CARE are committed to share lessons on conflict sensitive programming widely. Other partners should consider their staffing set up with regards to Conflict Sensitivity. We also recommend Oxfam undertake a specific conflict analysis with regards to this programme, as soon as is possible. All analysis needs to focus on how the programme itself interacts with the conflict. We will expect to see more tangible adaptation as a result from the analyses in year 2.
- Greater direct interaction between partners and DFID Yemen cross-cutting advisers will ensure that a more regular, and technical conversation can ensure meaningful progress across these areas.
- More work must be taken forward across the cross cutting issues, especially with regard to disability, which lacks in both technical and policy expertise at both partner and DFID Yemen level. Bringing in support, within DFID and partners, to see how this can be taken forward would be a good next step.
- On gender – we would also like to see Save the Children conduct a follow up assessment using its own gender marker tool, to assess the progress from their last C. It would be good to see other partners take the initiative to conduct similar self-assessments.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The above diagram sets out DFID Yemen’s overarching theory of change, across its programmes. The boxes highlighted in red, indicate the relevant theory of change for this programme.
There are no major changes to this portfolio level theory of change. Within this the above assessed programme outputs continue to work towards:
- Impact:	Vulnerabilities of people affected by the conflict in Yemen are identified and reduced, prioritising the most vulnerable
- Outcomes	- Food security of targeted conflict-affected families and their children is improved.
      - Improved access to humanitarian assistance through essential nutrition, health and WASH services reduces acute malnutrition among vulnerable conflict affected communities.

The steps to achieve these outcomes remain valid with no new evidence which challenges the programme design or rationale. The theory of change works on the assumption that security and access were maintained. There have been peaks in the year where this has not held true - for example the import restrictions at the end of 2017. As demonstrated throughout this review, access has been the biggest single constraint to the delivery of this programme. Significant administrative obstructions still exist which prevented most partners operating in the first half of the year. However, by the end of quarter three, all partners were able to sign MoUs with local authorities to start implementation. As such we conclude the theory of change logic, supporting evidence and assumptions still hold for the next year of this programme. It is recommended that over the coming months a tailored theory of change for this programme is developed in order to really explore the assumptions.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The impact and outcome indicators are measured annually and thus were not reported against at quarter three.
IMPACT	Impact Indicator 1
Vulnerabilities of people affected by the conflict in Yemen is identified and reduced, prioritising the most vulnerable	Average (mean) Coping Strategy Index score
OUTCOME 1	Outcome Indicator 1
Food security of targeted conflict-affected families and their children is improved.	Food Consumption Scores: % of targeted vulnerable households which have a food secure (> 42) Household Food Consumption Score (FCS )
OUTCOME 2	Outcome Indicator 2
Improved access to humanitarian assistance through essential nutrition, health and WASH services reduces acute malnutrition among vulnerable conflict affected communities.	GAM[9]/SAM Rates / (disaggregated by Governorate)
	Nutrition severity score (disaggregated by district)
	# of individuals (including women, elderly & persons with disability) reached with an integrated package of support of Health, WASH and nutrition activities
[9] Global Acute Malnutrition (GAM) is the presence of both MAM and SAM in a population.

At outcome level, results will be affected as partners were not able to deliver planned activities as detailed in the output section. Partners have taken contingency actions, approved by DFID, such as relocation and re-programming. Partners have been unable to fully populate targets for the impact and outcome level, and this is to be urgently addressed at the next quarterly meeting. One of the issues faced is that partners cannot meaningfully report against GAM/SAM rates, due the sensitivities in collecting data. As such, neither baselines nor targets could be set. We have kept the indicator in the logframe, in the hope that progress on this is made.
Outcome 1: Oxfam and Save the Children were able to deliver on their cash outputs, and by the end of the year it is expected CARE will have made significant progress towards their target. As such we expect that this outcome is broadly on track. Post distribution monitoring conducted by Oxfam and Save the Children has reported immediate positive outcomes from beneficiary households in terms of food consumption score and household diet diversity index.
Outcome 2: By the end of year one both ACTED and CARE Consortia will have delivered some of their activities with regards to WASH, Health and Nutrition. However despite DFID flexibility, both consortium have yet to demonstrate their ability to implement an integrated approach. The lack of integrated approach is a key reason why it has been concluded that the programme is off track to contribute to the second expected outcome.
Explain major changes to the logframe in the past year
The logframe reflects the results expected under the business case with the following changes:
- Milestones and targets were increased to account for changes in the currency exchange rate
- Milestones for Oxfam and Save the Children (for quarter four onwards) were increased to reflect the additional results expected from the ‘top up funds’
- A series of indicators were added under output 5 to better measure cross cutting issues. These changes provide DFID with improved oversight and will ensure that equitable access is a key factor of programme delivery. They will be revisited again following this report.
DFID has worked with partners to strengthen monitoring tools by ensuring that partners harmonise indicators where appropriate and to provide additional data on the quantities and frequency of cash transfers. Partners have all agreed to shift from just measuring number of beneficiaries in cash transfers to number of cash transfers directly, as well as recording the number of new households. This allows DFID to better account for variations in the number of rounds of distributions provided by different partner models, identify the number of unique beneficiaries, the amount of cash distributed and the average amounts of cash received.
Describe any planned changes to the logframe as a result of this review
One area that is missing from the logframe is a suitable single outcome indicator that measures the effective outcome of an integrated multisector response. Whilst we still resort to individual outcomes for WASH, health and nutrition, we should continue to encourage partners to come up with a suitable outcome indicator to measure the integrated nature of the interventions. In the meantime partners are required to measure the number of beneficiaries receiving assistance under all three sectors.
Output targets for year two will be reviewed taking into account constraints in year one and any agreed changes to activities. Output 5 indicators and targets are to be further refined, and where possible have both targets and reporting on them harmonised across partners. No other major changes to the logframe are anticipated at this stage.
## D: VALUE FOR MONEY (1-2 pages)
Assess VFM compared to the proposition in the Business Case, based on the past year
This review is based on the analysis of MHRP partners’ quarterly reports covering the first 9 months of a 3-year programme. Implementation delays and limited progress against targets has constrained the value for money aspirations set out in the business case. Operational overheads have continued regardless of delays to planned activities, thus increasing output costs. However the added burden of operational constraints has been partially offset by substantial savings on the YER exchange rate enabling both more beneficiaries to be met, and/or beneficiaries to receive more per pound spent.
Output 5.6 measures the cost of delivering cash. This will be reviewed on receipt of quarter four reports. Assessment will be made on consistency of costs across partners and any cost drivers causing the discrepancies. Following from this analysis specific recommendations on VFM will be discussed with partners.
Whilst results to date have been low, this was mirrored in spend. For the 9 months up until the end of December only £6.4 million GBP had been spent (out of the £22 million GBP originally planned for 12 months). Both a significant increase in spend rate, and in results are expected across the final quarter of the year.
#### Economy
One of the main successes in this programme to date has been the delivery of unconditional and conditional cash transfers. By the time of this report both Oxfam and Save the Children were demonstrating satisfactory ability to implement cash transfer programmes, even at times of heightened conflict, constrained access and severe import restrictions. As a result both Save the Children and Oxfam secured top ups towards the end of the first year. Due to the nature of cash transfers the additional beneficiaries were reached with only marginal increases to the administrative costs, thus increasing the ratio of cash delivered to beneficiaries vs administrative costs, improving the economy of scale of the programme.
All partners started this programme using the Central Bank of Yemen’s official exchange rate of 250 YER to USD. This rate was considerably lower than the market rate being used widely across Yemen. DFID worked with banking officials and the programme partners to secure significantly better exchange rates more reflective of the market rate. By September 2017 all partners were using 350+YER / 1USD. This meant that for every cash transfer delivery, partners were able to make savings of over 33%. The savings was then reinvested into the programme either with beneficiaries receiving additional rounds, or new beneficiaries being added, increasing our impact for the same cost. It also allowed partners to increase the amount of the cash transfers from 24,000 YER to 29,500 YER (in line with the cluster recommendation), with no additional cost to DFID. Since then the market has shifted, and the devaluing of the YER has remained a key issue for partners. Partners have remained alive to this, and adjusted their exchange rates. At the time of writing this report the exchange rate was around 485 YER to the USD.
On nutrition, DFID support to UNICEF and WFP supply pipelines, ensured that consortium partners did not have to procure nutrition products themselves. This demonstrates effective, complementary cross-programme coordination and ensures the best price is negotiated.
Efficiency
The business case made the assumption that as all NGO partners have an existing response in the selected governorates, access would be easier to attain and the programme could start-up relatively quickly. This turned out to be far from the truth. Partners require local authority permissions for each project they undertake. Administrative obstructions delayed these permissions. Other bureaucratic constraints included slow applications for visas. Compounded with delays in hiring local and international staff and security access restrictions due to conflict, this programme struggled to get off the ground. As a result more human resource and time were required to address these challenges making it hard to demonstrate that it has been an efficient year for the programme. Whilst we accept that partners had to go through a difficult process to sign MoUs with local authorities, all partners should use lessons learnt from the first year of the programme to both factor in a sufficient inception period in future projects but also for starting new activities as part of this programme.
Moreover, the assumption that there are increased efficiencies by working as a consortium and sharing some of the cross-cutting costs has been undermined by the lack of coordination and integration to date. This arrangement needs to demonstrably improve over the coming year to justify the continuation of this consortia model.
One successful area of efficiency is with regards to Save the Children’s piloting of mobile cash transfers. This innovate approach has allowed for beneficiaries to access cash on the move, reducing the time required both by beneficiaries, and by Save the Children. Scaling this up has the potential to further reduce costs, and increase accountability.
Effectiveness:
Effectiveness of the programme is measured through output 5. This includes a combination of indicators including beneficiary satisfaction, effective delivery of VFM, protection mainstreaming and an inclusive response. Many of these indicators will not be fully reported on until quarter four and as a result the output has scored a B. The slow start by all partners has clearly reduced the effectiveness of the programme. Under the cash component post distribution monitoring systematically showed quick, positive food security outcomes as a result of unconditional cash transfers. This effective way of addressing food insecurity (component 1) however needs to be strengthened through additional work on household economic security (resilience) as of Year 2. Conditional cash transfers (cash for work) and linkage to revived social protection networks are some of the options currently considered.
The delay in the launch of component 2’s integrated activities does not allow us to fully assess whether this approach is effective in containing and curbing the prevalence of acute malnutrition. Moreover, the assumption that there is enhanced beneficiary impact from multisector interventions has also been undermined by the lack of coordination and integration to date. At this stage it is hard to see the effectiveness of the proposed integrated responses coming into fruition – progress will be reviewed again in 6 months.
Equity
All project proposals were assessed against their consideration of gender and vulnerable groups as well as protection mainstreaming. Specific details were covered in the business case and progress has been monitored during the first year of the programme (see output 5). Quarterly reports included data disaggregated by sex and age, reporting that humanitarian assistance is delivered in a safe manner. It will be important to strengthen the programme with regards to equity and access for the most vulnerable – including disabled people. Refer to output 5 for further details and recommendations.
Cost Effectiveness:
During the call for proposal assessment stage, NGO project proposals were scored against a set of criteria, including VFM. NGOs provided DFID with their costs by component. Analysis was done on trends of cost per beneficiaries for the different interventions. The ongoing conflict and the economic crisis, in addition to the bureaucratic impediments, causing delays and re-selection of targeted areas, all had implications on partners’ budgets. For example, in December we saw an increase in costs for fuel, food, and other in kind goods. DFID offered additional flexibility during this period to all partners to assist continued delivery where possible. Excessive variances (over 15%) in budget lines have been challenged by DFID and explanations and approval sought.
Explain whether and why the programme should continue from a VFM perspective, based on its own merits and in the context of the wider portfolio
This programme was designed to complement the larger UN programmes and add value to the DFID humanitarian portfolio by targeting hard to reach areas. It therefore remains relevant in that it proposes to assist beneficiaries in hard to reach areas with a mix of integrated WASH/health/nutrition and food security assistance. This programme also remains innovative in its attempt to implement conditional and unconditional cash transfers in remote and sensitive parts of Yemen.
At the time of reporting, WFP has not yet launched its cash transfer programme and social protection activities are far from adequately covering needs both in terms of beneficiaries and in terms of cash amounts transferred. MHRP therefore remains a key funding instrument, allowing DFID Yemen to lower the risk of famine in pockets of extreme food security.
This review is based on the first 9 months of a 3-year programme. Given the delays in implementation evidence is limited on examples of VFM. There is evidence that the 9 month point has been a turning point in which nearly all activities were able to start delivering. It is recommended that progress – especially on component 2 – is reviewed in six months to assess progress and effectiveness. If it is not able to demonstrate this sufficiently, against the case set out in the business case, it is recommended that the programme considers the following three options:
1. The programme reduces to focus solely on the food security component (component 1).
2. In addition to component 1, the multi sectoral integrated response is delivered only by partners with the capacity and ability to deliver all sectors: WASH; health; and nutrition activities in the same districts.
3. New partnership options are explored with organisations demonstrating existing access.

E: RISK (½ to 1 page)
Overall risk rating: Major
The overall risk of the programme remains major.
Overview of programme risk
Yemen is widely considered one of the most challenging working environments for humanitarian workers. As well as the risks directly related to the conflict such as airstrikes, crossfire and other violence - there have also been instances of kidnapping, which calls for extreme precaution around the movement of international humanitarian workers across the country. As a result international staff movements are often confined to offices and guesthouses, mostly in Sana’a and Aden cities, resulting in limited direct interaction with key stakeholders across the governorates. The 2016 Operational Peer Review recommendation to develop humanitarian hubs in Aden, Mukalla, Sada’a, Hudaydah and Ibb/Taiz was broadly implemented and the year 2017 has seen the development of area Humanitarian Country Teams, area Humanitarian Access Working Groups and area security management teams. This did not translate in the deployment of international staff to hubs to the extent we had expected. This posture reduces security-related issues, but limits local first-hand INGO capacity to assess, plan, negotiate and monitor and therefore higher reliance on national staff to implement those key functions.
The period under review was marked by a series of offensives, which have rapidly stalled, affecting large urban centres including Aden, Taiz and Sana’a. Overall, NGOs were not targeted and very few indirect damage (airstrikes, looting, crossfire) was reported. Ironically, given this context of protracted conflict with unpredictable spikes of violence, partners’ biggest obstruction has been from bureaucratic impediments, constraining their access to districts and sub-districts for the conduct of needs assessments, the provision of assistance and the conduct of standard monitoring activities. The period under review saw a very worrying trend in both the north and south of Yemen where bureaucratic impediments have increased from programme inception.
MHRP cash transfer activities were affected by risks identified in the business case, especially obstruction by authorities. To some extent, this was a result of DFID Yemen encouraging our partners to target hard to reach areas in line with programme objectives, but was also affected by partner staff turnover and insufficient planning for an inception stage. As a consequence, geo-targeting had to be adjusted after access was denied by local authorities e.g. Oxfam was denied access to Al Taizia, Mawiyah and Sharab ar Rawnah districts of Taiz governorate. Where access was granted eventually, Oxfam and Save the Children have demonstrated that risks associated with the implementation of cash transfers in hard to reach areas were well identified and understood at the design and approval stage and were properly managed and mitigated, allowing very encouraging positive early food security outcomes.
MHRP partners have to provide an update on their understanding of risk, its management and mitigation measures in their quarterly narrative reports. Updated partners’ risk matrixes are systematically reviewed during quarterly meetings in Amman. Some of the key risks regularly monitored included: fiduciary risks, such as the risk of aid diversion, fraud and corruption; operational risks, such as partner capacity to deliver effectively; delivery risks, such as consortium coordination ensuring effective delivery in targeted locations. Enhanced due diligence assessments were undertaken on all partners during the year which included assessing these risks and specifically the risk of fraud. DFID will continue to work with all partners to strengthen the control environment and maintain a manageable level of risk. In particular we will put in place enhanced oversight arrangements to minimise the risk of further delivery delays.
The overall risk of this project remains high, as it involves operations in an active conflict environment specifically targeting hard to reach areas. Over the reporting period bureaucratic obstructions increased, as well as constrained access related to increased conflict in some part of the country. At the time of writing all partners have successfully negotiated access and operations are anticipated to pick up in pace from quarter four into year 2.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Performance of partners and DFID, notably on commercial and financial issues
Performance of the CARE and ACTED consortia has been disappointing this first year, with no activities’ targets being met. Reasons have been documented in the output section and include delays in contracting, and the escalation of conflict rendering more districts inaccessible. Delays to project implementation were also caused by the delay or rejection of sub-agreements and movement authorisation from local authorities for accessible districts. Partners have also faced obstructions from authorities on recruitment of project staff, causing delays to recruitment. High rates of staff turnover have also had an impact on implementation. However, partners have as much as possible tried to reach out to the communities using different approaches described here – remote management, working with local partners like the Ministry of Health, change in geographical targeting and modifying activities (e.g. exchange from food baskets to UCTs).
Performance of both Save the Children and Oxfam has been mostly strong, with the effective and safe delivery of cash transfers to the intended target of beneficiaries. Whilst the first quarter was taken up negotiating with DFID on the Accountable Grants, and with local and national authorities on the MoUs, both organisations were delivering from the second quarter onwards.
Both the quality and timeliness of narrative reporting has been impressive across partners, with only minor (pre agreed) delays in reporting have occurred. The work done by the DFID programme team to harmonise the reporting template, alongside the logframe, workbook and financial reports, has been on immense value to both the partners, and DFID. Consistency in reporting style and quality has allowed for more enhanced and timely analysis provided by the DFID team in response to partners too.
Narrative reports have been of good quality, with easy to read tables, covering the key areas we want to see reported on. Length is usually appropriate, and a good level of proportionality is applied by partners. There remain some discrepancies between the figures reported in the narrative, and that in the logframe, and all partners would benefit from reviewing the narrative reports, alongside the logframe before submitting. Annexes include post distribution monitoring reports, success stories, and progress on cross cutting analysis, which add useful weight and evidence to support the narrative report. Through the reporting template partners proactively update risk registers, delivery chains, and geographical coverage. Across the board more work needs to be done on the monitoring and recording of assets.
Most disappointingly, has been the inconsistency and weakness in the quality of financial management. All partners have had weak forecasting and/or financial reporting and substantial errors noted following DFID scrutiny. ACTED in particular have made a series of oversights, that led to a drop of £2.5 million from their forecast – one third of their annual budget - in the last six weeks of the financial year. This limits effective use of tax payers’ resources. CARE too, had too much optimism bias, in what could be delivered within the given time frames. Oxfam’s financial reporting also lacked scrutiny, and senior oversight, incorrect payment requests, inaccurate forecasting, and confused budget lines, were all issues that DFID programme team had to work with them to resolve. DFID appreciates the very difficult environment in which all partners are operating and anticipates a certain level of fluctuation; however, realistic planning for inception periods and factoring in for almost certain slippage due to access constraints must be factored in to forecasts going forward. Evidence of reliable financial data will give DFID confidence to be more flexible with the timing of resources to ensure the most effective delivery of this programme.
In addition to the narrative and financial reports, DFID holds quarterly meetings with each partner including consortia members, as well as quarterly roundtables – two per year at programmatic level, and two at strategic level with partner Country Directors expected to attend. These meetings are critical both to ensure a good understanding, and reflection on the previous quarters, but also to set out clear paths for the programme’s future. It also allows for greater consistency, lessons learned and best practice shared amongst all partners.
Whilst the narrative reporting has been strong the same cannot always be said for logframe completion. This is in part due to the number of changes made to the logframe in order to design and agree the overarching logframe. It is also due to the changes to programme activities that have had to occur due to the constraints on the ground. This has improved however throughout the year, and DFID has been sure to clarify and support where needed to ensure an accurate reflection of the achievements are held against the expected targets of this programme. Further clarification will be provided to all partners with respect to approvals required for any changes to the logframe to ensure consistent figures are reported against and any changes logged and appropriately authorised.
To monitor this more closely it is recommended that both the ACTED and CARE consortia are subject to additional performance measures. The terms of reference should be set out and agreed over the next month. Additional oversight measures that DFID will introduce include monthly progress meetings to cover: progress against specific performance targets; updates on access constraints and actions taken; detailed scrutiny of forecasts and budgets; evidence of regular coordination meetings within consortia as well as all MHRP partners in Sana’a, and more widely where relevant, e.g. with UNICEF on malnutrition. A formal review point at the end of September 2018 will determine whether it is feasible to continue with the integrated element of the programme or if further changes or suspension of activities is required.
It is recognised that in addition to this, CARE UK is already implementing its own performance plan for its consortium, covering several indicators including value for money, responsiveness to requests for information, spend rate, and accuracy of forecasting. The performance plan was finalised in quarter four and used in April/May 2018 to review performance of partners during Year 1 and suggest adjustments to programme implementation accordingly as needed. We hope that subsequent results of consortia strengthening will be evident in quarter four reports.
DFID should do more to ensure that consortium partners are working effectively as consortium and not in silos. In addition DFID should look to ensure all partners under the MHRP work more closely together, sharing best practice, supporting each other with access where possible, and have a more collaborative, and complementary approach. Relaying of consortium partner requests by lead partners has at times proven ineffective. Coordination leads need to be strengthened when appropriate and for efficiency DFID should have more direct dialogue with consortium partners to expedite decision making. Lastly DFID can also do more to engage cross cutting advisors in the programmatic detail more effectively.
Date of last narrative financial report(s)	15/02/2018
Date of last audited annual statement (s) (AAS) / Oxfam GB / Save the Children / CARE UK / ACTED	10/10/2017 / 10/05/2017 / 21/12/2017 / 23/06/2017

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)
Monitoring (1/2 page)
MHRP Partners conduct direct monitoring of their operations, as set out below:
Drawing from DFID Independent Monitoring recommendations (Tazee’z / British Council 2016), Oxfam and Save the Children are well aware of DFID expectations in terms of market surveys and in terms of monitoring cash transfer outputs and outcomes. In addition to first-hand monitoring by their national staff during distribution, both partners have systematically conducted post-distribution monitoring 2 weeks after each round of cash transfers. They shared all results with DFID in the form of separate reports and by integrating this information in the quarterly reports.
The recruitment of ACTED’s appraisal, monitoring, and evaluation (AME) focal point largely improved communication among the partners and facilitated information sharing, as well as harmonization of data collection tools and documents among all partners. The Consortium is regularly monitoring the market in the target governorates and post distribution monitoring will be conducted after each cash transfer round - once it is launched - to measure the effective delivery of the programme.
CARE did not share details of the monitoring of activities implemented by the end of December-, although a limited number of activities were actually implemented. The consortium has developed joint tools for Complaints Response and Feedback Mechanisms and Post Distribution Monitoring Surveys that will be used to track all beneficiary feedback. We expect to learn more on CARE consortium’s actual monitoring in their quarter four report.
Accountability to affected populations[10] was strengthened under MHRP as a key recommendation from the closure of the predecessor programme. Our vetting of grant proposals looked specifically at this aspect and this was included in our scoring matrix. Call for proposal instructions specifically invited applicants to detail their beneficiary feedback and complaint mechanism(s) and explain how this information would loop back into the adjustment of the projects as a way to improve accountability to beneficiaries. In practice, MHRP partners have to report on such adjustments – where necessary - in their quarterly reports. Partners have been regularly reminded that DFID will not accept a simple commitment to accountability to affected populations and that evidence that beneficiary feedback and complaints is taken into account and programmes adjusted accordingly must be provided with their reporting.
[10] Accountability to affected populations (AAP) can be understood as 'an active commitment by humanitarian actors and organizations to use power responsibly by taking account of, giving account to, and being held to account by the people they seek to assist'. It refers to the responsible use of power in humanitarian action, combined with effective and quality programming that recognizes the dignity, capacity, and abilities of communities of concern. (UNHCR Emergency Handbook)
The DFID programme team had no access to Yemen over the reporting period, a constraint that currently affects all DFID programmes in Yemen. In order to compensate for the absence of in situ first hand monitoring, DFID Yemen uses an independent monitoring programme. However no new studies took place over the first 9 months of this programme. As an additional measure DFID Yemen developed a new format for the quarterly narrative reports drawing lessons learnt from the MHRP predecessor programme. MHRP partners have to report activities and results for the period under review but also need to report any event that has positively or negatively affected the implementation of their respective programmes (constraints and opportunities).
In addition, based on good practice from the MHRP predecessor programme, DFID Yemen organises quarterly partner roundtable meetings in Amman. Every second roundtable focusses on the strategic direction of the MHRP and requires the presence of the NGO Country Directors, while the other one focusses on technical aspects and requires the presence of NGO operational staff. One round table was organised at programme inception stage, a second one focussed on technical, operational aspects in late 2017 and a third roundtable meeting with NGO country directors was organised right after the production of the third quarter report in early 2018.
We have kept our partners regularly aware (high staff turnover) of their obligation to report any suspicion or allegation of aid diversion, damage, loss or theft and we remain committed to immediately inform the Counter Fraud Unit whenever such case occurs. Above-described formal reporting is complemented with ad hoc requests related to programme issues but also to the situation on the ground. For example during the fighting in Sana’a city in December 2017, the DFID Yemen team was in daily contact with the Country Directors of Save the Children and ACTED, bunkered in their guesthouses, sharing information on the situation.
Amman has become a humanitarian hub for the region with many regional offices and a growing number of humanitarian donor representations based there. It is also the contractual R&R destination for many humanitarian workers based in Yemen. This offers many opportunities for the Amman-based DFID team to meet NGO partners face-to-face, allowing them to share more openly than they would on open phone lines.
Finally, the DFID Yemen team in London is organising regular NGO meetings which offer additional opportunities for our MHRP partners to share on their strategic direction, advocacy plans and also learn more from DFID’s own strategy and priorities.

Evidence
The selection of districts to be covered by the MHRP had to be continuously revisited since programme inception (the call for proposal was launched in November 2016) along the following criteria:
- Partner access to selected districts (mostly referring to obstacles such as the delivery of MoUs by the local authority, travel permits etc.).
- Regular assessment of unmet needs in districts. This is done by drawing information from cluster assessments and information issued from the Humanitarian Needs Overview and the Integrated Phase Classification (IPC)[11] revisions.
  [11] The Integrated Food Security Phase Classification (IPC) is a set of protocols to classify the severity and causes of food insecurity. The IPC standardised scale categorizes the severity of acute food insecurity from phase 1 (minimal) through to phase 5 (famine). (Integrated Food Security Phase Classification Factsheet)
- Coverage and gap analysis by clusters: coordinated by OCHA, clusters produce regular maps of sectoral assistance coverage and gaps, highlighting areas where assistance is the most needed.
- Access constraint scaling: this is a product of the OCHA & NRC co-chaired Humanitarian Access Working Group, which reports to the Humanitarian Country Team (HCT). Data combined by OCHA informs us on the level of access constraints (ranked between 1 and 3) experienced by UN agencies, INGOs and Local NGOs for each of Yemen’s 333 districts.
- Famine threat monitoring: this inter-cluster continuous assessment of famine risk led to the identification of 107 districts at highest risk of famine.
From the analysis of these criteria, DFID Yemen has discussed MHRP partners’ choice whenever they proposed to move planned activities from one district to another. DFID Yemen keeps updated a matrix that clearly indicates the level of needs and access constraint levels for each of the districts targeted by the programme
It is important to remember that this programme aims at delivering life-saving assistance in hard to reach areas of one of the toughest humanitarian working environments. As highlighted in the business case, it should therefore be no surprise that the selection of districts had to be revised on several occasions since programme inception and actually this can be seen as evidence that our partners have selected hard to reach areas as expected.
Learning
Quarterly partner meetings and bi-annual Partner Roundtable meetings have proven the right approach to interact with partners while DFID cannot travel to Yemen (see monitoring section above) allowing our NGO partners to step back and share openly with us on various operational and strategic aspects of MHRP. However given slow progress, this will be increased to monthly for the consortium partners with a review at end September 2018.
- MHRP partners’ quarterly reports include a section on lessons learned that allows the DFID team to capture these and share on the occasion of partners’ roundtable meetings.
- On the downside, one year on MHRP partners still have to meet and coordinate as a group, outside of formal donor meetings. This was a recommendation made in the Project Completion Review (PCR) of the predecessor programme with a view to make sure MHRP partners maintain a shared strategic view of their role in delivering a large, 3-year programme that pursues a common objective. Such meetings would also contribute to sharing information, lessons learnt and good practice both on access & administrative issues and on operational opportunities.
- Main learning from this first year of MHRP implementation is that cash transfer programmes remain feasible and the preferred transfer modality according to beneficiary feedback. Cash transfer programmes are supported by regular price and market monitoring and have been properly monitored by our partners Save the Children and Oxfam. As a next step (year 2) we will have to look more closely at the pros and cons of mobile cash programming (e.g. Mfloos) as a cash transfer modality that is more flexible and contributes to beneficiaries’ safety and dignity.
- The integrated approach whereby consortium members support the same set of beneficiaries in their respective sector speciality remains to be demonstrated as an effective approach because of serious delays in implementation. We hope to learn more with the production of partners’ quarter four reports mid-May 2018.