## A1 Goal, Purpose, Risk
Annual Review (reviewed August 2010)
ARIES Project Code | 113889
ARIES Project Description | CBFF Start Up Fund (working template)
A1: Goal, Purpose, Risk
Goal
Goal statement | The capacity of the people and institutions in Congo Forest Countries to manage and protect their forests sustainably enhanced
Indicator 1 | Effective participation of 4 of the 6 main Congo Basin Forest countries in collaborative programmes to conserve forests and enhance livelihoods of people living in / near forests
Milestone for this review (if any) | Sept 2010 (2 countries particpating)
What progress has been made in the period covered by this review? | Demand is strong from Congo Basin constituents (Governments, local and international non-government actors) to participate in and receive funding from the CBFF, particularly from DRC, Cameroon, Republic of Congo & Central African Republic. Demand from applicants for the first two calls for proposals has been high. Over 560 concepts were received, with 40 suitable proposals from 10 countries selected for available funding. These are Cameroon, DRC, Gabon, Congo Brazzaville, Central Africa Republic, and Equatorial Guinea, as well as Rwanda, Burundi and Sao Tome and Principle. More proposals were judged suitable if funds had been available.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | COMIFAC governments and secretariat actively engaged. Strategic alliances built for future CBFF implementation
Milestone for this review (if any)
What progress has been made in the period covered by this review? | The COMIFAC Secretariat is represented on the Governing Council (GC) of the CBFF, and has particpated in all GC meetings of the Fund to date. During this reporting period COMIFAC country representation has been via the Central African Republic (CAR), represented by the Minister of Environment, Water and Fisheries, and since November 2009 DRC, represented by the Minister for Environment, Nature and Conservation.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | There is good evidence that Congo Basin countries are engaged and collaborating in CBFF implementation, as in the indicators. Capacity of people and institutions to manage and protect forests as a result of CBFF projects will become clearer when CBFF projects have made more progress
Goal Recommendation 1 | The African Development Bank (AfDB) managed main CBFF will continue to help achieve the Goal when this project has ended
Goal Action Point 1 | DFID engagement with the AfDB managed CBFF will help review progress towards the Goal
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Congo Basin Forest Fund (CBFF) fully operational and supporting forest communites and countries to manage their resources sustainably
Indicator 1 | Number / Value ($) of high value quality projects approved by CBFF Governing Council and operational
Milestone for this review (if any) | Sept 2010: 20/$50 million
What progress has been made in the period covered by this review? | In November 2010, following two calls for proposals, 40 projects had been endorsed for funding, accounting for approximately $110 million
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | % of projects of Governments / national civil society / international NGOs in the CBFF Portfolio
Milestone for this review (if any) | Sept 2010 - 20/50/30
What progress has been made in the period covered by this review? | In November 2010, following two calls for proposals, the spilt was 32% Governments / 33% national civil society / 35% international NGOs. This was judged to be an appropriate balance of partners
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Yes. There is continued support from Congo Basin governments and original donor countries (UK and Norway)
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | Some evidence, though limited to date, given early nature of AfDB managed main CBFF interventions. Political will and desire for this support in the region is still strong. During 2011 increased interest from other donor countries in potentially joining the fund.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | Progress against the Outputs, especially Output 2 and 3, have demonstrated the type of projects that could be supported under the African Development Bank managed CBFF and so contributed towards the Purpose. Output 4 has helped the AfDB to operationalise the CBFF and so made a major contribution towards the Purpose. Output 1 has largely not been achieved, but the indicators that have not been achieved do not represent typical activities for the African Development Bank managed CBFF.
Purpose Recommendation 1 | Make sure that successful outputs inform the African Development Bank CBFF, especially the pilots of Output 2.
Purpose Action Point 1 | Encourage partners to communicate results to the AfDB CBFF Secretariat.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 2 | 2.4
Purpose Justification | There has been good general progress in the CBFF becoming fully operational. Some initial difficulties in contracting are being overcome, and the Fund now has a good set of initiatives
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | No
If Yes, why was/is this?
Logframe Recommendation 1
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Forest Resource assessment & monitoring technologies in place & operational
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision?
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 (leave blank if standard indicator) | High-resolution remote-sensing camera for forest assessment & monitoring built/operational (yes/no) | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 Built:Yes / Operational: No Sept 2011 Built: Yes/Operational yes | 0
Progress made in the period covered by this review, including numbers. | Agreement reached with a UK organisation to build the camera. But potential arrangements to place it on a Brazilian satellite fell through in August 2010. No immediate plans for an alternative, so this Output will not be delivered under this project. Brazil is looking for other means to assist Congo Basin countries outside this project. There has been little spend on activities for this indicator and all spend was stopped when it became clear that no progress was being made.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Remote-sensing data receiving station built / operational (yes/ no)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 - Built:Yes Operational: No Sept 2011 build Yes/operatinal Yes
Progress made in the period covered by this review, including numbers | Planned support for a French led Gabonese station stalled. The station will not now be possible in the lifetime of this project. Decision taken not to pursue further within this project. France is likely to take forward separately. There has been no spend on activities for this indicator.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Community forestry mapping extended to Republic of Congo/Central African Republic/Gabon
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 2 countries Sept 2011 3 countries
Progress made in the period covered by this review, including numbers | Milestones have been met and the indicator is likely to be achieved. The project activities to deliver this indicator are on track to achieve objectives. Forest communities and local government in 11 regions of 3 countries (Republic of Congo, Central African Republic, Gabon) are being supported to map community forest land tenure (an estimated 14,100 direct beneficiaries). This includes being able to compile and use data, and influence decisions related to forests, forest communities and land tenure. Communities are producing maps, and NGO and government staff able to use GIS to integrate community and remote sensing information into decision-making tools and processes, as well as participating in local and national dialogue regarding forest tenure and land planning.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 4 | 0.25
Impact Weighted Score | 5 | 0.05
Justification for the Score | There has been no real progress with indicators 1 and 2 for reasons outside DFID and UK control. Progress on the community participatory mapping component for Indicator 3 has been good
Output 1 Recommendation 1 | The component activities planned to deliver indicators 1 and 2 should be closed since there is no prospect that they can take place within the lifetime of the project
Output 1 Action Point 1 | Close component activities planned to deliver indicators 1 and 2. Consider adjusting the lograme. Indicators 1 and 2 should not need to be reviewed at project completion since the activities will be closed. Together with Procurement Group, review contractual issues involved with delivering the activities for indicator 1, including how to address the limited DFID funds that were disbursed.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Transformative pilot projects undertaken and results disseminated.
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Low | 3
0.9
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | Pilot roadmap for laws, policy and institutions required for community forestry developed in DRC
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010: 75% Sept 2011: 100%
Progress made in the period covered by this review, including numbers | About 80% has been achieved. A national community forestry dialogue was successfully completed. Amendments to the draft legislation were proposed and some incorporated in a revised draft under the chairmanship of the DRC Ministry of Environment legal counsellor. A proposal by DRC Ministry of Environment for long term funding to develop community forestry in DRC was produced and submitted to the AfDB managed CBFF, and it was endorsed subject to further progress on the law. Completing a road map identifying how community forest management can be implemented on a large scale in DRC is the principal task of the remaining months of the work
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Study to identify transformative rural energy interventions completed and recommendations implemented
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010: Study yes/no Sept 2011: study yes/yes
Progress made in the period covered by this review, including numbers | This project consisted of the production of a single review document, based in part on a short exploratory mission to the Democratic Republic of Congo, followed by a second mission to share the preliminary conclusions of the review. The work was conducted and completed in the first six months of 2009. It was made available for use by donors and others in DRC.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Community-level payments from international/global partners piloted in Cameroon, CAR and DRC
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 - 2 countries Sept 2011 - 3 countries
Progress made in the period covered by this review, including numbers | Following initial work it was decided to focus on Cameroon alone, the only country with community forestry legislation suitable for the pilot. It was decided not to pursue further work in CAR or DRC. Pilots in 2 villages with community forests in Cameroon have been established. The communities are different in geographic location, social make-up and size. These pilots are centred on achieving measurable reductions in losses of forest carbon through the adoption of improved agroforestry and more intensive agriculture on existing cultivated plots. To this end, a series of technical capacity building and training workshops were conducted. Research to establish baseline carbon stocks and future scenarios has been completed, and the methodology and results prepared for publication. Socio-economic studies have been undertaken at both sites. A proposal for payment for ecosystem services (PES) has been prepared and approved by the Plan Vivo Foundation, with the aim of the first PES payment before the end of 2011
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 2 | 0.75
Impact Weighted Score | 22.5 | 0.225
Justification for the Score | Output indicators are largely on track to be achieved
Output 2 Recommendation 1 | Draw out lessons of the payment for forest ecosystem services in Cameroon for use outside the project
Output 2 Action Point 1 | Work with implementing partners to encourage them to draw out lessons
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | The Democratic Republic of Congo Ministry of Environment, Tourism and Conservation (MENCT) supported in strengthening its capacity to manage the country’s natural resources
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share | 23%
Indicator 1 (leave blank if standard indicator) | Adequacy of MENCT offices, equipment & transport to perform tasks
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 - 2 Sept 2011- 2 (scale - 1=inadequate, 2=partially adequate, 3=adequate, 4=highly adequate)
Progress made in the period covered by this review, including numbers | A score of 2 - partially adequate is judged appropriate. One of the three main MENCT buildings has been completely refurbished, and the two others are due for completion in summer 2011. MENCT now have sufficient operational IT, telephone and communication systems.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Adequacy of staff numbers and competency to perform tasks for the MENCT
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 - 2 Sept 2011 - 2 (Scale - 1=inadequate, 2=partially adequate, 3=adequate, 4=highly adequate
Progress made in the period covered by this review, including numbers | A score of 2 - partially adequate is judged appropriate. More than 400 staff of the DRC Environment Ministry (MENCT) and Nature Conservation Agency (ICCN) have been trained, including in IT, accounting, project management, mapping, community conservation, forest surveying, environmental health, forest engineering, protected area management, and environmental law
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Adequacy of MENCT capacity to plan, prepare documents, implement & monitor its projects
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 - 3 Sept 2011 - 4 (Scale - 1=inadequate, 2=partially adequate, 3=adequate, 4=highly adequate)
Progress made in the period covered by this review, including numbers | A current score of 3 is judged appropriate. 48 staff have received training in project management, accountancy, and project monitoring and evaluation. The programme has also supported Ministry staff to produce successful financial requests and proposals to donors. The programme has also been working with the Ministry on various capacity building requests. In May 2010 two consultants helped the Ministry develop 7 proposals for AfDB managed CBFF projects, in particular those concerning community forestry, agro-forestry and reforestation. They have subsequently been endorsed.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 2 | 0.75
Impact Weighted Score | 15 | 0.15
Justification for the Score | The activities to deliver the indicators has been funded through GTZ, the German aid agency (now refered to as GiZ). GiZ reporting gives a good overview of progress towards indicators
Output 3 Recommendation 1 | DFID funding is complete, but GiZ continues some work. DFID should monitor the final outcome.
Output 3 Action Point 1 | Issue a no cost extension
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | African Development Bank (AfDB) supported to establish and operationalise the CBFF Secretariat on a sustainable basis
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Low | 3
0.9
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share | 100%
Indicator 1 (leave blank if standard indicator) | Interim Co-ordinator appointed and operationalised
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 - Yes sept 2011 - Yes
Progress made in the period covered by this review, including numbers | Indicator fully achieved. The Interim Co-ordinator was appointed and operational. DFID provided resources for the provision of an Interim CBFF Secretariat Co-ordinator, who was in post August 2008 - Nov 2009. A permanent co-ordinator was appointed by AfDB at end Nov 2009, and in place by December supported by 5 Secretariat staff at HQ and in the Congo Basin Region (DRC & Cameroon)
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | CBFF (Challenge Fund) Procedures and Guidelines in place/ Challenge Fund Operating effectively
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 - 75% Sept 2011 - 100%
Progress made in the period covered by this review, including numbers | An achievement of 80% is judged to be appropriate. This Output concerns helping the AfDB to make the main CBFF operational, and managed effectively. Procedures and guidelines were at least 75% operational by September 2010. Guidelines were developed in time for the first call for proposals in Autumn 2008 and operational in January 2009. Two calls for proposals have resulted in 560 concepts. 40 suitable proposals were selected for funding. More were judged suitable if funds had been available
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | CBFF Governing Council Meetings facilitated effectively and support provided to Co-Chairs
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Sept 2010 - 75% Sept 2011 - 100%
Progress made in the period covered by this review, including numbers | A score of 100% is judged to be appropriate. Five face-to-face Governing Council Meetings have taken place (DRC March 2009, Cameroon Nov 2009, Tunis March 2010, Gabon Nov 2010, and Republic of Congo June 2011). There have been 7 virtual meetings by telephone. The Secretariat has facilitated the GC and Co-Chairs effectively and with increasing confidence
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 2 | 0.75
Impact Weighted Score | 22.5 | 0.225
Justification for the Score
Output 4 Recommendation 1 | There should be continued DFID engagement with the AfDB CBFF Secretariat when this project has ended to review CBFF implmentation progress and encourage further improvement.
Output 4 Action Point 1 | Continued DFID engagement as part of DFID's representation in AfDB managed CBFF governance.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-07-20
Impact Weighting (must = 100) | 100%
Total Impact Score | 65 | 0.65
Output Risk | Low | 2.6
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study
Government assessment
Joint donor review
Independent consultant review | X
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant | X
Donor partners
DFID staff | X
Donor partners | GTZ (who are delivering / leading delivery of Output 3
Norway (for progress on the African Development Bank managed Congo Basin Forest Fund
Comment here on the Method of Scoring and Scoring Responsibility. | The assessment and scoring is based on an independent report, monitoring by the project officer and adviser, and quality assurance by a senior adviser.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Activities to deliver Outputs 2 and 3 involved support through a range of partners. This included agreements with UK based NGOs that in turn worked with local NGOs, community groups and local government. In general this has been an effective way of delivering many activities leading to the Outputs. There were some initial difficulties as UK based organisations developed working relationships with local organisations, which slowed the pace of implementation, although difficulties were largely overcome. The African Development Bank (AfDB) has been an essential partner for Output 4. It has taken some time to generate a good partnership with the Bank, as joint expectations were clarified. The AfDB was slow to put an effective Secretariat in place. But the partnership is generally now working well. Output 1 relied on other partners for initiation of activities. When this ran into problems it was very difficult to resolve, with eventual decisions not to proceed
Working with Partners Recommendation 1 | Clarity over aims and objectives among all partners from the outset is important. This applies to DFID working with NGO partners, and with international organisations such as the AfDB. It also applies to relationships between non DFID partners
Working with Partners Action Point 1 | Draw on lessons for the development and implementation of future UK assistance for forests and reducing emmissions from deforestation and degradation (REDD)
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | Some activities contributing towards Outputs 2 and 3 have demonstrated a range of innovative approaches. This includes methods of community based mapping of forest resources, and working with communities on the practical application of payment for forest based ecosystem services. These activities include their own means to draw out knowledge and disseminate for use elsewhere in country, more widely and internationally. Examples of dissemination include traditional reports and guidelines, as well as more innovative means such as web based methods
Best Practice / Innovation Recommendation 1 | The remainder of the project should ensure that activities that feature innovation and best practice are captured and easily available for use in other instances
Best Practice / Innovation Action Point 1 | Draw on examples of innovation and good practice for the development and implementation of future UK assistance for forests and REDD
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | The project contains a number of different components with a wide range of objectives and means of delivery. This has presented DFID project management challenges. Significant effort is required to manage the different strands. It also includes a range of delivery channels, from direct working with UK based NGOs, that in turn work with local partners, to working through other donors partners such as GTZ (GiZ). The relative complexity requires significant time and effort for project management. However, in many instances this way of working with project partners has resulted in some effective activities, for example the practical testing of payment for ecosystem services in Cameroon
Project Management Recommendation 1 | The management implications of the type of delivery mechanisms should be clear at the start of future projects, and the management time implications fully considered and accounted for.
Project Management Action Point 1 | Take account of project experience in the development and implementation of future UK assistance for forests and REDD
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
30139019 | Independent Annual Review of Congo Basin Start-up Fund (EDG Consultants, Oxford)
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | Benefits resulting from activities under the project, for example contributing towards Outputs 2 and 3, have sustainability built into their implementation. Relationships generated with the African Development Bank (AfDB) in Output 4 will continue through DFID engagement with the main Congo Basin Forest Fund managed by the AfDB. Activities in Outputs 1 were not implemented. Some elements might be picked up by others in future, but in general the need for sustainability does not apply to this Output
Sustainability Recommendation 1
Sustainability Action Point 1 | Draw on lessons for the development and implementation of future UK assistance for forests and REDD
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | The African Development Bank (AfDB) managed main CBFF will continue to help achieve the Goal when this project has ended | ARD forests/REDD policy adviser, with DFID Climate and Environment Department (CED)
R2 | 0
R3 | 0
A1: Purpose
R1 | Make sure that successful outputs inform the African Development Bank CBFF, especially the pilots of Output 2.
R2 | 0
R3 | 0
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | The component activities planned to deliver indicators 1 and 2 should be closed since there is no prospect that they can take place within the lifetime of the project | ARD forests/REDD policy adviser
R1.2 | 0
R1.3 | 0
R2.1 | Draw out lessons of the payment for forest ecosystem services in Cameroon for use outside the project | ARD forests/REDD policy adviser, with DFID Climate and Environment Department (CED
R2.2 | 0
R2.3 | 0
R3.1 | DFID funding is complete, but GiZ continues some work. DFID should monitor the final outcome. | ARD forests/REDD policy adviser
R3.2 | 0
R3.3 | 0
R4.1 | There should be continued DFID engagement with the AfDB CBFF Secretariat when this project has ended to review CBFF implmentation progress and encourage further improvement. | ARD forests/REDD policy adviser, with DFID Climate and Environment Department (CED
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Clarity over aims and objectives among all partners from the outset is important. This applies to DFID working with NGO partners, and with international organisations such as the AfDB. It also applies to relationships between non DFID partners
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | The remainder of the project should ensure that activities that feature innovation and best practice are captured and easily available for use in other instances
R2 | 0
R3 | 0
Project Management
R1 | The management implications of the type of delivery mechanisms should be clear at the start of future projects, and the management time implications fully considered and accounted for.
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | DFID engagement with the AfDB managed CBFF will help review progress towards the Goal
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | Encourage partners to communicate results to the AfDB CBFF Secretariat.
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Close component activities planned to deliver indicators 1 and 2. Consider adjusting the lograme. Indicators 1 and 2 should not need to be reviewed at project completion since the activities will be closed. Together with Procurement Group, review contractual issues involved with delivering the activities for indicator 1, including how to address the limited DFID funds that were disbursed.
AP1.2 | 0
AP1.3 | 0
AP2.1 | Work with implementing partners to encourage them to draw out lessons
AP2.2 | 0
AP2.3 | 0
AP3.1 | Issue a no cost extension
AP3.2 | 0
AP3.3 | 0
AP4.1 | Continued DFID engagement as part of DFID's representation in AfDB managed CBFF governance.
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Draw on lessons for the development and implementation of future UK assistance for forests and reducing emmissions from deforestation and degradation (REDD)
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | Draw on examples of innovation and good practice for the development and implementation of future UK assistance for forests and REDD
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | Take account of project experience in the development and implementation of future UK assistance for forests and REDD
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | Draw on lessons for the development and implementation of future UK assistance for forests and REDD
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3