The Independent Monitoring and Evaluation Project for the State Level Programmes (IMEP)

Annual Review SAVI

Client: UK Department for International Development (DFID)
Abuja, 4 July 2011

Funded by UKaid from the Department for International Development

Gareth Williams,
Maisha Strozier

Abuja 4 July 2011

Table of Acronyms
AP	Advocacy Partnership
IMEP	Independent Monitoring and Evaluation Project
LGA	Local Government Area
MDAs	Ministries, departments and agencies
MNCH	Maternal and New-born Child Health
MTR	Mid Term Review
MTSS	Medium Term Sectoral Strategy
SAVI	State Accountability and Voice Initiative
SDoC	State level Drivers of Change analysis
SHoA	State House of Assembly
SLP	State Level Programme

# Introduction
This report presents the findings of the 2011 Annual Review of the DFID Nigeria State Accountability and Voice Initiative (SAVI). This was a light touch review based on a one week mission to Nigeria (30 May to 3 June 2011) organised by the Independent Monitoring and Evaluation Project (IMEP). The evaluation team was led by Gareth Williams (The Policy Practice Ltd) assisted by Maisha Strozier (Africare Nigeria) and Alex Duncan (The Policy Practice Ltd).

DFID have opted for a light touch, summary review because the 2011 Annual Review is timed to take place only a few months before the Mid-Term Review (MTR) due in October 2011. In preparation for the more thorough assessment required for the Mid-Term Review, this Annual Review is intended to provide an interim assessment of progress and results, to identify the key issues to be addressed in depth at the MTR, and to enable a review of the logframe and indicators in advance of the MTR. The Terms of Reference for this Annual Review are shown in Annex 1.

This annual review is based on the following sources of evidence:

- Two half day meetings with SAVI core team staff in Abuja
- A review of key project documents including previous inception and annual reviews, recent quarterly progress reports (state level and SAVI-wide), logframes (state level and SAVI-wide), and state workplans.
- A self-assessment conducted by SAVI using the ARIES form.
- Visits to Kaduna and Lagos states (2 days each), where meetings were held with SAVI staff, members of civil society organisations participating in SAVI supported Advocacy Partnerships, members and support staff of State Houses of Assembly and staff of other DFID funded State Level Programmes (SLPs).
- Meetings with the DFID Governance Advisor and debriefing sessions with SAVI and DFID staff at the end of the mission.

In addition, the review draws on two field visits to Enugu and Kano states conducted by Gareth Williams and Maisha Strozier during the IMEP design mission in March 2011. Together the design mission and 2011 Annual Review mission have covered four out of five of the states where SAVI is working (Jigawa has not yet been visited).

The findings of this report should be viewed in the context of the short duration of the review and the fact that this is the first IMEP review of SAVI employing new consultants. While there has been general agreement between IMEP, SAVI and DFID on the main findings of the review, many of the issues raised will need to be addressed in greater depth at the Mid-Term Review. Following the in-country mission the consultants completed DFID’s ARIES form and provided scores against outputs and purpose. It has been agreed with DFID that for the purposes of this first IMEP Annual Review the consultants’ scoring on the ARIES form will taken as provisional and subject to confirmation by DFID.

# Review of the performance of the programme to date
## Progress made in the implementation of SAVI workplans
The limited duration of the field mission did not allow a detailed assessment of SAVI’s progress against its workplans. However, in broad terms SAVI is able to demonstrate good progress for most of its planned activities. Expenditure is roughly to plan with 28% of the budget spent at a point where the project is about 40% through its duration. Spending is expected to accelerate as activities scale up and SAVI begins operating in three additional northern states. There have been no major interruptions in project implementation, except in special circumstances. In Enugu the death of the State Team Leader and the recruitment of a replacement has slowed down SAVI’s work over the past year. The 2011 elections have also held back some aspects of SAVI’s work with State Houses of Assembly and affected the timing of studies. However, this has been foreseen by SAVI and planned for.

The evaluation team examined SAVI’s work plans for Kaduna and Lagos states. These are detailed and regularly updated plans that include budget provisions. The workplans appear to be used actively by staff and are regular updated (at least once every three months). The workplans correlate closely with the content and timing of activities seen by the review team in Lagos and Kaduna.

It is important to recognise that the nature of SAVI’s work makes it difficult to engage in detailed planning beyond the horizon of a few months. This is because the project needs to adapt flexibly to changing political circumstances and advocacy opportunities as they arise. The project appears to have adopted a sensible balance between the need for clear, forward looking plans and being able to adapt quickly to changing conditions. DFID’s oversight also appears to provide sufficient latitude to enable SAVI to work flexibly, while at the same time keeping track of the project’s progress.

SAVI’s quarterly progress reports mainly provide information on progress against expected outputs and the project purpose. It is not easy to assess progress against planned activities. However, the quarterly progress reports do list ‘key activities undertaken in this quarter’ and ‘key activities planned for the next quarter’. These sections of the report provide a general sense of the level of activity of the project, which appears to be quite satisfactory. However, it is difficult to judge whether activities have proceeded on track or have been implemented more slowly or to a lesser extent than planned. It is recommended that SAVI should consider adopting a reporting system similar to the ‘traffic lights’ used by SPARC to provide a rapid overview of progress against plan and to highlight variations in progress between types of activity and between states. For the sake of practicality these should be grouped at the level of sub-outputs (around 15-20 items in total) rather than individual activity lines in the workplan (around 100 in total).

## Progress made in achieving the programme logframe outputs
### Output 1 - Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy and monitoring.

This output concerns SAVI’s work in bringing together and strengthening the issue based Advocacy Partnerships (APs), raising the effectiveness of these groups in advocating for policy change, and ensuring their sustainability and potential for replication. The logframe contains three indicators to assess progress against this output.

- Strength of civil society partnerships for policy advocacy and monitoring.
- Dependency [of APs] on / independence from SAVI support.
- Civil society partners active support of replication of the approach.

SAVI’s milestones for 2011 appear to have been largely achieved in these three areas. SAVI reports that 65% of APs are satisfied with progress to date towards achieving their planned objectives (milestone for 2011 is 40%). The project considers that 75% of its Advocacy Partnerships under Output 1 have progressed from the ‘incubation’ stage to ‘call-down support’, of which 25% have progressed or are progressing to SAVI community-of-practice (CoP) stage. SAVI reports evidence of networking between Advocacy Partnerships within and between states (for further details and examples see ARIES form).

The consultants’ field mission also encountered several examples of effective advocacy work supported by SAVI that are generating tangible results. For example, over the past year in Lagos civil society advocacy has contributed to the drafting of a policy framework for Climate Change and a revised bill on People with Disability. In Kano and Kaduna SAVI supported Advocacy Partnerships have gathered evidence on the level of implementation of the states’ policy on free maternal and child healthcare.

In general terms SAVI’s model of bringing together civil society organisations in advocacy partnerships appears to be working well. Many of the groups are already, or will soon be, in a position to contribute to engage effectively in the policy process. The model established by SAVI is well suited to replication and scaling up. The Advocacy Partnerships are becoming less dependent on SAVI for organisational support and funding for their activities. SAVI has sought to promote sustainability and to minimise the Advocacy Partnership’s financial dependence on the project. However, the AP’s still receive considerable support from SAVI in the form of funding for particular activities, mentoring and advice, and access to government. There is a strong risk that there will be a loss of momentum in the work of the Advocacy Partnerships after the completion of the SAVI project.

In view of these considerations it is recommended that SAVI should receive a score of 2 against output 1 (milestones are likely to be largely achieved). However, as discussed in section 2.5 below IMEP recommends that some of the indicators and milestones need to be redefined to focus more on measuring the capacity of Advocacy Partnerships to influence policies and implementation in their area of interest.

### Output 2 - Civil society demonstrates a replicable and sustainable approach to engagement in government budget and planning processes.

This output concerns the work of the process-based Advocacy Partnerships that work on budget planning and monitoring and MTSS processes. The indicators and milestones are similar to output 1.

- Strength of civil society partnerships for engagement in government budget & planning.
- Dependency on / independence from SAVI support.
- Civil society partners active support of replication of the approach.

SAVI’s milestones for these three indicators appear to have been largely met for 2011. SAVI states that two out of the three Advocacy Partnerships that commenced in 2009 are satisfied with progress to date towards achieving their planned objectives. The Budget Analysis/Project Monitoring Advocacy Partnerships in Kaduna and Kano are working well, but not in Jigawa where the AP is presently being reconstituted. The other two APs covering MTSS/Local Government Monitoring in Lagos and Enugu are at an early stage, having only begun in earnest in 2010. Both are reporting satisfaction with their initial engagement with Government.

The indicators measuring the sustainability, independence and potential for replication of the Advocacy Partnerships under output 2 appear to be somewhat weaker than for those under output 1.[1] Only one of the five Advocacy Partnerships has reached the stage of ‘call down support’. Three are still in the ‘incubation stage’, and one is reported to be on the cusp of ‘call down support’. The status of the groups reflects the somewhat later start for output 2 activities in Lagos and Enugu, and the greater challenge of forming Advocacy Partnerships around broad policy processes rather than a specific issue.
[1] The difference in progress of the Advocacy Partnerships between outputs 1 and 2 may reflect the relative lack of experience of CSOs in Nigeria with budget monitoring,

Based on progress against the logframe indicators it is recommended to assign a score of 2 to output 2 (milestones are likely to be largely achieved). This score is somewhat tentative given the early stage of output 2 activities, and will need to be further assessed at Mid-Term Review. IMEP would also recommend the inclusion of an indicator for output 2 that rates the capacity of Advocacy Partnerships to engage constructively in state budget and policy planning processes and to influence change.

### Output 3 - An enabling environment for policy advocacy and monitoring, and engagement in government budget and planning processes.

Output 3 covers SAVI’s work in improving communication and collaboration between civil society organisations, the media and State Houses of Assembly, and improving understanding of the respective roles of these organisations by the organisations themselves and the public at large. The logframe includes two indicators for this output:

- Endorsement of collective action by civil society, the media and state houses of assembly.
- Public understanding of the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability.

SAVI has supported numerous activities and events bringing together civil society, the media and State Houses of Assembly, as well as broader civic education on the roles of these organisations. However, it has not been possible within the short duration of this review to obtain an accurate measure of the progress and effectiveness of these activities. In part this relates to the lack of objective data (the Citizen’s Perception Survey provides a baseline, but will need to be updated before any change can be established) and the short duration of the Annual Review, which did not permit many interviews with the organisations concerned. A more fundamental problem is that the indicators and milestones under output 3 lack clarity and do not describe SAVI’s work in a straightforward way. It is therefore recommended that in advance of the Mid-Term Review SAVI should reformulate output 3 to capture more clearly the focus of SAVI's activities and results. These are understood by IMEP to cover three areas: 1) improved communication and collaboration between civil society, media and State House of Assembly Partners based on a better understanding of their respective roles, 2) civic education on the role of these partners, and 3) support to the media in reporting on governance processes. IMEP will discuss further with SAVI how the project understands its role in these three areas, the balance between them, and what indicators would be appropriate. A specific focus on support to the media is needed as SAVI’s work with media organisations appears to be generally weaker than its support for civil society organisations and State Houses of Assembly. There is scope for SAVI to scale up its engagement with media organisations, and to find ways to link the media more systematically to SAVI’s work in promoting advocacy and better information on public policy.[2]
[2] IMEP is aware of the weaknesses in the media in Nigeria and the difficult challenge this poses for SAVI in strengthening its media work. Noted problems include: a) there is strong political bias and owner-direction of the news; b) the capacity of journalists to report is not high; c) the norm is that stories have to buy their way into the press.

For the purposes of this light touch review IMEP is prepared to accept SAVI’s self assessment for output, which provides a score of 2 (milestones are likely to be largely achieved). The Mid-Term Review will be able to provide an independent assessment based on revised logframe indicators and more thorough interviews with civil society, the media and State Houses of Assembly in a larger number of states.

### Output 4 - Improved state houses of assembly systems for transparency, public engagement and financial oversight.

SAVI assesses its progress in working with State Houses of Assembly against 4 indicators based on aggregated ratings generated by the 2009 Organisational Capacity Self-Assessment (conducted by SHoAs). The ratings were reassessed by SAVI in March 2011 and compared with the logframe milestones (table 1 below).

Table 1. Comparison of 2011 milestones against actual performance for State House of Assembly Systems.

	2011 Milestone	2011 Actual (from SAVI’s own assessment)	Comments from SAVI’s ARIES self assessment form
Indicator 1 - Quality of systems for public access to information and processes in the house and representation of public interests by members.	4 states score at least 2 out of 5, of which 1 state scores 3 out of 5 by mid to late 2011	3 states are scoring 2 and above, with 1 state scoring 3 (Enugu: 1.5, Jigawa: 1.5, Kaduna: 2.0, Kano: 2.0, Lagos: 3.0.)	The scores are lower than expected at this stage on constituency relations and feedback mechanisms, most states having focussed more initially on strengthening of internal systems than external relations.
Indicator 2 - Quality of systems for recruitment and retention of house support staff and aides	2 states score at least 2 out of 5, of which 1 state scores 2.5 out of 5 by mid 2011	3 states are scoring 2 and above, with 1 state scoring 3 (Enugu: 1.5, Jigawa: 2.0, Kaduna: 1.5, Kano: 2.0, Lagos: 3.0)	Scores are higher than expected at this stage reflecting the positive impact of the organisational capacity self-assessments and resulting ownership of the subsequent house reform plans, and realisation of the need to develop a cadre of support staff which a house service commission would help establish.
Indicator 3 - Quality of systems for induction and monitoring of compliance with house rules and procedures.	3 states score at least 2 out of 5, of which 1 state scores 3 out of 5 by mid to late 2011	1 state is scoring 2 and above, but no states have reached a score of 3 (Enugu: 1.5, Jigawa: 1.0, Kaduna: 1.5, Kano: 1.0, Lagos: 2.5)	Scores are lower than expected at this stage, but should improve by mid to late 2011 with the induction process for new SHoA members.
Indicator 4 - Quality of systems for scrutinizing public financial documents in the house	4 states score at least 2 out of 5, of which 2 state scores 3 out of 5 by mid to late 2011	5 states are scoring 2 and above, with 1 state scoring 2.5 (Enugu: 2.0, Jigawa: 2.0, Kaduna: 2.0, Kano: 2.0, Lagos: 2.5)	All states have improved on scrutiny, procedure and timing of the appropriation bill, but scored low on audit & query and member's capacity for financial and performance analysis. Scores are not likely to improve by mid to late 2011 with a new set of members coming into the house in June 2011.

The indicators suggest that progress has been ahead of target in relation to working with State House of Assembly support staff (indicator 2) and in terms of strengthening systems for House scrutiny of budget documents (indicator 4). Progress has been behind target for monitoring compliance with House rules and procedures (indicator 3) and improving public access to information (indicator 1). The induction programme will shortly come on stream following the state legislative elections in April 2011.

The Annual Review mission noted that SAVI has made substantial progress gaining access to and working with State Houses of Assembly. In most states the main focus of SAVI’s work has been on working with SHoA support staff, and strengthening internal systems. There has been less emphasis on working with House Members, although this will change with the induction programme supported by SAVI following the recent State Parliamentary elections. It is evident that there are marked differences between states in the effectiveness of State Houses of Assembly, with Lagos recognised as a clear leader.

In view of the progress reported in working with State Houses of Assembly, it appears likely that SAVI’s milestones will be largely achieved. Hence, a score of two against this output is justified. However, in reaching this judgement it is important to emphasise the risk that progress in systems building will not be sufficiently embedded to be sustained after SAVI completes its programme of support. The risks are greatest in the less performing State Houses of Assembly where systems and capacity are most evidently lacking and will take a longer time to embed. The suitability of SAVI’s approach to bringing about sustainable improvements in the working of State Houses of Assembly will be more thoroughly addressed at the Mid Term Review.

### Output 5 - Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches.

This logframe output has recently been reformulated to focus on external communication and the wider uptake of the SAVI approach. It includes two indicators:

- Accessibility of lessons learnt which are relevant and useful to other development partners.
- Commitment of other development partners to replicate key aspects of SAVI and its state partners' approaches.

Until recently SAVI has focussed mainly on internal communication and reporting to DFID. This is not oriented to the purposes of external communication. However, quarterly progress reflection and reporting systems are now more results focussed and serving to draw lessons for SAVI, DFID and external audiences. SAVI’s primary medium of communications with external audiences is face-to-face meetings through various networks and platforms (and as much informal as formal settings) and through joint planning and working with other SLPs.

SAVI recognises the importance of strengthening external communications, in particular to disseminate lessons learned and to promote the replication of its approach by other development actors.All five states teams have developed frameworks to guide their communications including with external audiences. SAVI is also working on the development of case studies to capture examples of how the project has supported particular episodes of change.

According to SAVI all 5 SAVI state teams now have at least 3 joint working relationships or other formal means of sharing lessons with development partners in their own states. It is unclear the extent to which these working lessons extend beyond operational coordination to the sharing of lessons and the broader uptake of SAVI’s approach.

In view of the level of progress achieved it is recommended to assign a score of 3 against this output (milestones likely to be partially achieved). Since SAVI recognises the need for improvement in its external communications, and has plans in place, there is a good prospect that SAVI will be able to improve its score against this output.

## Progress made towards achieving the project’s purpose
SAVI’s purpose is that civil society, state houses of assembly and government should demonstrate improved voice and accountability. There are three indicators to measure progress.

1. Replication of approaches to strengthening participatory governance demonstrated by SAVI and its state partners.
2. Peer review scoring of quality of governance in state houses of assembly – accountability & democracy.
3. Peer review scoring of quality of governance in civil society – inclusiveness, responsiveness, transparency and capability.

It is not possible to provide a complete assessment of progress against these indicators at this stage. The State Governance Baselines that are the source for the peer review scores covered by indicators 2 and 3 will not be updated until 2012. It is therefore not yet possible to report any change on the 2010 baseline scores. However, there are other sources of evidence that point to good progress against indicators two and three. SAVI's quarterly progress reports provide evidence of improvements in the working of State Houses of Assembly, including the use of public hearings in Lagos, CSO monitoring of House Committees in Jigawa and more in depth scrutiny of the 2011 budget (appropriation bill) by 4 out of 5 state assemblies. SAVI’s work under outputs 1-3 has contributed to an improvement in the quality of civil society governance within the organisations included in Advocacy Partnerships or connected with SAVI’s broader engagement with civil society, the media and State Houses Assembly (under output 3).

In relation to the first indicator, SAVI has listed 20 SAVI and non-SAVI partners who are reported to have adopted key components of SAVI's approach. However, the review team has difficultly with this indicator, which is vaguely defined and not suited to independent verification. It is not clear which elements of a ‘participatory governance approach’ would need to be adopted and to what extent to qualify as an instance of replication. In any case it is difficult to attribute the adoption of participatory governance to SAVI’s work given that much of SAVI’s approach is drawn from widely recognised good practice. It is recommended that SAVI should propose a more clearly defined and independently verifiable method for measuring replication and the scaling up of its approach to promoting voice and accountability.

The IMEP review team also recommends that an additional purpose level indicator should be included to measure SAVI’s contribution to bringing about tangible improvements in policy and implementation. This will provide a more immediate demonstration of SAVI’s effectiveness than longer term goals of replication and scaling up. The new indicator should seek to measure changes in legislation and policy (both the formulation and implementation of these) where it can be demonstrated that SAVI supported actions have played a significant role in bringing about change. Given measurement difficulties, a subjective rating scale may be adopted, but this will need to be supported by robust qualitative evidence on SAVI supported activities have contributed to particular change processes.

## Progress made in implementing the 2010 Annual Review recommendations
The review of the recommendations with the team in Abuja confirmed that good progress has been made on implementing the recommendations of the 2010 Annual Review. The most important measures include the termination of the small grants budget line, the redefinition of output 1 and 2, the more strategic focus on activities with strongest potential for demonstration and replication, the broadening of work in support of MTSS processes, the categorisation of Advocacy Partnerships according to their level of dependence on SAVI, the strengthening of SAVI’s communication strategy, and the review of SAVI’s oversight structures. SAVI has prepared a detailed matrix of these recommendations and actions taken (see annex 2). The general finding is that the recommendations of the 2010 Annual Review have been mostly implemented or are planned to be implemented over the next few months.

## Review of logframe
SAVI’s logical framework has undergone numerous revisions. The most recent in May 2011 is a significant improvement that addresses many of the concerns raised in the IMEP design mission report on SAVI (March 2011). However, the review team still have difficulties with certain aspects of the logframe and its indicators, which will need to be addressed in advance of the Mid-Term Review. IMEP will prepare a detailed set of comments on the logframe shortly after the submission of this Annual Review. The intention is to work with SAVI to arrive at a logframe providing a more succinct and straightforward description of SAVI with indicators that are more specific and amenable to measurement and independent verification. DFID will also be closely consulted in the process, and DFID’s agreement will be sought on the final version of the logframe.

General findings on logframe are reported in brief below. They will be elaborated in a forthcoming commentary on the logframe that will provide an input to further discussion with SAVI and DFID on the way forward.

There is a need for an additional indicator at purpose level to measure specific changes in policy and improvements in implementation that can be attributed to SAVI supported advocacy work. Under outputs 1 and 2 there is a need for additional indicators that would rate the capacity of Advocacy Partnerships to engage with and influence policy and budget processes.

There is a heavy reliance on the use of perceptions surveys and expert judgements covering broad aspects of governance for the construction of indicators. While these sources are useful and valid, it will be worth exploring additional sources of evidence that can provide more fact-based measures of changes in policies, budget processes and the performance of key voice and accountability institutions.

Several of the indicators are not measurable or reportable in a verifiable manner. This applies in particular to the first purpose level indicator (on replication), but also to then third indicator under outputs 1 and 2, and the first indicator under output 3. IMEP will work with SAVI to develop alternative indicators that are more specific and measurable. The indicators covering replication pose a particular challenge because it is vital to SAVI’s theory of change, but is subject to difficult problems of measurement and attribution.

As discussed in section 2.2.3 the presentation of output 3 in the logframe needs to be reformulated to describe SAVI’s work more clearly.

Several of the indicators need clearer definitions, including a statement of units of measurement that is used consistently in the definition of indicators, baselines and milestones.

# Key strategic issues
The ToRs request the annual review team to identify key issues to be considered in the Mid-Term Review. These are explored in the following sub-sections:

## Balance between states
The balance of support across states and whether this is appropriate for the maximization of impact and value for money.

SAVI implements a full package of activities in each of the five states. There are some variations in expenditure between Laos (greatest expenditure) and Jigawa (least expenditure). The initial view of the annual review team is that reallocating resources between states would not be justified on the grounds on maximising impact and value for money. While the political economy conditions are very different across the states, SAVI has demonstrated that its model is workable in both difficult and favourable environments. The project is working from a different baseline in different states, but there is the potential to add value in all types of situation. For example, the State House of Assembly is far better organised in Lagos than in Enugu, and the Lagos SHoA has been particularly receptive to SAVI support. However, even under the much less propitious environment in Enugu, SAVI does appear to have opened up valuable opportunities to work with the state legislature.

## Balance between outputs
The balance of support across thematic areas (Policy Advocacy, State House of Assembly Support etc), and whether more or less emphasis should be put on any thematic area or state.

The balance of support across SAVI’s outputs is indicated in the table below, which shows estimated expenditure to date and the share of the total budget against the five outputs.

Table 2 – Estimated expenditure against the five logframe outputs

Output	Estimated expenditure to date	Estimated share of total budget	Estimate % of total budget	Impact weight % (logframe)
1 - Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy and monitoring.	£1,223,715	£4,203,129	20.3	20
2 - Civil society demonstrates a replicable and sustainable approach to engagement in government budget and planning processes	£1,169,351	£4,138,764	20.0	20
3 - An enabling environment for policy advocacy and monitoring, and engagement in government budget and planning processes.	£1,066,350	£3,405,248	16.4	10
4 - Improved state houses of assembly systems for transparency, public engagement and financial oversight.	£1,276,837	£5,192,024	25.0	35
5 - Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches.	£1,149,940	£3,804,096	18.3	15

The table indicates that budgeted spending is concentrated on outputs 1,2 and 4, reflecting the logframe impact weights. However, spending to date has been more evenly distributed between the five outputs.[3] Spending on output 4 (State Houses of Assembly) appears to be well below the budgeted target. Even though this is now increasing substantially, it will remain below the level implied by the logframe impact weighting.
[3] This reflects an even pattern of spending between the five outputs in the inception phase. During the implementation more marked differences in spending between output areas are emerging, in particular the greater share allocated to supporting State Houses of Assembly (output 4).

The Mid-Term Review will analyse in further detail how the balance of spending between outputs varies between states. The initial impression of the review team is that such variations are quite significant. It will be important to examine how these variations reflect SAVI’s analysis of the particular opportunities and constraints within in each state (see S-DoC reports).

In the case of support for State Houses of Assembly (output 4) there is a strong case for a differentiated approach between states that recognises that the ease or difficulty of achieving SAVI’s objectives will vary between states. In some states the conditions may already be in place for the effective use of SAVI’s funds, whereas in other states SAVI cannot realistically expect that SHoAs will develop well functioning systems within the lifespan of the project. This is already reflected in the differences in SAVI’s approach between states. In individual states the logframe impact ratings for different outputs can vary by plus or minus 5% around the nationally agreed values, and levels of expenditure also vary substantially. SAVI Lagos reports that it devotes 45% of its time and resources to working with the State House of Assembly. In Enugu this proportion is much lower.

Following the inception review it had been recommended (as a broad guideline rather than fixed target) that SAVI should spend 50% of its resources in the State Houses of Assembly. This Annual Review recommends that this guideline should now be dropped in favour of an explicit recognition of the need for flexibility and adaptation to local conditions.

## The level of linkage and coherence between the programme components.
There is overall coherence between the programme components, which each address different aspects of strengthening voice and accountability in state level political processes. There are strong linkages between the Advocacy Partnerships under Output 1 and the APs working on budget and MTSS processes under Output 2. Output 3 activities seek to strengthen linkages between civil society, the media and State Houses of Assembly. In addition, the output 4 activities in the State Houses of Assembly help to create conditions for greater civil society and media engagement by strengthening SHoA oversight of budget processes and providing access to information. Output 5 serves to encourage lesson learning on voice and accountability, linkages with other development partners and broader replication of the approach.

The Annual Review team found that these linkages are generally working well, and serve to increase the effectiveness of SAVI’s work by connecting different actors working on voice and accountability. However, there is an important gap in relation to SAVI’s work with the media. SAVI’s media work is noticeably weaker than SAVI’s support to civil society and State Houses of Assembly. SAVI’s support to the media has included working with members of Advocacy Partnerships from media organisations, and seeking to strengthen media coverage of State Houses of Assembly and other governance processes under output 3. In practice these activities have tended to be rather ad hoc and modest in scale. The difficulties of working with the media have already been mentioned, but there is potential to scale up this work, and to gain leverage by working more systematically with the media to enhance its role in communicating on key policy and governance issues, encouraging public debate, and enabling political engagement. This could also include strengthening links between the media and other SLPs.

## State specificity
The extent to which the programme’s interventions are adapted to reflect state specific contexts

SAVI’s management structure is decentralised and provides each state team with considerable latitude to adapt the programme’s interventions to the local context. As discussed in section 3.2 the balance between programme outputs varies between states. In addition, the issues addressed by the Advocacy Partnerships differ between states. SAVI has invested in state level analysis, including the State level Drivers of Change (S-DoC) studies, which played a key role in identifying issues with local political traction and in informing the programme’s strategy for engagement in the state. SAVI is due to update the S-DoC studies before the Mid-Term Review, and also undertakes regular reviews of the state political context (reported in the quarterly progress reports).

## Linking short- and long-route accountability
How the programme should make the link between grassroots engagement with service providers and high level policy advocacy

SAVI’s inception review recommended that SAVI should focus exclusively on ‘long-route accountability’, which operates through the state level policy process. Short route accountability, which operates between service users and service providers at the point of service delivery, would be left to ESSPIN and PATHS2 through their work with School Based Management Committees and Facility Health Committees. While this separation has helped SAVI to define a clear and manageable role, it has arguably led to an unintended disconnect between the two routes to accountability. In particular, it is not clear how messages generated through short-route accountability are expected to be aggregated and fed upwards to the state policy process. This makes it difficult for SAVI to engage with the critical set of issues regarding the implementation of policies on the ground.

While it is clear that SAVI does not have the resources to engage in short-route accountability work, there are viable options to bridge this important gap in the accountability chain. In particular PATHS2 and ESSPIN have strengthened their voice and accountability work, and while differences in approach remain between these programmes and SAVI, there are now better prospects to make the connection to the state policy process. This will require strong coordination between SLPs around specific opportunities where short route accountability identifies common problems in service delivery that require higher level engagement in state policy processes. [4] SAVI could work more actively with its Advocacy Partnerships to encourage members to strengthen their presence at the grassroots level, to capture evidence on how service delivery is experienced at the local level, and to engage in local accountability processes. This approach has proven successful in Lagos State, where the SAVI supported LACSOP network has strong linkages at community and LGA level. However, such connections are not so strong elsewhere.
[4] There are some existing examples of where SAVI’s work on long route accountability has been linked to SLPs working on short route accountability. These could serve as a model for more systematic joint working. For example, SAVI Kano in collaboration with PATHS 2 sponsored CSOs working on free MNCH to undertake a survey to assess the health facilities these services. Similarly in Jigawa, SAVI has linked ESSPIN and PATHS 2 with CSOs who are currently working with School Based Management Committees and Facility Health Committees. Information CSOs receive from this lower level have been fed into their advocacy work at the state level.

## Engagement at the local government level.
Whether the programme should engage at the LGA policy level in addition to the state level.

It was reported to the Annual Review mission by numerous stakeholders that many of the blockages in service delivery occur at the LGA level. For example, LGA decisions about the deployment of resources and manpower shape the way in which state level policies for Free Maternal and Child Health are experienced on the ground. There is an ongoing debate in DFID about whether and how it programmes should seek to strengthen engagement at LGA level. LGA level engagement could also help to bridge the gap between short- and long-route accountability discussed in 3.5 above. However, it is clear that it will be very challenging for SAVI to engage at LGA level given its modest resources and organisational structure. This raises the question as to whether SAVI should engage at LGA level, or whether this should be left to other DFID programmes (or new programmes like M4M).

There are a number of options for LGA engagement by SAVI:

- Engagement with selected LGAs participating in the Conditional Grants Scheme (this option is already under discussion and likely to go ahead).
- Encouraging and supporting members of Advocacy Partnerships to engage at LGA level. For example, in Lagos the LACSOP network of CSOs has developed around strong LGA connections. In turn this helps LACSOP members to be effective advocates at state level. In Kaduna some of SAVI’s civil society partners are engaged in LGA level activities through their short-route accountability work with PATHS2 and ESSPIN.
- Engaging with LGAs on selected new issues, for example in relation to the delivery of primary health services through SAVI’s planned partnership with PRRINN-MNCH.

In all options there will be a need for SLP engagement with LGAs on strengthening public financial management processes.

## The Mid-Term Review will examine the question of LGA engagement in greater depth based on a more thorough assessment of how LGA political processes are affecting the issues and sectors covered by SAVI. Approach to working with State Houses of Assembly
SAVI’s support to State Houses of Assembly is based on an evolving approach that varies according to the conditions in different states, has been informed by the self-assessment exercise undertaken by SHoAs, and is both strategic and opportunistic. There has tended to be a greater focus on working with SHoA support staff than with SHoA Members. However, SAVI is about to begin a major induction programme for new Members following the state legislative elections. There has also been a greater focus on strengthening internal systems within State Houses of Assembly rather than seeking to strengthen linkages between SHoAs, constituencies and MDAs. This summary review has not been able to evaluate in depth whether this focus has been appropriate, or whether it needs to change. However, it has served to highlight a number of issues and key questions for the Mid-Term review:

How can SAVI promote stronger linkages between SHoA members and their constituencies? It is reported that constituency meetings are not frequent, and that SHoA members are not keen to meet with constituents because of the demands for patronage that commonly arise from such contacts.

How can SHoAs interact more effectively with the political executive? The State House of Assembly’s connections with MDAs are generally weak, and will need to be strengthened for the SHoAs to perform a more effective oversight role.

How can SHoAs strengthen their key legislative functions (drafting and reviewing legislation and overseeing budgets)? At present SHoAs generally operate in a perfunctory or reactive manner, and rarely take the initiative in proposing legislation or demanding budgetary changes.

How can SAVI help connect SHoAs with local sources of expertise and technical skills (universities, policy think tanks, private companies etc.)?

To what extent will the improvements to SHoA systems prove to be sustainable after the SAVI programme is completed? Many of the required changes may take 10-15 years to complete, well beyond SAVI’s lifespan.

## Expansion in the North
The implications of the possible expansion of the project into additional states on the approaches and programme of work in the existing focus states.

As requested by DFID, SAVI has put forward an approach to working in Yobe, Zamfara and Katsina states. This will begin with SAVI working as an embedded unit within PRRINN-MNCH. This represents a manageable and pragmatic way for SAVI to operate in the new states with its modest resources. However, there is a question as to whether this light touch approach will allow SAVI to engage in long-term relationship building with a wide range of actors, as it has done in the five existing states. SAVI’s initial activities in the new states will need to be seen as a first step in a longer-term and more comprehensive strategy for strengthening voice and accountability in the new states.

The question will be revisited at the Mid-Term Review, which may include visits to the new states and in-depth discussions with PRRINN-MNCH on planned collaboration.

## Lesson learning and sharing knowledge
SAVI’s performance in generating and sharing knowledge to support continuous learning within the project, and with actors involved in state government development across the country.
As discussed in section 2.2.5, SAVI’s lesson learning and knowledge management have mainly been internal to the programme rather than being oriented towards an external audience. However, as the programme approaches its mid-term there needs to be a much stronger focus on external communication in order to realise SAVI’s purpose as a demonstration project leading to replication. SAVI has identified external communication as requiring greater attention from now on, and has developed a plan to strengthen this. The adequacy of these plans and progress in implementation will need to be examined in depth at Mid-Term Review.
There appears to be a particular opportunity for the sharing of lessons between SAVI and the increasing number of DFID voice and accountability programmes in other countries. In particular, there would be value in sharing experience on the relative effectiveness of different operational models employed by voice and accountability programmes, and approaches to monitoring and evaluation (including the measurement of results and value for money).

## Performance Management System
The adequacy and effectiveness of the programme’s performance management system in helping steer the project’s intervention strategy and approaches to ensure project efficiency and effectiveness.

SAVI’s performance management system comprises its logframe and indicators, regular reflection meetings at state and national level, state level workplans, quarterly and annual progress reports (at state and national level), and external reviews. The initial view of this Annual Review is that SAVI’s process of internal reflection is working well and is enabling the sharing of ideas across states, as well as effective central oversight and strategy setting. SAVI’s work plans appear to be used as an effective management tool, are regularly updated and linked to budget provisions. However, as discussed in section 2.5improvements in the logframe are required.

SAVI‘s quarterly and annual reporting process provides valuable information on programme performance. The requirement to report on results has helped SAVI’s teams in the states and in Abuja to focus on critical aspects of programme performance. However, it is clear to the Annual Review team that the reporting process is quite burdensome on staff time. In part this reflects the complexity of the logframe (this is mirrored in the structure of the progress reports) and the difficulty of assessing progress against certain indicators. The structure of the reporting formats is rather heavy requiring reporting against every output and subindicator every quarter in every state. At the same time systematic reporting on activities delivered and progress against workplans is lacking (see 2.1). There is a sense that the present reporting formats are neither serving SAVI’s performance management purposes nor meeting DFID’s oversight needs. The Mid-Term Review will need to consider in greater depth the strengths and weaknesses of reporting formats, the needs of different users and the scope for simplification.

## Gender and Social Inclusion
The extent to which gender and social inclusion aspects have been adequately addressed in the design and application of the project’s activities, tools and approaches.

Gender and Social Inclusion has been addressed by SAVI in several ways:

- There is a strong focus on analysing gender relations and social inclusion issues in the S-DoC studies.
- Several states have Advocacy Partnerships focussed on gender and social inclusion issues (e.g. Lagos People With Disability, Enugu Inclusive Education, Kaduna Gender Working Group, Kaduna MNCH, Kano MNCH, Jigawa MNCH)
- All Advocacy Partnerships have been encouraged to consider gender and social inclusion as cross-cutting issues.
- SAVI’s staffing is well gender balanced.

These mechanisms appear to be working relatively well, but will need to be further examined at Mid-Term Review. One apparent gap is the lack of gender disaggregated indicators for monitoring programme performance, although SAVI has proposed gender specific indicators under output 3 (to be discussed further with SAVI).

## Programme oversight arrangements
SAVI’s oversight arrangements at state level include the Technical Executive Committee and the State Advisory Panel, which are specific to SAVI, and the State Steering Committee, which covers all of the State Level Programmes. These arrangements were not assessed by the Annual Review, but are generally acknowledged to be ineffective and undermined by lack of participation. There are differences between states with the programme oversight bodies being somewhat more functional in the North. Generally the expected functions and level of participation of these oversight bodies may have been unrealistic. The MTR will need to examine in depth the reasons for the underperformance of programme oversight arrangements and options for reforming these bodies on a state-by-state basis.

## Cross-SLP coordination
The review mission provided a mixed picture of state level coordination with substantial variations in the closeness of working relations between the State Level Programmes in different states. Good working relations were observed in Kaduna and Lagos, but everyday contacts between programmes appeared less frequent in Enugu and Kano. The review team encountered many good examples of SLPs working together on joint activities, but also some missed opportunities. This will be examined more systematically during the Mid-Term Review, which will assess in detail where there is scope and need for joint working, to what extent this has been realised, what value has been added, and where are the remaining gaps.

State level coordination appears to have improved over the past year. The Big Common Impact Areas (BCIAs) appear to be a useful management and monitoring tool that is helping SLPs to focus on collective goals through an agreed division of labour. Joint strategising by SLPs on political engagement at the state level has also been helpful. This will be supported by the imminent appointment of DFID state level representatives.

An additional question for the Mid-Term Review is whether and how SAVI should engage with the new GEMS3 project on business environment issues. The ENABLE programme currently covers demand side activities in this area, but options will need to be considered for the period after the completion of this programme.

In assessing cross SLP coordination, it is important to stress that SAVI alone cannot address all of these issues. This will require an effort across the SLPs backed by DFID. The mid-Term review process for SAVI and the other SLPs will be geared towards establishing where responsibilities for coordination lie, which specific coordination processes need to be strengthen and by whom.

## Measuring Value for Money
This Annual Review has not been able to assess value for money in a systematic way because of the lack of time and the lack of suitable indicators. However, the initial impression gained is that SAVI is achieving significant results with modest resources. In terms of economy SAVI has been able to contain its costs by making limited use of long-term expatriate TA. In terms of efficiency it is worth noting that SAVI is delivering significant outputs at state level on the basis of a relatively light resourcing and staff. In terms of effectiveness there are very large potential benefits to be gained from SAVI’s work in influencing policy change, bringing about more effective public financial management and promoting replication of its approach.

The Mid-Term Review will attempt to generate evidence on value for money on the basis of guidance on a measurement approach from IMEP’s VfM expert. It is unrealistic to expect to be able to provide precise measures of value for money, except perhaps in terms of economy and comparative unit costs. However, it should be possible to construct solid arguments about efficiency and effectiveness based on careful weighing of the evidence and comparison with benchmark programmes (EU SRIP in Nigeria and DFID voice and accountability programmes in other developing countries could be useful comparators). The proposals for additional indicators at purpose and output level should help to strengthen this evidence base. SAVI is able to provide disaggregated expenditure data by output, which will make it easier to establish the costs of specific deliverables.

# Conclusions, recommendations and next steps
The findings of this annual review provide a generally positive assessment of SAVI’s progress and performance. The output scores indicate that the programme is generally on track to meet its milestones as defined in the existing logframe. The recommendations of the 2010 Annual Review have mostly been implemented. SAVI’s approach has been found to be coherent and well suited to bringing about change in Nigeria’s political economy context. The programme has followed good practice in its way of working with demand-side actors to strengthen voice and accountability. It is implemented by a high quality team that is hard working, committed, thoughtful and well-managed.

On the basis of this light touch summary review it is not appropriate to make far reaching recommendations that would require a significant change in direction of the programme. Most of the recommendations in this report and specified in the ARIES form relate to the need to tighten the logframe and indicators. A separate note will shortly be provided bringing together the team’s comments and recommendations on the logframe. There are certain gaps and weaknesses in the programme, which do not require immediate action, but should be actively discussed in advance of the MTR, and suitable implementation options prepared. These priority areas include:

- Strengthening SAVI’s work with the media (see 3.3)
- Bridging the gap between short-route and long-route accountability (see 3.5)
- Considering options for engagement at LGA level (see 3.6). The proposal to work with LGAs participating in the Conditional Grant Scheme is DFID’s preferred option at this stage.
- Addressing questions relating the strategy for engaging with State Houses of Assembly (see 3.7)
- Preparing for the expansion of SAVI’s activities into the new northern states (see 3.8)
- Addressing weaknesses in programme oversight arrangements (see 3.12)

The next steps for IMEP support to SAVI prior to the Mid-Term Review include:

- Preparation of detailed comments and suggestions on the May 2011 version of the logframe for discussion with DFID and SAVI.
- Agreement on other areas of IMEP support to SAVI including technical assistance on indicator and survey design.
- Agreement on refinements to QPR that will strengthen routine monitoring.

Annex I – Terms of Reference
Annual Review of
State Accountability and Voice Initiative (SAVI)

Background
1. SAVI is one of a suite of State Level Programmes (SLPs) including SPARC (State Partnership for Accountability, Responsiveness and Capability), ESSPIN (Education Sector Support Programme in Nigeria), PATHS2 (Partnership for Transforming Health Systems 2, and GEMS (Growth and Employment in States).
2. SAVI currently focuses on 5 states, Enugu, Jigawa, Kaduna, Kano and Lagos) and is planning to expand into 3 additional states.
3. The main areas of support provided by SAVI are:
- Support to civil society organizations to improve their capacity and performance in conducting advocacy work around specific policy issues and in influencing and monitoring state government planning and public financial management.
- Strengthening the capacity and performance of the State Houses of Assembly in executing their oversight role in relation to the state executives.
- Supporting the demonstration and replication of the approaches supported by the programme.

The Mid-Term Review of SAVI is scheduled to occur towards the end of the current year.

Review Objectives
The objective of the review is to assess project progress and performance to-date and especially since the 2010 annual review. In addition, the review will identify key issues to be followed up in the Mid Term Review of SAVI later in the year.
As this is a ‘light-touch’ annual review the review team will not seek to review performance issues in depth in every state. The review team will be expected to make a recommendation on the performance score to be given to the project (to the extent possible, based on the information available).
The summary annual review report will be used by DFID-Nigeria to decide upon the final project score which will be entered into the ARIES system. IMEP will conduct a fresh programme performance scoring as part of its conduct of the MTR which will be conducted several months later, and will not be constrained by the results of this review when it is doing so.

Recipient
The primary recipients of this review are DFID Nigeria and the Government of Nigeria.

Aspects to be covered by the review
The Review Team will carry-out the following:

I	REGULAR REVIEW TASKS

1. Conduct a review of the performance of the project to-date in terms of:
1. Progress made in the implementation of the SAVI activity plans (the Activity Log and the 2010-2011 annual work-plans), together with the reasons for the level of progress made.
2. Progress made in achieving the project logframe outputs and relevant sub-outputs, including the quality of these.
3. Progress made towards achieving the project’s purpose[5].
  [5] It is recognized that there are some methodological limitations with the assessment of the progress made in achieving the programme’s outputs and purpose because in a summary review the review team will depend to a large extent on the programme’s own performance assessment.
Review the progress made in implementing the agreed recommendations from the 2010 Annual Review.
3. Review the adequacy of the programme’s current (approved) logframe, and make recommendations on required improvements to this (and any proposed revised logframe.

II	ADDITIONAL REVIEW TASKS
4. Review the extent to which the programme is currently monitoring and reporting on value for money, as well as its capacity to do this in terms of the alignment of financial and results monitoring systems.
5. Review the performance of the programme in harmonizing its approaches with those of the other DFID-supported state-level programmes in order to maximize the potential combined outcomes and impact in the focus states.
6. Review the functionality of the programme’s coordination and management arrangements, including those involving implementation partners at state level (eg State Advisory Panels, Technical Committees etc).
7. Review the nature and scale of resourcing of the different components of the programme, including of staffing, within each state and overall.
III	PREPARATION OF THE MID-TERM REVIEW
8. Make recommendations on the key issues to be considered in the Mid-Term Review of the programme planned for later in the year. These issues may include the following (amongst others):
  1. The balance of support across states and whether this is appropriate for the maximization of impact and value for money.
  2. The balance of support across thematic areas (Policy Advocacy, State House of Assembly Support etc), and whether more or less emphasis should be put on any thematic area or state.
  3. The level of linkage and coherence between the programme components.
  4. The balance of support between ‘capacity building’ and increasing ‘demand’ for better governance and improved service delivery.
  5. The extent to which the programme’s interventions are adapted to reflect state specific contexts.
  6. How the programme should make the link between grassroots engagement with service providers and high level policy advocacy,
  7. Identifying the most effective approach to supporting State Houses of Assembly.
  8. Whether the programme should engage at the LGA policy level in addition to the state level.
  9. The implications of the possible expansion of the project into additional states on the approaches and programme of work in the existing focus states
  10. SAVI’s performance in generating and sharing knowledge to support continuous learning within the project, and with actors involved in state government development across the country.
  11. the adequacy and effectiveness of the programme’s performance management system in helping steer the project’s intervention strategy and approaches to ensure project efficiency and effectiveness.
  12. the extent to which gender and social inclusion aspects have been adequately addressed in the design and application of the project’s activities, tools and approaches.
9. Make recommendations on the data collection and analysis preparations which should be made by the programme for the forthcoming MTR.

Review Organisation and Coordination
The review team will consist of one international (Gareth Williams) and one national consultant (Maisha Strozier) from the Independent Monitoring and Evaluation Project for the SLPs (IMEP). Another international consultant (Alex Duncan) who will participate in the MTR will be available for some days as resource person. The team will be guided and supported in its work by the IMEP team based in Abuja led by the National Team Leader (Tony Curran). This team will lead on organizing the logistics of the review.
The team may be accompanied in some of its meetings by members of the DFID Nigeria Governance team and the DFID-N Results Adviser.
The draft Summary Annual Review report prepared by the IMEP team will be quality assured by Anneke Slob, IMEP Project Director.
The lead DFID Governance Adviser for SAVI (Scott Caldwell) will be responsible for coordinating the review on DFID’s side. He will be supported by Odumu Ebegoyne, Programme Officer, Governance and Social Development Team (DFID Nigeria) who will cover logistics and planning aspects.
IMEP will be responsible for preparing the review report. IMEP will submit the draft report to DFID-Nigeria (i.e. to the lead adviser for SAVI Scott Caldwell, the SLPs Coordinator Alicia Herbert and the Results Adviser Esther Forgan) and to the SAVI team leader for comment.

Methodology
1) Prior to the review SAVI will prepare a document presenting its assessment of the programme’s performance in terms of the logframe result indicators and milestones and activity log milestones (for December 2010). This document will provide succinct summaries of the evidence used to make the assessments.
2) The review team will review performance evidence for all of the States where SAVI is operating, but will limit its field-visits to Lagos and Kaduna states. . The team will seek to arrange interviews with one or more SAVI team members from one or two other states either in Kaduna or Abuja.
3) The review will consist of pre-mission document review, meetings with SAVI and DFID, together with some meetings with a number of representatives of CSOs, state governments and State Houses of Assembly.
4) The main findings and recommendations of the review will be presented to a meeting of SAVI management and technical staff at the completion of the mission, in order to elicit initial reactions and to correct any factual errors. There will also be a final wrap up meeting / presentation with DFID.

Consultant Inputs

Skill Area	Category	No of days
Governance specialist (V&A) / (Gareth Williams)	International (TL)	10 days (1 prepn; 6 field-work; 3 write-up and finalization)
Governance specialist (V&A) / (Maisha Strozier)	National	9 days (1 prepn; 6 field-work; 2 write-up and finalization)
Governance specialist (V&A) / (Alex Duncan)	International	4 days (1 prepn; 3 resource/field-work)

Reporting
The IMEP team will produce the following reports:
- A short report (max. 20 pages) responding to the requirements outlined above.
- A completed Aries Annual Report Excel spread-sheet including recommended scores.
The IMEP report and spread-sheet will be supplied to DFID within one week of the completion of the mission.
DFID will share the draft review report with SAVI and its principal federal and state counterparts for comments – which will be expected to be provided within one week (ie within two weeks of the completion of the mission).
The IMEP team will produce the final report within one week of receipt from DFID of the collated comments.

Timing
The schedule for the conduct of field work and report submission is presented in the table below.

Stage/Activity	Timing
Conduct of in-country review	30 May to 3rd June
Submission of draft report by IMEP to DFID.	Friday 10th June
Submission by DFID of comments on draft report.	Friday 17th June
Submission by IMEP of final report	Friday 24th June

Annex II
## Action on July 2010 OPR Recommendations – Progress to Date (May/June 2011) – Report by SAVI

Executive Summary

Selected Recommendations
S/n	Recommendation	Action Taken/Required	Responsible
1	SAVI should introduce bi-annual structured reviews of each state portfolio of APs categorising them according to their level of independence and the level of staff support partners required from SAVI.	Covered below (8)
2	SAVI should terminate the Project Fund in the Small Grants Budget Line, which is in danger of creating unnecessary dependency, and incorporate this into overall programme funding.	Covered below (9 & 16)
3	As SAVI is seeking to demonstrate a replicable advocacy methodology, SAVI should select new APs on the basis of maximising the demonstration effect i.e. involving wholly new partners possibly in wholly new sectors - in addition to selecting issues with traction and buy-in across Civil Society and Government.	Covered below (10)
4	SAVI should draw on experience to date, as well as cross-SLP knowledge and linkages, to assist Output 1 APs to nuance and target their advocacy arguments onto priority actions that are achievable in their State context, and to move into Output 2 activities, once policies and bills are in place.	Covered below (12)
5	SAVI should simplify and sequence its Indicators for Outputs 1 and 2 to focus on the scaling up of impact over time.	Covered below (14)

Programme & Logframe
Programme Impact
S/n	Recommendation	Action Taken/Required	Responsible
6	SPARC and SAVI should commission updated political economy analyses to inform programme development after the 2011 elections.	Lead states and new states: 3 months after elections (scheduled for July-Sept 2011) / Sensitisation of other SLPs on need for political engagement – done / Consult CS partners in process and output of PE/S-DoC update (July-Sept 2011) / More in-depth analysis of new composition of SHoA (members, key support staff, relations with ExCo, external influences, etc) (initiated through induction process, ongoing, will continue July-Sept 2011) / To cover analysis of media orientation, from S-DoC update (July-Sept 2011) / Needs to feed into political engagement work with all SLPs linked to BCIAs (post October 2011 MTR) / ... and with CS partners to strengthen their advocacy strategies (Oct/Nov 2010) – done (needs repeating for Oct/Nov 2011)	Senior mgt of SPARC/SAVI + PRRINN-MNCH support / SPARC lead on follow-up to BCIA work / In TORs for lead consultants – looking to use SAVI national TA (Ishaya & Adam) under supervised from Soji / Simon, Soji & James from existing PE into current work, updates to feed into later / Ishaya & Soji with existing CS partners
7	DFID and the SLPs should consider focusing resources on States where State Government political will to reform provides the potential for opportunities to promote sustainable systems of good governance.	Key consideration in exploratory engagement in new states – done, reflected in state scoping studies, decisions taken by DFID on Yobe, Zamfara, Katsina and Ekiti / Needs: criteria, cut-off point (mid-term review), link to PE updates? progress against MOU indicators – done: all used	SAVI/SPARC / DFID, SG, NPC

Outputs 1 & 2
S/n	Recommendation	Action Taken/Required	Responsible
8	SAVI should introduce bi-annual structured reviews of each state portfolio of APs categorising them according to their level of independence and the level of staff support partners required from SAVI. This review suggests a three stage categorisation: / Stage 1: “incubation” phase, when AP partners require intense support; / Stage 2: “call down support”, when AP partners take forward their own work programme but occasionally call upon SAVI for technical advice and support; and / Stage 3: “SAVI Community of Practice” when AP partners are confident and independent in their ongoing advocacy activities, but remain part of the wider SAVI community of practice, participating in periodic structured opportunities for mutual support, sharing experiences and lessons.	Discuss while developing new targets and milestones in state LFs under indicators 1.1-3 and 2.1-3. Use as basis of setting criteria for deciding with AP partners what stage they are at. – done / AP portfolio assessment > feed into quarterly reporting and OPR reporting formats (e.g. updated 2 page state summaries) – done in preparation for May/June 2011 MTR / Broad reflection and revision of existing framework for ‘developing effective partnerships’ to better reflect this 3 stage demo process – done during February 2011 TGM in Kaduna, to be further developed/defined during August 2011 TGM	Core team with each state team / SAVI senior mgt discuss with DFID-N (their needs), / core team to discuss own and state teams needs / Core team > feedback and broader reflection with core ST-TA
9	SAVI should terminate the Project Fund in the Small Grants Budget Line and incorporate this into overall programme funding.	Explain to GRM (Huw & Jo) – done / Change SAVI chart of accounts – done, may need adjustment after contract amendment No.3 / Needs contract amendment – No.3 awaiting finalisation / Change SAVI workplan, budget, forecasting, financial reporting formats – done	Senior mgt / Huw & SAVI finance team / Jo / Core team
10	SAVI should select new APs on the basis of maximising the demonstration effect of the SAVI methodology i.e. involving wholly new partners possibly in wholly new sectors, who have not previously been exposed to the methodology. This is in addition to selecting issues with traction and buy-in across Civil Society and Government.	Extra support to Lagos and Enugu to strengthen their AP portfolio to address BCIAs and review approach to Output 2 work (LG > SG level/sector), but also reflect on in other states – done, all state portfolios to be reviewed after July-Sept 2011 S-DoC updates and any new AP work selected on this basis	Core team support to state teams in conjunction with LF & WP updates
11	Two issues raised in the inception Review and Mini Review remain pertinent to the selection of APs and AP activities. APs that rely on donor-brokered channels for communication with State or Local Government (through, for example, sector SLPs) need to be wary of building a dependence on communication platforms and processes that may be unsustainable. Secondly, where APs work very closely with Government, they need to consider carefully if and how they are remaining accountable to the poor and marginalised people whose interests they are seeking to promote, and to what extent they are providing technical support in fulfilment of the Government’s own agenda. / There are no straightforward conclusions to draw in relation to the above 2 issues – but it is important for SAVI and SAVI partners to continually reflect on the complex issues of their own accountability and the sustainability of the processes they are engaged in.	Without compromising SAVI approach to demonstrating a (longer-term) sustainable, replicable approach on key issues (aka BCIAs), intensify activity on these issues >>> MTSS and CGS are cases in point. – done: work on both intensified across SLPs / Negotiate broad resource requirements (programme staff and TA) with DFID & SLPs (i.e. potential for cross-SLP V&A resource transfer: e.g. other SLPs second a V&A SPO to SAVI state team) to tackle this within the V&A work of other SLPs linked to BCIAs – this is now historical: SAVI is looking at establishing ‘SAVI units’ in other DFID programmes/SLPs to extend and scale-up SAVI learning. Also from TA to TA across SLPs – will require joint working/learning arrangement – agreed with DFID in the case of PRRINN-MNCH in new northern states, with mentoring from SAVI state teams in nearest lead states, but not agreed with other SLPs in lead states – subject for discussion during October 2011 MTR ? / Continue liaising with Soji & James on these issues, feeding into DFID’s thinking for reconfiguring present SLPs and extension into new states, prior to (August) and in the course of the next state visits (early Sept) again, this is now historical: new direction/thinking has emerged from this – also with Simon, now taking the lead on cross-SLP PE work at state and federal level.	Core team > each state team > other SLPs / Senior mgt with DFID & other DFID programmes / Core team
12	SAVI should draw on experience to date, as well as cross-SLP knowledge and linkages, to assist Output 1 APs to nuance and target their advocacy arguments onto priority actions that are achievable in their State context, and to move into Output 2 activities, once policies and bills are in place.	State AP portfolio audit – review of each state programme’s focus (draw out the lessons from existing Output 1 APs, move those that can into Output 2 activity, and cut those that can’t) now historical: we have a new differentiation between O1 and O2 APs (issue based and process based) in which advocacy and monitoring happen in both – see revised LF	Core team > each state team
13	Issues to consider as part of this include facilitating the involvement of CS in the whole MTSS process as opposed to MTSS policy formulation only; cross SLP attention to blockages in the budget process; and the possibility of collaboration with SPARC on piloting monitoring of the Conditional Grants Scheme in selected States.	MTSS related recommendation: now being addressed by SLP coordination meetings in states progress – pilot work in Kaduna and Lagos with PATHS2 is emphasising this need: clear links to budget realism and project monitoring work – done: this is now the core of the work under Output 2 in all states, each state has an AP focussed on broad engagement in govt budget & planning processes. / CGS related recommendation: doesn’t tally with SAVI’s area of operation (CS/media/SHoA> ExCo>MDAs), CGS operates outside key state structures, SAVI presently has no plans or resources to engage at federal level to track policy & budget. C4C is working at this level. Suggest other SLPs that also work at this level should coordinate on this, with C4C, where there is potential impact on BCIAs > MDGs / Alternatively: SAVI core team to explore how it might establish and support a CS/media/NASS/ FG partnership in Abuja to work with other SLPs on CGS policy monitoring/budget tracking (NB. avoiding programme creep and overload on SAVI state teams). This has implications for SAVI’s resource requirements – this is the option now being explored, and linked to cross-SLP federal/ national level PE work. / Initiate discussions with AAN on CGS monitoring history/potential and their possible lead, with AP-type support from SAVI Abuja – awaiting establishment of SAVI ‘federal unit’ to take up this and other related engagement work. Other CS groups with federal/ state linkages and interest (e.g. SWEBNET) also being targeted.	Core team to follow this up with each state team / Senior mgt to discuss with DFID, SPARC and C4C / See below: / Senior mgt to discuss with AAN (+DEC to ground-truth) > core team > DFID
14	SAVI to simplify and sequence its Indicators for Outputs 1 and 2 to focus on the scaling up on impact over time: indicator 1 focusing on technical advocacy skills including attention to social inclusion; Indicator 2 focusing on partners’ satisfaction that their voice is being heard; and Indicator 3 on processes of replication and snowballing.	Done at programme level > still needs rolling out in the states and state teams still need to establish new milestones and targets in LFs to reflect – all done. Further modifications advised by DFID: ‘partners’ satisfaction that their voice is being heard’ incorporated into Indicator 1; ‘partners diminishing dependency on SAVI’ is now the focus of Indicator 2.	Core team > each state team

Output 3
S/n	Recommendation	Action Taken/Required	Responsible
15	SAVI to revise wording of Output 3 to more accurately reflect the way that this Output is now being used i.e. SAVI staff pro-actively brokering an enabling environment for collaboration between CSOs, SHoA and media, to complement existing APs, foster the development of new APs and contribute to constructive working relationships amongst demand side players.	Done at programme level > sill needs rolling out in the states and state teams still need to establish new milestones and targets in LFs and activities in WP to reflect – done	Core team > each state team
16	SAVI to terminate “Rapid Response” funding in the Small Grants budget line, and reintegrate into programme funding.	Ref to recommendation 9 above – done but awaiting finalisation of contract amendment No.3

Output 4
S/n	Recommendation	Action Taken/Required	Responsible
17	DFID to expedite confirmation of the SHoA TA appointments as soon as possible.	done

Output 5
S/n	Recommendation	Action Taken/Required	Responsible
18	SAVI should distinguish: / Organic processes of “snowballing”/replication as AP partners take on new advocacy issues or other CSO partnership adapt aspects of the SAVI methodology drawing on their personal exposure and personal contacts. These processes form part of Outputs 1 and 2; / Structured processes of reflection, recording and dissemination on: / lessons learned on advocacy processes, drawing on AP partners’ experiences to communicate to civil society/SHoA/media on working on V&A; / SAVI’s experience to communicate to donors/SLP partners/others seeking to support civil society/SHoA/media on V&A.	Done at programme level > still needs rolling out in the states and state teams still need to establish new milestones and targets in LFs to reflect – all done.	Core team > each state team
19	Both structured processes should form part of Output 5. SAVI to refine its Communications Strategy to consider the range of audiences and appropriate means of communication.	In progress, core team to revise, get input from each state team, and feed into revision of their workplans under Output 5, and the programme level workplan. Then harmonise and strengthen the frameworks (KM&C + M&E) for this & update LF milestones, targets and sources to reflect – all done.	Core team > each state team. Then Toyin & Adam, with additional input from Renee in early December

SLP Co-ordination
SLP Co-ordination
S/n	Recommendation	Action Taken/Required	Responsible
20	DFID and SPARC to agree a SAVI-related indicator for the SPARC Purpose to reinforce complementarity between the 2 programmes.	[Quality of governance in State & Local Government – inclusiveness, responsiveness and transparency] / Discuss with Chris and John before SPARC’s next PDG meeting (target week of 23-27th August) so far agreed with DFID: passage of key fiscal legislation – done, but DFID recommend this still needs looking at across both programmes LFs by IMEP. / Also discuss points of linkage between SAVI & SPARC LFs on support to SHoA budget oversight function (purpose?, output?, state level matrices?) need to take action on	Core team on M&E
21	DFID, SAVI and sector-based SLPs to work towards the development of reciprocal LF indicators to clarify complementary relationships between the SLPs and embed these in monitorable working practices.	[G2. ??? New indicator linking SAVI with all other SLPs on improving means to achieving big common impact areas ???] Continue liaising with Soji & James on this issue, from BCIA workplans up into state and programme LFs, feeding into DFID’s thinking for reconfiguring present SLPs (scoring on LF as the key incentive) and extension into new states, prior to (August) and in the course of the next state visits (early Sept) initial expectation that this will fall out of the BCIA work has been stalled, awaiting outcome of SPARC follow-up (PE push) around the states – as yet unresolved, DFID recommend this needs looking at across all programmes LFs by IMEP, for SAVI at Super Goal level. / Discuss with Scott, as part of internal DFID LF revision process – done, repeatedly, but deferred to IMEP / Ensure complementarity of community level V&A (sector SLPs) with policy level V&A (SAVI) through process of developing BCIA workplans (reflected in state LFs?) progress in practice with ESSPIN V&A team, state and national thru policy advocacy work in Kaduna, Jigawa, Kwara and Enugu; potential with PATHS2 V&A team, state and national, thru CS>MTSS pilot work in Kaduna & Lagos. More pressing now, SAVI needs to ensure complementarity of ‘issue-based’ impact focussed work and ‘process focussed (e.g. budget realism, MTSS) work with other SLPs – not yet resulting in conscious harmonisation of LF indicators across the programmes: again deferred to IMEP to address.	Core team, SPARC, DFID (Esther, Scott) / Senior mgt / Core team > state teams / Core team + state teams > SPARC during BCIA follow-up work (PE)
22	The V&A working group should agree and communicate a cross SLP rate for supporting CSO and media involvement in advocacy, as opposed to service delivery, / ... and a common approach to UKAid branding in relation to advocacy initiatives.	Proposal already with DFID > urgently needed in co-ordination with PATHS2 on support to CS>MTSS process – done, in principle / Get clarification from DFID of their position on branding for SAVI and the other SLPs specifically on advocacy work – done, gained thru ESSPIN	NTLs > DFID > V&A Working Group / NTLs > DFID
23	The V&A working group should provide a forum for non SLP V&A programmes, such as C4C and ENABLE, to share experiences and lessons learned.	It already is, before this OPR, but worth reinforcing. Promote role of V&A working group in facilitating DFID’s proposed one day LL sharing event between SAVI, C4C and ENABLE (now scheduled for October) – done, also with GEMS and J4A	Senior mgt > Julius & Tony > Lawal
24	SAVI, PATHS2 and ESSPIN should recognise the good will on all sides to move the issue of coordination forward, and the need for discussion on ways to accommodate structural differences between the programmes that cannot easily be changed.	Action is being taken on this through the ongoing work by DFID on SLP co-ordination, lead by Soji & James (see recommendation 11 above) / Discussions at state level to include meetings with other STLs to understand their concerns and broker better relations with SAVI STLs, wherever needed – done, to a large extent in every state through the PE work facilitated by SPARC (Simon & John)	Core team during state visits
25	SAVI to designate members of the Abuja team as links to other SLPs, mandated to ensure a flow of communication between SLPs and between Abuja and the States.	Programme level: delegate to individual core team members established but not solving the core problem of protocols needed when other SLP’s core team communicate with SAVI state teams (either through their own STLs or thru SAVI core team) – this has improved over time, especially with ESSPIN / State level: through ‘seconded sectoral SPOs’ at state level? (see recommendation 11 above) no longer appropriate	Core team / Core team > state teams & Soji & James > other SLPs > DFID
26	SAVI to produce accessible, user friendly material on its approach to working with CS on advocacy to enable other SLPs and partners to benefit from its expertise and experience.	Product of revised SAVI KM & communications strategy (see recommendation 19 above). This still needs follow-up at state and national level with targeted communications for other SLPs on SAVI’s approach explained in both principle and practice combined – repeated engagement at both levels continues, but joint activity (i.e. on BCIAs and PE) remains the best media for this.	Core team on KM&C with state teams

Oversight and Advisory Structures, Management and Staffing
Oversight and Advisory Structures
S/n	Recommendation	Action Taken/Required	Responsible
27	The “one size fits all” approach to SAVI TEC is not viable. SAVI to encourage State teams to establish mechanisms appropriate to their context to ensure structured and systematic communication on SAVI to the State Government and to the SSC.	Get a clear mandate for this from DFID, and pass this on to the SAVI state teams to act on – done, to a large extent: a more pragmatic approach has been adopted	NTL > DFID, then to state teams
28	DFID to review the viability of SSCs, consider alternative ways of harnessing high-level State Government political commitment including use of existing channels of communication and refinements to MoUs, and ensure that mechanisms to include the SAVI programme are explicit and viable.	Get state teams to push DFID regional offices to recognise need for this and discuss alternatives – done / Await action from DFID – likely to be stepped up post 2011 elections with the new administrations.	Core team > each state team > DFID regional / DFID

SAVI Staffing and Management
S/n	Recommendation	Action Taken/Required	Responsible
29	SAVI to convert Administrative Assistants in all States to Programme Assistants, in reflection of the changing needs of the programme, and change reporting lines.	Revised TORs and contracts (in August), agree any changes in fees between GRM & DFID – done	NTL > GRM > DFID
30	SAVI to include in all TORS and staff performance assessments their contribution to the team and the programme.	Build into revised TORs and contracts (in August) – done	NTL/AM/GRM
31	DFID, GRM and SAVI to agree flexible financial management and reporting mechanism suitable to the flexible and participatory nature of the SAVI programme.	Agreed in principle, modalities being worked out, ongoing, also to include funding alterations as recommended above (see recommendations 9 & 16) – done	Senior mgt & finance team > GRM and state teams

P.O. Box 4175
3006 AD Rotterdam
The Netherlands
Watermanweg 44
3067 GG Rotterdam
The Netherlands
T +31 (0)10 453 88 00
F +31 (0)10 453 07 68
E netherlands@ecorys.com
www.ecorys.nl