## NEW Logframe
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
ORGANISATION NAME | The Carter Center - DRC
PROJECT TITLE | Advancing Transparency and Accountability in the Democratic Republic of Congo's Extractive Industries
IMPACT | Impact Indicator A |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV) | Assumptions
Governance of the DRC's extractive sector is improved (sector data is more accessible, governance of revenues improves, and investment is more responsible, sustainable and equitable). | The DRC is in compliance with the EITI. | Planned | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | The EITI website. | • The government is responsive to public scrutiny. • The government has opportunities and the ability to improve the legal and fiscal regime. • The political will to continue to improve investments of extractive sector revenues exists. • Targeted extractive sector companies implement changes based on civil society recommendations in a timely manner. • The EITI-DRC Technical Secretariat does not impede the Executive Committee’s management of EITI-DRC implementation. • Delegates on the Executive Committee adequately represent the interests of Congolese civil society. • The Independent Administrator and the Multi-stakeholder Group (MSG) take civil society recommendations into account. • The time that EITI-DRC takes to implement civil society recommendations is short. • Procedures to institute civil society recommendations on the process of EITI implementation are effective. • Civil society advocacy is effective. • Civil society organizations (CSOs) leverage their participation in the discussion around extractive sector revenues and apply their technical knowledge toward improving their advocacy efforts. RISKS: • Government is not responsive to public scrutiny. • Companies are not responsive to public scrutiny. • Space for civil society to contribute to the governance processes (including EITI) continues to shrink. • EITI-DRC timelines continue to be rushed or ignored. • Key documents are not adequately shared amongst stakeholders. • EITI-DRC suffers from a sense of complacency following the 2014 validation of the DRC as EITI compliant.
|  | Achieved |  | Yes | Yes | Yes
Source
Continued EITI compliance will be confirmed quarterly.
| Impact Indicator B |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Cumulative number of sector-wide changes to fiscal governance of the DRC extractives sector influenced civil society advocacy. | Planned | Baseline for Phase II: 2 | 2 | N/A | N/A | N/A | N/A | N/A | N/A | 4 | Legal, policy, and/or enforcement reforms announced by government, state agencies, state-owned enterprises, etc.; CSO advocacy plans and advocacy implementation efforts.
|  | Achieved |  | 2 | N/A | N/A | N/A | N/A
|  | Source | [10 empty] | RISK RATING
|  | Sector-wide reforms are expected by the end of the project period. | [10 empty] | High
OUTCOME 1 | Outcome Indicator 1a |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV) | Assumptions
Congolese civil society partners are able to effectively monitor, and advocate for improvements to, EITI-DRC processes and reporting. | Number of partner civil society recommendations taken into account in final EITI-DRC reports and improved EITI-DRC process. | Planned | Baseline for Phase II: 10 | 8 | 0 | 2 | 5 | 5 | N/A | N/A | 12 | EITI-DRC reports; EITI-DRC Executive Committee minutes and official documents; Recommendations issued by civil society and submitted to EITI-DRC. | • CSOs are actively monitoring EITI-DRC implementation. • CSOs in new regions/cities actively participate in the monitoring exercises and developing EITI contributions. • EITI stakeholders are responsive to civil society recommendations. RISKS: • Space for civil society to contribute to the process continues to shrink. • Key documents are not adequately shared amongst stakeholders.
|  | Achieved |  | 10
Source
Recommendations are expected to be taken into account by the end of the project period. However, the number ofrecommendations taken into account is largely outside of our our the partners' control and depends on the EITI context.
| Outcome Indicator 1b |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Cumulative number of EITI contributions (e.g. memos, revenue estimates, etc.) from civil society teams receiving TCC’s technical support that achieve a quality by at least 60%. | Planned | Baseline for Phase II: 12 | 8 | 0 | 3 | 1 | 5 | N/A | N/A | 9 | Civil society contributions and memos; Technical Capacity scoring matrix.
|  | Achieved |  | 12
|  | Source | [10 empty] | RISK RATING
|  | Cumulative number of deliverables receiving at least a 60% quality score over the project cycle. | [10 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2a |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV) | Assumptions
Congolese civil society partners are able to effectively research and analyze revenue impacts and use their analysis to advocate for improved fiscal governance of key mining projects/companies. | Quality of civil society team’s case study interim deliverables. | Planned | Baseline for Phase II: N/A (New partners) | 75% | N/A | N/A | 60% | 70% | 75% | N/A | 68.33% | Civil society interim task deliverables and final report submitted to TCC; Technical Capacity scoring matrix, average score for deliverables produced in that quarter. | • Partner CSOs are actively engaged in research and analyze revenue impacts of extractive sector companies. • Deliverables are produced and shared in a timely manner. • Partner CSOs improve their skills over tie. RISKS: • Partner CSO teams lack consistent attendance at TCC trainings and workshops. • Limited publicly available data impedes partner CSOs' analysis.
|  | Achieved |  | 79% | N/A | N/A
|  | Source | [10 empty] | RISK RATING
|  | The indicator is not cumulative because the tasks change significantly from one to the next, although progress is shown in the final report in the last quarter. | [10 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 3 | Outcome Indicator 3a |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV) | Assumptions
Congolese civil society partners are able to effectively utilize EITI-DRC data and other sources for advocacy to address sector-wide fiscal governance challenges. | Cumulative number of interim deliverables on using the data and associated advocacy from civil society teams receiving TCC’s technical support that achieve a quality by at least 60%. | Planned | Baseline for Phase II: N/A (New partners) | 25 | 0 | 0 | 2 | 2 | 2 | N/A | 6 | Civil society deliverables (memos, pamphlets, etc.); Technical Capacity scoring matrix. | • CSO partners are actively engaged in workshops and other learning opportunities on sector-wide fiscal governance challenges. • Women and individuals representing CSOs that advocate for the empowerment of women and girls will be engaged in workshops and demonstrate an improved understanding of using EITI data and of advocacy between Pre-Tests and Post-Tests. RISKS: • CSO partner team lacks consistent attendance at TCC trainings and workshops. • Elections and an unstable political process limit willingness to improve fiscal governance of the mining sector. • CSO partners’ advocacy does not effectively complement their analysis. • Company or government advocacy overshadows that of the CSO partner.
|  | Achieved |  | 36
Source
Cumulative number of deliverables receiving at least a 50% quality score over the project cycle.
| Outcome Indicator 3b |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Number of meetings with targeted stakeholders. | Planned | Baseline for Phase II: 0 (Not measured in Phase I) | N/A | 0 | 0 | 2 | 6 | N/A | N/A | 8 | Mission reports; meeting reports.
|  | Achieved |  | N/A
|  | Source | [10 empty] | RISK RATING
|  | Number of meetings involving Carter Center staff and/or partners and targeted stakeholders that take place within the quarter. | [10 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.1 | Output Indicator 1.1a |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV) | Assumptions
Congolese civil society better understands EITI implementation in the DRC and is able produce contributions on EITI reporting and processes in the DRC. | Percentage of men and women of civil society organizations that have increased their knowledge on the EITI process and reporting by at least 20%. | Planned | Baseline for Phase II: N/A (New partners) | 25% | N/A | 60% | 75% | 80% | N/A | N/A | 71.67% | Pre- and post-tests to training participants (disaggregated by gender); mission reports. Final achieved is the average of previous quarters. | • CSOs are actively committed to engaging in EITI reporting and analysis. RISKS: • Inconsistent attendance at TCC trainings and workshops.
|  | Achieved |  | 77%
Source
Different workshops with substantially different content, so the indicator is not cumulative. It represents skill development over discreet workshops taking place in the quarter.
| Output Indicator 1.1b |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Overall level of satisfaction among men and women of civil society organizations participating in TCC-led workshops held on monitoring and advocating for improvements to EITI-DRC processes and reporting. | Planned | Baseline for Phase II: N/A (New partners) | 25% | N/A | 80% | 90% | 90% | N/A | N/A | 86.67% | Post-test survey of training participants (disaggregated by gender); mission reports. Final achieved is the average of previous quarters.
|  | Achieved |  | 88%
Source
Average satisfaction rating by workshop participants of workshops occuring in the quarter.
| Output Indicator 1.1c |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Cumulative number of contributions by members of civil society developed for use in advocacy with key targets of the EITI-DRC process (e.g. MSG, TS, IA, EC, TMC, etc.). | Planned: | Baseline for Phase II: 14 | 8 | 0 | 4 | 3 | 3 | N/A | N/A | 10 | Contributions of partner CSOs (e.g. memos including recommendations, suggested methodology, etc.).
|  | Achieved: |  | 14
|  | Source | [10 empty] | RISK RATING
|  | Cumulative number of advocacy deliverables developed throughout the project. | [10 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.1 | Output Indicator 2.1a |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV) | Assumptions
Congolese civil society partner develops mining sector revenue analysis skills. | Percentage of men and women of civil society organization that have increased their knowledge on mining sector revenue analysis by at least 20%. | Planned: | Baseline for Phase II: N/A (New partners) | 30% | N/A | 55% | 65% | 70% | 75% | N/A | 66.25% | Mission reports; activity plans.Pre- and post-training tests. Attendance sheets (disaggregated by gender). Final achieved is the average of previous quarters. | • CSO partners are actively committed to engage on mining sector revenue flows. • CSO partners selected will be responsive to the language in the call for collaborations encouraging that women and CSOs that advocate for the empowerment of women and girls will be included in activities. RISKS: • CSO partner team lacks consistent attendance at TCC trainings and workshops.
|  | Achieved: |  | 70%
Source
Different workshops with substantially different content, so the indicator is not cumulative. It represents skill development over discreet workshops taking place in the quarter.
| Output Indicator 2.1b |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Overall level of satisfaction with TCC-led workshops held on mining sector revenue analysis. | Planned: | Baseline for Phase II: N/A (New partners) | 65% | N/A | 80% | 90% | 90% | 90% | N/A | 87.5% | Post-test survey of training participants (disaggregated by gender); mission reports.
|  | Achieved: |  | 63%
Source
Average satisfaction rating by workshop participants of workshops occuring in the quarter.
| Output Indicator 2.1c |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Cumulative number of interim deliverables completed toward the final revenues impact analysis case study. | Planned: | Baseline for Phase II: 0 (New partners) | 20 | 0 | 0 | 6 | 8 | 2 | N/A | 16 | Deliverables produced by partner CSO.
|  | Achieved |  | 27
|  | Source | [10 empty] | RISK RATING
|  | Cumulative number of revenue analysis devlierables completed throughout the project. | [10 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.1 | Output Indicator 3.1a |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV) | Assumptions
Congolese civil society partners develop skills to use EITI data and other data for advocacy and produce interim deliverables for the implementation of evidence-based advocacy. | Percentage of men and women of civil society organizations that have increased their knowledge on data utilization and advocacy by at least 20%. | Planned: | Baseline for Phase II: N/A (New partners) | 30% | N/A | 55% | 70% | 75% | 75% | N/A | 68.75% | Pre- and post training tests: Training documents (manuals, modules, exercises) developed. Attendance sheets (disaggregated by gender). | • CSO partners are actively committed to developing their skills in using EITI data and other advocacy skills. • CSO deliverables are produced in a timely manner. RISKS: • Limited publicly available data inhibits CSO partners’ analysis. • Partners are not committed to the advocacy process and do not develop a strategy or interim deliverables.
|  | Achieved |  | 96%
Source
Different workshops with substantially different content, so the indicator is not cumulative. It represents skill development over discreet workshops taking place in the quarter.
| Output Indicator 3.1b |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Overall level of satisfaction with TCC-led workshops held on data utilizaton and advocacy. | Planned: | Baseline for Phase II: N/A (New partners) | 65% | N/A | 80% | 90% | 90% | 90% | N/A | 87.5% | Post-test survey of training participants (disaggregated by gender); mission reports.
|  | Achieved: |  | 80%
Source
Average satisfaction rating by workshop participants of workshops occuring in the quarter.
| Output Indicator 3.1c |  | Baseline | Target Q1 2017 (End of Phase I) | Target Q3 2017 | Target Q4 2017 | Target Q1 2018 | Target Q2 2018 | Target Q3 2018 | Target Q4 2018 | Final Target | Means of Verification (MOV)
| Cumulative number of deliverables developed for using EITI-DRC data analysis in the implementation of the advocacy strategy. | Planned: | Baseline for Phase II: 40 | 40 | 0 | 0 | 4 | 8 | N/A | N/A | 12 | Deliverables produced by partner CSOs
|  | Achieved | Achieved | 40 |  |  | .
|  | Source | [10 empty] | RISK RATING
|  | Cumulative number of EITI advocacy deliverables completed throughout the project. | [10 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.