## DfID Access FP Logframe
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Enhanced Accessibility to Quality Contraceptive Commodities in Nigeria
IMPACT | Impact Indicator 1 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (date) 2019 | Assumptions
Improved maternal and child health in Nigeria | Maternal Mortality Ratio (maternal deaths per 100,000 live births) | Planned (Govt targets) | 545 | 545 | 545 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | Targets are based on national targets set within the National Strategic Health Development Plan. These are highly ambitious and this programme will contribute to these targets. If the contraceptive prevalence rate increases, maternal and infant mortality will reduce. The NDHS indicates an increase in the MMR from 545 (2008) to 576 (2013) however there is no significant difference according to National Population Commission
|  | Achieved | 545 Per 100,000 live births | 545 per 100,000 live births | 545 per 100,000 live births | 576 per 100,000 live births | 576 per 100,000 live births | 576 per 100,000 live births | 576 per 100,000 live births | 576 per 100,000 live births
Source
National Targets - Demographic and Health Survey (DHS) 2008 and 2013. Next one planned for 2018 and Multi-Indicator Cluster Surveys (MICS) 2011 and 2016.
| Impact Indicator 2 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (date) 2019
| Infant Mortality rate (per 1000) | Planned | 75 | 70 | 65 | 60 | 55 | 50 | 45 | 45 | 45 | 45
|  | Achieved | 75 | 60 | 45 | 30 | 55 | 55 | 55 | 55
Source
National Targets - Demographic and Health Survey (DHS) 2008 and 2013. Next one planned for 2018 and Multi-Indicator Cluster Surveys (MICS) 2011 and 2016.
OUTCOME | Outcome Indicator 1 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (date) 2019 | Assumptions
Women and men have access to a mix of quality contraceptives and use them. | Contraceptive Prevalence (modern) (% of married women currently using modern contraceptives). | Planned | 9.7 | 10.7 | 11.7 | 12.7 | 13.7 | 14.7 | 15.7 | 16.7 | 17.7 | 18.7 | To reach these ambitious targets there will need to be a concurrent substantial increase in quality and accessibility (particularly for the poorest wealth quintiles) of child and maternal health services. However this intervention alone will have utility and could alone reduce maternal mortality by at least 10%.
|  | Achieved | Actual : 9.8 (NDHS 2008) | 9.8 (NDHS 2008) | 10.5 (MICS) | 10.3 (NDHS 2013) | 10.3 (NDHS 2013) | 14.53 (NHMIS) and 21% (NNHS Smart 2015 Survey) | 17% (PMA2020 2016) and 10.8% (MICS 2016) | 16.1% (PMA2020); FP2020 FPET estimation 14.72% (AW); 13% (MW) 2017 FP2020 FPET
Sources; NDHS 2008, 2013. MICS 2016, PMA2020 (2016), PMA 2020 (2017), FPET estimate (2016, 2017, 2018). Caveat: Data comparison should be between similar surveys e.g DHS vs DHS, MICS vs MICS, PMA2020 vs PMA2020. FPET tool is modeling done using all data sets by Track20 and FP2020
Government target in NSHDP 2009 planned for 2% point increase per year for total CPR,; attribute 1% point for modern methods
| Outcome Indicator 2 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (date) 2019
| Number of states with a CPR of less than national average of 15% (total) | Planned | 24 | 24 | 24 | 20 | 20 | 17 | 17 | 17 | 15 | 15
|  | Achieved | Actual states: 21 | 21 | 21 | 21 | 15 (NDHS 2013) | 15 (NDHS 2013) | 15 (NDHS 2013) | 17 (MICS 2016)
|  |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (date) 2019
|  | Planned | 126 | 121 | 121 | 121 | 100 | 100 | 100 | 100 | 100 | 90
| Adolescent birth rate (Births – girls age 15 to 19) per 1000 births (or Teenage fertility) or % of adolescents who are already mothers or currently pregnant | Achieved (126 per 1000 ; 2003 NDHS) | 121 per 1000 (NDHS 2008) | 121 per 1000 (28.6%) | 89 per 1000; 28.6% (MICS4) National Target 102 | 122 per 1000; 23% (NDHS 2013) National Target 90 | 122 per 1000; 23% (NDHS 2013) National Target 90 | 122 per 1000; 23% (NDHS 2013) National target 90 | 122 per 1000; 23% (NDHS 2013) National target 90 | 120 per 1000; 23% (MICS 2016) National target 90
Source
National Targets - DHS and MICS As above
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | [6 empty] | DFID SHARE (%)
| £18m | [10 empty] | Initially 50% of all public sector family planning commodities.
INPUTS (HR) | DFID (FTEs)
0.25
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (date) 2019 | Assumptions
Adequate quantities of appropriate mix of quality contraceptives procured and distributed. | Couple years of protection of family planning commodities procured with DFID funds and distributed to public facilities | Planned | 0 mil | 1 million | 1 million | 1 million | 1 million | 1 million | 1 million | 1 million | 1 million | Cumulative 8million | Increasing procurement and availability of contraceptives will increase the contraceptive prevalence rates as long as there is a concurrent demand for services. Current estimates of a 16% unmet need (2013 NDHS) support the fact that there is a demand for these services.
|  | Achieved | 300000 | 1013380 | 2099922 | 973192 | 1069513 | 1014000 | 1251000 | 1060000 |  | 8481007
Output Indicator 1.2
| CYP of commodities distributed/issued to states | Planned |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1500000 | 1500000 | 8000000
|  | Achieved |  | 368847.4487 | 909431.2943 | 866993.2323 | 1027713.9169 | 1992021.0145 | 1350246 | 1628118 |  | 8143370.9066
Output Indicator 1.3
| Procurement lead time (average) | Planned |  |  |  | 7 months | 7 months | 7 months | 7 months | 7 months | 7 months | 7 months
|  | Achieved |  | 12 months | 12 months | 9 months | 7.4 months | 4.1 months | 5.6 months | 6.6 months
UNFPA procurement records, FMOH Reproductive Health Logistics System and GPRHCS Survey on availability of essential medicines including Contraceptives
IMPACT WEIGHTING (%) | 70%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | [6 empty] | DFID SHARE (%)
| £24m | Planned | US$20 mil | US$25 mil | US$101.7 mil | [6 empty] | Initially 50% of all public sector family planning commodities (2012 -2016) and 35% from 2017-2019.
INPUTS (HR) | DFID (FTEs) | Achieved
0.25
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (date) 2019 | Assumptions and definitions
Efficiently managed national contraceptive supplies and logistical management system. | % of service delivery points reporting no stock outs of contraceptives in the last 3 or 6 months (no stock out in this case is a standard global indicator that measures stock out of any contraceptives currently offered by the health facility) | Planned | Unknown | 70% | 70% | 70% | 75% | 80% | 80% | 80% | 80% | 80% | It is assumed that; * as supply increases, acceptability and demand will also increase (given evidence from other countries). * that user fees in public services will be removed in line with new national policy. * correct contraceptive methods will be procured based on previous demand and survey information .* current trend toward greater cultural and religious acceptance toward contraceptives is maintained.
|  | Achieved | 40% (2007 LIAT Survey) | Actual: 42% (2011 GPRHCS Survey) | Actual: 75% | Actual: 50% | Actual: 78% | Actual: 61% | Actual 77% | Actual: 81.2%
The indicator on stock out was changed to reflect the tracking data available. The current data available does not track the number of days that stock out lasted. In order to track number of days stocked out of any commodities, we would have to restructure the current survey questionnaire. We hope to provide in the near future, a more robust indicator tracking number of days that stock out lasted in the health facilities
Source
National FMoH monitoring systems and GPRHCS/UNFPA Supplies Survey
| Output Indicator 2.2 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (2019)
| % CYP of States with requests for contraceptives resupplied (fill rate) within the reporting year (based on RIRF forms from states) | Planned | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
|  | Achieved | 93% | Actual: 34% | Actual: 84% | Actual: 86% | Actual: 73% | Actual: 86% | Actual: 79.78% | Actual: 64% |  |  | The fill rate is based on the 4 monthly distribution to states in line with the FMoH Contraceptives Logistics System (CLMS); and is calculated by comparing the CYP of total requested commodities in the year with CYP of actual supplied. This measures the extent to which the requests are filled or met
| Output Indicator 2.3 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (2019)
| % of primary health care public service delivery points currently providing FP services providing at least 3 modern contraceptive methods. % of secondary and tertiary health care public service delivery points currently providing FP services providing at least 5 modern contraceptive methods | Planned 85% for both indicators | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
|  | Achieved | Actual: **% of HF currently providing FP services; 90% (2011 GPRHCS Survey) | Actual - 90% | Actual 89% | Actual 89% | Actual - 86% of PHC at least 3 modern methods; Actual - 83% of 2ry and 3ry facilities at least 5 modern methods | Actual (PHC) - 90.1% Actual (secondary) - 86.2%) Actual (tertiary) - 100% | Actual (PHC) – 92.6% Actual (secondary) – 91.7% Actual (tertiary) - 100% | Actual (PHC) – 94.1% Actual (secondary) – 91.7% Actual (tertiary) - 100% |  |  | The indicator on at least 3 modern methods refers to condoms, pills and injectables. The indicator on at least 5 modern methods refers to condoms, pills, injectables, implants and IUDs
Source
GPRHCS/UNFPA Supplies Survey; ** % of Health Facilities providing FP services
| Output Indicator 2.4 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (cumulative) 2019
| # of Health Facilities supported to provide LARC; | Planned | 60 | 60 | 90 (150 cumulative) | 200 (350 cumulative) | 250 (600 cumulative) | 250 (850 cumulative) | 250 (1,100 cumulative) | 1,200 (2,300 cumulative) | 1,200 (3,500 cumulative) | 3500
|  | Achieved | 60 | 60 | 90 | 251 | 335 | 56 (792 cumulative) | 1250 (2,042 cumulative) | 1,211 ; 3,253 (cumulative) |  | 3324
Source
UNFPA and FMOH monitoring records
| Output Indicator 2.5 |  | Baseline (2008) | Milestone 1 (2011) | Milestone 2 (2012) | Milestone 3 (2013) | Milestone 4 (2014) | Milestone 5 (2015) | Milestone 6 (2016) | Milestone (2017) | Milestone (2018) | Target (date) 2019 | The data on current users of FP based on the NDHS % CPR and estimated number of Women of Reproductive Age. The routine data on new users of FP from the NHMIS (DHIS2 tool) is incomplete which necessitated the use of GPRHCS Survey estimates to track estimated new users. In future, it is hoped that the NHMIS would provide more complete data to track this indicator.Discontinuation also accounts for flunctuations
| # of new acceptors of FP Number of Currently married women using FP services who are new acceptors of FP Current users (2008) 3,361,596 | Planned | unknown | unknown | unknown | 1400000 | 1,400,000 (2,800,000 cumulative) | 1,400,000 (4,200,000 cumulative) | 1,400,000 (5,600,000 cumulative) | 1,400,000 (7,100,000 cumulative) | 1,400,000 (8,500,000 cumulative) | 8,500,000 (2013- 2018 cumulative )
|  | Achieved | unknown | unknown | unknown | 1,421,399 (GPRHCS Survey 2013 estimate) | 3,513,956 (GPRHCS Survey 2014 estimate) | New users - 3,846,226 (155%) (NHMIS FMoH routine data) | New users - 2,419,914 NHMIS FMoH routine data | New users - 2,909,970 NHMIS FMoH routine data |  | Cumulative current users 10,060,516 (including new users)
IMPACT WEIGHTING (%) | 30% | Source
National FMoH monitoring systems and GPRHCS Survey

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.