## A1 Goal, Purpose, Risk
Annual Review (reviewed July 2011)
ARIES Project Code | 113484
ARIES Project Description | Punjab Economic Opportunities Programme (PEOP)
A1: Goal, Purpose, Risk
Goal
Goal statement | Incomes of the poor increased in the poorest districts of Punjab
Indicator 1 | Rate of economic growth in the 4 selected districts: Districts: Bahawalpur, Muzzaffargarh, Lodhran, Bahawalnagar
Milestone for this review (if any) | To be determined after the baseline. (Milestones for this indicator will be established during the mid-term review (Feb, 2012) after the report of the household baseline study is available in December, 2011.
What progress has been made in the period covered by this review? | During the period under review the PEOP implmenting arrangements were made operational and no programme activities were implemented, hence impact of the PEOP activities on the rate of economic growth in the 4 selected district is not applicable yet. In addition, MICS data post 2007/8 is not avilable as MICS 2011 is going to be conducted this year. Meanwhile, district level GDP estimates are not available. However, household income data from the two rounds of MICS (2003 and 2007/8) was used to analyze differences in income at the district-level and to generate a proxy measure for the growth in income levels for target districts. Estimates show yearly growth between 2003/4-2007/8 as follows: Bhawalnagar=16%, Bhawalpur=19%, Lodhran=2% and Muzaffargarh = 2%. These figures confirm that economic growth in Punjab has not been uniform especially in South Punjab.(See Baseline Indicator Study of TAMA which is based on analysis of secondary data)
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Incomes of the targeted population
Milestone for this review (if any) | To be determined after the baseline. Milestones for this indicator will be set during the mid-term review (Feb, 2012) after the report of the household baseline study is available in December, 2011 and the specific target groups of PEOP have been defined.
What progress has been made in the period covered by this review? | During the period under review the PEOP implmenting arrangements were made operational. No programme activities were implemented, hence impact of PEOP activities on the incomes of the target population is N/A. In addition, MICS data post 2007/8 is not avilable as MICS 2011 will be conducted this year. Meanwhile, MICS 2003/4-2007/8 analysis shows that the average household real income of the Poor has decreased considerably in time period between 2003/4 and 2007/8. These households have lost up to 14% of their income every year to inflation during this time. Real per month income of Poor households in 2007/8 was as follows: Bhawalpur=Rs.3,005, Bhawalnagar = 2,890, Lodhran = Rs3,120 and Muzaffargarh=Rs.3,001.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Number of people living below the poverty line
Milestone for this review (if any) | To be determined after the baseline. Milestones for this indicator will be set during the mid-term review (Feb, 2012) after the report of the household baseline study is available in December, 2011 and the specific target groups of PEOP have been defined.
What progress has been made in the period covered by this review? | In the absence of an official recent poverty survey (the most recent official estimate dates from 2005/06) and a more current MICS, it is unclear what the distributional effects of developments in the global as well as domestic economic landscape over the past two years have been. The general consensus is the financial crisis of 2008 and an accompanying sharp increase in prices caused poverty to increase. The 2010 flooding (in which Muzaffargarh was one of the most badly hit areas) and steady increases in global food prices have seen the cost of food in Pakistan increase again. Yet greater unemployment and the fairly steep adjustment in administered prices of food and energy, has, in all likelihood, adversely impacted vulnerable segments of the population, especially those on low and fixed incomes.
On the other hand, a substantial rise in inflows of worker remittances, partly in response to a government policy initiative, combined with unprecedented transfers in 2008 and 2009 to the rural economy under the government’s crop procurement program, are likely to have provided significant support to large segments of the population. Cash transfers under the Benazir Income Support Program (BISP), amounting to an estimated Rs. 35 billion in 2009-10, are very likely to have been an additional source of support to those in need, although numbers of recipients are low relative to the numbers estimated to be below the poverty line.Meanwhile, MICS 2007/8 analysis shows the following percentage of people living below the poverty line: Bhawalpur=55.07%, Bhawalnagar = 51.3%, Lodhran = 50.04% and Muzaffargarh=51.75%.
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | The implementation units for PEOP i.e. the PSDF and PIT have been made operational and immediate TA support (until a TA firm is hired following OJEU) is being brought online.
Goal Recommendation 1 | Given the critical role of the baseline survey their timely completion needs to be managed closely and GoPb to continue to provide facilitative support.
Goal Action Point 1 | PEOP team to follow up closely on CERP and identify mitigation measures for bottlenecks and risks.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2 | During the mid-term review of the Programme in Feb, 2012 the feasibility of expanding the scope of the Programme to other districts and its duration should be determined.
Goal Recommendation 3
Goal Action Point 2 | Adjustments to the Log frame and the PC 1 need to be made accordingly.
Goal Action Point 3
Purpose
Project Purpose | Poor people actively engaged in more, and more diverse, economic activities in the 4 selected districts of Punjab
Indicator 1 | Number of skills trainees commencing income generating economic activities
Milestone for this review (if any) | Skills training fund is established and skills training commences
What progress has been made in the period covered by this review? | The Punjab Skills Development Fund (PSDF) was incorporated as a not-for-profit Section 42 company under the Companies Ordinance 1984 in October, 2010. The Fund has a proactive private sector dominant Board of Directors and a management hired on merit based open competition. The management and operational systems of the Fund are at varying levels of being finalized. Rs.30 million has been disbursed for the Fund. Budget for 2011/12 has been approved. In the absence of the baseline data that provides specific skills related information, the Fund has introduced two small schemes for taining upto 5,800 poor (1700 women). These are namely Skills For Employability and Vocational Training for 6 Model Villages in Muzaffargarh. 34 EOIs for Model Villages and over 110 for SE were received. The Fund has finalised the training organisations for model villages. JV of Hashoo Foundation/PVTC and TUSDEC will be contracted for provision of training August 15 onwards.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Number of people owning at least 1 animal for livestock farming (both men and women).
Milestone for this review (if any) | Number of people owning atleast 1 animal for livestock farming increased by 5% from the baseline.
What progress has been made in the period covered by this review? | Programme activities have not commenced yet, as the implmentation team for the L&D called the Programme Implmentation Team (PIT) was being made operational. Secondly, the baseline report will be available by December, 2011. Nevertheless, PIT has proposed an Asset Transfer Project under PEOP as experience in Bangladesh and elsewhere suggests that distribution of goats to poor families has emerged as a sound, low risk, easily manageable and high yielding investment. Target beneficiaries are proposed to be rural landless farmers or those having small landholdings. Goat units comprising 4-5 goats are proposed to be distributed to selected community members. The selection will be based on the results/recommendations of baseline survey being conducted by CERP and will be primarily based on poverty criteria. Project design and implementation and monitoring modalities will be defined with TC support that is in place by Sep/Oct, 2011.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Milk yields amongst dairy farmers
Milestone for this review (if any) | Milk yields amongst dairy farmers increased by 5%
What progress has been made in the period covered by this review? | The L&D Adviser PEOP and PIT Team Leader have drafted a set of interventions for improving the quality and quantity of yields that have been discussed under the progress made on indicators for Output 3.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4 | Increased participation of women and marginalised groups in income generating economic activities
Milestone for this review (if any) | The number of women and marginalized groups participating in income generating activities is increased by 3% from the baseline.
What progress has been made in the period covered by this review? | Through two of its initial schemes the Fund is targeting training of 1700 poor women. The nature of the skills being imparted will ensure enrollment of the poor. Skill providers will be given extra credit for targeting the rural and more poor groups. Meanwhile, related activites of the PIT for enabling farmers to earn more incomes are currently in their planning stage.
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Log frame assumes i) no severe and prolonged climate or weather event ii) GDP continues to grow and jobs are available and iii) Government continues to invest in supporting infrastructure such as electricity and roads. The factual situation has been quite adverse for the PEOP districts. Muzaffargarh was one of the worst hit areas in the floods of 2010. The GDP estimates for the districts are not available. National GDP grew at only about 2.4% during 2010/11 and growth dividends are not evenly distributed, particularly in South Punjab. In order to remove regional disparities, over the last 3 years, the GoPb. has been making direct investment in less developed areas (mainly S.Punjab and called Regional Planning Sector) to enhance rural household incomes and employment opportunities, improving infrastructure and provide financial support to enhance production and skill development of the target groups through participatory approach. In view of these factors, the sector has been provided with an allocation of Rs.15 billion during 2011-12 which is higher than the current year’s allocation of Rs 14,203.0 million. This includes three major interventions of Southern Punjab Development Programme (SPDP), with an allocation of Rs.10 billion, PEOP worth Rs.1.7billion and IFAD assisted Southern Punjab Poverty Alleviation Project (SPPAP) Rs. 780.0 million which are pro-poor. The PEOP districts are not expected to be hit by floods during this year's weather forecasts.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | Should high inflation rates continue, PEOP interventions will help provide the poor the cushion to withstand inflationary pressures.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | N/A
Purpose Recommendation 1
Purpose Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 3 | 2.75
Purpose Justification | PSDF: The Fund has become operational. It has high commitment of a private sector dominant board and management and increasing level of GoPb's commitment. Limited skills schemes were introduced only as more indepth knowledge and understanding of the skills market was unavailable due to delay in the baseline data. However, the Board is inclined to introduce further skills schemes based on district level consultations with stakeholders and the Chambers of Commerce and industries. Livestock and Dairy Development (L&DD): On the L&DD side, the Programme Implementation Team (PIT) has been engaged and interim TC arrangements are being made to boost its capacity for project planning, desgin, implementation and tracking. PIT has prepared project outlines and budget estimates for 3 of the initial projects to be implemebted until baseline results are available. In addition, district wide indpeth consultations have been held which have pointed out additional areas for support. The TC needs of the PIT could have been addressed earlier but due to the decision to drop Crown Agents a new TC management arrangement had to be planned and agreed with the implementing partners and the Steering Committee. This change in the TC arrangement has also affected the pro-poor research for shaping policies and regulations reform work planned under the PEOP. Nevertheless, a new TC managemenat arrangement was agreed at the last SC meeting held on July 25, 2011. Under this arrangement, Interim TC support (Adviser L&D, Project Development and Implementation Specialist, Procurement and Contracts Specialist and an Adviser Skills Strategy) will be provided and managed by DFID until a TC management agency is hired following DFID rules. A mid-term review of the Programme in Feb, 2012 will enable better understanding of what can be realistically achieved by the Programme given its target area, range of available potential partners and capacity of implementing units i.e. PSDF and PIT.
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability | i) Household Baseline report is delayed beyond December, 2011 and the employers baseline report is also beyond Jan,2012. ii) insufficient coordination between the P&DD and CERP regarding communities where development programmes are being implemented, distorts the RCT methodology being adopted for baseline and final evaluation of the Programme.
* High Impact / Low Probability | High dependence on CERP data for designing interventions can delay the implmentation of activities of both the PSDF and PIT
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks? | i) CERP has engaged an efficient survey company with which it has good experience in the past. Bureau of Statistics (BoS) has completed HH listings in time. Questionnaire are ready and the HH survey will be launched right after Eid holidays by mid-September, 2011. A tight quality control/supervision regime will be followed for the survey. ii) The risk of the Employer's survey getting delayed is being managed by CERP by actively engaging with BoS and the district level chambers of commerce to find alternatives ways to survey the employers as FBS has refused to provide employers survey design to CERP despite being approaced by several quarters.iii) In the second meeting of the Steering Committee (July, 2011), the P&DD committed to coordinate with the CERP about managing development programmes in communities so that RCT methodology of the PEOP evaluation is not compromised.
iv) The Board is trying to manage this risk by encouraging the PSDF management to come up with new schemes that can be introduced capitalizing on the exisiting information and support that the local Chambers of Commerce and Industries are willing to provide. PSDF is currently doing spade work to present the proposal of the new schemes to the Board at its next meeting in August/September, 2011. Once the TA for programme management and procurement support in online (expected by September, 2011) the PIT will be in a better position to initiate the 3 initial project that it has outlined and additional interventions based on its consultations with district players.
Risk Recommendation 1 | PSDF should focus on: i) Combining entrepreneurial/small business management training with skill training in order to improve self-employment opportunities for trainees. ii) Explore skill development opportunities in the more dominant sectors in the districts i.e. agriculture, manufacturing, and services. iii) Fund and the livestock and dairy component of the PEOP can collaborate for provision of L&D related training through the Fund. This will create synergies within the PEOP components and assist both the components to meet their goals drawing on each other’s strengths.
Risk Action Point 1 | Weekly follow up of the PEOP team required for i) CERP ii) engaging the TA iii) progress at PSDF regarding new products.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | Number of people to be skilled through the Fund and the increase in milk yields need to be made more realistic in keeping with the cost of training and the increase in milk yield that is realistically possible respectively. In addition, the division of the Programme funds between the L&D and Skills component need to be rationalized in light of the absorption/spending capacity of the L&D component. This will in turn have implications on the scale and nature of the L&D activities currently in the log frame. Lastly, the regulatory/policy activities of the PEOP need to be coordinated through an appropriate policy instrument e.g. the Livestock Development Strategy. clear.
Logframe Recommendation 1 | Log frame should be revised after the mid-term review in February, 2012
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision?
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Effective government policy for the economic opportunities for poor districts developed and implemented
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.3
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share | £0.5 million | 2
3
Indicator 1 (leave blank if standard indicator) | GoPunjab policy document for development of the poor districts | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Policy document produced and approved by the GoPb | 0
Progress made in the period covered by this review, including numbers. | The Programme document envisions this work to be conducted through creation of Center for Inclusive Growth (CIG) and £0.5 million has been allocated for it. During the course of the programme, thinking has evoloved.Instead of establishing an CIG, areas for pro-poor research and the potential and areas for forpilot projects will be established through consultations with the district administrations, think tanks, leading research out-fits and academicians. Evidence from CERP household survey will further help to triangulate key issues for further research and pilot projects. Leading economists/policy makers will be engaged for research with field support provided by local universities so that latter’s capacity in research and analysis is enhanced and the leading economists can steer research dissemination to influence and shape policy. This work will managed by the TC management Agency that is expected to be hired by the first quarter of 2012. In its current budet (2011/12) the GoPb has allocated Rs.15 billion (£107 million) for development of S.Punjab which includes a series of pro poor projects including the GoPb resources allocated for PEOP, IFAD's South Punjab programme very similar in focus to PEOP. Thinking on CIG and ground work for this indicator is evolving and progress can be considered on track.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Share of provincial budget allocation to the 4 selected districts of Punjab
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Disbursement to the 4 districts is at least x% of annual budget (to be determined after the baseline)
Progress made in the period covered by this review, including numbers | Due to delay in the baseline report, the minimum percentage of the provincial budget to be disbursed for the PEOP districts has not been determined yet. However, the GoPb has lived up to its committement to disburse funds matching DFID's disbursement as per the agreed terms of engagement between DFID and GoPb,. To date, DFID has disbursed £5 millin for PEOP (£2.8 million for PSDF and £2.2 million for PIT), while the GoPb has disbursed a total Rs.950 million (about £6.78 million at exch.@ of Rs.140). GoPb will make the next disbursement in Jan, 2012.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 3 | 0.5
Impact Weighted Score | 7.5 | 0.075
Justification for the Score | High government commitment and donors and private sector stakeholders interest.
Output 1 Recommendation 1 | PSDF is carving political support and influence to shape the development of a skills policy in Punjab. This needs to be reflected in the logical framework under output 1 indicators, since a skill policy will help to contribute to creation of economic opportunities for the poor which output 1 aims to do.
Output 1 Action Point 1 | The logical framework and the PC 1 should be revised during the mid-term review and a project management consultant should be engaged to help rationalize and logical framework. All indicators need to be sex disaggregated where possible.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | A group of leading economists should be engaged to initiate pro-poor research and policy formulation work. Areas meriting pro-poor policy reform should be sieved through the baseline report in December, 2011 and through consultations with a variety of relevant stakeholders.
Output 1 Recommendation 3 | Through TA support from DFID, PSDF should be provided the services of a Skills Policy and Strategy Adviser to help shape and influence development of a market oriented skills policy for Punjab through engagement of and debate among a cross section of relevant stakeholders drawn from industry, politics and bureaucracy. CERP household baseline will generate additional data and information to shape the policy and regulatory work govering skills sector in Punjab and identify additional areas that need addressing through a policy for poor districts..
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Better functioning livestock markets and linkages to these markets, are accessible to 50,000 livestock farmers in the 4 selected districts
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | To be determined after the workplanning exercise for PIT by Nov/Dec, 2011
Indicator 1 (leave blank if standard indicator) | Appropriate policies to enable the private sector to participate in livestock markets.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | GoPb to produces a policy to enable the private sector to participate in livestock markets and develop market linkages.
Progress made in the period covered by this review, including numbers | Nascent work for the reform of the outdated L&D laws is underway at the L&DDD. For example, L&DD, PGEIP and USAID are involved in varying degrees in rationalizing the regulations govering the L&D sector. Documentation of gaps in the existing regulations have been identified and documented so far. The L&DD is also working on updating about 6 laws that are outdated. A draft law for certification of Halal meat has also been prepared and after its approval by the Chief Minister it is expected to be forwarded to the Federal Government by late July, 2011 as this topic falls under Federal domain. Similarly theL&DD is also working on developing a Traceability and Hygiene Regime for exporting meat. A Milk and Meat Safety Agency has been established but as yet has not commenced operations. Coordination between this agency and the L&DD Dept will be important to avoid duplicity of work. A PPP law has been passed by the provincial assembly which covers L&D as well and currently, L&DDD has initiated work on privatizing 5 of its 22 farms and has a proposal from a US firm for supply of vaccines. Neverthless, progress is slow due to limited PPP transaction capacity at the L&DDD. Considerable ground work has been initated at the L&DD nevertheless, this needs to be given an impetus through TA support. Progress to date can be considered medium.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Regulatory framework in place to liberalise livestock sales and purchase
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Regulatory framework finalized to allow farmers to fetch competitive prices, reflecting quality and weight of animals
Progress made in the period covered by this review, including numbers | PIT has proposed an action plan under which it will enter into policy dialogue with the district government for instituting livestock market reforms such as trading of animals on live weight basis, minimizing the role of middle man and creation of essential infrastructure facilities (weighing scales, sheds, water troughs etc) in the market to attract livestock farmers. These activities can be sustained through a percentage of the revenue generated from the livestock markets. Incentives for the private sector will be created for investment in livestock market reforms. A model livestock market is proposed to be created in each of the 4 districts. Ideally, these markets should be linked to modern abattoirs with in or outside the district. Nevertheless, the feasibility of establishing and sustaining moder abattoir needs to be assed during the workplanning exercise that will be conducted with TC, which will be availale for the PIT by Sep/Oct, 2011. Progress to date on this indicator is medium.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Number of farmers accessing new micro-finance loans
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | number of farmers accessing microfinance loans is increased by 13% (to be triangulated with baseline report)
Progress made in the period covered by this review, including numbers | 4-6 MF providers are currently operating in the PEOP districts and the existing MF (active borrowers/savers/insurance policy holders) market is over 560,000 clients in Bhawalpur, over 360,000 clients in Bhawalnagar, over 160,000 clients in Lodhran and over 95,000 clients in Muzaffargarh. Through the provincial and district level consultations on PEOP all the relevant stakeholders including MF providers have been apprised of the Programme and the scope of MF in PEOP's activities. Meanwhile, linkage has been established with the Pakistan Microfinance Network for promoting access to financial services in PEOP districts. To begin with PMN will be providing MF data specific to the livestock and dairy sector clients for the 4 PEOP districts. Progress to date on this indicator can be considered medium.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 3 | 0.5
Impact Weighted Score | 12.5 | 0.125
Justification for the Score | Project preperation work is underway, TC arrangements to help boost the PIT are online, linkages with MF providers being established to help meet financial needs of the farmers.
Output 2 Recommendation 1 | The L&DDD has a Livestock Development Strategy that should be used as a focal document to determine what regulatory reforms are required to support the strategy implementation. Based on this analysis the gaps in the existing regulations should be addressed and new regulations formulated where required
Output 2 Action Point 1 | .
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2 | The L&DDD needs to be provided technical advisory support for formulating well considered PPP transactions as this capacity is lacking in the L&DDD and halting it from moving on the PPP proposals that it is currently working on.
Output 2 Recommendation 3 | USAID, PEGIP and DFID need to coordinate their efforts for regulatory reforms so that they can build on each others efforts, avoid duplicity of labour and reduce the transaction costs for L&DDD.
Output 2 Action Point 2 | With support of the interim TC, L&DDD will be facilitated to engage the required expertise to access PPP related transaction support.
Output 2 Action Point 3 | DFID to initate donor coordination mechanism for L&D with active support of the L&DDD.
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Access to yield enhancing practices, better healthcare, and better animal nutrition available to 100,000 dairy farmers in the selected 4 districts
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.25
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share | To be determined after the workplanning exercise for PIT by Oct/Nov, 2011
Indicator 1 (leave blank if standard indicator) | Access of farmers to a fully functional insemination centre
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 1 functional center is established
Progress made in the period covered by this review, including numbers | PIT has proposed improving the breeding services for small holders through creating a network of trained AI technicians who will deliver services on farm door step. Initially a total of 200 community nominee will be trained for 3 months. The training program will be outsourced to Livestock Training Institutes Bahadarnagar and Sheikhupra and Directorate of Continuing Education University of Veterinary and Animal Sciences (UVAS), Lahore who already have experience of conducting such trainings. Candidates for the training will be nominated by the community organization and selected by the training institute and PIT in accordance to set selection criteria. On completion of training they will evaluated through written and practical examination conducted by training institute and PIT. The successful trainees will be given AI kit and each will be assigned a cluster of 12-15 COs of their respective community. PIT through service provider will ensure in time supply of quality semen in required doses together with storage facilities in the form of liquid nitrogen and containers. The project design, impelementation, monitoring and procurement modalities of this intervention will be finalized with through the interim TC which will be operative by Sep/Oct, 2011. Their work will be augmented by livestock assistants who after completing two years trainings will join them later both for AI and animal health cover. Currently, L&DD Dept. has large number of AI centers in the four districts but is unable to extend AI services in remote rural areas because of shortage of trained manpower and lack of mobility. Private AI technicians mostly non qualified and not properly trained are offering AI services to such unreached farmers using sub standard seme which has added to the problem of repeat breeding and infertility. Progress on this indicator can be considered good since considerable spade work has been completed regarding building the AI delivery capacity in the districts.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Access of farmers to a fully functional animal health facility.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 1 animal health facility, equipped with qualified veterinarian is established and fully functional
Progress made in the period covered by this review, including numbers | Until the baseline resutls are available, 2 of the 3 initial activities being planned by PIT are the training of 200 Veterinary Assistants (VAs) and 3,000 Lady Extension Workers and 1200 Community Extension Workers (men) The rationale for training VAs and EWs is to help fill the gap of technical assistants in the veterinary hospitals and dispensaries in the 4 districts and provide on the door extension services in communities, particularly to women who are predominantly engaged in taking care of the animals.. The VA training will cover animal health, provision of AI services, and improved farm practices and livestock management while extension workers will provide basic health care services livestock farming information.. The VA training will take about 2 years while EW's training will be for about 4 weeks. The VA's and the EWs willl be able to find regular employment with either the the milk processors, the government or become microentrepreneurs providing their services for a fee. Project design, implementaton, monitoring and procurement of implementing partner for the two projects willl be managed through the interim TC arrangement. Progress on this indicator can be considered between good to medium.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Access of farmers to good quality fodder and better animal nutrition
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Fodder nutrition is accessible to beneficiary farmers in 1 of the 4 selected districts
Progress made in the period covered by this review, including numbers | Based on the district consultations held in all of the 4 PEOP districts and a provincial consultation with L&D related stakeholders, a set of interventions has been proposed by the L&D Adviser and PIT Team leader for improving the access of farmers to improved nutrition for livestock. These interventions focus on building the farmers capacity, involving the community organizations and the private sector. Focus of interventions is proposed to be on: increasing access to improved fodder seed, introducing modern fodder cultivation practices, fodder preservation through silage and hay making and supply of balanced protein rich feed (vanda) to farmers. The project rationale, design, implementation and procurement modalities of the proposed interventions will be determined with help from TC being planned for the PIT and that will be available by Sep/Oct, 2011. Actual activities are expected to commence in the first quarter of 2012. Considerable consultations at the district level have helped shape thinking of PIT and progress on this indicator can be considered medium.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | Community organisations of dairy farmers
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | An additional X community organizations will be established
Progress made in the period covered by this review, including numbers | PIT consultations with stakeholders reveal that instead of forming new cos', PIT should bank on those cos' which have formed for L&D related activities. In situations where none such cos' exist, new cos' will be formed. All community mobilization work is being planned in partnership with NGOs having good track record of social mobilization. The role of Cos will be central in most of PIT's activities given that they provide an entry point in communities, can ensure wider ownership of interventions and can help identify specific target groups for interventions. In addition, one of the 3 major initial activities of the PIT until the baseline data is available is the installation of 40 milk chilling plants, 10 in each of the 4 PEOP districts, with 3 cos/120 farmers supplying milk to each MCP.. 2 options are currently being contemplated both of which can be implemented to assess which one works best in terms of improving farmers negotiating leverage and is also sustainable beyond the programme life. One option involves engagement of the MCP by a private sector service provider and cos while the other option involves ownership of the MCPs by the Pakistan Dairy Association and a service provider. The final project design, implementation, monitoring and preocurement modalities will be defined through the interim TC in Sep/Oct, 2011. So far, PIT has done internal brainstorming about how and where the communities can be engaged. Actual engagement of community based organizations has been low. Progress can be considered low.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 3 | 0.5
Impact Weighted Score | 12.5 | 0.125
Justification for the Score | District and province wide consultations have taken place. All important L&D relevant stakholders are aware of the potential scope of the programme and there is considerable interest among them to engage with the project. L&DD Dept is providing facilitative support to the PIT by delegating its staff to it unitl PIT's full time staff joins. Nonetheless, the PIT needs strong project development, implementaion and procurement support, while the scope of the PIT as proposed in the log frame is very wide and comples. Adjustments will need to be made in the log frame and the PC 1 after the workplanning exercise is conducted with TC.
Output 3 Recommendation 1 | IFAD ($49 million) has a project for South Punjab with very similar objectives and 3 of the districts are also common with PEOP. Donor coordination facilitated by the L&DD Dept is crucial to ensure that the two programmes complement each other and not duplicate efforts..
Output 3 Action Point 1 | PEOP team at DFID to initate a donor coordination mechanism for PIT
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2 | During the mid-term review the log frame indicators for Output 3 need to be revisited in the light of their sustainability prospects, technical advice of the PIT Team, and capacities within the Programme. Changes in the PC 1 will be made accordingly.
Output 3 Recommendation 3 | During the mid term review in Feb 2012 allocation of the Programme Funds between the PSDF and the L&D component/PIT should be reassessed. PIT should also coordinate with PSDF for provision of L&D related training through PSDF.
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | At least 250,000 individuals are provided access to better skills through access to training opportunities in 4 selected districts of Punjab
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share | £25 million
Indicator 1 (leave blank if standard indicator) | Market relevant skills training to the poor
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Fully functional independent not-for-profit Punjab Skills Development Fund (PSDF) setup to provide market relevant skills training to the poor in the 4 selected districts of Punjab.
Progress made in the period covered by this review, including numbers | The Punjab Skills Development Fund (PSDF) was incorporated as a not-for-profit Section 42 company under the Companies Ordinance 1984 in October, 2010. The Fund has a proactive private sector dominant Board of Directors and a management hired on merit based open competition. The management and operational systems of the Fund are at varying levels of being finalized. Rs.30 million has been disbursed for the Fund. Budget for 2011/12 has been approved. In the absence of the baseline data that provides specific skills related information, the Fund has introduced two small schemes for taining upto 5,800 poor (1700 women). These are namely Skills For Employability (across the 4 districts) and Vocational Training for 6 Model Villages in Muzaffargarh. 34 EOIs for Model Villages and over 110 for SE were received. The Fund has finalised the training organisations for model villages. JV of Hashoo Foundation/PVTC and TUSDEC will be contracted for provision of training August 15 onwards. Progress on this indicator is excellent as the Fund has been incorporatated and has started its work.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Access of marginalised groups to skills training
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | A strategy to ensure marginalized groups can access training is in place and implemented.
Progress made in the period covered by this review, including numbers | The Fund's grant criteria favor skill providers who are reaching out to rural areas, targeting women and the poor. As a result consortiums of NGOs and skill providers are being formed to have outreach in the more rural and marginalized communities. The hands on experience of the intial schemes of the Fund, will help generate lessons and insights that will be useful in shapaing a strategy for targeting the marginalized that is rooted in the real life context of the districts. Baseline data will also be important in shaping such a strategy. Progress on this indicator can be considered medium but is expected to pick up by Nov/Dec, 2011 when more lessons and insights to inform a strategy will be generated through actual experiences of the Fund.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Access to private training courses through vouchers
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Design of needs based voucher scheme is approved by Steering Committee and tested by PSDF
Progress made in the period covered by this review, including numbers | Vouchers are being planned for targeting specific marginalized groups so that they get adequate opportunity to acquire skills. However, PSDF is awaiting the baseline data that will help determine the target groups for vouchers and the design details of this instrument. Progress on this indicator can be considered low.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 2 | 0.75
Impact Weighted Score | 18.75 | 0.1875
Justification for the Score | i) The Fund represnts the first initiave of its kind in Pakistan and has the potential of becoming a one-stop window through which public and development assistance for the skills sector is funneled in Punjab. ii) The Fund enjoys efficient governance, management and has the resources to undertake its activities. iii) Even though baseline data is delayed, the Fund has initiated two schemes which will help the Fund to learn about the market as much as to provide the training. Additional skill schemes are being designed based on district consultations and feedback of the Chambers of Commerce and Industries. These will be presented to the Board at its sixth Board meeting in Aug/Sep, 2011.iv). Within the districts and nationally the Fund has stimulated the skills market and innovative alliances were being formed in order to access Fund's grants. v) The target of 250,000 has not been agreed by the Board given the cost of training in Pakistan (on avg.Rs.30,000) and even overseas. Overall target for skilling people will be determined after the baseline report is available. During the APR, the management agreed to explore during the mid-term review in Feb, 2012 the possibility of further expanding the log frame indicators for the Fund, to include x% of people to be employed within x months of training and % increase in incomes of the skilled.
Output 4 Recommendation 1 | At the mid-term review in Feb, 2012 the log frame indicators for Output 4 need to be revised and expanded to include additional indicators if the Board agrees and adjustments made to the PC 1 accordingly.
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2 | During the mid-term review the Fund’s policy towards indirect and direct subsidies needs to be verified in light of CERP household baseline data and a strategy for targeting the marginalized groups (women, minorities, lower castes, the more poor among the poor and the disabled) should be formed.
Output 4 Recommendation 3 | The Fund should develop a coherent communications strategy that maps out all the stakeholders, and short and long term objectives that the Fund wants to achieve against them. In addition, the donor coordination for skills needs to be initated by PEOP team at DFID with engagement of PSDF.
Output 4 Action Point 2 | Social Development Adviser at DFID for PEOP can provide guidance and support for formulating the strategy for targeting the marginalized.
Output 4 Action Point 3 | PEOP team at DFID to provide a sample communication strategy to the Fund and facilitate it in conducting road shows for increasing awareness about the Fund and mobilizing potential funding support from it from UK based multinational companies based in Kh and Lh.
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5 | Knowledge management and sharing
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 10%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.2
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | £0.5 million
Indicator 1 (leave blank if standard indicator) | Research capacity on inclusive growth in Punjab
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Centre for Research on Inclusive Growth is established and functional in partnership with an existing academic institution in Punjab
Progress made in the period covered by this review, including numbers | Thinking has evolved during the last one year that instead of setting up a Center for Inclusive Growth as envisioned in the Programme Document, research and analytical capacity at local universities should be strengthened by promoting partnerships between leading international research tanks and academicans and the local universities, or by engaging leading Pakistanis economists who can draw on the in-field research infrastructure and capacitities of the local universities. Research topics will be determined by in collaboration with the GoPb based on dialogue and discussions with well reputed economists, CERP data, experience of PSDF and LIT in the field and dialogues with district administrations in the four districts. Progress on this indicator can be considered medium as thinking has evolved to do things differently from what is envisioned in the log frame. Once the TA firm is hired in first quarter of 2012 and CERP data becomes available work on this indicator will pick up speed.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Programme impact understood and shared
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers | Under an Accountable Grant Agreement, CERP has been contracted to conduct a set of baseline surveys covering the households (seperate questionnaires for women and men) the employers, the skills providers, milk supply side and indepth communities survey. These surveys are based on the Randomized Control Trials (RCT) methodology which is being followed to evaluate the programme at the end of four years. Understanding and appreciation about this metodology is clear among all stakeholders ie. the PSDF, LIT, P&DD, and donors. There is interest among donors and international NGOs to learn from the impact evaluation that comes out at the mid-programme review and its final evaluation. Nevertheless, the delay in the baseline surveys is constricting the potential of the PSDF and the PIT to undertake activities.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 | 3 | 0.5
Impact Weighted Score | 5 | 0.05
Justification for the Score | The research capacity involved in PEOP, through CERP (doing the baseline presently and the impact evaluation of the Programme following the RCT methodology) is of high international calibre.A very capable team of international economists drawn from reputed international universities (LUMS, Harvard, UCL, and the IGC) and research outfits are engaged in CERP. On the other hand, due to the change in thinking about the CIG and the TC management arrangement originally being envisioned there has been a delay in commissioning pro-poor research for influencing and shapring policy. In addition, the CERP baseline reports lag behind Programme implementation.
Output 5 Recommendation 1 | Output 5 can be merged into Output 1 as Output 1 builds on Output 5. The purpose of the pro poor research of the CIG, and the RCT impact evaluation of the Programme is to catalyze debate and formation of pro poor policies and regulatory changes.
Output 5 Action Point 1 | During mid term review of the Programme in Feb, 2012, log frame should be modified accordingly.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2 | DIFD to review the AG timeline and finance with CERP and amend the AG accordingly
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes
Note on D335: Akhlaq Ahmed: In addition to justification provided, delay in seting up AG and transfer of funds was also the reason. Let us be transparent and reflect this in justification. I will share a latest email from CERP on this.

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-07-29
Impact Weighting (must = 100) | 100%
Total Impact Score | 56.25 | 0.5625
Output Risk | Medium | 1.75
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment | X
Joint donor review
Independent consultant review | X
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner | X
National non-Government partner | X
Independent consultant | X
Donor partners
DFID staff | X
Donor partners | None
Comment here on the Method of Scoring and Scoring Responsibility. | Indepth discussions took place with all important stakeholders including for example: the PSDF board and management, the PIT Team leader, PEOP focal staff at the Livestock and Dairy Development Department, GoPb, the Planning and Development Department of the GoPb, Steering Committee members and third party objective reviewer from DFID Nepal and SolveAgriPak which is a consulting company in the L&D sector.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | PEOP is piloting a PPP model which is providing learning opportunities for both the public and the private sector led Board in terms of balancing between the strategic advice that is provided by the Programme's Steering Committee and the authority of the Board as provided for by the Companies Ordinance 1984 for a not-for-profit company ('housed' within a Programme).
Working with Partners Recommendation 1 | Roles of the Steering Committee, the Government and the Board need to be clearly spelt out and agreed upfront and political support should be mobilized to support the arrangement. In addition there should be flexibility to review and revise them as the Programme evolves. For example, the SC should be responsible for facilitating intergovernmental relationships and ensuring that the company's activities are in compliance with the Programme vision, while the Board should have full operational and policy responsibilities for the company.
Working with Partners Action Point 1 | DFID needs to facilitate formalizing the political support in the Punjab to rationalize the roles as recommended above. Articles of Association of the PSDF, the PC 1 and the Log Frame should be modified accordingly during the mid term review in Feb, 2012.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
2. Best Practice / Innovation | PIT/L&D: Though PIT is in its nascent stage, some good practices have emerged as follows: i) Though not envisioned in the Programme Document, based on the needs, a Livestock Development Committee has been constituted to serve as the governance structure for PIT. It comprises of a mix of L&D experts, economists, farmers/entrepreneurs and academicians and will provide strategic guidance and policy support to the L&D component. All workplans, projects and TA proposals will be reviewed and approved by it. Similarly, in order to help resolve local issues with government and influentials at the district level, District Coordination Committees are being formed. ii) PIT has involved government expertise and solicited their feedback on its early interventions. The contribution of University of Veterinary and Animal Sciences (Department of Continuing Education) and Directorate of Livestock Extension Services in development of early projects has been commendable. The project is also cognizant of other donor interventions that can be successfully replicated in the target area. iii) PIT started and completed its stakeholder consultations early. The programme organized a Provincial Livestock Forum and four district workshops. Record of all of these consultations, which were very well-attended, have been compiled and shared with the concerned. PSDF: i) The PSDF Board has voluntarily adopted SECP’s Code of Corporate Governance which is applicable on publicly listed companies. This shows the Board's commitment to follow high standards of management and corporate governance.ii) PSDF Board has decided to keep management lean. It has started operations with 18 staff members as opposed to the 81 envisioned in the PC 1. It has also decided to open one office rather than 5 suggested in the Programme Document(the Programme Document reflected one head office and 4 district offices). iii) An outsourced monitoring model will be followed. This will be an innovative management experience for the Fund as well as for the Government of Punjab. Engagement of an external monitor will provide PSDF with unbiased perspective and build the capacity of local firms for monitoring public service delivery. iv) Unlike many private sector-led Boards, the PSDF Board has demonstrated strong interest in the Fund’s operations and has taken the lead in all key strategic decisions. Since the company incorporation in October, 2011, five Board meetings have been held and a sixth is planned. The Board was required to hold three meetings (one in each quarter) during this period. v) The PSDF website (www.psdf.org.pk) is operational. All tendering (programme and operational) is posted on the website, for which urdu pages are also planned. PSDF has actively engaged with its stakeholders especially employers and trainers. It has held pre-proposal conferences in all four target districts to encourage and guide proposal development by private training institutes.
Best Practice / Innovation Recommendation 1 | i) The aim should be for the L&DD Dept to continue facilitating PIT and taking on the larger oversight and ownership of some of the PIT activities beyond the Programm life. L&DDD should also support the donor coordination mechanism.
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2 | Regular consultations with the stakeholders are important for reality check and to assess the feedback on ongoing and planned implementation activities.
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Preperation of a workplan for PIT and time bound project activities
Project Management Recommendation 1 | Time-bound milestones for preperation of a workplan and project activities with clear line of sight to results need to be put in place.
Project Management Action Point 1 | Under the TA arrangement a Project Development and Implmentation Specialist needs to be hired immediately to provide Programme planning and implementation support to PIT
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | When working in remote/rural areas the project design should be cognizant of the infrastructure and HR availability in those areas and make programme implementation arrangements accordingly.
Key issues, points of information or additional comments that may be useful for this or other project teams. | When joint programmes are being developed with the Government, the Programme Mgmt team and the Finance Dept of the Government should discuss and gain common understanding of the up-to-date required accounting and account opening procedures. This should be part of the Programme Design report and will help save time once the Programme is being made operational.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
Programme Document PEOP
PC 1 PEOP
Minutes of the 4 Board Meetings of PSDF
Report on the 4 workshops on capacity building held in the districts by PSDF
Minutes of the two Steering Committee Meetings held to date
Powerpoint presentation to the SC on the new TA arrangement
Progress Report of the L&D component
4 Reports on the district consultations and 1 provincial consultation of the L&D component with relevant stakholders and potential partners
Baseline Indicator Report of the TAMA (based on secondary data)
Baseline Surveys Proposal of the CERP and survey questionnaires
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | The PSDF model represents a very innovative approach, new to Pakistan, for provision of market based skills. The institutional sustainability prospects of PSDF are high as it is attracting political support and attention of the private sector and donors. If PSDF continues to enjoy the support of an efficient Board and management, it has high prospects of becoming a one-stop window through which investments in the skill sector are channelized in Punjab. Being a not-for-profit company under the Companies Ordinance, 1984 it can continue in perpetuity with recourse to funding support from the government, private sector and donors based on the strength of its performance. L&D: PIT is exploring three options (or a combination thereof) for the sustainability of its interventions i.e. projects have ownership of the communities, the private sector parties, and the L&DD Dept. Nevertheless, sustainability of the PIT interventions remain to be seen and depend highly on how well the design of the projects that are implmented mobilize ownership and partnerships of the communities, private sector and the L&D Department.
Sustainability Recommendation 1 | PSDF will prepare a communications strategy that among others aims to create awareness about the Fund and mobilizes government, private and donors funding support for it.
Sustainability Action Point 1 | PSDF will conduct road shows in Karachi and Lahore to create awarenewss about the Fund among UK based multinationals and try to mobilize funding support from them in the long run. DFID/PEOP team to provide a sample communications strategy to PSDF and take necessary steps to mobilize government and donor funding support for it.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2 | L&D: The design of all the projects that the L&D implmements should specifically address how the interventions being planned will be sustained beyond the life of the Programme
Sustainability Recommendation 3
Sustainability Action Point 2 | The PIT to develop a project document format for all of its projects/interventions that specifically addresses the issue of sustainability.
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation | By
A1: Goal
R1 | Given the critical role of the baseline survey their timely completion needs to be managed closely and GoPb to continue to provide facilitative support. | DFID to follow up CERP | ongoing
R2 | During the mid-term review of the Programme in Feb, 2012 the feasibility of expanding the scope of the Programme to other districts and its duration should be determined. | DFID in conjunction with L&DD, PIT, PSDF and P&DD | Feb, 2012
R3 | 0
A1: Purpose
R1 | 0
R2 | 0
R3 | 0
A1: Risk
R1 | PSDF should focus on: i) Combining entrepreneurial/small business management training with skill training in order to improve self-employment opportunities for trainees. ii) Explore skill development opportunities in the more dominant sectors in the districts i.e. agriculture, manufacturing, and services. iii) Fund and the livestock and dairy component of the PEOP can collaborate for provision of L&D related training through the Fund. This will create synergies within the PEOP components and assist both the components to meet their goals drawing on each other’s strengths. | PSDF Board and PSDF - DFID to follow up. And for (iii) PSDF and L&DDD | Oct/Nov, 2011
R2 | 0
R3 | 0
A1: Logframe
R1 | Log frame should be revised after the mid-term review in February, 2012 | DFID to initiate in conjuction with PSDF, PIT/L&DD, CERP and P&DD | March, 2012
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | PSDF is carving political support and influence to shape the development of a skills policy in Punjab. This needs to be reflected in the logical framework under output 1 indicators, since a skill policy will help to contribute to creation of economic opportunities for the poor which output 1 aims to do. | Skills Strategy Adviser PSDF and PSDF | March, 2012
R1.2 | A group of leading economists should be engaged to initiate pro-poor research and policy formulation work. Areas meriting pro-poor policy reform should be sieved through the baseline report in December, 2011 and through consultations with a variety of relevant stakeholders. | DFID to initiate a TA management firm which will initiate and manage this work | March, 2012
R1.3 | Through TA support from DFID, PSDF should be provided the services of a Skills Policy and Strategy Adviser to help shape and influence development of a market oriented skills policy for Punjab through engagement of and debate among a cross section of relevant stakeholders drawn from industry, politics and bureaucracy. CERP household baseline will generate additional data and information to shape the policy and regulatory work govering skills sector in Punjab and identify additional areas that need addressing through a policy for poor districts.. | DFID has engaged a Skills Adviser PSDF. Policy work to be initiated and managed by her. | Oct/Nov, 2011
R2.1 | The L&DDD has a Livestock Development Strategy that should be used as a focal document to determine what regulatory reforms are required to support the strategy implementation. Based on this analysis the gaps in the existing regulations should be addressed and new regulations formulated where required | Interim TA to initiate this work | Nov/Dec, 2011
R2.2 | The L&DDD needs to be provided technical advisory support for formulating well considered PPP transactions as this capacity is lacking in the L&DDD and halting it from moving on the PPP proposals that it is currently working on. | Interim TA to initiate this work | Nov/Dec, 2011
R2.3 | USAID, PEGIP and DFID need to coordinate their efforts for regulatory reforms so that they can build on each others efforts, avoid duplicity of labour and reduce the transaction costs for L&DDD. | PEOP L&D Adviser | Oct/Nov, 2011
R3.1 | IFAD ($49 million) has a project for South Punjab with very similar objectives and 3 of the districts are also common with PEOP. Donor coordination facilitated by the L&DD Dept is crucial to ensure that the two programmes complement each other and not duplicate efforts.. | P&DD | Sep, 2011
R3.2 | During the mid-term review the log frame indicators for Output 3 need to be revisited in the light of their sustainability prospects, technical advice of the PIT Team, and capacities within the Programme. Changes in the PC 1 will be made accordingly. | DFID in conjunction with implementing partners | Feb/March, 2011
R3.3 | During the mid term review in Feb 2012 allocation of the Programme Funds between the PSDF and the L&D component/PIT should be reassessed. PIT should also coordinate with PSDF for provision of L&D related training through PSDF. | DFID in conjunction with implementing partners | Feb/March, 2011
R4.1 | At the mid-term review in Feb, 2012 the log frame indicators for Output 4 need to be revised and expanded to include additional indicators if the Board agrees and adjustments made to the PC 1 accordingly. | DFID in conjunction with PSDF | Feb/March, 2011
R4.2 | During the mid-term review the Fund’s policy towards indirect and direct subsidies needs to be verified in light of CERP household baseline data and a strategy for targeting the marginalized groups (women, minorities, lower castes, the more poor among the poor and the disabled) should be formed. | PSDF Board/Mgmt, CERP and DFID | Dec, 2011
R4.3 | The Fund should develop a coherent communications strategy that maps out all the stakeholders, and short and long term objectives that the Fund wants to achieve against them. In addition, the donor coordination for skills needs to be initated by PEOP team at DFID with engagement of PSDF. | PSDF Board/Mgmt. Donor coordination to be handled by DFID | Nov, 2011 & ongoing
R5.1 | Output 5 can be merged into Output 1 as Output 1 builds on Output 5. The purpose of the pro poor research of the CIG, and the RCT impact evaluation of the Programme is to catalyze debate and formation of pro poor policies and regulatory changes. | DFID in conjunction with implementing partners | Feb/March, 2011
R5.2 | DIFD to review the AG timeline and finance with CERP and amend the AG accordingly | CERP and DFID | Sep/Oct, 2011
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Roles of the Steering Committee, the Government and the Board need to be clearly spelt out and agreed upfront and political support should be mobilized to support the arrangement. In addition there should be flexibility to review and revise them as the Programme evolves. For example, the SC should be responsible for facilitating intergovernmental relationships and ensuring that the company's activities are in compliance with the Programme vision, while the Board should have full operational and policy responsibilities for the company. | PSDF Board, P&DD and DFID | on going
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | i) The aim should be for the L&DD Dept to continue facilitating PIT and taking on the larger oversight and ownership of some of the PIT activities beyond the Programm life. L&DDD should also support the donor coordination mechanism. | L&DD and PIT | on going
R2 | Regular consultations with the stakeholders are important for reality check and to assess the feedback on ongoing and planned implementation activities. | PSDF and L&DD/PIT | on going
R3 | 0
Project Management
R1 | Time-bound milestones for preperation of a workplan and project activities with clear line of sight to results need to be put in place. | PIT with support of interim TA | Sep/Oct, 2011
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | PSDF will prepare a communications strategy that among others aims to create awareness about the Fund and mobilizes government, private and donors funding support for it. | PSDF Board and Management | Sep/Oct, 2011
R2 | L&D: The design of all the projects that the L&D implmements should specifically address how the interventions being planned will be sustained beyond the life of the Programme | PIT with interim TA support | ongoing
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | PEOP team to follow up closely on CERP and identify mitigation measures for bottlenecks and risks. | DFID | ongoing
AP1.2 | Adjustments to the Log frame and the PC 1 need to be made accordingly. | DFID | Feb/March, 2011
AP1.3 | 0
A1: Purpose
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | Weekly follow up of the PEOP team required for i) CERP ii) engaging the TA iii) progress at PSDF regarding new products. |  | Ongoing
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | The logical framework and the PC 1 should be revised during the mid-term review and a project management consultant should be engaged to help rationalize and logical framework. All indicators need to be sex disaggregated where possible. | DFID | Feb/Mar, 2011
AP1.2 | 0
AP1.3 | 0
AP2.1 | .
AP2.2 | With support of the interim TC, L&DDD will be facilitated to engage the required expertise to access PPP related transaction support. | Interim TA | Nov/Dec, 2011
AP2.3 | DFID to initate donor coordination mechanism for L&D with active support of the L&DDD.
AP3.1 | PEOP team at DFID to initate a donor coordination mechanism for PIT | Dfid | Sep/oct, 2011
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | Social Development Adviser at DFID for PEOP can provide guidance and support for formulating the strategy for targeting the marginalized. | DFID (SDA EGG) and PSDF | Nov/Dec, 2011
AP4.3 | PEOP team at DFID to provide a sample communication strategy to the Fund and facilitate it in conducting road shows for increasing awareness about the Fund and mobilizing potential funding support from it from UK based multinational companies based in Kh and Lh. | DFID | Done
AP5.1 | During mid term review of the Programme in Feb, 2012, log frame should be modified accordingly. | DFID in conjunction with implementing partners | Feb/Mar, 2011
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | DFID needs to facilitate formalizing the political support in the Punjab to rationalize the roles as recommended above. Articles of Association of the PSDF, the PC 1 and the Log Frame should be modified accordingly during the mid term review in Feb, 2012. | DFID/HC, PSDF Board | On going
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | Under the TA arrangement a Project Development and Implmentation Specialist needs to be hired immediately to provide Programme planning and implementation support to PIT | DFID | Sep, 2011
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | PSDF will conduct road shows in Karachi and Lahore to create awarenewss about the Fund among UK based multinationals and try to mobilize funding support from them in the long run. DFID/PEOP team to provide a sample communications strategy to PSDF and take necessary steps to mobilize government and donor funding support for it. | DFID-HC and PSDF | Oct, 2011
AP1.2 | The PIT to develop a project document format for all of its projects/interventions that specifically addresses the issue of sustainability. | PIT with interim TA support | Oct, 2011
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3