## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 108003
ARIES Project Description | Bihar Governance & Administrative Reforms Programme
A1: Goal, Purpose, Risk
Goal
Goal statement | Improved development outcomes as a result of better quality of service delivery
Indicator 1 | Development Index (Composite index across 8 service domains)
Milestone for this review (if any) | 1.5 Index score
What progress has been made in the period covered by this review? | Based on the State of States Report 2010 (India Today), Bihar has improved to 1.3 from a baseline of 0.74 in 2008, although its overall ranking remains same (20 out of 20 states). Assessment for 2010-11 will be released in Sept 2011.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target (s)? | The quality of governance in Bihar has undergone a transformation under the new regime which came to power in 2005. There has been significant improvement in development outcomes over the last five years. Some of the key areas of improvement in governance pertain to the following: - Plan expenditure has grown by almost 500% from £638mn to £3333mn between 2005-06 and 2011-12 - GSDP has grown at more than 10% between 2005-06 & 2010-11 - Improvement in law and order and significant reduction in serious crimes - Significant improvement in quality of social sector services - Enrolment in primary education, Institutional deliveries, vaccination etc. - Development of infrastructure - From 2006 till 2010, 23606 kms of road have been constructed in the State - Strong anti-corruption initiatives like disclosure of property by Ministers & public servants, forfeiture of property from corrupt officials, Right to Public Services Act etc. undertaken
Goal Recommendation 1 | There is need to continue to strengthen the institutional, financial, human resource management and infrastructural capacities for improving the quality of service delivery in Bihar.
Goal Action Point 1 | Along with cross-cutting reforms across sectors, reforms need to focus on district and sub-district administration.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Better governance (improved government capability, accountability and responsiveness) enables better delivery of basic services to all its citizens, particularly the poorest and most excluded.
Indicator 1 | Quality of service delivery; Citizen satisfaction
Milestone for this review (if any) | Baseline for Citizen Satisfaction developed
What progress has been made in the period covered by this review? | Between 2009 and 2010, Bihar has recorded improvements across different sectors as per the State of States Report 2010 - Agriculture: 1.07 to 1.1; Primary Health: 0.61 to 1.3; Infrastructure: 1.43 to 3.3; Law & Order: 0.43 to 0.5. Assessment for 2010 is yet to be released. A Citizen Report Card (CRC) is in the process of being undertaken, findings of which will be available by December 2011. The CRC will cover all 38 districts and 534 blocks in the state and will provide baseline information on quality of service delivery for 8 key services - primary healthcare, primary/secondary education, Integrated Child Development Services (ICDS), Public Distribution System (PDS), National Rural Employment Guarantee Scheme (NREGS), pensions, issuance of certificates and grievance redressal. The CRC will be repeated on an annual basis.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Own Tax Revenue as a Proportion of GSDP
Milestone for this review (if any) | 5.5%
What progress has been made in the period covered by this review? | Against a baseline of 4.7% in 2008-09, Tax to GSDP improved to 4.8% in 2009-10 and 5.4% in 2010-11 (revised estimates). Own tax revenue has seen significant growth in the last two years (31% year-on-year). Technical support under the programme contributes to strengthening the tax base in three key departments - commercial taxes, registration and transport. Based on 2010-11 revised estimates, annual tax revenue for these three departments has grown by 32% last year, up from £956m to £1259m.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Tax to GSDP Ratio
Milestone for this review (if any) | 4%
What progress has been made in the period covered by this review?
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | The purpose level assumptions have been realised to a large extent. The political and administrative commitment to governance reforms in the state has enabled the programme to become a key instrument to enable GoB to carry out those reforms. Strong leadership by the Chief Secretary, Department Heads and Mission Director enabled the programme to extend the depth and width of reforms across the government.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | At this stage, due to lack of availability of data, it is difficult to assess the degree to which achievement of purpose is contributing to realisation of goal.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | At this stage, there is qualitative evidence to suggest progress on outputs leading to achievement of purpose. The programme directly feeds into the purpose through varied interventions under the three outputs. However, we will estimate attribution from each output by triangulating data from different sources such as MIS, citizen report cards, employee survey, budget documents etc.
Purpose Recommendation 1 | With increase in programme uptake by different departments, there is need to strengthen programme oversight by the governing council
Purpose Action Point 1 | Bi-annual review of programme delivery by BPSM, focal departments and technical agency to be undertaken by governing council
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 2 | #VALUE!
Purpose Justification | The project has enabled GoB to undertake significant governance reforms viz. (a) Improved Human Resource Management: This includes (i) cadre restructuring, regular recruitment which have enabled streamlined personnel deployment at the frontline level (ii) training & capacity development across different cadres (Bihar Administrative Service, Commercial taxes, Bihar Public Service Commission, Education, Group D (Peons etc) services) (iii) New system of performance appraisal for state cadres (b) Responsive & accountable service delivery that involves launch of the Right to Public Services Act (40,000 applications registered daily) for time-bound delivery of services, simplification of certificate issuance process and use of low-cost technology solutions to make governance citizen-centric viz. citizen helpline, scheme monitoring etc. (c) increased uptake of the programme to a wider departmental spectrum including Commercial Taxes, Registration, Transport, Home/Police, SC/ST Welfare, HRD, Public Grievances. However, some of the proposed initiatives at departmental level and reforms at the district/block level need to be intensified.
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability | Lately, some management issues have emerged from the part of Mission Directorate in coordinating the technical assistance provided by GTAST. DFID team has been in discussion with the Mission Director and the GTAST to sort out the issues and a positive outcome is expected.
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1 | Monitor whether the situation improves as a result of intervention by the Mission Director and take necessary remedial steps if situation persists.
Risk Action Point 1 | Review the progress with both Mission Directorate and GTAST to see whether issues have been addressed.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Log frame, DSOs, Cross-Cutting Markers
Log frame revised/needs revision? | No
If Yes, why was/is this?
Log frame Recommendation 1
Log frame Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Log frame Recommendation 2
Log frame Recommendation 3
Log frame Action Point 2
Log frame Action Point 3
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision?
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Quality of human resource management viz. recruitment, training, performance management is more efficient and effective
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | The logframe was revised to reflect the importance assigned to the output.
Original or Revised Impact Weight (%) | 40%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.8
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 | (a) Proportion of vacancies against currently sanctioned strength for Bihar Administrative Service (BAS), Bihar Financial Service (BFS) and Bihar Registration Service (BRS) cadres | 4
Is this a Standard Indicator? | No | 5
Milestone for this review (if any) | 1) Less than 40% (Baseline ~ 50%) 2) Development of HR Database initiated | 0
What progress has been made in the period covered by this review? | Achieved. Overall vacancies across these cadres is less than 5%. For the BAS cadre, there are no vacancies; for BRS cadre it stands at 20% (reduced from 40% last year) and for BFS cadre it is 11% (down from 28% last year). Vacancies could be reduced due to (a) Strengthening of Bihar Public Service Commission (BPSC) which is the recruiting arm of GoB by improving their examination and recruitment processes. As a result, BPSC was able to clear the back log of appointment for the last 6 years from 47th to 52nd batch and recruitment is on for the 53rd-55th batch of officers into the BFS & BRS cadres and (b) The entire BAS cadre has been restructured reducing the total sanctioned strength to 1500 from 2100. In addition, new BAS cadre rules have been developed and submitted to GoB. The HR database for BAS officers has been completed and made online. A search engine has being designed through which employees can be searched on different parameters. The Secretariat Manual has been redrafted and submitted for government approval.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Training of BAS, BFS and BRS Officers
Is this a Standard Indicator? | No
Milestone for this review (if any) | All BAS probationers and 40% in-service BAS, BFS and BRS officers given training as per new training plan
What progress has been made in the period covered by this review? | Achieved. All probationers (47th to 52nd batch) have been given induction training including cross-state exposure. More than 40% BFS & BRS officers have undergone training as per the new Training Plan. For BAS officers, in-service training plan has been approved and will be rolled-out through BIPARD. Training for Group D staff (approx. 65000) has been initiated while a training plan for Group C staff (approx. 70000) is being developed. A comprehensive training strategy for GoB has been drafted and under review by GoB. The key features of this strategy are (a) Compulsory training of minimum 48 hours annually for all GoB employees (b) 1.5% of salary expenses to be earmarked as training expense for all departments (c) Training to be linked with ACR / Performance Appraisal, Promotions and increments.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Proportion of appraisal reports for BAS officers which are initiated and accepted every year
Is this a Standard Indicator? | No
Milestone for this review (if any) | 40%
What progress has been made in the period covered by this review? | Largely Achieved. Bihar is the first state to develop and implement a revised appraisal system in line with the Performance Appraisal Report (PAR) framework adopted by Government of India for IAS Officers. The revised PAR form was notified for BAS in Dec 2009 and was made applicable from FY 10-11. So far, 30% of PAR forms have been completed and accepted for FY 10. By year-end, it is expected that at least 50% of the officers complete self-appraisal using the new PAR form. This appraisal system is also being extended to cover other cadres. The new appraisal system shifts the onus on filling up the form to the employee rather than the reporting officer. Other features include developing a work plan for the year, indication of the training needs and objective rating on a scale of 1 to 10.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 | Establishment of a Centre for Good Governance (CGG)
Is this a Standard Indicator? | No
Milestone for this review (if any) | Roadmap for strengthening nodal Mission finalised
What progress has been made in the period covered by this review? | Moderate progress. It has been decided that instead of setting up a new institution, it is more appropriate to strengthen the Bihar Prashasnik Sudhar Mission (BPSM) for it to play the role envisaged for a CGG. The Memorandum of Association, Procurement Manual, Financial & Accounting Manual for BPSM have been developed and approved.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 1 | 2 | 0.75
Impact Weighted Score | 40 | 0.3
Justification for the Score
Output 1 Recommendation 1 | An institutional capacity development plan for BPSM needs to be developed to take on the role of CGG.
Output 1 Action Point 1 | A review needs to be undertaken to identify areas for strengthening institutional capacity of BPSM
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | Implementation of the new appraisal system to be completed in current financial year
Output 1 Recommendation 3
Output 1 Action Point 2 | GAD to regularly monitor progress of the new appraisal system
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Performance of focal Departments is made more effective, efficient and accountable
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | The logframe was revised to reflect the importance assigned to the output.
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.6
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Systems for enhancement of Tax Revenue (a) No. of registered dealers (Commercial Taxes Department) (b) Tax Rationalisation (Transport Department) (c) Digitisation of Registration Records (Registration Dept)
Is this a Standard Indicator? | No
Milestone for this review (if any) | (a) 200000 (Baseline 150000); (b) 500 crores (Baseline 303 crores in 2008-09 (c) Digitisation extended to 10 districts
What progress has been made in the period covered by this review? | Achieved to a large extent. No. of registered dealers increased to 180,123 in FY 11 from 123,040 in FY 08 and there has been a 36% year-on-year increase in revenue collection over the last three years (from £480m in 2007-08 to £1000m in 2010-11). A Tax Research Unit (TRU) has been established within the commercial taxes department for providing research support to the Department. Although the pace of reforms has been slower than expected, a range of critical initiatives has been agreed upon to be taken up over the next year. In Transport Department, tax reforms were undertaken (last 2 years) on the basis of a study on rationalisation of taxes for Transport Department. This resulted in Rs. 200 million incremental tax collected in FY 2011. A benchmarking study on staffing of the enforcement function helped create 67 additional posts at headquarter and field level. Digitization of old records(1995-2005) in Registration Department has been initiated in all 38 districts and 20% of old records numbering 12 million have been digitized. Technical training calendar has been developed and training undertaken for BRS cadre.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Delivery of social sector services (a) Adult Literacy Monitoring systems in Human Resources Dept. (b) Scholarships Monitoring System (SC/ST Dept)
Is this a Standard Indicator? | No
Milestone for this review (if any) | Institutionalisation of the adult literacy monitoring system; New online system for SC/ST scholarships
What progress has been made in the period covered by this review? | Achieved. Human Resources Department - HRD: The programme supported the development of a management information system (MIS) and establishment of a Project Management Unit (PMU) for monitoring the GoB's adult literacy programme (Akshar Anchal), which covered 40 lakh illiterate women across 200,000 centres. A sample survey revealed that after programme completion, 80% of women could read, write and do simple maths. The programme has also extended support through the creation of a technical support unit for the roll-out of centrally-sponsored Saakshar Bharat (National Literacy Mission) Programme. Technical assistance was also provided to HRD for designing the organizational structure of Education Infrastructure Development Corporation (EIDC). SC/ST Welfare Department: A static monitoring tool was developed for monitoring delivery of SC/ST post-matric scholarships. Based on a best practices study which mapped the delivery process across 4 states, a dynamic web-based tool is being designed with the support of National Informatics Centre (NIC), Bhopal.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Quality of Police Administration (a) Sensitisation/Training of frontline police personnel (b) Management of Human Rights Violation Cases
Is this a Standard Indicator? | No
Milestone for this review (if any) | Training Needs Assessment completed; Human Rights Cases Management System developed; Systems Strengthening for Prisons administration initiated
What progress has been made in the period covered by this review? | Achieved. A training needs assessment for Police Department has been completed. Currently a training programme on`Citizen-friendly Policing' is being designed. This will be rolled out over a 12 month period covering approximately 55,000 frontline police personnel across the state. For Home Department, the programme supported the development of a Human Rights Case Management system for monitoring pending human rights cases. This will ensure timely compliance with directives of the National/State Human Rights Commission. The system will be implemented and training of functionaries completed over the next 4 months. For improving prisons' administration, the old Prison Manual (1927) has been revised which will enable stronger organisational structures, streamlining of processes for handling prisoners and welfare & correctional aspects. Simultaneously, a jail management information system is also being designed.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 2 | 2 | 0.75
Impact Weighted Score | 30 | 0.225
Justification for the Score
Output 2 Recommendation 1 | Departments which have largely completed several reforms (such as Registration, Transport) may be excluded from future support while engagement with new departments like SC/ST welfare, Food & Consumer Protection and Home may be made more intensive.
Output 2 Action Point 1 | BPSM to rework the budgets and get approval from Governing Council
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2 | Technical assistance to HR Department (Education) and Energy Department can be strengthened in anticipation of future dedicated support through larger programmes
Output 2 Recommendation 3
Output 2 Action Point 2 | BGARP Team to coordinate with Education Team and CCEU to enable areas of technical support to be extended to HRD & Energy
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Strengthened district level administration and service delivery
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | The logframe was revised to reflect the importance assigned to the output.
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.6
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Quality of service delivery at district & sub-district level and its effective monitoring
Is this a Standard Indicator? | No
Milestone for this review (if any) | Delivery of public services strengthened; Monitoring system for service delivery institutionalised; First round of Citizen Report Card (CRC) initiated
What progress has been made in the period covered by this review? | Achieved. The programme extended technical and financial support for the design and implementation of the `Right to Public Services (RTPS) Act' in Bihar, which was formally launched on August 15, 2011. This included assistance for drafting the Act & its rules, standradisation & simplification of application forms & checklists, design & implementation of the monitoring system `Adhikaar', deployment of dedicated personnel at district/block level, training & capacity building (141 trainers and more than 28000 officials across the state) and communications support. The Act provides for time-bound service delivery of 50 services across 10 departments throughout the state. The Citizen Report Card (CRC) covering 8 key service domains will be undertaken from next month. The services of a professional research firm has already been procured and the CRC is expected to be completed by December 2011.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Redressal of public grievances
Is this a Standard Indicator? | No
Milestone for this review (if any) | Citizen information helpline institutionalised; Analysis of quality of grievance redressal undertaken
What progress has been made in the period covered by this review? | A centralised citizen information helpline ‘Jigyasa’ was operationalised in August 2010. Around 3000 calls are received every month and more than 80% callers surveyed have given positive feedback. This system was extended through a pilot to Nalanda district where a dedicated Interactive Voice Response System (IVRS) was implemented by the district administration, which provided citizens direct access to officials of 14 key departments. BPSM is now provided support for extending this system across the remaining 37 districts. Since May 2010, with programme support, BPSM has also appointed Public Grievance Officers (PGOs) in all districts and 10 key public service departments. Appointment of PGOs have helped reduce the backlog of grievance applications as well as enhancing the quality of redressal. Technical assistance has been provided for developing a typology of grievances and a system for monitoring pendency of grievances across departments and districts.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Implementation of Reform Strategy for Collectorate Modernisation
Is this a Standard Indicator? | No
Milestone for this review (if any) | Reforms implemented in at least five Collectorates
What progress has been made in the period covered by this review? | Moderate Progress. The programme has significantly helped build capacity at district & sub-district levels. Each district has been provided with one IT manager, one Public Grievance Officer and one executive assistant. At block level, each block has been provided with a block IT assistant for collating information and reporting. Based on a review of the certificate issuance process (income, domicile, caste certificates), GoB amended and simplified the process of certificate issuance. This has enabled the process to be made simpler and less cumbersome for the poor, particularly the scheduled caste, scheduled tribes & OBCs. It is expected to benefit 0.25 million people every year and significantly reduce processing time. A structural and functional review of the district administration and block administration will be taken up to identify reform priorities pertaining to organisational development & HR, service delivery, monitoring & evaluation, housekeeping & records management, training & capacity building etc.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 3 | 2 | 0.75
Impact Weighted Score | 30 | 0.225
Justification for the Score
Output 3 Recommendation 1 | Comprehensive strategy for strengthening district & block level administration required
Output 3 Action Point 1 | District & Block Administration Strengthening Plan to be prepared by GTAST and piloted across select districts before scale up
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 4 |  | 0
Impact Weighted Score |  | 0
Justification for the Score
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2010-09-15
Impact Weighting (must = 100) | 100%
Total Impact Score | 75 | 0.75
Output Risk | Medium | 2
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment | X
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner | X
National non-Government partner
Independent consultant
Donor partners
DFID staff | X
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility. | DFID team comprising of Emma Spicer, Peter Evans, Padma Kumar and Vivek Misra conducted the Annual Review from August 10 to 11, 2011. The scores given are based on the results shared by GoB/GTAST on various outputs which was reviewed by the DFID team during the Annual Review.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Ownership of the programme at the highest administrative level (Chief Secretary) has fostered greater uptake from other departments. Secondly, close coordination between TA team, BPSM and departments enabled the programme to successfully deliver on key government priorities such as the design & implementation of the Right to Public Services Act. By working with multiple departments on key areas, the programme has been able to enhance its profile substantially.
Working with Partners Recommendation 1 | Current Chief Secretary is likely to be retired in September 2011. DFID team should make proactive engagement with the new Chief Secretary to ensure that s/he takes active role in implementation of BPSM.
Working with Partners Action Point 1 | Meet with the new Chief Secretary as soon as s/he is appointed to ensure that he or she is briefed appropriately on the programme.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | The flexibility inherent in programme design enabled the programme to support a key priority of the government namely the `Right to Public Services Act', which was initially not envisaged as being part of programme support. The salience and relevance of the programme is largely due to the ability of the programme to support emerging government (and departmental) priorities along with high-quality technical assistance.
Best Practice / Innovation Recommendation 1 | While continuing to address emerging government priorities, it is important for the programme to resist ad-hoc requests from departments, which may have limited utility.
Best Practice / Innovation Action Point 1 | Departments provide detailed information to Governing Council on nature of support required from BPSM
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | 1. Development of a detailed work plan (department-wise) for the technical agency has helped to focus their work and helped monitor outputs better. 2. Support from the technical team to some departments have sometimes wavered. It is important to maintain a basic level of engagement and interest across the focal departments.
Project Management Recommendation 1 | The TA workplan to be reviewed by DFID every three months.
Project Management Action Point 1 | GTAST to report detailed progress on workplan every 3 months and provide key headlines every month
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2 | Need to have consistent technical support in key departments - CTD, Home, HRD, SC/ST, District Collectorates.
Project Management Recommendation 3
Project Management Action Point 2 | GTAST to deploy more quality personnel (& enhance the gender balance) in these key departments.
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
3195385 | BGARP Annual Review 2011 - Presentation
3195403 | BGARP: Interventions & Results Summary Aug 2011
3195364 | BGARP Annual Review 2011 - Aide Memoire
3195394 | BGARP Revised Logframe Aug 2011
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | The benefits arising will be largely sustained after the project. With the government agreeing to co-fund the Mission from October 2011 and strengthen it, institutional sustainability will be assured. The benefits from the programme interventions have been systemic in nature with a high level of ownership from nodal departments. Reforms undertaken through the programme have been institutionalised through formal orders and have been complemented by development of capacity for effective implementation. Some initiatives have already resulted in legislations for ex. Right to Public Services Act, Amendment to Motor Vehicles Act etc. However, some initiatives such as sms-based monitoring, grievance monitoring etc. need to be strengthened and higher administrative ownership needs to be fostered.
Sustainability Recommendation 1 | Improve systems and build higher ownership, particularly on monitoring mechanisms
Sustainability Action Point 1 | Integrate monitoring systems into departmental work; seek higher level review of schemes and services
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | There is need to continue to strengthen the institutional, financial, human resource management and infrastructural capacities for improving the quality of service delivery in Bihar. | GoB
R2 | 0
R3 | 0
A1: Purpose
R1 | With increase in programme uptake by different departments, there is need to strengthen programme oversight by the governing council | GAD / DFID
R2 | 0
R3 | 0
A1: Risk
R1 | Monitor whether the situation improves as a result of intervention by the Mission Director and take necessary remedial steps if situation persists. | DFID
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | An institutional capacity development plan for BPSM needs to be developed to take on the role of CGG. | GAD
R1.2 | Implementation of the new appraisal system to be completed in current financial year | GAD
R1.3 | 0 | GAD
R2.1 | Departments which have largely completed several reforms (such as Registration, Transport) may be excluded from future support while engagement with new departments like SC/ST welfare, Food & Consumer Protection and Home may be made more intensive. | BPSM
R2.2 | Technical assistance to HR Department (Education) and Energy Department can be strengthened in anticipation of future dedicated support through larger programmes | BPSM/DFID
R2.3 | 0 | GTAST
R3.1 | Comprehensive strategy for strengthening district & block level administration required | GTAST
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1
R5.2
R5.3
R6.1
R6.2
R6.3
R7.1
R7.2
R7.3
R8.1
R8.2
R8.3
R9.1
R9.2
R9.3
R10.1
R10.2
R10.3
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Current Chief Secretary is likely to be retired in September 2011. DFID team should make proactive engagement with the new Chief Secretary to ensure that s/he takes active role in implementation of BPSM. | BPSM
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | While continuing to address emerging government priorities, it is important for the programme to resist ad-hoc requests from departments, which may have limited utility. | DFID
R2 | 0
R3 | 0
Project Management
R1 | The TA workplan to be reviewed by DFID every three months. | GTAST / DFID
R2 | Need to have consistent technical support in key departments - CTD, Home, HRD, SC/ST, District Collectorates. | GTAST
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | Improve systems and build higher ownership, particularly on monitoring mechanisms | GTAST/ DFID/BPSM
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | Along with cross-cutting reforms across sectors, reforms need to focus on district and sub-district administration. | GoB
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | Bi-annual review of programme delivery by BPSM, focal departments and technical agency to be undertaken by governing council | BPSM
AP1.2 | 0 | GTAST
AP1.3 | 0
A1: Risk
AP1.1 | Review the progress with both Mission Directorate and GTAST to see whether issues have been addressed. | DFID
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | A review needs to be undertaken to identify areas for strengthening institutional capacity of BPSM | GAD
AP1.2 | GAD to regularly monitor progress of the new appraisal system | GAD
AP1.3 | 0 | GAD
AP2.1 | BPSM to rework the budgets and get approval from Governing Council | BPSM
AP2.2 | BGARP Team to coordinate with Education Team and CCEU to enable areas of technical support to be extended to HRD & Energy | BPSM/DFID
AP2.3 | 0 | GTAST
AP3.1 | District & Block Administration Strengthening Plan to be prepared by GTAST and piloted across select districts before scale up | GTAST
AP3.2 | 0 | GTAST
AP3.3 | 0 | BPSM/GTAST
AP4.1 | 0
AP4.2
AP4.3
AP5.1
AP5.2
AP5.3
AP6.1
AP6.2
AP6.3
AP7.1
AP7.2
AP7.3
AP8.1
AP8.2
AP8.3
AP9.1
AP9.2
AP9.3
AP10.1
AP10.2
AP10.3
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Meet with the new Chief Secretary as soon as s/he is appointed to ensure that he or she is briefed appropriately on the programme. | BPSM
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | Departments provide detailed information to Governing Council on nature of support required from BPSM | DFID
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | GTAST to report detailed progress on workplan every 3 months and provide key headlines every month | GTAST
AP1.2 | GTAST to deploy more quality personnel (& enhance the gender balance) in these key departments. | GTAST
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | Integrate monitoring systems into departmental work; seek higher level review of schemes and services | BPSM/GTAST
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3