## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 114487
ARIES Project Description | SARVA SHIKSHA ABHIYAN II (UNIVERSAL ELEMENTARY EDUCATION)
A1: Goal, Purpose, Risk
Goal
Goal statement | Improved education indicators leading to (i) increased life-time earnings of workers who have higher levels of educational attainment (there is strong international and Indian evidence of this); and (ii) increased productivity of workers in the future as a result of SSA’s quality-enhancing interventions
Indicator 1 | Youth Literacy Rate (15-24 year olds), disaggregated for: gender, SC, ST, Muslims, disabled, rural and urban.
Milestone for this review (if any) | None
What progress has been made in the period covered by this review? | The most recent data from UNESCO (2006) reports that total youth literacy increased from 76 to 82% between 2001 to 2006 (from 67% to 74% for girls and 84 to 88% for boys). We expect National Census data in 2012 to provide updated and disaggregated data by social group and geography. Note, however, that despite these increases, Indian industry continue to report a significant dearth of literate, employable youth.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Gross Enrolment Rate (GER) at Secondary school level, disaggregated for: gender, SC, ST, Muslims, disabled, rural and urban students.
Milestone for this review (if any) | None
What progress has been made in the period covered by this review? | The last Annual Review reported secondary GER as 53% (57% for boys and 50% for girls) using data from 2006/7 Selected Education Statistics (SES). The latest SES data (for 2007/8) reports GER of 58% (63% and 53% for boys and girls respectively). GERs for SC students are reported at 53% (56% and 49% for boys and girls); ST GERs are 43% (49% and 37% for girls); Rural GERs are 51% (55% and 46% for boys and girls). Disaggregated data are not available for Muslim, disabled and urban children. Our working hypothesis is that rising primary completion rates will result in increasing enrolments at the secondary level. This hypothesis is borne out by the data above, although not stictly within the time frame covered by this review. A more recent World Bank estimate (2010) suggests that the number of students graduating from upper primary school is increasing at the rate of 4% per year, and is expected to exceed 5% in 2011.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | We know that the growth of the elemetary education system is creating significant unmet demand at the secondary level. Beyond this, we have no fresh evidence during the period under review.C38+C30+C16
Goal Recommendation 1 | The findings confirm large gaps in literacy and enrolment between boys and girls, and the disadvantages faced by SC and ST children - most strikingly, ST girls. These gaps warrant remedial intervention for help ST and SC girls to complete upper primary and access secondary education. Essentially, this means that strong linkages between SSA and RMSA need to be developed.
Goal Action Point 1 | Targeted strategies to ensure that girls, particularly from disadvantaged groups, are able to access upper primary school as per the RTE norms of 3 km and are able to complete a full cycle of elementary education
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2 | DPs to pursue MHRD's agreement to develop SEMIS (Secondary Education MIS) nationally to the same standards as DISE, including social group dissaggregation. This should be a pursued actively during RMSA appraisal.
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | To significantly increase the number of 6-14 year old children, especially from special focus groups, enrolled, regularly attending and completing elementary education and demonstrating basic learning levels.
Indicator 1 | Retention rate at primary level increases from 75% to 80%. Disaggregated for gender; SC; ST; Muslims; disabled; rural and urban.
Milestone for this review (if any) | 75%
What progress has been made in the period covered by this review? | Partially Achieved. According to 2009-10 District Information System for Education (DISE), the primary retention rate was 74.0% in 2009-10, a modest improvement from 73.7% in 2007-8 (no data are available for 2008/9). However, this national figure hides wide disparities across and within States. For instance, Nagaland, Manipur and Arunachal Pradesh have retention rates below 50%, whereas HP, Punjab and Goa have rates that exceed 95%. In some cases, States have developed innovative strategies to keep children in school. Bihar, for instance, is helping to attract and retain girls in upper primary girls through such incentives as free bicycles for all girls continuing onto Class 9. Retention rates are a barometer of the overall efficiency of a school system, since they reflect such factors as drop out, repetition, transition, attendance, and completion. Retention appears to be progressing slowly year on year: meeting the 2012/13 national target will be challenging. No disaggregated data are available. States are also using different methodologies and data sources for reporting retention.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Improvement in learning levels at Grade 3. Disaggregated for gender; SC; ST; Muslims; disabled; rural and urban.
Milestone for this review (if any) | No specific value was set when the results framework was agreed. MHRD and donors' expectation was that (i)learning levels would improve and (ii) the results of the National Acheivement Survey would be dissemined to the States
What progress has been made in the period covered by this review? | Likely to be Partially Achieved As reported last year, the 2009 National Achievement survey reported modest gains in Grade 3 learning levels for language and maths. The 3rd round of Grade 3 Achievement Survey will be conducted in 2012/13. In the meantime, the 2010 'Annual Status of Education Report' (ASER, India's leading non- governmental assessment) finds a small decline in the % of children in Grade 3 able to read a short paragraph (Grade 1 text) from 27.4% in 2007 to 25.7% in 2010. According to ASER, the % of children able to do simple subtractions in Grade 3 has also decreased from 2007 to 2010 from 31.1% to 27%. Successive review missions have noted a 'plateau' in quality. Anecdotal evidence also suggests that parents are migrating from government to low cost private schools, in pursuit of education perceived as better quality. Our assessment is that implementing the Right To Education Act has put pressure on States to focus on a large number of quality-related inputs (eg reducing the Pupil Teacher Ratio, improving the school environment), detracting from a focus on strengthening the quality of classroom transactions, including attention to improving pedagogy, curriculum, and teacher training. C69
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Purpose assumptions are being realised, but these were partial and were not time-bound: (1) DISE data will continue to be collected, analysed and reported annually. DISE continues to gain traction as the main source of education data at the elementary level; and continues to be strengthened to iron out inconsistencies in reporting. Efforts are ongoing to align SES with DISE. (2) NAS is technically strengthened. DFID TC Fund efforts have successfully strengthened NAS and 'Item Response Theory' has been largely adopted. Capacity building efforts are ongoing. Report for Grade 5 NAS expected at end 2011. (3) The outputs will be delivered and these will positively impact retention and quality. We have not yet seen a huge jump in either retention or quality outputs and recognise that strengthening system efficiency (retention) and improving outcomes (learning levels) are a long term process. Other factors affecting quality - especially teacher preparation and classroom pedagogy were not spelled in our assumptions and now require more attention. These will be given more attention in the remainder of the project.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | The project purpose assumes that increasing retention in primary school (so that a child completes a full cycle of education) and improving child learning outcomes will contribute to the project goals (increased future earnings and productivity). There is reasonable evidence that the growth in India's elementary sector by one third in under a decade, including near universal access, has built an essential foundation for future earnings/productivity. However, a labour market analyis would be required to understand the linkages fullly. DFID has commissioned an independent evaluation looking at the Value for Money of its contribution to SSA specifically (conducted by Geeta Kingdon and Paul Atherton in 2010). This found an internal rate of return of around 13% and corroborated a direct link between purpose level indicators and the programme goal, when measuring the relationship between the costs of education during the period of study and the predicted lifetime financial gains from education.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | SSA outputs on access, equity and quality (weighted at 50%) are directly correlated with the project purpose (i.e. making sure all children, regardless of background are enrolled, completing 8 years of education and demonstrating basic learning levels). The milestones for all three outputs (All Children in School, Bridging Social and Gender Gaps, and Education of Satisfactory Quality) are on track, and there is strong evidence that the outputs are necessary for achieving the purpose. However, the project's purpose level indicators are only partially being met. Our assessment is that this gap is explained by wider and long-term systemic challenges that need to be addressed in the remainder of DFID support to SSA, such as (i) better preparation and deployment of teachers; (ii) location-specific action to address the root causes of poor retention and (iii) improving what happens in the classroom.
Purpose Recommendation 1 | MHRD and States to develop a more comprehensive understanding of retention, attendance and dropout. There is a need to harmonise the various sources of data to build a consistent and reliable database on retention and drop out.
Purpose Action Point 1 | Follow up on retention and attendance issues more comprehensively in the July 2011 JRM with a view to strengthening systematic data collection and use in these areas.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 1 | 1.25
Purpose Justification | SSA remains on track for the achievement of the project purpose, and to make a salient contribution towards the goal. Children are accessing elementary education in ever greater numbers. GoI, with States' and donor support, remains focused on closing the gaps between social groups, particularly for girls. Improving the quality of education, and children's overall school experience, is also getting greater attention and funding from GoI (i.e. over 50% of SSA spend + new national teacher education policy in preparation). However, there is still considerable uncertainty whether SSA can deliver demonstrable improvements in children's learning levels by 2013, given the long-term and systemic nature of the education quality challenge. An independent desk-based study on the Value for Money of UK support to SSA found a Rate of Return of approximately 13% and confirmed a) the direct and positive correlation between purpose level indicators and programme goal and b) that DFID investment delivers sound value for money.
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision?
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe needs revision? | Yes
If Yes, why is this? | SSA has outgrown many of the output indicators: those on quality especially are insufficiently targeted and ambitous. Further to the NAO Value for Money study and revised guidance for all education programmes, DFID India would find it useful to have additional indicators that capture efficieny measures in SSA, as well as the performance of DFID technical assistance.
Logframe Recommendation 1 | Incorporate 'smarter' output indicators on quality, and introduce new measures on SSA system efficiency and DFID TA performance if these can be agreed with DPs and MHRD
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision?
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | All Children in School
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision?
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 | Reduction in the number of out-of-school-children (OoSC) aged 6-14 years from 8.1 million to 5.1 million. Disaggregated for gender; SC; ST; Muslims; disabled; rural and urban. (Baseline obtained thro' 2009 Independent Study on Out of School children (SRI-IMBR) | 4
Is this a Standard Indicator? | No | 5
Milestone for this review (if any) | 6.6 million | 0
What progress has been made in the period covered by this review? | Exceeded According to the 2009/10 PMIS Household Survey, 5.2 million children remain out of school, rapidly approaching the end-line target of 5.1 million, although these data are not independently verified. This reduction in OoSC has being achieved by opening of new schools, construction of additional classrooms, upgrading Education Guarantee Scheme (EGS) centres to schools, and through special interventions aimed at urban, SC/ST/Muslim/girls and Children with Special Needs (CWSN). An 2010 evaluation for the Planning Commission conducted in 13 States (including Bihar, UP and MP) reported consistent decreases in OoSC but cautioned that the number of OoSc continue to be high in Bihar and UP. On average, 7.2% of sampled households had dropouts or OoSC and more than half of these children belonged to socially disadvantaged groups. In Haryana, Himachal Pradesh and Madhya Pradesh all the out of school children were from SC/ST households. In Rajasthan, the majority of OoSC/dropouts were girls. Overall, dropouts accounted for 76.6% of all OoSC and 55% of the dropouts/OoSC were girls.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Increased enrolments. Disaggregated for gender; SC; ST; Muslims; disabled; rural and urban
Is this a Standard Indicator? | No
Milestone for this review (if any) | Increases at commensurate level with OoSC target (1.5 million for 2009/10)
What progress has been made in the period covered by this review? | Likely to be Largely Achieved. DISE shows that elementary enrolments increased from 187.7 million in 2008/9 to 187.9 million in 2009/10. At the elementary level, the % of femal enrolment for 2009/10 is 48%; SC enrolment is 20% (Census 2001 population share 16.2%); ST enrolment 11% (Census 2001 population share 8.2%); Muslim enrolment is 13% (Census 2001 population share 13.43). ST and Muslims continue to be under-represented at the upper primary level. Note that different and inconsistent data sources are being reported for OoSC and enrolments. Thus while OoSC are reported to have declined by 2.9 million in 2009/10, enrolments are reported to have increased only by 0.2 million. Our assessment is that DISE is under-reporting enrolments, particularly as it does not capture effectively those in special training courses (bridge schools).
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Student attendance to increase to 85%. Disaggregated for gender; SC; ST; Muslims; disabled; rural and urban
Is this a Standard Indicator? | No
Milestone for this review (if any) | 78% for primary and upper primary
What progress has been made in the period covered by this review? | Likely to be Largely Achieved. Analysis of student attendance rates show improvements over time, as estimated from various school visit surveys. The evaluation report by the Planning Commission (2010) reported that improved access to schools had a positive impact on school attendance, with 62% of schools reporting student attendance of more than 75%. Similarly, ASER 2010 reported that on average 74% of enrolled students were present in class. However, statistics vary from state to state and district to district and we have no comparable data for last year. According to the Planning Commission and ASER, student absenteeism was high in most North Eastern and Eastern States: Assam, Bihar, UP, Chhattisgarh, Jharkhand and West Bengal. The 13th JRM noted improvement in states like Bihar and that the state has now appointed more teachers and has various state level initiatives and incentives to keep children in school. Note that an Independent Sample Study on student attendance was to be made available by July 2010 but remains pending.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 1 | 2 | 0.75
Impact Weighted Score | 18.75 | 0.1875
Justification for the Score | Significant progress has been made with regards to bringing out of school children into school - although there are still a few states with large number of children out of school. Enrolments are also increasing at a healthy pace, particularly at the upper primary level. In addition, student attendance continues to show a gradual improvement with marked improvements in several states including Bihar in this regard.
Output 1 Recommendation 1 | Sustained efforts are needed to increase enrolments at the upper primary level - 2009/10 NER is 58% and GER is 76%, indicating that many children are not enrolling at the upper primary level.
Output 1 Action Point 1 | Monitoring of RTE norms with regards to enrolment of all children between 6 and 14 years of age should continue with reinforced vigour through the JRM process. Specifically, we should look at the availability of upper primary schools within 3 KM of every habitation as required in RTE.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Bridging gender and social gaps
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Girls, as a share of students enrolled at Primary and Upper Primary level.
Is this a Standard Indicator? | No
Milestone for this review (if any) | Target and milestone: As a share of students, girls enrolled at 47.9% and 47.4% respectively (i.e. girls' share of the population for 6-10 years and 11-14 years according to the 2001 census)
What progress has been made in the period covered by this review? | Exceeded The end-line target has already been met, at both both primary and upper primary levels: i.e. % of femal enrolment in primary is 48.5 for 2009/10 - compared to 48.4 in 2008/9. At upper primary level, % of female enrolment is 48.1, compared to 47.6 in 2008/9). However, we continue to see a high gender gap in several districts of Rajasthan (7), and Punjab (5). Similarly, Haryana, J&K, Bihar have one or two districts with a persistent gender gap. Note that the trend to educate boys privately may be skewing this indicator.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Enrolments of Scheduled Castes & Scheduled Tribe children reflect their shares in 6-14 age group population in Primary and Upper Primary Schools
Is this a Standard Indicator? | No
Milestone for this review (if any) | SC and ST children enrolled reflect their share in the 6-14 child population (share of SC population is 17.6% and 17.1% at primary and upper primary; share of ST is 9.3% and 8.6% respectively)
What progress has been made in the period covered by this review? | Achieved. DISE data of 2009/10 finds that SC and ST children are enrolled broadly in numbers that reflect their share in the child population at both primary and upper primary levels -- SC are enrolled at 20% and 19% at primary and upper primary and ST are enrolled at 11.5% and 9.4% respectively. Note however that children from these groups are disproportionately represented among out of school children, although a decline in their share of OoSC can be seen from 2005 to 2009 (eg SC children were 8.1% of all OoSC and in 2009 this fell to 5.9%, similarly for ST the percentage share fell from 9.5% to 5.2%.)
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Number of children with special needs (CWSN) enrolled in school or alternative system including home based education.
Is this a Standard Indicator? | No
Milestone for this review (if any) | 2.5 m CWSN are enrolled in school or alternative system including home based education (no Target set for this indicator)
What progress has been made in the period covered by this review? | Achieved. The number of CWSN enrolled in school increased by 6.59% from 2008/9 to 2009/10. Nearly 2.6 million CWSN are now enrolled in school. Another 138,000 CWSN are covered through home based education. However, we know that 2% of the school age population, some 4 million children, have special need. An accelerated effort C113is therefore required.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 2 | 1 | 1
Impact Weighted Score | 25 | 0.25
Justification for the Score
Output 2 Recommendation 1 | Given that all three indicators for Output 2 (bridging gender and social gaps) have been achieved, SSA needs to take a far more nuanced approach - (1) focus on specific states (or even districts) where gaps for girls, disadvantaged groups persist; (2) given anecdotal evidence about higher drop out / lower retention among girls and disadvantaged groups, start reporting on these. The equity issues associated with selective migration to low fee private schools also need to explored and taken into account.
Output 2 Action Point 1 | DPs to suggest to MHRD a more nuanced and dynamic approach to understanding persistent gender and social gaps and to move beyond a focus on measuring access/enrolment of girls and disadvantaged groups
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Education of satisfactory quality
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 50%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
1
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Teacher Availability
Is this a Standard Indicator? | No
Milestone for this review (if any) | Maintain Pupil Teacher Ratio below 40:1 for all states
What progress has been made in the period covered by this review? | Achieved. Average PTR at the primary level is 33:1 and upper primary level is 31:1 for all states; Only 3 States - Bihar, UP and West Bengal continued to reflect high PTRs. There are only 10 Districts with PTR greater than 60.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Increased teacher attendance to 90% at both primary and upper primary
Is this a Standard Indicator? | No
Milestone for this review (if any) | 85% teacher attendance at primary and upper primary
What progress has been made in the period covered by this review? | Achieved. A review of ASER 2010 data on teacher attendance finds that on average 86.3% of teachers were present for grades 1-8 in 2010 and that only 0.1% of schools had no teacher present. Also on the positive side, 52% of schools for grades 1-8 had all teachers present. While most states reported teacher attendance over 80%, two states showed low teacher attendance: Assam at 68% and Manipur with 75% -- All others reported attendance at or above 80%. The Ministry has also shown commitment to launch new teacher attendance studies during FY2010-11, and the initiatives of several States (e.g. Delhi, Karnataka, Gujarat) to improve teacher regularity is commendable. Additionally, the development by the All India Primary Teachers Federation of its own Code of Professional Ethics for Teachers (and its endorsement by its membership) is a very positive step.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Availability of teaching and learning materials (TLM)
Is this a Standard Indicator? | No
Milestone for this review (if any) | 96% or more eligible students receive free textbooks
What progress has been made in the period covered by this review? | Achieved. 99% of all eligible students received free textbooks in time according to the Quarterly Progress Report, 2010. The Planning Commission evaluation study from 2010 finds, however, that only 84.4% of surveyed students reporting receiving books on time. This was particularly problematic in Bihar (25%) Himachal Pradesh (54%) and Haryana (63%). Additionally, to note that 95% of teachers reported receiving the Teaching Learning Material Grant and 75-100% of schools in 27 states reported using material in addition to textbooks for teaching and learning.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 3 | 1 | 1
Impact Weighted Score | 50 | 0.5
Justification for the Score
Output 3 Recommendation 1 | Output 3 focuses on providing education of satisfactory quality. According to our logframe indicators, this output has been achieved. However, there is agreement across all SSA partners, independent commentators and parents that a great deal remains to be done on improving quality. This Logframe includes 3 process-based indicators that are important initial steps towards improving quality but that need to be made more ambitious and 'smart' in a revised logframe.
Output 3 Action Point 1 | SSA team to revisit Logframe and review by April 2011.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 4 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy)
Impact Weighting (must = 100) | 100%
Total Impact Score | 93.75 | 0.9375
Output Risk | Medium | 2
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study
Government assessment | X
Joint donor review | X
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner | X
National non-Government partner | X
Independent consultant
Donor partners | X
DFID staff | X
Donor partners | The World Bank
European Union
Govt of India
Comment here on the Method of Scoring and Scoring Responsibility. | The Joint Review Team of 12 GoI and 12 DP representatives went to 10 States for field visits in January 2011. The review considered the information presented by the GoI, State Governments, data collected from the field and information gained from meetings at the Central, State, District and sub-district levels. Prior to that, the July 2010 Joint Review team conducted a desk based review of the SSA programme which included extensive presentations by GoI, state governments and partners
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | In previous years we have reported the efficiency gains possible within a mature sector- wide approach (SWAP) such as SSA. Whilst these remain valid, SSA's maturity and its contribution to capacity at national and state level, now make it more challenging for DFID (and all DPs) to 'add value' through the SWAP mechanism. More and more, DFID needs to rely on persuading partners thro' expertise and access to comparative international experience.
Working with Partners Recommendation 1 | SSA is scoring very well against all existing performance criteria. While national trends in access, equity and quality are positive, averages conceal significant state and intra-state disparities. In order to ensure continued focus and dynamism, a set of more stretching targets would be helpful. DFID to broker discussions on finessing targets to better focus SSA interventions, particularly on learning outcome.
Working with Partners Action Point 1 | Broker discussion on the continued appropriateness of existing targets and performance criteria - seek change where feasible.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2 | GoI has requested all donor partners graduate from SSA support by 2012/13 . Discussions are required about continuing need for support, divisions of labour and appropriate approaches post SSA graduation.
Working with Partners Recommendation 3 | DPs are less likely to visit States outside of the Joint Review Mission process. Over time for the DP group as a whole is having less "unscripted" contact with States, potentially missing opportunities for informal intelligence-gathering and lesson-learning. Revised ways of working and being connected to States may need to be considered, especially with the start up of RMSA
Working with Partners Action Point 2 | DFID to convene discussions to map out DP future plans and ensure coordination there of.
Working with Partners Action Point 3 | A greater effort needs to be made to visit weaker states and particularly weaker districts outside the JRM process.
2. Best Practice / Innovation | Responsiveness of SSA. The 13th JRM paid particular attention to learning outcome measurement and the use of data at all levels of the education chain inform remedial action. The use of Item Response Theory enables detailed diagnosis of levels of performance around specific learning areas (rather than just average overall scores) and gives much greater diagnostic power and therefore better information for remediation. To our knowledge, India is the only DFID programme where state of the art techniques of learning assessment are being supported.
Best Practice / Innovation Recommendation 1 | There is a need to support states to build capacity to 'mine' data and to use it to inform action in areas such as teacher training and materials provision with the view to address areas of low learning.
Best Practice / Innovation Action Point 1 | MHRD to strengthen efforts to better use learning assessment data by all stakeholders.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | DFID is playing a critical catalytic role in raising the capacity of learning outcome assessment and its use to drive quality improvement. This includes international workshops on teacher education, learning assessment systems and impact evaluation - and increasingly providing India with access to international education expertise (eg Institute of Education, OECD.) The DFID TC fund (which operates outside government systems) has proved a nimble and effective channel to bolster capacity and focus attention on key issues. But DFID needs better ways of attributing the value of its support, including its VFM.
SSA was part of a multi-country Value for Money Assessment on Education published by NAO in 2010. Whilst the performance of SSA was seen as broadly positive, the NAO was concerned about the relatively high unit cost of SSA (permanent) teachers, as well as having independent teacher attendenance reporting. Since the NAO's report, the Education Team has done considerable work to assess the quality, unit costs and poverty reach of Government and low fee private schools to inform future strategy. During the life of SSA increasingly reliable and timely government and independent data sources have been built to monitor peformance. Ensuring these are in place for the next phase of DFID support - to secondary education - will be essential.
Project Management Recommendation 1 | The remaining period of DFID support to the TC Fund should focus on: (i) maximising capacity building to all states through focus on a common issue e.g. teacher education or continuous and comprehensive evaluation (ii) focus on a long term sustainability strategy which prepares the unit within NCERT for continuation following the graduation of DFID support.
Project Management Action Point 1 | Above priorities to be stressed by DFID during TC Fund executive committee meetings
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | Convergence with RTE. SSA is the primary vehicle for the delivery of Right to Education. The Ministry would like RTE to be treated as a sovereign issue. However, DPs can play an important role in engaging with RTE where it impacts on SSA norms and implementation -eg, the 25% reservation of seats in private schools for children from economically weaker and disadvantaged sections. This could potentially have beneficial and or perverse impacts upon the entire education systems management. The donor partners can have a role in brokering informed discussion in formulating the implementation of the existing guidelines.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
NAO Value for Money in Education Study
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project.
Sustainability Recommendation 1
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | The findings confirm large gaps in literacy and enrolment between boys and girls, and the disadvantages faced by SC and ST children - most strikingly, ST girls. These gaps warrant remedial intervention for help ST and SC girls to complete upper primary and access secondary education. Essentially, this means that strong linkages between SSA and RMSA need to be developed.
R2 | DPs to pursue MHRD's agreement to develop SEMIS (Secondary Education MIS) nationally to the same standards as DISE, including social group dissaggregation. This should be a pursued actively during RMSA appraisal.
R3 | 0
A1: Purpose
R1 | MHRD and States to develop a more comprehensive understanding of retention, attendance and dropout. There is a need to harmonise the various sources of data to build a consistent and reliable database on retention and drop out.
R2 | 0
R3 | 0
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | Incorporate 'smarter' output indicators on quality, and introduce new measures on SSA system efficiency and DFID TA performance if these can be agreed with DPs and MHRD
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Sustained efforts are needed to increase enrolments at the upper primary level - 2009/10 NER is 58% and GER is 76%, indicating that many children are not enrolling at the upper primary level.
R1.2 | 0
R1.3 | 0
R2.1 | Given that all three indicators for Output 2 (bridging gender and social gaps) have been achieved, SSA needs to take a far more nuanced approach - (1) focus on specific states (or even districts) where gaps for girls, disadvantaged groups persist; (2) given anecdotal evidence about higher drop out / lower retention among girls and disadvantaged groups, start reporting on these. The equity issues associated with selective migration to low fee private schools also need to explored and taken into account.
R2.2 | 0
R2.3 | 0
R3.1 | Output 3 focuses on providing education of satisfactory quality. According to our logframe indicators, this output has been achieved. However, there is agreement across all SSA partners, independent commentators and parents that a great deal remains to be done on improving quality. This Logframe includes 3 process-based indicators that are important initial steps towards improving quality but that need to be made more ambitious and 'smart' in a revised logframe.
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | SSA is scoring very well against all existing performance criteria. While national trends in access, equity and quality are positive, averages conceal significant state and intra-state disparities. In order to ensure continued focus and dynamism, a set of more stretching targets would be helpful. DFID to broker discussions on finessing targets to better focus SSA interventions, particularly on learning outcome.
R2 | GoI has requested all donor partners graduate from SSA support by 2012/13 . Discussions are required about continuing need for support, divisions of labour and appropriate approaches post SSA graduation.
R3 | DPs are less likely to visit States outside of the Joint Review Mission process. Over time for the DP group as a whole is having less "unscripted" contact with States, potentially missing opportunities for informal intelligence-gathering and lesson-learning. Revised ways of working and being connected to States may need to be considered, especially with the start up of RMSA
Best Practice / Innovation
R1 | There is a need to support states to build capacity to 'mine' data and to use it to inform action in areas such as teacher training and materials provision with the view to address areas of low learning.
R2 | 0
R3 | 0
Project Management
R1 | The remaining period of DFID support to the TC Fund should focus on: (i) maximising capacity building to all states through focus on a common issue e.g. teacher education or continuous and comprehensive evaluation (ii) focus on a long term sustainability strategy which prepares the unit within NCERT for continuation following the graduation of DFID support.
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | Targeted strategies to ensure that girls, particularly from disadvantaged groups, are able to access upper primary school as per the RTE norms of 3 km and are able to complete a full cycle of elementary education
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | Follow up on retention and attendance issues more comprehensively in the July 2011 JRM with a view to strengthening systematic data collection and use in these areas.
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Monitoring of RTE norms with regards to enrolment of all children between 6 and 14 years of age should continue with reinforced vigour through the JRM process. Specifically, we should look at the availability of upper primary schools within 3 KM of every habitation as required in RTE.
AP1.2 | 0
AP1.3 | 0
AP2.1 | DPs to suggest to MHRD a more nuanced and dynamic approach to understanding persistent gender and social gaps and to move beyond a focus on measuring access/enrolment of girls and disadvantaged groups
AP2.2
AP2.3 | 0
AP3.1 | SSA team to revisit Logframe and review by April 2011.
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Broker discussion on the continued appropriateness of existing targets and performance criteria - seek change where feasible.
AP1.2 | DFID to convene discussions to map out DP future plans and ensure coordination there of.
AP1.3 | A greater effort needs to be made to visit weaker states and particularly weaker districts outside the JRM process.
Best Practice / Innovation
AP1.1 | MHRD to strengthen efforts to better use learning assessment data by all stakeholders.
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | Above priorities to be stressed by DFID during TC Fund executive committee meetings
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3