Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Supporting the 2015 – 2016 Electoral Process in the Democratic Republic of Congo
Programme Value: £11,400,000		Review Date: 01 March 2016
Programme Code: 204889	Start Date: 17/04/2015	End Date: 25/03/2017

Summary of Programme Performance
Year	2016
Programme Score	A
Risk Rating	Major

Summary of progress and lessons learnt

This programme was designed to support and strengthen the credibility of DRC’s suite of elections (local, provincial and national; legislative and presidential), scheduled for 2015-16. The context for the programme has continued to deteriorate, with the electoral calendar slipping well behind initially proposed deadlines, for a range of reasons beyond UK/DFID control.

Performance of the different programme components has been varied. The civic education component has worked well with CENI on the selection of civic education materials, but has experienced delays in recruiting and working with the CSOs who will ultimately be responsible for educating several million Congolese in terms of civic and democratic behaviours. The elections observation and monitoring programme has engaged well with the CEJP, which is the principal partner for training and deploying observers and collecting data. It has exceeded expectations for the reporting year, and is well positioned to provide oversight for elections if and when they take place. The component for strengthening the Congolese electoral commission has been particularly affected by the political context. Nevertheless, DFID has been able to use its pledge finance elections (subject to certain political conditions being met) as a mechanism to signal the electoral commission, the Congolese government and other partners about the UK position with regards the electoral process. Lastly, at the end of the reporting year, the flexible fund component is now well positioned to provide support to two interventions which will address the political and social context surrounding elections: these interventions will focus on (a) youth & media, and (b) human rights.

Programme outcome, outputs and main activities

In this uncertain polical context, the programme continues to adapt in order to achieve its outcome. To date, it represents good value for money.

The programme outcome is:

Congolese citizens (men & women) benefit from an enhanced democratic environment, are aware of their electoral rights and responsibilities, call for greater accountability/ transparency in the electoral process and are seen by elections observers as exercising their right to vote.

The programme has four outputs that reflect its different components:

Congolese citizens (men & women) able to make informed voting decisions and participate actively and peacefully in the electoral process;

Increased capacity of local electoral observation CSO partners to monitor electoral developments, and analyse electoral processes based on international obligations and standards, and effectively advocate for electoral reform;

Electoral commission (CENI) coordinates equitable civic education activities and updates voters roll in a transparent and accountable manner;

Political and social environment is more conducive to the holding of credible elections.
These outputs correspond to four main groups of activity: (a) civic education; (b) electoral observation; (c) capacity strengthening for the Congolese electoral commission and (d) flexible programming.

Civic Education

The Congo Demokrasia (civic/voter education project with USAID) was launched in July 2015. In the course of the year Counterpart International, the implementing agent, started its registration process with DRC officials. It established provincial offices, and conducted a rapid assessment of CSOs to select local partners (tier 1 and tier 2 CSOs) through which civic/voter education would be provided. This selection process was lengthy, and delayed deployment of local CSOs. To cover this gap, the programme reverted to an interim CSO selection process in order to accelerate voter education messaging. As such, they organised a series of popular forums through which focused electoral education was provided to 3254 people. This programme component also organised workshops with CENI and enabled the selection of 222 civic/voter education materials (caps, t-shirts, waistcoats) for official use. With regards programme management, the agreements concluded between key stakeholders (an MoU between DFID and USAID; and a contract between Counterpart International and USAID) meant that DFID could not provide direct instructions/guidance to implementing agent without passing via USAID. This structure introudced delays in the implementing partner’s response time to programme issues raised by DFID. Monthly meetings and the adoption of an alternative management structure helped resolve this situation. The final version of the programme logframe was approved on 24th February 2016 after USAID/Counterpart International agreed on the final results framework indicators.

Electoral Observation

The Carter Centre worked to strengthen CEJP (Commission Episcopale Justice et Paix),which is the primary partner for deploying observers and collecting data. Training materials were jointly developed with CEJP’s core team. A total of 120 manuals for LTOs (long-term observers) were printed for distribution. The training materials enabled the training of 15 ‘super trainers’ who then provided cascade training for a further 120 LTOs, of whom 51 were deployed to observe the pre-election activities for provincial assembly elections, initially scheduled for October 2015, but subsequently cancelled. Despite the cancellation, LTOs were still able to observe CENI’s sift of candidates, planning for electoral logistics, and deployment of CENI agents. In turn, LTOs were able to produce an observation report. Both DFID and USAID provide support CEJP’s 102 LTOs. DFID’s grant with the Carter Centre enabled CEJP to benefit from technical assistance (training materials, training of LTOs), whilst USAID’s direct direct grant to CEJP covered logistics (deployment of LTOs, venues for workshops, payments of CEJP staff). Both donors have remained complementary in their support to CEJP. The programme also contributed to the establishment of the CENCO[1]/CEJP’s call centre. The software for the call centre (ELMO[2] and training materials) were developed by the Carter Centre. USAID financed logistics and equipment (computers, staff payment, SMS costs for the 102 LTOs). Bridge training (‘training of trainers’) on gender was also provided by the programme in this reporting period. An assessment was conducted to identify the benefits and risks of conducting Parallel Vote Tabulation (PVT) in DRC (PVTs reduce the risks of electoral manipulation).
[1] National Episcopal Commission of Congo
[2] ELMO (data collection system)

PACEC/CENI (UNDP basket fund for donors’ support to the elections)

No direct programme activities with the Congolese electoral commission (CENI) have been financed via this component to date. The political context has not been sufficiently favourable for the UK to effectively contribute to the PACEC and thus support CENI.
Flexible funds (support to additional elections-related initiatives)

Two projects have been identified in the course of this reporting period and will be funded through the flexi component. (i) An Accountable Grant will soon be signed between DFID and Avocats Sans Frontières to support human rights defenders during this electoral year. Activities are due to start early April 2016. (ii) We are preparing to finance Fondation Hirondelle for delivery of a project that engages with youth and the media during elections. Activities are also likely to start in April 2016.

Summary of recommendations for the next year

Civic education

- The programme should continue to collaborate with CENI in the development of civic/voter education materials.
- Counterpart International should ensure that their proposed selection process for primary local partners is completed at the beginning of next reporting year.

Electoral Observation

- The Carter Center/UKAID/USAID should closely monitor CEJP’s ability to absorb support from different donors.
- The Carter Center/ UKAID should further enhance management processes for the observation component.

PACEC/CENI

DFID and other international partners must encourage PACEC to work with CENI in order to identify solutions in order to reduce the proposed timelines for the holding of credible elections.

Progamme to reinforce collaboration with CENI through its civic education component (Counterpart International) thus contribute in dissemination of civic education/voter materials

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204889/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204889/documents

Primacy of politics on programme implementation

Approved on 17th April 2015 with an original budget of £4.8m, the current election programme was conceived to support DRC’s 2015-2017 electoral process, and to build longer-term electoral accountability systems. In December 2016 we asked minister to approve an additional £6.6m (Quest n°5265464) in order to support the revision of the electoral roll as it represented an opportunity to remove a key blockage to the holding of timely and credible national elections. The programme currently has a budget of £11.4m and consists of four main components:
- £2m civic education component (an MoU signed with USAID)
- £1.5m election monitoring/observation component (accountable grant signed with The Carter Centre)
- £6.6m capacity strengthening component, focussed on the Congolese independent electoral commission (CENI) and possible support for the revision of the electoral roll (MoU with UNDP in the event that we wish to proceed with this component)
- £1.3m flexible fund to allow the UK to support additional elections-related initiatives (accountable grants likely to be signed with different partners).
Throughout this first year of reporting, the programme was implemented in a period of high uncertainty. Uncertainty related specifically to the type and number of elections that the government would sanction. A series of positions have been taken by the government allegedly designed to keep President Kabila in power beyond the end of his current mandate.
These moves have ranged from attempts to amend the constitution in September 2014; efforts to change the electoral law in January 2015; the rushed implementation of a politically sensitive decentralisation process in mid-2015; and deliberate withholding of funds from the electoral commission (CENI). In November 2015, President Kabila convoked a political dialogue, to discuss timing, sequencing and resources for elections. At the writing of this report the dialogue has still not been organised.
Both the population (civil society, youth, the Church) and substantial parts of the political opposition are strongly opposed to these moves. This creates real tension in the DRC: political space has been substantially closed, with a crackdown on human rights NGOs, opposition parties and the media which could flare up into serious civil unrest.
International Community portrayed as failing to support the electoral process
Recently the GoDRC released US$40m to support the electoral process. This covers the months of January and February 2016, and is equivalent to just 3.6% of the US$ 1.1bn required to hold elections). Although not clear which electoral activities these funds will finance, the gesture has further positioned GoDRC’s to claim that the international community are vocal critics of delays in the electoral process, but are not contributing to finance it. To mitigate for the risk of unwittingly becoming complicit in the delaying tactics, the international community has pledged funds to finance elections (but has not disbursed them, GoDRC having not met key milestones that would enable disbursement to occur). Canada has pledged with CAD $3.5m, and the UK has reiterate its readiness to provide support up to a limit of £11.4 million.

Revision of electoral roll prioritised by CENI as pre-condition for organising of elections

In the course of this reporting period Abbot Malu Malu (the former chairperson of CENI) resigned for health reasons. The new CENI chairperson and his board have so far not published a revised electoral calendar as demanded by the international community, the opposition and civil society. They have published a calendar for the indirect election of governors in new provinces. They have also proposed a plan for a full revision of the electoral roll prior to organising elections, a process which they estimate will take 16 months and cost US$202m. This means that .Presidential elections cannot be organised within the timing enshrined in the constitution.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The overall outcome for this programme is assessed as B.

Overall output score and description

The overall output score is A. In spite of the difficult context, the programme has managed to deliver against a number of milestones. Implementing partners have adapted their interventions to local realities on the ground and have built strong relationship with supported CSOs, with a view to supporting longer-term democratic behaviours in DRC. With regards electoral observation, the programme has strengthened the CEJP, and has developed observation materials for LTOs who were able to undertake pre-election observation activities and contribute to the production a high quality observation report of CENCO[3]/CEJP. Through the rapid civic/voters education forums the programme provided civic/voters’ education to 3254 people. The programme has also worked in close collaboration with CENI in the selection and production of civic education materials. An initial 222 civic/voters education materials were produced by the programme for use across the country. Together, and based on the programme logframe, these activities justify a score of A.
[3] CENCO: National Episcopal Commission of Congo

Key lessons

Both DFID and USAID are supporting the CEJP on civic education and electoral observation, but they do so via with different management agreements (USAID makes a direct grant to CEJP, whilst DFID uses The Carter Center as an intermediary). Programme coordination will be reinforced as familiarity with reporting lines and accountability is built.

International experts embedded within CENI have not been proactive in terms of suggesting alternative options for resolving technical issues likely to delay elections (i.e. revision of the electoral roll) independently from those developed within CENI. This has weakened donors’ ability to technically challenge CENI.

Donors’ communication has been mainly addressed towards DRC institutions and less to the population. As such, donors have not played a significant role in informing the population of current electoral dynamics.

Key actions

Ensure the USAID/UKAID management agreement is shared with implementing partners (Counterpart International and The Carter Centre) and that communications with CEJP are such that the overall programme vision is clear.

Donors contributing to PACEC are to collaborate and work to encourage international experts to be active suggest alternative options to resolve issues likely to delay elections, independently from CENI’s proposals as appropriate.

Donors are to to reflect on ways to start communicating more directly towards the population on the reasons for blockages to the electoral process.

Has the logframe been updated since the last review?
This review is the first since the start of the programme. The logframe was updated in February 2016, and approved by Head of Office (Quest: 4976072).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Congolese citizens (men & women) able to make informed voting decisions and participate actively and peacefully in the electoral process
Output number per LF		1	Output Score	B
Risk:		Major	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2015 – 2016 (programme year 1)	Progress
# of supported civic education CSOs engaged in election-focused advocacy interventions promoting political participation and voter education for men & women	49 CSOs	This indicator did not meet expectation. / 21 CSOs were able to promote voter and political participation through organised popular fora that were facilitated by the programe’s rapid civic education messaging mechanism. Counterpart International’s selection process of the principal local CSOs (tiers 1 and 2) had been delayed and was not finalised at the time of writing.
# of trained beneficiary CSO leaders with understanding of elections and the electoral process	20 beneficiary CSO	0. This indicator did not meet expectation / The selection process for the principal local CSOs was lengthy. At the writing of this report, the process was being finalised. No CSO leaders have been trained to date.
# of advocacy activities implemented by civic education /voter education CSOs that are supported by this programme	6 CSOs	0. This indicator did not meet expectation. / The selection process for the principal local CSOs (tiers 1 and 2) was delayed. At the writing of this review, no local CSO had been deployed to undertake advocacy activities.
% of persons reached through this programme's voter education activities who are women	35%	37%. This indicator exceeded expectation / A total of 1193 (37%) women were reached through a civic/voter education messaging forums. Overall, 3254 men and women were reached during this reporting period

Key Points

The process for selecting CSOs due to undertake civic/voters’ education activities was lengthy and delayed. This prevented the programme from beginning civic education activities as originally conceived.

Even so, organising popular forums to provide ‘rapid voter education’ messaging enabled the programme to compensate for the delays to the original selection process.

By engaging closely with CENI on the selection of civic education materials, tensions relating to CENI’s initial insistence that the programme focus on the revision of electoral roll were reduced.

Counterpart International needs to finalise its registration process with DRC authorities to be able to continue operating smoothly on the ground.

Recommendations

Programme to continue close collaboration with CENI in developing civic/voter education materials

Counterpart International to ensure selection process of primary partners completed at beginning of next reporting year

Counterpart International to complete the registration process with DRC officials to be able to operate smoothly on the ground

Output Title	Increased capacity of local electoral observation CSO partners to monitor electoral developments, and analyse electoral processes based on international obligations and standards, and effectively advocate for electoral reform
Output number per LF		2	Output Score	A+
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone 2015 – 2016 (programme year 1)	Progress

Technical capacity of CEJP (Commission Episcopale Justice et Paix) to collect information and monitor electoral developments, assessed according to 'The Carter Centre Technical and Organizational Capacity Assessment' (TOCA)	( scale from 1 - 5)	This indicator exceeded expectations with a score of 3.41 achieved as assessed by the TOCA. / Observation material developed by The Carter Centre in consultation with CEJP. Overall 120 manuals for LTOs (Long Term Observers) were printed and distributed. / 15 participants were trained as super trainers (12 from CEJP and 2 from other religious confessions) to provide training to LTOs. / The 12 CEJP super trainers provided training to a total of 102 LTOs who were then deployed in 51 electoral regions (in the 26 provinces) to assess and report back on the pre-electoral period of the provincial elections (initially due to end on 25th of October 2015, according to CENI’s electoral calendar). / 5454 weekly reports from the deployed CEJP LTOs were compiled and organised according to the current 26 provinces, then analysed and utilised for the drafting of the CEJP’s pre-election observation report.
Technical capacity of CEJP to analyse data relating to electoral cycle assessed according to 'The Carter Center Technical and Organizational Capacity Assessment' (TOCA)	1.5 (scale from 1 - 5 assessed according to TOCA)	This indicator exceeded expectations with a score of 3.6 assessed against the TOCA. / In advance of the start date for LTO reporting, CEJP established a data centre that was staffed with 9 individuals (initially staffed with 3 individuals but number increased on recommendation from The Carter Centre) who received training on data cleaning, verification and generation of reports on ELMO (The Carter CENCO/CEJP’s electoral monitoring software). / Increase of data analysts for use of ELMO enabled acceleration of cleaning and verification of 5454 LTO reports submitted from the fields

# of statements and reports released by CEJP (Commission Episcopale Justice et Paix) that assess the credibility of the electoral process against election obligations and standards	Three statements & reports released	This indicator did not meet expectation. Only 2 reports released to the public. / In Feb 2015 CEJP organised a forum on the analysis of the electoral law. CEJP used these recommendations to develop advocacy strategy, which were presented to members of parliament. The findings in CEJP's report were also used for drafting CEJP's 2015 pre-electoral observation report. / CEJP/CENCO publicly released its first pre-election observation report completed between August and December 2015. This report was presented to CENI and key stakeholders on 15th December 2015. Findings and recommendations were discussed between CEJP and CENI officials showed eagerness to continue receiving this type of reports. Plans are in place to ensure proper dissemination.
# of statements, reports and recommendations released by CEJP that reference and improve women's participation in the electoral process against international standards	a) 3 statements/reports in line with election obligation and international standards & b) 2 recommendations that reinforce women participation	This indicator met expectation with 4 recommendations to improve women’s participation and one report/statement publicly released / The pre-election observation report compiled by CEJP’s observers and made public by CENCO included 4 recommendations targeted at women’s participation. / Additionally ‘bridge’ training (‘training of trainers’) focused on women’s participation was organised in the first quarter of 2016 to increase CEJP’s attention to women and strengthen related recommendations in their future reporting.

Key Points

Although activities were implemented in very particular context with continued uncertainty on the electoral calendar, the programme managed to adapt its interventions to achieve its objectives.

CEJP outlined the need to see UKAID’s support revisited to enable increase in number of LTOs (CEJP aim to have at least 500 LTOs deployed for coming elections).

CEJP is the primary partner in terms of electoral observation for both UKAID/USAID as well as other donors, and is at some risk of over-stretch.

Compared to the USAID observation programme (Bokengi wa Maponomi), the visibility of UKAID/The Carter Centre’s was limited in course of this reporting period.

Recommendations

Clarification between all partners about the relative contributions of USAID and DFID to the activities of the CEJP is required in order to improve contribution/attribution of results.

The Carter Centre should reflect on an approach that will enable a realistic increase of CEJP LTOs.

The Carter Centre/UKAID/USAID are to closely monitor CEJP’s ability to absorb support from different donors.

The Carter Centre/ UKAID are to develop better communication approach for the visibility of the observation programme.

Output Title	CENI coordinates equitable civic education activities and updates voters roll in a transparent and accountable manner.
Output number per LF		3	Output Score	B
Risk:		Severe	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Counterpart International prepares civic education materials / tools for validation by CENI	1 x tool OR 1x civic education publication	Indicator met expectation / Inventory of existing civic education materials/tools was undertaken from October – July 2015. Overall 3 samples of materials were identified (t shirts, caps, waistcoats) and were validated by CENI for re-use.
Civic education materials validated by CENI	YES /NO	Indicator met expectation / Revised messaging on civic education tools/materials was validated at workshop organised by CENI from 1st to 2nd March 2016.
# of copies of civic education materials / tools validated by CENI produced by this programme	0	Indicator exceeded expectation / 222 civic education tools/materials were produced in course of this reporting. period.
Dissemination of civic education materials is facilitated by CENI	NO	Indicator met expectation. We did not expect CENI to begin dissemination of civic education materials to begin in this reporting period. This has proved to be correct.
Updated electoral roll sufficiently legitimate to enable elections	Stakeholders reach consensus on what a legitimate electoral roll would look like	Indicator did not meet expectation / So far consensus has not been reached on the extent of revision to the electoral roll that is required. CENI, opposition politicians, and donors all have different perspectives.

Key Points

Political uncertainty on the organisation of election means that the UK has been able to pledge, but not disburse funding to the PACEC/UNDP basket fund.

Indicators assessed in this output are in part about synergies with output 1 on civic education. The overachievements of some indicators have contributed to CENI playing its coordination role with regards to civic education tools/materials, even though we have not worked through the PACEC mechanism to date.

The electoral roll is central for the holding of elections. Revision of the electoral roll continues to be controversial. At present, CENI are opting for the most expensive and time intensive alternative to revise the electoral roll. Lack of progress in this area strongly impacts on the overall ouput. Therefore the weight and importance of this indicator moves the overall output score to B.

Recommendations

The progamme should continue to reinforce collaboration with CENI through its civic education component (Counterpart International). In time, this will enable dissemination of civic education/voter materials.

With regards to CENI’s position, the UK will need to decide the degree to which it wishes to associate itself with a revision of the electoral roll.

Output Title	Political + social environment is more conducive to the holding of credible elections
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
% of CSOs supported through this component that contribute effectively and robustly to the reporting of the human rights situation and make recommendations accordingly during the electoral period	Accountable Grant signed[4]	Indicator meet expectation / Accountable grant with ASF (Avocat Sans Frontière) signed and Sub-component implementation is due to start in April 2016
# of human rights defenders (HRD) and other civil society actors threatened who benefit from a) direct protection measures and legal protection measures including b) legal advice and c) judicial assistance	Accountable Grant signed	Indicator met expectation / Accountable grant with ASF (Avocat Sans Frontière) signed and Sub-component implementation due to start in April 2016.
# of young beneficiaries with access to civic education materials	TBD for both 2015/16 and 2017
[4] Milestone column for 2015 - 2016 in the Logframe that was reviewed in Feb 2016 should have been for process indicator

Key Points
Use of the flexible fund has progressed satisfactorily. We have sensitised the market to DFID’s preparedness to support a range of activities that will make the political and social environment more conducive to the holding of credible elections. We have now identified human rights and media projects to be funded through this component. These have recently been selected and interventions are due to start in course of next reporting period.

Recommendations

DFID to accelerate processes that will enable start of activities in this component.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for this programme relate to staff costs of implementing partners and, in the case of Counterpart International, the establishment of sub-national offices in order to conduct civic education operations.

USAID/Counterpart International: personnel costs represent 19% of the budget. Programme activities represented 21% of the budget. The programme required highly skilled personnel to ensure that quality of technical support is of high standard. Counterpart International conducted three rounds of recruitment to hire the election specialists and the civic education specialist.

The Carter Centre: fixed personnel costs represented 13% of the budget. Additional costs for technical experts represent 14% of the budget. The Carter Centre also experienced challenges in recruiting highly skilled staff to implement the programme. Project partners have ensured that the technical experts recruited are at the market rate and not above average DFID’s international rates. For instance, three technical experts were hired during this first year under the Observation component by The Carter Centre. The total cost was £78,864 going from June until December 2015 (an average of £3,755 per person on monthly basis). This includes the Kinshasa-based programme manager, the M&E manager, and work that was undertaken to set up the ELMO system for use in the DRC context and the PVT assessment

The programme is in its first year of implementation. Up to 23/03/2016; funds disbursed amount to £1,350,000 out of a total budget of £11,600,000. To maximise Value For Money on key cost drivers, the team will continue to ensure that the personnel costs are maintained at agreed level and that running and operating costs are monitored closely.Due to security constraints, we may expect an increase of office operational costs in the course during the second year of implementation. This will be monitored closely with implementing partners.

VfM performance compared to the original VfM proposition in the business case

Some activities have been delayed due to uncertainty in the organisation of elections. Because the programme is in its first year of implementation, it is not yet possible to assess results versus costs at this stage.

With regards to the three Es (Economy, Efficiency and Effectiveness) we note the following:

Economy: DFID ensured that technical assistance on this programme is procured at the best price for the quality needed. Management costs are maintained at less than 7% for all the programme components. The programme implementing partners ensured that the recruitment processes for technical experts and regular staff were rigorous and competitive. For instance, costs of the election specialist that was hired in our 2010 elections programme was at the daily fee rate of £827, as compared to £350 for the current Carter Center election specialist.

Efficiency: The Business Case estimated that the cost for reaching one person through civic education activities was of £0.15 (based on UK contribution to IFES in 2011). At this stage, there is insufficient data to enable au to compare the cost per beneficiary. This data will be gathered in conjunction with USAID. Relevant technical assistance is provided to the CEJP sub-grantees and it is ensured that the The Carter Centre provides the right level of training to local observers.

Effectiveness: We expect that results of each programme component will be used for other activities and the built capacity of CSOs will be sustained and used for future elections.

Assessment of whether the programme continues to represent value for money

With regards to the achievements made so far, and based on the data available, this programme remains good VFM. We recognize that the programme overall experienced delays in delivery of activities on the ground. In part due to the political context and to administrative constraints (office set-up and organisation registration).

Quality of financial management

DFID receives quarterly financial reports with narrative financial reports from The Carter Centre and USAID that contain breakdown of expenditure from Counterpart International. The financial reporting requirements have been adhered to by the implementing partners and monitored by DFID. The Carter Centre financial team sends and update on forecasts at least on a quarterly basis. Each month DFID interacts with partners to ensure accuracy of the forecasts and thus avoid to have a big difference between forecasts and expenses.
The variance between forecasts and expenses does not exceed 5%.
Reports are analysed by DFID team and questions sent to partners and discussed during monthly meetings.

Date of last narrative financial report	25/02/2016
Date of last audited annual statement	n/a

E: RISK (½ page)

Overall risk rating: Major
Programme risk was rated as High in the Business Case.
The new risk management framework has changed the risk rating descriptions to Minor, Moderate, Major and Severe. In this instance the overall programme risk is rated as Major. Most risks identified in the programme risk matrix remain relevant (see annex 1). The risk matrix will be closely monitored and updated as appropriate in the course of next reporting year.

Overview of programme risk

- There is a risk of political manipulation of civic education activities by DRC officials (CENI) to send messages that makes revision of electoral roll pre-condition for organising elections;
- There is a risk of prevention of International NGOs from operating in DRC if they do not follow standard registration processes;
- There is a risk of the international community becoming complicit in electoral delays if they support the revision of an electoral roll that goes beyond constitutional delays;
- There is a risk of elections not happening in 2016;
- There is a risk of an outbreak of violence if there is no sign of elections being planned ahead of the end of President Kabila’s mandate in December 2016.

Outstanding actions from risk assessment

- The programme will continue working with CENI to ensure they validate all civic education messaging (not only the ones related to revision of electoral roll);
- The programme will follow up with implementing partner (Counterpartart International) to accelerate the process of obtaining full registration;
- DFID will continue working hard with other partners to help develop alternative options for the revision of the electoral roll in a more realistic timeframe;
- The programme will continue working to ensure that local partners (CEJP, CSOs) are strengthened institutionally and are sustainable after 2016
- The programme will support the protection of human rights defenders and document electoral violence and abuses in the course of the next reporting period.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme was approved in April 2015 but activities have experienced delays in delivery partly due to (i) administrative delays (USAID, Counterpart International); (ii) the recruitment of relevant staff (Counterpart International and The Carter Centre); and (iii) uncertainty due to the political context. This context has included delays to the electoral timetable, a rushed decentralisation process, and a change in plans for gubernatorial elections. We estimate these contextual issues have caused delays of approximately 6 months in terms of implementation of activities.

Performance of partnership(s)

Partners have adapted relatively well in this complex environment, ensuring that delivery on the ground gets the consent of main national counterparts (i.e. close collaboration of Counterpart International with CENI). Exchanges of information between implementing partners has been crucial to ensure complementarity and cohesion of the entire programme.

Asset monitoring and control

The team will conduct a spot check after receiving the next implementing partner reportson 29th April 2016. These reports contain full asset listings.

Overall all partners have their own standard operating practices on the management of assets. These were reviewed through due diligence assessments. Implementing partners are required to provide updated asset lists in line with their regular reporting requirements.

DFID/USAID are confident in Counterpart International’s ability to appropriately manage programme assets. Likewise, DFID is confident that the Carter Centre has appropriate mechanism in place to manage assets. With regards to UNDP PACEC, the UN asset management procedures will be applied.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Both Counterpart International and the Carter Centre have monitoring and reporting plans developed for this programme. Monitoring specialists have been hired for both the civic education and observation components of this programme. Monitoring tools are being developed to ensure that results are tracked against agreed milestones (i.e. the Activity Monitoring Plan revised by USAID/Counterpart International). DFID’s own M&E specialist is regularly brought in to advise on specific issues (i.e process to finalise programme logframe).

There is no independent evaluation planned for this programme. However, as and when elections take place, DFID will draw upon reporting from independent international observation missions, typically provided by The Carter Center, and the EU.

Monitoring progress throughout the review period

The programme logframe was updated and milestones and indicators are a better presentation of the complex reality on the ground. Although there have been delays to implement activities, programme progress is being assessed against the revised milestones.

Annex – SRO Risk Matrix