## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 200625
ARIES Project Description | Zambia Social Protection Expansion Programme
A1: Purpose, Risk
Purpose
Project Purpose | Households receiving Social Cash Transfers have improved stardards of living by 2015
Indicator 1 | Food security: % of households having no more than one meal per day reduced from 21% in baseline year to 15% at time of impact evaluation.
Milestone for this review (if any) | Baseline has shown that 21.13% of households have one meal per day.
What progress has been made in the period covered by this review? | Too early to tell. Impact evaluation planned for 2012 and 2013. Qualitative information obtained from beneficiaries during this review suggests the trend is in the right direction. Beneficiaries reported spending the cash transfer on more food, a better variety of food, assets (chickens, pigs and seeds) and small trade (fish and maize). Modelling of impact based on the baseline data suggests that the majority of extra spending is likely to be on food.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Education: School enrolment in households in SCT districts increased from 44% in baseline year to 70 % at the time of impact evaluation.
Milestone for this review (if any) | Baseline enrollment in households in SCT district stands at 44%
What progress has been made in the period covered by this review? | Too early to tell. Impact evaluation planned for 2013. Qualitative information obtained from beneficiaries and school headmasters during this review suggests the trend is in the right direction. Changes in on time enrolement for younger children and continued enrollment (progression) in older children are considered to be a more direct consequence of cash transfers than absenteeism and attendance.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Health: Proportion of persons reporting illness in households in SCT districts reduced from 15% in baseline year to 12% at time of impact evaluation
Milestone for this review (if any) | 15% at baseline in project districts
What progress has been made in the period covered by this review? | Too early to tell. Impact evaluation planned for 2012 and 2013. Qualitative information obtained from beneficiaries during this review suggest the trend is in the right direction. Modelling of impact based on baseline data suggests little change in health outcomes.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4 | Child wellbeing: % of children in households receiving SCT without material needs ie (shoes,blanket, change of clothing) reduced from 25% in baseline year to 15% at the time of impact evaluation.
Milestone for this review (if any) | 25% at baseline in SCT districts
What progress has been made in the period covered by this review? | Too early to tell. Impact evaluation planned for 2012 and 2013. Qualitative information obtained during this review suggest the trend is in the right direction.
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5 | Women's empowerment: women's empowerment index
Milestone for this review (if any) | 65% of women in SCT households make own decisions (or jointly with partner at baseline)
What progress has been made in the period covered by this review? | Too early to tell. Impact evaluations planned in 2012 and 2013. Qualitative information obtained from beneficiaries during this review suggest the trend is in the right direction.
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | The current purpose assumption is 'No natural or man made disasters increase in poverty levels'. Zambia has experienced 2 years of bumper harvests since the programme started and food security levels have been good. The principal purpose assumptions should perhaps be related to Government of Zambia ownership and sustanability of the cash transfer programme. Government of Zambia is in the lead on this cash transfer programme and are starting to commit significant funds. At the opening of Parliament on 14 October 2011, the President committed "to improving the scheme and make it sustainable by gradually increasing support from the domestic budget".
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | The Goal of the programme is to reduce extreme poverty and the intergenerational transfer of poverty in the districts covered by the National Social Cash Transfers Programme as evidenced by a drop in the extreme poverty gap. During the review, field trips were undertaken and a range of beneficiaries consulted in group discussions. Increased expenditure, as a result of the transfer, was reported on food, health, education, accumulation of assets (livestock) and other livelihood activities (home gardens). Modelling based on baseline data also predicts improvements in a range of indicators.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | 28,340 recipients are currently receiving regular cash transfers and the systems for the delivery of these transfers and the monitoring of impact are being strengthened. Control groups in the independent impact evaluation will allow attribution of programme impacts. Recipients in child grant districts currently benefit from few other programmes.
Purpose Recommendation 1 | Qualitative monitoring is urgently needed to provide 'real time' feedback to inform programme design changes and complement quanititative impact evaluation by investigating the mechanisms through which changes are occuring and what unexpected changes.
Purpose Action Point 1 | DFID to contract research organisation to carry out qualitative analysis around key themes (gender, climate change, Community Welfare Assistance Committes (CWAC's)), provide recommendations on programming and policy, inform qualitative analysis and document process and findings fror dissemination.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 1 | #VALUE!
Purpose Justification | Despite manual systems and lack of automated Management Information System (MIS), Ministry of Community Development, Mother and Child Health (MCDMCH) have been able to deliver cash transnfers to an increasing number of beneficiaries with limited delays and security problems. With a fullly operational MIS and electronic payment system, securing payments to beneficiaries will be less of a challenge and should be fully achieveable. Field level interviews confirmed expenditure patterns consistent with purpose level indicators.
Risk
Project Risk Rating or latest Overall Risk Score | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability | New payment mechanism not procured and rolled out.
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks? | DFID is supporting the process of procuring a payment service provider through participating in the tender committee and funding technical advice from Crown Agents (on procurment) and Bankable Frontiers (electronic payment mechanisms). The shortlist of bidders is strong but given the difficult environments they will be asked to work on this risk needs to be monitored.
Risk Recommendation 1 | Fiduciary risk: The Office of the Auditer General (OAG) has been carrying out annual audits of the cash transfer programme. Fiduciary risk will be reduced through procurement of electronic payment service provider and broader capacity building support on financial management planned jointly by Cooperating Partners (CP's). Care is needed in selection of payment provider that to ensure that a potential monopoly is not created and there is full flexibilty in the future to layer other support onto this transfer programme.
Risk Action Point 1 | DFID to contract fiduciary risk and financial management capacity assesment to be carried out during first quarter of 2012.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2 | Political Support: The Government of Zambia is clearly in the lead on this cash transfer programme and are starting to commit significant funds. At the opening of Parliament on 14 October 2011, the President committed "to improving the scheme and make it sustainable by gradually increasing support from the domestic budget".
Risk Recommendation 3 | Implementation capacity: is being strengthened through additional staffing (cash transfers unit and scheme assistants), new MIS and payment service provider, and simplification of targeting approach. Review of role of CWAC's and subsequent training for CWAC's and MCDMCH officials nation wide is being funded through new Finland programme.
Risk Action Point 2 | DFID/UNICEF to arrange CP meeting with new Ministers by end of 2011 to clarify new governments commitment to cash transfers programme and social protection more broadly.
Risk Action Point 3 | Comprehensive capacity assesment to be carried out by MCDMCH/CP's during first quarter of 2012 to inform further capacity strengthening.

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | 69,000 targeted recipients receive regular Social Cash Transfers by 2015
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | Original Logical Framework had four outputs. After extensive consultation between Government of Zambia and CPs these have been reduced to two. New impact weights reflect this.
Original or Revised Impact Weight (%) | 70%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
|  | 1.4 | 1. Number of teachers trained
DFID Share revised/needs revision? | No |  | 2. Number of classrooms constructed or rehabilitated
If Yes, why was/is this? |  | 1 | 3. Number of health professionals trained
Original or Revised DFID Share | £32 million | 2 | 4. Number of one year olds vaccinated against measles
|  | 3 | 5. Number of insecticide treated bed nets distributed
Indicator 1 (leave blank if standard indicator) | Number of households receiving timely and regular payments | 4 | 6. Number of people with advanced HIV infection receiving ARVs
Is this a Standard Indicator? | No | 5 | 7. Number of condoms distributed
Select standard indicator from drop down list |  | 0 | 8. Number households provided with new/improved drinking water sources
Milestone for this review (including number, if any) | 34,383 beneficiaries paid by end 2011. |  | 9. Number of new/improved sanitation facilities provided
Progress made in the period covered by this review, including numbers | Despite the cumbersome manual payment mechanism and the programme scaling up into some of the most inaccessible districts in the country, the number of cash transfer recipients has increased to 28,340 and payments are being made with miminumal delays or security problems. An additional 4,220 recipients will receive payments in new districts before the end of 2011 bringing the total number of recipients to 32,560 (95% of the target). Scaling up of the programme will be smoother once the MIS and payment mechanism are in place. Under enrolment of eligible households in child grant districts will be rectified once the new payment mechanism is in place. Continuous enrolment of newly eligible recipients is being implemented in child grant and pension districts, but not 10% model districts. The new payment mechanism will also address problems in recipients forfeiting payments when they miss the 2 day payment window under the manual system. The child grant baseline report concluded that targeting was 'highly progressive' with recipients being poorer, less well nourished and more food insecure than other households in rural Zambia. |  | 10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
Indicator 2 (leave blank if standard indicator) |  |  | 13. Number of people directly assisted by food security programmes
Is this a Standard Indicator? |  |  | 14. Number of people directly assisted by social assistance programmes
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 1 | 1
Impact Weighted Score | 70 | 0.7
Justification for the Score
Output 1 Recommendation 1 | The new payment system must be prioritised to improve security of payments, improved service to recipients and ability to scale up.
Output 1 Action Point 1 | DFID to continue to support procurement of electronic payment mechanism.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | A review of the 3 targeting approaches to ascertain inclusion and exclusion errors, strength of implementation and cost-effectiveness.
Output 1 Recommendation 3
Output 1 Action Point 2 | CP's to contract a targeting review to feed into the long-term planning of cash transfers programmes nationally and the social protection policy development.
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | MCDMCH develops and uses sustainable systems appropriate to run a cost effective national social cash transfer scheme by the end of 2012
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | The original Logical Framework had four outputs. After extensive consultation between Government of Zambia and CPs the outputs have now been reduced to two. The new impact weights reflect this.
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.6
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | £6 million
Indicator 1 (leave blank if standard indicator) | Administration costs maintained at under 20%
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Under 20%
Progress made in the period covered by this review, including numbers | Current overhead has been estimated at 18%, and this at a time of dramatic scale up in new and inaccessible districts.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | % of funds ( Admininistration and transfers) reported to have been misappropriated according to the final audit report
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 0
Progress made in the period covered by this review, including numbers | The 2010 OAG audit report raised concerns around management systems. The final audit report showed K109million (0.9% of total) unacquitted payments to pay point managers. This will be removed in new payment mechanism. A strengthened greivance system is needed to track misappropriation of funds between pay points and beneficiaries.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Standard quarterly reports submitted on time
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Quarterly reports submitted as per Joint Financing Agreement (JFA)
Progress made in the period covered by this review, including numbers | Quarterly reports have been submitted and summaries presented at the review workshop. Recommendations have been followed up. MIS system needed to ensure timely and accurate reporting. This has been developed and use is being rolled out.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | Amount (%) of Government funding to Social Cash Transfers budget
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any) | K 7,800,000,000 (15%)
Progress made in the period covered by this review, including numbers | Government of Zambia released full commitment to the cash transfer programme in 2010 and 2011. Because budget requirements were less than planned, % contribution from Government of Zambia was 32% (2010) and 29% (2011) of programme costs.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator) | Number of grievance reports received and dealt with effectively in a timely manner
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | None
Progress made in the period covered by this review, including numbers | MCDMCH staff reported that grievances have been brought to the attention of district staff. Major issues are reported in quarterly meetings, but there is no sytematic recording of grievances or tracking whether, or how, they have been addressed. This will be addressed through the new MIS system.
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 1 | 1
Impact Weighted Score | 30 | 0.3
Justification for the Score
Output 2 Recommendation 1 | A review of the role of Community Welfare Assistance Committees (CWACs) and how to support/incentivise them to ensure sustainability is urgently needed. This work fall sunder the review of Public Welfare Assistanec Scheme (PWAS) to be funded by Finland. An increased role for women, particularly in leadership positions should recommended.
Output 2 Action Point 1 | DFID to support formalisation of Finnish funding and urgent implementation of CWAC review.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2 | New MIS system including greivance tracking module needs to be rolled out as a matter of urgency.
Output 2 Recommendation 3
Output 2 Action Point 2 | DFID to support MCDMCH and monitoring and evaluation consultants to complete development and roll out of MIS.
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | No. of households receiving timely and regular pension
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 3 Recommendation 1
Output 3 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | No. of reported cases of misappropriation or wrongful deduction of funds from SCT programme at any level
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 |  | 0
Impact Weighted Score |  | 0
Justification for the Score
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision? |  |  | 1. Number of teachers trained
If Yes, why was/is this? |  |  | 2. Number of classrooms constructed or rehabilitated
Original or Revised DFID Share |  |  | 3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
Indicator 1 (leave blank if standard indicator) |  |  | 5. Number of insecticide treated bed nets distributed
Is this a Standard Indicator? |  |  | 6. Number of people with advanced HIV infection receiving ARVs
Select standard indicator from drop down list |  |  | 7. Number of condoms distributed
Milestone for this review (including number, if any) |  |  | 8. Number households provided with new/improved drinking water sources
Progress made in the period covered by this review, including numbers |  |  | 9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet |  |  | 11. Total length of roads maintained or rehabilitated
Indicator 2 (leave blank if standard indicator) |  |  | 12. Number of households provided with new/improved access to basic electricity supply
Is this a Standard Indicator? |  |  | 13. Number of people directly assisted by food security programmes
Select standard indicator from drop down list |  |  | 14. Number of people directly assisted by social assistance programmes
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 8/10/11 - 14/10/11
Impact Weighting (must = 100) | 100%
Total Impact Score | 100 | 1
Output Risk | Medium | 2
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment | X
Joint donor review | X
Independent consultant review | X
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner | X
National non-Government partner | X
Independent consultant | X
Donor partners | X
DFID staff | X
Donor partners | UNICEF
Irish Aid
Government of Finland
Comment here on the Method of Scoring and Scoring Responsibility | The review involved consultations with stakeholders at all levels. Two Teams (comprising DFID, Irish Aid, FinAid, UNICEF and MCHMDH) undertook two field visits, one to Shang'ombo (child grants) in Western Province, and the other to Monze (10% model) in Southern Province, where meetings were held with CWACs, Social Welfare Officers (SWOs), communities and individual beneficiaries. A two day workshop following the field visit allowed both teams to share findings. DFID staff scored the programme's performance based programme documentation, information provided during the workshop and field consultations. A full annual review report will be produced by the end of November by the facilitators of the workshop.
Scoring Recommendation 1 | The logical framework has recently been reviewed based on child grant baseline findings. Finalisation of the logframe taking into account comments from this annual review is urgently needed. Additional outcome indicators on nutrition (pending further analysis of baseline data), livelihoods (accumulations of assets and retention) and a more refined indicator of women's empowerment should be considered. Additional output 1 indicators on payment timeliness and targetting effectiveness should be considered. On output 2, the indicator on quarterly reports should more closely refer to the MIS system.
Scoring Action Point 1 | DFID to provide comments and support finalisation of logframe by MCDMCH.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Systems and capacity within the MCDMCH continue to need strengthening. The finalisation of the MIS and payment mechanism should be a priority. New support to financial management capacity is to be developed jointly with other CP’s. The cash transfer programme continues to add significantly to the burden on volunteer CWACs resulting in strong demand for incentives or renumeration. The introduction of simpified targeting and electronic payment mechanism will reduce the workload on CWAC's, but issues of sustaining volunteer's particpation need to be considered. The role and incentive structure of CWAC's is to be reviewed using Finnish funding.
Working with Partners Recommendation 1 | A review of the role of Community Welfare Assistance Committees (CWACs) and how to support/incentivise them to ensure sustainability is urgently needed. This work falls under the review of Public Welfare Assistanec Scheme (PWAS) to be funded by Finland. An increased role for women, particularly in leadership positions should recommended.
Working with Partners Action Point 1 | DFID to support formalisation of Finnish funding and urgent implementation of CWAC review.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2 | Broad capacity building support on financial management to be jointly planned and supported by Cooperating Partners (CP's).
Working with Partners Recommendation 3
Working with Partners Action Point 2 | DFID to contract fiduciary risk and financial management capacity assesment to be carried out during first quarter of 2012.
Working with Partners Action Point 3
2. Best Practice / Innovation | The independent impact evaluation is based on a randomised control trial (RCT). The child grant baseline report was robust and included an innovative section on predictions of impact. The RCT design results in a three year delay for the control group. The delay was originally considered a factor of the capacity to roll-out, but the simplified targeting approach and new payment mechanism mean this may not continue to be the case. Given the high poverty rates in the child grant districts and limited window of opportunity to impact on childhood stunting (the 1,000 days from conception to age 2), continued exclusion of control groups from the programme could become unethical. Bringing the control into treatment earlier would however limit the longer term impact evidence needed to inform programming and policy in Zambia and beyond. The MIS system includes indicators that will allow beneficiaries to be compared with national data beyond the impact evaluation, as well as management information. MCDMCH needs increased capacity to maintain the MIS and analyse future M&E data.
Best Practice / Innovation Recommendation 1 | Consideration to be given to reducing the length of the control trial and ensuring full coverage in existing districts before expanding to new ones. This should take place once the payment mechanism roll out strategy is known.
Best Practice / Innovation Action Point 1 | DFID Zambia to discuss the issue of long term randomised control trials and seek advice from Evaluation department on establishing other sample monitoring mechanisms. Decision on maintaining control groups to be made only once payment service provider roll out schedule known as this is critical factor in scale up rate.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Procurement of goods (DFID) and technical support (UNICEF) has experienced delays which has slowed implementation. Increased local capacity of the procurement agent and more intense management by DFID has resulted in performance improvements but these need to be continually monitored. The MCDMCH/CP relationship remains strong, but decision making needs to be more systematic and better documented, both between MCDMCH and CP's and within the CP group.
Project Management Recommendation 1 | More timely procurement of goods and services by CP's on behalf on MCDMCH.
Project Management Action Point 1 | DFID to provide continued strong oversight of procurement agent. UNICEF to bundle technical assistance to speed up procurement.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2 | More formalised documentation of consultation and decision making between Government of Zambia and CP's needed.
Project Management Recommendation 3
Project Management Action Point 2 | Decision making process and documentation to be agreed between MCDMCH and CP's, building on existing reporting and consultation processes (namely quarterly meetings and reports and CP meetings).
Project Management Action Point 3
Other Comments
Key issues, points of information or additional comments that may be useful for this or other project teams | Government of Zambia should be congratulated that in the absence of robust electronic payment system, they have succeeded in delivering cash transfers to over 28,000 people in very remote districts on time, and with no reports of misappropriation.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3 |  | 5. Child Grant baseline report
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
2525708 | 100217_ Project Proposal_ Annex 1 - MCDSS PROPOSAL for Scaling Up SCTs
2525699 | 100217_ Project Memorandum_Zambia Social Protection Expansion PM Feb 2010
2525684 | 100217_ Submission _ Zambia SP Expansion Programme
2999121 | 110325_2010 SCT Summary Review_Quality Assured
3002640 | 110330_MCDSS SCT Programme Logframe_Updated
2549904 | 100309_ Risk Assessment_ Detailed Risk Assessment Annex 13
2549883 | 100309_Budget_ Detailed budget for MCDSS programme Annex 11
2549875 | 100309_ Budget_ Summary budget for the whole programme Annex 10
2549813 | 100309_ Appraisals_ Detailed Economic, Social, Political and Results Appraisals Annex 5
110609 Evaluation report_Monze cash transfers.vso
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality
D: Conditionality
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Purpose
R1 | Qualitative monitoring is urgently needed to provide 'real time' feedback to inform programme design changes and complement quanititative impact evaluation by investigating the mechanisms through which changes are occuring and what unexpected changes. | DFID Zambia Vulnerability & Food Security Adviser
R2 | 0
R3 | 0
A1: Risk
R1 | Fiduciary risk: The Office of the Auditer General (OAG) has been carrying out annual audits of the cash transfer programme. Fiduciary risk will be reduced through procurement of electronic payment service provider and broader capacity building support on financial management planned jointly by Cooperating Partners (CP's). Care is needed in selection of payment provider that to ensure that a potential monopoly is not created and there is full flexibilty in the future to layer other support onto this transfer programme. | DFID Zambia Vulnerability & Food Security Adviser with irish Aid
R2 | Political Support: The Government of Zambia is clearly in the lead on this cash transfer programme and are starting to commit significant funds. At the opening of Parliament on 14 October 2011, the President committed "to improving the scheme and make it sustainable by gradually increasing support from the domestic budget". | DFID Zambia Vulnerability & Food Security Adviser & UNICEF Chief of Social policy
R3 | Implementation capacity: is being strengthened through additional staffing (cash transfers unit and scheme assistants), new MIS and payment service provider, and simplification of targeting approach. Review of role of CWAC's and subsequent training for CWAC's and MCDMCH officials nation wide is being funded through new Finland programme. | DFID Zambia Vulnerability & Food Security Adviser with Embassy of Finland
A2: Outputs
R1.1 | The new payment system must be prioritised to improve security of payments, improved service to recipients and ability to scale up. | DFID Zambia Vulnerability & Food Security Adviser with MCDMCH and M&E consultant
R1.2 | A review of the 3 targeting approaches to ascertain inclusion and exclusion errors, strength of implementation and cost-effectiveness. | DFID Zambia Vulnerability & Food Security Adviser
R1.3 | 0
R2.1 | A review of the role of Community Welfare Assistance Committees (CWACs) and how to support/incentivise them to ensure sustainability is urgently needed. This work fall sunder the review of Public Welfare Assistanec Scheme (PWAS) to be funded by Finland. An increased role for women, particularly in leadership positions should recommended. | DFID Zambia Vulnerability & Food Security Adviser with Finnish Embassy
R2.2 | New MIS system including greivance tracking module needs to be rolled out as a matter of urgency. | DFID Zambia Vulnerability & Food Security Adviser with MCDMCH and M&E consultant
R2.3 | 0
R3.1 | 0
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | The logical framework has recently been reviewed based on child grant baseline findings. Finalisation of the logframe taking into account comments from this annual review is urgently needed. Additional outcome indicators on nutrition (pending further analysis of baseline data), livelihoods (accumulations of assets and retention) and a more refined indicator of women's empowerment should be considered. Additional output 1 indicators on payment timeliness and targetting effectiveness should be considered. On output 2, the indicator on quarterly reports should more closely refer to the MIS system. | DFID Zambia Vulnerability & Food Security Adviser with MCDMCH
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | A review of the role of Community Welfare Assistance Committees (CWACs) and how to support/incentivise them to ensure sustainability is urgently needed. This work falls under the review of Public Welfare Assistanec Scheme (PWAS) to be funded by Finland. An increased role for women, particularly in leadership positions should recommended. | DFID Zambia Vulnerability & Food Security Adviser with Bankable Frontiers Associates and MCDMCH
R2 | Broad capacity building support on financial management to be jointly planned and supported by Cooperating Partners (CP's).
R3 | 0
Best Practice / Innovation
R1 | Consideration to be given to reducing the length of the control trial and ensuring full coverage in existing districts before expanding to new ones. This should take place once the payment mechanism roll out strategy is known. | DFID Zambia Vulnerability & Food Security Adviser with MCDMCH and AIR
R2 | 0
R3 | 0
Project Management
R1 | More timely procurement of goods and services by CP's on behalf on MCDMCH. | DFID Zambia Vulnerability & Food Security Adviser and UNICEF Chief of Social Policy
R2 | More formalised documentation of consultation and decision making between Government of Zambia and CP's needed. | DFID Zambia Vulnerability & Food Security Adviser with UNICEF Chief of Social Policy and MCDMCH
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points
A1: Purpose
AP1.1 | DFID to contract research organisation to carry out qualitative analysis around key themes (gender, climate change, Community Welfare Assistance Committes (CWAC's)), provide recommendations on programming and policy, inform qualitative analysis and document process and findings fror dissemination. | DFID Zambia Vulnerability & Food Security Adviser with Irish Aid
AP1.2
AP1.3
A1: Risk
AP1.1 | DFID to contract fiduciary risk and financial management capacity assesment to be carried out during first quarter of 2012. | DFID Zambia Vulnerability & Food Security Adviser
AP1.2 | DFID/UNICEF to arrange CP meeting with new Ministers by end of 2011 to clarify new governments commitment to cash transfers programme and social protection more broadly. | DFID Zambia Vulnerability & Food Security Adviser with UNICEF Chief of Social Policy
AP1.3 | Comprehensive capacity assesment to be carried out by MCDMCH/CP's during first quarter of 2012 to inform further capacity strengthening. | UNICEF Chief of Social policy
A2: Outputs
AP1.1 | DFID to continue to support procurement of electronic payment mechanism. | DFID Zambia Vulnerability & Food Security Adviser with PrG
AP1.2 | CP's to contract a targeting review to feed into the long-term planning of cash transfers programmes nationally and the social protection policy development. | DFID Zambia Vulnerability & Food Security Adviser with UNICEF Chief of Social Policy
AP1.3 | 0
AP2.1 | DFID to support formalisation of Finnish funding and urgent implementation of CWAC review. | DFID Zambia Vulnerability & Food Security Adviser with Finnish Embassy and MCDMCH
AP2.2 | DFID to support MCDMCH and monitoring and evaluation consultants to complete development and roll out of MIS. | DFID Zambia Vulnerability & Food Security Adviser with MCDMCH and AIR
AP2.3 | 0
AP3.1 | 0
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | DFID to provide comments and support finalisation of logframe by MCDMCH. | DFID Zambia Vulnerability & Food Security Adviser and DFID Zambia Results Adviser
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | DFID to support formalisation of Finnish funding and urgent implementation of CWAC review.
AP1.2 | DFID to contract fiduciary risk and financial management capacity assesment to be carried out during first quarter of 2012.
AP1.3 | 0
Best Practice / Innovation
AP1.1 | DFID Zambia to discuss the issue of long term randomised control trials and seek advice from Evaluation department on establishing other sample monitoring mechanisms. Decision on maintaining control groups to be made only once payment service provider roll out schedule known as this is critical factor in scale up rate. | DFID Zambia Vulnerability & Food Security Adviser and DFID Zambia Results Adviser
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | DFID to provide continued strong oversight of procurement agent. UNICEF to bundle technical assistance to speed up procurement. | DFiD Zambia Vulnerability & Food Security Adviser and UNICEF Chief of Social Policy
AP1.2 | Decision making process and documentation to be agreed between MCDMCH and CP's, building on existing reporting and consultation processes (namely quarterly meetings and reports and CP meetings). | DFID Zambia Vulnerability & Food Security Adviser with MCDMCH
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3