## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 107891-101; 107891-102; 107891-103
ARIES Project Description | Kolkata Urban Services for the Poor Programme
A1: Goal, Purpose, Risk
Goal
Goal statement | Reduced Poverty in West Bengal
Indicator 1 | Human Development Index (HDI)
Milestone for this review (if any) | 0.7
What progress has been made in the period covered by this review? | The 2nd State Human Development Report is awaited. No information additional to last years reporting is available. However, trends have been indicating improvements in urban areas, for example; immunisation for children has increased to 76% (69% among urban poor) in 2008 - up from 70% in 2004; 27% reduction in maternal and infant mortality over the last 5 years - compared to the national average of 16%; around 90% of urban households reporting improved sanitation facilities; 89% primary school children age 6-10 years in urban areas attending school (up from 79% in 2004).
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Proportion of urban poor population
Milestone for this review (if any) | Kolkata Metropolitan Area (KMA) - 12 Non-KMA - 27
What progress has been made in the period covered by this review? | The 2006 Urban Household Survey (UHS) reported 14% and 34% poverty figures for KMA (Kolkata Metropolitan Area) and non-KMA urban local bodies (ULBs) respectively. The 2011 UHS is likely to be published by mid-2011. However, milestone target of 12% for KMA ULBs and 27% for non-KMA ULBs is expected to have been met attributable largely to 1.81 million urban poor direct beneficiaries from KUSP's slum infrastructure and livelihood generation activities (1.32 million urban poor benefitting directly from infrastructure provision and 0.49 million urban poor benefiting from livelihood and poverty alleviation program activities), additional 3.39 million urban beneficiaries from KUSP intra-municipal infrastructure projects, as well as KUSP's strong role in supporting Government of West Bengal leverage central funds to the tune of £20 million under Jawaharlal Nehru National Urban Renewal Mission's (JNNURM's) Basic Services for Urban Poor (BSUP) sub-component in 2010-11.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Proportion of the poor disaggregated by social groups, reporting improvement in livelihood opportunities and security of tenure
Milestone for this review (if any) | Dec 2009: Livelihood - 20 Tenure - 5
What progress has been made in the period covered by this review? | 44% urban poor in KMA report improvement in livelihood opportunities (CMU 2011). 2,100 slum households provided tenure security with focus now on scaling up (GoWB 2011; Independent Review 2011). 350,000 urban poor have benefitted directly from improved livelihood opportunities through KUSP activities under Innovative/Challenge Fund (over 90% beneficiaries of skill development project report doubling of income leading to generation of £4.8 million additional income over the 2009-11 period). The draft Tenure Security Policy note prepared by KUSP received cabinet approval in 2010. Till date 2,100 slum households (in 4 towns/cities) have received rental tenure security with the GoWB looking to scale up this number to reach another 75,000 households by 2013.
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Approval of Tenure Security Policy in late-2010 has directly benefited 2,100 households receive tenure security. Improved performance of West Bengal Municipal Development Fund (WBMDF) based on DFID recommendations in mid-2010 has meant that an additional 100,000 urban poor/slum dwellers have benefited from improved access to basic services, while an additional 70,000 poor have benefited from livelihood activities supported by KUSP; skill development efforts have led to an additional £2.4 million income being generated this year. All these have contributed to achievement of goal-level targets.
Goal Recommendation 1 | Scale-up tenure security provision efforts targeting 20,000 additional households by 2013.
Goal Action Point 1 | Continued TA support to KUSP CMU beyond March 2011 towards overcoming barriers on tenure security provision to slum dwellers may be considered by DFID.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Improved quality of life for 2.4 million poor people in target slums at Kolkata Metropolitan Area (KMA)
Indicator 1 | Proportion of poor reporting satisfaction on inclusion of their 'voice' in urban local body (ULB) decision making and functioning.
Milestone for this review (if any) | 70
What progress has been made in the period covered by this review? | Partly achieved. An independent assessment indicates notes that 41% slum dwellers (50% women, 55% vulnerable group) were aware and participated in city-level decision making processes. However, only 17% slum dwellers reported satisfaction. Considering that (i) non-slum poor people were not covered under the assessment, (ii) engaging of poor in city-level decision making process before KUSP was unusual, and (iii) evidence of municipal governments moving towards more inclusive decision making, this is a substantial achievement.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Proportion of target slum dwellers reporting improvement in access and coverage to basic services disaggregated by social groups
Milestone for this review (if any) | 80
What progress has been made in the period covered by this review? | Completely achieved. In an independent evaluation in 2011, 94% slum dwellers in KUSP supported slums indicated an improvement in coverage to basic infrastructure - an increase from 65% recorded in the 2008 Citizen Report Card (CRC). Over this period (580 slums in 2008 and 807 slums in 2011), proportion of slum dwellers indicating improved access to water supply increased from 81% to 83%, drainage from 79% to 89%, and sanitation increased from 70% to 80%. The major achievement recorded was improvement on O&M (access) of services provided recording 86% for water supply in KUSP slums (against 56% recorded in non-KUSP), 93% on drainage (against 77% recorded in non-KUSP slums and 79% recorded in 2008 CRC), and 82% on sanitation (against 40% recorded in non-KUSP slums and 70% recorded in 2008 CRC).
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Household expenditure
Milestone for this review (if any) | .+25% from baseline
What progress has been made in the period covered by this review? | Completely achieved. Proportion of households reporting monthly expenditure below Rs.1500 (approx. £4/person/month; household size is 4.9) has reduced from 76% in 2004-05 (NSS) to 56% in 2009-10 (SUDA) indicating a 26% improvement from baseline. A number of KUSP initiatives have directly contributed towards this outcome including West Bengal Urban Poverty Eradication Mission (WBUPEM) - for which CMU is the Secretariat - taking more than 26,000 BPL families out of poverty through a coordinated mission approach, 350,000 poor benefiting from livelihood activities under KUSP leading to cumulatively additional income generation to the tune of £2.4 million in this reporting year, 1.32 million urban poor benefitting directly from infrastructure provision, among others.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Purpose assumptions are being largely realised. Even with a change in political leadership in many ULBs in municipal elections in mid-2010, new leaders remain committed to efforts of sustained poverty reduction and land tenure reforms, as well as other reforms propagated by KUSP. Ongoing GoWB efforts to ensure long-term sustainability of KUSP funded positions in ULBs by mainstreaming these also demonstrate strong resonance of the reform agenda. The State and ULBs are also making efforts to improve citizen feedback mechanisms through the e-governance pathway, especially in KMA ULBs.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | Strong evidence available. KUSP has benefitted 1.32 million poor people directly through improved access to basic services and 0.49 million poor directly through its livelihood and poverty alleviation activities - laying the foundation for these people to move above the poverty line. KUSP has also benefited 0.53 million slum dwellers report better health outcomes (through the urban health strategy) and indirectly benefited an additional 3.39 million people access better services. KUSP has also contributed to increased resource allocations towards pro-poor development including (i) earmarking of 25% expenditure on pro-poor development, (ii) mobilisation of additional £20 million for slum infrastructure development from central schemes in 2010-11, and (iii) 33% increase in own-source revenues of municipal governments. Looking at KUSP's success, GoWB has taken necessary steps to sustain key KUSP reforms beyond March 2011 thereby ensuring Goal realisation sustaining beyond programme period.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | Strong evidence available. All four outputs have contributed substantially towards achievement of Purpose in this reporting period as evidenced below: Under Output 1, own source revenue increase registered a 50% growth over the previous years increase, while 25% mandatory earmarking of municipal expenditure was successfully met. Under Output 2, an additional 460,000 urban poor population indicated improved access to basic infrastructure while around 22,000 additional households were taken out of poverty. Under Output 3, an additional 100,000 poor people benefited from livelihood and local economic development activities. Under Output 4, KMC posted around a 8% increase in spend on pro-poor service delivery taking the Corporation beyond the 25% mandated under JNNURM.
Purpose Recommendation 1 | Ensure stronger engagement of poor in city-level planning and decision making exercises, especially in preparation of second generation Draft Development Plans (DDP) over 2011-13 period.
Purpose Action Point 1 | DFID may consider limited TA to KUSP to support preparation of 2nd generation DDPs.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 1 | 1.45
Purpose Justification | The Purpose rating of '1' is justified based on achievement of Purpose and strong output performance. Cumulatively, KUSP has directly benefitted 2.34 million urban poor/slum dwellers (basic infrastructure, livelihoods, health, poverty alleviation programmes) and indirectly benefitted 3.4 million people. This excludes beneficiaries of JNNURM-BSUP wherein KUSP has been instrumental in mobilising £87 million of central funds on pro-poor development. Independent assessments indicate that 41% slum dwellers (50% women; 55% minorities) participated in city development planning a sea-change from the non-inclusive approach adopted when KUSP was initiated. Improved service provision and livelihoods development component are reflected in the over 26% increase in household expenditure in urban areas. Independent assessments also indicate that slum citizens' satisfaction of services provided, including operation and maintenance, has improved over the last two-year period (and are substantially higher in KUSP slums compared to non-KUSP slums) highlighting the strong performance of this programme.
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised? | No
If Yes, why was/is this?
Logframe Recommendation 1
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Improved Urban Planning and Governance in KMA urban local bodies (ULB)
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 40%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.8
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share | Original (FA):£21.77 million; TA (combined amount for all outputs): £13.26 million | 2
Indicator 1 | Aggregated own source revenue collection of KMA ULBs (Rs. Lakh) | 4
Is this a Standard Indicator? | No | 5
Milestone for this review (if any) | 27,981 (50%) | 0
What progress has been made in the period covered by this review? | Largely achieved. Aggregated own source revenue collection of KMA ULBs for 2009-10 was recorded as Rs.24,825 lakh registering a 33% increase from baseline (2006-07). In non-KMA ULBs, aggregate own-source revenue collection increased to Rs.21,044 lakhs registering a 55% increase from baseline (2006-07).
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Number of ULBs in which e-governance system fully operationalised, including municipal GIS with satisfied slum customers
Is this a Standard Indicator? | No
Milestone for this review (if any) | E-Gov: 41 KMA Satisfaction levels: 60
What progress has been made in the period covered by this review? | Partly achieved. Roll-out of e-governance has not been completed. As of Jan 2011, roll-out had been done for 39 KMA ULBs and 31 non-KMA ULBs. In KMA of the five most-critical modules, three have been operationalised in 39 ULBs including birth and death registration, trade license and MIS/administration. Public grievance module has been operationalised in 3 ULBs while property tax module is being tested in 5 ULBs for scale-up by March 2011. The complete roll-out is expected to be done by December 2011. The central data server has not been procured due to procurement constraints wherein only a single bidder qualified for financial opening. Exit surveys undertaken by independent consultants on satisfaction level indicate a 95.6% satisfaction with birth and death certificate module and a 98.5% satisfaction with the trade license module.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Proportion of ULB expenditure spent on pro-poor service delivery and related operation and maintenance (O&M) and proportion of O&M costs met through own sources of revenue.
Is this a Standard Indicator? | No
Milestone for this review (if any) | Dec-09: Spend: 25 O&M: 55
What progress has been made in the period covered by this review? | Completely achieved. Independent assessments indicate that 30% of ULB expenditure is spent on pro-poor service provision and related O&M, while 51% of O&M costs are met through own sources of revenue.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 1 | 2 | 0.75
Impact Weighted Score | 30 | 0.3
Justification for the Score
Output 1 Recommendation 1 | Focus on public financial management reforms at ULB level to allow greater mobilisation of own-source revenues.
Output 1 Action Point 1 | Limited TA support should include a component on sustaining and strengthening PFM functions at the ULB level.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Improved access to urban basic services in target slums and convergence with national programmes
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 40%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.8
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | Original (FA): £59.03 million
Indicator 1 | Number of slum dwellers accessing all basic services (matching NSDP guidelines) and proportion of satisfaction of O&M
Is this a Standard Indicator? | Yes
Milestone for this review (if any) | 2.4 million (satisfaction levels: water 80% ; drainage 80%; sanitation 80%; roads 80%)
What progress has been made in the period covered by this review? | Completely achieved. KUSP has directly benefitted 1.32 million urban poor through slum level infrastructure provision, and an additional 3.4 million indirect urban beneficiaries from KUSP intra-municipal infrastructure projects (linking city infrastructure to slums). Independent evaluation (2011) improvement on O&M of services provided recording 86% for water supply in KUSP slums (against 56% recorded in non-KUSP), 93% on drainage (against 77% recorded in non-KUSP slums and 79% recorded in 2008 CRC), and 82% on sanitation (against 40% recorded in non-KUSP slums and 70% recorded in 2008 CRC). This demonstrates strong O&M structures in KUSP slums as number of slums under KUSP coverage increased from 580 in 2007-08 (when CRC was undertaken) to 807 in 2011.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Number of households taken out of poverty through coordinated Mission approach
Is this a Standard Indicator? | No
Milestone for this review (if any) | 7000
What progress has been made in the period covered by this review? | Completely achieved. WBUPEM has effectively scaled up its efforts to ensure coordinated access to all central and state government poverty alleviation programmes/projects to targeted urban poor population. Till Jan 2011, around 26,000 households have benefited from this approach (CMU - Review Presentation, 2011).
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Proportion of target slum dwellers reporting Honorary Health Workers (HHW) as first point of contact for RCH and immunization purposes
Is this a Standard Indicator? | No
Milestone for this review (if any) | 90
What progress has been made in the period covered by this review? | Largely achieved. An independent evaluation (2011) indicates that 79% slum households have reported HHW as the first point of contact for RCH and immunisation (KUSP has trained 10,500 HHWs and given them Health Kit Bags) - although evaluation of benefits of this component is not available, it is estimated that nearly 530,000 slum dwellers have benefitted through improved health outcomes (especially on referrals, institutional delivery, immunisation, etc.). This is also reflected in increase in immunisation rate in urban areas from 70% in 2004 (NFHS-3) to 76% in 2008-09 (GoWB). GoWB plans to scale up the urban health component through KUSP (so far, KUSP has trained over 13,000 girls under an Adolescent Health Care Programme and conducted health check-ups for 210,000 children under a School Health Programme). The success of the KUSP model prompted the Ministry of Health and Family Welfare, and the Ministry of Housing and Urban Poverty Alleviation (Government of India) to research and study this model closely towards their efforts of designing a National Urban Health Mission programme.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 2 | 1 | 1
Impact Weighted Score | 40 | 0.4
Justification for the Score | Two of the three indicators have been completely achieved, while the third has been largely achieved.
Output 2 Recommendation 1
Output 2 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Economic Development Promoted
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.3
DFID Share revised/needs revision? | Yes
If Yes, why was/is this? | Meeting EoP targets for few outputs require additional allocations which are to be adjusted against savings in other outputs. Overall DFID share for programme to remain same.
Original or Revised DFID Share | Original (FA): £8.21 million
Indicator 1 | Innovative/Challenge Fund (I/CF) directly benefits poor persons
Is this a Standard Indicator? | No
Milestone for this review (if any) | 150000
What progress has been made in the period covered by this review? | Completely achieved. Till date, I/CF has benefited 217,619 poor persons (55% women beneficiaries, 53% SC and ST beneficiaries, 2% disabled beneficiaries). Over 90% beneficiaries of income generation projects have reported doubling of income (between Rs.800-Rs.1200/month additional income). Independent assessments indicate that I/CF interventions have led to generation of additional £2.4 million income in this reporting year alone. I/CF is also receiving corpus contribution from Jamsetji Tata Trust (~£0.65 m) with support upto 2012 contingent on DFID corpus contribution continuing beyond March 2011. I/CF also received recognition from Government of India (GoI) as an innovative approach towards sustainable poverty reduction at the India Urban Space National Award 2010 (runners up). The national Ministry of Housing and Urban Poverty Alleviation, Government of India, has indicated interest in scaling up I/CF at the national level in the near future.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Livelihood promotion efforts directly benefit poor youth ensuring placements
Is this a Standard Indicator? | Yes
Milestone for this review (if any) | Number trained: 3000; placements 80%
What progress has been made in the period covered by this review? | Completely achieved. Till date, 18,738 poor youth have received wage employment training. Independent assessments indicate a 80% placement success. However, retention ratio is close to 60% due to drop outs primarily contributed to the odd working hours making it difficult for female youth to continue for long. Field visit interaction with recently placed youth indicate that these youths (given training on how to operate financial software packages) are earning around Rs.3000 per month additional to what they were earning earlier (£500/year additional income). Learning from success of this initiative, GoWB is considering setting up of a dedicated Skill Building Institute in Kalyani in 2011-12 period. In addition, around 42,000 people have benefitted directly from self employment training (323 training events) undertaken by KUSP.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Number of self help groups (SHGs) mobilised and proportion of these linked to banks
Is this a Standard Indicator? | Yes
Milestone for this review (if any) | SHGs: 100,000 Linkages: 30%
What progress has been made in the period covered by this review? | Largely achieved. 34,568 SHGs have been mobilised with 41% accessing bank loans and 58% accessing Swarn Jayanti Shehri Rojgaar Yojana (SJSRY) revolving fund. KUSP support to strengthen SJSRY in this reporting period has led to additional £1.25 million being accessed by around 1500 thrift and credit groups (TCGs), and 306 community development societies (CDS) focusing on micro-enterprise development. The number of SHGs mobilised being substantially below the milestone can largely be attributed to setting of extremely ambitious targets, and are not a reflection of poor performance.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 3 | 1 | 1
Impact Weighted Score | 15 | 0.15
Justification for the Score | Two of the three indicators have been completely achieved while the third has been largely achieved.
Output 3 Recommendation 1 | The unspent I/CF corpus amount may be retained for sustaining activities beyond March 2011 as well as ensuring continued support from external partners such as JTT beyond life of the programme.
Output 3 Action Point 1 | DFID to approve retaining of this amount by March 2011.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Service delivery mechanisms improved in Kolkata Municipal Corporation (KMC)
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 5%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.1
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Property tax demand, coverage ratio and demand collection ration (DCR)
Is this a Standard Indicator? | No
Milestone for this review (if any) | Jan 2010: Demand: Rs. 600 Crore Coverage Ratio: 78%; DCR: 84%
What progress has been made in the period covered by this review? | Largely achieved. KMC reports current demand as Rs.556.56 crore (including arrears) with 70% coverage ratio. The demand collection ratio is 59%. While notable progress has been made on implementation of the unit area method of property taxation (the first notification was issued in Oct 2010, thereby formally initiating the process) the cautious approach adopted by KMC (with a new Mayor at helm since mid-2010) has meant that the date of start of implementation has slipped and is now likely to operationalised by autumn of 2011. Progress on the GIS exercise has been very weak and this is critical for KMC to ensure that it benefits substantially from property tax reforms.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Time taken for approval of application for mutation of domestic property
Is this a Standard Indicator? | No
Milestone for this review (if any) | 7 days
What progress has been made in the period covered by this review? | Largely achieved. Independent assessment shows that the fastest 85% applications are cleared within 10 days, a substantial reduction from the baseline of 20 days in 2008. However, if the slowest 15% applications (usually involving complex cases) are also considered, this goes up to 13 days. The milestone target for this review is quite ambitious considering baseline conditions, and the progress made is satisfactory.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Proportion of KMC expenditure on pro-poor service delivery
Is this a Standard Indicator? | No
Milestone for this review (if any) | 35%
What progress has been made in the period covered by this review? | Largely achieved. Independent assessment show that KMC has spent 30% of its total expenditure on pro-poor service delivery, an increase of 8% over previous financial year - by this, KMC has also qualified the JNNURM reform requirement of 25%. Additionally, share of own-source revenues spent on pro-poor development has increased from 13% to 21% over the programme period - this is a substantial achievement as it demonstrates that increased pro-poor spending has mainstreamed into KMC's decision making process and is not dependent on grants from state and centre alone.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 4 | 2 | 0.75
Impact Weighted Score | 3.75 | 0.0375
Justification for the Score | Very strong performance is demonstrated on all three indicators although none of these have completely hit the original targets.
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 09/02/2011 (09-10 February 2011)
Impact Weighting (must = 100) | 100%
Total Impact Score | 88.75 | 0.8875
Output Risk | Medium | 2
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment | X
Joint donor review
Independent consultant review | X
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners
DFID staff | X
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility. | (1). The DFID review team was led by Abhijit S.Ray (Urban Advisor) and included Shantanu Das (Programme Manager and Economist), Anjali Sablok (Programme Officer), and Agnes Rozario (Asst. Prog. Officer). This OPR was written by Abhijit and Anjali. (2). Site visits were undertaken to New Barrackpore; detailed discussions were held with Chairperson and Executive Officer, and other concerned officials, as well as with beneficiaries of LED and I/CF initiatives. Detailed discussions were also held with CMU (Project Director, Project Manager and all Advisors); Commissioner KMC, Deputy Commissioner KMC, and Deputy Manager KMC. Concluding discussions were held with Secretary, Municipal Affairs Department, GoWB and Minister, Urban Development and Municipal Affairs, GoWB. (3). Progress assessment was undertaken jointly with the government and scoring was done by DFID review team, following which it was shared and agreed with GoWB. DFID review team benefited from Impact Assessment of KUSP prepared by consultants (TARU) and Impact Assessment of KMC Activities report prepared by consultants (IPE), as well as numerous Government of West Bengal documents.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Graduating from a state/country requires DFID to consider a short-term limited strategic engagement beyond FA closure for very large projects. This not only ensures last mile connectivity, ensures better relationship management with the partner and value for UK investments.
Working with Partners Recommendation 1 | DFID to consider a limited strategic engagement with KUSP for upto 2 years as a TA support, after completion of the FA support.
Working with Partners Action Point 1 | DFID India senior management to take a decision on this.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation
Best Practice / Innovation Recommendation 1
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | (1) Large urban/infrastructure programmes take time (2 years in case of KUSP) for institutional systems to be put in place before they start responding to the Purpose actively. This has implications on programme financial management, wherein majority spends are recorded after this period - new programme designs need to keep this into account.
Project Management Recommendation 1
Project Management Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
Project Memorandum | 806544
OPR 2009-10 | 2511563
Aide Memoire MYR Oct 2010 | 2838131
KEIP Performance Assessment Presentation | 2962256
Presentation by CMU Feb 2011 | 2962249
Presentation on I/CF Feb 2011 | 2962255
Presentation on KUSP evaluation | 2960667
Graduation Strategy Note Oct 2009 | 2450130
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | Benefits from KUSP are likely to sustain beyond EoP as an institutional architecture for sustaining KUSP reforms has been jointly agreed by GoWB and DFID, wherein all institutions (CMU, WBMDF, I/CF, WBUPEM) and all positions set up under KUSP will be sustained by GoWB. This includes absorption of over 200 ULB level positions on ULB rolls permanently and absorption of around 30 positions in CMU into GoWB rolls for two years. Learning from KUSP has been instrumental in influencing city and state-level decision making and these have already been mainstreamed in State and ULB level decision making. Continued limited strategic support through TA funds will also ensure that benefits arising out of KUSP are responsibly sustained beyond March 2011. Learning from KUSP is also influencing thinking at GoI level in areas of inclusive planning (3x3 matrix), urban health delivery (role of Honorary Health Workers), and engaging community groups in service delivery through innovative delivery models (I/CF).
Sustainability Recommendation 1
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | Scale-up tenure security provision efforts targeting 20,000 additional households by 2013. | MA Department, GoWB & DFID
R2 | 0
R3 | 0
A1: Purpose
R1 | Ensure stronger engagement of poor in city-level planning and decision making exercises, especially in preparation of second generation Draft Development Plans (DDP) over 2011-13 period. | DFID
R2 | 0
R3 | 0
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Focus on public financial management reforms at ULB level to allow greater mobilisation of own-source revenues. | MA Department, GoWB & DFID
R1.2 | 0 | MA Department, GoWB & DFID
R1.3 | 0
R2.1 | 0
R2.2 | 0
R2.3 | 0
R3.1 | The unspent I/CF corpus amount may be retained for sustaining activities beyond March 2011 as well as ensuring continued support from external partners such as JTT beyond life of the programme. | DFID
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | DFID to consider a limited strategic engagement with KUSP for upto 2 years as a TA support, after completion of the FA support. | DFID
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | 0
R2 | 0
R3 | 0
Project Management
R1 | 0
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | Continued TA support to KUSP CMU beyond March 2011 towards overcoming barriers on tenure security provision to slum dwellers may be considered by DFID. | DFID Task Team Leader and Secretary MA, GoWB
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | DFID may consider limited TA to KUSP to support preparation of 2nd generation DDPs. | DFID Task Team Leader
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Limited TA support should include a component on sustaining and strengthening PFM functions at the ULB level. | DFID Task Team Leader
AP1.2 | 0 | DFID Task Team Leader
AP1.3 | 0
AP2.1 | 0
AP2.2 | 0
AP2.3 | 0
AP3.1 | DFID to approve retaining of this amount by March 2011. | DFID Programme Manager
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | DFID India senior management to take a decision on this. | DFID Programme Manager
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3