Project Completion Review

Title: Supporting Effective Democratic Governance
Final Programme Value £ (full life): / £9.3m (DFID contribution), £10.5m (FCO contribution)	Review Date: / June 2018
Programme Code: / 204757	Start Date: / 1 April 2015	Final End Date: / 31 March 2018

Summary of Programme Performance

Year	2016	2017	2018
Programme Score	A	A	A
Risk Rating	Moderate	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5080269.odt
DevTracker Link to Log-frame:	http://iati.dfid.gov.uk/iati_documents/5080297.xlsx[1]
[1] NB – the version of the logframe accessible via this link is the original version accompanying the Business Case and referenced in year 1 of the Annual Review. WFD have since updated the logframe to amend the wording of indicator 5.2, and add a further indicator under Output 5 (see Section B). The current Review is based on this modified version of the logframe.

List of Acronyms

CA	Context Analysis
CBO	Community-Based Organisation
CPA (UK)	Commonwealth Parliamentary Association (United Kingdom)
CSO	Civil Society Organisation
DFID	Department for International Development
EMC	Executive Management Committee (WFD)
FCO	Foreign and Commonwealth Office
IDC	International Development Committee
MENA	Middle East North Africa
MP	Member of Parliament
MPO	Multi-Party Office
M&E	Monitoring and Evaluation
NAO	National Audit Office
NGO	Non-Governmental Organisation
NDPB	Non-Departmental Public Body
PAC	Public Accounts Committee
PBO	Parliamentary Budget Office
PFO	Public Financial Oversight
PPO	Political Party Office
PPP	Purchasing Power Parity
PWD	People with Disability
RAC	Risk Audit Committee
SNP	Scottish National Party
ToC	Theory of Change
TWP	Thinking and Working Politically
TR	Tailored Review
UK	United Kingdom
VfM	Value for Money
VAWP	Violence Against Women in Politics
WFD	Westminster Foundation for Democracy

## A. SUMMARY AND OVERVIEW

Description of programme and what it has achieved
Supporting Effective Democratic Governance was a 3 year programme providing £9m to the Westminster Foundation for Democracy (outputs 1-4 below), and a small fund for DFID to support research and evaluation on democratic governance (output 5). DFID funding to WFD was provided alongside £10.5m from the Foreign and Commonwealth Office (FCO). WFD is a non-departmental public body sponsored by the FCO.
The Westminster Foundation for Democracy (WFD) has met expectations.
WFD supported changes in parliamentary and political party practice in many countries, including training young parliamentarians in Nigeria in skills to inform national policy development, developing post legislative scrutiny in Pakistan as a tool for parliament, and encouraging parties in Sierra Leone to include disability in their manifestos.
WFD also fostered processes to increase women’s participation in politics, including changes to voter registration periods to increase women’s participation in elections in Sierra Leone and bringing parliamentarians, academics and women activists together at a high-profile conference in London on violence against women in politics.
WFD has 27 country offices and operates programmes in around 40 countries. WFD provides sub-grants to four UK Political Party Offices (PPOs)[2], which manage programmes to strengthen ‘sister’ parties. The PPOs operate programmes which reach about 40 more countries (although often through regional networks). The expansion of programmes and the broad geographical spread have posed significant challenges to some parts of the organisation (notably financial management and monitoring and evaluation (M&E)), particularly in Year 2 and Year 3 of the programme. Some of these challenges have already been addressed through new roles/recruitment, while others (such as new finance and M&E reporting systems) will need to be carefully managed in the planned new programme.
[2] The Conservative Party, the Labour Party, the Scottish National Party, and a Multi-Party Office (MPO).
WFD has sought to analyse the political context of its programmes more comprehensively and to use its analysis to support programme implementation. It has had some success in doing so, but both programme teams and other stakeholders suggest that there is still scope to improve the relevance of this analysis.
WFD’s research programme has performed well in linking academic research to policy implementation, both externally and to inform WFD’s own programming.
UK parliamentary and HMG personnel have generally seen WFD as an effective partner over the life of the programme, although there is scope to improve communication and co-operation further in-country.
The programme also supported the Secretariat of the Thinking and Working Politically Community of Practice, hosted by the University of Birmingham, to carry out research and analysis on how best to support effective governance (see Output 5 below). This work was positively evaluated by independent external review.
Summary of outputs
On Output 1, WFD supported parliaments to apply learning in the areas of gender, financial management, committees, research, anti-corruption and tax, social media outreach, and legislation. WFD was able to demonstrate numerous instances of changes resulting from interventions but missed the target set for the number of instances where MPs or staff apply relevant principles of parliamentary practice. WFD met the target for increasing women’s political participation, including some strong examples of success in this area. WFD’s support for political parties included initiatives integrated with parliamentary programmes, and multi-party and bilateral sister party programmes led by the UK Political Party Offices. After a slow start, WFD exceeded their target for political parties. Concerns remain, however, about WFD’s ability to demonstrate the value for money of the political party work in particular, and about levels of transparency - acknowledging that this type of work is often locally sensitive. Overall, WFD met Output 1, with some good achievements and beneficiaries’ feedback on the general quality and usefulness of support was positive. Met expectation.
On Output 2, WFD exceeded its target for providing new support to regional and thematic networks, helping to establish and formalise networks in regions including the Middle East, Africa and the Western Balkans. However, this support did not translate into many tangible examples of networks successfully advocating on policy issues at national level. This was partly because WFD co-funded some of its network support with other donors, meaning that the outputs cannot be attributed fully to the DFID/FCO grant. WFD should review whether the level and duration of its support for such networks is sufficient, or whether a change of approach would provide more effective and sustainable support.. Moderately did not meet expectation.
On Output 3, brokered relationships and political space, WFD organised network events on topics including human rights and the cost of politics, and facilitated cross-party/cross-institutional dialogue on women in politics, constitutional reform, and transparency in oil, gas and other extractives. However, WFD struggled throughout the programme to meet its intended aims of brokering and enhancing civil society organisations’ access to parliament. Moderately did not meet expectation.
On Output 4, WFD has produced a large number of context analyses over the life of the programme. However, based on a reworded indicator definition introduced in 2016/17, WFD did not produce the required number of ‘second-generation’ context analyses by the end of the programme. WFD programme staff are generally positive about the quality and usefulness of these documents, although some suggested that that they do not cover all relevant topics in the required depth. Conversely, some programme staff suggest that lengthy and labour-intensive context analyses are not proportionate to the relatively modest scale of WFD programmes, and that a more iterative approach, that is responsive to change, would be preferable. WFD is reviewing its approach to context analysis, with a view to addressing these issues through a revised format going forward. Moderately did not meet expectation.
On Output 5, WFD has been producing high-quality research and policy analysis, exceeding the expected number of outputs, and generating strong awareness in the sector. Feedback from expert stakeholders on the quality of this work has been predominantly positive, albeit with the suggestion that more funding and longer timeframes would offer greater scope for deep analysis and engagement - which would in turn increase quality and impact. Although there is some recent evidence that WFD research is directly supporting the design and implementation of its activities, this is chiefly anecdotal at present, and mainly relevant to programmes starting in the next programming period, currently at planning stage. Moderately exceeded expectation.
Summary of Recommendations
R1. WFD should ensure as far as possible that it tailors its political party support to the wider political and cultural context, and identifies the most appropriate and effective type of intervention.
R2. WFD should continue to improve monitoring, evaluation and learning, and demonstrate improved value for money, particularly in relation to political party strengthening work.
R3. WFD and DFID should implement the recommendation made in previous Annual Reviews to understand poor performance against indicator 2.2 on networks. They should also consider introducing new indicators covering project sustainability, ideally covering not just the existing financial or in-kind contributions by beneficiaries, but actual benefits achieved by programmes once initial WFD support has ended.
R4. WFD and DFID should reconsider the planned ‘network of UK-based democracy assistance providers’, and decide what format, membership and performance metrics would best support this policy priority going forward.
R5. WFD and DFID should discuss the reasons for the programme’s underperformance against indicator 3.2 (working with civil society), and identify how it can be addressed as part of future programming and log-frame design. This should include a consideration of whether WFD’s assumptions and intervention logic with regard to CSOs are aligned with the actual capacity and maturity of the CSO sector on the ground.
R6. WFD should continue to review its approach to context analysis and consider the optimal balance between detail and specificity, and cost and usefulness. WFD should consider how to support greater use of analysis across the organisation to design programmes that are relevant, responsive, and well-adapted to local political context.
R7. WFD should revisit its assumptions regarding possible VfM metrics. In particular, it should acknowledge that macro-economic / population-level indicators are not suitable for measuring the effectiveness of its programmes, and instead focus on process and activity-based metrics of efficiency and cost-effectiveness. It should also consider how to capture and report its performance with regard to equity.
R8 WFD should consider including ‘benefits-in-kind as a percentage of total expenditure’ as a VfM indicator for benchmarking individual programmes or country offices.
R9. WFD should review the effectiveness of individual programmes and WFD country offices and seek to understand why some are more cost-effective than others.
R.10 WFD should provide more evidence of documented success stories and strong examples of political party work in particular.
R.11 WFD should review its business model to determine whether its current emphasis on growth and reach is likely to deliver strong outcomes, compared to more focused and deeper engagement in fewer countries. We recommend that the FCO’s next Tailored Review, due late 2018, examines this issue.
R.12 WFD should review how to further strengthen its management of overseas funds, following findings from the NAO and internal audits. DFID should share its internal guidance on Aid Diversion as an additional resource.

Note
This Project Completion Review was carried out by external consultants Moore Stephens LLP, commissioned by the WFD Monitoring and Evaluation Steering Committee on behalf of DFID. There was feedback and detailed engagement from Westminster Foundation for Democracy (including a party representative), the Foreign and Commonwealth Office, and the Department for International Development. Responsibility for the overall review, including final edits and scoring, is held by the Department for International Development.

## B: DETAILED OUTPUT SCORING

Output Title	Parliaments and parties where WFD works apply relevant lessons, including from British democratic experience
Output number per LF		1	Output Score	A
Impact weighting (%)?		40	Impact weighting % revised since last AR?	No

Indicator(s)	Targets[3]	Progress[4]
1.1 Number of instances where MPs or staff apply relevant principles to parliamentary practice	120	Moderately did not meet expectation. 100 instances (2016:13, 2017: 55, 2018: 32) including the Kenyan parliament using UK principles for the induction of its Speaker, MPs and support staff; young parliamentarians in Nigeria using skills learned from WFD to inform national policy development; and the National Assembly in Botswana designing job specifications for staff using processes and principles learned via WFD.
1.2 Number of instances where political parties apply skills or lessons learned from interactions with UK sister party representatives	40	Moderately exceeded expectation. 42 instances (2016: 10, 2017: 13, 2018: 19), including Nicaraguan parliamentary candidates using campaigning approaches learned from the UK Conservative Party; political parties in Sierra Leone addressing disability issues in their manifestos following cross-party WFD support; and Social Democratic Party in Bosnia and Herzegovina consulting with young people on policy-making using approaches learned from the Labour party.
1.3 Number of instances where parties or parliaments develop policies or processes for increasing women's participation in politics	18	Met expectation. 18 instances (2016: 4, 2017: 6, 2018: 8), including changes to voter registration periods to increase women’s participation in elections in Sierra Leone, and implementation of a 25% quota for women in the Sri Lankan parliament.
[3] Final targets are cumulative, and hence subsume both the previous milestone figures for 2016 and 2017 and the in-year target for 2018.
[4] Reported outputs are cumulative, and hence subsume both the previous output figures for 2016 and 2017 and the in-year outputs for 2018.

Supporting narrative for the score
Output met expectation
Under indicator 1.1, WFD performed well in supporting MPs and parliamentary staff to apply relevant principles to parliamentary practice over the course of the programme. Performance tailed off somewhat in Year 3 resulting in WFD narrowly missing its overall target for this indicator. WFD explains this curve as due to the programme cycle, with some initiatives begun in Year 1 being closed in Year 3 and target outputs peaking in the second year.
Some examples under this indicator included that the Kenyan parliament applied UK-style induction processes for a new Speaker and newly elected MPs, drawing on advice from the Scottish Parliament Finance Scrutiny Unit. The Scottish parliament provided tools and knowledge to hold county-level services to account in important decentralised sectors such as water, health and education. The Mozambique parliament drew on WFD experience and expertise provided by the UK and Portuguese parliaments to implement a Parliamentary Budget Office. In Botswana, the focus was on improving communications between Parliament and its research staff, committee clerks and other information units. One direct result of this work was the National Assembly Clerk incorporating new job specifications and structures into the draft parliamentary budget. In Uganda, WFD supported the Parliamentary Forum on Youth Affairs through training on drafting and the use of the Human Rights Checklist - skills which the Forum put into practice in developing its national youth legislative agenda and strategic plan.
Under indicator 1.2, WFD moderately exceeded the target for beneficiaries applying lessons learned through political party support. Examples included the Youth Empowerment Programme in Nigeria, where beneficiary parties took part in a joint Labour- and Conservative-run workshop on youth policy and engagement, subsequently using the knowledge and skills they learned to draft party action plans and youth strategies. Conservative sister parties in Lebanon and Nicaragua used skills obtained from WFD training to shape their approach to grassroots campaigning and outreach, while the Social Democratic Party in Bosnia and Herzegovina consulted with young people on policy-making, using approaches learned from the Labour party. The Eastern Africa Green Federation developed its social media presence, website and candidate messaging using lessons learned from a WFD / Green Party media workshop, while the People’s Progressive Party in Uganda adapted its party messaging and campaign slogans for a by-election based on learning from a WFD / Scottish National Party (SNP) communication workshop.
As part of the WFD integrated programme in Sierra Leone, the UK Conservative and Labour parties ran a two-day workshop for sister parties, aimed at raising awareness of people with disabilities when developing manifestos. The attendees – the Sierra Leone People's Party, All People's Congress and National Grand Coalition – used the learning to include extensive coverage of disability issues in their 2018 election manifestos.
An independent assessment of the political party work (See Section G) found that the UK Political Party Offices’ sister party projects often only realised expected changes to a limited extent. The report recommended that multi-party programmes and those integrated with WFD’s parliamentary work had greater potential to affect the political system as a whole.
Under indicator 1.3, WFD met the required target. One example was in Sierra Leone, where WFD support to the All Political Party Women's Association cross-party group resulted in the voter registration period for the 2018 elections being extended in order to allow potentially disenfranchised (particularly female) voters time to register.
Beneficiaries interviewed told the reviewers that various appointments of women to senior political positions could be directly attributed to WFD’s influence, notably leadership and skills training provided by the Labour Party Office. For example, a former Chairwoman of Labour’s Women's Academy for Africa was appointed as Deputy Minister of Foreign Affairs and later Minister of Sports in Mozambique, and a woman was appointed as a minister in the new government of the Democratic Party of the Chadian People. In Pakistan, a recipient of WFD leadership support and training became the first female to deputise for the Speaker in the Provincial Assembly of Punjab, as well as a key instigator for increasing the legal age for marriage from 16 to 18 years.
Lessons identified this year linked to this output and recommendations for future programmes
Media (and particularly social media) are a potent and growing means of achieving voter engagement – particularly among potentially disenfranchised groups. Political party beneficiaries find the media and social media training provided by WFD particularly useful, and have expressed a strong desire for more. That said, some noted that the de facto impact of such skills is limited in regions where electoral systems and associated media do not support transparency and due process, and where citizens may fear persecution or reprisals for explicit association with opposition parties.
Some beneficiaries suggested that pursuing a women’s rights agenda in some regions may be incompatible with working directly with local party leaders, since the latter may themselves be opposed to greater political participation by female members, even in their own party. WFD should consider how to provide more direct support to women on a cross-party and network basis, rather than via the (predominantly male) leadership of individual parties.
Recommendations
R1. WFD should ensure as far as possible that it tailors its political party support to the wider political and cultural context, and identifies the most appropriate and effective type of intervention.

R2. WFD should continue to improve monitoring, evaluation and learning, and demonstrate improved value for money, particularly in relation to political party strengthening work.

Output Title	Support to or creation of dynamic regional peer-to-peer networks that address thematic priorities
Output number per LF		2	Output Score	B
Impact weighting (%)?		20	Impact weighting % revised since last AR?	No

Indicator(s)	Targets[5]	Progress[6]
2.1 Number of networks provided new or additional support to advance thematic priorities or strengthen regional cooperation.	10	Substantially exceeded expectation. 20 networks provided with new or additional support. (2016: 5, 2017: 7, 2018: 8), including integration of Mozambique in the African Network of Parliamentary Budget Offices; SNP support to the cross-party Ra’edat women’s regional network; and the Conservative party supporting establishment of a centre-right regional Western Balkans Network.
2.2 Number of instances where issues championed by networks translate into policy proposals advocated at the national level	15	Substantially did not meet expectation. 8.5 instances (2016: 3, 2017: 2.5,[7] 2018: 3[8]), including establishment of a Macedonian Parliamentary Budget Office influenced by the Balkan Network of Parliamentary Committees, and advocacy of legislative changes regarding disability rights and poverty eradication (also in Macedonia).
[5] Final targets are cumulative, and hence subsume both the previous milestone figures for 2016 and 2017 and the in-year target for 2018.
[6] Reported outputs are cumulative, and hence subsume both the previous output figures for 2016 and 2017 and the in-year outputs for 2018.
[7] One output by the MENA Women programme was partially attributed (0.5) to the DFID/FCO core grant, since the programme was part-funded by Magna Carta at the time.
[8] One output by the MENA Women programme and two outputs from the Macedonia Parliamentary programme were included in the count. These programmes are funded partly from the core DFID/FCO grant and partly from other sources (The FCO’s Magna Carta fund and European Union funding respectively). Hence a proportion of their total relevant outputs are included in the counts above, equivalent to the percentage of their total funding covered by the DFID/FCO grant.

Supporting narrative for the score
Output moderately did not meet expectation
WFD has performed strongly in providing new and additional support to networks against indicator 2.1. In Mozambique it supported the integration of the Unit for Economic, Financial and Budget Studies in the African Network of Parliamentary Budget Offices. Other examples of successful network activity relate to WFD’s political party programmes. Examples include Conservative Party support to the Southern African Development Community network, including a workshop in London, leading to the signing of Memoranda of Understanding between the Conservative Party and the network Chair and individual member parties. The Conservative Party also supported sister party representatives from Bosnia and Herzegovina, Albania, Macedonia and Kosovo to set up a centre-right Western Balkans Network, including establishing an Executive Board and signing bilateral Memoranda of Understanding. The SNP began to support the cross-party regional Ra’edat Network in the Middle East and North Africa (MENA) to advance the thematic priority of increased women's political representation.
Despite the strong performance in terms of providing initial support to networks under indicator 2.1, this has not translated fully into strong performance under indicator 2.2. There have been notable successes building upon previous groundwork – for example the final implementation of two separate pieces of legislation combatting rape in marriage and domestic violence, for which WFD-supported female MPs in the MENA region had advocated throughout this programming period. There have also been new instances of beneficiary networks advocating on policy issues with WFD support. However, these instances had either already been included in previous years’ indicator scores, or were partly or wholly funded by sources other than the DFID/FCO grant – so were only partly eligible for inclusion in reported performance for the PCR (see footnotes).
The reasons for the relatively weak performance under indicator 2.2 are not straightforward. The previous review recommended that WFD discuss with DFID the reasons why indicator 2.2 no longer appears well aligned with WFD’s de facto priorities and activities. However, this issue was not resolved before the end of the programming period, and no reprogramming or adjustment to log-frame targets was carried out during year 3.
Part of the explanation for the discrepancy is that WFD has transferred some programmes from the DFID/FCO grant to third-party funding, which means that benefits occurring after the transfer are not attributed to the DFID/FCO-funded support.
In addition, where networks become self-sustaining and are not given further support, WFD’s monitoring ends so that, again, longer-term benefits are not captured.
A number of WFD staff and beneficiaries told the reviewers that they felt that a longer funding period, ideally crossing the boundaries of the three-year funding cycle, would help to improve programmes’ effectiveness and sustainability in the longer term. Similarly, a number of WFD programme staff commented that WFD was spreading its resources thinly between many small projects, and that consolidating into a smaller number of larger-scale interventions might improve effectiveness overall (see also Section E).
Previous Annual Reviews recommended that WFD introduce metrics of sustainability for relevant programmes. However, in practice these metrics have been limited to the collection of data on financial or ‘in-kind’ contributions received from beneficiaries (see Section D below), which WFD considers a proxy for the extent to which beneficiaries are supporting or sustaining the network themselves. This data does not, however, throw light on whether activities (including networks) previously funded by WFD have continued to generate relevant benefits once the initial support has ended.
Recommendation
R3. WFD and DFID should implement the recommendation made in previous Annual Reviews to understand poor performance against indicator 2.2 on networks. They should also consider introducing new indicators covering project sustainability, ideally covering not just the existing financial or in-kind contributions by beneficiaries, but actual benefits achieved by programmes once initial WFD support has ended.

Output Title	Brokered relationships and political space for policy change amongst civil society, parties and parliament in or across countries
Output number per LF		3	Output Score	B
Impact weighting (%)?		20	Impact weighting % revised since last AR?	No

Indicator(s)	Targets[9]	Progress[10]
3.1 Establish an active network of UK-based democracy assistance providers	At least 8 events sponsored by network partnership and cooperating on one joint programme	Moderately did not meet expectation. 3 meetings held, following a change of format and approach to this network midway through the programme.
3.2 Number of instances where civil society organisations indicate that they have improved access to parliament	30	Substantially did not meet expectation. 17 instances (2016: 2, 2017: 7, 2018: 8), including a think tank gaining access to the Moroccan Health and Environment Committee, and the Lebanese Coalition for Good Governance of Extractive Industries obtaining access to the national Parliament.
3.3 Number of instances of substantive cross-party/cross-institutional dialogue on policy issues	50	Moderately did not meet expectation. 42 instances (2016: 7, 2017: 17, 2018: 18), including an international summit on Violence against Women in Politics, bringing together multiple parties and international organisations, civil society and academia; and a roundtable on women in politics in Slovenia, which brought together legislators, civil society and party activists.
[9] Targets are in-year only (2017/18) for indicator 3.1, and cumulative (i.e. subsuming 2015/16, 2016/17 and 2017/18) for indicators 3.2 and 3.3.
[10] Reported outputs are in-year only (2017/18) for indicator 3.1, and cumulative (i.e. subsuming 2015/16, 2016/17 and 2017/18) for indicators 3.2 and 3.3.

Supporting narrative for the score
Output moderately did not meet expectation
Indicator 3.1 was originally designed in response to the 2014 International Development Committee (IDC) inquiry into parliamentary strengthening,[11] which recommended that the UK democracy and parliamentary support sector should aim to coordinate its activities better and collaborate more effectively. In response, WFD and other stakeholders set up the Westminster Community of Practice, comprising the Commonwealth Parliamentary Association (CPA) UK, House of Commons and House of Lords Overseas Offices, and the Inter-Parliamentary Union, with the aim of organising relevant events, raising mutual awareness and facilitating joined-up working.
[11] https://publications.parliament.uk/pa/cm201415/cmselect/cmintdev/704/704.pdf
Originally, WFD and DFID expected that this Community of Practice would be the ‘active network of UK-based democracy assistance providers’ mentioned in the indicator wording, and that its meetings would constitute the outputs reported against this indicator. However, in practice, the membership and focus of the Community of Practice did not remain aligned to these original intentions, and it did not continue in its original form. It was instead relaunched in March/April 2017 as the Deepening Democracy Working Group, whose membership includes WFD, DFID, DAI, Global Partners Governance, International IDEA, Netherlands Institute for Multiparty Democracy, Coffey, Chemonics, Overseas Development Institute, CPA UK, and Democracy Reporting International. This group has met three times – i.e. significantly fewer than the eight prescribed by indicator 3.1 – and hence WFD has not met the indicator as originally conceived. However, WFD considers that reconstituting the group in this form has fulfilled the intended spirit of the output more effectively than if the network had continued to meet on its original basis, since it includes a more diverse and representative group of stakeholders from the democracy support community.
Regarding the requirement to cooperate on at least one joint programme (which also forms part of indicator 3.1), WFD has been collaborating with CPA UK on a Gambia programme[12] and (to a lesser extent) in Sierra Leone – which it ascribes partly to interaction in the context of the current Working Group. It has also been involved in bidding for other new work with partners, albeit with mixed success. WFD has a lead role managing and implementing a two-year, £4m FCO-led programme in 18 Commonwealth countries, in partnership with the CPA and the Commonwealth Local Government Forum.
[12] http://www.wfd.org/wfd-and-cpa-uk-together-for-gambian-national-assembly/
Regarding indicator 3.2, the relatively weak performance identified in the previous review continued into year 3 of the programme, with WFD substantially failing to meet its target for numbers of civil society organisations (CSOs) indicating improved access to parliament as a result of WFD interventions. The Theory of Change identified an assumption that ‘most CSOs lack the requisite skills/relationships to access and influence parties and parliament effectively’. Based on evidence from programme staff at HQ and in-country (notably in Mozambique and Sierra Leone), this assumption has proven correct – i.e. that a combination of training/capacity-building and brokerage activity would be needed to achieve the intended result. However, senior programme staff suggested that WFD may not have struck the right balance between these two elements, having initially overestimated the maturity and capacity of the CSO sector in some countries. With hindsight, greater efforts to first build CSO capacity and capability before attempting to broker parliamentary access might have been more effective.
The 2017 Annual Review recommended that, should WFD choose to maintain its focus on civil society access in future, it should consider at the context analysis and design stage whether the local CSO sector is mature enough to take advantage of opportunities for access, or whether initial capacity building might be a more appropriate intervention given the baseline position. This recommendation still applies in 2018, and the start of the new programming period provides an opportunity for WFD to revisit its priorities and approach to civil society engagement going forward.
Despite these issues, there were a few notable successes in facilitating CSOs’ access to parliaments. For example, the Lebanese Coalition for Good Governance of Extractive Industries acknowledged the role of WFD in facilitating access to parliament, and improving the dialogue and relation between national CSOs and Parliament. In Uganda, WFD ran four platform meetings to facilitate access to parliament by citizens and civil society, resulting in parliamentary motions to pursue the issues raised. In Morocco, WFD facilitated access by the Dar al Khibra think tank to the Health and Environment Committee, who adopted a suggestion made by the organisation in a policy paper on medical supplies.
Under indicator 3.3, despite year-on-year growth in fostering cross-party and/or cross-institutional policy dialogue over the life of the programme, WFD very narrowly failed to meet its final target for this indicator. There were nonetheless many examples of successful multi-lateral dialogue facilitated by WFD and its partners – notably through political parties operating on a cross-party basis. One high-profile example was a London-based conference on Violence Against Women in Politics (VAWP) organised by the Multi-Party Office in March 2018. WFD leveraged the support of all seven political parties in Westminster to bring together speakers from over 20 countries, including UK political figures, international activists, experts and academics. This event will lead to a report with concrete actions and recommendations on how political parties and systems can tackle violence against women who want to engage in politics.
Other notable examples of political parties facilitating dialogue included a workshop on regional government and decentralisation organised by the Multi-Party Office in Ukraine, and a forum in Uganda on policy issues of climate change, including parties, civil society representatives and the media, and brokered by the Green Party and Eastern Africa Green Federation . Similarly, the Labour party organised a round table event on women in politics in Slovenia, bringing together legislators, civil society and party activists to identify ways of furthering the role of women in their parties and across the region.
Recommendations
R4. WFD and DFID should reconsider the planned ‘network of UK-based democracy assistance providers’, and decide what format, membership and performance metrics would best support this policy priority going forward.
R5. WFD and DFID should discuss the reasons for the programme’s underperformance against indicator 3.2 (working with civil society), and identify how it can be addressed as part of future programming and log-frame design. This should include a consideration of whether WFD’s assumptions and intervention logic with regard to CSOs are aligned with the actual capacity and maturity of the CSO sector on the ground.

Output Title	Effective use of political context analysis by WFD
Output number per LF		4	Output Score	B
Impact weighting (%)?		10	Impact weighting % revised since last AR?	No

Indicator(s)	Targets[13]	Progress[14]
4.1 Number of countries with a completed context analysis	30 second-generation political context analyses that analyse the environment in order to develop a regional strategic plan of action for current and future programming	Substantially did not meet expectation - 27 CAs, but not all second-generation (12 new second-generation CAs,[15] 2 new first-generation CAs,[16] 10 updated first-generation CAs,[17] 3 other first-generation CAs adapted to new template.[18])
4.2 The extent to which parliamentary, political party and integrated project objectives align and respond to analysis, as judged by WFD internal review processes and independent external evaluation	WFD programmes can produce a full record of revisions to context analysis over life of the programme and of programmatic responses to those revisions	Moderately did not meet expectation - Programme teams report strong alignment between CAs and programme design and objectives; mixed evidence as to whether programmes are using analysis to inform programming, and updating CAs over life of programme.
[13] Target for indicator 4.1 is cumulative (i.e. subsuming 2015/16, 2016/17 and 2017/18).
[14] Reported outputs for indicator 4.1 are cumulative (i.e. subsuming 2015/16, 2016/17 and 2017/18).
[15] Venezuela, Kyrgyzstan, Moldova, Ukraine, Nigeria, Myanmar, Kosovo (already counted in 2016/17), plus Laos, Sri Lanka and Sierra Leone (new in 2017/18). ), Bosnia Hercegovina, multi-party office Serbia Political Context Analysis
[16] Venezuela, Montenegro.
[17] Uganda, Sierra Leone, Tunisia, Sri Lanka, Moldova, Myanmar, Serbia, Pakistan, Jordan, Indonesia.
[18] Kenya, Ghana and Nigeria.

Supporting narrative for the score
Output moderately did not meet expectation
In Quarter 1 of 2016/17 WFD identified the need for two different types of context analysis – ‘first-generation’ and ‘second-generation’.[19] This resulted in an amendment to the milestone / target wording for indicator 4.1 in the corporate log-frame – from ‘20 [Year 3: 30] political context analyses that analyse the environment […]’ to ‘20 [Year 3: 30] second-generation political context analyses that analyse the environment […]’. As a result of this change of wording, WFD failed to meet the required milestone for this indicator in Year 2.[20] Although it had produced 22 CAs (some written from scratch and others updated from year one), the number of actual ‘second-generation’ CAs (seven) fell short of the prescribed milestone of 20.
[19] The current definitions used by WFD state that ‘first-generation’ context analyses seek to provide sufficient baseline macro-level information about a country and its parliament’s democratic status to begin a programme’s inception phase, while ‘second-generation’ analyses focus on a micro-level aspect of a parliament’s operation to answer identified programmatic questions emerging during the inception phase. However, WFD states that its main intention in rewording this indicator was to ensure CAs were fit for purpose, and that ‘second generation’ should simply mean that the CA is an improvement on the previous version - not that it should necessarily have a different scope or focus. This led to some uncertainty in assessing performance against this indicator in Year 2.
[20] 7 new second-generation CAs, 2 new first-generation CAs, 10 updated first-generation CAs, 3 other first-generation CAs adapted to new template.
To address this issue, WFD set up a small technical advisory unit to support its parliamentary adviser and country representatives in producing CAs, with the aim of allowing WFD to maintain and improve CAs’ quality and comprehensiveness. This also helped to keep pace with demand, particularly given the rapid growth in the number and spread of programmes in 2016/17. The increase in capacity was also intended to allow WFD to recover ground against the more challenging ‘second generation’ wording of the milestone, and hence ultimately produce the requisite number of second-generation CAs by the end of Year 3. However, the total number of CAs as at the 31 March 2018 (including new ones identified for 2017/18) was 25, of which just ten were ‘second generation’ based on the criteria applied for this review. Hence WFD ultimately failed to meet the target of producing 30 ‘second-generation’ context analyses by the end of the programme.
With regards to the quality of CAs, the review team found a mixed picture – including the extent to which CAs were contributing to programme design and implementation, and being revised and reiterated during the life of the programme (as reflected in indicator 4.2).
For example, the reviewers’ survey of WFD programme staff in London and in-country found that just 56% (2017: 75%) of staff who expressed an opinion felt that the objectives and approaches of WFD’s programmes were adapted to the local context as set out in the CA. Although 79% (2017: 80%) of staff felt that CAs are sufficiently detailed and relevant in their coverage of the local political and legislative context, this figure dropped to 49% and 35% regarding coverage of local civil society and the media respectively (2017: 50% and 34% ). Indeed, 22% and 35% of staff (2017: 21% and 28%) actively disagreed that coverage of these two aspects was sufficiently detailed and relevant.
Overall, only 49% of programme staff who expressed an opinion agreed that the CAs contained the information necessary to support optimal implementation of WFD programmes, with 18% stating that they disagreed. Some of the reasons provided by respondents for the limited usefulness and relevance of CAs included:
- uncertainty as to their intended purpose, leading to them being treated as a ‘box ticking’ exercise rather than being actively linked to country, regional or organisational strategies;
- uncertainty as to who is responsible for maintaining and updating the CA, and when ‘ownership’ passes from Technical Advisory Unit (TAU) staff to country teams – meaning that the CA does not always remain a ‘live document’, even if country teams are gathering relevant information on an ad hoc basis;
- linked to the above point, failure to revisit the CA during the life of projects, with programming being driven by brief initial analysis and the parliament’s stated priorities, rather than a dynamic and pro-active needs assessment by WFD;
- predominant focus on parliamentary structures, but with less coverage on how these interact with external factors and potential drivers of change;
- limited information to support engagement with local media and civil society organisations, and in some cases local government bodies;
- lack of consistent guidelines or templates to codify what a good CA should look like, and what information it should contain; and
- limited information on how local legislative processes work in theory and in practice.
The previous review also found that WFD should expand the prescribed content of CAs to include greater coverage of local civil society and media engagement, particularly in the case of ‘second-generation’ CAs for programmes where these elements are key prerequisites for successful implementation. This year’s Review suggests that WFD staff have not yet noted improvements in these areas, although this is not surprising given the lack of new programmes in Year 3, and hence the time required for such changes to feed through into large numbers of up-to-date CAs.
Lessons identified this year linked to this output and recommendations for future programmes
WFD has acknowledged that there is scope to improve its approach to context analysis, and has been working on developing an alternative during 2017/18. Activities have included a workshop and consultation with WFD staff, and research into how other organisations’ approach context analysis or political economy analysis (PEA). A key question has been whether WFD’s whether context analyses should continue to use the current lengthy format, developed chiefly at the start of the relevant programme, or instead use a more agile and iterative approach – initially mapping out key information only, and then maintaining a live document updated with relevant changes and learning on an ongoing and adaptive basis. The above feedback obtained from programme staff suggests that the latter option may be preferable going forward, particularly given resource constraints and the relatively small size of many of WFD’s programmes.
Recommendations
R6. WFD should continue to review its approach to context analysis and consider the optimal balance between detail and specificity, and cost and usefulness. WFD should consider how to support greater use of analysis across the organisation to design programmes that are relevant, responsive, and well-adapted to local political context.

Output Title	High-quality research and evidence informs support to democratic governance internationally
Output number per LF		5	Output Score	A+
Impact weighting (%)?		10	Impact weighting % revised since last AR?	No

Indicator(s)	Targets[21]	Progress[22]
5.1 Number of research outputs [papers, briefs, etc.] that generate findings on agreed topics.	40	Moderately exceeded expectation. 46 outputs (2016: 26; 2017: 8, 2018: 12) outputs, including 5 policy briefs, 4 applied research pieces and three journal articles.
5.2 Number of instances where international and donor community demonstrate awareness of research	20	Moderately exceeded expectation. 27 instances (2017: 13, 2018: 14[23]), including presentations at 10 conferences and other events, and four citations in specialist papers and fora.
5.3 The extent to which WFD programmes respond to and integrate research analysis and findings into their work, as judged by WFD internal review processes and independent external evaluation	WFD Research can demonstrate substantive programme design or implementation responses based on outputs	Met expectation.[24] Positive feedback from programme leads on research input, and 1 example of direct influence of output on design of new post-legislative scrutiny (PLS) programme in Pakistan.
[21] Final targets for indicators 5.1 and 5.2 are cumulative, and hence subsume both the previous milestone figures for 2016 and 2017 and the in-year target for 2018.
[22] Reported outputs for indicators 5.1 and 5.2 are cumulative, and hence subsume both the previous output figures for 2016 and 2017 and the in-year outputs for 2018.
[23] NB – comparable figures for year 1 (2016) are not available, as the number and wording of these indicators was altered as part of updates to the logframe in August 2016. Indicator 5.2 was amended (from ‘Number of instances where research is used by international and donor community’ to the current wording), and a new indicator (5.3) was added. The former change reflects WFD’s greater emphasis on outreach and engagement from 2016/17 onwards, while the latter recognises that WFD itself is a key potential user of this research in designing its own approach to programming and implementation.
[24] Note that this target is not quantified as a specific number of such instances, and the assessment is based on the agreed scope and approach of the Programme Completion Review (consisting of a limited sample of interviews, e-surveys and a document review).

Supporting narrative for the score
Output moderately exceeded expectation
Over the life of the programme, WFD has collaborated successfully with UK academia and other research stakeholders on a range of research and policy activities and papers. Although the definition of a research output under indicator 5.1 was adjusted after Year 1 to exclude blog posts, and the total number of required outputs across the three years was increased from 30 to 40, WFD nonetheless exceeded its overall target for this indicator. Notable examples in 2017/18 included a policy paper co-produced with the University of Birmingham, on Defending democracy - When do parliaments protect political space?; a joint study with the Ghanaian Centre for Democratic Development on The cost of politics in Ghana, and a journal article on The promise – and pitfalls – of collaboration with development organizations and policy makers in Africa.
Under indicator 5.2, there were numerous examples of the international and donor community being aware of WFD’s research. This manifested itself chiefly in invitations to present at events hosted by (among others) the German Development Institute, the European Consortium for Political Research, and the European Association of Development Research and Training Institutes, and in citations of published research in specialist for a such as blogs, books and reports.
Regarding indicator 5.3, the WFD Research team demonstrated several examples of joint working between WFD’s research programme staff and individual programme teams over the course of the programme – notably with the Africa team on the cost of politics in Ghana, and with the Multi-Party Office and the MENA team on decentralisation and political party systems. Moreover, 75% of programme managers and team members responding to the 2018 survey of WFD staff felt that the Research team supports their work ‘fairly’ or ‘very’ effectively. This is a positive result (although slightly lower than the 86% achieved in 2016/17), which suggests that WFD research is actively informing programmes to good effect. One concrete example of substantive influence on programme design is the current post-legislative scrutiny programme in Pakistan.
The four specialist research stakeholders surveyed by the review team were generally very positive about WFD’s research and policy outputs. All were aware of WFD’s policy papers and research events/conferences, and three agreed strongly that ‘WFD is a recognised source of policy-relevant evidence in the fields of parliamentary and political party strengthening’. Two respondents stated that the quality of the underlying work is ‘very good’, one that it is ‘good’, and one that it is ‘satisfactory’, and all four rated the usefulness of WFD’s research for sharing lessons and good practice among the donor and democracy assistance community as either ‘good’ or ‘very good’.
One significant difference between Year 2 and Year 3 related to the balance between academic research and practical policy implementation. In Year 2, respondents suggested that WFD should seek to improve the practical application of its research, for example by identifying further means of disseminating and operationalising its research among non-academic stakeholders (e.g. politicians / parliamentary partners, DFID, FCO and other policy-makers and implementers). However, in Year 3, respondents all agreed (two strongly) that ‘WFD research is an important source of knowledge and evidence for policymakers’, suggesting that this issue had to an extent been addressed. They were less convinced, however, that ‘WFD research is an important source of knowledge and evidence for academics’, with one suggesting that more funding and longer timeframes would offer greater scope for deep analysis and engagement – which would in turn increase quality and impact.
Most scores as to the value and approach of WFD research were very similar to those in the previous year, suggesting that its quality and relevance has been maintained despite a 21% reduction in spend on the research programme between Year 2 and Year 3 (2017/18: £405,096; 2016/17: £514,863).
Support for the Thinking and Working Politically Community of Practice:
In addition to WFD’s activities, the programme separately supported the Secretariat for the Thinking and Working Politically (TWP) Community of Practice between June 2017 and March 2018, hosted by the International Development Department at the University of Birmingham. The Secretariat’s modest workstream made a significant contribution, producing research and analysis to support innovation and the international community’s understanding of how best to support effective governance through TWP approaches[25], convening policy dialogues and workshops, and establishing four working groups[26] to continue to advocate and learn from TWP approaches internationally. These outputs were positively evaluated by independent external review conducted by Oxford Policy Management.[27]
[25] https://twpcommunity.org/learning
[26] (1) Democracy Assistance Working Group (led by WFD), (2) Washington DC Working Group, (3) Anticorruption Working Group, (4) Monitoring, Evaluation and Learning Working Group.
[27] The review identified key strengths of the CoP and Secretariat as (1) creating and maintaining safe spaces to enable honest discussion and learning, (2) development of working groups and encouraging autonomy to enable their growth and quality of work, and (3) the development of the website as a key resource for new members, as well as for existing ones. See Review of the Thinking and Working Politically Community of Practice, OPM, 2018.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved
The intended outcome of the programme is: “Democratic culture and practice in parliaments and political parties that will support inclusive and effective governance.” Four outcome indicators contribute to this overall measure:
1. Policy. The extent to which public policies are formulated or drafted or scrutinised by parliaments or political parties based on evidence and an open, transparent and consultative process. This measures outcomes accomplished by parliament or within parties.
2. Accountability. The extent to which parliaments or political parties hold other government institutions or actors to account or enhance their own accountability to their constituents and stakeholders. This measures outcomes achieved by parliament or within parties.
3. Representation. The extent to which parliaments or political parties represent effectively their specific constituencies and are representative of the interests and needs of their citizens as a whole. This measures outcomes observed by parliament or within parties.
4. Citizen participation. The extent to which citizens, particularly women, youth or other marginalised groups, have greater access to and a more active role in parliamentary and political processes. This measures outcomes observed by parliament or within parties.
The current PCR does not attempt to analyse outcomes quantitatively, but rather provides a qualitative overview of performance against each of the four outcome targets, based on a detailed document review and interviews with WFD staff and stakeholders. Five countries – Kenya, Kyrgyzstan, Mozambique, Pakistan and Nigeria –were selected for in-depth enquiry as part of this year’s work.
Policy – the development of a budgetary office in Mozambique is the stand-out example which has attracted sufficient resources, staffing and standing among parliamentarians to make a valuable contribution. However, it remains early days, with the official launch only in May 2018. In other cases, WFD has been able to develop important new skills in policy-making among citizen groups – for example in Macedonia by working with the university and a range of NGOs to enable them to contribute effectively to specialist committees in health and women’s representation.
Accountability – the scrutiny and oversight of public accounts are traditionally strong aspects of WFD work. Examples include in Pakistan the development of post legislative scrutiny. This has proven to be a very useful tool for parliament, which has the full backing of the Speaker of the National Assembly (who was introduced to UK and French practice during recent visits). In Kenya, WFD has found particular traction through working with county-level administrations following decentralisation of key services in health, education and agriculture. Similarly, in Kyrgyzstan the emerging focus on local government structures in Bishkek and three other cities is promising as a means of improving service level functions, and draws upon the UK and other experience by working with the Local Government Association.
Representation – this year the political parties have been particularly active in this area. The focus has been increasingly on building in-country capacity, with less reliance on traditional training or study tours to the UK. Notable contributions to this outcome include securing reforms in party policies in Bosnia and Herzegovina to increase numbers of female board members and election candidates; achieving changes in party structures to increase youth participation in Ecuador; and supporting female candidates to win parliamentary seats and ministerial positions in the Caribbean. In Kenya, WFD has helped to make the Senate more engaged with citizens through outreach activities, and more transparent and responsive to incoming queries via interactive social media. In Nigeria, WFD has increased the representation of young people in national politics, by strengthening youth platforms’ capacity to engage with political leadership and young people, and engaging leadership of political bodies to advocate youth participation.
Citizen Participation – in many cases, WFD’s work has been a by-product of other activities, for example interfacing with citizens only where necessary to ensure adequate representation of neglected minorities such as the rural poor. However, WFD is now using a more direct approach, particularly in Africa. For example, WFD supported Sierra Leone to register, familiarise and better record People with Disabilities, young people and women in the electoral process. In Nigeria, the Youth Empowerment Programme is also gaining traction working with youth, linking them with policy-makers in the UK and pushing for a greater say in parliament - for example through the ‘Not too Young to Run’ campaign. WFD has also employed more indirect methods such as working on traditional parliamentary systems, Rules of Procedure and legislative practice in Burma. There is some evidence that this approach is bearing fruit, with local government scoping opportunities to invite further participation of citizens.
The overall intended impact of the programme is that "Developing and transition countries provide inclusive and effective democratic governance for their citizens”. The two indicators for this impact in the corporate log-frame are:
i) Level of liberal democracy within countries where WFD works (as represented by the V-Dem Index[28]); and
[28] This index includes the following components 1. Media freedom, 2. Electoral quality, 3. Freedom of Expression, 4. Rule of Law and Individual Rights, 5. Judicial Constraints of Executive, 6. Legislative Constraints on Executive. The V-Dem Index was selected as it encompasses best the areas in which WFD works.
ii) Examples of WFD-supported parliamentary or political party reform yielding tangible positive outcomes for citizens (as represented by stories of change, drawing on qualitative methodologies of reporting).
It is not possible to establish the programme’s contribution towards this impact and its indicators. Although the potential linkages between the reported outputs (see Section B) and ‘positive outcomes for citizens’ are not too remote, demonstrating causality is extremely challenging. Moreover, making a meaningful and measurable contribution to this impact would likely require large-scale and long-term systemic interventions, addressing the many political, social and economic factors which underpin the V-Dem Index. WFD’s limited resources are currently spread thinly across a large number of small programmes and WFD mainly focuses its work on needs arising in parliaments and political parties.
WFD has made increasing efforts during the programme to analyse outcomes quantitatively, using country-specific ‘outcome matrices’ – effectively versions of the corporate log-frame designed and populated by country teams, with bespoke milestones scored from 0-4 serving as proxies for progress against overall outcomes. At an operational level, these outcome matrices are increasingly appreciated as a useful tool, with their intuitive nomenclature around levels of engagement (“Need to See”; “Expect to See”; “Like to See” and “Love to See”). However, the degree to which they are understood and applied in-country varies based on understanding and capacity. Any tool of this nature is dependent on not only setting realistic indicators of change, but then gathering the data to monitor progress and report back. In small operations of one or two staff coping with a sophisticated model, this is not feasible without additional capacity.[29]
[29] A good example of this is apparent in the Kenya programme Annual Report, which notes that there is often only partial evidence at any one stage of the matrix – for example, ‘use of research products by the Senate to inform policy’ shows some signs at the “need” and “expect” to see levels, but has not yet developed strongly enough to record signs at higher levels.
Hence although WFD now has outcome matrices and some data from all programmes in this format, there are wide variations in terms of both the quality / completeness of the data and the timeframes covered. This makes it difficult to conclude quantitatively on whether the programme has achieved its intended outcomes. This difficulty is compounded by the fact that the overall intended outcome of ‘Democratic culture and practice’ does not in itself have a finite endpoint or objective. Although the corporate log-frame theoretically reports quantitative progress against this outcome using an average of the underlying programme scores, in practice the variations in the quality and consistency of the underlying data limit the usefulness of the corporate-level outcome figures at this stage.
Summarise the programme’s Theory of Change (ToC) and major changes to it in the past year
The Theory of Change (ToC) has remained broadly unchanged throughout the programme, although there have been some small changes to the associated log-frame indicators and wordings (see Section B). The ToC is broadly as follows: if British MPs and experts provide knowledge about the British experience of parliamentary democracy and elections, technical advice to parliaments and political parties on rules/structural reform is provided, linkages are built with parliaments and political parties and other UK-based institutions, regional cooperation and south-south learning is supported, and evidence on good practice is shared, this will foster “democratic political systems in which parliamentary and political party dynamics promote inclusive and effective democratic governance”.
In practice, WFD draws upon a wider set of international experience including European and developing country partners in order to provide an appropriate match to needs - for example, the programme management office in Mozambique which included Portuguese experience, and the post-legislative scrutiny support in Pakistan which included France (with its bicameral parliament) as well as Westminster and the UK devolved parliaments.
A thematic evaluation of WFD’s political party assistance carried out in 2017/18 summarised the underlying ToC for this strand of the programme as follows: ‘WFD supports democratisation by sharing experiences from the UK political system. Political Party Offices at WFD provide capacity-building support (in particular training and peer support from UK politicians and party staff) which is meant to generate improved individual skills and the organisational development of separate parties. Networks are meant to support both individual and organisational objectives. Together, stronger, more accountable, representative and policy-based parties are assumed to offer more choice to citizens in elections. This should contribute to multi-party democracy.’[30]
[30] Laure-Hélène Piron and Halfdan Lynge-Mangueira, Evaluation of the Westminster Foundation for Democracy’s political party assistance, p. 4.
However, the evaluation also suggested that the inherent assumptions of this ToC (chiefly that capacity building will influence the behaviour of politicians, and that UK political experiences based on the Westminster parliamentary model will be relevant in the countries where WFD operates) did not necessarily hold true. This question mark as to the inherent effectiveness of the political party model also links to the concerns over visibility and value for money outlined in Section D and Section E below, and DFID/WFD are currently reviewing their approach to funding and implementing this strand of WFD’s work – potentially with implications for the ToC in future programming periods.
## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme
The total DFID/FCO-funded expenditure on the programme (both for Year 3 only and overall) is shown below:
Categories of expenditure (programmes / admin)	Expenditure / (1 April 2017 to 31 March 2018)	As % of total expenditure / (1 April 2017 to 31 March 2018)	Expenditure / (1 April 2015 to 31 March 2018)	As % of total expenditure / (1 April 2015 to 31 March 2018)
Political Party Programmes	2,309,235	33.0%	7,043,797	34.3%
Parliamentary Programmes	1,524,816	21.8%	4,866,115	23.7%
Programme Staff	1,168,371	16.7%	2,665,684	13.0%
Integrated Programmes	611,558	8.7%	1,797,818	8.8%
Research Programme	405,096	5.8%	1,129,147	5.5%
Security	12,646	0.2%	79,260	0.4%
Rapid Response	38,131	0.5%	165,430	0.8%
Corporate Staff Costs	813,996	11.6%	2,028,746	9.9%
Premises and Overhead Costs	603,169	8.6%	1,718,577	8.4%
Recovery Costs	- 494,231	-7.1%	-940,633	-4.6%
	6,992,787	100.0%	20,553,941	100.0%

Total programme expenditure for 2016/17 amounted to £6,992,787 of which the DFID contribution was £3,477,966 (49.7%). Total programme expenditure for the period of the programme (2015-2018) amounted to £20,553,941, of which the DFID contribution was £9,062,572 with an overall burden share of 44.1%. In the business case burden share was forecast at 46.2%.
Both in Year 3 and over the whole life of the programme, actual expenditure met the criteria prescribed in the original Business Case. For example, that over 70 per cent of the costs (including programme staff) should go on the political party, parliamentary and integrated programmes (Year 3: 80.3%, overall: 79.7%), and that overheads should be no more than nine per cent of total spend (Year 3: 8.6%, overall 8.4%).
WFD’s main cost drivers across its programmes are its field offices. These normally comprise 2-3 local staff, often located in parliament buildings (and hence potentially subsidised by an ‘in kind’ arrangement – see below). Field offices’ non-staff expenditure is chiefly on a planned schedule of activities and services directly procured by WFD (typically travel, accommodation, venue hire, specialist contractors, event expenses). WFD may delegate some activities (for example using a local civil society organisation to arrange and deliver a programme module), and in doing so seeks to apply its procurement standards. Direct procurement is also applied to M&E assessments, auditing, and programme publications.
The original business case for the programme proposed a number of metrics/proxies for economy, efficiency and effectiveness,[31] including:
[31] http://iati.dfid.gov.uk/iati_documents/5080269.odt, pp. 23ff.
1. the percentage of programme expenditure made up by premises/overhead costs (economy);
2. the monetary value of facilities/services provided to WFD free of charge, as a percentage of total programme expenditure (economy);
3. number or scale of projects per staff member (efficiency); and
4. improvements in growth, public services, stability or other areas which (if monetised) would cover or exceed the cost of the programme (effectiveness).
These VfM proxies remain conceptually valid, and in addition to its year-on-year analysis of a), since 2016/17 WFD has also been analysing data on b). Whilst collection and validation of the latter data from individual programme teams is time-consuming, it has allowed WFD to estimate that it received a total of £110,057 in such ‘benefits-in-kind’ in 2017/18, i.e. around 2% of the total annual budget for parliamentary, integrated and parties programmes. This compares favourably with the 1% predicted in the original business case, and – given that this amount was distributed across just 11 programmes – there is likely to be scope for further such cost savings in future. ‘Benefits-in-kind as a percentage of total expenditure’ could potentially be a useful VfM indicator for benchmarking individual programmes or country offices, and hence encouraging staff to seek further economies. For example, if all programmes receiving low or no ‘benefits-in-kind’ could increase these to the current average across the programme, WFD would achieve a further £77,000 cost savings per year.
This year’s review and discussions with the M&E team confirm that the most challenging VfM metrics and concepts from the original business case remain those related to effectiveness. It is extremely difficult to robustly capture and quantify the benefits of WFD’s interventions, and numerical indicators such as those reported in Section B above are at best a rough proxy for the benefits which WFD are aiming to achieve.
As outlined in the Year 2 Annual Review, one possible approach which can make use of existing data (albeit with caution) is a composite ‘cost-effectiveness’ metric, based on the number of validated log-frame outputs per £100,000 of expenditure, by programme (not including Outputs 4 and 5, since these are not project/implementation-specific but instead relate to context analysis and research).
Although the various activities making up the output figures are very diverse in scope and nature, they are nonetheless proxies for the WFD’s stated programme priorities, and hence can be considered a reasonable indicator with which to compare programmes’ performance against their costs. Moreover, the financial data can also be adjusted using ‘Purchasing Power Parity’ (PPP) indices to reflect the differential buying power of the pound in the different countries where the programmes are taking place. The effect of this adjustment is to reveal that some programmes are performing more cost-effectively than it might seem, since – because the cost of living is higher in some countries than others - in real terms they are spending less money to deliver these outputs than first appeared.
As in year 2, several programmes in particular appear to be generating a high number of outputs relative to their cost (e.g. Indonesia, the Gambia, Iraq), in some cases despite being in their first full year of implementation. This suggests one (or more) of several conclusions:
- These programmes are an especially good fit to WFD’s objectives, and hence particularly effective at achieving the outputs prescribed in in the corporate log-frame if implemented properly.
- Staff are delivering the programme in an especially effective, efficient or economical way, so that resources are used to optimum effect.
- Staff are particularly good at identifying and/or reporting ‘qualifying’ outputs in the course of implementation, particularly compared to their peers who may be delivering similar projects but with less of an eye for benefit realisation.
More detailed research and discussion with individual teams would be needed to understand which of these points applies in a given case. The same applies to the programmes which have not contributed to WFD’s output targets over the life of the programme, despite incurring significant expenditure.
A new fourth ‘e’ has been introduced to the DFID VfM framework since the start of the programme, namely equity. Equity is a key principle underpinning WFD’s activity, for example with regard to gender balance and access to parliamentary structures and representation. There is wide qualitative evidence of WFD’s work supporting this agenda – for example, in Sierra Leone where WFD has pioneered the inclusion of People with Disabilities (PWDs) in elections, and in Morocco, where the WFD parliamentary programme has led to the adoption of new rules and procedures in the Lower House, resulting in at least a third of key roles in the political bureau and standing committees being held by women.
Individual programme teams usually collect some information on the profile of participants accessing interventions such as workshops and training. However, WFD does not routinely collect comprehensive and granular output and outcome data which would allow it to assess whether results are equitably distributed across different beneficiaries (for example by gender, disability or social group). This is particularly true of wider societal benefits resulting from WFD interventions, which - as with WFD’s work on disability awareness in Sierra Leone - can potentially improve outcomes for ‘indirect’ beneficiaries from minority groups. For example, the 2018 thematic evaluation of citizen participation in WFD programmes found a range of awareness-raising and equity initiatives around access to parliament, but concluded that WFD needs to build a stronger evidence base to demonstrate how such initiatives can improve prospects for disadvantaged groups. This needs to be part of a wider discussion about how DFID and its partners can explore, analyse and demonstrate equity not just anecdotally / qualitatively, but also quantitatively – and in a way which robustly links resources, outputs and outcomes to the ‘four ‘E’s’ as part of a consistent VfM framework.
Value for Money Statement
Although the programme as a whole has ultimately fulfilled the VfM proposition set out in its original business case (i.e. delivering most of its planned outputs to budget), there is clearly scope to improve the consistency with which programmes are delivering the prescribed outcomes (and hence VfM), and/or the reporting and monitoring systems whereby such instances are captured (i.e. management’s ability to measure and optimise VfM).
Recommendations
R7. WFD should revisit its assumptions regarding possible VfM metrics. In particular, it should acknowledge that macro-economic or population-level indicators are not suitable for measuring the effectiveness of its programmes, and instead focus on process- and activity-based metrics of efficiency and cost-effectiveness. It should also consider how to capture and report its performance with regard to equity.
R8 WFD should consider including benefits-in-kind as a percentage of total expenditure’ as a VfM indicator for benchmarking individual programmes or country offices.
R9. WFD should review the effectiveness of individual programmes and country offices and seek to understand why some are more cost-effective than others
## E: RISK

Overview of programme risk
Overall risk rating: Major
The programme risk rating was raised to major following the second annual review which found that the wide geographic scope and resulting thin financial spread of WFD’s work could undermine delivery at country level. The value for money of the political party work in particular needed strengthening. There was also some uncertainty over WFD’s delivery chain and pressure on central financial and management capacity due to the pressure of WFD’s rapid expansion and the growth in its sources of funding.
The programme ultimately delivered moderately successfully on the outputs foreseen in its log-frame. However, the high risk of delivery through WFD’s programme model continued throughout the programme. This was largely due to the complexities of securing a democratic culture and practice in challenging environments, and the fact that governance and parliamentary work is prone to uncertainties and unforeseen factors.
Concerns emerged over some aspects of WFD’s delivery chain – in particular, the management of the small proportion of funds that the political party offices grant to their partners or beneficiaries in-country. WFD’s internal auditors, BDO, carried out a review of Political Party Offices’ controls in September 2017, examining arrangements for programme procurement (including engagement and use of sub-contractors), budget monitoring, claims and anti-fraud/bribery controls. The level of assurance the audit was able to give was moderate in respect of the design of the controls and their operational effectiveness. Overall the audit found that the design of the relevant controls was generally sound (albeit with scope for improvement), and that their operation was generally satisfactory – but with some evidence of non-compliance which could pose risks to the fulfilment of objectives.
Further risks relating to management of overseas funds were identified by the NAO statutory audit of WFD in 2016/17. These included lack of oversight of all individual bank accounts held overseas (some of which had been opened by individual staff members in order to avoid the delays of establishing a WFD business account), and incorrect postings of cash receipts and the recognition of expenditure at the field offices, which had not been reflected in the Head Office General Ledger. Although the amounts involved are relatively small (<£200k across the entire programme), it is important that WFD central finance uses its increased capacity and links to field offices (particularly via finance business partners ) to address the associated risks to regularity.
Beyond potential issues with regularity of expenditure, DFID considers that more transparency is needed of the VfM of WFD’s political party work, particularly with regard to evidencing the effectiveness and sustainability of the relevant interventions. WFD’s annual reporting, as well as the associated data review and validation for the Annual Reviews and PCR, provides some evidence of individual outputs. However, it provides only limited evidence of wider impacts or sustainability (see also Section D). DFID has therefore tasked WFD with providing more evidence of documented success stories and strong examples of political party work in particular, while acknowledging that work in this area may be particularly sensitive.
More broadly, there are also risks that the wide geographic scope and resulting thin financial spread of WFD’s parliamentary strengthening work could undermine the delivery of strong, sustainable outcomes and change at country level (see also Section C). DFID considers that WFD needs to consider how best to distribute its resources and activities to optimise effectiveness going forward.
WFD’s Risk Audit committee (RAC) carried out an in-depth review of risk management arrangements in 2017/18, aimed at identifying and managing risks to achievement of WFD’s new strategy. This included a workshop (to which the Board was invited), where RAC members and management identified strategic and operational risks. WFD also undertook a major review of its corporate risk register, updating and rationalising the risks. WFD’s internal auditors have judged the level of risk affecting its corporate systems to be low or moderate, although with some significant issues to be addressed around business continuity planning and local office security arrangements. Remedial work to implement the auditors’ recommendations and mitigate these risks is currently in train.
Recommendations
R.10 WFD should provide more evidence of documented success stories and strong examples of political party work in particular.
R.11 WFD should review its business model to determine whether its current emphasis on growth and reach is likely to deliver strong outcomes, compared to more focused and deeper engagement in fewer countries. We recommend that the FCO’s next Tailored Review, due late 2018, examines this issue.
R.12 WFD should review how to further strengthen its management of overseas funds, following findings from the NAO and internal audits. DFID should share its internal guidance on Aid Diversion as an additional resource.

## F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Expenditure from 1 April 2015 – 31 March 2018
	Agreed budget (DFID contribution)	Actual expenditure / (DFID contribution)	Carried forward	Variance %
Year 1	2,500,000	2,364,218	(135,782)	-5.4%
Year 2	3,250,000	3,220,388	(29,612)	-0.9%
Year 3 (Revised budget) [32]	3,325,000	3,477,966	152,966	+4.6%
TOTALS	9,075,000	9,062,572	(12,428)	-0.1%
[32] The original DFID-funded budget for Year 3 of the programme was £3,250,000. DFID and WFD agreed an extension of this amount to £3,325,000, to include an additional £75,000 for three thematic evaluations (see Section G, below) carried out in Quarter 3 and 4 of 2017/18. WFD’s actual spend against this additional budget was £70,996. The remaining balance is to be spent on further evaluation activities in 2018/19.

April 2017 marked the start of the third and final year of the accountable grant period. The total budgeted DFID contribution for the three years was £9,000,000, which was increased by £75,000 to cover three additional thematic evaluations carried out in Q3 and Q4 of 2017/18 (see Section G). Total DFID-funded programme expenditure for 2017/18 amounted to £3,477,966. This represents an in-year overspend of £153k (4.6%) against budgeted DFID contribution of £3,325,000, but a small underspend of £12k (0.1%) over the whole life of the programme (£9,062,572 against a revised budget of £9,075,000).
Overall the quality of financial management has been good during the reporting period. WFD has provided timely invoices with a breakdown of expenditure by output and also by programme/admin. Although there were relatively small variances between quarterly forecasts and actual expenditure the overall budget forecast for the three-year period against actual expenditure was good (-0.1%).
Annual statutory audits conducted by the National Audit Office (NAO) (most recently in 2017) have provided an unqualified opinion on WFD’s financial statements, and neither the NAO nor WFD’s internal auditors BDO have found any serious issues with WFD’s financial management systems. The size of the adjustments required between the draft 2018 figures and the audited final accounts (which will not be finished until after this Review is already complete) will provide an indication of the de facto accuracy of financial management and reporting in 2017/18. The net effect of last year’s audit adjustments on the statement of comprehensive net expenditure and statement of financial position was £3k, although correcting uncorrected misstatements would have increased expenditure and decreased net assets by a further £47k. Overall, these factors suggest that the risk of irregular expenditure or material error in WFD’s financial reporting remains low, although there is scope to improve control and oversight over in-country expenditure in particular (see Section E).
WFD maintains an asset register centrally and in-country, consisting mainly of office furniture and IT equipment. WFD is responsible for the ownership, custody, maintenance, and control of any assets purchased with DFID funds, and has appropriate controls and procedures in place. The majority of WFD’s field offices are rented on short leases or received as a ‘benefit in kind’ from host parliaments, and WFD’s principal work relates to procurement and delivery of services rather than assets. Therefore risks around asset management are low. As of the 31 March 2018, the value of assets for this programme amounted to £22k. We are currently evaluating the business case for the next phase of funding and once this has been completed we will make a decision on the disposal of assets and what represents best value for money for DFID, i.e. rolling over the assets to the next phase, transfer of assets to a third party, or selling the assets.
In 2016/17, the central WFD Finance function was placed under considerable strain due to staff turnover and rapid growth in the number and scale of WFD’s programmes, many of which are increasingly funded by third parties – thus creating further complexities for financial management, attribution and reporting both locally and centrally. This created pressure on central finance capacity, as well as some knock-on effects on the oversight and support provided to field offices (for example processing payments), as reflected in both interviews and an e-survey of programme staff in London and overseas.
WFD has since implemented a new permanent structure for its finance department, including a new Head of Finance (appointed in September 2017, and reporting to the Finance Director) and two Finance Officers. There are also two finance business partners, whose role is to support programme staff on budgeting, forecasting, and finance aspects of business development, and assist the Head of Finance with management reporting.
Further improvements to WFD’s finance structures are ongoing, and include an extensive planned upgrade of the accounting system in 2018/19. Changes already made appear to have had a positive effect on the support provided by the central finance team, as reflected in the results of the repeat survey of WFD programme staff in Spring 2018. This year, 79% of respondents who expressed an opinion stated that the WFD Central Finance function helped them to do their job ‘very effectively’ or ‘fairly effectively’, compared to just 48% in 2017.
WFD’s delivery chain relies chiefly on its country and regional offices to deliver its parliamentary strengthening and integrated political parties and parliaments work, supported by central programme and financial management capacity at the centre. The political party assistance work is implemented by the international offices of the UK political parties, under annual contract to WFD. Annual financial allocations to the political parties’ work are approved by the Board.
The international offices and the multi-party international office submit annual plans to WFD, for consideration and approval. The annual contracts set out clearly WFD’s requirements of the international offices’ management of and reporting on WFD funds, and details WFD’s internal audit procedures, assurance, fraud and whistle-blowing requirements. Limits are set on the proportion of funds that can be spent on administrative costs.
All Political Party Offices submitted risk sub-registers for their party programmes for the first time in 2016/17. In 2017/18, the Risk and Audit Committee of WFD’s Board tasked WFD’s internal auditors to undertake a review of the political parties’ due diligence and assurance policies and financial control procedures. The auditors found that the design of the relevant controls was generally sound (with some recommendations for improvement, see Annex 1), and that their operation was generally satisfactory – but with some evidence of non-compliance which could pose risks to the fulfilment of objectives (see also Section E). As with other organisations, DFID has been in discussions with WFD regarding safeguarding and for any future funding DFID will need to ensure that WFD has robust safeguarding arrangements in place.

Date of last narrative financial report	30 January 2018
Date of last audited annual statement	19 July 2017

Thinking and Working Politically
Expenditure
	Agreed Budget	Actual expenditure	Balance	Variance %
2018/19	£150,000	£144,857	-£5,143	-3.4%

Project expenditure has closely matched the planned budget. A reserve of £3,706 to cover audit costs has not yet been spent, and when the audit is completed this will result in an overall underspend of £1,437. The quality of financial management for this accountable grant has been good and the University of Birmingham has provided DFID with timely and accurate forecasting and invoicing.

## G: MONITORING, EVIDENCE & LEARNING

Monitoring
WFD has developed its monitoring and evaluation systems considerably over the life of the programme, with key changes being the introduction of a SharePoint system to capture performance indicator data, and a more rigorous approach to the quality and comprehensiveness of quarterly reports. These reports are scored by the Monitoring and Evaluation (M&E) team across a range of indicators covering timeliness, content, format, and quality of drafting.
The Research and Evaluation Director is responsible for the development of WFD’s strategies and methodologies on impact measurement and reporting, while the M&E team advises and supports the programme teams through the development of a framework of monitoring and evaluation tools. Oversight of programme performance is chiefly through the Programme Performance Review process, which is carried out by the WFD Executive Management Committee (EMC). The EMC receives quarterly programme updates based upon four key performance measures; M&E, Risk, Financial and Communications. Programmes are assigned a quarterly RAG rating based on a weighted average score from across these performance categories.
Programme-level reports include self-assessments of progress against corporate output targets and programme-specific outcomes using RAG-rated milestones based on progress against bespoke outcome matrices (which, although still of varying quality, are now being used by all DFID/FCO grant-funded programmes). Implementing such a systematic milestone-based monitoring approach is challenging in programmes that do not run simultaneously, and that experience different barriers to implementation, impacting on comparability of reported progress between programmes. Nonetheless, it appears that this approach has enabled WFD staff and other stakeholders to have a clear view of the direction of travel. The quarterly self-assessment/RAG rating approach also allows the reports to serve as a basis for possible further review and intervention or support by WFD HQ.
A 2017/18 review of the programme performance monitoring review by WFD’s internal auditors found that the scoring methodology for programme performance was well-reasoned and appropriately balanced, and that the process was operating as intended. That said, the auditors confirmed that there were a number of gaps in the required programme documentation submitted by teams in line with the requirements of the Programmes Manual. There were also a number of areas where the Programmes Manual was not fully integrated with the workflows within SharePoint, and mitigation plans were not documented consistently. The auditors also raised concerns that the implementation of plans is not subject to central oversight from WFD's core management structure in London. It appears that there have also been issues with the capacity of the SharePoint system to deal with collecting, monitoring and reporting large volumes of monitoring data from individual programmes. Although the output tracker system (see Recommendations table below) is still working, the M&E team have had to revert to manual collection of activity data – placing a large administrative burden on both central and in-country staff. WFD is hoping to address these issues through planned upgrades to its systems in 2018 – ideally by implementing an integrated system able to deal with both finance and activity data, which it hopes will also assist with generating and analysing metrics for VfM (see Section D).
Evidence
An independent mid-term evaluation of the programme, originally scheduled for the first quarter of 2017 to be commissioned by DFID, was ultimately cancelled owing to difficulties in procuring a suitable provider. This has limited the quantity of external assessment of performance and impact over the lifetime of the programme. The planned new programme will redress this with an independent evaluation to be commissioned in the first year. In addition, the FCO has not yet conducted its required Tailored Review (TR) of WFD, as its sponsoring department. The TR would take a strategic look at WFD’s fit with FCO and HMG objectives, its governance arrangements, and continuation as a NDPB. FCO plan to conduct this review in late 2018.
In year 3, with DFID approval and oversight, WFD commissioned three smaller independent evaluations on specific themes, namely citizen participation, political party assistance and financial oversight. These reviews were carried out by external contractors in quarter 3 and quarter 4 of 2017/18. Their main findings with implications for the programme’s evidence base were as follows:
Common findings:
WFD is respected among a wide range of parliamentary stakeholders and donors; country programmes appear to have sufficient flexibility and a high degree of autonomy which allows priority themes to emerge; theories of change at thematic level are under- developed; systems to record data and track outcomes and impact are not consistently used; estimates of audiences reached and influenced could be put in place; learning and knowledge management should be strengthened; and the pilot use of outcome matrix completed and lessons applied (see also Section C).
Specific to Citizen Participation:
The decision to upgrade citizen participation to a core pillar of WFD’s work was only formally taken in 2017, and is now included in all strategic documents. The emphasis, however, is variable with the best examples in sub-Saharan Africa and the Balkans. These all include working with CBOs or NGOs, and have had variable success in areas of policy-making, women’s representation, media and leadership. Elections offer opportunities, as in Sierra Leone, to engage with marginalised groups and bring them closer to parliament. The main recommendations were: develop a clear strategy for systemic change around how WFD enables citizen participation in parliament; measure and track better against criteria using indicators of inclusion, equity and gender; strengthen capability and know-how, particularly in highlighting citizens’ centrality in democracies and parliament; appoint a lead at WFD for this function and an advisory committee; make greater use of peer learning, intranet sites and case studies; focus more strongly on this topic in corporate communications – for example, as part of the UN’s ‘Leave No One Behind’ 2030 Agenda for Sustainable Development; showcase WFD work at conferences and seminars; identify a pipeline of funded opportunities; and identify strategic partnerships at centre.
Specific to Political Party Assistance:
The assessment found that, overall, the PPOs’ sister party projects often only realised expected changes to a limited extent and there was no evidence of impact or potential impact at the level of an entire political system. The theory that capacity building will influence the behaviour of politicians, and that UK political experiences based on the Westminster parliamentary model will be relevant, was not substantiated – in part as many of the countries where WFD operates have presidential systems. All PPOs are committed to WFD’s overarching objective of multi-party democracy, constituted by representative, inclusive and accountable parties competing on a more level playing field, and pursue this through sister-party assistance (bilaterally or through networks). Although there are positive examples of multi-party activities, there is little independent monitoring, which would provide more credible evidence. The main recommendations were: use more explicit criteria to select sister parties in order to manage reputational risks; develop more realistic interventions; continue to improve monitoring, evaluation and learning; and consider how to reward good project performance to improve value for money.
Specific to Public Financial Oversight (PFO):
Appropriately, there is no single model of public financial oversight which is consistently applied in all countries, but there are some similarities and common principles applied throughout. WFD has contributed to the setting up of Public Account Committees (PACs) and Parliamentary Budget Offices (PBOs) where none existed before, such as in Serbia, Montenegro, Morocco, Tunisia and Ukraine. Some of this has probably led to significant financial savings, but this is often not tracked or known. WFD is selling itself short in communicating and celebrating its successes, both within programme countries and more widely. There is scope, for example, for WFD to do more to communicate its work via DFID and FCO networks. Overall there is little evidence of the financial sustainability of many PBOs or PACs that WFD has supported. The main recommendations were: WFD should develop a detailed strategy for sustainable strengthening of PFO; more attention to working with PBOs, parliamentary finance committees and PACs; better integration of WFD programmes, with stronger links between PFO and the other WFD thematic areas especially civil society engagement and political party work; identify six to eight priority countries for PFO strengthening over the next three years; a stronger advocacy approach; and a higher proportion of PFO programme spending on mentoring, peer-to-peer support and action learning and less on study tours and workshops.
Learning
Over the course of the programme, WFD has implemented a number of initiatives to identify and share lessons within the organisation. These include: the appointment of a new member of the M&E team whose role is to feed back WFD research findings into subsequent programme design; lessons learned sections in Annual Programme Reports; annual retreats, and dissemination of ‘success stories’ by the M&E and communications teams.
Respondents to the reviewers’ surveys of WFD Programme staff in 2016/17 and 2017/18 were generally positive about the lesson learning aspect of WFD’s activities. That said, between Year 2 and Year 3 there was a noticeable decline in the proportion of respondents who agreed that ‘WFD has effective systems for learning lessons and sharing these among staff’, accompanied by an increase in the proportion that disagreed with this statement.
Respondents in both years highlighted specific areas where there was scope for improvement - for example by better disseminating and publicising lessons learned and success stories through mechanisms such as blogs, case studies and articles. Several respondents cited the existing SharePoint system as a possible means of collecting and disseminating lessons, but felt that it was not currently used very effectively to do so. This was particularly the case for Party Political Offices, who reported difficulties in accessing the system, which also impacted on their ability to learn relevant lessons from across the wider organisation.
Progress on recommendations from annual reviews for this programme
A full list of the recommendations made in the 2015/16 and 2016/17 Annual Reviews is provided in Annex 1. The paragraphs below provide a brief summary of the more significant issues covered by these recommendations, as well as progress in addressing them.
A number of previous recommendations related to apparent misalignment between log-frame priorities and actual programme performance in generating the related outputs – particularly with regard to indicators 2.2 (issues championed by networks translating into policy proposals) and 3.2 (civil society access to parliament). The original recommendations were for DFID and WFD to review the reasons for these discrepancies, and consider whether they might be addressed by reprogramming or revising the log-frame wording and indicators. However, these discussions have not yet taken place. In establishing their priorities and approach to the next programming period, DFID and WFD will need to revisit these topics to ensure that the associated risks to programme effectiveness are addressed.
Several previous recommendations related to the need to improve frameworks for reporting, monitoring and analysing performance and VfM. WFD has since rolled out its outcome matrix and tracking approach across all programmes (albeit with varying levels of data quality and completeness). It has developed some limited VfM metrics (see Section D), but more work is needed to develop a workable approach to defining and analysing VfM in the context of WFD’s work – particularly given the new requirement to cover equity as well as the traditional three ‘E’s of efficiency, economy and effectiveness.
Another important issue and recommendation from the previous Annual Review related to pressures on the central finance function following WFD’s rapid expansion in 2016 and 2017. The recommendation to review and expand finance capacity has since been addressed, chiefly through the creation of a new Head of Finance role. This year’s feedback from WFD programme staff suggests that the support they receive from Finance has improved significantly in 2017/18 (see Section D).
A further important recurring theme over the life of the programme has been the need to improve WFD’s internal lesson learning, an issue covered by recommendations in both 2015/16 and 2016/17. There has been progress on implementing these recommendations but feedback from programme staff on how well WFD learns and shares lessons was noticeably less positive in the current year than in the year before (see previous section on Learning). That said, WFD has made progress in implementing most of the key recommendations in Annex 1, suggesting that its ability to apply evidence-based organisational learning – at least from external evaluation activities such as the current source – is satisfactory.

## ANNEX 1: RECOMMENDATIONS FROM PREVIOUS ANNUAL REVIEWS, INCLUDING PROGRESS WITH IMPLEMENTATION
Recommendations from the Year 1 Annual Review
Recommendation	Progress update
R1. If DFID’s annual outcome scoring pilot is implemented in future years, the WFD M&E team should work with programme teams to begin annual outcome scoring across the full range of WFD programmes.	WFD has made progress in rolling out country-specific ‘outcome matrices’ against which a number of individual programme teams are now reporting. This has been supported by the implementation of an online ‘outcome tracker’ tool. However, it does not currently have complete and comprehensive benchmarks and performance from across the whole programme in this format, making it difficult to conclude quantitatively on whether the programme as a whole has achieved its intended outcomes.
R2. The citizen participation outcome should be a focus of assessment at the mid-term evaluation and next annual review.	The Year 2 Annual Review included some targeted interviews to explore this topic, which confirmed that there was relatively weak progress towards this outcome. / The mid-term evaluation for the programme was ultimately cancelled (see Section G), hence this topic could not be covered through that means. However, the mid-term evaluation was partly replaced by a specific thematic evaluation of citizen participation, carried out in Q3 and Q4 of Year 3. The findings from this evaluation are briefly summarised in Section G.
R3. WFD’s parliamentary and party expertise should attempt to address issues around decision making and political negotiation as well as technical skills around legislative drafting.	WFD has reported strong performance against all three indicators of output 1 (the most relevant to this recommendation) since Year 1 of the programme. This has included some examples of ‘softer’ interactions, such as developing leadership skills and supporting / advocating for minority groups (e.g. PWDs, women parliamentarians). This suggests that WFD has not restricted the application of its expertise to ‘technical’ skills only.
R4. The sustainability of peer-to-peer networks should be incorporated in their design and explicitly covered in reporting. Sustainability indicators could be considered as part of this.	Peer-to-peer networks have become less of a priority for WFD’s DFID/FCO-funded activity over the course of the programme, WFD did however introduce relevant indicators into its outcome matrices as ‘progress markers’, either as a financial or an “in kind” contribution – i.e. evidence that the beneficiaries themselves are supporting or sustaining the network.
R5. WFD could make much more of its ability to leverage its different parliamentary and party expertise to enhance its ability to broker relationships and space for policy change.	Although some important relationships were developed over the life of the programme, WFD’s performance against the most relevant proxy for this recommendation (Output 3) remained relatively weak for the remainder of the programme.
R6. WFD should review its focus on civil society organisations’ access to parliament, which is currently underdeveloped given its importance in the theory of change.	Although some important relationships were developed over the life of the programme, WFD’s performance against the most relevant proxy for this recommendation (Indicator 3.2) remained relatively weak for the remainder of the programme. The required number of outputs was not achieved, and - due to staff changes within DFID – planned discussions as to the ‘fit’ of this objective with WFD’s current activities and priorities did not take place. Hence WFD and DFID will need to revisit this topic as part of discussions over future funding and programming from 2018 onwards.
R7. WFD should take forward its primarily technical parliamentary context analyses to in future include political context assessment of parliaments, parties and the political system to support politically informed programming decisions.	The scope of Context Analyses was expanded in Year 2, to include greater coverage of these issues. The log-frame indicator wording was amended to specify that the target and milestone referred to these ‘second-generation’ context analyses (although these targets were not subsequently met in Years 2 and 3). See Section B for details.
R8. WFD should further develop in consultation with DFID its concept of VfM, ensuring it is operationalised across the organisation by October 2016, with suitable indicators and means for assessing, particularly in terms of efficiency and effectiveness.	WFD has been experimenting with both cost-efficiency and cost-effectiveness metrics, but these have yet to be operationalised or used to inform programme management and reporting. / WFD has been testing an activity tracker tool to identify and analyse trends, such as the type of activities implemented, any recurrent topics covered, the profile of the participants and the experts hired. The aim is also that it will help WFD understand where it has made cost savings.
R9. WFD should encourage its country staff to consider how their daily relationships and interactions contribute to programme log-frame outputs and to record this influencing work. Indicator 1.3 should be revised to reflect the greater number of activities following annual review.	The M&E team created various training and guidance on the corporate log-frame and its practical application (e.g. online animation), as well as including it in induction training provided to new staff. It also adjusted the pro forma structure and content of individual programme annual reports to emphasise the importance of the corporate log-frame as well as the individual programme log-frame. / The milestones and targets for Indicator 1.3 were revised upwards from Year 2 onwards, with the final target (as applied in Section B above) increasing from 10 to 18.
R10. Good progress should continue, and internal dissemination of lessons should be further enhanced across WFD.	WFD commissioned three thematic learning evaluations in Q3 and Q4 of 2017/18 (see Section G), and – now that the resultant reports have been finalised – intends to use the results and recommendations to support institutional learning. / WFD has introduced a staff blog via SharePoint, intended to present professional tips and lessons learnt as well as staff profiles and updates from WFD HQ. It has also been promoting the use of the enterprise social networking site Yammer to update on activities and share professional advice and insight. Political Party Offices have access to both channels (although some PPO respondents to the 2018 staff survey reported difficulties in achieving consistent access, see Section G). / WFD is also planning to hold an organisational learning event within the first quarter 2018/19, to provide HQ staff, UK political party staff, and all WFD Country Representatives with detailed training on WFD’s new systems and approaches.

Recommendations from the Year 2 Annual Review
Recommendation	Progress update
R1. WFD to consider carefully the size, structure, history and personnel of beneficiary parliaments, and ensure whenever possible that the UK exemplar chosen matches these criteria.	WFD has sought to increase its engagement with the devolved Assemblies, and widened the range of institutions from which it draws MPs and parliamentary staff, including both developed and emerging democracies. It notes, however, that the availability of such staff is not always optimal to match beneficiaries’ requirements.
R2. WFD to consider ways of further exploiting the similarities in the political and operational environment of Northern and Southern Africa to improve networking opportunities between the two regions.	WFD has sought to support communication with regard to the through regular meetings between Regional Teams for MENA and Africa. It also considers that political parties’ African party networks bring together party activists and MPs from both regions on a regular basis.
R3. WFD and DFID to discuss the reasons why indicators 2.2 and 3.2 no longer appear well aligned with WFD’s de facto priorities and activities at programme level, and consider how this discrepancy should be addressed.	Due to staff changes within DFID, these discussions and associated changes to the log-frame did not take place prior to the end of the programme. Hence WFD and DFID will need to revisit this topic as part of discussions over future funding and programming from 2018 onwards.
R4. WFD to consider at the context analysis/design stage whether the local Civil Society Organisation (CSO) sector is mature enough to take advantage of opportunities for access, or whether initial capacity building might be a more appropriate intervention given the baseline position.	WFD has begun adapting its context analysis tool to incorporate civil society more comprehensively. However, this is likely to be operationalised only from April 2018, since few programmes were designed in the months between the Year 2 review and the end of the programme period.
R5. WFD to review the staff resources available for writing and updating Context Analyses (CAs), and ensure that capacity remains sufficient to sustain the quality, timeliness and coverage.	WFD carried out this review and developed a proposal for a new approach to knowledge gathering during the programme cycle to support it to deliver its future objectives. The proposal is intended to promote collaborative information-gathering amongst WFD staff to overcome limitations in capacity, promote knowledge sharing and quality control. WFD also intends to continue training staff, particularly those based in field offices, to allow them to contribute more effectively to CAs.
R6. WFD should expand the prescribed content of CAs to include greater coverage of local civil society and media engagement.	WFD has been developing a series of adaptive knowledge gathering tools and templates to enable programme teams to zoom in on coverage of local civil society and media engagement. It has also been considering how to work with other organisations to understand better how to integrate CSOs, electoral stakeholders, and media into the analysis.
R7. WFD should identify further means of disseminating and operationalizing its research among non-academic stakeholders, including politicians/parliamentary partners, DFID, FCO and other policy-makers and implementers.	WFD launched newsletters aimed at reaching new audiences, and began to develop an engagement strategy with HMG in-country staff. It also sought to feature research content in WFD newsletters, and to publicise its research programme at stakeholder engagement events such as the WFD 25th Anniversary Conference and events organised in the Scottish Parliament and other devolved legislative assemblies.
R8. WFD should consider analysing website data to identify which research outputs and topics are most in demand, and use this analysis to inform future research and programme planning.	WFD considers that its website is not the best means of disseminating its research products and judging demand for research. Instead, it uses analysis of trends on social media and discussions with key stakeholders to inform research topics.
R9. DFID should work closely with WFD on the planned review of due diligence procedures and the full delivery chain mapping, to ensure it will meet DFID’s new requirements.	During autumn 2017, DFID supported WFD to complete a full map of its delivery chain, and ensure its due diligence procedures, including safeguarding, are in line with DFID requirements.
R10. WFD should continue to develop the performance monitoring and Value for Money (VfM) framework, with a particular focus on consistently defining and capturing all relevant outputs, and developing a ‘cost-effectiveness’ metric to compare performance between programmes.	WFD has been experimenting with both cost-efficiency and cost-effectiveness metrics, but these have yet to be operationalised or used to inform programme management and reporting. / WFD has been testing an activity tracker tool to identify and analyse trends, such as the type of activities implemented, any recurrent topics covered, the profile of the participants and the experts hired. The aim is also that it will help WFD understand where it has made cost savings.
R11. WFD should further review central Finance capacity to ensure it is sufficient to manage the increased volume of transactions and support needs of in-country programme staff.	In 2017, WFD created the new role of Head of Finance, reporting to the Finance Director and overseeing all aspects of finance. This role was filled in September 2017. / It also introduced two Finance Business Partners (FBPs) to work closely with programme staff on budgeting, forecasting, and financial analysis, as well as finance aspects of business development. / A full upgrade of WFD’s financial systems is planned for 2018/19.
R12. DFID should revise its risk register and statement.	DFID updated its risk register following assessments during 2017 annual review.
R13. WFD should review Programme Management capacity and ensure it is sufficient in the light of increased third-party funding relationships, additional risk management and due diligence requirements.	WFD moved one member of staff from business development into a programme systems management role for the remainder of Year 3. This role includes responsibilities for risk management and due diligence, as well as improving and embedding management practices - including the holding of monthly internal Executive Management Committee meetings and quarterly Programme Quality Committee meetings with members of WFD’s Board.
R14. WFD to review the corporate risk register to ensure that risks to pipeline management, accessibility and sustainability of non-UK funding, capacity planning and financial management are captured and mitigated.	In addition to reviewing the corporate risk register, WFD’s audit committee (ARC) carried out a more in-depth review of risk management arrangements per se, to identify the strategic and operational risks to achievement of WFD’s new strategy. / This included a workshop (to which the Board was invited), where ARC members and management began the process and discussed and identified a number of strategic risks and related operational risks. / The revised risk register is now being finalised, having been rationalised and the number of risks reduced in order to ensure that it contains only corporate-level risks. More operational risks have been removed and/or allocated to sub-risk registers, although WFD has made efforts to align the terminology and classifications to ensure maximum comparability and complementarity between the corporate and sub-risk registers (see Section E for details).
R15. WFD to issue guidance to Country Representatives regarding communication, relationship management and coordination opportunities vis-à-vis in-country HMG staff.	WFD surveyed engagement with FCO and DFID personnel in 28 countries, and found that there is proportionate and regular engagement in a clear majority of them. It identified seven countries where it needed to promote greater engagement (including two where it did not engage locally at all). / It carried out various actions to address the issues in these countries, including meetings and the requirement to provide regular updates and engage systematically. It also issued guidance to all Country Representatives together with details of relevant FCO and DFID contacts, and published an article on SharePoint on how to best engage.
R16. WFD to explore ways of further improving internal lesson learning, e.g. through peer review, more structured and formal events for programme staff, and increased use of SharePoint.	WFD commissioned three thematic learning evaluations in Q3 and Q4 of 2017/18 (see Section G), and – now that the resultant reports have been finalised – intends to use the results and recommendations to support institutional learning. / WFD has introduced a staff blog via SharePoint, intended to present professional tips and lessons learnt as well as staff profiles and updates from WFD HQ. It has also been promoting the use of the enterprise social networking site Yammer to update on activities and share professional advice and insight. Political Party Offices have access to both channels (although some PPO respondents to the 2018 staff survey reported difficulties in achieving consistent access, see Section G). / WFD is also planning to hold an organisational learning event within the first quarter 2018/19, to provide HQ staff, UK political party staff, and all WFD Country Representatives with detailed training on WFD’s new systems and approaches.

Smart Guide
The Project Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Project Completion Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it aimed to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. You should assume that readers may not go beyond this summary. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. There needs to be a record of any follow up actions that may be required after completion of this review (eg related to final payments, audited statements etc – see the extension and closure section in the Smart Rules). These may sit best in the Delivery Plan – but you should agree them with the person signing off the PCR and include them in this (publicly available) report or the Delivery Plan.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current log-frame. This will need to be entered on AMP as part of loading the PCR for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review (Business Case approval if the programme is under 15 months and hasn’t had an AR) and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in Section A. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the log-frame and add new sub-sections for additional outputs.
C: Theory of change and progress against outcomes
Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved? Review this in view of the overall programme score; but it is possible that outputs were delivered but the envisaged outcomes or impact were not – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact. You should refer to the indicators in the log-frame. Did any unexpected outcomes emerge? Were there any significant changes in the planned timetable for delivery of the programme? Were there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact were valid e.g. did the ToC logic, supporting evidence and assumptions hold up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Log-frame. Describe major changes in the past year –including when they were made and why- and what their implications were for the programme. Ideally changes should not have be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the log-frame template). If relevant you might also want to flag any major changes since the programme started.
D: Value for Money
Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme You should refer to VfM measures and metrics from the Business Case and/or ARs. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind. You should note any formal extensions or amendments to the programme giving brief details about cost, duration and the reasons why. Significant changes to log-frame indicators or targets may also be relevant.

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) during the past year and over the life of the programme / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context in the past year and how they impacted on the programme and were mitigated. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review (remember that projects remain open until they are archived, even after the PCR is complete). / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences?
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could have been a more effective partner to help deliver the programme (key points could be included in Section G too). / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how they engaged with the programme implementer(s) and DFID. Briefly describe the PCR process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Include any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned or has taken place set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications or follow-up actions of that learning for this programme may be best captured in Section A / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from ARs (especially the last one) should be provided.