Project Completion Review - Top Sheet

Review Date:	21 June 2018

Title: Yemen Social Fund for Development (SFD)
Programme Code: 201427	Start Date 10/05/2010	End Date: 31/03/2018
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme Performance

Year	2011	2012	2013	2014	2015	2016	2017
Programme Score	n/a	A	A	A	A	A	A
Risk Rating	High	High	Medium	Medium	Medium	Severe	Major

Financial Position

Original Programme Value	£100,000,000
Extensions/ amendments	£8,400,000
Log-frame revisions (with dates)	11 April 2018 / 26 February 2018 / 16 January 2017
Total programme spend	£108,400,000

Follow up actions required following closure

1. Recommend continuing UK support to SFD, in recognition of its importance as a resilient, national institution, providing life saving and poverty reducing support to vulnerable people in Yemen.
2. Ensure that any future programme to support SFD is designed according to DFID’s capacity to deliver.
3. Share PCR and lessons learnt with SFD and donors, and ensure that recommendations are implemented and used to inform Phase V planning and design.

Table 1: Summary of key recommendations (see detailed output scoring for further, programme specific recommendations).

Recommendation	Priority / H/M/L	Owner
Programming
DFID should regularly assess the balance of benefits and risks associated with DFID being the only donor providing unearmarked funding to SFD in any future programming	H	DFID
SFD should outline a rigorous, systematic approach to cross-cutting agendas, including conflict sensitivity, gender and disability. DFID and/or other donors should consider providing SFD technical assistance, including on these cross-cutting agendas.	H	SFD & DFID (PM / advisors)
SFD should continue to ensure that any decisions to build or rehabilitate infrastructure are based on clear contracts and Memorandum of Understandings (MoUs) with relevant stakeholders that determine the roles and responsibilities for the operation and maintenance of projects after their completion. SFD should also continue to systematically conduct project and community-level surveys to verify how projects are perceived by beneficiaries, and monitor projects after completion.	H	SFD’s Community and Local Development Programme (CLD)
SFD should explore the possibility of introducing multi-year cash for works interventions, and enhance its coordination with partners who are delivering cash programming.	M	SFD’s Labour Intensive Public Works (LIWP)
Results
SFD should improve the clarity of its results reporting by breaking down results according to programmes, including clear and concise explanations for each indicator, and making the Management Information System (MIS) available to donors online. This will decrease the risk of double counting, enable better evaluation on a programme (rather than sector) basis, and improve transparency. Notably, SFD should consult DFID about revising results milestones, targets and methodologies for reporting.	H	SFD’s Monitoring & Evaluation (M&E)
Communication
SFD should continue to actively share data and information, and to communicate and coordinate with the UN’s Health, Protection, Nutrition, Education and WASH Clusters to inform their delivery as well as progress reporting.	M	SFD (CLD)
Finance
SFD should inform DFID monthly on financial management, including any expected delays in its rate of spending, and share financial reports that provide DFID with oversight on the link between expected results and budgets. This includes consulting DFID on plans to reprioritise funding and how this affects results. SFD & DFID	H	SFD & DFID
Risk
SFD should continue to improve its risk management processes, via a more regular and systematic approach to reviewing the risk register and programme impacts, rigorous contextual analysis and scenario planning. DFID should continue to engage closely in the future.	M	SFD & DFID

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Log frame

DFID’s support to Social Fund for Development’s (SFD) Phase IV programme intended to improve access to basic services, enhance economic opportunities, reduce the vulnerability of the poor, and increase the capacity of local authorities, NGOs and communities. Initially intended to run for five years (2011-15), Phase IV was extended for a further two years (2016-17) as a consequence of the current conflict which began in 2015. DFID committed £100 million to the programme in 2011 and a further £8.4m in 2017. A further three months no cost extension was approved in January 2018 to enable SFD to finalise activities.[1] DFID’s funding was un-earmarked and in total amounted to 18% of the total donor contributions to Phase IV.
[1] This took our support to SFD Phase IV to 31 March 2018. SFD reported that the delay in delivery and spending was caused by the period of access restrictions for imports (including fuel) that started in November 2017, and the shortage of liquidity.
SFD
The Yemen Social Fund for Development (SFD) was established in 1997 under Yemeni law as a national development institution. Its objectives are to: 1) improve access to basic services; 2) enhance economic opportunities, and; 3) reduce the vulnerability of the poor. It has national coverage and delivers through various partners, including commercial contractors, Yemeni NGOs, Microfinance Institutions and local community groups. It is recognised as a key development institution and pillar of social protection system in Yemen, receiving funding from a broad international donor base.[2] SFD is overseen by a Board of Directors whose duties include approval of the main policies and annual and five year plans; its direct management falls under the Managing Director who is supported by the Headquarters Office; and its programmes are delivered by nine branch offices who are responsible for coordination with local communities, project identification, monitoring of implementation and ensuring quality assurance.
[2] These include, but are not limited to, Germany, the Netherlands, the Islamic Development Bank, UNDP, UNESCO and the World Bank.
Wider context
The period covered by this programme has been one of continuous political, security and economic turmoil. This started with popular protests in 2011 that led to the resignation of President Saleh, the appointment of President Hadi and the transitional period of 2012-14, dominated by the National Dialogue Conference. Following the failure of the conference at the end of 2014 and the take-over of Sana’a by the Houthi rebel movement, the country descended into conflict. The Saudi-led Coalition began military action in support of the Government of Yemen in March 2015 and the conflict continues.
Before the outbreak of the conflict, Yemen was already the Middle East’s poorest nation and the eighth most food insecure country in the world. By 2017, Yemen had become the worst humanitarian crisis in the world and one of the world’s largest protection crises.[3] The 2018 UN Humanitarian Needs Overview assessed that: 22.2 m Yemeni people (82% of the population) are in need of some form of humanitarian and/or protection assistance; 11.3 m in acute need; 8.4 m are severely food insecure and at risk of starvation; 1.8 m children and 1.1 m pregnant or lactating women are acutely malnourished, including 400,000 children under the age of five years who are suffering from severe acute malnutrition; and over 2 m people are internally displaced. Yemen ranked 114 out of 119 in the 2017 Global Hunger Index and ranks lowest in the Global Gender Gap Index.
[3] ‘Protection’ in this context refers to maintenance of the rights of the individual in accordance with the letter and the spirit of relevant bodies of law, including international human rights, humanitarian, and refugee law.
Since 2015, Yemen has faced the collapse of the economy and formal banking sector, creating a liquidity crisis (i.e. shortage of hard currency) and contributing to significant depreciation of the Riyal.[4] Its import sector (responsible for 90% of food and fuel in Yemen) is also in crisis. Together, these factors have placed significant pressures on the population. The outlook for 2018 looks set to continue on a similar trajectory.
[4] The Riyal has depreciated by 50% (from 250 to 500 Riyals to the dollar) since the Central Bank of Yemen floated the currency in August 2017.
This has presented a volatile and challenging operating environment for SFD to deliver its Phase IV programme. Delivery has been hampered and slowed by obstacles such as the lack of liquidity, restriction of access of contractors to some areas of the country and increased bureaucracy caused by the political divide between North and South. SFD’s funding was also disrupted for a period during this programme[5]. This led to frequent temporary closures of Branch Offices in Aden and Taiz, cuts in staff hours and salaries, and the suspension of the majority of projects.[6] Funding remained unstable until late 2016 and has presented continuous challenges to SFD project planning. It has also affected the rate of DFID funds spent by SFD, at times leading to underspend and disbursement delays.
[5] Funding disruptions were particularly damaging in 2014 and 2015 when many – including their largest donors, the Saudi Fund for Development and the World Bank - suspended funding completely.
[6] For example, in September 2015 SFD had 93 active projects out of a portfolio of 1841 projects registered in their MIS as “under implementation”, and mainly in the labour-intensive public works and water sectors. During April–September 2015, SFD completed 119 projects compared to 670 projects completed during the period October 2014-March 2015.

Programme overview
From inception, the SFD Phase IV has been comprised of four programmes:

1. Community Led Development (CLD): Providing basic services (including education, health, water and sanitation), reconstructing and rehabilitating facilities and training personnel.
2. Small and Micro-Enterprise Development (SMED): Support to the policy environment, microfinance loans to individuals and small businesses, and grants to improve production value chains
3. Labour Intensive Public Works (LIWP): Cash-for-work (CfW) schemes providing short-term employment for vulnerable households, whilst creating community assets.
4. Empowerment for Local Development (ELD): Local level capacity building for development, including support to local NGOs, Village Cooperative Councils (VCCs) and local authorities.

Prior to the outbreak of the conflict in 2015, the focus of these programmes was on achieving longer term development outcomes. In response to the conflict, SFD has adapted to the crisis at hand. The initial, ‘emergency’ phase of the Phase IV extension focussed on: 1) providing immediate wage income; 2) improving conditions in communities through infrastructure rehabilitation and provision of access to services; 3) assisting small and microenterprises (SMEs) to survive, diversify and/or improve, and; 4) supporting community structures to play a role in reconciliation. Despite developing plans for further recovery and reconstruction phases of their work, SFD has, understandably, continued to operate predominantly in emergency mode through to the end of Phase IV.
High level results achieved by SFD overall
SFD’s Phase IV interventions have had a positive impact on the lives of vulnerable Yemenis. In total across the whole programme (to which DFID has contributed 18% of funds), they have directly benefitted 9.1 million Yemenis (55% female) and generated 35.1 million person days of temporary employment. They have also:
- Expanded short term cash for works to directly reach 460,026 people in urban areas, and a further 862,417 in rural areas;
- Formed 5,067 Village Cooperation Councils capable of delivering results to communities (for example, small scale infrastructure projects and life-skills training);
- Supported the resilience of the microfinance sector (e.g. providing 85,716 people with access to loans in 2017, of which 42.8% are women);
- Trained 7,535 teachers and educational professionals across the formal and informal sectors;
- Made significant contributions to the 2017 cholera response (e.g. they provided house-to-house and village-to-village awareness sessions on cholera and symptoms of cholera, and ways to prevent and treat it, that reached more than 50,000 rural people).
Support to SFD is aligned to the UK Aid Strategy, the Single Departmental Plan (SDP) and DFID-Yemen Business Plans (both 2012-16 and 2016-18). It directly contributes to SO4: tackling extreme poverty and helping Yemen’s most vulnerable people. It indirectly supports SO2: strengthen resilience and response to crises in Yemen (SO2). Because it reaches the extreme poor and vulnerable groups (e.g. women, disabled and internally displaced persons (IDPs)), it is central to DFID-Yemen’s efforts to leave no one behind. It fits with the objectives of the DFID humanitarian reform policy and Building Stability Framework. More broadly, it fits with National Security Strategy and Strategic Defence and Security Review commitments to spend at least 50% of DFID’s budget in fragile states and regions annually.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment
SFD have continued to operate across Yemen over the past seven years and have delivered assistance at scale despite the volatile security situation. As outlined in Table 2 below, results against targets are mixed. SFD has exceeded their targets for indicators 1 and 3, but under-performed on indicators 2[7] and 4.[8] In response to the operating environment some activities designed at the outset of the project were prioritised and expanded (for instance community led development, labour-intensive cash for works and rain water harvesting), whereas others were de-prioritised and/or under-resourced, for example education. Recommendations in this report related to milestones, targets and reporting will help address some of the issues that led to underperformance for indicator 2.
[7] On Indicator 2, over the five years 2011 to 2015, DFID expected SFD to support 11.7 m people, but SFD supported 7.1 m (55% of target). Over 2016 and 2017, SFD supported 0.8 m males and 1.2 m females. While we take into account the funding shortfall and use revised targets for this period (see text box entitled ‘A Note on Results’), SFD only met 44% of its two year target for 2016 to 2017.
[8] On Indicator 4, the number of pupils enrolled in SFD supported schools over the seven years was 326,223 (54% boys). This represents a significant shortfall against DFID expectations for the programme. Over the five years 2011 to 2015, DFID expected SFD to support 360,000 pupils but SFD supported only 255,000 i.e. 71% of the target. Over 2016 and 2017, SFD supported 11,434 boys and 14,246 girls. While we take into account the funding shortfall and use revised targets for this period, SFD still only met 36% of its two year target for 2016 to 2017.
Table 2: Outcome results
Outcome indicator	Target	Results
60% of CLD and LIWP resources go to the lowest 50% deprived villages	60%	69% CLD / 85% LIWP
Total number of direct beneficiaries of SFD funded projects (sex disaggregated)	11,681,000 (4,827,000 male, 6,854,000 female)	9,100,000 (4,100,000 male, 5,000,000 female)
Water access: Percentage of households in rural CLD areas where time to collect water is 30 minutes or less	58%	77% dry season / 83% rainy season
Education access: Number of pupils enrolled in SFD supported schools, disaggregated by: / - Boys / - Girls / - Children with special needs	Total: 34,744 / 176,410 / 150,794 / 7,540[9]	Total: 288,306 / 150,342 / 130,424 / 7,540
[9] DFID’s target for this is unclear and so this figure represents the target provided by SFD, which may have been revised.

Output Score and Description
Based on the four outputs listed in Table 3 below, SFD have achieved an overall score of A (outputs met expectations) for Phase IV. This reflects overall achievement against targets but also includes some inconsistencies: significant over-achievement in some areas (e.g. output 1.2 – number of teachers trained, and 4.1 – number of people trained) and under-achievements in others (e.g. output 1.1 – number of classrooms constructed/rehabilitated). Revisions of output targets were made in the log frame to account for the underfunding in 2016 and 2017; however, these revisions were not consistently reflected in the outcome targets (presented in Table 2). Inconsistencies in the results framework have been addressed in the recommendations.

Table 3: Summary of output scores by programme

Output title	Weighting	Output score
Community and Local Development Programme: Basic services improved	70%	A
Small and Micro Enterprises Development Program: Economic opportunities created	5%	A
Labour Intensive Works Program: Reduced vulnerability for the poor	20%	B
Capacity Building: Stakeholders capable and empowered	5%	A

Ways of working:

SFD’s decentralised structure, flexibility, innovation and commitment to learning lessons have assisted in delivering results throughout Phase IV. Its commitment to political neutrality and independence has also been vital in securing national access, which is a challenge for almost every partner operating in Yemen.

SFD have also made some progress towards integrating cross-cutting agendas, notably:

- Gender: Building on their 2009 gender strategy, SFD have prioritised gender mainstreaming and have achieved good results throughout Phase IV. Data is disaggregated and there is some evidence that the interests of women have been taken into consideration in projects - for example, 50% of seats of the Village Cooperative Councils are held by women. However, lessons identified by DFID’s Independent Monitoring (IMP) study on the LIWP included the need for interventions to be better tailored to women’s inclusion, which suggests more can be done. SFD should commit to a more rigorous, systematic approach to integrating the different needs of women, men, boys and girls throughout all stages of the project cycle, underpinned by gender analysis. DFID should continue to scrutinise this aspect of SFD’s work and make specific recommendations in the future.
- Disability: SFD’s consideration of children with special needs’ access to education is welcome. However, no progress was made on this during 2016-17 and there are likely to be other programme areas which could include those with disabilities and opportunities for SFD to expand their work accordingly.
- Conflict sensitivity: SFD speak confidently about conflict sensitivity. They are able to draw on their wide network to regularly monitor local and national conflict dynamics and adapt their programmes where needed. For example, they apply conflict sensitive targeting approaches, recognise the positive benefits of their work on social cohesion and have delivered some training across the organisation. Some progress could still be made on ensuring conflict sensitivity is integrated throughout the programme cycle across the whole organisation, for instance in ensuring conflict analysis is undertaken rather than just monitoring.

Lessons and how these have been shared
Key lessons learnt:
SFD is a valued partner and Yemeni institution: The events of 2011-17 have emphasised the value of SFD in a challenging conflict environment. Its perceived neutrality, reputation and long-established relationships with communities, authorities and donors provide SFD with unequalled access nationwide. It is a source of resilience for Yemen’s most vulnerable.
- SFD’s reporting mechanisms need revising for Phase V: Reporting from SFD has been a complicated issue (see “a note on results” and section H below for more information) throughout Phase IV causing difficulties with monitoring. Another method of reporting should be worked on with SFD and the donor community to resolve these issues for Phase V.
- The importance of programme and organisational flexibility: SFD’s ability to be flexible (which has included changing types and locations of projects, as well as organisational structures and procedures) has enabled them to continue operating and manage some of the risks faced over the period. Given ongoing fragility, it is important that this is institutionalised and embedded throughout all stages of the programme cycle.
- Value of unearmarked, core funding: DFID’s commitment to providing unearmarked funding has been vital in giving SFD the flexibility to continue operating under adverse circumstances and meet the shifting needs of the population. However, there are risks attached to the provision of unearmarked funding. DFID should regularly assess whether the benefits continue outweigh the risks and to mitigate any new risks associated with it
- Challenge of assessing the quality of interventions: The remote management of SFD has made it hard to assess the quality of the interventions. Across Phase IV, this has highlighted the importance of third party monitoring (TPM), technical assistance and donor coordination, which should be strengthened in the next phase of programming.

## C: DETAILED OUTPUT SCORING (1 page per output)
A note on results
Previous annual reviews noted SFD’s reporting and results framework needed improving. DFID has faced difficulties in understanding the variability of results delivery, and calculating the output scores for SFD’s programmes, especially for the years 2016 and 2017. This is largely due to SFD’s revision of milestones, which were driven in part by funding changes.

In the 2016 annual review, DFID reduced the milestones by 43% to reflect the 43% shortfall in funding for that year. We judged that this provided DFID with the most consistent, coherent and fair scores against the milestones originally agreed. For 2017, the final cumulative targets (listed under Phase IV overall in the tables below) were adjusted to take into account the performance of SFD in 2016 and reduced funding in 2017 (90% of expected budget).

Output Title	Community and Local Development Program: Basic services improved
Output number per LF		1	Output Score	A
Risk:		Major	Impact weighting (%):	70
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	No

Year	2012	2013	2014	2015	2016	2017	Overall
Score	A+	A	A	A	A	B	A

Year	2012	2013	2014	2015	2016	2017[10]	CT[11]
1.1 Education access: Number of classrooms constructed or rehabilitated	2,721 (2,400)	5,260 (4,600)	7,996 (6,800)	9,157 (9000)	9,637 (10,498)	9,875 (10,927)	90%
1.2 Education quality: Number of formal teachers trained (8 days training, sex disaggregated)			189 male (80) / 218 female (80)	232 male (100) / 226 female (100)	232 male (232) / 226 female / (226)	1,097 male / 447 female / (n/a already achieved)	330%
1.3 Rural roads access: Total length of roads improved/built (km)	323 (350)	619 / (460)	914 / (880)	1,168 / (1,300)	1,306 / (1,348)	1,420 / (1,473)	96%
1.4 Number of people provided with access to improved water sources (within 30 mins walking distance or less)	39,193 / (256,000)	68,097 (386,000)	530,834 / (516,000)	774,251 / (646,000)	941,801 (981,426)	1,150,537 (1,258,887)	91%
1.5 Sanitation access: Number of people with access to improved sanitation facilities	9,156 / (70,000)	23,134 / (135,000)	192,230 / (200,000)	232,725 / (265,000)	279,232 (323,955)	317,965 (348,060)	91%
1.6 Number of Primary Health Care workers qualified (3 year qualification)			206 male (240) / 168 female / (240)	266 male (300) / 220 female (300)	271 male (296) / 294 female (242)	320 male (325) / 315 female (264)	107%
To note: achieved scores are in bold while the numbers in italics indicate milestones or targets
[10] Targets (in brackets) for 2017 revised according to note at beginning of section C. See Annex I for 2017 in-year target scores.
[11] This is the score against DFID’s revised cumulative target (CT) based on the note at the beginning of section C

Key Points
SFD’s Community and Local Development Programme (CLD) aims to improve access to basic social services by implementing community-based projects and building the capacity of local authorities implementing development projects. Sectors of work include health, water and sanitation, education, and rural roads. All of the sectors involved in the programme actively coordinate and share information with their relevant UN Clusters (Health, Protection, Nutrition, Education and WASH). At 70%, the CLD programme has been assigned the highest impact weighting of SFD’s Phase IV.

SFD scored an overall result of A (outputs met expectations) for Phase IV of the CLD programme. This result is based on the lifetime of the programme during which SFD scored an A or higher for five years running (from 2012 to 2016) and a B in 2017. Cumulatively, SFD reached more than three times the amount of teachers it targeted (indicator 1.2), and also surpassed its target for the number of primary healthcare workers qualified (indicator 1.6). SFD only narrowly missed its cumulative targets for the remaining indicators (1.1 education access; 1.3 rural roads access; 1.4 water access; 1.5 sanitation access) due to underperformance in 2017[12]. While SFD attributes this underperformance to funding suspensions, the re-prioritisation of funds towards other activities, such as the cholera response, has also had a negative impact on reaching the CLD programme’s output targets.
[12] See Annex I for detailed in-year scores across indicators.

In general, SFD’s delivery in the CLD programme has been severely hampered by funding constraints, security concerns, restrictions of movements of goods and imports into Yemen, increased fuel prices, and power outages. While challenges to SFD’s work increased after the conflict erupted in 2015, funding and security concerns in the CLD programme were already noted in the annual reviews for 2013 and 2014.

Education
Under Phase IV, from 2011 to December 2017, SFD has built and/or rehabilitated 9,875 classrooms (indicator 1.1), and trained a total of 1,544 formal teachers (indicator 1.2), of whom 1,097 are male and 447 are female. Hence, cumulatively, SFD has reached 90% of DFID’s revised target of 10,927 classrooms, and 330% of DFID’s revised target of 458 formal teachers (232 male, 226 female). SFD missed its overall Phase IV target for built and/or rehabilitated classrooms due to underperformance in 2016 and 2017 - while fewer than 1,000 classrooms were built and rehabilitated in total between 2016 and 2017, nearly 9,000 classrooms were built and rehabilitated between 2011 and 2015[13].
[13] The in-year scores throughout SFD Phase IV are publically available in DFID’s Annual Reviews at https://devtracker.dfid.gov.uk/

As in other sectors, SFD has been under-resourced in education sector funding. Coupled with this, security challenges led to damage of a total of 207 education projects funded by SFD (53 completely, 119 partially and 35 slightly). DFID has previously expressed concerns about the maintenance and sustainability of built and rehabilitated classrooms. SFD has informed DFID of the measures in place to ensure maintenance is carried out[14].
[14] The SFD sub-project finance agreement signed by the Education Office and the Local Council states clearly that Local Authorities are fully responsible for the operation and maintenance of projects; SFD’s BOs monitor projects for 1 – 2 years after completion; SFD’s monitoring and evaluation unit conducts annual project- and community-level surveys to verify how projects are perceived by beneficiary communities and whether they are fulfilling their original objectives; findings reports are distributed to all SFD’s branches and units as well as to SFD's donors; SFD raises community awareness throughout sub-project lifecycles; and the community contribution to the project, whether land or in-kind, contributes to maintaining continuity of operation and maintenance.

Roads
Under Phase IV, from January 2011 to December 2017, a total of 1,420 km of rural road has been improved (indicator 1.3), of which 114 km was constructed during 2017. This means that SFD met 96% of DFID’s revised target of 1,473 km for Phase IV. SFD missed its final Phase IV target by 4% largely due to reaching only 68% of its in-year target of 167km in 2017. The conflict has negatively impacted the maintenance of constructed roads by local communities. This is an issue that must be addressed and is included in our recommendations.

Water and Sanitation
Under Phase IV, from 2011 to December 2017, 1,150,537 people were provided with access to improved water sources (indicator 1.4), while 317,965 people were provided with access to improved sanitation (indicator 1.5). Both of these figures fell 9% short of DFID’s revised targets of 1,258,877 and 348,060 for Phase IV, respectively. Delivery performance was lower in 2017, where SFD reached just 65% of its in-year target for access to improved water sources and 56% of its in-year target for access to improved sanitation[15]. Here, SFD has once again noted the funding constraints as the key reason for the suspension of projects.
[15] See Annex 1 for more details on SFD’s results for 2017

Around 90% of SFD's investments in the water sector have been towards rooftop rainwater harvesting systems. These systems are high in demand and have been very important during the crisis, where the provision of basic services and importation of fuel (which many water systems rely on) came to a halt. SFD has recently decided to include household water filters in every rural water project. However, there are only a limited number of suppliers of those filters due to the access restrictions into Yemen. In urban areas, where most of the water supply systems are completely dependent on the support of humanitarian agencies, SFD is supporting the use of solar panels as a form of renewable energy.

SFD has provided guidelines for the engagement of women in all stages of water project cycles, and hires female consultants to participate in the design and supervision of staff. DFID should follow-up on the results of SFD’s planned evaluation of these guidelines.

The Water & Sanitation Unit has contributed to the response to the 2017 cholera outbreak. Although SFD has no specifically allocated funds for the cholera response, it integrated cholera awareness campaigns into active projects across sectors. In 2017, 300,410 households in 1,148 urban and rural settlements received these cholera awareness messages, while 1,857 volunteers (1,061 male and 796 female) were trained to raise awareness on cholera in their communities. SFD also cooperated with communities to implement 674 initiatives related to combating cholera and acute watery diarrhoea. SFD continuously collects updates and disseminates information on the cholera outbreak in coordination with partners who are working in the field. This is welcome as it is important that SFD and the humanitarian community mutually interact and coordinate.

Health
Under Phase IV, from 2011 to December 2017, a total of 113 health facilities were constructed and/or renovated and equipped and 85 facilities were furnished. These facilities are expected to create access for 1.9 million people (67% female). Furthermore, a total of 635 primary healthcare personnel (320 male, 315 female) were qualified (3-year qualification) with nursing, laboratories and medical assistant diplomas (indicator 1.6). The latter number exceeded the original milestone of 589 (325 males and 264 female) by 7%.
The conflict and resulting suspension of funding has caused a number of projects in the pipeline of the health sector to be frozen. Furthermore, the health sector in Yemen (especially at unit levels of 5,000 people), has collapsed completely at an institutional level. Here, Sa’ada governorate is the most affected, with 80% of its health facilities damaged. Since 2015, the lack of capacity of the Ministry of Public Health and Population (MoPHP) has challenged SFD’s work. While SFD gathers and shares information on health needs from the grassroots levels, the Ministry is failing to act as a centralised body that makes decisions and strategies regarding health.
Summary of responses to issues raised in previous annual reviews
Previous annual reviews have noted the challenge of the sustainability and maintenance of infrastructure in the education and health sectors. While this is the responsibility of the GoY and/or communities, and outside of SFD’s direct control, SFD should ensure that any decisions to build or rehabilitate infrastructure are based on clear agreements with relevant stakeholders to look after these projects after their completion. SFD continue to coordinate with local authorities and stakeholders on these issues, and have informed DFID about the measures and processes in place that ensure maintenance of finished projects. This is particularly relevant given the current conflict and likely future scarce resources.

The 2016 Annual Review noted that DFID should increase the level of engagement and dialogue with SFD and structure it around specific sector issues to allow for focussed and more technical discussion of performance. In 2018, SFD began hosting monthly donor meetings where sector-wide issues and questions could be raised.

Recommendations
As poor maintenance and damages to infrastructure in education, health, and roads have been reported, SFD should ensure that any decisions to build or rehabilitate infrastructure are based on clear agreements with relevant stakeholders to look after these projects after their completion.

In order to improve communication and share technical knowledge on sector-specific challenges in the CLD Programme, DFID’s Programme Manager should invite sector-specific advisors on health, education, roads, and water and sanitation to review and discuss the CLD programme with the relevant SFD colleagues responsible for the given sectors at regular intervals.

SFD should consult DFID and other partners about any changes in their results framework, including the revision of targets and milestones.

SFD should consult DFID in their plans to change the allocation of funds in response to changes in prioritisation of projects.

SFD should continue promoting investments in clean water (e.g. rooftop rainwater harvesting systems). These systems are high in demand and a sustainable alternative to fuel-reliant water systems. They play an important role as a safe water source during outbreaks of diseases, such as cholera.

Output Title	Small and Micro Enterprises Development Program: Economic opportunities created
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	5%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	No

Year	2012	2013	2014	2015	2016	2017	Overall
Score	A	A	A	B	A+	B	A

Year	2012	2013	2014	2015	2016	2017[16]	CT[17]
2.1 Outreach Number of active borrowers: - % female - Number of additional branches in rural areas	79,563 clients (67,000) / Female - 64% (60%) / Rural - more than 15% (n/a)	94,966 / (78,000) Female -59% / (60%) / Rural – n/a (2)	118,223 (90,000) / Female -54%[18] by SFD) / (60%)	103,837 (100,000) Female - 56% (60%) / Rural - 6 / (6)	89,514 (90,000) / Female - 46% (50%;) / Rural – 2 (0)	85,716 (100,000) / Female – 42.8% (50%) / Rural – 2 (2)	N/A – target changed yearly
2.4 Financial Sustainability: Number of MFIs that are financially sustainable	1 / (3)	4 / (6)	1 / (7)	[19] / 0 / (7)	2 / (0)	1 / (2)	N/A – target changed yearly
To note: achieved scores are in bold while the numbers in italics indicate milestones or targets
[16] Targets (in brackets) for 2017 revised according to note at beginning of section C
[17] Cumulative target (CT) for Phase IV
[18] 62% if counting only those loans from MFIs directly supported.

Key points
SFD is a pioneer of the microfinance sector in Yemen. Starting in 1997, SFD began establishing a microfinance network and helping the Central Bank to issue microfinance loans in Yemen. Microfinance has since spread from rural to urban areas and attracted the private sector, while microfinance institutions, such as microfinance banks, have formed.

Throughout Phase IV, the microfinance sector has faced numerous challenges and instability. The early period of Phase IV saw the microfinance sector recover from the political uncertainty of 2011, and reach almost 120,000 borrowers in 2014 (exceeding their cumulative target for Phase IV). This relative stability was temporary due to the political volatility that evolved into conflict in 2015, as the number of active borrowers decreased from over 100,000 in 2015 to around 85,000 by 2017, and the number of microfinance institutions (MFIs) deemed financially stable fell from 5 out of 11 in 2014 to 1 out of 11 in 2015[20]. Furthermore, the proportion of the MFI portfolio classed as “at risk” increased from under 5% to nearly 55% between the end of 2014 and September 2016. Further challenges include the lack of liquidity, which has caused banks to set liquidity limits that make it hard for MFIs to disburse large sums of money.
[20] Previous Annual Reviews have suggested that the financial stability indicator is not a relevant measure for the current context of Yemen where risk and instability are vast.

In 2017, the Small and Micro-Enterprise Promotion Services (SMEPS) - a specialised unit working under the SMED unit to support microfinance institutions, small and micro enterprises and entrepreneurs - supported the diversification of twenty value chains, including support for 6,912 direct beneficiaries in the agriculture sector (28% female), from which 22,789 individuals (23% female) gained short and long term work. SMEPS’ support for farmers, fishers, midwives, households, youth, women and individuals through economic activities has provided communities with better access to education and health services. SMEPS is using innovative methods, such as matching grants, to leverage investments from the private sector. These projects have leveraged around $4 million from the business community.

The SMED unit has steadily increased its work since 2016, and remains important for maintaining the resilience of the microfinance sector. The new Loan Guarantee Programme[21] will help existing MFIs to cope with the negative effects of the conflict. Through the Loan Guarantee Programme, SFD shares the risk with MFIs that are lending to those who do not have sufficient guarantees. The Loan Guarantee Programme issued its first guarantee certificate in November 2017, and has received a total grant of $2 million to cover the guarantees of loans disbursed by MFIs. SFD is also assisting the Takaful Fund, which is designed to refund all small and medium enterprise owners who have lost their businesses and homes due to the ongoing armed conflict, or have suffered death or physical injury. Furthermore, the SMED unit has supported MFIs to establish risk management departments through training, capacity building and grants. This has resulted in each MFI in Yemen having a risk management department, which is a notable achievement, as none of the MFIs had this before the conflict erupted in 2015.
[21] In our discussions, SFD noted that they see the Loan Guarantee Programme as an emergency / contingency plan to support MFIs for a maximum duration of 4 years in case of protracted conflict. Without this service, they assess that 12 MFIs will stop providing services. SFD sees access to credit as a basic service that all people should have.

Throughout Phase IV, the SMED unit has proactively increased the capacity of its Management Information System (MIS). SMED regularly updates the loan tracking, HR, and accounting systems used in the MFIs. Mobile phone banking has also seen an increase during Phase IV, and is now provided through three banks, including Al Kureimi Islamic Microfinance Bank, which SFD helped establish and works with. Several MFIs have subscribed to these mobile phone banking services, and SFD expects that mobile phone banking will reach one million users in Yemen this year.

In the second half of 2017, SMED carried out field audits on clients of Al Itihad Microfinance Programme and Hadhramout Microfinance Programme. Respectively, these two MFIs received a total of $270,221 and $18,369 in grants in 2017. Clients of the Hadrhamout programme were generally satisfied, and recommendations relating to issuing loans, updating manuals, and overlapping tasks between some employees have now been implemented or are in progress. The report for the Al Itihad programme is being finalized and will be shared with the programme’s management.

Summary of responses to issues raised in previous annual reviews
Last year’s Annual Review recommended that DFID continue to monitor the state of the micro-finance sector in Yemen as well as the progress in use and scaling up of mobile phone banking. It also recommended that DFID intensifies its engagement with SFD’s SMED and SMEPS units, and that DFID officials should increase their engagement with the International Finance Corporation on issues affecting the private sector, banking system and MFIs.

Recommendations
DFID’s Economic Advisor should continue to develop DFID’s relationships with SMED and SMEPS and support their current operations and engagement with the International Finance Corporation and Yemeni institutions on issues affecting the private sector, banking system and MFIs

SFD should continue to monitor the state of the micro-finance sector in Yemen. This should include reporting on innovations, such as the increasing use of mobile phone banking.

SFD and DFID should review the indicator on financial sustainability to assess its feasibility in the current economic environment.

Output Title	Labour Intensive Works Program: Reduced vulnerability for the poor
Output number per LF		3	Output Score	A
Risk:		Major	Impact weighting (%):	20
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Year	2012	2013	2014	2015	2016	2017	Overall
Score	B	A	B	B	B	A	B

Year	2012	2013	2014	2015	2016	2017[22]	CT[23]
3.2 Number of people directly benefiting from short term workfare assistance in - rural areas - urban areas	Total -166,448 / (250,000; 85,300)	Total - 422,550 / (570,000; 85,300)	Rural -566,892 (768,000) / Urban - 255,570 / (331,600)	Rural – 648,712 (900,000) / Urban – 409,571 / (416,900)	Rural - 725,617 (798,712) / Urban - 426,026 / (479,571)	Rural - 819,203 (793,825) / Urban - / 497,290 / (510,986)	Rural - 103% / Urban - 97%
3.4 Number of working days employment created under workfare assistance program for: - Short term activities in rural areas - Short term activities in urban areas	Total - 2,322,173 / (3,000,000; 540,000)	Total - 7,215,612 / (5,500,000; 1,380,000)	Rural - / 7,800,000 / (9,500,000) / Urban -1,600,000 / (2,100,000)	Rural – 9,000,000 (13,100,000) / Urban – 1,800,000 / (2,640,000)	Rural – 10,200,000 (10,000,000) / Urban - 1,860,000 / (2,000,000)	Rural – / 11,200,000 (11,440,000) / Urban – / 2,200,000 / (2,400,000)	Rural – / 98% / Urban – / 92%
3.5 Land: Total area of agricultural rehabilitated terraces and land (hectares)	821 / (745)	2,878 (1,525)	3,635 (3,753)	4,441 (4,980)	4,579 (4,741)	5,187 / (5,227)	99%
To note: achieved scores are in bold while the numbers in italics indicate milestones and targets
[22] Targets (in brackets) for 2017 revised according to note at beginning of section C
[23] This is the score against DFID’s revised cumulative target (CT) based on the note at the beginning of section C

Key points
The Labour Intensive Works Programme (LIWP) was established in 2008 to provide temporary employment (4-6 months) on community asset construction projects to poor rural households facing food insecurity. In Phase IV, SFD planned to develop longer-term, multi-annual support (3-5 years) aimed at building productive capacity in poor households and enhance beneficiaries’ employability. However, in response to the increased unemployment and food insecurity since 2011, SFD scaled up short-term works rather than commencing multi-year interventions. This has allowed them to reach greater numbers of beneficiaries as a humanitarian measure, but not to provide the longer-term support which would aid early recovery into sustainable livelihoods.

LIWP has scored an overall result of a B (outcome moderately did not meet expectation) for Phase IV. Whilst improved performance in 2016 and 2017 (after World Bank funding was resumed in October 2016) meant that cumulative targets were almost reached, early delays to implementation, funding shortfalls and political and conflict developments led to mixed results prior to this time. Some of these - particularly related to the number of working days created and long-term workfare (cash for work) assistance - have at times been missed by considerable margins. The number of workdays created proved a problematic target even in 2017. Whilst SFD have put this down to funding shortfalls, our Independent Monitoring Programme highlighted this as an area where there were poor processes around data and monitoring, which may also have led to inaccuracies.[24]
[24] The Independent Monitoring Programme study concluded that there was inconsistency in data quality, and of implementation of quality and targeting standards and protocols across governorates. For example, on the number of workdays created, they found a discrepancy of 23.3% with SFD reports, with a bias towards over reporting.

The progress made since the end of 2016 is to the credit of SFD, however, and reflects what they can do when funding is readily available. For instance, the number of people directly benefiting from short term cash for works assistance increased in 2017 to 164,850 (covering urban and rural areas) up from 126,500 in 2016, and the total area of agricultural rehabilitated terraces and land to 608 hectares up from 173 hectares.[25] The type of activities undertaken were also expanded to reach new kinds of beneficiaries, for example through the introduction of new youth-led community activities. At the end of December 2017, there were 251 projects under implementation with an estimated cost of $19.5 m. This reflected the scale of humanitarian need and SFD’s prioritisation of cash provision to the most food insecure, as well as the fact that LIWP had become the largest recipient of donor funds. The adjustment of wage rates in 2013, 2016 and 2017 to increase the coverage of the programme also contributed to its expansion, and is an indication of SFD’s flexibility. As such, LIWP has remained an important social safety net, increasing people’s quality of life, prospects and resilience in a way that complements the wider humanitarian response.
[25] See Annex III for detailed 2017 scores. Further detail on the in-year scores for 2016 can be found in the 2016 Annual Review, publically available at devtracker.dfid.gov.uk/

DFID’s Independent Monitoring Programme visited LIWP in 2017. Please see the Monitoring and Evaluation section for further details.

Summary of responses to issues raised in previous annual reviews
Despite progress, some issues that have been prevalent over the course of Phase IV remain. This includes the challenge of women’s participation (largely due to the nature of work and cultural norms), to which SFD is aware. Women’s participation has increased incrementally over the years to its current 30% and SFD continue to work to improve.
Other recommendations raised in previous annual reviews include the need for more precise targeting, a thorough review of indicators (especially regarding the number of days worked and removal of the multi-year indicator), linkages with other sectors and the resumption of multi-year interventions. While there has been progress in linkages with other sectors, most of these recommendations are yet to be addressed.

Recommendations for future programmes
- SFD should continue to build on the positive advancements made over the course of 2016-17, including: finding ways to increase and improve the quality of women’s participation (notably, finding roles that are suited to women’s employment); expanding the types of beneficiaries reached (to include youth, marginalised communities and the disabled); and linking the activities with other sectors (for instance, SMED).
- Whilst acknowledging the positive impact of the short-term CfW on Yemenis, we continue to recommend that SFD implement multi-year CfW interventions as well, bearing in mind improved funding for the LIWP, the endurance of the conflict and SFD’s unique place to effectively complement the work of humanitarian agencies. This could be focussed in more stable areas more suited to early stages of recovery, leaving short-term interventions active in more fragile environments and where the needs are greatest.
- The number of days worked has remained a problematic indicator throughout Phase IV and the Independent Monitoring Programme project’s finding of poor processes and possible over-reporting is a concern. In line with other recommendations on reporting, SFD should ensure accuracy in the future and DFID should pay close attention in any future programmes.
- DFID should review the weighting of the Labour Intensive Works Programme (currently at 20%), given that it has become an area of increased focus by SFD, and is expected to continue to be so in the future.

Output Title	Capacity Building: Stakeholders capable and empowered
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	5%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	No

Year	2012	2013	2014	2015	2016	2017	Overall
Score	A	B	A	B	C	A+	A

Year	2012	2013	2014	2015	2016	2017	CT[26]
4.1 Number of people trained in M&E, participatory methods, planning or other strategic information management (disaggregated by male, female and Local Authority (LA) members trained on Empowerment and Local Development programme	Male - 334 (1,400) / Female – 311 (1,000) / LAs - 1,065 / (600)	Male - 475 (1,800) / Female - 485 (1,300) / LAs – 20[27] / (900)	Male – 777 (2,000) / Female – 681 (1,200) / LA - 4,868 / (1,200)	Male – 887 (2,500) Female – 702 (1,500) / LAs – 4,868 / (1,500)	Male – 887 (1,007) / Female – 702 (782) / LAs - 5,122 / (80)	Male -1,899 (1,127) / F- 1,667 (862) / LA: - 5,542 / (111)	Male - 168% / Female - 193% / LAs / 4,992%
4.2 Number of village councils in pilot areas which are functioning effectively: - meeting regularly - wide participation (sex disaggregated) - initiate self-help initiatives	1,344 / (600)	2,486 / (1,000)	3,806 / (1,200)	3,893 / (1,500)	4,316 / (4,283)	5,067 / (4,587)	110%
4.3 Organisation supported - Number of NGOs supported - Number of local authorities supported - Number of Community-Based Organisations formed			NGOs - 55 (75) / LAs - 50 (70) / CBOs -1,805 / (2,200)	NGOs – 55 (90) / LAs – 50 (90) CBOs - 1,832 / (2,500)	NGOs – 55 (66) / LAs – 50 (80) CBOs - 1,832 / (1,982)	NGOs – 55 (65) / LAs – 58 (77) / CBOs - 2,015 / (1,967)	NGOs –84% LAs - 75% CBOs -102%
To note: achieved scores are in bold while the numbers in italics indicate milestones or targets
[26] This is the score against DFID’s revised cumulative target (CT) based on the note at the beginning of section C
[27] Government Orgs - 9; NGOs & coops - 36; Local Coms - 1059; Priv. sector/indiv: 3,917

Key points
The Capacity Building Programme was designed to contribute to SFD’s three other programmes by building the capacity of local entities, including local and central government bodies, NGOs and community-level groups, who deliver services to poor people and communities. It has also worked to strengthen SFD’s own institutional capacity such as support for M&E and programme management. During the transitional period in Yemen, SFD saw this work as supporting the National Dialogue commitments to greater decentralisation and contributing to building the Yemeni state from the bottom up through linking communities with district authorities. It has adapted since 2015, most notably with the work of the Village Cooperative Councils and District Councils which have refocussed their attention to support the development of resilience and recovery plans. The Capacity Building Programme represented 14% of the total planned Phase IV budget but was consistently the most underfunded programme of SFD’s four.

This programme has seen mixed progress and somewhat erratic results over the course of Phase IV. In 2017, SFD fell far short on in-year indicator 4.3, particularly on the number of NGOs and local authorities trained (reaching 0% and 29% of their targets, respectively – see Annex IV for further break-down), primarily reflecting the prioritisation of funds in other areas of work. However, they considerably over-achieved in indicators 4.1 and 4.2: the number of people trained (1,432 people, achieving 421% of the in-year target for men trained and 603% of women) and the number of functioning Village Cooperative Councils (751, achieving 277% of the in year target). The former was down to an increase in the number of youth and the de-centralisation of training courses to branch offices, thus expanding into new geographical areas; the latter builds on a positive and resilient trajectory of the Tamkeen Empowerment and Local Development programme[28] over the course of Phase IV.
[28] Tamkeen Empowerment and Local Development programme constitutes one of two main components within the Capacity Building Programme, covering the activities monitored by DFID. It aims to empower the local authorities (LA) and communities to adopt participatory planning in line with the available local resources and in consistence with the national development strategies and policies.

This pattern is generally reflective of the scores over the course of Phase IV. Even in 2015 when the other strands of activity in this programme (and others across SFD’s portfolio) were suspended, Village Cooperative Councils continued to function and provide valuable contributions to local communities. Since their inception, Village Cooperative Councils and district committees have grown in number and become increasingly self-sufficient, playing active roles in creating local development plans, self-help initiatives and, since 2015, humanitarian and relief interventions. They also continued to function despite the funding shortfalls in 2016, and during the 2017 cholera outbreak proactively coordinated and supported awareness campaigns and conducted over 800 WASH related self-help initiatives. Women’s engagement has been strong, with women occupying 50% of the seats of the elected members by 2017. The contribution of the Tamkeen Empowerment and Local Development programme to community resilience, particularly in the current context, should not be underestimated.

The less consistent results for indicators 4.1 and 4.3 across the span of this programme have been down to a lack of funding, issues with indicators and contextual changes. The latter primarily concerns the impact of the conflict local governance arrangements which rendered SFD’s work to build community-authority relations more challenging.

Summary of responses to issues raised in previous annual reviews
The primary issue raised in previous reviews has been the indicators and targets for this programme. This has included both the realism applied to some of the targets and the appropriateness of the indicators, most notably whether the number of district level plans and initiatives should have been recorded rather than the number of Village Cooperative Councils and people trained.

Recommendations for future programmes
The Tamkeen Empowerment and Local Development programme should continue and possibly expand in Phase V, with note made of the positive role the programme is playing in maintaining social cohesion and, should the time come, in future efforts to strengthen peacebuilding and local governance.

In line with similar recommendations above, DFID should work closely with SFD on indicators and targets for Phase V to ensure suitability and mitigate a repeat of the over-reporting issues. This should include activities related to indicator 4.3, which have proved unsuitable in the post-2015 context.

In 2017, SFD were able to link their youth training and Tamkeen Empowerment and Local Development programme projects for the first time; they should continue to build on this progress and look at ways to join up within the Capacity Building project and other areas of SFD’s work.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Under Phase IV, from 2011 to December 2017, SFD completed 5,548 projects at a total contracted cost of about $779 million (not including SFD’s operation expenses and cost of studies and evaluations) with a total disbursed amount of $912 million (of which about $90 million was disbursed during 2017). Some of the agreements, which were signed during Phase III but concluded during Phase IV, are estimated to contribute around 23% of the total disbursement from 2011 to 2017. The estimated number of people directly benefiting from the interventions during Phase IV is 9.1 million (55% female). Completed and ongoing projects have generated 35.1 million person days of temporary employment. For a country with a population of 27 million, SFD’s investments have had a major impact on the country’s non-oil economy and particularly on the lives of the most vulnerable.

The deteriorating political, economic and security context in Yemen continues to have a significant impact on SFD’s cost drivers. Access restrictions and the fluctuation of currency exchange rates are amongst the economic concerns that have limited the availability and increased the prices of goods, such as fuel - a critical cost driver for SFD’s operations. Prices of other goods, such as construction materials, have also increased, while industries supporting SFD’s projects (including cement manufacturing, energy generation, trucking and transport) have also suffered disruptions and closures. The current import restrictions on spare parts may negatively impact SFD’s operations as well. SFD has taken measures to mitigate travel related expenses – by hiring consultants from local areas and remote monitoring of projects. While geographical barriers and remoteness may increase costs, SFD has noted that contractors are often willing to deliver project at lower prices than before.

While disbursement was highest in 2013, it began to decline in 2014 as a result of the political crisis and the suspensions of funding. This severely impacted SFD’s performance in 2015 and 2016, and forced SFD to enact cost-saving measures, including the reduction of staff numbers and salaries. SFD reported that there are still 12 agreements suspended, and one pending in parliament, worth a total of $441 million, of which only $162 million was received before the situation in Yemen declined.

The year 2017 has signalled a positive shift from 2015 and 2016, as some 788 new projects were approved at a total estimated cost of $166.5 million, of which 384 projects were completed at a cost of $57.9 m (in 2016, only 160 new projects were approved at a cost of $39.2 m). The increase of new approved projects in 2017 is attributed to additional funding signed with the United Nations Development Programme (UNDP) (as part of the Yemen Emergency Crisis Response Project) in late 2016, DFID’s additional funding of £8.4 m in 2017, and new agreements signed with KfW Development Bank in the third quarter of 2016 and in 2017. While the liquidity crisis still exists, the number of processed transactions has increased from 14,233 in 2016 to 19,904 in 2017. SFD enjoys the privilege of being a VIP client in local banks, and engages regularly in meetings with the heads of local banks to minimise the crisis impact on SFD’s operations.

VfM performance compared to the original VfM proposition in the business case

When considering the VfM of DFID’s contribution to SFD, this Review applies the ‘4E’ principles: Economy, Efficiency, Effectiveness and Equity. Following from the last review, DFID have considered the merits of different VFM indicators - the most relevant are discussed below:

Economy: the operating costs associated with managing the Fund were originally set at 6.4% of total costs, which is positive compared with other mechanisms that pool donor funds (UN rates are typically set at 8%). The actual annual allocations towards operating costs in 2015 and 2016, however (according to the independent auditor’s report from the end of 2016), were 9.9% and 12.7%, respectively. These figures are significantly higher than the actual allocation prior to the conflict in 2014 (3.2%). This is likely due to the operating costs becoming proportionally higher in the budget against the drop in funding for 2015 and 2016. While we have not yet received the financial audit report for 2017 (expected later in 2018), SFD has informed us that the expected figure for operational costs against total costs will be around 7%.

Efficiency: The Annual Reviews from 2015 and 2016 both highlighted the efficiency benefits of SFD as a means to pool and coordinate donor support to Yemen, but that suspended donor funding would represent a challenge. In 2017, this situation has improved through significant new funding from donors, such as the World Bank, UNDP and DFID. However, funding from regional donors, including the Kuwait Fund, Saudi Fund for Development and Arab Fund, remains suspended. Currently, there are 18 active donors; certain donors, such as the EU, now fund SFD through the UNDP, and are therefore no longer counted as a separate donor. Crucially, we do not see a growth in separate independent development projects that are not coordinated with others. The merits of SFD as an efficient mechanism to pool donor resources for development remains.

SFD’s SMEPS has shown remarkable efficiency as a VfM indicator. SMEPS is using innovative methods, such as matching grants, to leverage investments from the private sector. These projects have leveraged around $4 million dollars from the business community.

Effectiveness: Effectiveness can be measured by assessing progress against targets. Due to the challenging circumstances caused by funding suspensions, political and economic instability, and the conflict, progress has been notably slower during the years 2015 - 2017. While we acknowledge the role that funding shortfalls have played in SFD’s performance, SFD has been ineffective in clearly communicating how the reprioritisation of funds impacted different programmes. Nevertheless, when revising targets against the funding actually received from 2015 - 2017, SFD still scored A (outputs met targets) yearly. SFD’s effectiveness in terms of poverty targeting, community consultations and participation; efficiency in terms of coverage; and outcomes attributable to SFD interventions in the areas of education, health, water, rural roads and microfinance (accounting for 70% of SFD investments) were examined through external quantitative and qualitative evaluations at the end of Phase IV. Key findings confirmed SFD’s capacity to ensure the Labour Intensive Works Programme targets poor deprived communities and meets priority needs with 74% of households having at least one member participating in the programme. This proved to be a productive safety net approach to mitigating the impact of economic shocks, although evaluations found that benefits were unequally distributed across participants.

Equity: SFD is a neutral, non-partisan and autonomous institution that works to benefit all Yemenis. It has no political affiliation and has consolidated its reputation as a development agency working to benefit all vulnerable individuals and communities irrespective of their political, territorial or sectarian affiliations. Their needs are the guiding factors for SFD responses. SFD interventions also target the youth, for example through training programmes, and women and girls - the most vulnerable group in the current conflict.

Assessment of whether the programme continues to represent value for money

Last year’s Annual Review stated that SFD’s value for money performance is considered satisfactory in comparison to the original VfM proposition in the business case, particularly given the context within which it is operating. This remains the case for 2017, as highlighted by the improved disbursement rate and increased number of approved projects. The Annual Review noted that DFID should pay specific attention to SFD’s operating costs, which reached 9.9% in 2015 and 12.7% in 2016. However, this is expected to fall back to a level closer to the set target of 6.4% in 2017, as the proportion of operational costs against the total budget has decreased. Whilst SFD will highly likely remain the best value for money intervention of its type for Yemen, we should expect continued cost pressures for as long as the crisis continues. DFID and SFD should also consider ways of monitoring the economy and efficiency of work at a project level, which are both easy to collect and informative. For example:
- Typical consultancy day rates
- #km rural roads built per 1,000 workdays
- Total area of agricultural rehabilitated land and terraces (Hectares) per 1,000 workdays

Quality of financial management

SFD’s historically strong financial management track record has been praised throughout our Annual Reviews. SFD has received unqualified opinions by annual external auditors since 1997; the World Bank’s financial management experts have consistently given SFD positive ratings; and all disbursements by the Islamic Development Bank have been individually audited. SFD has also been subject to a DFID Due Diligence Assessment which concluded that SFD has the capacity and processes in place to effectively manage donor funds. An internal EU-commissioned assessment by the independent auditors Grant Thornton also reached a similar conclusion.

SFD’s automated, multicurrency/multi-donor financial management system allows SFD to track and record each transaction made across the organisation. SFD BOs and HQ also regularly undertake sample checks on payments.

Though the state of the banking system in Yemen continues to deteriorate, SFD currently reports that all local banks with which it has accounts are still functioning and are safe and feasible. DFID should continue to watch the status of the banking system within Yemen closely to mitigate developing risks, as well as the ability of donors to get funding to SFD in Yemen through the international banking system. We have continued to successfully make payments to SFD this year but have experienced significant delays in making the payments which has affected our internal forecasts due to SFD slower than expected rate of spending. SFD were also unable to fully spend all our funds by 31 December 2017 and provided DFID with very late notice (even although DFID continued to ask for updates and receive assurances on the spending situation) that a no cost extension until 31 March 2018 would be needed. Our payments are made directly from our bank account in the UK to an assigned DFID-SFD bank account in the Commercial Bank of Yemen. At no point do funds pass through the Central Bank of Yemen. We are confident in SFD’s management of these funds and receive financial expenditure statements before each new payment.

Date of last narrative financial report	December 2017
Date of last audited annual statement	December 2016

E: RISK (½ page)

Quality of risk management over the life of the programme
SFD Phase IV has taken place in an exceptionally difficult, changeable and risky environment. Between 2011-15, the main risks include: the political transition, economic decline, increased insecurity impeding programmes; SFD becoming unable to maintain its political neutrality; and suspension of donor funding. These remained much the same following the outbreak of the conflict, except with more emphasis placed on the conflict negatively impacting operational delivery and staff safety and increasing fiduciary risk. In addition to the conflict, the risk that has affected most greatly SFD’s operations has been the interruption of donor funds. In 2014/15 this forced SFD to significantly reduce both its staff and projects, and has since introduced a level of unpredictability that has been difficult to manage and had a significant impact on delivery.

That SFD has survived the funding shortages as well as the changes in the political, security and economic environment, is testament to the seriousness with which they have taken their risk management and the rigorous systems and procedures they have in place. These have evolved continuously over the course of Phase IV as SFD has responded to events, planned for possible future scenarios and learnt from its experiences, in particular from events in 2011 and 2015. Changes have ranged from the closure of branch offices to the introduction of new and secure Management Information Systems. More recent developments, such as the establishment of a new Complaints Handling Mechanism section in 2016 and organisation-wide training of anti-corruption procedures, demonstrate their continued efforts to improve. Their continued neutrality, access and long-established relationships have also been keen enablers in their adaptation and management of the situation.

The improvements to mitigate risks as well as the continued and uninterrupted funding to SFD in 2017 (after the suspensions that nearly halted their operations entirely in 2016) have allowed DFID to downgrade SFD’s residual risk rating from ‘Severe’ to ‘Major’. DFID should continue to engage closely on SFD’s risk management. Benefit might also be gained from a more regular and systematic approach to reviewing the risk register and assessing how these risks could impact the programmes, underpinned by rigorous contextual analysis and scenario planning.

DFID and other donors have also put appropriate risk measures in place. DFID’s Independent Monitoring Programme (see section H) has been key amongst these, in addition to our Anti-Corruption Counter-Fraud policy and due diligence assessments, which in 2017 included a review of SFD’s downstream partners. In 2013, USAID conducted a pre-award assessment of SFD’s fiduciary management and the World Bank undertook a financial management review, both of which were found to be satisfactory. The open and transparent process taken to appoint a new Managing Director in 2013 also proved critical for donor confidence, securing trust both in SFD’s commitment to good financial management and political neutrality.

The table below sets out the top risks remaining at the end of this programme:

TYPE	DESCRIPTION	RISK	MITIGATION MEASURES	RESIDUAL RISK
Fiduciary/ Delivery	Undermining SFD’s autonomy and/or undue interference in its operations, including a change in leadership leading to an increase in government coercion and misuse of funds.	Severe	As per the SFD establishment law and manuals, the Board of Directors has a limited authority over SFD's operational-level issues. / SFD to further elaborate its communication strategy with different parties. / Donors and SFD maintain a good geographical and sectoral balance in investments to avoid accusations of bias. / SFD informs donors of any event that affects its autonomy. / Donors should develop a harmonized supportive position towards SFD’s autonomy and political neutrality. / Donors have a third party verification mechanism to acknowledge and enhance SFD's credible performance. / Grant-based governance to be considered/adopted as a key safeguard. / Donors to play an assurance and mediation role with different parties whenever needed. / SFD has robust finance controls which limits the risk of misappropriation of funds.	Major
Delivery	Shortage of liquidity that hinder implementation	Severe	Introduce\use mobile banking as a mechanism for paying beneficiaries. / Where required, use alternative channels, such as money exchangers. / Work closely with the banks on more elaborate forecast of disbursement at various geographical levels.	Major
Delivery	Hard currencies/YER exchange rate differences further increase and decreased value for the extended benefits mainly through Cash for Work due to inflation	Major	Aligned exchange rate with active international agencies in Yemen. / Review and adjust share of HHs accordingly.	Moderate
Delivery	Insecurity effects delivery of programme. / Office level: / Possibility of SFD offices to be affected by violent activities / Office attendance disrupted	Major	Communicate with UN to de-conflict SFD premises / Activate emergency offices / Maintain data back-up in different places / Update and trigger emergency plans as the situation may develop	Moderate
	Field level: / Possible exposure of SFD's staff and consultants to direct life-threatening risk / SFD’s staff and consultants mobility limited	Major	Communicate with UN to de-conflict SFD project sites. / Avoid travelling to high-risk areas. / HQ and Branch Offices monitor security developments. / Intensify communication between offices and fields as required. / Use resident projects' implementation supervision consultants in project sites whenever possible.	Moderate

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
SFD has faced ongoing challenges to deliver against agreed timeframes over the course of Phase IV, due primarily to the difficult operating environment. As detailed above, this led to some targets being missed across the years, while the revision of milestones in 2016 was a contributing factor in the decision to extend Phase IV in 2015 and for DFID to provide the no-cost extension in early 2018. An MOU was in place between DFID and SFD to set out the requirements of DFID’s funding relationship with SFD. DFID ensured that payments to SFD were based on need i.e. at least 70% of previous payment tranches needed to be disbursed before any further payments were made to SFD. During the final year of funding, SFD frequently underspent against the planned payment schedule, leading to changing financial forecasts and a slower than expected spending rate. DFID continued to provide support to SFD despite the ongoing challenges as there is no credible alternative to SFD in Yemen. DFID is reassured that overall, SFD delivers good results and value for money.

Performance of partnership(s)
SFD has been a resilient and reliable partner throughout Phase IV, with a strong track record for delivery in the most challenging contexts. However, whilst remaining engaged and cooperative, there have been times when staff could have more proactively informed DFID of issues as they have arisen, and this is an improvement that should be pressed in future engagements. SFD recognises DFID’s core funding as being vital to their ability to remain resilient and adaptable, and would welcome a greater degree of technical support from DFID and other donors in the future. Donor coordination on SFD has been good across the Phase, but with room for improvement, particularly in terms of reducing the burden on SFD. Improvements should continue in this area.

Asset disposal and value obtained by DFID
N/A. DFID does not control or claim ownership of SFD assets. This is due to the un-earmarked nature of our support. However, downstream partner interviews conducted by DFID in June 2017 found that good practice was reported on asset management, with all partners except suppliers reporting SFD requesting regular asset registers. SFD also keep track of assets damaged during the conflict.

G: CONDITIONALITY (½ page)

Partnership principles assessment

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
DFID’s core funding includes support to SFD’s Monitoring and Evaluation (M&E) Unit. This Unit serves two objectives: a) supporting accountability to the GoY and donors, and; b) Supporting internal learning and development. The unit tracks the progress of sub-projects under implementation and SFD conducts annual project and community-level surveys to obtain beneficiary feedback. The unit also conducts and disseminates annual reports and six-monthly progress reports to donors. Additionally, as recommended by DFID in the Annual Review 2016, SFD now includes stories and case studies from the field and distributes them to donors.

SFD’s M&E Unit has performed well throughout Phase IV. M&E is an integrated aspect of all of SFD’s work, and is conducted thoroughly throughout project cycles. Furthermore, the improvements and innovations that SFD have made to data collection allow for enhanced and real time oversight of projects. SFD’s M&E activities include but are not limited to project surveys and impact evaluations. While progress reports and annual reports have at times been delayed, the Unit has responded pro-actively to any requests or suggestions for improvements. The Donor Relations Management Team has liaised effectively between SFD units and DFID.

Monitoring progress throughout the programme
SFD's Management Information System (MIS) collects data on the processes and progress of projects implementation including physical progress. Additionally, SFD staff at the BO level regularly visits project sites and discuss the progress of projects with beneficiaries. During 2017, more than 452 visits were carried out under the Cash-for-Work (CfW) program as well as 102 visits under the Roads sector’s interventions. Other activities in 2017 included evaluation studies on the impact of nutrition and community support interventions under the cash-for-social services components and a survey on the operational status of completed projects in 4 governorates. We recommend that SFD makes MIS accessible to donors online.

Since the start of the conflict in 2015 until December 2017, the number of projects damaged by the conflict reached 264 (compared to 225 in December 2016). In 2016 and 2017, SFD assessed the impact of the conflict on their work through monitoring their accessibility across Yemen and damaged projects. The number of inaccessible districts decreased to 15 in December 2017, compared to 21 districts in in December 2016. However, 11 governorates were reported by BOs as inaccessible, partially accessible, or difficult to access (compared to 10 governorates in December 2016).

SFD has conducted Project Utilization and Operational Status Surveys (UOSS) throughout Phase IV. The fourth round of UOSS covered 834 projects completed during the period (2011-2016) in education, roads, water, cash-for-work, and training sectors in four governorates: Hajjah, Amran, Hodeidah, and Raymah. The survey aimed to measure SFD projects’ operational status at the level of targeted community, as well as projects’ effectiveness, sustainability, and appropriateness toward community needs. The fieldwork was carried out during May-August 2017. The performance indicators for community participation and contribution were highly satisfactory. The surveys found positive overall results in a comprehensive array of sectors: education, water, roads, health, labour-intensive (cash-for-work) program, training and institutional support, and empowerment.

DFID has also monitored SFD's performance through its Independent Monitoring Programme. In 2016, a verification study of SFD's WASH interventions confirmed delivery of work, with strong performance in the targeting and quality of water provision projects. The study did, however, record several reporting issues that were leading to over-reporting and ineffective targeting (for sanitation projects). These issues were primarily the result of gaps in SFD’s MIS which they are now working to solve. SFD have also pro-actively identified a series of other follow up actions as a result of the study; we will monitor these to assure they are implemented.

An Independent Monitoring Programme study conducted on LIWP in 2017 found that more ‘affirmative action’ is required to overcome gender-specific constraints. Local attitudes and practices regarding women’s participation vary across governorates, districts and villages, indicating that a standardised protocol for working with women will not be adequate without being tailored to the local communities. SFD should take into account local practices and attitudes, and intensify work with communities to provide women with better options.

SFD should improve the reporting of results of its interventions. While SFD is continuously improving the methods of its data collection, namely through its Management Information System (MIS), the setting and revision of milestones and targets lacks adequate transparency. While we are aware that the suspension of earmarked funding affected sectors of SFD’s work at different scales (thereby requiring different prioritisation of funds available), there has been a lack of clear communication between SFD and DFID about how SFD restructured its funding allocation and revised the milestones. This has made it difficult to provide robust monitoring of SFD’s performance.

Lastly, improvements should be made to measure the quality of SFD’s interventions. Whilst DFID’s Independent Monitoring Programme provides some insights and assurances, it is hard to assess the quality of the interventions across the board. This should be considered in Phase V and as part of donor coordination.

Review Process

The Project Completion Review was completed by the Deputy Conflict Advisor and Policy Officer for DFID Yemen, with technical inputs from the team’s Statistics and Evaluation Adviser, Social Development Adviser and Economist, through a desk-based review. The data for the review is based largely on narrative and reports provided by SFD on a six-month and quarterly basis, interviews and other dialogue with SFD staff, and subject to discussion and scrutiny by DFID staff. The PCR has been quality assured by a Policy Manager of DFID Yemen.

Annex I. 2017 focused Detailed Output Scoring for Community and Local Development Program

Indicator(s)		Target 2017[29]	Achieved 2016	Achieved 2017	% of target reached	Score
1.1 Education access: Number of classrooms constructed or rehabilitated	Cumulative	10,927	9,637[30]	9,875	90%	B
	In Year	1,304		238	18%	C
1.2 Education quality: Number of formal teachers trained (8 days training, sex disaggregated)	Cumulative	232 male, / 226 female	232 male [31] / 226 female	1,097 male / 447 female	330% (target was achieved in 2016)	A++
	In Year	Target achieved in 2016		865 male / 221 female	No target set: unexpected increase	A++
1.3 Rural roads access: Total length of roads improved/built (km)	Cumulative	1,473	1,306	1,420	96%	A
		167		114	68%	C
1.4 Number of people provided with access to improved water sources (within 30 mins walking distance or less)	Cumulative	1,258,877	941,801	1,150,537	91%	B
	In Year	317,076		208,736	65%	C
1.5 Sanitation access: Number of people with access to improved sanitation facilities	Cumulative	348,060	279,232	317,965	91%	B
	In Year	68,828		38,733	56%	C
1.6 Number of Primary Health Care workers qualified (3 year qualification)	Cumulative	325 male / 264 female	271 male / 294 female[32]	320 male / 315 female	107%	A
	In Year	29 male / 22 female		49 male / 21 female	%	A+
[29] Target adjusted to account for the fact that SFD only had 90% of the anticipated budget for 2017.
[30] In 2016 Annual Review this is 9,715, but corrected in SFD progress report 2017 to 9,637
[31] In 2016 Annual Review this as 264 males, but corrected in SFD progress report 2017 to 232
[32] In 2016 Annual Review this is 274 females, but corrected in SFD progress report 2017 to 294

Annex II. 2017 focused Detailed Output Scoring for Small and Micro Enterprises Development Program

Indicator(s)	Milestone 2017	Achieved 2015	Achieved 2016	Achieved 2017	% of target reached	Score
2.1 Outreach Number of active borrowers: / - % female / - Number of additional branches in rural areas	100,000 / Female – 50% / Rural - 2	103,837, 56% female, 6 rural branches	89,514[33] / Female - 46% / Rural – 2	85,716 / Female – 42.8% / Rural - 2	86% / 86% / 100%	Overall: A / (target reached 2015) / 2017: B
2.4 Financial Sustainability: Number of MFIs that are financially sustainable	2	1 out of 11	2 out of 10	1 out of 10	50%	B
[33] Figures derived from SFD Progress report 2017. In 2016 Annual Review this is 90,416, 46% female, rural – 0.

## Annex III. 2017 focused Detailed Output Scoring for Labour Intensive Works Program

Indicator(s)		Target / 2017[34]	Achieved 2016	Achieved 2017	% of target reached	Score
3.2 Number of people directly benefiting from short term workfare assistance in / - rural areas / - urban areas	Cumulative	Rural – 793,825 Urban – 510,986	Rural - 725,617 / Urban - 426,026	Rural – / 819,203 / Urban – / 497,290	103% / 97%	A
	In Year	Rural – / 91,100 / Urban – / 84,960		Rural – / 93,586 / Urban – / 71,264	102% / 83%	B
3.4 Number of working days employment created under workfare assistance program for: / - Short term activities in rural areas / - Short term activities in urban areas	Cumulative	Rural – / 11,440,000 / Urban – / 2,400,000	Rural – 10,200,000 / Urban - 1,860,000	Rural – / 11,200,000 / Urban – / 2,200,000	98% / 92%	A
	In Year	Rural – / 1,440,000 / Urban / 540,000		Rural – / 1,000,000 / Urban – / 340,000	69% / 63%	C
3.5 Land: Total area of agricultural rehabilitated terraces and land (hectares)	Cumulative	5,227	4,579	5,187	99%	A
	In Year	648		608	94%	A
[34] 2017 output targets have been adjusted to account for the fact that SFD only had 90% of the anticipated budget for 2017.

## Annex IV. 2017 focused Detailed Output Scoring for Capacity Building Programme

Indicator(s)		Target 2017[35]	Achieved 2016	Achieved 2017	% of target reached	Score
4.1 Number of people trained in M&E, participatory methods, planning or other strategic information management (disaggregated by male, female and Local Authority (LA) members trained on Empowerment and Local Development programme	Cumulative	Male: 1,127 / Female: 862 / LA: 111	Male: 887 Female: 702 / LA: 5,122	Male: 1,899 / Female: 1,667 / LA: 5,542	Male: 168% / Female: 193% / LA: 4,992%	A++
	In Year	Male: 240 Female: / 160 LA: already achieved		Male: 1,012 / Female: / 965 / LA: 420	Male: 421% / Female: 603% / LA: already achieved	A++
4.2 Number of village councils in pilot areas which are functioning effectively: / - meeting regularly / - wide participation (sex disaggregated) / - initiate self-help initiatives	Cumulative	4,587	4,316	5,067	110%	A+
	In Year	271		751	277%	A++
4.3 Organisation supported / - Number of NGOs supported / - Number of local authorities supported / - Number of Community-Based Organisations formed	Cumulative	NGOs: 65 LAs: 77 CBOs: 1,967	NGOs: 55 / LAs: 50 CBOs: 1,832	NGOs: 55 / LAs: 58 / CBOs: 2,015	84% / 75% / 102%	B
	In Year	NGOs: 10 / LAs: 27 / CBOs: 135		NGOs: 0 / LAs: 8 / CBOs: 183	0% / 29% / 135%	C
[35] Target adjusted to account for the fact that SFD only had 90% of the anticipated budget for 2017.