Annual Review

Title: Central African Republic Humanitarian Recovery Programme 2016-2019
Programme Value £ (full life): £41,000,000		Review Date: 30 June 2018
Programme Code: 205286	Start Date: 30/06/2016	End Date: 31/03/2019

Summary of Programme Performance
Year	2017	2018
Programme Score	A	A
Risk Rating	Severe	Severe

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5236583.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-205286/documents

A. Summary and Overview

Description of programme

This is the second annual review of the Central African Republic Humanitarian Recovery Programme (CHURP). It contributes to three of the Single Departmental Plan results: humanitarian (# of people reached with humanitarian assistance - food aid, cash and voucher transfers - through DFID support); water, sanitation and hygiene (# of people with sustainable access to clean water and/or sanitation through DFID support); and nutrition (# of children under 5, women (of childbearing age) and adolescent girls reached by DFID through nutrition-related interventions). The programme was approved in 2016 and provides support totalling £41 million, with a further £19 million as internal contingency.

The objective of CHURP is to addresses urgent life-saving and protracted needs of conflict-affected populations in CAR and refugees in neighbouring countries who have fled violent conflict since December 2013. The programme focuses on two outcome areas in order to achieve this overall objective: (1) Address essential humanitarian needs in CAR and among CAR refugees; (2) Better co-ordination and coherence of the humanitarian, development and UN system in CAR. Both outcomes remain contextually relevant for achieving the programme objective, taking into account the significant increase in violence and resulting humanitarian needs in 2017, and the programme remains on track to achieve these outcomes.

Assistance is delivered across all sectors, with a focus on healthcare, food security and livelihoods. The programme has reached a total of 891,176 beneficiaries out of a target of 764,128.

Agencies - CAR response	Description
Food and Agriculture Organisation (FAO)	Livelihoods assistance
International Committee of the Red-Cross (ICRC)	Emergency and protracted assistance and protection
CAR Humanitarian Fund (CHF)	Emergency multi-sector assistance
MENTOR Initiative-led consortium*	Basic healthcare
Solidarités International (SI)-led consortium**	Livelihoods and protection support
Agencies - CAR refugees
World Food Programme (WFP) Cameroon	Food and nutrition support
UN High Commissioner for Refugees (UNHCR) Cameroon	Emergency multi-sector assistance

*NGO consortium led by MENTOR Initiative including International Medical Corps (IMC), Cordaid and Oxfam Intermón.
**NGO consortium led by Solidarités International including Action Contre le Faim (ACF) and Danish Refugee Council (DRC).
Summary supporting narrative for the overall score in this review

The project has scored an A overall, and is currently meeting expectations in terms of delivery and achievements in the face of a deteriorating and challenging environment. While the total number of beneficiaries reached in the past year has exceeded the target, this score represents the weighted scoring across outputs, outlined in the below table:

Output	Assessment	Score
1 – improve agro-pastoral production	Met expectations, with a significant increase in cash-based modalities compared to initial target.	A
2 - healthcare and protection support	Moderately did not meet expectations, as the MENTOR consortium significantly underachieved on healthcare milestones, which are disproportionately high for the challenging operational environment, although was able to adapt its response to emergency needs. The MENTOR consortium was also unable to meet its WASH targets, however the overall target was exceeded through CHF and ICRC activities.	B
3 – nutrition in CAR	Moderately did not meet expectations, FAO was able to meet its nutrition prevention targets, but was unable to demonstrate the nutritional outcomes of this activity. The MENTOR consortium has performed well in treatment of malnutrition, but was unable to meet its nutrition prevention targets due to deteriorating security conditions.	B
4 – humanitarian coordination (rapid and effective decision-making)	Met expectations, with the CAR Humanitarian Fund continuing to perform at a high level and making significant contributions to coordination and enabling actions.	A
5 – Displaced Central Africans see their basic needs met and communities are supported in hosting them	Met expectations, with both WFP and UNHCR meeting their targets for assisting displaced Central Africans in Cameroon.	A

The scoring also reflects the impact of the significantly deteriorated security situation on the programme’s activities in CAR during the past year. 2017 saw a resurgence of violence and proliferation of hotspots across the country, at a level which had not been experienced since 2014. The fragmentation of armed groups and increase in community based militias resulted in a surge of violence in areas of previous stability, and areas which had become calm fell back into instability. The sharp rise in conflict across the country has had devastating humanitarian consequences, with a 70% increase in internally displaced persons (IDPs) by the end of the year.

While humanitarian actors have stretched resources to respond to these increasing needs, they have also faced an increasingly challenging and hostile operating environment. Security incidents involving humanitarian staff have increased significantly (332 in 2017 compared to 131 in 2016), and several DFID partners had to suspend or relocate activities due to insecurity. The moderate underachievement in nutrition and health activities during this review period can largely be attributed to these operational challenges hampering partners’ ability to meet ambitious targets. While the deteriorating security context hampered the country’s early recovery gains initially envisaged at the start of 2017, DFID’s partners have exceed their targets in terms of agricultural support activities although the impact of these interventions on household food security is not yet clear due to a lack of evidence from implementing partners.

As the Humanitarian Response Plan remained significantly underfunded at 39%[1], a symptom of CAR continuing to represent one of the world’s most severe forgotten crises[2], the programme’s focus on maximising the performance and efficiency of the humanitarian response remains extremely relevant. DFID’s support to the highly performing Humanitarian Fund continues to represent a strong vehicle for achieving this objective.
[1] CAR Humanitarian Fund Annual Report 2017
[2] ECHO Forgotten Crisis Assessment 2017, https://ec.europa.eu/echo/sites/echo-site/files/annex_4_fca_sep2017.pdf

With spreading violence in CAR limiting the potential for Central Africans to return from Cameroon, DFID’s support of £2.25M to WFP (representing 11% of their total funding) remained relevant and appropriate. WFP has increased the efficiency of its food security and nutrition interventions to continue meeting the needs of the full refugee caseload despite significant funding gaps. While UNHCR’s livelihoods interventions have contributed to increasing refugee’s self-reliance, it has been more difficult to ascertain how DFID’s support of £1M has contributed to UNHCR’s operation.

Recommendations for the year ahead

The following recommendations cover multiple partners or outputs. Partner-specific recommendations are listed under each output.

- Accountability to affected populations: The inadequate provision of relief and protection activities, resulting from chronic underfunding, may have adversely impacted affected communities’ perception and acceptance of humanitarian actors. As such, strong accountability to communities, in the form of communications on activities and feedback mechanisms, is an essential part of the humanitarian response in CAR. Despite the recommendations in the previous Annual Review, accountability continues to represent a weakness in several partner’s response. In addition to continue to pushing partners to develop their own accountability tools, such as complaint response mechanisms, it is recommended that DFID contributes to supporting the roll-out of a collective accountability system, and encourages participation amongst implementing partners.
- Food security and nutrition outcomes: DFID to engage with FAO and CHF to develop appropriate evaluation frameworks for measuring the outcomes of food security and nutrition interventions, in coordination with relevant clusters. This may include adoption of standard universal outcome indicators, including Coping Strategy Index, Food Consumption Score, and Food Diversity Score. It is recommended that DFID CAR team liaise with nutrition colleagues to support the development of appropriate indicators for FAO’s nutrition sensitive programming.
- Integration of services for refugee response: With the recent approval of the World Bank IDA Sub-Window for Refugees, there is a good opportunity for provision of refugee services (education, health, livelihoods etc.) to be further integrated into national systems. DFID should follow up with WFP and UNHCR, both of which plan to access IDA funds, to ensure these agencies support this integration through strong coordination with relevant development and government actors.

## B: DETAILED OUTPUT SCORING

Output Title	The agro-pastoral production and food security in the targeted areas is improved and reinforced
Output number per LF		1	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	Yes ↑

Indicator(s)	Milestone(s) for this review	Progress
Number of people in CAR reached through livelihood and food security assistance / (FAO, ICRC, CHF, Solidarités International-led Consortium)	109,090 / (of which FAO: 75,000; ICRC: 4,813; CHF: 22,308; SI: 6,969)	Met expectation: 103,341 / (of which FAO: 75,000; ICRC: 4.365; CHF:18,638; SI: 5,338)
Number of beneficiaries receiving assistance through market-based cash and vouchers / (FAO, ICRC)	25,206 / (of which FAO: 25,00; ICRC: 206)	Significantly exceed expectation: 42,900 / (of which FAO: 42,500; ICRC: 400)

Provide supporting narrative for the score

The programme has achieved its milestone for livelihood and food security assistance, reaching 96% of persons targeted for assistance in the past year. The CAR Humanitarian Fund (CHF) had a slight shortfall in reaching its target, as food security was not prioritised by the CHF this year due to complementary funding from OCHA’s Central Emergency Reserve Fund (CERF); a total of $1.7M USD was provided from the CHF to fund seven food security projects, while the CERF provided $6M USD in February 2017 for food distribution by WFP.[3]
[3] CAR Humanitarian Fund 2017 Annual Report

FAO has provided support to a total of 117,500 beneficiaries in 2018 through both the direct distribution of seeds and tools (Indicator 1: 75,000 beneficiaries), and the provision of vouchers to be used to purchase agricultural inputs at local seed fairs (indicator 2: 42,500 beneficiaries). FAO was able to substantially exceed its target for assistance through market-based vouchers through efficiency savings, also taking into account evidence from the 2017 post-distribution monitoring showing this to be the preferred assistance modality by persons targeted under the programme. Initial results from post-harvest monitoring show that on average each household was able to produce approximately 950kg of peanut, maize, rice, squash, and sorghum, and earn approximately $285 USD from the sale of surplus produce. While these initial results are encouraging, it is not yet possible to determine the extent to which these achievements have affected household food security. According to FAO, a more comprehensive post-harvest evaluation has taken place in 2017, which includes specific food security indicators, and it is expected that these will be reviewed as part of the PCR. As such, while FAO has significantly exceeded its beneficiary target, the current lack of evidence concerning the outcomes of its interventions has reduced the scoring of this output to an A instead of an A+.

ICRC has supported a total of 139,000people (4,365 through DFID funds) with productive inputs to improve food insecurity (Indicator 1), including seeds, tools, and disease-resistant cassava cuttings; the provision of these cuttings takes into account that cassava represents the staple diet of much of the CAR population, and therefore reinforces traditional, pre-existing coping strategies. The cultivation of the cuttings provided to beneficiaries also provided cash for work opportunities (Indicator 2) for households to cover their basic expenses, along with other activities including the rehabilitation of marketplaces and the construction of structures to support vaccination activities. Through these activities, ICRC has provided cash support to 12,728 people (400 through DFID funds).

Despite significant security challenges in the Ouham prefecture in 2017, the Solidarités International-led consortium (SI) was able to reach 77% of its beneficiary target for livelihood activities (Indicator 1: 5,338 beneficiaries). Following serious security incidents, consortium partner DRC was forced to re-locate its activities from Batangafo to Bossangoa, and SI’s activities around Kabo were severely restricted. The consortium’s value-chain approach, which included market rehabilitation, the provision of grants to traders, and supporting small-scale agriculture through seeds and tools, has benefited a total of 5,338 people during the six-month intervention. 80.7% of beneficiaries indicated an improvement in their living condition by the end of the project. Given the project’s relatively short (six month) implementation period, the project’s longer term impact on household food security will be more difficult to determine.

Summary of responses to issues raised in previous programme

- Accountability measures and targeting: In order to further reinforce accountability to affected populations and to improve feedback on the quality of beneficiary selection and the performance of partners, it is recommended that FAO develops a feedback and complaints mechanism across its operations: While this issue has been taken forward with FAO, there was no clear evidence that actions have been taken during the past review period.
- Coping strategies: Consider revising the indicator targets to map against expected incremental reduction in negative coping strategies and ensure the indicator is ‘SMART’: As FAO did not propose a revision of the indicator despite prompting from DFID, it has been subsequently removed from the logframe. While it may not be feasible to include this specific indicator in FAO’s logframe, discussions need to continue concerning appropriate methods for evaluating programme outcomes.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Accountability measures and targeting: it is recommended that DFID continue to engage with FAO on the implementation of a feedback and complaints mechanism. This may involve, or be additional to, participating in the planned collective accountability system.
- Food Security Outcomes: DFID to follow up with FAO on the issue of evidence relating to food security outcomes, and to engage with the Food Security Cluster and Humanitarian Country Team on the potential development of harmonised inter-agency approaches for evaluating food security programmes.

Output Title	Affected population are reached by healthcare, water and sanitation and protection support
Output number per LF		2	Output Score	B
Impact weighting (%):		25%	Impact weighting % revised since last AR?	Yes ↑

Indicator(s)	Milestone(s) for this review	Progress
Number of beneficiaries reached in CAR by healthcare support / (ICRC, MENTOR Initiative-led Consortium)	454,451 / (of which MENTOR: 452,801; ICRC: 1,650)	Significantly did not meet expectation: 250,129 / (of which MENTOR: 247,630; ICRC: 2,499)
Number of people with improved access to water and sanitation - hard activities only / ICRC, CHF, MENTOR Initiative-led Consortium)	85, 880 / (of which MENTOR: 55,34; ICRC: 19,333; CHF: 11,200)	Significantly exceed expectation: 162,982 / (of which MENTOR: 13,246 ; ICRC: 30,951, CHF: 118,785)

Briefly describe the output and provide supporting narrative for the score

Due to the sharp deterioration in security across partners’ areas of operation in 2017, the healthcare milestones set for this output have not been achieved. In the case of the MENTOR Consortium, reduced access to locations affected by conflict significantly limited the number of curative consultations. The CAR government’s public health financing (PHF) policy of targeted gratuity, which limits free treatment to children under 5 and pregnant or lactating women, has also continued to present a barrier to healthcare access in certain areas covered by consortium partners. While the consortium switched to full gratuity in most areas during the past review period, in response to the emergency needs of affected populations, this change only came into effect from January 2018 for certain health centres within MENTOR Initiative’s areas of operation (Paoua) and remains in place in other areas (Batangafo). Despite an increased number of consultations in health centres which have switched to full gratuity, the healthcare milestones set for the consortium remain disproportionately high considering the challenging operational context.

While the consortium was unable to meet its specific healthcare support milestone, it was able to adjust its approach to respond to the needs of the conflict-affected communities through re-prioritising resources for emergency activities. This included the activation of mobile clinics to increase availability of services, increasing support to secondary healthcare facilities, and the switch to full gratuity to ensure access to treatment for all. These emergency activities allowed the consortium to provide healthcare support to approximately 30,860 people. The consortium now has an established emergency response budget line to allow partners to rapidly re-allocate resources in response to any further emergencies.

Deteriorating security conditions severely impacted planned water and sanitation (WASH) infrastructure activities at health facilities. While consortium partner Oxfam was able to rehabilitate one water point at a health facility in Markounda in December 2017, benefiting an estimated 492 people[4], they were unable to initiate any other construction or rehabilitation works planned during the past review period. Unlike other consortium partners, who were able to adjust and continue implementation, Oxfam’s internal security and risk management processes limited the organisation’s capacity to implement. In January 2018 the decision was taken to discontinue Oxfam’s role in the consortium and find other solutions to deliver WASH activities. Despite the limited progress made implementing WASH activities in the past review period, an estimated 12,754 people have continued to benefit from Cordaid’s rehabilitation of the Nzelete Health Facility water point in from October 2016.
[4] This figure is calculated based on the number of people who have received consultations at the health facility from December 2017.

Projects supported by the CAR Humanitarian Fund ensured the provision of healthcare services to 125,501 patients through the supply of medicines and equipment, the training of health personnel, and the management of maternal and infant health services. The CHF was able to significantly surpass its water and sanitation targets, and with DFID funding provided 118,785 people in IDP camps and host communities with potable water and access to household and public latrines. Projects also focused on light rehabilitation of water and sanitation infrastructure at health facilities to support medical interventions.

ICRC was also able to overachieve on both healthcare and water and sanitation infrastructure targets. Through the provision of medical supplies, staff support, and infrastructure upgrades, ICRC supported four primary healthcare facilities to provide consultations to 79,588 people. A total of 698 patients were also referred to an ICRC-support hospital for secondary healthcare. ICRC supported local water authorities to construct and repair urban water networks, benefitting approximately 836,000 people, and a further 149,700 people in rural/semi-urban areas and IDP camps.

Summary of responses to issues raised in previous programme

- DFID to include the case of CAR, alongside discussions of DRC and other countries, in ongoing discussions on World Bank’s health financing policy in fragile and conflict contexts including issues of free access to healthcare and Performance Based Financing (PBF) approach: Dialogue on health financing policy has been maintained with the World Bank and other humanitarian and early recovery donors during regular visits to CAR (quarterly visits by DFID Humanitarian Adviser).
- DFID to revise indicators around health utilisation rate and GBV services to improve measurability while recognising the barriers to achieving international standards for access to healthcare: this has been completed.
- DFID to request a detailed follow up of the WASH component of the MENTOR Consortium to avoid delays and ensure integration with the health component: the consortium has responded to delays in WASH implementation with the termination of consortium partner Oxfam and the re-planning of activities. Further detailed follow up is required.
- DFID to request MENTOR to assess the capacity of the consortium to respond to emergency healthcare needs, given the changes in the context and capacity of other healthcare actors, and consider whether a revision may be necessary given the significant increase in needs: the consortium budget has been revised to facilitate emergency activities, with a new emergency preparedness and response line in place.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Healthcare targets: the targets for MENTOR Consortium do not seem to be achievable, and it is recommended that these are revised for the next review period.
- Public health financing: In order to influence the development of health financing policies which are most appropriate for the population, it is recommended that DFID supports MENTOR Consortium to source additional capacity to enable effective and constructive participation in these policy discussions.
- Water and sanitation infrastructure: In light of the limited timeframe available for MENTOR Consortium to implement the WASH component of their programme, it is recommended that DFID follow up with the consortium to ensure that a detailed new work-plan and budget is developed, with a regular review to evaluate progress and make any necessary adjustments.

Output Title	DFID helps improve children's, women's and girls' nutrition in CAR
Output number per LF		3	Output Score	B
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of new malnutrition cases from children under 5, adolescent girls (10-19) and women under 50 in CAR that gain access to treatment (includes SAM and MAM cases) / (MENTOR Initiative-led Consortium)	769	Significantly exceed expectations: 1,501
Number of children under 5, adolescent girls (10-19) and women under 50 in CAR with improved capacity to prevent malnutrition / (FAO, MENTOR Initiative-led Consortium)	52,780 / (of which MENTOR: 45,280; FAO: 7,500)	Significantly did not meet expectations: 17,531 / (of which MENTOR: 7,531; FAO: 10,000)
Cure rate among children treated for acute malnutrition / (MENTOR Initiative-led Consortium)	Above 75%	Significantly exceeded expectations: 87%

Provide supporting narrative for the score

DFID’s programme in CAR specifically addresses the issue of undernutrition through support to MENTOR Consortium and FAO, through healthcare services and nutrition sensitive activities. While these activities form part of a wider response programme for these partners, the specific nutrition indicators are outlined here in order to assess how DFID’s funding is addressing malnutrition in CAR.

Through its healthcare support activities, MENTOR Consortium has treated 1,501 children, girls, and women under 50 years old for severe and moderate acute malnutrition (SAM and MAM), significantly exceeding its target for 2017. This is a reflection of both increased humanitarian needs in 2017, as well as the consortium’s ability to adapt its response and respond to emergencies (outlined further in Output 2). Cordaid’s capacity to effectively treat malnutrition cases was supported by International Medical Corps (IMC) through a ‘reinforcement team’ visit to Alindao in early 2018. The consortium’s average cure rate for SAM over the past year stands at 87%, well above SPHERE standards and higher than the national average of 84%. Despite these achievements, healthcare providers continue to face delays in the supply of therapeutic rations from UNICEF, which poses a potential risk of reduced treatment capacity amongst partners and a subsequent increase in the default and mortality rate. In MENTOR Initiative’s area of operation (Paoua and Batangafo) only MSF provides treatment for cases of severe acute malnutrition with complication, and there is no treatment of cases without complications. There are also continued gaps in the treatment of moderate acute malnutrition.

Consortium partners have continued to conduct nutrition sensitisation activities, including culinary demonstrations with groups of pregnant or lactating women with children in Bria hospital, supported by IMC. The deteriorating security situation and resulting access limitations for community health workers (CHWs) in 2017 has significantly affected the consortium’s information, education, and communication activities (IEC) activities, including sensitisation on malnutrition. As a result, the consortium has fallen significantly short of meeting its malnutrition prevention target (7,531 beneficiaries reached from a target of 42,280). Given that the security situation in 2018 is likely to continue causing access restrictions for CHWs, it may be necessary for the consortium to revise the IEC targets to reflect what is achievable in the challenging operating environment.

FAO has reached 2,000 households (approximately 10,000 people) through supporting 50 groups of poultry producers in and around Bangui. FAO identified poultry rearing as an appropriate nutrition-sensitive intervention based on the lack of protein in diets and poor availability of meat at local markets. Each group was provided with a package of inputs to start their projects (eggs, equipment, vaccines, and feed for three months), in addition to training on poultry management, finance (for managing income from poultry sales) and basic hygiene (focused on prevention of malnutrition). While FAO has recently conducted an evaluation of this activity to verify the outcomes of the intervention, initial observations from a DFID monitoring visit in April 2018 indicate the impact on household nutrition may be limited; semi-structured interview with DFID revealed that beneficiaries did not intended to consume the chickens, nor use the funds raised through the sale of poultry to improve household dietary conditions. It is expected that these outcomes will be assessed in further detail during the PCR, assuming that FAO is able to provide relevant evidence.

While the programme has significantly exceeded expectations in terms of the treatment of malnutrition, both in terms of beneficiary numbers and cure rate, the significant underachievement of the malnutrition prevention component has resulted in the overall output scoring of a ‘B’ (moderately did not meet expectations). This scoring also emphasises the need for follow up on key actions in order to improve overall output performance.

Summary of responses to issues raised in previous programme

- DFID to follow up on FAO’s implementation of nutrition activities and measurement of outcomes: DFID has conducted a field monitoring visit in April 2018 to selected project sites in order to verify progress and any initial outcomes. Initial observations from the visit suggest that the intervention may have limited nutritional outcomes. Although FAO has confirmed that an evaluation has taken place, they were not able to provide any evidence for this review.
- DFID to continue to follow up on the wider issue of access to nutrition case management across the response, including coordination between actors for prevention and case management, supply issues and achieving quality indicators: DFID has supported the CHF to fund the WASH and Health & Nutrition cluster NGO co-facilitator positions in order to improve sectoral coordination. The increasing complementarity of the health and nutrition clusters is a positive sign to improving the profile of nutrition within the crisis, and ensuring integrated approaches. MAM services remain a gap, which will be difficult to address given the security and underfunding situation. Following the last Annual Review, DFID increased scrutiny on the performance of nutrition activities implemented by Cordaid, including through a monitoring visit. Performance and complementarity has considerably improved in this review period. Supply issues continue to be challenging requiring the use of buffer stocks in addition to UNICEF’s RUTF pipeline.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Nutrition prevention milestones: As deteriorating security conditions have adversely affected MENTOR Consortium ability to deliver Information-Education-Communication activities, it is recommended that the malnutrition prevention milestone is revised for the next review period.
- FAO nutrition prevention outcomes: DFID to continue following up on FAO’s measurement of nutritional outcomes, in order to ascertain the appropriateness of continuing this activity in the next business case.

Output Title	DFID empowers humanitarian coordination for rapid and effective decision-making in CAR
Output number per LF		4	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	Yes ↓

Indicator(s)	Milestone(s) for this review	Progress
% of emergency reserve allocations dispersed to projects within 30 days	85%	Significantly did not meet expectation: 29%
% of CAR HF projects monitored through field visits within their project duration	40%	Significantly exceed expectation: 69%

Provide supporting narrative for the score

The CAR Humanitarian Fund disbursed a total of $26.3M USD in 2017 through two standard allocations and five emergency reserve allocations, benefiting an estimated 990,858 people in need.[5] The majority of funds (59%) were disbursed during the first 6 months of the year, which represents a significant improvement compared to 2016 where only 41% of funds were disbursed before July. Significant 4th quarter donor contributions, which lead to significant budget carry over to the next year, remained a challenge in 2017 and is likely to continue given the reality of donor funding cycles and CAR’s neglected crisis status. DFID was the largest fund donor, contributing $7.13M USD by August 2017. The fund retained its base of nine donors from 2016, demonstrating continued donor confidence.
[5] This figure includes a certain amount of double counting. While the CHF has made progress on reducing double counting within clusters, which partly accounts for the reduction in beneficiaries compared to 2017, it is difficult to fully avoid double counting between clusters.

Given the high demand for limited CHF funding, detailed geographical and thematic prioritisation of allocations was necessary, taking into account other funding sources to avoid duplication. As the $6M USD allocation received from the CERF in February 2017 was entirely allocated to WFP for food distribution, food was not prioritised for the CHF’s first standard allocation. The CHF conducts regular consultations with key donors (OFDA, ECHO, Bekou Fund) to map funding gaps, and the CHF Advisory Board (which includes several donors) provided an addition level of analysis to ensure the avoidance of duplication.

Five emergency reserve allocations, representing 33% of total allocations, were used to address emergency ‘hotspots’ of acute humanitarian needs resulting from conflict, including Bria and Bambari. 29% of emergency reserve disbursements were made within a 30 day period from the decision of the CHF advisory board to activate an allocation. Key challenges impacting the speed of allocations include the managing agent’s (UNDP) complex global finance system, resulting in protracted timelines for fund transfers, and delays in partners signing the grant documents. OCHA and UNDP are developing strategies to increase disbursement efficiency, which includes further automating the CHF grant management system and outsourcing financial spot-checks to a dedicated financial audit firm. It is expected that these initiatives will increase UNDP’s capacity to manage contracts and payments with greater efficiency.

The CHF was able to monitor 69% of projects in 2017, with project visits prioritised based on budget and risk level. These monitoring visits are supported by cluster co-facilitators, who provide added technical value based on their sector-specific expertise. Four of the co-facilitator positions (health & nutrition, WASH, food security, and protection) are funded through the CHF. In addition to supporting with CHF allocations and monitoring, these NGO co-facilitators make strong contributions to strengthening their clusters through NGO capacity building and maintaining links with regional sub-clusters. The CHF has also supported the humanitarian system through funding two logistic platforms managed by NGOs Premiere Urgence International (PUI) and Humanity and Inclusion (HI). The transport and storage solutions offered through this platform, which can offer significant efficiency savings, is currently used by 18 NGOs and UN agencies. While CHF funding is not a sustainable solution for these types of ‘enabling’ activities, it has allowed these activities to continue while agencies try and access more long term donor funding.

While the CHF has not succeeded in meeting its milestone of dispersing 85% of emergency reserve allocations within 30 days, as per the reasons outlined above, other performance-related factors have resulted in this output scoring an ‘A’ for this review (met expectations). These include the CHF’s ability to effectively prioritise funds, thematically and geographically, and support enabling activities which strengthen the overall humanitarian response in CAR.

Summary of responses to issues raised in previous programme

- DFID, together with other donor representatives on the CHF Advisory Board, will engage with the CHF’s donor base to encourage other donors to resume or increase funding to the CHF, by September 2017: DFID has regularly engaged with SIDA and SDC to discuss CHF funding and adopt common positions on the Advisory Board. DFID encouraged donors such as Germany to continue to support the CHF, offering to share feedback on CHF performance. While DFID’s share of contribution to the CHF has increased in 2017, the overall number of donors has remained the same.
- DFID to do a lessons learning piece on the CAR CHF’s continued high performance: This has not been completed and will be prioritised for the next review period.
- DFID to consider the weighting and nature of this output as part of the logframe review: The weighting was changed from 20% to 15% and indicator 4.1 has been revised.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Accountability to affected populations: While the CHF expects its downstream partners to have appropriate beneficiary complaints and feedback mechanisms, there is no specific CHF-level system aside from a complaints email address which is not accessible for the majority of the affected population. To increase accessibility, it is recommended that the CHF contributes to the development of system-wide accountability mechanisms.
- Outcome indicators: The CHF currently lacks tools and processes for measuring project outcomes, making it difficult for DFID to evaluate the effectiveness of the CHF. It is recommended that the CHF engages with relevant clusters to explore possibilities for developing outcome indicators, drawing on best practices from other country based pooled funds.

Output Title	Displaced Central Africans see their basic needs met and communities are supported in hosting them
Output number per LF		5	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Yes ↑

Indicator(s)	Milestone(s) for this review	Progress
Total number of people who have received basic food assistance / (WFP)	191,000 / (DFID proportion: 80,300)	Met expectation: 189,258 / (DFID proportion: 51,008)
Number of pregnant women and children under five who receive nutrition support aimed at preventing MAM - blanket feeding / (WFP)	40,000 / (DFID proportion: 40,000)	Met expectation: 40,675 / (DFID proportion: 11,293)
Number of individuals (refugees and most vulnerable nationals) who benefit from livelihoods support activities / (UNHCR)	5,280	Met expectation: 5,527
Number of persons of concern registered by biometric registration / (UNHCR)	61,518	Met expectation: 58,759
Number of refugees who access primary healthcare services / (UNHCR)	5,280	Significantly exceeded expectation: 90,044

Provide supporting narrative for the score

The number of CAR refugees in Cameroon remained relatively stable in 2017, although approximately 9,000 entered into the northern region of Touboro in April 2017 following clashes in communities over the border. While voluntary repatriation was considered in early 2017, increasing violence in potential areas of return has put the development of a Tripartite Agreement on hold. UNHCR has registered an additional 58,759 refugees through its biometric enrolment system, which aims to eliminate duplicate registrations and provide all refugees with identification documents.

UNHCR has also supported 90,044 refugees to meet their basic healthcare needs through the provision of staff, training, and equipment to 39 health centres. Within the framework of implementing community activities, refugees are included as Community Health Agents which allows for a better sensitization within the refugee community and reinforces social cohesion. A livelihoods strategy has recently been developed by UNHCR, and in 2017 5,527 individuals have been supported to increase their self-reliance through activities including agricultural development and vocational training. In order to increase social cohesion, approximately 30% of people benefiting from these activities came from host communities. UNHCR has recently piloted multi-purpose cash in order for refugees to meet their non-food needs, with cash delivered through a joint transfer with WFP.

In 2017 the World Food Programme (WFP) provided food assistance to approximately 189,000 CAR refugees in Cameroon through a combination of in-kind and cash transfer support. Approximately 51,000 of these refugees were assisted through DFID funding. While this DFID-specific figure is significantly lower compared to the milestone of 80,300, this is based on a re-prioritisation of DFID’s resources to provide food assistance to a smaller number of refugees but for a longer period of time. As such the number of person/months of support remains the same as the original target.

Refugees were located in seven established UNHCR refugee sites and 78 off-camp sites, situated along border entry points and local villages in the East, Adamaoua and North regions. Following extensive market analyses and series of beneficiary consultations, WFP have increased the proportion of beneficiaries receiving food assistance through cash transfer from 16% in 2016 to 25% in 2017. The increased use of the cash modality has also benefited local traders, the majority of whom are also refugees and are no longer dependent on food assistance.

Funding constraints resulted in WFP reducing the size of the monthly food ration and cash transfer value to 50% for most of 2017, impacting refugees’ food consumption; monitoring results from September 2017 showed that 25% of refugees had poor or borderline food consumption scores, compared to 16% for the same period in 2016. Following an increase in funding, WFP was able to increase ration sizes to 75% from September 2017. While ration cuts allowed WFP to continue providing food assistance to all CAR refugees, it is expected that the implementation of vulnerability-based targeting in 2018 will minimise the risk of further cuts through ensuring that adequate assistance is provided to only the most vulnerable households. The ‘food for assets’ programme has helped to increase the self-reliance of approximately 3,300 refugees in 2017, which included the creation of fish	ponds and planting of moringa trees to strengthen dietary diversity.

In agreement with the Government of Cameroon, WFP included preventative activities in its 2017 nutrition programme in order to tackle long term issues concerning nutritional practices and child stunting. Through establishing ‘preventative platforms’, WFP provided supplementary feeding to 40,675 children aged 6-23 months, in addition to complementary services including immunisation, micronutrient supplementation, and sensitisation on appropriate hygiene, feeding and cooking practices. Nutritional screening results at the end of 2017 showed Global Acute Malnutrition (GAM) levels amongst children aged 6-59 months at 1.94 percent compared with 4.2 percent the same period in 2016, and down from a staggering 30% at the peak of the refugee influx.

Summary of responses to issues raised in previous programme

- DFID to set up Headquarters level dialogue with UNHCR, to support in-country engagement on improving coordination and partnerships, and to track progress with the development of a livelihoods strategy to promote refugee self-reliance, in parallel with continued engagement with the World Bank as they develop their programme, by December 2017: UNHCR is in the process of submitting several proposals for IDA Refugee Window funding covering 2018- 2020, which will complement its recently developed livelihoods strategy. The headquarter-level dialogue scheduled for October 2017 was cancelled by UNHCR and never rescheduled. DFID has engaged with the UNHCR country office to produce more transparent reporting on the use of earmarked funds, however this continues to be a challenge.
- DFID to encourage other donors to support refugee operations, highlighting the risk that underfunding will reverse gains made in stabilising the nutrition and food security status of CAR refugees: DFID has engaged with BPRM, ECHO, Bekou Fund and Food for Peace on refugee funding issues.
- Continue to monitor funding levels, and advocate to other donors on maintaining funding for refugees in Cameroon, given the lack of conditions for large-scale sustainable returns: As above.
- As part of the logframe review DFID to ensure the milestones for UNHCR are correct: this is ongoing, and relates to the aforementioned challenge concerning UNHCR reporting.
- DFID to continue to engage with WFP and the Cash Working Group to promote an increased uptake in cash programming, where appropriate to context: WFP has increased the proportion of refugees receiving cash transfers, and UNHCR will start piloting multi-purpose cash in 2018.
- DFID to engage with WFP on aligning strategy and targets with available resources; and to monitor the impact of the reduction in food rations and cash transfer values: DFID’s monitoring mission in August 2017 facilitated engagement in WFP’s strategy to move towards targeted assistance and increased cash transfers. WFP has monitored the impact of ration cuts on food consumption scores in 2017.
- DFID to ensure WFP’s data and expertise is used in influencing other actors (UNHCR, FAO, International Fund for Agricultural Development (IFAD), World Bank) to developed appropriate resilience and long term Livelihoods Strategy: WFP has contributed to the development of CAR refugee profiling and IDA refugee sub-window strategy.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Vulnerability targeting: DFID to follow up with WFP and UNHCR on implementation of vulnerability targeting, particularly in terms of accountability to affected populations and budgetary implications.
- Livelihoods coordination: DFID to engage with WFP and UNHCR to understand how DFID-funded livelihood activities integrate with IDA programmes as part of wider livelihoods strategy.
- Milestone indicators: DFID to follow up with UNHCR and WFP on their 2018 milestones to ensure that these are appropriate and achievable.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The programmes’ theory of change (TOC) is summarised in the below diagram:

Reduced suffering and improved resilience among CAR populations and refugees
To help create security, political and governance environment conducive to recovery through advocacy with FCO, the EU and MINUSCA.
Improved humanitarian coordination and flexibleresponseto surge in neds
Empower humanitarian coordination for rapid and effective decision-making
Provide rapid reponse to spikes in needs among CAR populations, IDPs and returnees.
Improved response to protracted needs and transition to recovery in CAR
Provide access to essential health services
Support early recovery in livlihoods and agriculture
Help reinforce social cohesion and support local reconciliation
Address urgent needs among CAR refugees
CAR refugees access food assistance
CAR refugees see other essential needs met
Ensure key development actors (WB, EU) are adequately linked up with humanitarian funding streams.
Ensure IFIs provide adequate support to economic recovery.

All components of the TOC remain relevant to the context and for reaching the programme’s overall objective, and there have been no major changes in the past year. As part of the annual review process, TOC assumptions have been tested through consultations with partners and relevant actors from the wider humanitarian and development communities. The programme’s delivery approach has allowed DFID to support an appropriate balance of early recovery, protracted needs, and acute emergency interventions for Central Africans in CAR and Cameroon. Furthermore, the programme has also demonstrated the flexibility required to adapt to the deteriorating security situation in CAR. As this is one of world’s most under-funded crises[6], DFID’s emphasis on ensuring strong coordination within the humanitarian community and between development and humanitarian actors is essential for maximising the delivery of available resources. The DFID and FCO joint advocacy strategies, focusing on key issues including effective peacekeeping, fighting impunity, and security sector reform, remain essential for the programme’s early recovery objectives and ensuring space for humanitarian action.
[6] According to the ECHO Forgotten Crises Index

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The planned impact of CHURP is ‘reduce suffering of crisis affected people in CAR and among CAR refugees, and support to recovery’. The related outcomes are:

- Increased effectiveness of humanitarian action in protracted crises
- Improved quality and coverage of emergency response
- Enhanced focus on supporting simultaneous delivery of relief and recovery assistance at individual, community and country level.

 The programme remains on track to achieve its outcomes based on three indicators:

1. Number of people in CAR reached yearly with DFID humanitarian assistance (2018 milestone: 622,422; achievement: 750,845)
2. Number of displaced Central Africans reached yearly with DFID humanitarian assistance (2018 milestone:141,796; achievement: 141,052)
3. The CAR Humanitarian Fund (CHF) continues to have a sustained donor base (2018 milestone 8; achievement:9)

The beneficiary figures outlined above are directly attributable to DFID funding. As such there are no significant changes required in programme delivery in order to achieve the objective outlined in the TOC.

Explain major changes to the logframe in the past year

The changes made to the logframe as a result of the 2017 Annual Review are outlined below.

Output	Change	Rationale
1 - The agro-pastoral production and food security in the targeted areas is improved and reinforced	Removal of indicator ‘Up to 95% of project beneficiaries are not induced to resort to negative mechanisms related to food insecurity’	The indicator was removed as it was not possible to set a meaningful target or reformulate the indicator to make it ‘SMART’
2 - Affected population are reached by healthcare, water and sanitation and protection support	Removal of indicator ‘health service utilisation rate per person per year’	The indicator was not appropriate to the context, given the significant barriers to healthcare access
	Removal of indicator ‘Number of beneficiaries in CAR supported in the protection sector’	The indicator was considered too broad given the diversity of protection activities
	Removal of indicator ‘Number of GBV survivors in CAR who access remedial services’	This indicator was not appropriate, as any increase in number may have been a result of an increase in actual incidences of GBV
6 - Displaced Central Africans see their basic needs met and communities in are supported in hosting them	This output was merged with the previous Output 5 ‘Central African refugees in Cameroon access basic food assistance’	The outputs were merged as it was decided that food assistance and nutrition activities could be included under the category of ‘basic needs’
7 - Participation in HCT and donor meetings, and contribution to EU Trust Fund and World Bank consultations	This output was removed from the logframe	Output 4 – ‘DFID empowers humanitarian coordination for rapid and effective decision-making in CAR’ is more relevant for ensuring the CHF has a sustained donor base compared to the previous Output 7. The programme should therefore focus on achieving the indicators under Output 4.

Describe any planned changes to the logframe as a result of this review

1. Review of Mentor Consortium’s healthcare and nutrition prevention milestones: it is recommended that this milestone is revised to a reduced figure based on what is achievable for the CAR context.
2. Review of WFP and UNHCR milestones: Based on further discussions with the partners, it may be necessary to adjust these milestones to better reflect DFID’s proportion of funding for their refugee response operations.

## D: VALUE FOR MONEY

Assess VFM compared to the proposition in the Business Case, based on the past year

The VFM propositions outlined in the business case remain relevant and valid, based on the ‘3E’s model’ of effectiveness, efficiency, and economy. Implementing partners have made progress maximising VFM in their interventions, based on metrics such as cost, timeliness, and quality/appropriateness.

Effectiveness (spend wisely)

The portfolio of implementing partners allows the programme to continue providing an effective combination of early recovery and relief support. In addition to protracted needs in areas of existing insecurity, humanitarian operations in CAR have been further stretched in 2017 through sharp spikes of insecurity in previously stable areas. Through the programme’s partnerships with ICRC and the CHF, DFID has been able to support rapid responses to meet the acute needs of conflict affected populations in these ‘hot spot’ areas. In 2017 the two partners have supported the basic needs of approximately 2 million Central Africans.[7]
[7] This figure may include (a level of) double counting between the two partners.

The partnership with the MENTOR Consortium has proved particularly effective for responding to emergency health needs, as demonstrated through the consortium’s capacity to re-allocate resources to support gaps in secondary healthcare and facilitate mobile clinics to access displaced populations. After two years of implementation the programme is able to demonstrate the effectiveness of multi-year programming, through the use of learning, skills transfer and evidence to more appropriately respond to the needs of affected populations. Following beneficiary feedback gained from the first year of implementation, FAO and WFP have increased the proportion of beneficiaries receiving cash-based transfers compared to direct distributions during this review period.

Tools for gaining beneficiary feedback on programme effectiveness, such as complaint response mechanisms (CRMs) have been embedded in the programme, although vary in scope and quality among partners. Mentor Consortium has conducted a satisfaction survey across its areas of operation, the result of which show 89% of people were satisfied with the services provided by health facilities. In response to this feedback the consortium is implementing an action plan to address specific shortcomings identified through the survey. SI’s final evaluation highlighted that 80% of beneficiaries were very satisfied, in terms of quality and timeframe, with the support they received.

WFP and UNHCR implement CRMs comprised of complaint management committees and hotlines for the Cameroon refugee response. Between July and December 2017 WFP’s hotline system received approximately 400 calls per month, a significant decrease compared to 2016, and separates the complaints and feedback into specific categories in order to identify challenges and respond accordingly. In comparison to other partners, FAO and CHF currently lack comprehensive feedback mechanisms, and it is recommended that these partners engage in system-wide accountability initiatives to ensure people who benefit from their activities are able to provide feedback.

Efficiency (spend well)

In response to the increase in humanitarian needs in 2017, an additional £3M was provided to the CHF through the business case’s contingency facility. Funds were disbursed to the CHF approximately one month after the internal funding submission was made by DFID’s CAR team. This represents the programme’s flexibility to scale up where necessary, a key efficiency metric outlined in the business case.

Certain partners have integrated cost-per-beneficiary analysis into their monitoring and planning as a standard metric for maximising output efficiency. This analysis forms part of the CHF’s scorecard system used for evaluating and selecting potential projects through its standard and emergency reserve allocations. To ensure funds are provided to partners within an appropriate timeframe, the CHF’s Common Performance Framework sets a timeframe of 11 days from project approval by the HC to disbursement of funds.

MENTOR Consortium has developed harmonised efficiency metrics between the consortium partners, including cost-per-beneficiary and timeliness of implementation compared to work-plan timeframes. As of May 2018, 70% of the consortium’s activities are ‘on track’ or ‘in progress’, with WASH interventions representing the 30% of activities indicated as ‘delayed’ or ‘off schedule’ Partners have used ‘reinforcement visits’ to increase technical capacity within the consortium. This has included IMC supporting Cordaid to improve their malnutrition treatment capacity. This system of capacity exchange has demonstrated the added value of the consortium approach, allowing DFID to support the capacity development of multiple agencies through a single partnership agreement.

WFP’s switch from malnutrition treatment to prevention activities has resulted in a 20% increase in beneficiary reach, while reducing the total programme costs by almost 50%. As malnutrition rates have continued to decrease amongst the refugee population (1.94% in 2017 compared with 4.2% in 2016), this change of strategy has proven to be both effective and efficient.

Economy (spend less)

FAO was able to group its purchases across the three main donors (DFID, OFDA, ECHO) thus minimising input acquisition costs and increasing synergy across agricultural activities. All tools and 94% of seeds were purchased in country, compared to 2016 when 88% of seeds were bought locally, and 2015 when 80% were locally purchased. Through these efforts to maximise economies of scale and reduce procurement costs, FAO was able to re-allocate savings to provide an additional 17,500 households with seeds and tools.

While there are opportunities to reduce implementation costs in CAR, cost drivers such as limited transport infrastructure, insecurity and local availability of quality inputs (such as medical equipment and medicines) continue to result in an expensive operating environment when compared to other humanitarian contexts.

Equity (spend fairly)

While not originally assessed in the business case, DFID and its partners have implemented measures to ensure that assistance is available to all persons of concern as per the Core Humanitarian Standard and DFID’s policy of leave no one behind. Beneficiary data disaggregated by age and sex has been collected by the majority of partners to ensure potentially marginalised groups (children, women, elderly) are fully incorporated into programmes. The CHF’s gender mainstreaming approach and associated gender marker ensures that partners take into account the participation and representation of women in their proposals, which is then verified by the CHF during monitoring visits. These processes have been supported through OCHA’s gender adviser.

MENTOR Consortium uses ‘Female Focal Points’ to sensitise their communities, particularly women and girls, on sexual and reproductive health issues as well as on other general health topics. Mentor has also implemented a coding system in order to ensure confidentiality when SGBV survivors are referred to MSF, which has resulted in an increase in women seeking treatment. The consortium has also collected details of people with disabilities using the standardised ‘Washington Short Set’ of questions,

SI’s approach of integrating livelihood and psychosocial activities ensured that particularly vulnerable groups of individuals in psychological stress were included in the programme. The consortium ensured that the needs of girls, boys, women, and men of all ages were taken into account during community-level needs assessments.

Explain whether and why the programme should continue from a VFM perspective, based on its own merits and in the context of the wider portfolio (1 page)

Based on the above review of four dimensions of economy, efficiency, effectiveness and equity, the programme is delivering good value for money in a very difficult operating environment. The limited resources available for humanitarian and early recovery interventions means there is a strong VFM culture amongst DFID’s partners. Through the business case’s contingency facility and the partner flexibility and adaptability, the programme has been able to adapt and respond to the deteriorating humanitarian situation in 2017. While there are possibilities for adjusting certain aspects of partners’ implementation to deliver even stronger VFM, such as improving beneficiary feedback mechanisms, these can be achieved within the parameters of the current programme.

E: RISK

Overall risk rating: Severe
CAR risk rating: Severe
Cameroon risk rating: Major

Overview of programme risk (noting the rating from p.1) and mitigation

While the programme’ risk registers have been regularly reviewed and updated, through monitoring visits and discussions with partners, the overall and country-specific risk ratings for the programme have not changed since the last annual review. The deterioration in the security and political context in CAR over the last 12 months means that the overall risk rating for programme delivery in the country remains ‘severe’. Partners in CAR have demonstrated their ability to scale up and respond to increasing humanitarian needs, as per the mitigation strategy outlined in the programme’s risk register. Despite this achievement, reduced humanitarian access and minimal early recovery interventions caused by the continuing proliferation of conflict remains a severe risk for the programme. The significant security challenges experienced by the two NGO Consortia during the past year, resulting in the re-location and suspension of activities, illustrates the challenging operating environment which aid organisations face in CAR.

Escalating conflict in CAR continues to present a severe risk of spill over in the form of increased refugee numbers to neighbouring countries, particularly Chad, DRC and Cameroon. The presence of DFID staff in these countries ensures that this risk is closely monitored, and the programme’s contingency facility allows DFID to support partners to scale up their response if necessary.

DFID’s CAR Humanitarian Adviser for the programme has travelled to the country every three months to meet with partners, donors, and relevant humanitarian and development agencies in order to continually assess the contextual risks, as well as partners’ individual risk management and mitigation processes. Contact with partners in Cameroon is closely maintained through a Humanitarian Adviser based in-country. In the case of the CHF, risk of potential resource mismanagement and fraud is mitigated through a due diligence process conducted for new partners. The CHF grant management system ensures that partners’ risk levels are assessed at the end of each stage of the project cycle, with controls such as withholding payments introduced where necessary. The harmonised due diligence approach used by OCHA, UNDP, WHO, and UNICEF facilitates the sharing of information on potential fraud between these agencies.

MENTOR Consortium continues to perform particularly strongly on security and risk management, which includes the maintenance of a risk register outlining the potential impact on activities and mitigation measures. An updated risk register is shared with DFID as part of the consortium’s quarterly reporting, in addition to a security bulletin to provide further details on security issues and implications on consortium partners’ activities.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

Delivery against planned timeframe

The programme is on track to reach its objectives by 2019, with the majority of output indicators achieving their 2018 milestones.

Delivery chain map

DFID has worked with partners to map the delivery chain of downstream partners and will continue to update the delivery chain as required over the course of the programme. Summary diagram of the delivery chain map:

DFID
FAO
NGOs
1 Government body
ICRC
2 Red Cross societies
UNDP (CAR HF)
NGOs
UN agencies
WFP
NGOs
M&E
Palladium
Standby Partnerships
UNHCR
NGOs
1 UN agency
Mentor Initiative
IMC
Cordaid
Oxfam Intermon
Solidarites International
DRC
ACF

Performance of Partnerships

DFID continues to maintain a collaborative approach with the partners in this programme. Of note:

- MENTOR Consortium maintains strong communications with DFID, particularly on issues concerning security and implementation challenges. This strong communication has proved effective for re-prioritising resources in light of the increased emergency needs in the consortium’s areas of operation. The recommended revision of Mentor’s targets will help to ensure that the consortium achieves its healthcare support milestones.
- FAO has achieved its milestones for its agriculture support activities for the second consecutive year. Further efforts need to be made to demonstrate the nutritional outcomes of the poultry component of the project. The partner also needs to put the necessary systems in place to reinforce accountability to affected populations.
- CHF continues to perform well in terms of responding to funding gaps and emergency needs through its system of standard and emergency allocations. Further work is also required to strengthen the CHF’s accountability to affected populations.
- There continue to be issues with UNHCR’s reporting and responsiveness to requests for information, particularly concerning beneficiary numbers, although the quality of their narrative reporting has improved since 2016.
- WFP continues to provide accurate and timely reporting, in addition to responding quickly to DFID’s additional requests for information.

Asset monitoring and control

This programme includes two Accountable Grant Arrangements - the MENTOR Initiative-led Consortium and the Solidarités International-led Consortium - in which DFID owns the project assets until transfer or disposal is agreed. Asset spot-checks were carried out for each consortium by DFID’s Humanitarian Adviser in October 2017. MENTOR Consortium carried out a full asset check across all partners in early 2018. Following the completion of SI’s project, DFID is working with SI to agree the transfer and disposal of the consortium’s assets.

All partners have agreed visibility statements where applicable. Recent field visits have confirmed that MENTOR are branding UKAid appropriately and FAO have provided photographic evidence of branding at their distribution sites and seed fairs. WFP also adhere to the agreement with WFP food commodity packages, vendors participating in cash-based transfers, and distribution sites being appropriately branded. CHF branding was observed to be uneven, during field visits.

Date of receipt for last narrative financial report(s)	FAO	November 2018 (interim report)
	ICRC	June 2018 (annual report)
	CHF	January 2018 (2017 annual report)
	WFP	February 2018 (interim-report)
	UNHCR	February 2018 (interim report)
	MENTOR Consortium	May 2018 (quarterly report)
	Solidarités Consortium	February 2018 (final report)
Date of last audited annual statement (s)	FAO	Due July 2018
	ICRC	N/A
	CHF	May 2018
	WFP	June 2017
	UNHCR	August 2017
	MENTOR Consortium	June 2018
	Solidarités Consortium	June 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

DFID does not have a country office in CAR, although a Humanitarian Adviser (HA) is fully allocated to oversee the programme and conduct regular monitoring visits. During the past review period, the HA visited CAR in May 2017, September 2017, January 2018, and April 2018, with each visit lasting 7-10 days. During these visits, in-depth meetings were held with each partner and with a wide range of stakeholders. Several field locations were visited in order to monitor partners’ activities (MENTOR Consortium and CHF), including Bambari (Ouaka), Paoua (Ouham-Pende), and Alindao (Basse Kotto). The results of these field visits allowed the HA to verify the quality and appropriateness of activities, and provide feedback and recommendations to implementing partners. While a planned field visit to Bocaranga in April 2018 was cancelled due to insecurity, the HA and additional DFID staff were able to monitor FAO’s nutrition prevention activities in Bangui’s peripheral areas. The field visits also provided DFID staff with an opportunity to interact with beneficiaries and receive direct feedback on any concerns or suggestions relating to programme activities. DFID received narrative reporting from partners on progress and issues and held calls with partners on a regular basis. WFP agreed to clarify in their results reporting whether the figures quoted relate to the overall achievement or DFID’s attributable proportion.

DFID engaged a HA based in Yaoundé in 2015 to provide oversight of DFID programmes in, Chad and Cameroon, including the CAR refugees in Cameroon under this programme. The Cameroon-based HA regularly liaises with the DFID CAR team, and maintains contact with implementing partners (WFP and UNHCR). In August 2017, the Programme Manager and HA fully allocated to CHURP travelled to eastern Cameroon to visit WFP and UNHCR-funded projects. The visit resulted in several recommendations, which have been communicated to partners and followed up by the HA, covering issues such as targeting, accountability to affected populations, and the need for a more comprehensive livelihoods strategy.

Evidence

Partners have generally provided a good degree of evidence in order to determine the achievements made during the programme thus far. This includes data from monitoring reports, post-distribution surveys, and health centre records. WFP and SI have conducted evaluations to determine the food security outcomes of their interventions using food consumption score (FCS) and coping strategy index (CSI) indicators. While WFP’s programmes in Cameroon have a clear impact on the refugee population’s overall food consumption, as evidenced by the significant reduction in FCS following the 50% reduction in rations, SI’s agricultural programmes in CAR only resulted in 20.5% of beneficiaries experiencing an improved CSI score. As outlined in Section B, the short implementation period of SI’s project (six months) makes it difficult to draw out any significant food security outcomes. As FAO has not yet provided details concerning the impact of their programmes, more evidence is required to better understand how agricultural interventions implemented under CHURP have improved food security in CAR. It is expected that the results of FAO’s post-harvest evaluations will allow further details of this to be provided at PCR stage.

WFP, CHF, and MENTOR Consortium have used universal indicators (SAM cure rates, and GAM rates) to demonstrate the outcomes of their nutritional programmes in CAR and Cameroon. FAO has not yet provided evidence concerning the outcomes of their nutrition sensitive poultry programme, although findings from DFID’s direct monitoring visits suggest that the programme is unlikely to have a significant impact on beneficiaries’ nutrition levels. Further evidence may be provided by FAO to be reviewed during the PCR.

Partners have included beneficiary data disaggregated by age and sex in their reporting, with MENTOR Consortium also providing details on persons with disabilities through the inclusion of the ‘Washing Short Set’ of disability-related questions in its recent beneficiary satisfaction surveys. UNHCR has introduced questions on disabilities as part of their biometric registration of refugees. WFP has a specific indicator to ensure at least 10% of households assisted through its programmes include persons with disabilities, as per its Corporate Results Framework for guiding performance monitoring. DFID is currently working with partners to increase the quality of reporting on persons with disabilities where possible.

Learning

In addition to the specific recommendations outlined in sections A and B, developed through the annual review process, the following key lessons can be taken from the programme thus far:

1. Humanitarian programme delivery in complex crises requires tools and flexibility to adapt to changes in context: The range and diversity of partners funded through CHURP (UN, NGO, ICRC, pooled fund) has allowed the programme to respond to shifting protracted and emergency needs across the country. The support to ICRC and CHF has allowed the programme can quickly provide multi-sector responses to acute emergency needs. CHURP’s in-built contingency mechanism has enabled DFID to increase this support when necessary. Multi-year funding provided to MENTOR Consortium and FAO has ensured that the programme is also able to support the affected population’s protracted needs (health, food security).
2. Outcome indicators should be included in partner’s logframes and reporting requirements: This will help ensure that evidence concerning the programme’s impact on areas such as household food security are systematically captured over the course of the programme.
3. Milestone targets should be tailored to context: Programme delivery in complex crises should strive to meet universally agreed standards as much as possible. Where certain standards, such as providing one healthcare consultation per year, are clearly unachievable then it is appropriate to set targets which are appropriate to the context.

Progress on recommendations from previous reviews (1/2 page)

- Accountability to affected populations: In line with the Grand Bargain commitment on the participation revolution and the recommendations of the Evaluation of the Inter-Agency Humanitarian Response to the Crisis in the Central African Republic[8], and building on the World Food Programme’s (WFP’s) work in Cameroon, DFID will seek to strengthen feedback and complaints mechanisms (including regarding exclusion), and encourage learning and shared analysis between partners across the response: DFID has engaged with OCHA and UNICEF concerning potential support to a system-wide system accountability system, and is currently exploring the possibility of supporting this project through CHF funding.
  [8] http://www.interagencystandingcommittee.org/system/files/print_final.pdf
- Logical framework: the overall logical framework should be simplified, and milestones should be corrected and/or updated in light of DFID’s contribution to multi-donor programmes, while maintaining more detailed indicators for each component: this has been completed.
- Protection: DFID to ask partners in CAR and Cameroon to demonstrate how protection and social cohesion form part of their programme approach, by December 2017: In Cameroon, UNHCR ensures host community populations are integrated into livelihood programmes to facilitate social cohesion. In CAR, a protection strategy has recently been approved by the HCT.