Annual Review – post April 2018

Title: Programme to pilot Development Impact Bonds (Project ID: 204722)
Programme Value £ (full life): £6,300,000		Review Date: 15 June 2018
Programme Code: 204722	Start Date: 30 June 2017	End Date: 31 March 2023

Summary of Programme Performance
Year	2017/18
Programme Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	Business Case / 2017 BC Addendum
DevTracker Link to Log frame:	Logframe (Version including results and updates from this AR will be published ASAP)

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The purpose of this programme is to pilot the Development Impact Bond (DIB) model, to generate evidence on the suitability and cost-effectiveness of DIBs in improving development outcomes. The programme launched in June 2017.

During the first year of the programme DFID has identified, assessed and structured financial support to three projects where there is a strong rationale for using a Payment by Results (PbR)/DIBs approach to achieve DFID results priorities. These projects provide a rich set of case studies from which we can generate learning on the suitability of the DIB model. DFID is an outcome funder in two projects – this means that DFID will only pay the providers and their investors if pre-agreed outcome level results are achieved:

The first project with the International Committee of the Red Cross will provide new more efficient physical rehabilitation services that help people living with physical disabilities in conflict affected areas to regain mobility. The Humanitarian Impact Bond is a 5 year programme. It will set up (2017-20) and run (2020-22) three new physical rehabilitation centres in Mali, Nigeria and Democratic Republic of Congo, providing people living with physical disabilities with access to rehabilitation services that enable them to re-gain mobility – helping them to live better lives, work and go to school. The goal of the impact bond is to increase the efficiency of new centres, and generate learning that can be applied across the ICRC Physical Rehabilitation programme. ICRC will use the HIB to invest in innovating and piloting new ways of delivering services that increase efficiency while protecting quality. DFID has committed £2m to this project (of ~£20m total size). DFID’s payment is strictly tied to the level of efficiency the new centres achieve after 2 years of operations, with the ICRC and its investors only being repaid in full if the centres are more efficient than benchmark centres. It’s expected that during the HIB the new centres will support more than 2,700 individuals to regain mobility. When fully operational, each centre is designed to serve up to 2,000 people with disabilities each year. This video summarises the ICRC HIB.

The second project with the Global Development Incubator and Village Enterprise aims to sustainably increase the incomes of at least 12,660 very poor households[1] in Kenya and Uganda by helping them set up income-generating microenterprises. Under the DIB, the NGO (Village Enterprise) and its investors are only paid for the outcomes they achieve: $1 for every $1 of increased income[2] gained by participating households measured 6-18 months after the end of the intervention. Under the DIB Village Enterprise will significantly increase the scale of their operation, while also testing larger asset transfers with the aim of increasing their impact. DFID has committed $2.02m to this project (of $5.3 total size). A portion of DFID’s funding will support the costs of the independent results evaluation ($0.48m), as well as learning activities managed by Instiglio.
[1] Those living on less than $1.90/day
[2] This is measured using an RCT approach that will measure households consumption, assets and savings

In addition, following a £1.5m project addendum in November 2017, DFID is also providing technical assistance to a third DIB managed by the British Asian Trust, where UK funding helps leverage in $10m of new philanthropic outcome funding to improve education outcomes for 200,000 marginalised children in India. DFID’ is supporting the structuring, results measurement and wider learning activities in the DIB. The Education DIB aims to demonstrate that Impact Bonds can be used efficiently at scale, by using one DIB contract structure to work with multiple NGOs. The project is at an advanced stage of design, and should launch later in 2018.

Summary supporting narrative for the overall score in this review (1/2 page)
Year 1 was a crucial year for the pilot programme, and represents achievement of a key output in the programme’s theory of change. DFID has successfully launched two DIB projects, each of which has appropriate payment by results contracts, governance structures and independent results verification procedures. This first year has allowed DFID to assess when impact bonds are a tool that is relevant and useful to DFID in achieving development results, and has created a rich portfolio of DIB projects from which we can robustly evaluate the impact bond suitability and how it affects development project performance and costs. The third project (in education) is on track to launch later this year, and be part of the DFID-led evaluation. DFID has successfully tendered for a specialist evaluation provider to generate learnings from these three DIB projects. The evaluator has proposed a robust approach that meets the learning expectations targeted in the DFID Business Case.

Recommendations for the year ahead (1/2 page)

For the Impact Bond Field
- Pilot so far has shown that it is possible to design quality projects through a detailed and robust design process. However, outcome funders are continuing to build their understanding of outcomes-tied funding and have varied preferences to technical details in programmes (e.g. results metrics, thematic areas): We will work with funders to share learning, build capacity and alignment of expectations. This will reduce time service providers expend on-boarding donors.
- Models and contract templates are replicable, but there are few opportunities to immediately replicate. We will look proactively at opportunities for scaling and replicating with other donors to capitalise on the research and design investments we’ve made so far.
- It is important to tie payment to a small number of key metrics that reflect the programme goal, but it is still valuable to have a comprehensive monitoring and evaluation framework for generating learning across a variety of wider benefits. We will continue to advocate for partners to share programme learning during implementation.

For the Project
Continue to monitor that verification approaches for each project are operating effectively on the ground and generating robust evidence on outcomes.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	DIB programmes deliver improved results for poor people
Output number per LF		1	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1: Number of direct beneficiaries with improved outcomes as a result of DFID funded DIB projects: / (i) ICRC = No of patients regaining mobility in new Physical Rehabilitation centres / (ii) VE DIB: Number of VE households with average (i) USD per capita increase in monthly consumption compared to control group; AND (ii) USD per capita increase in asset stock compared to control group.	(i) ICRC – 0 people (but project on track against project level output milestones). / (ii) VE – 0 households (but project on track against project level output milestones).	(i) ICRC project is on-track against build phase project milestones. Facing some delays – but these were anticipated and built into the timeline. / (ii) VE – Effect on household asset and consumption outcomes will be measured in 2020 and 2022. In interim, VE is on track against project outputs, 832 beneficiaries (570 female, and 262 male) have completed VE training and received initial cash transfer to start microenterprise businesses (279 businesses = 130 Crop businesses / 29 Livestock / 102 Retail / 19 Service / 4 skilled) by March 2018.
1.2: Number of DFID supported DIB projects that complete programme cycle as planned	6 projects appraised / 3 projects supported	9 projects appraised / 3 projects supported
1.3: Number of DFID supported DIB projects with improved cost-effectiveness ratio compared with service providers' own past performance	N/A. 0 (as too early to assess)	0 (but data being generated to answer this question)

Provide supporting narrative for the score

The first year of the programme was spent appraising, and structuring DFID support to the pilot DIB projects that would form the learning case studies under this pilot programme. We appraised 9 DIB projects – generating learning on different payment models and approaches to engaging investors and outcome funders. DFID has selected to support 3 projects – where there is a strong rationale for a DIB model, a close fit with DFID results priorities, and where the projects were at an advanced design stage enabling early learning.

DFID has agreed to be an outcome funder in two projects – the ICRC HIB and the Village Enterprise DIB. The ICRC HIB launched in July 2017 and the Village Enterprise DIB in November 2017, following detailed project appraisal, negotiation of outcome payment metrics and finalising of the independent verification approaches and agents for each project. In January 2018, DFID agreed technical assistance grant support to enable a third DIB focused on improving Education Outcomes in India to launch later this year – having raised private philanthropic funding to pay for outcomes.

Indicator 1.1 was developed to monitor the number of people who benefit from improved outcomes under the ICRC and Village Enterprise (VE) projects where DFID is an outcome funder. The new ICRC centres will not be operational until 2020 so until then we are using project reporting to track progress against the design, build and training phases of the project. The ICRC is on track with its timelines – though facing anticipated delays in finalising the agreements to start building. Similarly, we will need to wait until 2020-22 to measure if Village Enterprise households are better off as a result of the programme. In the interim we are monitoring VE’s progress in engaging households in the programme and launching businesses.

It is also too early to report against Indicator 1.3, as the projects have not yet delivered results. However, we are collecting cost and benefit data against which performance under the DIB can be compared to past cost-benefit data. The DFID evaluation will help to answer this question in future years, collecting data on transaction costs, as well as delivery costs.

Lessons identified this year
- DFID project selection, appraisal and agreement structuring process is as intensive as it is in other DFID projects that include an significant monitoring and evaluation component – with specialist skills required on results definition and measurement approaches.
- Unlike many DIBs that engage investors as the outcome payment contract is negotiated, Village Enterprise opted to self-raise their investment having agreed the outcome payment contract with donors. Village Enterprise has successfully raised the capital required to deliver the programme within first six months of the programme.

Recommendations for the year ahead linked to this output
N/A

Output Title	Independent robust qualitative evidence available on whether Development Impact Bonds enable efficient and effective delivery in DFID priority results areas and the conditions for DIBs to be an appropriate commissioning tool, and the costs and benefits of using them.
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1: Quality independent evidence of programme effectiveness is generated by DIB Project level Verification Providers	Independent Results verification process established for 2 of the 3 DIBs	Independent Results verification process established for 2 DIBs (ICRC and VE) and at advanced design for Education DIB.
2.2: Quality Independent Process Evaluation Reports produced by contracted Evaluation Provider that have been published.	Independent Evaluation Provider is contracted by DFID. Their evaluation approach has been approved, and has started implementing evaluation activities.	Contracted, but only in inception phase. Provided detailed evaluation design in bid, confident will deliver. Still on track for first output in October.

Briefly describe the output and provide supporting narrative for the score

Indicator 2.1: Independent results verification agents have been contracted and methodologies agreed for the Village Enterprise and ICRC impact bond. An independent results verification agent has also been contracted for the Education Impact Bond, and is at an advanced stage of design.

Outcomes in the Village Enterprise DIB will be verified using a village level Randomised Controlled Trial conducted by independent evaluator, IDinsight. IDinsight verifies the cash transfers, and the endline impacts on household incomes through a household survey on consumption, assets and savings. Endlines occur 6-18 months after cohort households have completed the programme, incentivising VE to focus on sustainability of outcomes. The RCT is also designed to generate learning on the impact of different sizes of cash transfer. We engaged expert evaluation advice to review the evaluation design.

The ICRC results will be verified through an audit procedure. The auditor will visit a random sample of patients to confirm that patients have regained mobility. The project uses a standardised Physical Functionality Assessment that measures beneficiaries’ ability to perform daily living activities such as walking, sitting, picking up objects, feeding, and washing.

Indicator 2.2: The DFID Programme Level Evaluation is integral to the theory of change for the pilot programme. The focus and of the evaluation is described in the Monitoring Evaluation and Learning section below. The evaluator (Ecorys) was contracted in May 2017, following a competitive tender process using the DFID Global Evaluation Framework. Ecorys is an experienced evaluator of impact bonds: currently evaluating and researching more than 39 impact bonds. The evaluation inception phase completes in July 2018. We are slightly behind our original timeline, having delayed the tendering of the evaluation to enable the India Education Impact Bond to be included – enabling the evaluation to have 3 DIB case studies to learn from. This does not delay the outputs or quality of the evaluation. The first learning report on the process of designing impact bonds is due in late 2018.

Lessons identified this year, and recommendations for the year ahead linked to this output

Since launching the VE DIB we have needed to adjust the cash transfer verification procedure. Initial plans to rely on remote geo/time-stamped photos to verify cash transfers proved unreliable due to poor lighting, cultural sensitivities, and the time it takes. Low levels of mobile phone ownership make remote monitoring difficult so we will move to a local independent enumerator verifying the transfers. This demonstrates the need to check verification procedures operate effectively early in programme implementation.

Output Title	Evidence generated on the process of agreeing and managing a project on a Development Impact Bond basis, including implications for DFID's funding arrangements, assurance and management
Output number per LF		3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Internal policy guidance generated on process of agreeing and managing a project on a DIB basis.	Internal paper produced on internal learning on due diligence, template grant arrangements, and payment mechanisms for first DIBs.	Completed. Knowledge box containing first DIBs set up on vault and 4 DIBs guidance presentations are available on PbR Yammer site accessible to all DFID staff.

Provide supporting narrative for the score

We have established an internal knowledge box that shares the design and forms of agreement for our first Impact Bonds. The team has also produced four internal power point presentations that summarise how DFID’s first impact bonds operate, considerations on when to use impact bonds, and learning from the process of designing, appraising and structuring first impact bonds. These were published on the Yammer PbR teamsite, and have been used by the team (alongside other presentations) to share learning within DFID. The DFID DIBs team is also providing advice to other parts of DFID, NGOs and other donors, informing their use of the impact bond instrument.

Lessons identified this year, and recommendations for the year ahead linked to this output

The programme is still at an early stage. Learning is emerging, and we expect to work toward formalising a smart guide next year based on robust learning and reflections from one year of delivering impact bonds, and the first evaluation output. The team will also do more to promote these products and share learning internally.

Output Title	Resources are produced that support other outcome funders to use development impact bonds to achieve sustainable development goals in DFID priority countries in South Asia. [New British Asian Trust Output – added with 2017 cost-extension]
Output number per LF		4	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of resources created to enable the entry of new funders into the impact bond market in other DFID priority countries in South Asia (not cumulative)	Research providers are contracted, and research framework is agreed.	Not achieved, still in progress.
Number of proof of concept studies completed to assess potential for establishing DIBs in other SDG sectors (such as health, livelihoods, micro-finance, WASH) in DFID priority countries in South Asia.	N/A. No milestone for this review. First milestone due March 2019.	N/A

Provide supporting narrative for the score

The British Asian Trust has defined a research framework, but is still in the process of identifying a research provider. The timeline for procuring the research provider was too optimistic when initially added to the logframe. This was realised as we finalised the BAT grant and reflected the need to prioritise the tendering and contracting of the verification provider and the negotiation of the impact bond payment terms.

Lessons identified this year, and recommendations for the year ahead linked to this output

We recommend updating the project level milestones to reflect the updated research agenda with BAT.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

A diagram summarising the Theory of Change for this programme is included as Annex 1. Impact Bonds are a potentially valuable tool for achieving development outcomes. However, there is a lack of experience and evidence on their suitability in a development context. The DIBs pilot programme works to overcome this barrier by i) establishing a portfolio of DIB projects, which will act as case studies from which ii) to gather initial evidence and learning on the models suitability and effectiveness in achieving development outcomes, and their value as a commissioning tool used by DFID, and iii) share this learning within DFID and the wider international development community to enable replication of effective approaches.

The initial theory of change planned for DFID to be an outcome funder in multiple DIBs. However, in the first year, we responded to an opportunity for DFID funding to be used to structure a large scale DIB in education that brings together multiple services providers – offering a different DIB model for case study. This project also tests if strategic investments by DFID to structure DIBs can facilitate a broader market for outcomes, by enabling other outcome funders to use pay for success models to increase the effectiveness of their philanthropic funding. It also responds to a new opportunity to apply learning from the education DIB in considering how the model could be applied to support the achievement of other development outcomes in the South Asia region.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The outcome targeted by the programme is improving DFID’s ability to make informed choices on how to use DIBs and compare the instrument to other PbR and non-PbR tools in commissioning and management, and emerging evidence on impact and value. On outcome indicator 1 we achieved the target of 3 new DFID programmes interacting with DIBs guidance, evaluation findings and reports. We have been supporting two DFID country offices (India, Kenya) and one centrally managed programme team (WASH) in thinking through the initial stages of impact bond design – sharing evidence and insights generated during the first year of programme implementation. Milestone 2 is 8 new programmes interacting with guidance – this is likely to be a challenging target as it depends on both the number of new programmes coming through the pipeline, as well as availability of guidance/reports. While the evaluation timeline is slightly behind schedule (tender delayed to incorporate BAT project), first outputs should still be produced and disseminated in 2018/19. We have also engaged the support of a commercial adviser to establish better links with new programmes prior to commercial option appraisal and will look to disseminate evidence proactively.

Outcome indicator 2 is the proportion of new DFID DIBs commissioned that are informed by recommendations of DFID DIBs evaluation reports. Similar to the above, this is dependent on successful delivery of first evaluation outputs – we are confident that the 100% target specified for Milestone 2 can be achieved.

In terms of impact, the programme aims to deliver value for money, better results for more poor people, and ensure that money spent where it makes the most difference. On the impact indicator value of DFID spend delivered through PbR programme financing structures that target increased efficiency and/or cost-effectiveness, the team is still working on understanding baseline data better before finalising milestones. Early challenges include ensuring the sustainability of impact generated through pilot DIBs – e.g. through planning to use DIB evidence in attracting follow-on funding from donors or national governments.

Explain major changes to the logframe in the past year (1/2 page)

The Business Case planned for the logframe to be finalised within the first six months of the programme to reflect the DIB pilot projects selected during the programme inception phase. As such the programme now includes milestones and targets for output indicator 1.1 “Number of beneficiaries with improved outcomes as a result of DFID funded DIB projects”. We have also adjusted the milestones associated with the DFID funded Evaluation in Output Indicator 2.2 to better reflect the final evaluation design and timing of evaluation outputs agreed following the evaluability assessment and evaluation tender. Finally a new output 4 has been added to monitor the additional work supported by the project addendum.

Describe any planned changes to the logframe as a result of this review (1/2 page)

We have made some minor changes to the logframe, primarily adjusting the milestones in Output Indicator 4 to reflect the final grant agreement signed with British Asian Trust and a more realistic timeline for delivering outputs. The Risk for each output has also been amended to move from low/medium/high to DFID’s new 4 risk levels so “Medium” changed to “moderate”; and “low” to “minor”.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

‘Driving value for money’ was one of the criteria against which delivery options were appraised in the Business Case. Funding externally designed DIBs meant that the programme team initially relied on VfM considerations being incorporated into project design by other donors/designers. However, we have locked in VfM into final DIB agreements in the following ways (starting with projects where DFID is an outcome funder):

Efficiency – the following features of our payment agreements ensure that service providers are incentivised to maintain or improve efficiency of delivery:
- ICRC: Efficiency in operating physical rehabilitation centres is at the heart of the ICRC impact bond agreement. ICRC must deliver at least a 10% increase in efficiency in operating physical rehabilitation centres built under the DIB (as compared to current centres) to recover costs. The outcome payment grows with additional efficiency increases (capped at 80% increase in operational efficiency).
- VE: the payment from donors is contingent on VE achieving growth in income of targeted households, with donors paying $1 per $1 additional income generated, as measured by a randomised controlled trial. This is an incentive for VE to deliver outcomes whilst also managing delivery costs (to ensure costs are covered by outcome payments).

Effectiveness – under both the ICRC and VE projects, if service providers do not meet the outcome targets outlined in DIB agreements outcome payments will not be made by donors and investors stand to lose money. On the other hand, outcome payments increase with increasing effectiveness (subject to a budget cap). In both programmes, we carried out due diligence with inputs from technical experts within DFID to ensure that targets are stretching.

- ICRC: the efficiency metric outlined above relates to the number of patients who have regained mobility (per member of staff employed). ICRC is therefore incentivised to maximise the number of patients regaining mobility vis-à-vis its staff costs.
- VE: As outlined above, the donor payment to VE is directly contingent on programme effectiveness – as measured by growth in household income

Considerations of equity were important in assessing the suitability of efficiency and effectiveness measures, e.g. in ensuring that measures do not introduce perverse incentives to only target easy-to-reach populations or those for whom outcomes may be easier to deliver. Both DIB agreements include additional equity safeguards through specifying that targeting is to be carried out according to need (health and poverty, respectively). The Equity section further details approaches to targeting.

Economy – at project level, the pay-for-success nature of the above agreements means that DFID payments are tied to results achieved, and providers work with investors to deliver economy in procuring inputs. At a programme level, we have made use of DFID’s tender processes to secure quality inputs at the best available cost in procuring the pilot programme evaluation.

For the British Asian Trust (BAT) technical assistance piece, organisational capability in driving economy in procuring outcomes was assessed at the due diligence stage prior to signing the grant agreement. All inputs will be procured competitively, using BAT’s existing systems. The grant agreement specifies timelines and performance indicators against which DFID will disburse grant payments, ensuring that individual services are delivered efficiently, and that they are effective at onboarding other donors and accelerating the launch of the DIB. Unintended negative equity impacts of the programme are mitigated through the programme’s risk management – e.g. BAT (with DFID support) ensuring that those involved in designing the outcomes metrics and evaluations, performance management framework, and social finance tools for replication have relevant expertise to design programmes and tools that work to mitigate inequalities and create suitable incentives and avoid perverse incentives.

Equity – equity is a key consideration across all three pilot projects. Prior to signing agreements, we focused on evidence on providers’ ability to deliver interventions that promote equity (e.g. through targeting disadvantaged groups) and capability to provide appropriate data (monitoring outcomes for these groups). Specifically:
- ICRC: is building three new centres in regions affected by conflict, where mobility impairments are often associated with socioeconomic disadvantage. All three regions were selected from a shortlist identified by ICRC on the basis of local need for physical rehabilitation services, in addition to other practical considerations (e.g. security, ongoing conflict, supportive local government). ICRC will provide services based on a clinical need assessment, and provide service provider data disaggregated by gender. ICRC have considered key local barriers to inclusion in physical rehabilitation provision and look to mitigate through specific intervention design, e.g. providing accommodation to parents who have travelled in with child patients from remote locations.
- VE: targets the poorest households in villages identified for the intervention. Households are firstly identified using Participatory Wealth Ranking where villagers are asked to identify the poorest households; the accuracy of this is then tested and final household selection made using the Poverty Probability Index to ensure that marginalised households are included in the programme. VE’s track record shows that a majority of beneficiaries of the programme are female (~70%). Gender disaggregation and outcome analysis are part of the evaluation of the programme.
- BAT: DFID funds TA rather than beneficiary outcomes. However, we are working with providers selected for the programme (e.g. evaluators) to ensure appropriate data is collected throughout the progamme to enable equity monitoring.

In all programmes, we have used the due diligence assessment prior to signing agreements to consider approaches to ensure equity at the inputs level – e.g. staff pay and equal opportunities policies, ability to promote equity through programme decisions (e.g. procurement, recruitment of participants). We will monitor this regularly as part of the risk management process.

In the follow-up to the Annual Review, we will work with the above three projects to help us identify additional indicators to track VfM consistently in future Annual Reviews, most notably through using monitoring data on the equity side – ensuring that those in need have been reached.

Gender - We have considered how a DIBs pilot could contribute to DFID’s strategic vision for girls and women. As outlined above, impact on gender equality is not defined by the DIB instrument (which is just a financing arrangement), but driven by the interventions selected for trialling DIBs, as well as the detail of PbR arrangements used. We carried out qualitative gender equality assessment as part of assessing the evidence base prior to signing each agreement, drawing on inputs by DFID technical advisors. As outlined above, each project has considered a range of barriers to equity (including gender equity) and will be providing data on beneficiaries disaggregated by gender (among other characteristics). In addition, we have drawn on DFID’s Violence Against Women and Girls (VAWG) helpdesk to carry out a safeguarding/gender-based violence assessment to deepen understanding of gender-based risk on the VE DIB (chosen due to strong focus on women and economic empowerment). Prior to the next AR, we will consider whether similar assessments could be appropriate/effective for other DIBs or whether lessons can be drawn for the instrument more generally.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme has a strong focus on Value for Money and evidence of impact – its objectives include building understanding of whether DIBs enable efficient and effective delivery of programmes, and understanding the costs and benefits of using DIBs. The section above explains how VfM is driven in project agreements. Here, we outline arrangements put in place to build evidence and generate data on VfM, at both project and programme level.

Project level - where DFID acts as an outcome funder (ICRC, VE), each outcome agreement sets out specifically the outcomes/outputs DFID is looking to pay for. Independent verification has been commissioned to generate data on outcomes achieved (effectiveness) and enable a calculation of ‘cost per outcome’ (efficiency) as well as deeper analysis of effects on specific beneficiary groups (equity, e.g. gender analysis). In the BAT project, we have leveraged our position as TA funder to drive similar evidence standards in evaluation.

Programme level – section G highlights the core questions posed by the programme-level evaluation. This has a strong focus on generating insights into the costs and benefits of the DIB instrument, looking to gather data from across projects supported, as well as centrally incurred costs such as staff time. The data will be used to understand the ‘transaction costs’ of each DIBs, and attempt to generalise (though recognising differences in individual projects) and make recommendations on how future DIBs could be commissioned to improve economy and efficiency during the commissioning/structuring process.

Note that all projects supported have committed to transparency on costs. Both ICRC and VE have agreed to report actual costs of project delivery (ICRC on a quarterly basis, VE annually). The BAT performance management and evaluation frameworks will generate insights on unit costs across multiple service delivery models in the education space.

From a VfM perspective, the programme should therefore continue as it has been set up with a focus on both driving and monitoring VfM throughout. The evidence generated will be vital for effective decision-making in DFID, among other donors and local governments in using Development Impact Bonds.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The overall Programme Risk level continues to be Moderate. We have successfully put in place planned risk mitigation actions when selecting and formalising agreements with the Impact Bond pilot projects. An up to date lists of risks is shown on AMP. The majority of risks, with mitigating actions in place are moderate – but require continuous monitoring. There are no risks to escalate at this time.

Key risks include
- Volatility of spend owing to uncertainty over the level of results and therefore uncertainty over the level of payment that will be due, and because of exchange rate fluctuations.
- Effectiveness of verification procedures, including the risk that external factors contaminate the randomised controlled trial approach which is being used for outcome verification.
- Transaction costs increase e.g. due to additional verification or management costs. (This has not materialised as yet).

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

An up to date Delivery Chain Map is included as a tab in the Delivery Plan. Overall all partners are performing well on commercial and financial matters.

Evaluation Contract has just been signed, having offered the most economically advantageous bid. Their contract includes contract relevant key performance indicators that will be monitored during catch up meetings, and formally reviewed on an annual basis. Payment by results is used on the contract, with payments tied to DFID’s acceptance of the primary output of the work – the Evaluation Reports – as containing the agreed information and being of a high quality.

GDI is performing their trustee role effectively, but still has a number of minor due diligence actions to complete. We will monitor that these are completed by the end of the year, and not further delays elapse. The do not increase the risk level for DFID given the trustee role that GDI plays in the transaction. Their sub-contractors (the NGO delivering the outcomes – Village Enterprise, the outcome verifier and the process learning partner are all delivering their activities effectively and proving to be strong collaborators; each providing quality reports as agreed at design stage, and being transparent in the management of their programme activities). The delivery chain is reasonably complex and we have worked to establish an oversight structure that brings together all outcome funders and delivery partners – for direct interactions, which gives DFID direct sight of all delivery partners. DFID SRO and Programme Manager visited Village Enterprise offices and team, attended programme delivery activities and met with participants in both Uganda (Nov 17) and Kenya (Jun 18).

ICRC is producing quality reporting as agreed in the programme documentation, and manages a well-attended and thorough first donor oversight meeting in February.

British Asian Trust (BAT) first reports are good quality, though forecasting was optimistic in the first quarter of the grant, so we are closely monitoring this. BAT are driving value for money through effective tendering for their technical assistance partners including for legal services and the outcome evaluator. DFID Programme Manager met the verifier and NGOs in Delhi in January 2018.

	GDI/VE DIB	ICRC	BAT	Ecorys
Date of last narrative and financial reports[3]	16 April 2018 / 19 April 2018	11 May 2018 / 11 May 2018	08 May 2018 / 05 Jun 2018	Just started
Date of last audited annual statement (s)	31 Dec 2016	31 Dec 2016	31 March 2017	Centrally managed
[3] Reports saved to vault folders on Financial Management and ICRC, BAT, GDI/VE reporting folders

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

A key benefit of the DIB model is focus on monitoring, evaluation and learning (MEL). This programme will generate learning at project and programme level through a set of complementary activities. Each DIB project has a dedicated outcome verification process, delivered by an independent expert organisation. They also have embedded complementary project learning activities, summarised below:

The Village Enterprise DIB includes a randomised controlled trial design that will measure the impact of the programme on a sample of households’ incomes, assets and consumption 6-18months post-intervention. It is also designed to generate learning on the impact of higher value cash transfers ($50 per household, and $150 per household). It will also produce learning on how programme impacts persist in the months post intervention. Data will be disaggregated by gender, location and disability. The evaluation reports will be produced in 2020 and 2022. In the interim Village Enterprise relies on its internal enumerators to monitor performance against intervening milestones.

The India Education DIB will use a quasi-experimental approach to measure the impact of the NGO projects in improving children’s maths and literacy, delivered by an expert independent evaluator of Children’s learning. The evaluation will generate data that can be disaggregated by age, class and gender, and will measure children’s performance on an annual basis enabling performance to be tracked over time. To monitor performance in year – the investor in the Education Bond has invested in a performance management system that will gather data on student performance in year, while also seeking regular direct feedback from students, parents, teachers and supervisors on key risks, likes and concerns about the programme. This data will be aggregated and shared annually with the outcome funders and DFID to enable wider sector learning. Finally BAT is just commissioning learning activities that includes generating evidence on the process of pricing learning outcomes. The learning from this programme will benefit the education sector – generating data on cost-effectiveness of different approaches in achieving learning outcomes.

Programme Level Evaluation: At the programme level, DFID has commissioned an evaluation that will generate learning on the “DIB effect” – that is the effect of using a DIB instead of a grant or other PbR mechanism and will answer two key evaluation questions:
- EQ1: Assess how the DIB model affects the design, delivery, performance and effectiveness of development interventions (including conditions, costs and benefits)
- EQ2: What improvements can be made to the process of designing and agreeing DIBs to increase the model’s benefits and reduce the associated transaction costs?
A summary table showing the evaluation purpose, key questions and proposed subsidiary questions is included below. We may make small adjustments to this framework during the evaluation inception. The evaluation will produce three learning reports. The first will be on the process of designing and structuring impact bonds – and should be produced in Autumn 2018. A second report will be produced in 2020 after the first outcomes have been verified in the Education DIB and the Village Enterprise DIB. A final report will be produced in 2023 after the projects have finished implementation, enabling an assessment of the sustainability of any DIB effects.

Evidence: This is the first year of the programme, and no evidence has been generated to date.

Learning: emerging learning from the past year of the programme’s operation indicates that:
- It is vital that there is a strong rationale for the impact bond model. It is not relevant/useful everywhere and needs to be used only where there is a strong rationale for a PbR approach, and value in engaging an investor
- Pricing outcomes is challenging in the absence of data on previous outcome costs – this makes generating robust evidence through first DIBs even more vital
- The design of robust outcome verification requires specialist skills. Outcome measurement and verification is difficult to do in remote rural areas where the poorest live, particularly in the absence of government data collection systems, or where there is limited mobile phone ownership. This creates need for innovative verification approaches that make use of new technologies and are open to experimentation
Progress on recommendations from previous reviews: N/A as this is the first annual review
Purpose of Evaluation	Key Evaluation Questions	Proposed Subsidiary Evaluation Questions
To confirm whether the DIB model actually improves performance and effectiveness of development programmes, covering factors, such as: / Enabling outcome funders to use PbR with more providers / Changing incentives of the stakeholders / Increasing focus on desired outcome, and managing for results / Transferring delivery risk from outcome funder to provider/investor / Role of investors, outcome funders and service providers in design and delivery of intervention / Incentive structure encourages provider fidelity to implementation of activities that works / Increased flexibility/ autonomy for providers enabling more innovation in service delivery to improve performance/ results / Service provider is incentivised to deliver for the whole cohort – despite cohort having differing vulnerabilities &/or capabilities / The 3 DFID funded DIB projects should serve as case studies, enabling programme level learning.	EQ1: Assess how the DIB model affects the design, delivery, performance and effectiveness of development interventions.	1.1 How does the DIB model affect key stakeholders including service providers, outcome funders, investors, beneficiaries, and what are the reasons behind the effects / 1.2 Can we say anything about the sustainability of the effects on stakeholders?
		1.3 Which factors in a DIB are most important in improving the performance of a development programme, if at all, in terms of achieving results efficiently?
		1.4 How does the performance and effectiveness of development programmes financed using a DIB mechanism compare with providers’ experience of other funding mechanisms in terms of efficiency and results?
DFID and others are interested to use DIBs and similar financing models in the future. However, we need process of commissioning DIBs to be more efficient, accessible to more providers, funders and investors, and less costly. Stakeholders need a roadmap for an improved/optimal design process – covering the necessary conditions (e.g. projects attributes, stakeholders attributes) for DIBs to be suitable; key tools; and the roles of stakeholders at different design stages.	EQ 2: What improvements can be made to the process of designing and agreeing DIBs to increase the model’s benefits and reduce the associated transaction costs?	2.1 Under what conditions are DIBs an appropriate tool for the key stakeholders (outcome funders, investors, service providers, beneficiaries), and why? / 2.2 How can we improve the design process to produce DIBs that maximise the benefits for stakeholders (outcome funders, investors, service providers, beneficiaries) while reducing transaction costs? Including making the design process more efficient and accessible to more service providers, outcome funders and investors.

Summary of Programme Level Evaluation Questions
Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g. on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (e.g. first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc.) as a result of the review and once agreed at the appropriate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g. costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g. Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible e.g. categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided

## Annex 1: DFID Theory of Change for Development Impact Bonds Pilot Programme