## Logframe
Eritrea Nutrition, Health and Sanitation programme Logframe - 1st April 2018
PROJECT TITLE | Nutrition and Water, Sanitation and Hygiene (WASH) support in Eritrea
IMPACT | Impact Indicator 1 |  | Baseline (2010 EPHS) | Milestone 1 (August 2018) | Target (December 2018) | Assumptions
Improved nutritional status of children under five in Eritrea | Under-five prevalence of stunting | Planned | 50% | Decreasing on baseline towards target | 49% | Assumes that the baseline is the same as 2010 EPHS rate. It is not known when the next official EPHS will be but it is assumed that some data will be available through the Nutritional Sentinel Site Surveillence (NSSS).
Achieved
Source of data
Baseline EPHS 2010 Target NSSS 2020
| Impact Indicator 2 |  | Baseline (2010 EPHS) | Milestone 1 (August 2018) | Target (December 2018)
| Under-five prevalence of acute malnutrition (wasting) | Planned | 15% | Decreasing on baseline towards target | 14%
Achieved
Source of data
Baseline EPHS 2010 Target NSSS 2020
Outcome | Outcome indicator 1 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | Assumptions
By 2020, increased number of people benefitting from improved access to and utilise quality Health, Nutrition and WASH services. | Per cent of children under five years of age with severe acute malnutrition cured | Planned | 89.5% | 90% | 90% | Increase case search at each zoba Coverage for programme set at 80% SPHERE minimum recovery rate at 75%
Achieved
Source of data
|  |  | MoH IMAM database |  |  | Sustained good working relationship with government and partners
| Outcome indicator 2 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018)
| Number of people using basic sanitation and hygiene services (number of additional people benefiting as a result of this project) | Planned | 52000 | 5000 | 10000
|  | Achieved (female) |  |  |  | SPHERE minimum coverage for rural is 50%. However, indicator 1 will not be achieved if actual coverage falls below 80%
Achieved (male)
Source of data
MoH reports, CLTS monitoring system & field monitoring reports
| Outcome indicator 3 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018)
| Number of under-five children treated in the IMNCI programme (status at baseline in 2017 and numbers of additional children benefitting in 2018 as a result of this project) | Planned | 111061 | 55000 | 110000 | A child can be treated more than once during the programme. No outbreak recorded
Achieved
Source of data
MoH IMNCI database
INPUTS (£) | DFID (£): 3,242,853 |  | Govt (£): unknown | Other (£): 1,556,085 | Total (£):4,798,938 | DFID share: 68%
INPUTS (HR) | DFID (FTEs): 1 (SRO, plus input from advisers and Senior Management)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | Assumptions
By 2020, the delivery of effective, quality treatment for children under five with global acute malnutrition is achieved | Number of MoH staff trained on IMAM services in line with national guidelines (number of MOH staff trained in 2018) | Planned | 500 | 300 | 600 | Government ensures even distribution of trained staff
Achieved (female)
|  | Achieved (male) |  |  |  | Sustained good working relationship with government and partners
Source of data
MoH reports
| Output Indicator 1.2 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | Targets have been set based on previous perfromance and experience and deemed achievable by UNICEF
| Number of under-five children with severe and moderate acute malnutrition (SAM and MAM) treated in therapeutic and supplementary feeding centres (numbers treated in 2018) | Planned | 57,682 GAM ( SAM 15,981 and MAM 41,701) | 35000 (SAM 7,000 MAM 28,000) | 60,000 (SAM 16,000 MAM 44,000) | Social mobilization activities are instrumental to convince care givers to seek treatment A child can be treated more than once during the programme but not in the same year.
Achieved (SAM)
Achieved (MAM)
Source of data
MoH IMAM database
| Output Indicator 1.3 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | CHW continue to be motivated to provide crucial services A child or PLW can be treated more than once during the programme.
| Number of children aged 6-59 months and pregnant and lactating women (PLW) in arid and drought affected areas receiving supplementary feeding (numbers benefitting in 2018) | Planned | 48,470 - PLW (7,047) and chn 6-59 mnth (41,423) | 40,000 - PLW (10,000) and chn 6 - 59 mnths (30,000) | 60,000 - PLW (18,000) and chn 6 - 59 mnths (42,000) | Supplementary feeding is integrated into the MAM services - food rations are handed over to caregivers of children who attend the MAM clinic
Achieved (PLW)
|  | Achieved (chn 6-59mnths) |  |  |  | Provision of IMAM is already high and will be maintained and increased slightly towards 92%
Source of data
MoH IMAM database
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | RISK RATING
40 | Percent of health facilities providing IMAM services | Planned | 90% | 91% | 92% | moderate
Achieved
Source of data
MoH IMAM database
INPUTS (£) | DFID (£): 1,898,938 |  | Govt (£): unknown | Other (£): 1,108,085 | Total (£): 3,007,023 | DFID share: 63.15%
INPUTS (HR) | DFID (FTEs): 1 (SRO, plus input from advisers and Senior Management)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | Assumptions
By 2020, the delivery of effective MIYCF interventions through community based approaches and routine health services is achieved | Number of pregnant women who receive iron folate supplementation (numbers benefitting in 2018) | Planned | 86000 | 45000 | 86000 | Planned mixture of multiple delivery channels both routine and child health and nutrition weeks
Achieved
Source of data
|  |  | MoH reports |  |  | A pregnant woman or a child can be treated more than once during the programme.
| Output Indicator 2.2 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018)
| Number of children 6-59 months who receive vitamin A supplementation (numbers benefiting in 2018) | Planned | 431141 | 160000 | 360000 | Planned mixture of delivery channels including routine and child health and nutrition weeks
Achieved
Source of data
MoH reports
| Output Indicator 2.3 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018)
| Number of communities sensitized on MIYCF, WASH and appropriate health seeking behaviours (number at baseline in 2017 and additional in 2018) | Planned | 734 | 25 (759) | 50 (784)
Achieved
Source of data
MoH reports
| Output Indicator 2.4 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018)
| Number of sub zoba level MIYCF action plans developed (total number of sub-zobas = 58; in 2016, no sub-zoba action plans were produced in 2017, but 12 targeted in 2018) | Planned | 0 | 7 | 12
Achieved
Source of data
MoH reports
| Output Indicator 2.5 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | Effective community mobilization sessions are implemented at scale and CHWs remain motivated to provide counselling
| Number of pregnant women and caregivers with children <2 years counselled on MIYCF (number of pregnant women and caregivers targetted for counselling in 2018) | Planned | 86000 | 40000 | 90000
|  | Achieved |  |  |  | Pregnant women and caregivers can be counselled more than once during the programme.
Source of data
MoH reports
| Output Indicator 2.6 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | The Ministry of Health remains open to Operational Research being conducted.
| Number of Operational Research studies supported/ conducted. | Planned | 0 | 0 | 1
Achieved
Source of data
MoH reports
IMPACT WEIGHTING (%) | Output Indicator 2.7 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | RISK RATING
30 | Number of community volunteers trained on MIYCF | Planned | 2158 | 300 | 600
Achieved (female)
|  | Achieved (male) |  |  |  | Low
Source of data
MoH reports
INPUTS (£) | DFID (£): 612,963 |  | Govt (£): unknown | Other (£): 0 | Total (£): 612,963 | DFID share: 100%
INPUTS (HR) | DFID (FTEs): 1 (SRO, plus input from advisers and Senior Management)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | Assumptions
By 2020, communities have improved access to safe, sustainable hygiene and sanitation services | Number of villages declared open defecation free | Planned | 25 | 6 (6,000 people) | 10 (10,000 people) | Communities work together to achieve ODF status, sufficient MoH capacity to support villages through to ODF status, sufficient number of community volunteers to be trained as Community Health Workers. Village health promoters will reach every household. The Government of Eritrea has no CLTS Roadmap, and UNICEF is the sole agency supporting the CLTS programme. The GoSE-UNICEF annual workplan target has been pitched at 100 villages declared ODF per year.
Achieved
Source of data
MoH reports, CLTS monitoring systems & field monitoring reports
| Output Indicator 3.2 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | RISK RATING
| Number of people reached through hygiene promotion messages (total numbers to be reached in 2018) | Planned | 52,000 ODF and 91,000 triggered | 6,000 (3,100 female 2,900 male) | 10,000 (5,100 female 4,900 male)
|  | Achieved (female) |  |  |  | Moderate
IMPACT WEIGHTING (%) |  | Achieved (male)
10 |  |  | Source of data
MoH reports, CLTS monitoring system & field monitoring reports
INPUTS (£) | DFID (£): 50,000 |  | Govt (£): unknown | Other (£): 0 | Total (£): 50,000 | DFID share: 100%
INPUTS (HR) | DFID (FTEs): 1 (SRO, plus input from advisers and Senior Management)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018) | Assumptions
By 2020, the delivery of effective treatment of children under five years in the IMNCI programme is achieved | Number of villages implementing IMNCI programme (number of additional villages implementing in 2018 through this project and cumulative numbers) | Planned | 734 | 25 (759) | 50 (784) | CHWs remain motivated to provide services
Achieved
Source of data
MoH IMNCI database
| Output Indicator 4.2 |  | Baseline (2017) | Milestone 1 (August 2018) | Target (December 2018)
| Number of volunteers trained in IMNCI and health and nutrition promotion (number of additional volunteers trained in 2018 through this project and cumulative numbers) | Planned | 1072 | 60 (1132) | 100 (1172)
|  | Achieved (female) |  |  |  | RISK RATING
|  | Achieved (male) |  |  |  | Low
IMPACT WEIGHTING (%) |  |  | Source of data
20 |  |  | MoH IMNCI database
INPUTS (£) | DFID (£): 440,741 |  | Govt (£): unknown | Other (£): 0 | Total (£): 440,741 | DFID share: 100%
INPUTS (HR) | DFID (FTEs): 1 (SRO, plus input from advisers and Senior Management)