## A1 Goal, Purpose, Risk
Annual Review (2011)
ARIES Project Code | 201578
ARIES Project Description | African Risk Capacity (ARC) - Establishing a Pan-African Disaster Risk Pool for Food Security
A1: Goal, Purpose, Risk
Goal
Goal statement | Effective use of financial weather risk management by tools and funds for sub-Saharan countries to deal with extreme climate events
Indicator 1 | No. of countries using contingency financing instruments and strategies as part of their national disaster preparedness
Milestone for this review (if any) | None for this reporting period
What progress has been made in the period covered by this review?
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Value of contingent funds available to sub-Saharan countries specifically for extreme weather events
Milestone for this review (if any) | None for this reporting period
What progress has been made in the period covered by this review?
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)?
Goal Recommendation 1
Goal Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | African-owned risk pool (ARC) provides pooled contingency funding mechanism to African countries for planned responses to extreme climate emergencies
Indicator 1 | No. of risk pool participation requests received by project from national governments
Milestone for this review (if any) | None for this reporting period
What progress has been made in the period covered by this review?
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | No. of countries with developed drought response contingency plans linked to contingent funds
Milestone for this review (if any) | None for this reporting period
What progress has been made in the period covered by this review?
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Purpose assumptions are still valid
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | Still in phase of delivering elements required to lead to achievement at purpose level; too early to say regarding realisation of Goal
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | A viable and functional African owned regional risk pool would not be possible without robust design, full consultation and strong endorsement. These attributes are being provided for under the specific Outputs of the ARC design process.
Purpose Recommendation 1
Purpose Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 2 | 1.75
Purpose Justification | Assessment is based on progress at Output level. During this reporting period the ARC Project Team has mobilised and been successful in advancing awareness and endorsement of the base ARC concept, embedding in African Union led process and decision-making, forging numerous strategic partnerships and, at a high level, establishing ARC feasibility. This will be critical as the project moves towards its purpose and goal. It has also made progress on several of the technical aspects associated with ARC's design. Given a design project of this size, scope and political sensitivity, it has faced several challenges and constraints, many beyond the project's control. In particular delays in signing the WFP-AU Special Agreement, which has anchored the project firmly with the African Union Commission, took 6 months to secure. Delays with the World Bank supervised study also prevented effective movement on country consultations and some aspects of the technical work required.
Nevertheless as country consultations have now begun, the project is well positioned to to move foward more rapidly with its work programme in 2012. It is likely to achieve many of the original targets by the end of 2012 as envisaged, despite certain of the current intermediate milestones having been missed.
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | Implementation delays mean updated milestones are required
Logframe Recommendation 1
Logframe Action Point 1 | Update milestones - see specific output recommendations/action points
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Capacity built for African governments to take a fully informed decision on participating in the African Risk Capacity (ARC) pool
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 (leave blank if standard indicator) | No. of countries where ARC working groups – comprised of relevant government ministries and their partners in food security and risk management – are established, meet regularly and are considering ARC participation | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 4 | 0
Progress made in the period covered by this review, including numbers. | 3 groups identified and interacting with ARC Project, although not yet formally constituted as ARC in-country working groups. The Project Team is moving forward with technical work in Rwanda, Kenya and Ethiopia and has been interacting with existing national multi-stakeholder, government-led working groups, or members from them, in these countries. Groups have been identified that will be tasked with considering ARC participation: Kenya Food Security Steering Group (KFSSG); the newly formed Rwandan Disaster Management Task Force (strategic, minister-level) and Disaster Management Working Group (technical, P.S.-level) and most likely the Risk Financing Management Committee in Ethiopia (state minister-level) which oversees the risk financing component of the Ethiopia Productive Safety Net Programme. As more of the scheduled scoping missions are completed the list of agreed working groups is set to grow rapidly.
At the request of the AU, at the beginning of the year the ARC team modified their strategy: the key objective of the first six months of the project was not country-level consultations but conducting the necessary advocacy, securing the AU Special Arrangement with WFP and preparing the design and feasibility research to be presented to a consultation with AU member states, from which country consultations would follow. This consultation did not occur until August in Kigali, and has had knock-on implications for the timing of country consultations and working group formalisation (see action points). Despite the timing setbacks, there is significant evidence of progress towards this indicator. Following the Kigali regional workshop, the ARC Project is doing well: 15 countries requested missions, 15 have been planned, and to date five have been carried out (Ethiopia, Kenya, Rwanda, South Africa, Malawi (just completed, 25th November) and all five have requested follow-up visits and technical workshops. The remaining 10 countries will be visited in December 2011 and January 2012.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | No. of Africa RiskView and ARC training workshops held for stakeholders, including government and their partners, and regional body representatives
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 15 (including baseline of 2)
Progress made in the period covered by this review, including numbers | 4 major workshops conducted. A regional workshop approach was adopted initially rather than individual country workshops as orginally envisaged. In particular a regional ARC workshop in Kigali was attended by representatives from 27 member states at budget director level. The milestone was originally set to reflect country-level workshops, assuming those consultations would begin at the start of 2011. However at the request of the AU the project refined its consultation strategy, formally launching the project consultation with a regional workshop in August 2011 in Kigali, followed by scoping missions to interested countries. This outreach is leading to detailed in-country workshops in early 2012, and additional strategic training opportunities. Rwanda, Kenya and Malawi have already specifically requested Africa RiskView technical training workshops in February, March and April respectively. In addition Africa RiskView will be featured as a third of the UNECA’s DRR/DRM quantification training for their regional bureaux and RECs scheduled now for January 2012 (postponed from August 2011).
A key workshop was held with the World Bank in October 2011. A first technical workshop on the Africa RiskView tool was held with the Director and his staff of the Early Warning Response Directorate in Ethiopia; finally the team presented ARC and Africa RiskView to a convening of the Rockefeller Foundation’s climate smart agriculture in Africa grantees (25 academic institutions and NGOs).
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | No. of peer-reviewed studies written by leading experts on the cost benefits of contingency financing mechanisms
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2 (including baseline of 1)
Progress made in the period covered by this review, including numbers | The envisaged major technical economic study expected to be completed in this reporting period is delayed . Terms of reference were drafted for a cost benefit analysis, incorporating several elements (previously anticipated to be done discretely, which was reflected accordingly in the milestones) into one larger deliverable for one research team by the end of the project – a cost benefit analysis focusing on the ARC concept, in addition to reviewing the existing Ethiopia and Malawi country examples. These were shared with several research groups and economists, and despite interest in the concept there were challenges in finding economists with the appropriate skill set for this cross-cutting work. Input from the DFID Chief Economist recently helped to identify the right economist team (IFPRI/Oxford University) and the project is now in the process of formalizing the commissioned study with final delivery in May 2012. Given the importance of this analytical element securing the right team is essential. The Project team was waiting for the World Bank study to be completed before commissioning this study, but in June started the process without the WB.
More generally, the ARC Project has been engaging with several parties in the context of external peer reviews. Africa RiskView has and is being reviewed by USAID’s FEWSNET and EC’s Joint Research Centre (JRC) and risk modelling firm AIR-Worldwide to assess its market readiness. The private reinsurance sector has also continued to express interest in ARC and Africa RiskView, not only to test the tool but also for it to help support ongoing commercial activities in Africa. Swiss Re in particular has expressed an interest in licensing the software, an example of the favourable external view of the robustness of this key ARC platform.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 3 | 0.5
Impact Weighted Score | 12.5 | 0.125
Justification for the Score | The delays in country consultations and a rescheduling of country outreach led to shift in timeline that in particular affected progress on Indicator 1 and prevented progressing even further against Indicator 2. Delays with the World Bank study and challenges in finding suitable economist candidates led to a delay in progress in Indicator 3; a research team has now been identified and will start work in the New Year. The evidence of recent progress suggests that the majority of final target indicators for Output 1 will still be met by the end of 2012, but an extension may be warranted for full completion of capacity building (see recommendation).
Output 1 Recommendation 1 | The ARC team and DFID team are already in consultation with the DFID Chief Economist to help secure the right economist team and strengthen the Terms of Reference for this key piece of work.
Output 1 Action Point 1 | Given the revised ARC Project country outreach strategy and the explained delays, milestones should be updated. Indicator 1 Milestone 2 of 6 ARC in-country teams should be recalibrated to end of June 2012; indicator 2 milestones should also be updated; Indicator 3 milestones should be updated to reflect the adjusted approach of consolidation of various studies.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | In the context of the explained delays, a 6 month no cost-extension to June 2013 should be considered to allow for in-country capacity building activities to continue for the 12 months (as orginally envisaged) after ARC working groups formally and operational active, to enable full achievment on Output 1. This will also allow for enhanced achievement, and also provide a contingency buffer, across all other outputs.
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Detailed design study for a feasible ARC risk pool architecture completed and discussed with key stakeholders
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Low | 3
0.75
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | ARC financing strategy approved and institutional structure agreed by all stakeholders
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | ARC financing strategy developed and institutional structure defined
Progress made in the period covered by this review, including numbers | 50% completed, expected to be fully completed in April 2012. The 9 month delay associated with a key component study supervised by the World Bank work slowed progress, but the team has made advances on ARC’s financial and institutional design. Work on the latter topic is now being led by WFP’s General Counsel who has brought together a team of internal and external legal experts, pro bono legal counsel and the recently retired General Counsel of the African Union. An initial report from this team on ARC legal and institutional options is expected in March 2012 to be completed in April 2012. Significant progress has been made on the financial feasibility. This has been through the dynamic financial analysis (DFA) conducted as part of the Work Bank study (utilising the approach employed on the Caribbean Catastrophic Risk Insurance Facility, CCRIF) which demonstrated the technical feasibility in constructing a solvent and sustainable pool of risk. Building on this work the ARC team has developed that underlying model in-house, defining various pricing and risk management strategies under different scenarios and to develop communication material on risk transfer costs and potential risk pool saving for the country consultations. The model will be developed further with the assistance of the facility management service providers for the CCRIF, so that it can be used for financial risk management decision making purposes for an operational ARC and as more information emerges on country composition, participation and scope of initial capitalization. Other technical work completed during the reporting period includes further work on the climate change stress tests; further development of Africa RiskView, with the creation of a new pan-African rainfall dataset from 1983 by the US National Oceanic and Atmospheric Administration Climate Prediction Centre, co-funded by the ARC Project; and a joint proposal for a NASA Earth Science Division, Applied Sciences Program grant for a one-year feasibility and prototype development study for an ARC-specific flood model together with research firm AER.
Significant progress has been made on the financial feasibility. This has been through the dynamic financial analysis (DFA) conducted as part of the Work Bank study (utilising the approach employed on the Caribbean Catastrophic Risk Insurance Facility, CCRIF) which has demonstrated the technical feasibility in constructing a solvent and sustainable pool of risk. Building on this work the ARC team has developed that underlying model in-house, defining various pricing and risk management strategies under different scenarios and to develop communication material on risk transfer costs and potential risk pool saving for the country consultations. The model will be developed further with the assistance of the facility management service providers for the CCRIF, so that it can be used for financial risk management decision making purposes for an operational ARC and as more information emerges on country composition, participation and scope of initial capitalization.
Other technical work completed during the reporting period includes further work on the climate change stress tests; further development of Africa RiskView, with the creation of a new pan-African rainfall dataset from 1983 by the US National Oceanic and Atmospheric Administration Climate Prediction Centre, co-funded by the ARC Project; and a joint proposal for a NASA Earth Science Division, Applied Sciences Program grant for a one-year feasibility and prototype development study for an ARC-specific flood model together with research firm AER.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | ARC participation and operation guidelines developed
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Process for approving contingency plans and monitoring ARC payouts defined
Progress made in the period covered by this review, including numbers | Partially completed, with a process to be fully defined – for further refinement and consultation with stakeholders – by April 2012. The basic core elements for country participation have been defined. As work has progressed in 2011 it has reinforced the need for a full consultative process to finalize some of these elements, including the degree of flexibility that can be accommodated. In particular, processes for approving contingency plans and monitoring ARC payouts require consultation with countries and their partners, and is requiring longer than anticipated. This process will be documented in the final ARC Design Document. During this reporting period, the ARC project team has focused its efforts on studying existing examples of related complex approval processes and extracting lessons learned to refine existing mechanisms that can be used for ARC. In particular the CAADP process of approving agricultural investment plans across all participating countries, the recent contingency planning experience of Ethiopia as part of the risk financing mechanism, the World Bank study recommendations and recent discussions with the World Bank team working on the fourth weather derivative in Malawi, have helped the ARC team identify generic elements that contingency plans will need to have, bounds within which responses mechanisms should fall and criteria that they should fulfil, national institutional requirements and pit-falls that should be avoided. These concepts will be further refined as more detailed discussions are held at the country level and our working assumptions are tested by the wide-ranging on-the-ground feedback.
During this reporting period, the ARC project team has focused its efforts on studying existing examples of related complex approval processes and extracting lessons learned to refine existing mechanisms that can be used for ARC. In particular the CAADP process of approving agricultural investment plans across all participating countries, the recent contingency planning experience of Ethiopia as part of the risk financing mechanism, the World Bank study recommendations and recent discussions with the World Bank team working on the fourth weather derivative in Malawi, have helped the ARC team identify generic elements that contingency plans will need to have, bounds within which responses mechanisms should fall and criteria that they should fulfil, national institutional requirements and pit-falls that should be avoided. These concepts will be further refined as more detailed discussions are held at the country level and our working assumptions are tested by the wide-ranging on-the-ground feedback.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | No. of active users of Africa RiskView online platform
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 30
Progress made in the period covered by this review, including numbers | 20 enabled online accounts in total with several multiple users on each account, in addition to (non-online) Africa RiskView desktop users (8 country offices and three review teams). Curently Desktop version use is increasing rather than on-line version. Africa RiskView online is available to all WFP HQ staff via the intranet on request and several staff have requested access. Access has also been granted to additional WFP staff in-country (Ethiopia, Kenya and Rwanda and West Africa regional bureau to date) and those working on helping the team refine the tool (AIR, JRC, Italian National Agency for New Technologies, Energy and Sustainable Economic Development). Africa RiskView desktop version is being used by several additional WFP offices and reviewers. The ARC Project has been in discussions with Google Africa on the potential of creating an Africa RiskView v2, a second generation climate service tool that could be used to monitor and quantify weather risk by a wider base of users, but that does not necessarily reveal proprietary or potentially politically sensitive information on populations affected or response costs that are required for ARC.
The ARC Project has been in discussions with Google Africa on the potential of creating an Africa RiskView v2, a second generation climate service tool that could be used to monitor and quantify weather risk by a wider base of users, but that does not necessarily reveal proprietary or potentially politically sensitive information on populations affected or response costs that are required for ARC.
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 3 | 0.5
Impact Weighted Score | 12.5 | 0.125
Justification for the Score | Based on current progress, the ARC project will only partially achieve the original final targets by May 2012 for Output 2 due to delays with country consultations and the World Bank feasibility study which delayed the timeline. Full achievement of Milestone 1 for Indicators 1 and 2 is expected to happen in April 2012 with the completion of the required technical work pieces. However, full achievement of Indicators 1 and 2 can still be achieved by current design end date December 2012.
Output 2 Recommendation 1 | Milestones for Indicator 1 and 2 require revisiting in light of implementation experience and strategy refinement.
The ARC Steering Committee is due to review financing and institutional products, as part of the draft ARC Design Document, early in the second quarter of 2012. This is now expected to form the basis for subsequent drafting of the detailed Operations Manual and will lead to an agreed-upon process for inviting actors to participate on ARC’s governing board. In parallel the softer, flexible aspects of ARC’s design, such as the contingency planning component, will be further refined through interactive consultations with countries and stakeholders throughout 2012. During 2011 it became clear that the Operations Manual (Indicator 2, Milestone 3) will be the last design and consultation component to be completed, based on detailed legal work required given the final entity’s structure and jurisdiction. Refinement of the Manual may be required by ARC governors even after ARC is established, i.e. in the first half of 2013 and beyond the design phase project. However the critical components of the Operational Manual can be defined by December 2012.
Output 2 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2 | Given the project’s change in strategy regarding sharing Africa RiskView online, Indicator 3 warrants modification.
It is difficult to assess “active” users and, despite significant demand (30 external requests have been received), the team has also been actively limiting access to external parties outside of ARC due to the political sensitivities surrounding drought need estimates. The team has decided to currently limit ARV online access primarily to countries and their stakeholders working towards ARC participation, thus reviewing and customizing the model, and those who have received training on the tool. Following the planned in-country workshops, now scheduled to happen in early 2012 following the delays in the country outreach, access to participants will be granted.
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Consultation and political engagement carried out
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Low | 3
0.75
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | No. of consultations held with countries, Regional Economic Communities (RECs), donors, Non Governmental Organisations (NGOs) , International Organisations (IOs) and leading thinkers consulted on ARC concept
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 55 (including baseline)
Progress made in the period covered by this review, including numbers | 115 in total, including the baseline of 25. The ARC Project team has made excellent progress on this indicator briefing many partners on ARC. Broken down against broad classes of consulted parties, the numbers of institutions are as follows (individuals briefed are significantly higher): Countries: 30, e.g. including Ministerial consultations like the South African Minister of Finance, Praveen Gordhan; Hon. Mohamed Elmi, Minister, Ministry of State For Development of Northern Kenya and Other Arid Lands; Mr Antoine Ruvebana, Permanent Secretary, Ministry for Disaster Management and Refugee Affairs Donors: 7 (see Indicator 2). Regional Bodies & AUC Departments: 10, e.g. including AU Chairperson Dr. Jean Ping and Dr. Ibrahim Assane Mayaki, NEPAD CEO and their staff NGOs: 25, e.g. Oxfam , International Federation of the Red Cross and Red Crescent and other Rockefeller NGO grantees UN/IFIs: 8, e.g. World Bank, African Development Bank, UN Office for the Coordination of Humanitarian Affairs Technical/Academia/Private Sector: 10, e.g. Swiss Re, International Research Institute for Climate & Society, Google Africa, African Climate Policy Centre The consultations to date have been very positive, with significant interest and support for the project from a wide range of actors and sectors. Although country consultations are just beginning several interesting themes are emerging that are helping the team with ARC’s design. For example, the Kigali consultation clearly highlighted that participants prioritized the importance of a facility established and regulated in a robust and secure jurisdiction, executing a prudent financial risk management strategy with conservative solvency and sustainability goals. This observation led the ARC Project Team revisit the basic underlying criteria for the facility, removing the requirement of an African domain as a primary prerequisite and taking a more “function over form” approach to the facility’s institutional design. Consultations in Ethiopia have led to important lessons for contingency planning and associated approval processes; in Kenya, information about Kenya’s national drought contingency fund and drought early warning system are helping the team refine Africa RiskView to align better with these in-country systems.
The consultations to date have been very positive, with significant interest and support for the project from a wide range of actors and sectors. Although country consultations are just beginning several interesting themes are emerging that are helping the team with ARC’s design. For example, the Kigali consultation clearly highlighted that participants prioritized a facility established and regulated in a robust and secure jurisdiction, executing a prudent financial risk management strategy with conservative solvency and sustainability goals. So the ARC Project Team revisited the earlier underlying criteria for the facility, removing the requirement of an African domain as a primary prerequisite and taking a more “function over form” approach to the facility’s institutional design. Consultations in Ethiopia have led to important lessons for contingency planning and associated approval processes; in Kenya, information about Kenya’s national drought contingency fund and drought early warning system are helping the team refine Africa RiskView to align better with these in-country systems.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | No. of different actors financially supporting the ARC initiative (donors, private sector, Member States etc.)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 5 (including baseline of 3)
Progress made in the period covered by this review, including numbers | To date the ARC project still only officially has three financial donors: DFID, Rockefeller Foundation and IFAD. However, SIDA is now finalising approval to make a contribution, expected to be operational in early 2012. The team is in advanced discussions with the UAE and the US for contributions to the design phase. A US$1 million contribution from WFP’s internal Saudi innovation fund has been technically approved and is awaiting final endorsement. The European Commission are also considering a contribution to the ARC design phase. The Government of South Africa have expressed interest in contributing in some form. Following initial discussions in late 2009 KfW Bankengruppe, the German development bank, has also recently expressed interest in financially supporting the design project. The project is expected to achieve Milestone 1 by the end of 2011 and is on track to achieve Milestone 2 in May 2012.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Positive mention of ARC in national, regional, AU strategy papers, indicating its potential use as a risk management tool by governments
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 6 (including baseline)
Progress made in the period covered by this review, including numbers | There have been at least 11 positive mentions (including baseline). During the reporting period the focus has been on high level engagement and coverage, with national coverage being somewhat dependent on the delayed national outreach and detailed consultations. Coverage being achieved is demonstrating that ARC is seen as relevant to the needs and development response mechanisms for Africa. In addition to discussion at the January and June AU Summits, ARC has received positive mentions in other AU documents, events and interactions, such as: • NEPAD/AUC joint interventions at G20 Experts' Meeting (prior to Agriculture Ministers' meeting). This was captured as "national and regional pilots in weather risk management" in the final report. • South Africa sponsored resolution at the AU Conference of Ministers of Economy and Finance in Addis Ababa, March 2011, which tied in other decisions on disaster risk funding, such as under the Africa-Arab Cooperation agreements/summits • CABRI’s Annual Meeting Summary report, including reference to ARC, will be shared for consideration at the Fourth High-Level Forum for Aid Effectiveness in Busan • African technical negotiators have proposed language on the importance of risk financing and the benefits of regional risk pooling for Africa to the UNFCCC Loss and Damage Work Programme • AU Chairperson Ping hosting COP-17 High-Level Side Event on ARC in the Africa Pavilion • AU Chairperson Ping Op-Ed to be published in next issue of FT Magazine This is Africa on ARC as a critical component of the African COP17 agenda
• NEPAD/AUC joint interventions at G20 Experts' Meeting (prior to Agriculture Ministers' meeting). This was captured as "national and regional pilots in weather risk management" in the final report. • South Africa sponsored resolution at the AU Conference of Ministers of Economy and Finance in Addis Ababa, March 2011, which tied in other decisions on disaster risk funding, such as under the Africa-Arab Cooperation agreements/summits • CABRI’s Annual Meeting Summary report, including reference to ARC, will be shared for consideration at the Fourth High-Level Forum for Aid Effectiveness in Busan • African technical negotiators have proposed language on the importance of risk financing and the benefits of regional risk pooling for Africa to the UNFCCC Loss and Damage Work Programme • AU Chairperson Ping hosting COP-17 High-Level Side Event on ARC in the Africa Pavilion • AU Chairperson Ping Op-Ed to be published in next issue of FT Magazine This is Africa on ARC as a critical component of the African COP17 agenda
Indicator 6 (leave blank if standard indicator) | • NEPAD/AUC joint interventions at G20 Experts' Meeting (prior to Agriculture Ministers' meeting). This was captured as "national and regional pilots in weather risk management" in the final report.
Is this a Standard Indicator? | • South Africa sponsored resolution at the AU Conference of Ministers of Economy and Finance in Addis Ababa, March 2011, which tied in other decisions on disaster risk funding, such as under the Africa-Arab Cooperation agreements/summits
Select standard indicator from drop down list | • CABRI’s Annual Meeting Summary report, including reference to ARC, will be shared for consideration at the Fourth High-Level Forum for Aid Effectiveness in Busan | 0
Milestone for this review (including number, if any) | • African technical negotiators have proposed language on the importance of risk financing and the benefits of regional risk pooling for Africa to the UNFCCC Loss and Damage Work Programme
Progress made in the period covered by this review, including numbers | • AU Chairperson Ping hosting COP-17 High-Level Side Event on ARC in the Africa Pavilion
Output Performance for Output 3 | 1 | 1
Impact Weighted Score | 25 | 0.25
Justification for the Score | The Project has out-performed two of the three indicators in this output and although the current milestone for one indicator was not fully met, it is on track for the next milestone in May of 2012.
Output 3 Recommendation 1
Output 3 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | ARC established and capitalized
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.25
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | ARC entity established and able to take in funds? (Yes/No)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | None - First milestone is for Jan 2013
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Percentage of funds committed against ARC donor appeal
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | None - First milestone is for May 2012
Progress made in the period covered by this review, including numbers | The ARC team is already including preparatory discussions with prospective donors for ARC capitalisation in conjunction with their discussions to secure full financing for the design phase work
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 0 | 0
Impact Weighted Score | 0 | 0
Justification for the Score | No milestones for this reporting period. This output relates to progress in last phase of project lifetime, based on progress on other outputs.
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-12-01
Impact Weighting (must = 100) | 100%
Total Impact Score | 50 | 0.5
Output Risk | Medium | 2.25
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners
DFID staff | X
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility. | Undertaken by DFID staff in dialogue with project implementers based on their annual report; together with some consultation with other DFID country offices
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | The reality of navigating the institutional bureaucracies and structures of multiple political organs in a regional initiative such as ARC should not be underestimated. The mandate and legitimacy conferred by the institutions involved is key for the long term but the bureaucracies can result in unpredictable and variable pace of implementation in the short term
Working with Partners Recommendation 1
Working with Partners Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | Many of the constituent elements of ARC are not groundbreaking in themselves and build on approaches and experience of more limited application elsewhere but in combination and scale, and application in the African context, ARC constitutes an innovative approach to climate risk management
Best Practice / Innovation Recommendation 1
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | In a complex regional design process for a new instrument with multiple partners such as is the case with ARC, a strong degree of flexibility is required to enable response to potential changes in the landscape in which ARC operates and allow adjustment of approach and methodology; in this context, if refined approaches are adopted, then similarly updating indicators and milestones may well be warranted. The current approach of iterative and interwoven analytical work, consultation and capacity building for a novel instrument like ARC seems to be working and enhancing prospects of success but pace of progress can be slow as a result and transaction costs high.
Project Management Recommendation 1
Project Management Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
3289502 | African Risk Capacity (ARC) Annual Progress Report Dec 2011
3292763 | Additional Annexes for Annual Report
2882426 | Africa Risk Capacity ARC Project Memorandum Version 11 (2 December 2010)
3188319 | ARC Project Six Month Report, January-June 2011
2971403 | ARC UK-WFP Framework Arrangement and Admin Arrangement
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions?
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | The project is a design process - integral to the design work is how best to configure and operate an ARC regional contingency fund in a manner that maximises not just impact but longer term sustainability
Sustainability Recommendation 1 | The current Purpose statement and associated indicators reflect the level of the project's ambition. Neverthelesss, the Head of ARD noted that, given the project's central focus on design, it may be necessary to re-draft these to better reflect expected outcome at the end of the project ie. a robust design. This should be discussed with the ARC team, and conclusions reflected in next major reporting .
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | 0
R2 | 0
R3 | 0
A1: Purpose
R1 | 0
R2 | 0
R3 | 0
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | The ARC team and DFID team are already in consultation with the DFID Chief Economist to help secure the right economist team and strengthen the Terms of Reference for this key piece of work. | ARC Team is in direct contact with DFID Chief Economist; Lead Adviser is faciliating
R1.2 | In the context of the explained delays, a 6 month no cost-extension to June 2013 should be considered to allow for in-country capacity building activities to continue for the 12 months (as orginally envisaged) after ARC working groups formally and operational active, to enable full achievment on Output 1. This will also allow for enhanced achievement, and also provide a contingency buffer, across all other outputs. | DFID Lead Adviser to discuss further with ARC Team, and request extension if apropriate
R1.3 | 0
R2.1 | Milestones for Indicator 1 and 2 require revisiting in light of implementation experience and strategy refinement. | ARC Team to propose recalibrated milestones for DFID approval
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | 0
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | 0
R2 | 0
R3 | 0
Project Management
R1 | 0
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | The current Purpose statement and associated indicators reflect the level of the project's ambition. Neverthelesss, the Head of ARD noted that, given the project's central focus on design, it may be necessary to re-draft these to better reflect expected outcome at the end of the project ie. a robust design. This should be discussed with the ARC team, and conclusions reflected in next major reporting . | DFID team with WFP ARC team
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | Update milestones - see specific output recommendations/action points | ARC Team to propose recalibrated milestones for DFID approval
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Given the revised ARC Project country outreach strategy and the explained delays, milestones should be updated. Indicator 1 Milestone 2 of 6 ARC in-country teams should be recalibrated to end of June 2012; indicator 2 milestones should also be updated; Indicator 3 milestones should be updated to reflect the adjusted approach of consolidation of various studies. | ARC Team to propose refined milestones for DFID approval
AP1.2 | 0
AP1.3 | 0
AP2.1 | 0
AP2.2 | Given the project’s change in strategy regarding sharing Africa RiskView online, Indicator 3 warrants modification. | ARC Team to propose alternative indicator and milestones for DFID approval
AP2.3 | 0
AP3.1 | 0
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3