Programme Memorandum

Building Empowerment and Accountability in Malawi (BEAM)

December 2010

Table of contents

1.	Summary	4

2.	Programme Details	6

3	Programme Appraisal	14

Political Appraisal	14
Institutional Appraisal	15
Economic Appraisal	16
Gender and Social Appraisal	16
Fiduciary Appraisal	17

4.	Management, Contracting and Procurement Arrangements	19

5.	Methodology and Timing	21

6.	Funding	22

7.	Accounting and Audit	23

7.	Monitoring and Evaluation	24

8.	Risks	26

Annexes
Annex I	BEAM thematic Log Frame
Annex II	BEAM Budget
Annex III	Desk Review of Civil Society Funds
Annex IV	Situation Analysis on the State of Civil Society
Annex V	Technical arrangements for the Civil Society Fund
Annex VI	Full Appraisals (Restricted)
Annex VII	Signed UNDP Project Document for the Elections Trust Fund
Annex VIII	Draft NDI Project Document for Civic and Voter Education Civil Society Support project
Annex IX	Environmental Screening Note

Acronyms
ACB	Anti Corruption Bureau
BHC	British High Commission
CAP	Country Assistance Plan
CBM	Community Based Monitoring
CGA	Country Governance Analysis
CSF	Civil Society Fund
CVE	Civic and Voter Education
DPP	Democratic Progressive Party
ETF	Elections Task Force
EU	European Union
FA	Financial Aid
AGDI	Africa Gender Development Index
GGF	Good Governance Fund
GoM	Government of Malawi
GTF	Governance & Transparency Fund
GTZ	German Technical Assistance
IMF	International Monetary Fund
LGEs	Local Government Elections
MCP	Malawi Congress Party
MEC	Malawi Electoral Commission
MGDS	Malawi Growth and Development Strategy
MIS	Management Information System
NICE	National Institute Civic Education
OPC	Office of the President and Cabinet
PAC	Public Accounts Committee (of Parliament)
PAF	Performance Assessment Framework
PEA	Performance, Evidence and Accountability
PETS	Public Expenditure Tracking Survey
PPEs	Presidential, Parliamentary Elections
PRBS	Poverty Reduction Budget Support
SSAJ	Safety, Security and Access to Justice
UDF	United Democratic Front
UNDP	United Nations Development Programme

SUMMARY

  1. Malawi is a largely rural country and, despite impressive recent progress, poverty rates and basic service delivery remain a challenge. 16 years since multi-party democracy replaced 30 years of single party rule, many people are still unused to holding Government to account for services they provide, how they manage public money, or protection of basic rights. This leaves communities, especially the poor, lacking the ability to address the problems that reduce their quality of life and vulnerable to the impact of corruption.

  1. This programme will address these challenges by giving people the information, support and opportunities they need to play a greater role in their own development. Up to £14.4 million DFID funding will be provided over 5 years (2010-15), with different elements coming on stream at different points. It has been designed flexibly, to respond to changes in the governance or development context.

  1. The goal of the programme is more accountable, responsive and inclusive governance in Malawi, to support progress on off-track MDGs. The purpose is to empower citizens to hold the Malawi state to account and improve the delivery of basic services.

  1. The majority of DFID’s funding will be prioritised for a joint donor Civil Society Empowerment and Accountability Fund (DFID £8 million, Irish Aid £2.4 million, EU £4.2 million). This will support a range of innovations by civil society groups and others to achieve the overall objectives of the Programme, and specifically to enable citizens to:

- hold service providers to account for their performance (e.g. helping communities  to track the quality of health or education or agriculture services in their area, and make their views heard)
- increase government transparency and public accountability (e.g. helping communities to monitor  how funds allocated for their area are spent and what they achieve, and to feed in their views to national budget consultations); and
- enable excluded groups to improve their access to services and realise their rights  (e.g. helping people with disabilities to tackle the barriers that make it harder for them to access health or education, or action to address specific human rights concerns and gender inequality).

  1. The programme will also support key public oversight bodies or government led initiatives that demonstrate their ability to promote and enforce accountability and help combat corruption, such as the National Audit Office and Anti-Corruption Bureau. Specific funding arrangements and results will be negotiated during the inception phase and as current agreements expire (up to £4 million over 4 years).

  1. This programme marks a shift in DFID’s support away from core funding of formal democratic structures including Parliament. Instead, we will support civic and voter education to underline the importance of democratic institutions and encourage greater public engagement. £1.01m has been allocated to help the Malawi Electoral Commission deliver a credible local election in April 2011 (via a UNDP managed basket fund). We will consider a potential contribution to Malawi’s next national elections in 2014 at the programme mid point.

  1. This programme is in line with the UK Government’s Structural Reform Plan focus on building greater accountability and empowering citizens and DFID Malawi’s Operational Plan priorities 2011-15. The programme also supports the Malawian Government’s Growth and Development Strategy and the Democratic Governance Sector Policy Framework, and promotes aid effectiveness through joint donor work.

Programme Details

  1. The goal is increasingly accountable, inclusive and responsive governance in Malawi. The purpose is to empower citizens to hold the government to account for realisation of rights, inclusion and the improved delivery of basic services.

Rationale

  1. This programme marks a shift in DFID’s governance programming, to focus much more on local accountability and transparency to improve government responsiveness, and away from core funding to formal democratic structures.

  1. The shift is based on results of past programme evaluations as well as analytical work. We also recognise that the current governance situation in Malawi is subject to change and so we have designed the programme to be flexible.

  1. Multi-party democracy and the institutions and processes that go with it are still relatively young in Malawi. After independence in 1964 thirty years of one-party rule followed. Since 1994 Malawi has been a multi-party democracy, but is still a very rural and poor country and there remains a strong patrimonial trend, from village level to formal political structures.

  1. There has been definite progress since 1994. Human rights and the space for debate are much better than under one-party rule, although there is still scope for improvements. An increase in women MPs between 2004 and 2009 elections (14% to 23%) suggests progress on gender equality, but it is still a concern, and other marginalised groups have limited ‘voice’. The potential to build on gains is restricted by a trend towards increased centralisation of political power.

  1. Recognising persistent capacity constraints in formal political structures there has been extensive work to strengthen institutions and systems (key focus of Tikambirane programme 2003 to 2010, including Malawi Electoral Commission and Parliament). But progress was affected fundamentally by political context. This been very fluid and likely to remain so. Between 2004 and 2009 there was a minority Government in Parliament which led to stagnation in legislative reform, though strong legislative challenges to the executive. A big Government majority since May 2009 provides potential for driving forward development policy and legislation. But it does risk weaker scrutiny and oversight and increased centralisation of power. The local elections are due April 2011. This is an important opportunity for improving local governance, though after 10 years without elected councils there will need to be clear agreements on how to work with other local structures, including traditional authorities, and with central government. National elections are in 2014 and the race has already begun.

  1. The objective of the programme is to promote poverty reduction and the MDGs, and improve governance and security. Analysis suggests that a critical factor for accountable, inclusive and responsive governance is empowering local communities to demand such accountability. There has been a major focus in DFID Malawi on supply side interventions, to help Government build up systems to deliver effective public services (health, education etc). But we know it is important to balance these with more on the demand side to ensure gains are sustainable, especially in a context where decision making appears increasingly centralised. Supporting people’s voice is critical to making sure that the formal legal and administrative aspects of the state are not unduly influenced by those who wish to use the state to serve private interests. Otherwise, this can limit the ability of the state to make policies in the public interest, respond to genuine needs and to achieve pro-poor development objectives. In these situations formal mechanisms of accountability (including parliament, electoral processes etc) do not necessarily operate effectively as other factors might interfere with their ability to respond. .

  1. In Malawi, patrimonial traditions are more likely to reinforce private rather than public accountability, with citizens likely to make requests from public authorities for private goods rather than public goods (i.e payment of schools fees rather than improvement in school access per se). 75.9% of people expect their MP to deliver goods and services to people in their community above wider benefits[1].
    [1] Afrobarometer 2008 perception survey results

  1. Although poor local communities are often very distant from political and economic decision making in the capital, Malawi does have a tradition of engagement in civic life and organisation for collective action at the local level. Citizens do take action to hold public officials and other office holders to account[2], as evidenced by our experience in previous governance programming, including Tikambirane (2003-2010). Civil society and faith based groups also played the pivotal role in transition to multi-party democracy in early 1990s.
    [2] Ibid

  1. This programme will aim to build on this Malawian tradition of civil engagement, to support moves to greater public accountability and faster progress on development outcomes. Global evidence provides many examples of how citizen action can lead to the improvement of service delivery; can contribute to the development of new accountability frameworks; and help poor and marginalised groups realise political rights and democracy[3]. It also suggests that civil society can play a major role in empowering citizens and helping them hold public officials to account, but also to work with the state (and the government) and actors within it to achieve common aims. These issues were scrutinised in detail during the recent DFID Bilateral Aid Review, and preparation of DFID Malawi’s Governance and Security ‘offer’, which this programme is a key part of. DFID Malawi’s Operational Plan 2011-15 will reflect many of the high-level indicators associated with this programme, as well as the understanding that, although state capability is increasing, state accountability and responsiveness risk falling behind and we need to prioritise support to strengthen them.
    [3] See for example the work of the “Citizenship, Participation and Accountability” Development Research Centre housed at the Institute for Development Studies. Their publication “Putting Citizens at the centre: linking state and societies for responsive governance” provides a good overview.

  1. It is with this knowledge and experience that DFID Malawi intends to focus its current democratic accountability efforts on working to bolster those positive trends that already exist and can be harnessed to support pro-poor development. We will do this by supporting the role of civil society and other organised groups to broaden citizen demands for accountable and responsive governance, social inclusion and improved service delivery through a multi-donor Civil Society Fund.

  1. A key policy conclusion coming from current research is that “citizen-led initiatives are most likely to be effective when combined with support to formal accountability institutions and engagement across the state society divide”[4]. We will support those public oversight bodies, such as the Anti-Corruption Bureau and National Audit Office (NAO), and consider support to government-led initiatives (such as through the Ministry of Finance) that can make a genuine impact on political and economic accountability.
    [4] Ibid

  1. While many of the aspects of the formal system of democratic accountability are not functioning effectively, there is much evidence to suggest that elections in and of themselves have a positive impact on the institutionalisation and consolidation of democracy.[5] Based on current budgets the Local Government Elections (LGEs), gazetted to be held in April 2011, will require considerable outside assistance. Civic and voter education will also require outside support if it is to raise voter turnout and embed understanding of local governance issues. While long-term support to the Malawi Electoral Commission has proven to achieve little sustainable impact, DFID will support the planned LGEs to take place to help consolidate democracy and enable local level representatives to take their places in local governance after a 5 year gap.
    [5] Chauvet, Lisa and Collier, Paul (2009) ‘Elections and economic policy in developing countries’ Economic Policy 24 (59): pp. 509-550 and Lindberg, S. 2009 Democratization by Elections: A New Mode of Transition. Lindberg, S. 2006 Democracy and Elections in Africa

  1. We have not included support to the 2014 elections in this Programme Memorandum at this stage. We will however consider the size and form of a contribution to them at this programme’s mid-point.

Programme Interventions

  1. The BEAM Programme will bring together the range of interventions that were approved on June 18th 2010 under the initial inception phase submission[6]. These Inception Phase Interventions are: design, analysis and baseline work; support to the local government elections; and support to civil society to achieve results over the next year, through individual projects and grants from the Good Governance Fund. These Inception Phase Interventions will all be completed by late 2011, feed into the new components and be succeeded by consolidated support to civil society through the Civil Society Fund and direct support to autonomous public oversight institutions.
    [6] For the Deepening Democracy in Malawi programme, now re-designed and called Building Empowerment and Accountability in Malawi programme.

Inception Phase Interventions

  1. The one-year extension of the Good Governance Fund (to support civil society and media initiatives on civic education) and the one-year support to both Storyworkshop and the Malawi Economic Justice Network (MEJN) through accountable grants are interim measures to maintain support for civil society to increase government transparency, accountability and improve service delivery accountability at the local level, especially for marginalised people.

  1. Design work for the BEAM programme will continue into the 1st quarter of 2011. The central piece of work on designing a multi-donor civil society fund has already produced a desk-review of civil society funds elsewhere (annex III), a situation analysis on the state of civil society (annex IV), a technical arrangements for the civil society fund and Terms of Reference to be used to recruit the implementing agent for the fund (annex V). Final validation of this work and the beginning of the OJEC tendering process will start in January 2011.

  1. 2 further pieces of design work are also being commissioned: a Social Exclusion Analysis, to help define specific outputs for the Civil Society Fund and act as a baseline for measuring results, and a Political Economy Analysis of Development in Malawi, to help guide the Civil Society Fund (and civil society) in identifying entry points where increased accountability, inclusion and responsiveness can be achieved.

  1. BEAM also includes support to the Local Government Elections through an MoU to a UNDP-managed Electoral Trust Fund to strengthen the capacity of the Malawi Electoral Commission to conduct the elections (comprising of funding for UNDP-managed procurement and UNDP-contracted technical assistance) and support through an accountable grant for a National Democratic Institute for International Affairs (NDI) managed Civil Society Support programme that will assist the National Institute for Civic Education (NICE) and the Malawi Electoral Support Network (MESN) to undertake intensive civic and voter education. This will be achieved through the provision of technical assistance and management of sub-grants to CSOs.

New interventions

  1. While all the above Inception Phase Interventions will be completed within the first year, two other interventions are being proposed to come on-line in mid 2011 until 2015.

  1. Firstly, DFID will launch a Civil Society Fund, jointly with Irish Aid and the European Union. This will be based on the design work mentioned above, will run for four years and will begin to disburse grants in late financial year 2011/12 with final grants disbursed in 2014/15. The fund will provide grants to civil society organisations supporting citizen actions aiming to achieve results in three thematic areas, in-line with the first three outputs of the BEAM programme. Specific results will be identified and reviewed as the programme begins to ensure they remain relevant and appropriate. Activities supported will depend on the results we are looking to secure. However, current work supported by DFID can give an indication of the types of interventions the CSF might fund.

  1. Output 1: Civil society enables citizens to hold service providers to account for service delivery performance. DFID currently funds Community Based Monitoring (CBM) in 10 districts. This work brings citizens together to “score” health, education, water and agriculture services in their area and opens dialogue with service providers and local leaders to discuss how to tackle any problems. The CSF might scale-up such activities.
2. Output 2: Civil society engagement and action to improve government transparency, public accountability and responsiveness. The Inception Phase of BEAM supports a civil society network to bring citizens together with parliamentarians and other local leaders in 8 districts to provide input into the national budget process and monitor local expenditure and projects to ensure promises are delivered. The CSF might enable more people to engage in this process and increase its influence.
3. Output 3: Excluded and marginalized groups better able to access services and exercise their rights. The Inception Phase of BEAM is supporting a civil society organisation to develop a drama and discussion series for Radio coupled with listener groups, to open discussions on what groups in their community are disadvantaged with regard to access to services and what they can do to enable improvements and empower marginalised groups themselves. The CSF might allow this drama series to be extended to cover other issues, syndicated on other Radio networks or transferred to TV or other media such as community theatre.

  1. The fund will provide a range of grant sizes from small c.£20,000 grants to small CBOs, to large multi-year grants of £100,000+ to civil society networks, INGOs and coalitions of actors. Full details on the design of the fund are available at annex V.

  1. Secondly, BEAM will balance support for citizen-led action from below with support to effective autonomous public oversight bodies and government led accountability initiatives to take action from above and respond to public demands for accountability. This will involve up to 6 months of discussions with development partners, government and relevant public bodies to design a flexible but committed programme of support for submission by July 2011.

Background and Approach

  1. This programme began with an inception phase, approved in June 2010 to last until March 2011. This Programme Memorandum for the BEAM programme encompasses these interventions as well as proposing new areas of programming. Although design, analysis and baseline work will continue for the rest of the inception phase, the technical design of the major component of the BEAM programme, the Civil Society Fund, is complete and needs approval to enable DFID to undertake contracting in time to allow the Fund to become operational when the Inception Phase Interventions finish.

  1. DFID has a wealth of experience in governance programming to draw on in Malawi, with the most recent long-term programme being Tikambirane (2003-2010). As a successful initiative it provided many recommendations that have directly influenced BEAM. In particular, the experience that working to support the administration of formal accountability institutions, such as Parliament, actually made only “a limited contribution to processes of democratic accountability”[7] and that supporting “demand side” citizen accountability was often more effective have helped in developing our approach here that focuses on supporting citizen demand.
    [7] Tikambirane PCR, March 2010

  1. In terms of operation we have also taken from the experience of working on Tikambirane. As a diverse and varied programme of interventions it required a large number of contracts and accountable grants, with many relationships being directly managed by DFID. In recognition of the transaction costs of this, BEAM will contract out its major component- the Civil Society Fund. While this will not reduce transaction costs to zero, once it is operational it should enable less administration time from DFID staff.

  1. Our experience with current programme Performance, Evidence and Accountability (PEA) has also been formative. Under PEA we first supported Community Based Monitoring- a method of involving communities in scoring their services and engaging government to negotiate improvements. We have also been able to support many government-led initiatives to improve economic accountability that have been effective at delivering results, such as supporting the National Audit Office to ensure local government accounts are up-to-date and support to Public Financial Management reforms through the Ministry of Finance. These crucial initiatives to support government accountability will need a home when PEA is finished and with a mandate to link civil society support for demand to effective national public oversight and government-led accountability initiatives, we will have a good idea of what works with which to base this component upon.

  1. The programme will advance donor harmonisation. The two major components will both be undertaken in collaboration with others: initially Irish Aid and the EU for the CSF and Norway for the ACB support. Close working with the British High Commission will also be necessary due to the political nature of the work.

  1. It is important to note that BEAM is designed to complement and reinforce a number of DFID Malawi programmes, in particular General Budget Support and sector programmes which are helping to build service delivery capacity and other capabilities of the state. Support for accountability, inclusion and empowerment will ensure funds are monitored and therefore used more efficiently and effectively, and basic services meet citizen’s basic needs.

Stakeholder consultation

  1. A wide variety of stakeholders were consulted at the initial stages of design of this programme including civil society, media, government and the MEC.

  1. The design process for the Civil Society Fund (CSF) has provided a platform for us to undertake further consultation with government, development partners and civil society organisations. During this process Irish Aid and the EU have signed up to contribute to the CSF, and interest has been expressed by other DPs. Civil Society have been consulted individually and together and provided a input into how the CSF can meet CSO needs and achieve the results we are looking for.

  1. With regard to support to ACB, DFID currently has a joint programme of support with Norway, as well as beginning to engage in joint discussions with other donors about overall support to ACB and broader support to public oversight institutions. DFID have also been involved in discussions with the Government and APOBs themselves who have established a sub-sector working group on democratic accountability (chaired by the Ombudsman) to support donor-government engagement, especially on support to oversight institutions, as detailed in the Malawi Growth and Development Strategy (MGDS).

  1. The Elections Task Force (ETF) and Donor ETF have been the main coordination groups for support to the electoral process. UNDP’s role as coordinator of the Elections Trust Fund will help ensure coordination and dialogue with all relevant actors. The NDI programme will also involve all those involved in CVE and create a practical mechanism for coordinating activities through NICE and MESN.

Beneficiaries
  1. Poor and marginalised groups in Malawi will directly benefit from initiatives to provide them with the opportunity to voice their needs and hold government and others to account for their actions. This will be a benefit in instrumental terms as it will help improve basic services and speed up progress on MDGs. But it will also be of intrinsic benefit, increasing citizen’s ability to exercise freedoms and realise their rights.

  1. Women, girls and other marginalised and excluded groups will benefit through prioritised support to initiatives that promote social inclusion, equitable access to basic services and enable them to realise their fundamental rights.

  1. Civil society organisations will benefit from funding that will enable them to carry out their mandates and improve their ability to represent citizens. They will also receive targeted capacity building support to help create improved abilities on financial and project management.

  1. A wide range of public institutions and government departments will benefit from this programme, with specific beneficiaries at this stage being staff at MEC being provided technical support to increase capacity. Other beneficiaries will be defined as part of the planning for Output 5.
3.	Programme Appraisal
  1. This Programme Memorandum was has benefited from a wide range of inputs from outside DFID Malawi in the form of Marc Cassidy, Blessings Chisinga, Rachel Waterhouse, Tanweena Chowdury, Sam Waldock and Robert White and DFID Malawi staff comprising Charlotte Duncan, Jimmy Kawaye, Manu Manthri. Austin Msowoya, Thoko Chisale and Mulle Chikoko. The final version was drafted by Alex Stevens.

  1. Full Political, Institutional, Economic and Gender/Social Appraisals can be found in Annex VI.

Political Appraisal

  1. The 2009 elections delivered President Mutharika with a large majority in parliament (around 72% for his party, the DPP) changing the political environment and providing the opportunity to pass long-awaited bills and make appointments to senior state positions. However, the new situation also enabled an increase in the centralisation of power around the executive arm of government, and could potentially weaken formal accountability and scrutiny by formal bodies such as the parliament.

  1. However, despite formal accountability being weakened, civic action does have a strong tradition in Malawi. At a local level people are engaged with politics and do voice demands to office holders. This tradition of active citizenry and the existence of informal systems of accountability provides a potential entry point. By working with the grain of these systems, broadening them and using opportunities to push for public rather than private accountability where possible, BEAM can help support and empower people to demand increased accountability.

Institutional Appraisal

  1. Democracy is still young in Malawi and democratic institutions are still weak in many ways.

  1. The Electoral Commission was successful in managing the 2009 elections but with significant support from development partners. However, the impact of long-term support to develop MEC capacity has been largely minimal and suggests capacity is not necessarily the only problem.

  1. Most public oversight bodies also have weak capacity created by a lack of staff and financial resources and can face challenges to their role (e.g Director of the ACB can be removed by the President). However, there is evidence of agencies undertaking actions that are for the benefit of the public and help drive accountability, often because interests are aligned with groups in and outside government who can play an enabling (or disabling) role. For example, the Anti-Corruption Bureau has been provided with good capacity (partly through donor support) and has been able to take action on corruption.

  1. CSOs face many challenges, including institutional weaknesses such as poor capacity and financial management. However, given that formal institutions are playing a less robust scrutiny and oversight role, civil society will be increasingly important in filling this gap. The BEAM programme will contribute both to the institutional development of civil society and improving internal good governance, as well as to strengthening the role of civil society to implement programmes to promote more responsive and accountable government.

Economic Appraisal

  1. The rationale for intervention is described as a principal-agent problem, where low levels of political accountability weaken the control by the principals (citizens) over the agent (Government). This leads to socially sub-optimal provision of public goods, inequality (for those groups with particularly weak accountability), and a lower likelihood of government failure being addressed.

  1. The logic of the intervention design is that the supply and demand side interventions will be mutually reinforcing. Increased demand for accountability by CSOs and citizens will strengthen the hand of accountability institutions within government, and increased information flows from those institutions will provide material for the newly empowered CSOs to more effectively monitor performance and advocate for reform.

  1. The key economic benefits expected from the programme are a more pro-poor and equitable budget, and a more conducive environment for growth. Strong economic performance has increased levels of spending by government, but there is still scope in some areas for spending to be more pro-poor, and in particular for improvements in the quality of service delivery. Engaging CSOs in monitoring service delivery and policy debate has shown results in Malawi and internationally in terms of impacting spending decisions. Ongoing progress on political accountability will also be important for maintaining support from donors, especially general budget support, the Government’s preferred aid modality, which this year is expected to fund around 7% of Malawi’s budget.

  1. It is difficult to specify value for money at this stage since we do not know what projects the Civil Society Fund, which will absorb the bulk of the funds from BEAM, will fund. The management arrangements for the Civil Society Fund will therefore be crucial for ensuring value for money for BEAM as a whole. This will be delivered through a strong focus on results by the management agent for the Fund, and an independent M&E agent who will provide annual reports to the Board with recommendations for improving the delivery of results.

Gender and Social appraisal

  1. Poverty is estimated at 40% and remains particularly high among households headed by women and the elderly estimated at 48% compared to 38% of men. The 2010 Human Development Report (HDR) ranks Malawi in 153rd out 182 countries. The richest 10% of the population have an income eight times higher than the poorest 10% (a gini coefficient of 0.39).

  1. Women make up 51% of the population of Malawi. However, there is a huge gender gap between women and men in political, social and economic spheres. The Gender and Development Index (GDI) is estimated at 0.374. Women are not adequately represented in decision-making in the public sector. In 2004, one third of all women reported they had experienced gender based violence.

  1. The disabled constitute one of the single largest groups amongst the marginalized and socially excluded. The 2009 scoping study on disability and development highlighted that civic education and human rights agencies are still not aware of the need for disability access and inclusion. The disabled capacity to influence and engage in policy dialogue is weak.

  1. Increasingly more programmes are focusing on citizen voice including coalition building and access to information. In this context, the BEAM programme’s focus on improved service delivery outcomes for the poor, and for marginalized groups sets a critical challenge to achieve more accountable and inclusive governance. As part of the inception phase design a Gender and Social Exclusion Analysis will be undertaken and used to help target support in this area, create a baseline and inform the operation of the programme

Fiduciary Appraisal

  1. It is possible some of our support to autonomous public oversight bodies might use Financial ASid as a funding modality, as we currently do for support to the Anti-Corruption Bureau. In relation ot the ACB, a review of their financial and procurement systems of the ACB was undertaken in 2008 against the 15 benchmarks under DFID’s 8 Good Practice Principles and recommendations made in a 2005 financial systems review. The review rated risk at a low-level and programmes of improvement to address minor concerns raised were deemed credible. DFID will undertake a further review of this type before agreeing on-going support to ensure that all issues of concern have now been addressed. For any agreements to provide Financial Aid to other bodies or government departments under BEAM a similar review of fiduciary risk will be undertaken.

4.0	Management, Contracting and Procurement Arrangements

  1. BEAM will increasingly consolidate its work and simplify its management arrangements. The Inception Phase Interventions will be completed within the first year of BEAM leaving only two major components operating for the final 4 years. The Inception Phase Interventions will be implemented by DFID directly through accountable grants to civil society and contracts for analysis, baseline and design work.

  1. Support to the Local Government Elections will be administered by a UNDP Trust Fund (arranged through and MoU) and an accountable grant with NDI (see Annex VIII and VIX respectively for specific project documents for the Elections support). These will both be front-loaded to enable activities to start as soon as possible while funding from other development partners comes on-stream.

  1. The Civil Society Fund will be contracted out through an implementing agent, agreed through an open tender process open to both NGO’s and private companies. The tender will be conducted in line with EU OEJU procedures.

  1. In addition to the implementing agent, an Independent Evaluation Agent (IEA) will also be contracted. The IEA should have experience of administering a wide range of methodological approaches to measuring impact including randomised control trials, to contribute to a stronger evidence base for future governance interventions in Malawi.

  1. Although contracting out will significantly reduce transaction costs for DFID over the long-term, it will require heavy engagement in the first year to set the Fund up, and on-going engagement with the fund, engaging in reviews, maintaining links with civil society groups, on-going political analysis etc. For this reason we will also recruit a locally-employed Assistant Governance Adviser to manage DFID’s interest in the CSF

  1. The support to autonomous public oversight bodies and government-led accountability initiatives will begin with negotiations with development partners, oversight bodies and government Ministries to agree where DFID would be most effective at leveraging support for political and economic accountability. We hope that the agreed plan of action for Output 5 will be developed as a joint donor initiative. Contributions might be Financial Aid or through a joint donor mechanism.

Output	Key activities	Implementation Modality
Output 1: Civil society enables citizens to hold service providers to account for service delivery performance	Support to civil society organisations to support service delivery accountability initiatives such as Community Based Monitoring, creation of Health Action Committees, Service Delivery Satisfaction Surveys etc	Contracted out Civil Society Fund (2011-15) / Storyworkshop accountable grant (Dec 2010- Dec 2011) / MEJN accountable grant (Dec 2010- Dec 2011)
Output 2: Civil society engagement and action to improve government transparency, public accountability and responsiveness	Support to civil society organisations engaging in national policy processes to improve formal accountability (such as legislative change to improve access to information) and other initiatives such as budget transparency, engagement with parliamentary committees, anti-corruption, political reform etc	Contracted out Civil Society Fund (June 2011- Dec 2015) / Storyworkshop accountable grant (Dec 2010- Dec 2011) / MEJN accountable grant (Dec 2010- Dec 2011)
Output 3: Excluded and marginalized groups better able to access services and exercise their rights	Support to civil society representatives and organised groups of excluded citizens who aim to promote social inclusion, push behavioural change and enforce realisation of rights through initiatives such as advocacy for legislative change or support to leaders of excluded groups to improve political representation.	Contracted out Civil Society Fund (2011-15) / Storyworkshop accountable grant (Dec 2010- Dec 2011) / MEJN accountable grant (Dec 2010- Dec 2011)
Output 4: Electoral processes able to deliver free and credible local elections in 2011 with increased public participation	Strengthen the Electoral Commission to manage general and local elections following an electoral cycle approach; / National civic and voter education program that strengthens citizens understanding of and participation in civic and political processes and support to election monitoring.	Contribution to UNDP Trust Fund (Dec 2010-May 2011) / Accountable Grant with NDI (Dec 2010-May 2011) / Some Good Governance Fund Projects (on-going until May 2011)
Output 5: Key Malawian public oversight bodies and government-led initiatives step-up actions to promote political and economic accountability and combat corruption	Supporting activities of public oversight bodies and government Ministries to tackle corruption and promote political and financial accountability, and promoting their links with civil society and others with similar aims	Development of a (joint donor) programme of support to a range of institutions

Methodology and Timing

  1. The BEAM programme will be implemented in two main phases from June 2010 until March 2015:

    1. An inception phase, already begun, from June 2010 to March 2011, with the following key milestones:

By end December 2010
- Good Governance Fund Grants agreed and disbursed
- Storyworkshop accountable grant agreed and first tranche disbursed
- MEJN accountable grant agreed and first tranche disbursed
- Accountable Grant with NDI agreed and disbursed
- MOU signed with UNDP and contribution to Trust Fund agreed, and disbursed

By end January 2011
Final design of the Civil Society Fund and Independent Evaluation Agent agreed and contracting process begun

By end February 2011
- Social Exclusion Analysis undertaken and changes to PM agreed
- Political Economy Analysis study undertaken and changes to PM agreed
- Programme funded Assistant Governance Adviser recruited
- Inception phase ended

    1. A 4 year implementation phase from March 2011:

By end July 2011
- Civil Society Fund contracting finished and chosen implementing agent and independent evaluation agents contracted
- Support to Elections programmes completed and wrapped up
- Programme of Support for Output 5 submitted and approved

By end September 2011
Civil Society Fund managing agent in place and preparing first call for proposals

By end January 2012
- Accountable grants to Storyworkshop, MEJN and under the Good Governance Fund all completed and wrapped up
- First grants to civil society organisation under the CSF agreed and disbursed

Funding

  1. DFID’s contribution to BEAM is £14,388,300.00. This can be accommodated within the aid framework and is consistent with the BAR final settlement. (NB- in budget below other donor contributions- marked in red and smaller type- are not captured in sub-totals or totals)

Intervention	2010/11	2011/12	2012/13	2013/14	2014/15	TOTAL
Inception Phase Interventions
UNDP Electoral Trust Fund	1,070,000
Other donors contribution (approx)	2,500,000					2,500,000
NDI accountable grant for Civic and Voter Education	410,000
USAID Contribution (approx)	2,500,000					2,500,000
Good Governance Fund accountable grants	130,500	51,500
Story Workshop accountable grant	82,200	56,800
MEJN accountable grant	60,000	40,000
Drivers of Change Study	70,000
Social Exclusion Study	50,000
Civil Society Design Consultancy	35,000
4% contingency	89.300
Sub-total	2,000,000	148,300				2,148,300

Civil Society Fund
Set-up, running costs, capacity-building, out-reach, independent evaluation agent and implementing agent overheads		444,756	461,578	440,128	419,451	1,765,913
CSF Grants		1,182,245	2,120,928	2,329,943	2,366,883	8,000,000
A2L Assistant Governance Adviser		60,000	60,000	60,000	60,000	240,000
Sub-total		202,245	2,140,928	2,349,943	2,386,883	8,240,000
EU Contribution						4,134,550
Irish Contribution						2,362,600

Support to Autonomous Public Oversight bodies
Programme of Support to be agreed by July 2011		1,000,000	1,000,000	1,000,000	1,000,000	4,000,000
Sub-total		1,000,000	1,000,000	1,000,000	1,000,000	4,000,000

GRAND TOTAL	2,000,000	2,350,545	3,140,928	3,349,943	3,386,883	14,388,300

Accounting and Audit

  1. BEAM will use a range of funding modalities including accountable grants, contracts, multi-donor trust funds and financial aid. An imprest account is not required.

  1. For the accountable grants, normal DFID Malawi procedures will be used, including the requirement for annual audits.

  1. For the UNDP Multi-Donor Trust Fund, DFID will sign a standard MoU. The Trust Fund will be subject to an audit at the end of its operation.

  1. For the civil society fund although final arrangements have not been agreed, it is likely a multi-donor account will be set up to receive quarterly payments by each of the contributing partners for draw-down by the contracted managing agent. This account will be audited on an annual basis. Specific procurement audits will be undertaken where required and procurement practices will require standard international best practice (3 competitive quotes) and a no objection from contributing partners. For the grants provided by the fund, the managing agent will undertake annual audits of all grantees with specific focus on procurement.

  1. For any financial aid agreed to the Anti-Corruption Bureau or other public bodies or government Ministries DFID will use standard provisions which require annual audits of the receiving body before the disbursement of a tranche of funding into the bank account.

  1. In cases where audits provide evidence of financial mismanagement DFID will retain the right to claim refunds of their money and where fraud or corruption is uncovered, seek prosecution of those responsible. Similar language to this will be added to all agreements signed under BEAM.

Monitoring and Evaluation

  1. There will be a strong focus on impact and results. Outcomes and impact will be measured through SMART indicators and OVIs using baseline information gathered and analysed during the inception phase and other data gathered during the lifetime of the programme to fill gaps in existing information.

Inception Phase Interventions

  1. Storyworkshop and MEJN both have agreed logframes linked to their accountable grants to enable us to track progress and measure results. We will use their results as baselines, as well as provide evidence on “what works” to the Civil Society Fund partners. Both programmes contribute towards outputs 1, 2 and 3.

  1. Our support to the UNDP Electoral trust Fund (ETF) for the local government elections is agreed under an MoU with UNDP against their Project Document and an additional logframe agreed between us that contributes towards output 4 of the BEAM logframe. Monthly tracking of the progress with the elections at Elections Task Force meetings, including progress of the UNDP project, will enable us to ensure results are being achieved.

  1. Our support to Civic and Voter Education for the elections will be though an accountable agreement with the National Democratic Institute for International Affairs (NDI). A full logframe will be agreed during the first month of the project’s inception. It will contribute towards output 4 of the BEAM logframe.

Civil Society Fund

  1. The Civil Society Fund is the major contribution to outputs 1, 2 and 3 of the BEAM logframe from late 2011. Its own draft results framework will mirror these outputs and it is significantly reflected in the BEAM programme purpose and goal.

  1. In recognition of the weakness and lack of data on accountability and empowerment interventions, an Independent Evaluation Agent will be contracted separately from the management agent and is to be overseen by the CSF board. Responsible for evaluation of the impact of individual projects and the portfolio as a whole, the independent evaluation agent, along with the board, will keep the fund focused on the delivery of results.

  1. The Terms of reference for the Independent Evaluation Agent will be developed in the first month of BEAM and tendered alongside those of the implementing agent for the fund.

Autonomous public oversight bodies and government-led accountability initiatives

  1. As the funding to public bodies is yet to be finalised, output 5 of the BEAM logframe provides an indicative over-arching purpose for support and an indicative indicator for monitoring ACB impact on corruption. Another indicator relating to PEFA scores will be added following next year’s EU supported PEFA exercise

Risks

  1. This is a medium risk but potentially high impact programme. Some immediate risks identified are:

Risk	Likelihood	Impact	Mitigating Measures
MEC is unable to act independently to deliver a free and fair election	Medium	Medium	Monthly engagement with GoM, MEC and development partners at Electoral Task Force will manage any issues.
Weak MEC capacity leads to financial mismanagement of donor funds	Low	High	UNDP will manage all donor funds and all procurement. MEC has implemented new financial management practices since 2009 and will be strengthened by officers from GoM.
Civic and Voter Education begins too late to have significant effect on voter turnout	High	Medium	By using NDI DFID will maximise chance of a speedy implementation. Impact of CVE will also last beyond elections and support on-going citizen-local government engagement based on awareness of roles and responsibilities.
Opposition from Government to a programme enhancing scrutiny/oversight of its role.	Medium	High	Dialogue with GoM during design for greater understanding of objectives and benefits to Government.
Complex implementation arrangements leading to transaction heavy programme for DFID and/or delays in implementation	Medium	Medium	Progressive consolidation of interventions over year one should ensure a lower level of transaction costs by December 2011. An Assistant Governance Adviser will also be hired to oversee and manage advisory inouts into the Civil Society Fund, reducing DFID’s transaction costs further.
Weak capacity of civil society (particularly in financial management and corporate governance) leading to mismanagement of funds or poorly managed programmes	Medium	High	Fund manager appointed with sufficient financial management expertise. Capacity building of CSOs included across the board.
Poor links between different components with the programme leading to a disjointed approach	Low	Medium	By bringing together projects that support civil society to demand accountability together with autonomous public oversight institutions that enforce accountability of government BEAM will ensure better linkages than if both areas were managed separately. Regular BEAM partner meetings will be developed to bring the two sides together.
Curtailing of media and civil society and/or media increasingly resorting to ‘self censorship’ reducing their accountability role	Medium	Medium	Programme to counteract this by providing financial support and a degree of financial independence. BHC/DFID meetings with media and civil society to encourage robust and professional reporting and support to citizen action.
Duplication of donor funded programmes in accountability overstretching capacity of civil society	Low	Medium	Civil Society Fund will be a multi-donor fund and encourage others beyond the current three partners to join.
Autonomous public oversight bodies mismanage financial aid	Medium	High	Audits will be undertaken on an annual basis, including procurement audits where appropriate, and all funding will be provided on the basis that it is a) against a strategic plan and b) is immediately refundable should financial mismanagement be uncovered.
Autonomous public oversight bodies have their independence curtailed by government/legislative change	Medium	High	On-going political economy analysis will assess the ability of APOBs to operate freely and entry points to push for change. Engagement in the GoM’s sub-sector working group on democratic accountability will enable concerns to be raised.

  1. An independent risk register will be maintained for the Elections project, the Civil Society Fund, and the funding to autonomous pubic oversight bodies, including the ACB.