## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 113862
ARIES Project Description | Regional HIV AND AIDS STIGMA AND DISCRIMINATION UNIT (RSDU)
A1: Goal, Purpose, Risk
Goal
Goal statement | to contribute to a reduction in stigma and discrimination against PLWHAs, their families, and other vulnerable groups in the Caribbean region.
Indicator 1 | No. of project countries reporting a reduction in stigma and discrimination among people living with HIV (PLHIV)
Milestone for this review (if any) | Baseline data collection completed by March'11. SUAG agree on baseline and endline targets by May'11
What progress has been made in the period covered by this review? | No baseline data available and no targets set as yet. SUAG has proposed to use a 20% reduction as anticipated target. Stigma community response assessment tool (SCOR-B) designed, pre-tested and validated. Baseline assessment conducted in 7/12 project countries; field work completed in 5/7- statistical analysis underway/draft data available for a few countries, all 7 reports to be finalised in Dec'11/Jan'12. Validation of assessment tool took longer than anticipated (completed in Aug'11) and baseline assessment commenced much later than planned. Various projects initiated with the potential to achieve the targets set. Interventions have been selected based on participatory country needs assessments and best practices collated in the Inception Phase and from regional/global best practices.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | No. of project countries reporting an increase in percent of population 15-49 with a positive attitude towards the rights of PLHIV
Milestone for this review (if any) | Baseline data collection completed by March'11. SUAG agree on baseline and endline targets by May'11
What progress has been made in the period covered by this review? | See response indicator 1
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Targeted interventions commenced in 11 countries in close collaboration with national partners involving and reaching identified target groups (PLHIV, sex workers, youth, MSM and migrants) directly and through identified pivotal actors. It is anticipated that these interventions will lead to a reduction in the levels of stigma and discrimination experienced by PLHIV and other vulnerable groups and improve attitutdes towards the rights of PLHIV.
Goal Recommendation 1 | Stigma Unit Advisory Group (SUAG) to confirm goal level targets during Feb'12 SUAG meeting.
Goal Action Point 1 | • RSDU to finalise reports of baseline assessments and share a summary of core baseline data for each of the 7 countries in which SCOR-B has been completed with SUAG members by late January 2012 latest. • RSDU to include a summary of relevant (baseline) data/information collated during the initial needs assessment for the 5 project countries where no detailed baseline survey is done.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | PANCAP's capacity to coordinate regional and country level stigma and discrimination work enhanced
Indicator 1 | SMART indicators to measure reduction in stigma and discrimination integrated within PANCAP's routine monitoring framework (monitoring)
Milestone for this review (if any) | Draft (SMART) S&D related indicators identified based on S&D projects monitoring reports. Draft RSDU results framework with indicators completed to be reviewed by PANCAP, TWG & partners by Dec'11
What progress has been made in the period covered by this review? | Slight delay - milestone expected to be achieved by Jan/Feb’12 • Draft stigma assessment framework being finalised as well as a community-based interviewers’ training guide to accompany the survey instruments. The data collection instruments cover aspects of self stigma, experiences of stigma and discrimination, attitudes towards marginalised groups, human rights knowledge. The framework includes explanations for each key indicator used to measure a change in stigma and discrimination. • TWG Monitoring and Evaluation, including PANCAP PCU staff, has been actively involved in the various stages of development of the assessment tool and in its pilot testing and validation. Further work is planned over the coming 2 months.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Funding to sustain Regional Stigma and Discrimination Unit (RSDU) beyond end of Stigma Unit project secured (resource mobilisation)
Milestone for this review (if any) | 2012 budget includes funding for RSDU
What progress has been made in the period covered by this review? | • Milestone not achieved; no budget secured as yet. • PANCAP Project Co-ordination Unit (PCU) is awaiting outcome of the planned external appraisal (Feb/March '12) on role/responsibilities as well as location and staffing requirements of RSDU. Draft ToRs for this review reviewed during Dec'11 SUAG meeting. • PANCAP PCU not succesful as yet in identifying funding to retain technical officer stigma discrimination within PANCAP PCU. As DFID funding comes to an end-this post currently included in the PCU staff establishment- might end and the tasks/responsibilities of this post will be combined with other core functions of the PANCAP PCU.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | No. of best practice intervention packages adopted by the Regional Coordination Mechanism (RCM) of PANCAP (advocacy)
Milestone for this review (if any) | 5 draft best practices intervention packages endorsed by SUAG by Sep'11.
What progress has been made in the period covered by this review? | Milestone not achieved by Sep'11, expected to be achieved by Jan/Feb'12 • 5 intervention packages in various stages of development. One package for each of the 5 key target groups identified (PLHIV, sex workers, youth, migrants and Men having Sex with Men (MSM) • Each intervention package covers P0) participatory needs assessment, P1) preparing for action – community advocacy & leadership development, P2) building champions for change, P3) training and capacity building (target groups as well as pivotal groups), P4) development/production Behaviour Communicaction and Education materials for advocacy/awareness raising with ongoing assessment of achievements and effectiveness of approaches and P5) end evaluation for a more objective assessment of achievements to ensure the ultimate package is effective in initiating change. • PANCAP PCU has committed to include discussions and endorsement of the intervention packages on the agenda of the March’12 RCM meeting.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4 | No. of countries with national programmes addressing stigma and discrimination (advocacy-coordination)
Milestone for this review (if any) | 10 countries involved in stigma unit project by Sep'11
What progress has been made in the period covered by this review? | • Milestone achieved • RSDU supporting implementation of activities in 11/12 project countries in close collaboration with national partners; interventions aligned with national programmes.
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | The main purpose level assumption concerns the importance of continued political commitment of governments to promoting human rights and reducing stigma and discrimination. • For 11/12 countries this assumption is largely being realised. • Engagement of national level government and National AIDS Committees in project activities is good. Country level stakeholders appreciate efforts of the project to support activities to reduce stigma/discrimination – a key driver of the epidemic in the region. • However, initiation and completion of project activities are severely hampered in one country (Guyana) due to political situation. RSDU and PANCAP PCU will consider whether continuation in Guyana will be feasible.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | • The project is expected to achieve a reduction in S&D amongst identified vulnerable groups in project countries through implementation of intervention programmes based on evidence and good practice. Too early to identify the extend of change expected. • The developed S&D assessment tool (SCOR-B) and evidence-based intervention packages have the potential for replication/dissemination beyond the project reach and thus enhance PANCAP’s capacity to advocate, co-ordinate and monitor work on S&D in the region. • The project is contributing to achievement of targets as set in the Caribbean Regional Strategic Framework on HIV/AIDS (2008-2012). Its country level focus is greatly appreciated by PANCAP PCU director. Other regional partners/stakeholedrs (KfW, UNAIDS) however are awaiting prove of effectiveness of RSDU approach. • Human Resource (HR) capacity at PANCAP PCU is a concern. The HR capacity has been enhanced by the project, but PANCAP PCU has indicated that the post responsible for enhancing work on S&D in the region might not be retained due to funding constraints. This post is currently paid for by the project.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | The work towards the establishment of baselines for stigma and discrimination; the development and dissemination of intervention strategies for key vulnerable populations; and the engagement of National AIDS Programmes and other county level stakeholders and pivotal groups (inc. Faith-Based Organisations, health workers) in the development of programmes to tackle stigma and discrimination are all key contributions to the purpose that are attributable to progress made in delivering outputs in this project.
Purpose Recommendation 1 | • PANCAP PCU to obtain endorsement/support from Regional Co-ordination Mechanism (RCM) for dissemination and utilisation of the SCOR-B and the 5 intervention packages across programmes at the next RCM meeting in March 2012
Purpose Action Point 1 | • PANCAP PCU Director to include RSDU project outputs (SCOR-B and 5 intervention packages) on agenda of next RCM meeting (March’12) • RSDU to finalise SCOR-B framework and summary page of baseline data for each of the 12 countries for sharing with TWG and subsequently SUAG members for review/endorsement during planned Feb’12 steering group meeting. • RSDU to summarise intervention packages on a flow chart with reference to relevant projects/materials developed and assessments/reviews conducted to collate the evidence required to show the packages are good practice and evidence based (1 chart/target group). Make reference to use of PANCAP HIV Anti Stigma Toolkit as appropriate. This will be shared with SUAG members for review/discussion at the planned Feb’12 SUAG meeting. • RSDU to draft presentation for PANCAP PCU Director for use at the March’12 RCM meeting. This should include a summary of external review findings on options for RSDU future.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2 | • PANCAP PCU to address imminent HR constraint and identify key person to take forward work on stigma and discrimination
Purpose Recommendation 3 | • DFIDC to explore option for a cost and time extension of the MOU with PANCAP to extend the strategy and resourcing officer’s post till August’12, the current end-date of the RSDU project. This would enable active involvement of PANCAP PCU in the crucial stages of the project as well as assist PANCAP with exploring options for continuation of key RSDU functions/roles based on the planned external review.
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 2 | 2.3
Purpose Justification | • Notwithstanding delays in project implementation, substantive progress has been achieved over the last year. Sharing and presentation of key RSDU outputs (SCOR-B and good practices/evidence-based intervention packages) at the upcoming RCM for endorsement/support is seen as a crucial step to ensure sustainability and use of RSDU outputs beyond the project period and beyond project countries. • While acceptance of the assessment tool and intervention packages by the RCM will boost and enhance PANCAP’s capacity to enhance co-ordination, advocacy and monitoring of stigma and discrimination work in the region, staffing and funding constraints might hamper the full achievement of project purpose at the end of the project.
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | No
If Yes, why was/is this?
Logframe Recommendation 1
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision?
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Regional Stigma and Discrimination Unit (RSDU) fully established and functioning
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | Yes
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.3
DFID Share revised/needs revision?
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 | Stigma Unit Advisory Group (SUAG) established and functioning | 4
Is this a Standard Indicator? | No | 5
Milestone for this review (if any) | At least 2 meetings per year conducted | 0
What progress has been made in the period covered by this review? | • Milestone achieved: 2 meetings conducted (April and December 2011). • April’11 meeting: 64% attendance rate of SUAG members. Minutes prepared/shared • Dec’11 meeting (5 Dec’11): 77% attendance rate
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Regional Stigma and Development Unit (RSDU) fully staffed
Is this a Standard Indicator? | No
Milestone for this review (if any) | Review (options appraisal) conducted on future role/responsibilities and staffing requirements by Sep'11
What progress has been made in the period covered by this review? | • Milestone not achieved • RSDU fully staffed (6 staff members) but final organogram and job descriptions not yet shared with SUAG members. • Draft ToRs for the external review of role/responsibilities and future of RSDU shared at 5 Dec’11 SUAG meeting. Review planned for Feb/March 2012. Selection panel in principle agreed upon during 5 Dec'11 SUAG meeting.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | RSDU workplan implemented
Is this a Standard Indicator? | No
Milestone for this review (if any) | Year 1 (April'10 - March'11) activities of workplan completed as scheduled.
What progress has been made in the period covered by this review? | • Substantive progress made, although not all activities completed as per planned timeline. An estimated ….% of activities completed as per workplan by Sep'11 • 38% of year 3 budget spent as per Sep’11 and …..% of total budget allocated for implementation phase spent
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 1 | 2 | 0.75
Impact Weighted Score | 22.5 | 0.225
Justification for the Score | There has been good progress on this Output although not all milestones have been reached. The most important outstanding issue relates to an external review to guide the future role/responsibilities/location/size of the RSDU. Plans are however in an advanced stage to move this forward.
Output 1 Recommendation 1 | External review of current and especially future role/responsibilities, location and funding requirements of the RSDU to be conducted Feb/March 2012 latest to ensure findings can be shared with the Regional Coordination Mechanism at their next meeting (March’12)
Output 1 Action Point 1 | As agreed at 5 Dec’11 SUAG meeting: • RSDU to update and share ToRs for external consultancy with SUAG members (mid Dec'11) • SUAG members to provide feedback within 1 week • RSDU to place advert as soon as ToRs finalised: draft advert to be reviewed by SUAG • RSDU and PANCAP PCU to review RSDU budget as well as explore other funding sources to fund the external review • Selection panel to convene mid/late January 2012. OECS HIV/AIDS project unit (Dr James Catherine) has been appointed (and accepted) to chair the selection panel.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | RSDU to share RSDU organogram and job descriptions with the SUAG members (outstanding action from SUAG meeting and from 2010 review)
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Evidence based programmes developed addressing stigma and discrimination
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Baseline and endline assessments completed and findings dissseminated to National AIDS Programmes (NAPs) and SUAG
Is this a Standard Indicator? | No
Milestone for this review (if any) | Baseline surveys completed in all 12 countries by March 2011
What progress has been made in the period covered by this review? | Milestone not achieved Needs assessments in all 12 project countries were completed by October 2010. The validation of the baseline assessment tool (SCOR-B) took longer than anticipated and was only completed in August 2010 and findings shared with NAPs and other stakeholders. Field work for baseline data collection has been completed in 5 countries with analysis expected to be completed within next month. In 2 countries baseline data collection is currently being finalised. No further baseline data collection is planned. All reports are expected to completed by the end of January 2012.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Operational research conducted in target countries as per identified needs and findings disseminated to NAPs and SUAG
Is this a Standard Indicator? | No
Milestone for this review (if any) | Operational Research including human rights surveys completed for all key target groups (youth, MSM, sex workers, MSM, PLHIV and migrants)
What progress has been made in the period covered by this review? | Milestone achieved Human rights surveys and formative assessments (Belize) completed as part of baseline survey in 5 countries (St Lucia, Grenada, Belize, Dominica, St Vincent)
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | No. of projects designed including M&E framework with SMART indicators based on research findings
Is this a Standard Indicator? | No
Milestone for this review (if any) | 12
What progress has been made in the period covered by this review? | Milestone achieved • 14 projects planned to follow a full project cycle their design based on country assessment/baseline data, country consultations and participatory priority setting, empowerment/leadership skills building, champions-for-change, BCC development/advocacy, working with media, FBOs and health care workers to create a conducive environment and end evaluation. • For 4 of the 5 identified vulnerable target group a full/complete project is being implemented in at least 2 countries. Migrants are only reached in one country. 1. Belize 2 full projects: PLHIV and MSM/LGBT (+substantive work with FBOs, media, health workers, govt) 2. Guyana 3 full projects: PLHIV, MSM, sex workers (+ substantive work with FBOs and health workers) 3. St Lucia 4 full projects: PLHIV, MSM, sex workers, youth (+ substantive work with FBOs, health care workers) 4. St Vincent No full projects, but some activities with PLHIV and MSM and substantive work with FBOs and health care workers 5. St Kitts No full projects, but some activities with PLHIV, youth and FBOs, while supporting work on S&D through other organisations 6. Antigua No full projects, but TA to Govt and activities with FBOs and partnership with Caribbean HIV AIDS Alliance for further work 7. Jamaica 2 full projects MSM, youth (+ substantive work with FBOs) 8. BVI no full project. TA to NAP for work with youth, PLHIV 9. Dominica : No full projects, but provision of TA to government, other partners to reach PLHIV, MSM, SW as well as FBOs, health care workers 10. Grenada 3 full packages PLHIV, MSM, SW/migrants (+ substantive work with FBOs, health care workers) 11. Anguilla no full project, but TA to government for work with youth, tourism workers 12. Montserrat no full project, but TA to NAP for work with MSM
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 2 | 2 | 0.75
Impact Weighted Score | 18.75 | 0.1875
Justification for the Score | There has been good progress against the milestones for this output. The progress in the design and implementation of country-led targeted activities is especially impressive. In some countries activities were designed based on initial needs assessment. However, in countries targeted for a full baseline assessment activities could only commence once field work was completed.
Output 2 Recommendation 1 | RSDU to prepare overview of content of full intervention package per target group highlighting how each of the activities currently planned/implemented in the 12 countries will contribute to the evidence of good practice.
Output 2 Action Point 1 | • RSDU to re-assess the ambitious workplan and consider a reduction in those activities that are considered not essential to inform the development of evidence-based intervention packages • RSDU to carefully plan and communicate in close consultation with PANCAP PCU any planned reduction in activities
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2 | RSDU to review and if required re-profile budget to ensure sufficient funds is allocated for external TA to assist with finalising baseline data analysis and report writing as well as assist/conduct the end-line assessment.
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Country-led Coordination Committees monitor achievements of stigma and discrimination programmes developed based on research findings
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | Yes
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.3
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | No. of countries with NAP-led coordination mechanisms addressing priorities in stigma and discrimination
Is this a Standard Indicator? | No
Milestone for this review (if any) | 12
What progress has been made in the period covered by this review? | Milestone not achieved Four countries have established Community Advisory Board (CAB) committees (St. Lucia, Jamaica, Grenada and Belize), while Guyana has integrated the oversight of projects within its prevention committee. Discussions ongoing in other project countries on best modality to provide oversight to avoid duplication with other partners/stakeholders and an additional burden on NAP/govt staff.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | No of partnership agreements signed for the management and implementation of stigma and discrimination projects developed on the basis of research findings
Is this a Standard Indicator? | No
Milestone for this review (if any) | 16
What progress has been made in the period covered by this review? | Milestone not achieved. A total of 9 partnership agreements have been signed to date, while an additional 6 are currently being discussed/negotiated. 1. Regional: Agreement signed with Caribbean Broadcast Media Partnership and Caribbean HIV AIDS Alliance, while working partnerships (without formal agreement) are ongoing with Health Policy Project - Futures Group, World AIDS Campaign, Caribbean Health Research Council and University of the West Indies (the latter two related to the development and pretesting of SCOR-B) and Dance4Life 2. Belize - UNDP, National AIDS Programme 3. Guyana - planned partnership with Lifeline Councelling Services and National AIDS Programme 4. St Lucia 5. St Vincent - HPU (write full) 6. St Kitts - National AIDS Programme 7. Antigua - planned partnership with National AIDS Programme 8. Jamaica - Caribbean Vulnerable Communities Coalition 9. BVI 10. Dominica - Ministry of Health 11. Grenada - Hope Pals 12. Anguilla - National AIDS Programme 13. Montserrat
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | No. of evidence informed projects addressing stigma and discrimination with M&E framework and SMART indicators
Is this a Standard Indicator? | No
Milestone for this review (if any) | 10
What progress has been made in the period covered by this review? | Milestone achieved • In all countries activities are being supported for which the design was based on the initial needs assessment conducted in the country • In 5 countries a total of 14 projects are in various stages of implementation following the full project cycle for various target groups (see response output 2/indicator 3 for further details). • An end-line survey will be conducted in these 5 countries to objectively measure achievements. • In the other countries the ongoing review, pre/post test of (master) training and subsequent use of skills will be assessed using the routine monitoring and evaluation system established by the project (forms designed and partners trained in their use)
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 3 | 3 | 0.5
Impact Weighted Score | 15 | 0.15
Justification for the Score | Progress on this output has been varied and the slow progress in the identification of country led co-ordination/oversight mechanisms is a matter of concern. However, many of the agreements signed or under discussion involve national partners. The involvement of long established regional and country partners is an excellent initiative as this would enhance visibility and possible replicability of succesful approaches beyond the project countries and project reach.
Output 3 Recommendation 1 | RSDU to highlight for each country involvement of national government partners and NAPs and non government partners (estimated degree of national ownership) in country level work on stigma and discrimination and the projects supported by RSDU. In the same table reference could be made to the extend the respective country national plan/strategy includes activities to reduce stigma and discrimination (with/without funding).
Output 3 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Best practices disseminated
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.3
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | Number of S&D work related 'best practice' dissemination workshops/seminars facilitated by RSDU in country and in the region
Is this a Standard Indicator? | No
Milestone for this review (if any) | 3
What progress has been made in the period covered by this review? | Milestone achieved • Six best practice dissemination workshops completed using lessons learnt from the inception phase (Dominica, Grenada, Belize, Guyana, St. Lucia, Jamaica). • At the regional Caribbean HIV Conference 1. RSDU organised a 2 hour skills building session: Development of a Community Driven Rights-based stigma response model: human rights messaging campaigns in St Lucia, Jamaica and Dominica 2. RSDU organised a partners meeting over dinner to share/discuss progress/plans
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Number of websites used to disseminate best practices/lessons learnt with link to PANCAP/RSDU website
Is this a Standard Indicator? | No
Milestone for this review (if any) | 2 regional and 2 country-based websites within partner organisations
What progress has been made in the period covered by this review? | Milestone not achieved • Only one regional website is up and running (http://www.rsdu.org/RSDU_documents.html). • No information available whether country-based websites have been used to share/disseminate success stories/best practices. Major delays have been experienced in establishing the RSDU website within PANCAP website mainly due to frequent staff changes and staff shortages within PANCAP. The website would be hosted within PANCAP’s website, while RSDU would be responsible for content and building and maintenance of the actual website. The following website name has been proposed by PANCAP PCU www.pancap.org\stigmaunit
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | Number of presentations at global and regional conferences sharing lessons learnt from Stigma and Discrimination project
Is this a Standard Indicator? | No
Milestone for this review (if any) | 2
What progress has been made in the period covered by this review? | Milestone achieved At the regional Caribbean HIV Conference: • RSDU presented ‘Assessment findings related to stigma and discrimination in the Caribbean’ – using the participatory Community Response (SCOR) assessment tool (session Stigma, evidence and health systems strengthening in the Caribbean) • RSDU in partnership with Health Policy Project and Future Groups manned a stigma booth ‘responding to stigma and discrimination in the Caribbean’ • RSDU presented lessons learnt in 1 poster (and related short 5 min explanatory presentation): RSDU pilot series; using a rapid participatory ethnographic intervention to inform the design of community-based anti-stigma responses and to foster partnerships and leadership capacity in marginalised groups.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 | Number of best practice case studies from Stigma and Discrimination Project published in country, regional journals and international magazines and papers etc.
Is this a Standard Indicator? | No
Milestone for this review (if any) | 2 regional publications
What progress has been made in the period covered by this review? | Milestone not achieved RSDU published its first newsletter just in time for the regional Caribbean HIV conference. The newsletter provides a wealth of information on the project and was very well received by SUAG members. The newsletter will be widely distributed to project partners/stakeholders/beneficiaries, while PANCAP PCU Director agreed to share the newsletter widely with its contacts/partners. Hard copies were available at the stigma booth for HIV conference participants. An article on the SCOR-B tool is currently being finalised and will be submitted for publication in January 2012.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 4 | 2 | 0.75
Impact Weighted Score | 11.25 | 0.1125
Justification for the Score | • Progress on this indictor has generally been good although only 2 of the 4 milestones were fully achieved. • Sharing of lessons learnt of successful approaches and good practices is of utmost importance at this stage of the project to ensure outputs of the RSDU will reach beyond the project time frame and project reach. The newsletter resulted in a very attractive means to share lessons learnt. • RSDU has fully utilised the opportunity the regional Caribbean HIV conference provided to share lessons learnt. • The packaging of the evidence-based intervention packages currently being developed will be crucial to ensure that these will be easy to use and easy to access and will indeed constitute best practices and complement the PANCAP stigma tool kit.
Output 4 Recommendation 1 | RSDU and PANCAP to move forward as possible with the set-up of a RSDU web portal link within PANCAP website (outstanding action annual review 2010)
Output 4 Action Point 1 | RSDU to update its website and upload relevant documents to ensure these are widely available for use
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2 | RSDU to explore with country and regional partners avenues for sharing lesson learnt through inclusion of success story in existing newsletters and existing govt/NGO websites and presentation at national fora.
Output 4 Recommendation 3 | RSDU to develop and propose suitable/appropriate packaging of the 5 evidence-based intervention packages currently being developed at the Feb’12 SUAG meeting. The intervention packages (hard copy/electronic vevrsion) should be easy to access and easy to use with adequate reference/links to existing toolkits such as the tourism tool kit and the PANCAP stigma toolkit.
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-12-10
Impact Weighting (must = 100) | 100%
Total Impact Score | 67.5 | 0.675
Output Risk | High | 1.4
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners
DFID staff | X
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | The project was originally conceptualised as a joint-funding arrangement with KfW which had agreed to make a financial contribution of at least 300,000 euros to the delivery of the Regional Stigma and Development Unit. Notwithstanding considerable efforts, an appropriate funding arrangement was not achieved. This led to a funding shortfall requiring amendments of the RSDU workplan. However earlier this year KfW has agreed with PANCAP to fund another initiative aimed at enhanced media involvement in the response. PANCAP PCU technical officer has been involved in the development of this programme to ensure complementarity with the RSDU project, building on its lessons learnt and success stories.
Working with Partners Recommendation 1
Working with Partners Action Point 1 | Regional Social Development Adviser to follow up with PANCAP regarding KfW/PANCAP arrangement.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | The Stigma Community Response (SCOR) assessment tool uses participatory methodologies and focuses on engaging members of the target communities as researchers. This peer process facilitates ownership and empowerment of the affected communities and encourages their participation in the design of initiatives to address identified issues. The tool measures levels of stigma. including stigmatizing attitudes amongst health care workers, faith based organisations and other key groups. The UNAIDS PLHIV stigma index only measures stigma/discrimination as perceived by PLHIV (including self stigma), but does not measure S&D amongst other vulnerable groups. Also, the UNAIDS stigma index has not been validated in the Caribbean region. Stigma and discrimination is a major driver of the HIV epidemic in the Caribbean region. The SCOR assessment tool therefore has the potential to become an uniform tool for measuring levels of stigma and discrimination amongst various target groups in the Caribbean region as well as achievements of targeted needs-based programmes developed based on the SCOR assessment with involvement of the target groups.
Best Practice / Innovation Recommendation 1 | RSDU to develop a concise booklet explaining the SCOR assessment tool in simple terms with short clarification/justification of SMART indicators selected as well short ovevrview of resources required to utilise/implement the tool (human resources, time required for interviews, collation and analysis of the data).
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management
Project Management Recommendation 1
Project Management Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | • Role/responsibilities and sustainability of the RSDU itself will depend on the outcome of the external review, opportunities to integrate/link the unit within existing structures and availability of funding. CARICOM Secretariat has indicated that no funding is available to continue funding the PANCAP PCU post responsible for stigma/discrimination. USAID and KfW have already indicated that they will not be able to provide funding for the RSDU. Nonetheless, • The project developed and validated a participatory assessment tool to measure stigma levels and subsequent changes as a result of targeted interventions. The acceptance and use of an uniform monitoring tool would facilitate regional level monitoring and collation of data by PANCAP and others. • The evidence-based good practices intervention packages being developed as well as BCC materials/training manuals will be available for continue used within project countries and beyond. • Capacity building has been an integral part of the project and skills gained are expected to benefit vulnerable groups beyond the life of the project.
Sustainability Recommendation 1
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | Stigma Unit Advisory Group (SUAG) to confirm goal level targets during Feb'12 SUAG meeting.
R2 | 0
R3 | 0
A1: Purpose
R1 | • PANCAP PCU to obtain endorsement/support from Regional Co-ordination Mechanism (RCM) for dissemination and utilisation of the SCOR-B and the 5 intervention packages across programmes at the next RCM meeting in March 2012
R2 | • PANCAP PCU to address imminent HR constraint and identify key person to take forward work on stigma and discrimination
R3 | • DFIDC to explore option for a cost and time extension of the MOU with PANCAP to extend the strategy and resourcing officer’s post till August’12, the current end-date of the RSDU project. This would enable active involvement of PANCAP PCU in the crucial stages of the project as well as assist PANCAP with exploring options for continuation of key RSDU functions/roles based on the planned external review.
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | External review of current and especially future role/responsibilities, location and funding requirements of the RSDU to be conducted Feb/March 2012 latest to ensure findings can be shared with the Regional Coordination Mechanism at their next meeting (March’12)
R1.2 | RSDU to share RSDU organogram and job descriptions with the SUAG members (outstanding action from SUAG meeting and from 2010 review)
R1.3 | 0
R2.1 | RSDU to prepare overview of content of full intervention package per target group highlighting how each of the activities currently planned/implemented in the 12 countries will contribute to the evidence of good practice.
R2.2 | RSDU to review and if required re-profile budget to ensure sufficient funds is allocated for external TA to assist with finalising baseline data analysis and report writing as well as assist/conduct the end-line assessment.
R2.3 | 0
R3.1 | RSDU to highlight for each country involvement of national government partners and NAPs and non government partners (estimated degree of national ownership) in country level work on stigma and discrimination and the projects supported by RSDU. In the same table reference could be made to the extend the respective country national plan/strategy includes activities to reduce stigma and discrimination (with/without funding).
R3.2 | 0
R3.3 | 0
R4.1 | RSDU and PANCAP to move forward as possible with the set-up of a RSDU web portal link within PANCAP website (outstanding action annual review 2010)
R4.2 | RSDU to explore with country and regional partners avenues for sharing lesson learnt through inclusion of success story in existing newsletters and existing govt/NGO websites and presentation at national fora.
R4.3 | RSDU to develop and propose suitable/appropriate packaging of the 5 evidence-based intervention packages currently being developed at the Feb’12 SUAG meeting. The intervention packages (hard copy/electronic vevrsion) should be easy to access and easy to use with adequate reference/links to existing toolkits such as the tourism tool kit and the PANCAP stigma toolkit.
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | 0
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | RSDU to develop a concise booklet explaining the SCOR assessment tool in simple terms with short clarification/justification of SMART indicators selected as well short ovevrview of resources required to utilise/implement the tool (human resources, time required for interviews, collation and analysis of the data).
R2 | 0
R3 | 0
Project Management
R1 | 0
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | • RSDU to finalise reports of baseline assessments and share a summary of core baseline data for each of the 7 countries in which SCOR-B has been completed with SUAG members by late January 2012 latest. • RSDU to include a summary of relevant (baseline) data/information collated during the initial needs assessment for the 5 project countries where no detailed baseline survey is done.
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | • PANCAP PCU Director to include RSDU project outputs (SCOR-B and 5 intervention packages) on agenda of next RCM meeting (March’12) • RSDU to finalise SCOR-B framework and summary page of baseline data for each of the 12 countries for sharing with TWG and subsequently SUAG members for review/endorsement during planned Feb’12 steering group meeting. • RSDU to summarise intervention packages on a flow chart with reference to relevant projects/materials developed and assessments/reviews conducted to collate the evidence required to show the packages are good practice and evidence based (1 chart/target group). Make reference to use of PANCAP HIV Anti Stigma Toolkit as appropriate. This will be shared with SUAG members for review/discussion at the planned Feb’12 SUAG meeting. • RSDU to draft presentation for PANCAP PCU Director for use at the March’12 RCM meeting. This should include a summary of external review findings on options for RSDU future.
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | As agreed at 5 Dec’11 SUAG meeting: • RSDU to update and share ToRs for external consultancy with SUAG members (mid Dec'11) • SUAG members to provide feedback within 1 week • RSDU to place advert as soon as ToRs finalised: draft advert to be reviewed by SUAG • RSDU and PANCAP PCU to review RSDU budget as well as explore other funding sources to fund the external review • Selection panel to convene mid/late January 2012. OECS HIV/AIDS project unit (Dr James Catherine) has been appointed (and accepted) to chair the selection panel.
AP1.2 | 0
AP1.3 | 0
AP2.1 | • RSDU to re-assess the ambitious workplan and consider a reduction in those activities that are considered not essential to inform the development of evidence-based intervention packages • RSDU to carefully plan and communicate in close consultation with PANCAP PCU any planned reduction in activities
AP2.2 | 0
AP2.3 | 0
AP3.1 | 0
AP3.2 | 0
AP3.3 | 0
AP4.1 | RSDU to update its website and upload relevant documents to ensure these are widely available for use
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | #REF!
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3