## A1 Goal, Purpose, Risk
Annual Review (reviewed August 2010)
ARIES Project Code | 200787
ARIES Project Description | DFID Uganda HIV/AIDS Prevention Programme (2010-2014)
A1: Goal, Purpose, Risk
Goal
Goal statement | To reduce the number of new HIV infections occuring annually in Uganda
Indicator 1
Milestone for this review (if any) | No milestone set
What progress has been made in the period covered by this review? | Preliminary data suggests that new infections are likely to have risen to 150,000 during 2011 (refer New Vision 1st October 2011)
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Evidence suggests that the rate of new HIV infections is still on the rise in Uganda.
Goal Recommendation 1 | It is too early to make recommendations regarding the project goal.
Goal Action Point 1 | None
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Improved effectiveness of the prevention response
Indicator 1 | Proportion of adults aged 15 to 49 reporting more than one on-going sexual partnership
Milestone for this review (if any) | Year one milestone was not yet set because implementing partners' workplans were under development during 2011.
What progress has been made in the period covered by this review? | All contracts for the four programme partners have been signed by UK Department for International Development (DFID), and the required funding disbursed. The workplans have been developed and inception activities for the programme initiated. It is too early to report progress on the indicator. Next year's Demographic Health Survey will provide new data.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Number of new child infections due to Mother-To-Child-Transmission
Milestone for this review (if any) | Year one milestone was not developed mainly because implementing partners' workplans were still under development.
What progress has been made in the period covered by this review? | DFID provided funding to UNICEF mainly for capacity building for mother to child transmission (MTCT) service delivery.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | % of adults aged 15 to 49 reporting the use of a condom the last time they had sex with a casual partner
Milestone for this review (if any) | Year one milestone has not been developed
What progress has been made in the period covered by this review? | DFID has an agreement with the Civil Society Fund (CSF) to implement interventions that mitigate social, cultural and behavioral drivers of HIV infection. Civil Society Organisations (CSOs) from six focus districts have submitted proposals to the CSF. It is too early to report progress on the indicator. Next year's Demographic Health Survey will provide new data.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | The purpose level assumptions are still valid. All programme partners have been brought on board and oriented on the programme, though there is yet to be any significant scaling up of activity, even in the project's focus districts. The impact evaluation is not yet suffciently advanced to provide lessons to influence national policy.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | As yet there is no evidence that the project is impacting on the goal, either positively or negatively. However, if implemented according to plan, interventions are expected to contribute to the realisation of the goal, which is based on national targets.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | It is too early to assess whether delivery of outputs will lead to purpose achievement. All programme contracts have been signed, designed to deliver results on each of the four outputs. The lead partners on each output have started inception work. UN/UN Joint Programme of Support on AIDS (JUPSA) completed programme planning for Outputs 1 & 2; the CSF has received proposals for pre-selected applications for Output 3; the Knowledge Management Communications Centre (KMCC) contract has been awarded and the preparation phase for the World Bank-led baselines and Impact study have been completed.
Purpose Recommendation 1 | To strengthen coordination at purposel level, its recommended that DFID holds discussions with its core partners on each of the ouputs to set up a Coordination Forum that brings together all programme partners for the four outputs. Uganda AIDS Commission (UAC) and UNAIDS should spearhead the initiative.
Purpose Action Point 1 | Set up Core Technical Group for Programme composed of DFID, UNAIDS, CSF, Delta, World Bank (WB)
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2 | UNAIDS in collaboration with UAC should strengthen coordination of implementation at district level by strengthening the District AIDS Coordination Committees (DACCs). The support is required to convene periodic meetings, communicate with partners in their districts and the centre as well as support supervision of these implementing partners
Purpose Recommendation 3 | DFID should reflect all milestones for year one, and any other missing in the programme logframe. Data from inception phase of the 6 focus districts baseline assessments are expected by end of March 2012.
Purpose Action Point 2 | UAC & UNAIDS support for DACCS in 6 districts
Purpose Action Point 3 | Partners should complete the Logframes and include the missing milestones with data obtained from the baseline assements
Project Purpose Score | 2 | 1.65
Purpose Justification | Although progress in the first year of the programme has been slower than expected, important measures have been taken to solicit buy in for the approach, notably from the Uganda AIDS Commission.
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability | Expiry of the CSF management agent's contract may interrupt programme implementation for output 3. This will remain a risk unless a more long term solution is sought.
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability | Slow buy-in for the programme by Ministry of Health (MoH) may affect the pace of implementation for output 2
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks? | DFID is negotiating extension of the management agent's contract up to December 2012, and has obtained a waiver from competition requirements. A new funds manager procured through open competition is expected to be in place by January 2013. Swedish International Development Cooperation (SIDA) has agreed to commission a study on behalf of CSF funding partners to assess the long term management options for the CSF basket fund. On MoH, DFID has planned a meeting with leadership of MoH to address the issues.
Risk Recommendation 1 | Urgently issue contract to ensure continued financial management in place for CSF
Risk Action Point 1 | Ensure 'bridging contract' is in place by March 2012 and long-term contract for the financial management agent (FMA) issued by 2013
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | Milestones are missing at purpose and output level.
Logframe Recommendation 1 | Ensure that Programme Partners develop annual milestones against programme outputs by March 2012
Logframe Action Point 1 | Reflect milestones where there are gaps on the logframe
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1 | None
DSO Action Point 1 | None
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1 | None
CCM Action Point 1 | None
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Completion, implementation and monitoring of a national HIV prevention strategy and action plan
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.3
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 (leave blank if standard indicator) | National HIV Prevention Strategy (NPS) & Action Plan addressing socio-cultural and structural drivers of the epidemic | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Approved NPS and Action Plan reflects understanding of socio-cultural and structural drivers & consensus on the response | 0
Progress made in the period covered by this review, including numbers. | The National Prevention Strategy has been approved by Cabinet, published and was launched by Government on International AIDS day, December 1st 2011. The NPS costed Action Plan was also completed. The UN Prevention Technical Working group has convened meetings, which have resulted in clarified plans and division of labour among the UN actors to address various components of the programme. Under the leadership of World Bank (WB) and United Nations Fund for Population (UNFPA), the combination HIV prevention concept has been clarified and documented.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Effective intervention packages identified through the NPS
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Effective intervention packages designed, costed and guidelines produced.
Progress made in the period covered by this review, including numbers | Intervention packages have been developed by the Uganda AIDS Commission. There are plans to develop guidelines for implementing combination prevention packages. UAC has advertised for 2 additional staff to join their Prevention Department, and are working towards establishing a Prevention Forum and Secretariat.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | NPS monitoring and impact evaluation including evaluation of complex combination prevention
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Tender awarded for NPS monitoring and impact evaluation and baseline underway
Progress made in the period covered by this review, including numbers | UNAIDS and World Bank provided monitoring and evaluation (M&E) technical advce for the the National Prevention Strategy. The World Bank has been contracted to carry out the baseline and impact evaluation. Terms of Reference for the baseline have been developed, and research protocols have been developed and ethical clearance obtained. UNFPA has started the procurement process for the baseline, expected to commence in January 2012.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 2 | 0.75
Impact Weighted Score | 11.25 | 0.1125
Justification for the Score | The output is firmly on track. The NPS has been launched though its roll out across the country will be the biggest challenge, despite assurances by UAC. M&E support has been provided to UAC and an M&E strategy for NPS is under development. This should ensure close monitoring of the NPS. The World Bank has made significant progress on the design of the impact evaluation.
Output 1 Recommendation 1 | More coordinated support to UAC by all programme partners.
Output 1 Action Point 1 | UN Agencies should work with UAC according to a single joint workplan
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | There have been significant challenges with coordination under the UN Joint Programme of Support on AIDS (JUPSA). These challenges are likely to increase as the programme develops. UNAIDS is tasked with bringing together 12 UN agencies and needs to strengthen its human resource capacity to fulfill this function.
Output 1 Recommendation 3
Output 1 Action Point 2 | The JUPSA should recruit a senior programme coordinator immediately.
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Improved delivery of HIV prevention services
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.6
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | Number of babies born to HIV positive mothers receiving anti-retrovirals to protect them from mother to child transmission (MTCT)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestone set for year 1
Progress made in the period covered by this review, including numbers | There is no data available to measure progress against this indicator. Funds have been disbursed to UNICEF to strengthen service delivery for prevention of mother to child transmission (PMTCT). UNICEF has had discussions on strengthening capacity for PMTCT with the six focal districts. Funds for start up activities have been disbursed to two districts.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of men safely circumcised and counselled
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestone set for year 1
Progress made in the period covered by this review, including numbers | There is no data available to measure progress against this indicator. Funding has been provided to World Health Organisation (WHO) to support safe male circumcision (SMC) in the focal districts. WHO took the lead selecting programme focal districts. Discussions have been initiated with Ministry of HealthMoH to ensure SMC scale up in the 6 focal districts.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Number of women and men with access to integrated SRH and HIV prevention services
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestone set for year 1
Progress made in the period covered by this review, including numbers | Funds were provided to UNFPA and the CSF to increase communities' knowledge and use of sexual reproductive health and HIV related services. UNFPA implemented some advocacy activities with traditional leaders in the focus districts.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 3 | 0.5
Impact Weighted Score | 15 | 0.15
Justification for the Score | The was only limited roll out of activities in the first year, hence this has been reflected in the score. However, year 2 should see an intensification of activities, thus increasing the chances of this output ultimately being achieved. Investment in these areas has proven to be successful in the past. The programme's success will also depend on other partners' support support for bio-medical service delivery, such as PEPFAR and MoH.
Output 2 Recommendation 1 | Success will depend on coordination between service delivery and demand side work under the CSF.
Output 2 Action Point 1 | Negotiate a Memorandum of Understanding (MoUs) with organisations providing biomedical services in the component in the 6 districts focal districts to ensure a common understanding on roles between DFID and partners.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2 | District AIDS Coordination Committees(DACCs) need support to enable them convene periodic meetings, communicate with partners in their districts and the centre as well as support supervision of these implementing partners
Output 2 Recommendation 3 | Baselines and milestones for indicators 1, 2 and 3 should be developed and reflected on the DFID log frame with data from the baseline assessments in the districts by end March 2012.
Output 2 Action Point 2 | JUPSA partners, in collaboration with UAC, should support provide direct support to DACCs in the six focus districts to better understand and promote combination HIV prevention approaches .
Output 2 Action Point 3 | JUPSA partners should complete the baseline survey in the focus districts as a matter of priority.
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | More effective prevention response through community mobilisation and engagement in addressing structural drivers of the epidemic
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | Yes
If Yes, why was/is this? | Ending of the contract for the CSF Financial Management Agent
Original or Revised Risk | Medium | 2
0.6
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | Number of people reached through new social change communications programmes focusing on HIV prevention
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestone established for year 1
Progress made in the period covered by this review, including numbers | A social appraisal of the CSF was undertaken. Partnership meetings were held among the Development Partners (DPs) supporting the CSF to discuss DFID's programme approach. A focus on prevention was approved by the CSF steering committee. Requests for proposals were advertised and pre-bid meetings held in the six districts. The meetings oriented CSOs on the programme approach. CSOs also received training on the National Combination HIV Prevention strategy. 122 concept papers were assessed. Pre-qualified CSOs submitted full proposals in November 2011. These are now under review and contracts will be awarded in January 2012.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of women and of men reporting safer sex practices in pilot districts
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestone established for year 1
Progress made in the period covered by this review, including numbers | CSF request for applications (RFAs) were advertised, concept papers written by applicants, and pre-qualified CSOs from districts invited to write proposals. Proposals under review (as indicated above).
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Stigma, measured by proportion of people with accepting attitudes towards persons living with HIV/AIDS (PLHA) in pilot districts
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Not milestone established for year 1
Progress made in the period covered by this review, including numbers | CSF proposals have included efforts to address stigma.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 3 | 0.5
Impact Weighted Score | 15 | 0.15
Justification for the Score | The first year focused on establishing the CSF fund and inviting CSO applications, therefore there is little to show in terms of results. Full implementation is expected to begin in 2012. The CSF will collect monitoring data through its own M&E system.
Output 3 Recommendation 1 | Ensure coordination between CSOs in each district once CSF contracts are awarded. CSO activities should be formally linked to the coordination mechanism proposed for outputs 1 and 2.
Output 3 Action Point 1 | Orientate the DACCS and JUPSA partners on approved CSF activities.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2 | The CSF should develop Combination HIV Prevention indicators for each of the CSO projects supported.
Output 3 Recommendation 3 | Baselines, milestones, targets and means of verification should be developed for output 3 indicators.
Output 3 Action Point 2 | M&E and Technical Management Agent (TMA) should work with the new CSF supported CSOs under the programme to develop indicators for the programme approach especially in relation to socio-cultural and behavior change issues.
Output 3 Action Point 3 | Update the DFID logframe to reflect baselines, milestones and targets
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Improved policy and practice through effective dissemination and uptake of HIV-related research, evidence and lessons learned from experience
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | Effectively functioning KMCC
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | KMCC created and costed work plan developed
Progress made in the period covered by this review, including numbers | A contract was awarded by DFID to Delta Partnership to establish and run the KMCC.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | No of dissemination events and quality reports from HIV related bio-medical and social science research & analysis produced by KMCC
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestone established for year 1
Progress made in the period covered by this review, including numbers | No progress was anticipated on this indicator in year 1 of the project.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | HIV policy and programmes informed by quality operational and academic research including social science
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestone established for year 1
Progress made in the period covered by this review, including numbers | No progress was anticipated on this indicator in year 1 of the project.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 2 | 0.75
Impact Weighted Score | 18.75 | 0.1875
Justification for the Score | The main activity planned for this output was the award of a contract to manage the KMCC and the design of an impact evaluation research prgramme. Both have been achieved. The KMCC is now in its inception phase, which includes establishing a KMCC board. The World Bank has designed the impact evaluation and has held a number of workshops to ensure buy-in to the approach. There is good reason to believe that, once established, this ouput will be substantively achieved.
Output 4 Recommendation 1 | Develop 3 year work plans, revising output indicators and milestones.
Output 4 Action Point 1 | Approve a 3 year KMCC work plan at the end of the incepetion phase and update the DFID project logframe to reflect agreed indicators and milestones.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 21/11/2011 - 15/12/2011
Impact Weighting (must = 100) | 100%
Total Impact Score | 60 | 0.6
Output Risk | Medium | 1.5
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment | X
Joint donor review
Independent consultant review | X
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant | X
Donor partners
DFID staff
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility. | The scoring reflects the fact that the first year of the project has mainly focused on establishing partnerships and developing buy-in to the project's approach. In the absense of milestones for many of the indicators, a subjective assessment has had to be applied in most cases.
Scoring Recommendation 1 | It is important that milestones are agreed for the remaining years of the project and that implementing partners established the means of measuring results in time for the next annual review.
Scoring Action Point 1 | Agree on milestons and MoVs before releasing further funds to project partners, especially the JUPSA.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | DFID has developed strategic partnerships for each of the four outputs. Working in partnership requires a coordination mechanism to ensure overall programme cohesion
Working with Partners Recommendation 1 | Support UAC to improve its coordination function. Ideally this should be done by UNAIDS, but human resource capacity constraints may not permit this. DFID may consider providing technical assistance directly to UAC to fulfill this function.
Working with Partners Action Point 1 | Discuss with partners the best means of strengthening UAC's coordination function.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2 | Programme implementers should establish a working relationship with the KMCC for collection and dissemination of evidence and knowledge.
Working with Partners Recommendation 3
Working with Partners Action Point 2 | KMCC should liaise with JUPSA partners, including UAC and the CSF.
Working with Partners Action Point 3
2. Best Practice / Innovation | The DFID programme has been catalytic in finalising the NPS and in pioneering implementation of the combination HIV/AIDS prevention approach
Best Practice / Innovation Recommendation 1 | Having helped build consensus about the need for a combination prevention approach, it is important that the programme can now demonstrate what this means in practice by mobilising activities in the focus districts.
Best Practice / Innovation Action Point 1 | Programme Partners especilay JUPSA/UNAIDS should negotiate memorandum of Understanding (MoUs) with complimentary partners especially PEPFAR
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2 | Impress upon JUPSA partners and CSF grantees the importance of intensifying and coordinating biomedical, structural and behavioural activities in the focal districts with immediate effect
Best Practice / Innovation Action Point 3
3. Project Management | The programme lacks an apex body to bring all actors togather, share experiences and results. DFID should set up a coordination mechanism at purpose level. The forum should come under the auspices of the National Prevention Sub Committee and National Partnership Committee (NPC).
Project Management Recommendation 1 | DFID should initiate discussions with partners, and propose to them the establishment of a coordination mechanism that brings together key actors on all four outputs. The partners should decide on the role and responsibilities of the forum, its final nature and form.
Project Management Action Point 1 | Establish Core Technical Team composed of UNAIDS/JUPSA, KMCC, CSF and WB, with DFID in attendance
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2 | Secure 'bridging contract' with Financial Management Agent for CSF to ensure continuity after March 2012; and together with other CSF funding partners ensure long term contract for new FMA in place by January 2013
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams. | Programme is faced with coordination challenges especially at UAC. Slow buy-in from MoH is also affecting building of effective relationships for implementation at district level
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
3327679 | Final HIV Prevention Annual Review Narrative Report 16 Dec 2011
3294162 | WB Aide Memoire 26 July - 6 August 2011
3322486 | Background documents for meeting on Impact Evaluation of HIV Combination Prevention interventions
3293339 | HIV Prevention Programme Risk Management Matrix
3294201 | National Prevention Strategy Pilot Concept Note
3294070 | UN Joint Programme of Support on AIDS - Narrative and Matrix, Annual Workplan and Mid year Review September 2011
3294115 | Civil Society Fund agent study ToRs Nov 2011
3294659 | AIDS Development Partners' Retreat Report 5 - 6 Oct 2011
3294665 | AIDS Development Partners' Work Plan 2011 - 2012
3028879 | Notes of Initial Programme meeting with UAC 22 Feb 2011
2907423 | HIV Prevention Programme Logframe
2889384 | Project Memorandum
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | Significant efforts have been made to introduce DFID's programme as a contribution to the roll out of the National Prevention Strategy, rather than a stand alone project. This message will need reinforcing continously. The likelihood of the project's benefits being sustainable will depend in large part on the success of the impact evalaution demonstrating that the combination prevention approach works and in disseminating these findings through the KMCC. Without an intensification of activities under outputs 2 and 3 however, the chances of a nil result from the impact evaluation will increase.
Sustainability Recommendation 1 | Continue engagement with the Prevention thematic lead and UAC to ensure that the districts identify any gaps and alternative sources of funding through the planning frameworks.
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | It is too early to make recommendations regarding the project goal.
R2 | 0
R3 | 0
A1: Purpose
R1 | To strengthen coordination at purposel level, its recommended that DFID holds discussions with its core partners on each of the ouputs to set up a Coordination Forum that brings together all programme partners for the four outputs. Uganda AIDS Commission (UAC) and UNAIDS should spearhead the initiative. | DFID to propose idea to UAC & UNAIDS. Partners to set up the Core Technical Team
R2 | UNAIDS in collaboration with UAC should strengthen coordination of implementation at district level by strengthening the District AIDS Coordination Committees (DACCs). The support is required to convene periodic meetings, communicate with partners in their districts and the centre as well as support supervision of these implementing partners | UNAIDS and UAC with JUPSA UN Agencies
R3 | DFID should reflect all milestones for year one, and any other missing in the programme logframe. Data from inception phase of the 6 focus districts baseline assessments are expected by end of March 2012. | DFID
A1: Risk
R1 | Urgently issue contract to ensure continued financial management in place for CSF | DFID
R2 | 0
R3 | 0
A1: Log frame
R1 | Ensure that Programme Partners develop annual milestones against programme outputs by March 2012 | UNAIDS, CSF, KMCC
R2 | DFID should update milestones on the DFID Log Frame | DFID
R3 | 0
A1: DSOs
R1 | None
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | None
R2 | 0
R3 | 0
A2: Outputs
R1.1 | More coordinated support to UAC by all programme partners. | UNAIDS
R1.2 | There have been significant challenges with coordination under the UN Joint Programme of Support on AIDS (JUPSA). These challenges are likely to increase as the programme develops. UNAIDS is tasked with bringing together 12 UN agencies and needs to strengthen its human resource capacity to fulfill this function. | UNAIDS, Irish Aid and other DPs, UNRCO and UNAIDS
R1.3
R2.1 | Success will depend on coordination between service delivery and demand side work under the CSF. | UAC, UNAIDS, DFID
R2.2 | District AIDS Coordination Committees(DACCs) need support to enable them convene periodic meetings, communicate with partners in their districts and the centre as well as support supervision of these implementing partners | UNAIDS and UAC
R2.3 | Baselines and milestones for indicators 1, 2 and 3 should be developed and reflected on the DFID log frame with data from the baseline assessments in the districts by end March 2012. | UNAIDS, CSF
R3.1 | Ensure coordination between CSOs in each district once CSF contracts are awarded. CSO activities should be formally linked to the coordination mechanism proposed for outputs 1 and 2. | UNADS with UAC
R3.2 | The CSF should develop Combination HIV Prevention indicators for each of the CSO projects supported. | CSF
R3.3 | Baselines, milestones, targets and means of verification should be developed for output 3 indicators. | CSF
R4.1 | Develop 3 year work plans, revising output indicators and milestones. | KMCC
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | It is important that milestones are agreed for the remaining years of the project and that implementing partners established the means of measuring results in time for the next annual review.
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Support UAC to improve its coordination function. Ideally this should be done by UNAIDS, but human resource capacity constraints may not permit this. DFID may consider providing technical assistance directly to UAC to fulfill this function.
R2 | Programme implementers should establish a working relationship with the KMCC for collection and dissemination of evidence and knowledge.
R3 | 0
Best Practice / Innovation
R1 | Having helped build consensus about the need for a combination prevention approach, it is important that the programme can now demonstrate what this means in practice by mobilising activities in the focus districts. | DFID with PEPFAR
R2 | 0 | UNAIDS/JUPSA, CSF
R3 | 0
Project Management
R1 | DFID should initiate discussions with partners, and propose to them the establishment of a coordination mechanism that brings together key actors on all four outputs. The partners should decide on the role and responsibilities of the forum, its final nature and form. | DFID with UAC
R2 | Secure 'bridging contract' with Financial Management Agent for CSF to ensure continuity after March 2012; and together with other CSF funding partners ensure long term contract for new FMA in place by January 2013 | DFID
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | Continue engagement with the Prevention thematic lead and UAC to ensure that the districts identify any gaps and alternative sources of funding through the planning frameworks.
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | None
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | Set up Core Technical Group for Programme composed of DFID, UNAIDS, CSF, Delta, World Bank (WB) | DFID to discuss with partners. UNAIDS and UAC to tale the lead.
AP1.2 | UAC & UNAIDS support for DACCS in 6 districts | UNAIDS and UAC
AP1.3 | Partners should complete the Logframes and include the missing milestones with data obtained from the baseline assements | ALL Partners & DFID
A1: Risk
AP1.1 | Ensure 'bridging contract' is in place by March 2012 and long-term contract for the financial management agent (FMA) issued by 2013 | DFID
AP1.2 | 0
AP1.3 | 0
A1: Log frame
AP1.1 | Reflect milestones where there are gaps on the logframe | ALL Partners & DFID
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | None
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | None
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | UN Agencies should work with UAC according to a single joint workplan | UNAIDS, UAC
AP1.2 | The JUPSA should recruit a senior programme coordinator immediately. | DFID, Irish Aid, UNAIDS & UNRCO
AP1.3 | 0
AP2.1 | Negotiate a Memorandum of Understanding (MoUs) with organisations providing biomedical services in the component in the 6 districts focal districts to ensure a common understanding on roles between DFID and partners. | UNAIDS, UAC, DFID
AP2.2 | JUPSA partners, in collaboration with UAC, should support provide direct support to DACCs in the six focus districts to better understand and promote combination HIV prevention approaches . | UNAIDS, UAC
AP2.3 | JUPSA partners should complete the baseline survey in the focus districts as a matter of priority. | UNAIDS and Agencies, DFID for DFID Log frame
AP3.1 | Orientate the DACCS and JUPSA partners on approved CSF activities.
AP3.2 | M&E and Technical Management Agent (TMA) should work with the new CSF supported CSOs under the programme to develop indicators for the programme approach especially in relation to socio-cultural and behavior change issues. | UNAIDS, UAC
AP3.3 | Update the DFID logframe to reflect baselines, milestones and targets | CSF, DFID
AP4.1 | Approve a 3 year KMCC work plan at the end of the incepetion phase and update the DFID project logframe to reflect agreed indicators and milestones. | KMCC,/Delta, DFID
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | Agree on milestons and MoVs before releasing further funds to project partners, especially the JUPSA.
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Discuss with partners the best means of strengthening UAC's coordination function.
AP1.2 | KMCC should liaise with JUPSA partners, including UAC and the CSF.
AP1.3 | 0
Best Practice / Innovation
AP1.1 | Programme Partners especilay JUPSA/UNAIDS should negotiate memorandum of Understanding (MoUs) with complimentary partners especially PEPFAR | DFID at National level with USG. UNAIDS/JUPSA and UAC at district level
AP1.2 | Impress upon JUPSA partners and CSF grantees the importance of intensifying and coordinating biomedical, structural and behavioural activities in the focal districts with immediate effect
AP1.3 | 0
Project Management
AP1.1 | Establish Core Technical Team composed of UNAIDS/JUPSA, KMCC, CSF and WB, with DFID in attendance | DFID in discussion with Partners. UNAIDS and UAC to take the lead
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3