Annual Review – post April 2018

Title: Scaling Up Family Planning (SUFP) in Zambia
Programme Value £ (full life): : £24,853,793		Review Date: May 2018
Programme Code:	Start Date: 1 March 2012	End Date: 31 March 2019

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017	2018
Programme Score		A	A+	A+	A+	A	A
Risk Rating	High	High	Medium	Low	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202342/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202342/documents

A. Summary and Overview

The Scaling Up Family Planning programme is in its sixth year of programme implementation and has made good progress in the delivery of its outputs with an overall performance score of A. Performance in expanding availability of family planning methods met expectations with increasing availability of at least five family planning methods in hospitals and clinics. Four health centres of excellence for family planning services were assessed as fully functional in Western province. As a result, the programme exceeded expectation with 122,810 Couple Years of Protection achieved in Western province.

Performance in increasing community support for family planning exceeded expectation with 163 adolescent peer educators trained and active, and a 97% retention rate was achieved for community based distributors of family planning methods. Public sector capacity to provide comprehensive family planning services for adolescents was strengthened through an assessment of adolescent friendly services that informing guidance notes to health facilities to improve services to this vulnerable and underserved group; and shaped the training package for adolescent peer educators.

Insufficient progress was made by the Government of Zambia (GRZ) in increasing its funding of family planning (FP) commodities, with 24% of FP commodities funded by the programme against a target of 17%. Within the current climate of limited donor support to family planning, the Scaling Up Family Planning life of programme target of contributing 15% of Zambia’s FP commodities requirements will not be met without a significant gap in FP commodities’ availability. There is an urgent need for a substantial and sustained increase in GRZ resourcing of family planning activities and commodities to ensure that Zambia keeps to its Family Planning 2020 commitments and stays on track to attain the anticipated demographic dividend.

With the recommendation that programme closure be brought forward to December 2018 to facilitate a responsible transition to the DFID’s Zambia Health Systems Strengthening programme, programme priorities in the final months of the programme will include dissemination of lessons learned to stake holders and a push for greater GRZ leadership and commitment to family planning at all levels.

Description of programme

The Scaling Up Family Planning programme (SUFP) aims to increase access to family planning services in Zambia through addressing the high unmet need for family planning services and building government capacity to deliver comprehensive and quality family planning services. SUFP is implemented by Abt Associates and UNFPA.

The implementation period is from 2012 to 2019. The first phase was implemented from 2012 to early 2016 and focused on scaling up family planning services in 26 rural districts. In response to the additional UK manifesto and FP 2020 commitments, approval was granted to extend the programme for an additional 36 months. The total budget for both phases is £24.9 million (£14.9m phase one and £10m phase two).

Since its inception in March 2012, the programme has expanded access to modern family planning methods by mobilising communities, building service delivery capacity in public health facilities, and strengthening commodity distribution in targeted districts. This has resulted in an additional 295,100 women and girls using a family planning method and achieving 578,240 couple years of protection by 2016.
The second phase of the programme (SUFPII) was approved for the period July 2016 up to March 2019 although the Scaling Up Family Planning component implemented by Abt Associates will end in October 2018. Under phase two of programming, there is a shift to embedding the SUFP model within the Government of Zambia (GRZ) systems, focusing on a province-wide approach initially in Western and expanding to Central Province. The expected outcomes are full ownership and implementation of the SUFP model by the Ministry of Health and significant contribution towards achievement of national FP2020 targets.

The expectation is that key elements of SUFP will be incorporated into DFID’s Zambia Health Systems Strengthening Programme (ZHSSP). The ZHSSP programme implementation in the two provinces was delayed and commenced in October 2017.The programme has as among its objectives, the strengthening of reproductive, maternal, new-born, child and adolescent health and nutrition services across the continuum of care in Western and Central provinces. A key deliverable of the ZHSSP is increased number of additional users of modern family planning methods in the two provinces. To achieve best use of DFID resources and avoid duplication of effort, the programme end date for SUFPII will be brought forward from March 2019 to December 2018.

The Scaling Up Family Planning programme phase two (SUFPII) has two main components:
1. Scaling Up Family Planning, implemented by Abt Associates, £4,854,390[1]
  [1] Funding amounts relate to the programme extension 2016-2019 only
  1. Works with the Ministry of Health and key stakeholders to institutionalise the SUFP model in Zambia and support its implementation in Western Province. The expected outcomes are the full ownership and implementation of the SUFP model by the Ministry of Health, and significant contribution towards achievement of the FP2020 targets.
2. Strengthening Reproductive Health Commodity Security, implemented by UNFPA, £5,000,400
  1. Supports the government of Zambia to accelerate achievement of FP 2020 targets through generating and using evidence-based approaches.  The project supports the government to reduce the national gap in reproductive health commodities and improve the availability of contraceptives.  In addition to procuring commodities, the project supports coordination, lesson learning and advocacy at district, provincial and national level to ensure a rights based approach to family planning is achieved for all women and young people.

The SUFP model is defined as a package of interventions incorporating:
- Expanded availability of family planning method choice
- Increased access to family planning services
- Increased community support for family planning
- Capacity of public health facilities to provide quality comprehensive family planning services

In addition to procurement of contraceptive commodities and national level policy work, this phase of the programme focuses on improving service delivery in Western Province where family planning indicators are worse than the rest of the country, and during this annual review (AR) period, has expanded into Central Province.

Indicator	Zambia	Central Province	Western Province
Total Projected 2015 Population	15.5m	1.5m	1.0m
Total fertility rate (TFR)	5.3	5.9	5.6
Adolescent Pregnancy Rate (%)	28.5	29.9	40.4
Unmet Need for Family Planning (%)	21.1	25.7	24.2
Modern Contraceptive Prevalence (%)	44.8	41.3	31.7

Source: Zambia Demographic and Health Survey 2014

Summary supporting narrative for the overall score in this review

Overall output score and description: A : Programme is meeting expectations

The programme has met expectations on three outputs (expanding availability, increasing public sector capacity and increasing access to underserved populations) and moderately exceeded expectation on one output (increasing community support for FP services).

Generally, Ministry of Health capacity has been built at provincial, district levels and health facility levels especially in Western province. Skills and knowledge have been imparted because the SUFP programme has been implemented side by side with MoH staff from programme from the start of SUFPII – for example, in applying the rapid cycle learning and quality assessment tools.

The provincial and district health offices feel ready for the transition to take over the SUFP model. Most officials met were able to articulate the benefits of the SUFP model and the tools and approaches used such as the Centres of excellence (CoEs), mentorship. and the camping approach to social mobilization. However most said that the three years period for implementation of SUFPII was too short. Fears where expressed by MoH staff that FP may still not yet be a top priority of GRZt and that the integrated approach to delivery of reproductive, child, adolescent health and nutrition services under ZHSSP may mask the importance of FP. Despite adequate programme progress during the AR period, challenges still exist such as inadequate numbers of trained health workers, insufficient numbers of community based distributors (CBDs) and adolescent peer educators trained, poor/inadequate infrastructure in some health facilities and limited logistics for supervision activities. In addition, the high attrition and frequent changes in the MoH is a challenge to transition as it affects commitment to FP especially at senior levels. Even though the ZHSSP is designed to make significant inroads to addressing these issues, it was acknowledged that the funds available under the ZHSSP cannot fully address the challenges and a significant increase in GRZ allocation to health would be required.

Significant differences were observed during the review between the two provinces (Western and Central) in terms of SUFPII model progress and achievements. As per programme plan, SUFPII activities only started in the Central province in late 2017 to enable adequate focus on the comparatively underserved Western province. With only a few months to go before end of SUFP however, SUFPII needs to intensify efforts in building the capacity of the provincial and districts offices and health facilities in Central province for meaningful and sustainable transition to take place after the SUFP programme ends.

Despite meeting programme expectations, this AR also highlights some concerns regarding SUFPII assumptions that GRZ will take full responsibility for the FP programme and fulfil its FP2020 commitments to increase FP resources. This is unlikely to materialise as quickly as envisaged because of limited fiscal space and competing priorities. Consequently, there is need for all key players including Government to collectively revisit the purpose and objective of SUFPII which is to institutionalize the SUFP model in the government systems. Transition affects not only GRZ but also other partners as poor implementation may disrupt or undermine the gains made and also may affect future relations depending on how the exit is handled. The MoH commitment, in terms of strengthening systems for continuity after closure of the programme is critical for sustainability of FP services. It is also important to balance demand creation with supply of services at public facilities especially for adolescents. SUFPII should diligently record lessons learned to inform future programmes.

Recommendations for the year ahead

This section outlines some of the key recommendations for the year ahead. Detailed recommendations are found under each output:

- With the imminent end of SUFP and limited donors’ commitment on FP commodities, DFID and UNFPA to intensify advocacy for increased domestic financing of reproductive health commodities, particularly family planning products. The upcoming budgeting and planning process in commencing in July provides a platform to advocate for increased MoH allocation to the reproductive health commodities budget to meet Zambia’s FP2020 commitment line to spend $1.5million annually on Family planning products from the average of $1million. (DFID, UNFPA commencing July 2018)
- Abt to focus more on capacity building training efforts in all facilities where they had done previous trainings to ensure that staff left out of previous trainings are trained to increase service coverage and impact. In the event that this cannot be achieved, a full list of staff to be trained should be submitted to UNFPA under the ZHSSP for action (by September 2018)
- The issue of lack of data disaggregation and how best to provide and incorporate data on sexual and reproductive health services for adolescents aged 10-14 years should continue to be discussed at FP technical working group meetings and brought to the RMNCAH&N committee for solutions (DFID, Abt, UNFPA).
- SUFP to expedite the proposed mapping exercise of worst affected health facilities in the 2 provinces during rainy season by September 2018 and support maternal and child health coordinators and district pharmacists to pre-position sufficient FP commodities in affected facilities ahead of the rainy season (Abt, UNFPA)
- Additional focus is needed in the coming year to define a package of adolescent friendly services and begin to expanding adolescent access to FP services, for example, through increasing mobile services to bring adolescent sexual and reproductive health services closer to the communities. Provision of youth friendly communication materials should also be prioritized. (SUFP, UNFPA by October 2018)
- Abt to ensure that provincial and district health offices, through the Government's Medium Term expenditure framework (MTEF) 2019 planning process, budget to train increased numbers of trained peer educators and health workers in youth friendly Adolescent reproductive health at facility, district and provincial levels to improve reach and increase impact (Abt with support from UNFPA as ZHSSP technical lead by September 2019).
- Abt to intensify activities in the Central province to ensure that they bring the province up to speed in terms of identification of existing and potential CoEs and identify capacity needs before handing over to UNFPA by September 2018 (Abt, UNFPA).
- SUFPII to advocate during the 2019 MTEF planning process that district health offices make specific provision in health facility budgets for supervision and mentorship of CBDs (Abt, UNFPA commencing July 2018).
- SUFP to advocate to during the 2019 MTEF planning process for district health offices to budget for more youth-friendly spaces in health centres with their ZHSSP funding. (Abt Associates by September 2018).
- UNFPA finalize the SUFPI end line report and disseminate findings by September 2018 to inform future implementation of FP services in the country (UNFPA).
- Abt, UNFPA and MoH to develop a plan by August 2018 to provide additional capacity building in the FP2020 indicators at provincial and district health levels where there are still knowledge gaps (Abt, UNFPA).
- The issue of long term motivation of volunteers should be raised by DFID, Abt and UNFPA at national level policy meetings as the issue is not limited to FP CBDs but is common to all volunteers that do not receive financial or non-financial remuneration for their services. At the provincial and district levels, UNFPA and Abt should explore with provincial and district teams ways of ways of maintaining the motivation of CBDs.

For the Log frame
- DFID to include a ‘finalized Family Planning 2018-2021 costed Road Map’ as the 2018 indicator for indicator 4.1 by July 2018.
- There is need to realign the output indicators in the DFID log frame with that of SUFP log frame (Abt Associates) to ensure consistency. For example, Output 3.2 ‘Number of Community Based Distributors (CBDs) trained in Western Province, of which number who are also community leaders’ is actually Output indicator 2.4 in the DFID log frame. (Abt Associates by August 2018).

## B: DETAILED OUTPUT SCORING

Output Title	Expanded availability of choice of family planning methods
Output number per LF		1	Output Score	A
Impact weighting (%):		25	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) July 2018	Progress - June 2017 to April 2018
1.1 Number of new users of family planning in Western and Central Provinces	18,200	Met: 76,228 / Indicator is assessed as met based on concerns about data quality.
1.2 Percent of i) health centres and ii) hospitals offering at least 5 different types of modern contraceptive methods (national)	75% / 96%	Met: / 63.3% / 90%
1.3 Number of fully functional Centres of Excellence	4	Met: 4
1.4 Number of Centres of Excellence that have been assigned functions and budget allocation in the district's annual plan and budget (methodology note - given the budget cycle this can only be added as an end of project target, baseline is the 6 CoEs that SUFP is working with)	No indicator for 2018	The indicator target for end of programme is 4/6. To support target achievement, / -SUFPII produced a review of existing Centres of Excellence, highlighting best practice and supported assessment for new CoEs in Central province. / -SUFPII participated in the 2018 planning and budgeting processes of the districts and advocated for increased focus on family planning services at facility and district levels

This output assesses the increased availability of family planning measured through the number of health facilities with a full range of family planning methods, the number of districts increasing their capacity to offer these methods, and the number of new users of modern family planning methods.

Score: A: The output met expectation. Only 3 out of four indicators had milestones for the year under review. One indicator (indicator 1.1) greatly exceeded expectation and two were met. The overall score is however an ‘A’ because weaknesses in data quality and collection on indicator 1.1, the ‘number of new users of family planning’.

Output 1.1: Increasing access to family planning services through training of health workers and ensuring availability of FP commodities contributed to the attainment of 76,228 new users. SUFPII intensified building the capacity of health service providers to provide Long Acting Reversible Contraceptives (LARC) as well as training community based distributors (CBDs) to provide oral contraceptives and Depo Provera. Trained CBDs increased demand for family planning services in the communities and increased provision of LARCs in hard to reach communities. During the annual review field visit, provincial, district and health facility staff in Western province also reported that strides had been made in increasing access to family planning methods through ensuring the availability of FP commodities.

Although the actual number of new users of FP achieved is in question, a quantitative analysis carried out through a programme rapid cycle learning (RCL) activity showed an overall increase in the number of new users of family planning methods in Western province focus districts between July 2013 and September 2017 (SUFP RCL Report 2018), confirming the strong likelihood of an upward trend in the number of new users in our focus province during the AR period.

Trends in New Family Planning Acceptors In Central and Western Province -2015 to September 2017

During the AR period, SUFPII also advocated for the replacement of the indicator ‘new users of contraceptive methods’ with the indicator ‘additional users of contraceptive methods’ to align with global best practice on family planning indcators. This indicator is recommended for use in all FP2020 countries in place of “new users’ as this indicator was poorly measured across countries, including Zambia, due to misunderstandings on the definition of a new user. The indicator ‘number of additional users of contraceptive methods’ is defined as the number of additional women (or their partners) of reproductive age currently using a modern contraceptive method compared to the previous measurement period (in this case, the previous year). SUFPII have started building the capacity of provinces to model family planning data using historic national population data and services statistics to support the measurement of this new indicator. During the AR visits, interviews with provincial, district and health facilities staff revealed they were not confident about the definition of the new FP2020 Track20 indicator, suggesting additional work is required on FP data collection before the new indicator is used with some confidence.

It was also found that FP data at provincial and district levels was not disaggregated by age to monitor use by adolescents, and that even when good family planning records existed, as judged by FP registers, these were not analysed for decision making.

Ministry of Health staff also mentioned that some challenges exist. These include
- Large sections of the population that have limited access to FP and other services in the rainy season when certain communities get completely cut off from services.
- Inadequate number of trained providers because of frequent staff movements.
- Varying confidence among health workers in providing the full range of FP methods. Particularly concerning is the lack of confidence in inserting intrauterine contraceptive devices despite training.

MoH staff acknowledged that SUFPII is providing mentorship to build confidence and capacity to meet gaps. In addition, the DFID Zambia Health Systems Strengthening programme is providing support for reproductive, maternal, neonatal, child and adolescent health and nutrition (RMNCAH&N) services, providing the opportunity for continued support after SUFPII programme end.

Output 1.2: Overall, there is a positive trend in terms of the FP methods mix offered at all levels of service delivery points. The annual review targets were judged to have been met with an achievement of 84% or above of set targets.

In the 2017 Zambia Reproductive Health Commodities Survey (ZRHCS), a slightly higher percentage of primary health facilities (63.3%) reported offering at least five contraceptives as part of normal service delivery compared to 2016 (59.7%), whilst an average of 90% of secondary and tertiary level hospitals reported offering at least five methods. The 2017 availability of five methods in hospitals is higher than the 2016 report of an average 82% availability. All assessed facilities in Central and Western Provinces were offering at least three different methods of contraceptives.

SUFPII contributed to averting national level commodity stock-out through targeted technical and financial support which included; procurement of approximately 50% of the national contraceptive needs for 2017, mid-year review of the 2017 National Supply Plan for reproductive health (RH) commodities to inform targeted actions, monthly review of RH stock through the Family Planning technical working group, and quantification of the 2018 national RH commodities need.

SUFPII also conducted a wide range of activities in the supply chain technical area, operating at the national, provincial (both Western and Central), district, and facility levels. Specifically, SUFPII supported MOH to conduct trainings for trainers and the corresponding trainings and mentorship in supply chain management at the district level in selected sites. SUFP also financially and technically supported selected districts to conduct FP commodity audit trails on a quarterly basis. Previously, inconsistent commodity record keeping in many facilities resulted in frequent stock outs. For example, commodities were exchanged without reviewing and recording the goods delivered. However, through the quarterly auditing and other improvements to documentation, the frequency of discrepancies between actual stocks and records decreased. As a result, out of 11 districts, only one district reported a discrepancy. During the annual review field visits M& E officers verified the trainings and explained how the e-system has eased their work. However they reported often having to use their personal money to buy internet bundles to support the electronic supply chain system.

SUFPII also piloted tracking commodities via mobile technology. Eight facilities from both Western and Central provinces participated in the pilot by entering data every week on the current level stock, stock initially received, outages, and other issues. The data is captured in the National electronic logistics management system (eLMIS) and can be followed at district, provincial and national level including Medical Stores Limited. This activity is still in the pilot phase and will continue into Year Three. The dissemination of the findings from the pilot and recommendations are a part of the year three workplan.

In order to minimise data quality issues with the new family planning acceptor rate, SUFPII embarked on training District Health Information Officers and MCH Coordinators and emphasized the need to support health facilities to collect data elements as defined in the HMIS procedures manual.

Output 1.3: Centres of Excellence (CoEs) were generally regarded during the AR field trip as one of the key successes of the SUFP model with its emphasis on capacity building and mentorship. An analysis of 2017 DHIS2 data demonstrated that SUFPII support to CoEs had improved their provision of FP services, as demonstrated by the relatively high rates of LARC provision compared to other health facilities in the districts. The programme however has limited performance indicators on its cost effectiveness and overall success in meeting all stated objectives. An Abt Associates 2018 milestone report on CoEs described the model and reviewed implementation in Western and Central provinces. The rapid learning cycle in July will follow on with more detailed analysis of the impact of CoEs in meeting stated objectives.

Lessons identified this year
- Mentorship through CoE in SUFPII has improved service provision and commodity management.
- SUFPII facilitated the training of trainers and mentors in LARC, supply chain management and for CBDs. This created a pool of trainers in both Western and Central provinces who are available for use closer to where the needs are, removes the need to bring trainers at greater expense from the national level and promotes sustainable provision of FP services.
- The Rapid Cycle Learning (RCL) process implemented in CoEs was useful in helping facilities identify weaknesses in service provision through data analysis, exit interviews and focus group discussions in CoEs.
- The mobile phone technology pilot and use of the electronic logistics management information system contributed to proactive management of FP commodities in health facilities by helping to manage stock imbalances, reducing the risks of stocks expiring and improving restocking rates. Staff attrition meant that the mobile phone technology was not however implemented optimally in all sites. The final report with recommendations will be disseminated through the national supply chain technical working group.

Recommendations for the year ahead
- Abt to focus more on capacity building training efforts in all facilities where they had done previous trainings to ensure that staff left out of previous trainings are trained to increase service coverage and impact. In the event that this cannot be achieved, a full list of staff to be trained should be submitted to UNFPA under the ZHSSP for action (by September 2018)
- The issue of lack of data disaggregation and how best to provide and incorporate data on SRHR services for the adolescents aged 10-14 years should continue to be discussed at FP Technical working group meetings and brought to the RMNCAH&N committee for solutions (DFID, Abt, UNFPA).
- Abt, UNFPA and MoH to develop a plan by August 2018 to provide additional capacity building in the FP2020 indicators at provincial and district health levels where there are still knowledge gaps (Abt, UNFPA).
- Abt Associates and UNFPA to follow up with district health offices to ensure that internet bundles are included in the health facilities plans and budgets during the MTEF planning process beginning in July.

Output Title	Increased access to family planning services for underserved areas and population
Output number per LF		2	Output Score	A
Impact weighting (%):		25	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress June 2017 to April 2018
2.1 Mobile platform to increase access to family planning amongst young people	Roll-out of TuneME platform to target provinces	Moderately Not Met: TuneMe platform functional at national level and adolescents accessing it. Mapping of partners working with adolescents and young people in Western province completed to facilitate rollout in Q2 2018
2.2 Number of completed, costed district family planning scale up action plans	7	Met: 27 / 11 Central Province; 16 Western Province / SUFPII leveraged the opportunity provided by the ZHSSP to provide additional technical support to developing and costing FP scale up plans in all 27 provinces
2.3 Percentage of districts that acted on the recommendations on FP from their performance assessment (methodology note: baseline SUFP supported districts in Western and Central)	50%	Moderately exceeded: 100% / All SUFPII assessed districts had acted on some recommendations from their FP performance assessment
2.4 Number of Community Based Distributors trained in Western Province, of which number are also community leaders	138 by July 2018	Met: 148 of which 20 (14%) are community leaders

Output 2 assesses the increased accessibility of family planning services to underserved areas and populations measured through the plans and resources dedicated to scaling up access through the public health systems, and the increased availability of information on service points for young people.

Score: A: Output met expectation. Targets were met on two indicators, exceeded on one and another indicator moderately underperformed. SUFPII leveraged the DFID ZHSSP planning exercise in Western and Central province to provide additional FP technical assistance to provinces, contributing to exceeding target for indicators 2.2 and 2.3. As a result, FP plans were completed and costed for all districts and action plans finalized during the planning process to address issues arising from previous performance assessments.

Output 2.1: In addition to the preparations for the role out of the mobile platform ‘Tune Me’, Abt reported intensified efforts to increase access to modern contraceptive for young people during the year under review. They hired a full time adolescent health specialist who conducted an informal assessment of the current situation for adolescent family planning with UNFPA, visits to various health centres. The AR visits confirmed the assessment findings that challenges still exist for this underserved population. The issues include insufficient youth friendly spaces in health facilities; inadequate numbers of trained health workers in youth friendly ARH, long wait times; health workers attitudes; poor turn out in youth friendly spaces activities, negative parental attitudes; limited access to technology, high attrition rates among the peer educators due to high mobility in this population (i.e. moving for college, marriage, jobs and lack of motivation). The peer educators interviewed during the annual review field visits complained about the lack of communication materials and entertainment equipment to attract the youth. It was also found out that adolescents in the age band 10-14 years were not routinely captured in facility registers and included in planning for adolescent reproductive health activities.

Output 2.2: SUFPII actively participated in the 2018 MoH provincial and district MTEF planning meetings in September 2017, providing technical support on FP services. In addition, SUFPII partners actively participated in the DFID ZHSSP work plan development processes in November and December 2017. During the meetings, SUFPII provided technical input to the planning discussions, reading through draft district plans and advising the districts on high impact family planning activities during group work. The activities that SUFPII advocated for included CBD training and follow up; training of health service providers in LARC, providing mentorship in LARC, and building capacity and allocating resources to strengthening FP supply chain management.

The MoH headquarters, provincial and district teams met during the AR field visits confirmed that support provided by SUFPII was appreciated and adequate at national, provincial and district levels. SUFP facilitated strengthening of national and subnational level coordination mechanisms for family planning. Coordination meetings are being held monthly at national level and quarterly at provincial level. SUFPII support to Central province however was further behind when compared to activities in Western province.

Output 2.3: The institutionalization of the SUFP Model and strengthening health systems is possible when health facilities identify a need and actively seek avenues for solutions. As an example, Litambya Health Centre identified a need (specifically, purchase of FP equipment for IUCD insertion) and worked with the district to allocate funding for FP activities. Litambya’s finance committee – comprised of Health Centre staff and a representative of the community – agreed on the importance of FP and need for intrauterine contraceptive device insertion equipment to improve LARC service delivery. In response, the district gave the centre permission to purchase equipment from the World Bank RBF programme budget under the indicator “Increasing family planning acceptors.”

Output 2.4: A total of 148 CBDs were trained during the AR period of which 20 (14%) were community leaders. Community leaders, FP and adolescent sexual and reproductive health sensitization meetings were conducted in seven districts in the Western province in October 2017. In addition to meetings, sensitization efforts included designing radio broadcasts in 10 districts to ensure local buy-in to the CBDs programme. During the annual review field visits, it was discovered a significant number of the CBDs were opinion leaders, for example, members of Safe Motherhood Action Groups or other groups of influence in their communities. Whilst this increased their effectiveness in FP service delivery, it could potentially create conflict of interest issues with communities having no recourse to an objective arbitrator should issues with CBD performance arise.

Lessons identified this year
- From the review field visits, youth indicated that although the health facility and the health worker were still the most preferred source of sexual and reproductive health information, they would like to have more private spaces and greater confidentiality in their dealing with health facilities.
- Adolescent reproductive health is a sensitive area which can be effectively tackled if the communities are involved as parental consent is required to provide services to youth below 16 years. Involvement of traditional leaders has been key to reaching adolescents.
- Sensitization and involvement of a wide range of community leaders help communities understand the challenges within their own context and ensure full ownership of solutions.
- CoEs are taking a leadership role within their districts on capacity building through on-site mentorship. Monitoring visits to the CoEs have observed that mentorship is carried out more frequently than costly off-site trainings that take staff out of their posts for long period of time. In some instances, mentorship has been conducted without donor support.
Recommendations for the year ahead

- Additional focus is needed in defining a package of adolescent friendly services and begin to expand adolescent access to FP services in a more concrete way, for example, through increasing mobile services to bring adolescent reproductive health services closer to the communities and provision of youth friendly communication materials (SUFP, UNFPA by October 2018)
- Abt to ensure that during the MTEF 2019 budget processes, province and district health offices continue to budget to train increased numbers of trained peer educators and health workers in youth friendly adolescent and reproductive health services at facility, district and provincial levels to improve reach and increase impact (Abt with support from UNFPA as ZHSSP technical lead by September 2019).
- Abt to intensify activities in the Central province to ensure that they bring the province up to speed in terms of identification of existing and potential CoEs and identify capacity needs before handing over to UNFPA by September 2018 (Abt, UNFPA).

Output Title	Increased community support for family planning
Output number per LF		3	Output Score	A+
Impact weighting (%):		30	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress June 2017 to April 2018
3.1 Availability of a national Social and Behaviour Change Communication strategy, implementation guidelines and tools	RMNCAH communication strategy approved, FP chapter implementation and monitoring framework agreed	Moderately underperformed: RMNCAH communication strategy that incorporates FP chapter and M&E framework finalized - awaiting MOH to host validation meeting before publishing
3.2 Number of trained peer educators active in the last reporting period (methodology note - active means involvement in district adolescent activities e.g. meetings and outreach activities and has submitted activity or peer contact reports to the district)	150	Moderately exceeded: 163
3.3 CBD retention rate in Western Province	85%	Moderately exceeded: 97% / (115 of 118 reported to be active)

This output assesses increased community support for family planning, focusing on community based distribution and behaviour change communications as a means for monitoring whether attitudes towards women’s use of family planning are changing.

Score: A+: Output moderately exceeded targets on two of the three indicators and moderately underperformed on one indicator.

Output 3.1: The Reproductive Health Communication Strategy that includes an FP chapter and an M&E framework has been finalized and reviewed technically by MoH and the FP technical working group. The report is now with the Ministry of Health awaiting a final validation meeting with stakeholders before publishing. The changes in leadership in the directorate of public health, under which FP falls and the lack of continuity that has resulted from this has contributed to the delay in holding the validation meeting. It is anticipated that this process will be completed by September 2018.

Output 3.2: SUFPII supported peer education trainings and trainers activities for a total of 163 per educators in five districts - 115 adolescents in the Western Province and 48 in Central Province. Training contents and guidance to health facilities were informed by the assessment of adolescent health services carried out by the full-time Adolescent Health Specialist hired in December 2017 (described under Indicator 4.2).

Output 3.3: A total of 115 of the 118 trained CBDs were reported to be active in their target communities. During the AR period, SUFPII supported three Depo Provera trainings in Western and two in Central with a total of 118 participants to enable them provide an expanded range of FP methods. Alongside the trainings, SUFPII conducted community sensitization to ensure local understanding of and buy-in to the CBD programme. Although retention rate is high, additional work is required to further assess quality of services delivered by CBDs and the 100 teachers previously trained in comprehensive sexuality education by SUFPII; and level of uptake by school girls through the referral mechanisms to health facilities.

Through the SUFPII community engagement process, SUFPII learned that while the communities appreciated the CBDs, they felt that the numbers of CBDs were insufficient. This finding on the insufficient numbers of CBDs was verified during this AR process in all the health facilities visited including from the provincial and district health teams. Among the challenges mentioned by CBDs and health facilities during the review were low involvement of men, inadequate supervision of the trained CBDs to check quality in delivering the methods due to transport problems and motivation issues for CBDs, a volunteer cadre.

Lessons identified this year
- Community involvement on key problems in the district/province through an Indaba (gathering of leaders, technical people and community members) to discuss key problems such as high teenage pregnancies, high HIV prevalence helps community engagement in agreeing solutions they can own and sustain.
- An increasing number of young people appear to be shifting from short term methods to LARCs
- Young people prefer feel that what they get from the school comprehensive sexual education programme is not adequate and would prefer getting sexual and reproductive health information from peers and health providers.
- In the longer term, the volunteer status of CBDs may impede their motivation and overall effectiveness.

Recommendations for the year ahead
- The issue of long term motivation of volunteers should be raised by DFID, Abt and UNFPA at national level policy meetings as the issue is not limited to FP CBDs but is common to all volunteers that do not receive financial or non-financial remuneration for their services. At the provincial and district levels, UNFPA and Abt should explore with the provincial and district teams ways of ways of motivating CBDs e.g. linking them to other income generating projects in their districts.
- SUFPII to advocate during the 2019 MTEF planning process that District health offices make specific provision in health facility budgets for supervision and mentorship of CBDs (Abt, UNFPA commencing July 2018).
- SUFP to advocate to during the 2019 MTEF planning process for district health offices to budget for more youth-friendly spaces in health centres with their ZHSSP funding. (Abt Associates by September 2018).

Output Title	Increased public sector capacity to provide comprehensive family planning services
Output number per LF		4	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress June 2017 to April 2018
4.1/ Number of new or revised key policy commitments incorporating best practices identified by SUFP for family planning scale up	No Target for 2018	The following documents contained SUFP best practices: / Adolescent Strategy 2017 -2021, the Reproductive, Maternal, Newborn, Child and Adolescent Health and Nutrition Communication and Advocacy Strategy 2017-2021; Community based distributors DMPA roadmap and implementation plan.
4.2 Evidence generated and used for advocacy for FP activities	Mapping of adolescent friendly service provision (SUFP to define good practice in adolescent family planning through an evidence review and use this definition to map the availability of service provision)	Met: Assessment of adolescent friendly services carried out in Central province informed training of peer educators, guidance notes to Centres of Excellence and final year work plan.
4.3 Established and operational family planning coordination mechanisms	Western district level established with ToRs, Western Provincial level operating as per ToR	Met: Western FP coordination group operating in Western province as per TORs with participation of all districts. Districts to use integrated performance reviews as a platform to discuss FP issues and follow up with FP specific issues as needed.

Output 4 assesses public sector capacity to provide comprehensive family planning services, focusing on strengthening GRZ coordination, developing national level policy and use of evidence as a means for monitoring whether the public sector is better equipped to deliver family planning services.

Score: A: Output met expectation on the two indicators with targets for the AR period.

Output 4.1:  At the national level, SUFPII technical staff participated in planning meetings of the FP technical working group, sharing reports and lessons learned from the programme to inform on the development of national strategies and plans, informed by best practice in Zambia and elsewhere. Of note is SUFPII support to the CBD Task Force meetings and orientation meetings on Sayana Press (a newly available form of Depo Provera, which can be self-administered). MoH has committed to the roll out of Sayana Press through CBDs in Zambia. SUFPII contributed to the development of a road map for training on and dissemination of Sayana Press. SUFPII action will complement and contextualize DFID commitment of £30million towards Sayana Press product procurement globally through UNFPA.

Output 4.2: SUFPII conducted an assessment of the current state of adolescent services on Central Province in December 2017. Meetings were held with UNFPA and MoH in selected health centres of Luano, Ngabwe and Chitambo districts and conducted follow-ups via phone. The assessment found that there were insufficient youth-friendly spaces, long waiting times and loud name calling at the clinics which deterred youth because they did not want to be seen waiting outside the clinic. In addition, FP services were only offered on certain days so that youth going on those dates were immediately known to have gone for contraceptives. Findings were incorporated into the training of 163 adolescent peer educators in Western and Central provinces (see indicator 3.2). SUFPII, informed by the assessment, provided facilities, including the selected CoEs, with guidance on “quick fixes” to improve adolescent services.

Output 4.3: SUFPII successfully advocated for the establishment of a provincial technical working group supported by a TOR. As a result, FP and adolescent sexual and reproductive health services were integrated into the province wide child health week activities, increasing FP access to hard to reach areas. A mapping exercise of all FP partners in the province was conducted through the provincial technical working group, to help identify partners and gaps in FP service provision. To reduce the number of meetings, MoH advised that districts should review FP service outputs through their quarterly integrated performance review meetings and follow up issues through meetings to be led by the district maternal and child health coordinators.

Lessons identified this year

-The SUFP programme successfully piloted in selected CoEs a ‘quick fix’ solution to the problem of health staff calling out names of clients waiting for FP services, exposing the purpose of visiting the health facilities and embarrassing clients, particularly adolescents. The programme encouraged facilities to employ a numbering system for waiting clients so that numbers, instead of names were called and the purpose of the visit not revealed.
- Integration of services as usually happens at youth friendly spaces works best for most clients especially the youth as there is greater confidentiality.

Recommendations for the year ahead

-DFID to include the ‘Family Planning 2018-2021 costed Road Map’ as the 2018 indicator for indicator 4.1 now that the MoH has confirmed that they will go ahead in developing this document (DFID by August 2018)

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The overall Theory of Change (ToC) for SUFP has remained unchanged since the programme was approved in 2011. Whilst the method of implementation and choice of inputs has been altered, the overall combination of procurement of commodities, training of staff, community outreach and sensitisation with the aim of increasing use of family planning remains valid. For SUFP II the additional focus on adolescents represents a major shift in addressing unmet need of this vulnerable population. Results to date in terms of additional users of family planning indicate that overall the theory of change is holding.

Evidence and evaluation
In the period under review, DFID commissioned an evaluation of SUFPI that was conducted by UNFPA in collaboration with Population Council. The final review report has been substantially delayed in its execution but will be finalized in August 2018.

SUFP Theory of Change

Describe where the programme is on track to contribute to the expected outcomes and impact, where it is off track and if so, what action is planned as a result in the year ahead
Improved maternal health
Increased birth spacing and healthier children
Reduced costs to health service
Slower population growth and associated environmental benefits
Increased participation of women in economic and political life
Expanded availability of choice of FP
Increased access to FP services for under-served areas and populations
Increased community support for FP
Increased public sector capacity to provide quality, comprehensive FP services
Increased use of FP
Reduced unintended pregnancy
Reduced unsafe abortion
Commodity procurement
Staff recruitment and training
Outreach services
Community sensitisation
Training public sector providers on LTRM and adolescent friendly services
Outputs
Outcome
Impact
Wider impact
SUFP Theory of Change

For the year under review, the programme achieved 122,810 CYPs exceeding the AR target of 100,000 CYPs which is not surprising given the increase in uptake of long acting reversible contraceptive methods (LARCs), and increased number of new users of modern methods attributable to the programme.

Insufficient progress however has been made in GRZ increasing its funding of FP commodities, with 24% of FP commodities funded by SUFP against a target of 17%. In total during the AR period, DFID through the DFID funded UNFPA global RH supplies programme and SUFP provided approximately 50% of all RH commodities needs for Zambia. On closer interrogation of data, it emerged that the DFID 25% contribution to meeting the 2016 FP national commodities funding gap was sufficient in closing the funding gap only because of a significant injection of commodities by USAID that amounted to over 60% of 2016 FP needs. At the 2017 FP2020 summit, Zambia committed to increasing government funding for FP commodities to $1.5million per year by 2020. This amounts to approximately 15% of current needs. With no further USAID support to Family planning currently planned, at the current trajectory, the SUFP life of programme target of contributing 15% of RH commodities will not be met without a significant gap in FP commodities availability.

The UNFPA global RH commodities security team visited Zambia in May 2018 to better understand the constraints within the government in increasing funding to RH commodities. The team raised awareness of MoH, Ministry of Finance and parliamentarians of the urgent need for a substantial increase in annual RH commodities to support Zambia’s attainment of the demographic dividend. UNFPA will be conducting a review of the Zambia donor landscape in September and produce a paper for stakeholders and GRZ to help with advocacy towards sustainable domestic RH commodity financing.

The demographic and health survey currently being implemented will track national and provincial progress against outcome targets for contraceptive prevalence rates and reducing unmet need for family planning. It is anticipated that preliminary results will be released by May 2018 to assess progress against all SUFP outcome indicators.

Explain major changes to the log frame in the past year

A few indicators, specific to Abt were redefined. These include:-

- Indicator 1.3 (Number of target districts (Western) that received technical expertise and assistance to build capacity using the Family Planning Centre of Excellence),
  - The Intention was to capture sustainable capacity building of service providers outside the CoE setting and to critically assess the best approach to sustainable rural capacity building.
- Indicator 2.3 (Number of target districts (Western) receiving financial support from the province to conduct scaled up family planning activities),
  - The Intention was to focus on the quality and substance of GRZ support to family planning scale up and reflecting the overall shift to district managed financing with less reliance on the Province

These were redefined with the following indicators to concretely measure progress on the intentions behind the original indicators as follows:
- Indicator 1.4: Number of CoEs that have been assigned CoE functions and allocated a budget; and
- Indicator 1.3 - Number of fully functional CoEs.

In addition, an indicator to track progress on adolescent health services was added, namely indicator 3.2. ‘the number of peer educators trained active in adolescent health’.

Describe any planned changes to the log frame as a result of this review

There are no new planned changes to the log frame with only 5 months to the end of the Abt Associates component of the programme in October. There is still however the need to insert a target for 2018 for Indicator 4.1. ‘Number of new or revised key policy commitments incorporating best practices identified by SUFP for family planning scale up’.

In terms of recommendations for the 2018 target for 4.1, it is proposed that ‘National Family Planning 2018-2021 costed Road Map’ be the 2018 target now that the MoH has confirmed that they will go ahead in developing this document.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

As part of last year’s annual review, Programme SRO and Economic Adviser reviewed the VfM framework, recategorised some of the indicators and introduced new measures to better capture value for money along the results chain.

UNFPA Component

In the period to 31 March 2018 the key cost drivers for UNFPA were as follows:

Category	Total Amount (£)	Percentage
Commodities	£1,489,044	79%
Capacity building (training and project planning)	£245,032	13%
UNFPA cost recovery	£150,789	8%

The SUFPII, through UNFPA, contributed 24% towards national FP commodities supplies for Zambia during the AR period. This represents approximately 91,440 additional users nationally according to the FP2020 modelled results for Zambia for 2017, and 65% of the 140,000 additional users target for SUFPII. Overall, UNFPA has between 2013 and 2018 provided approximately 54% of FP commodities for Zambia, primarily through the global UNFPA Reproductive Health Supplies programme to which DFID contributes, and bilaterally through the SUFP programme.

Recommendation

With the imminent end of SUFPII and limited donors interest in FP commodities, DFID and UNFPA to intensify advocacy for increased domestic financing of reproductive health commodities, particularly family planning products. The upcoming MTEF process provides a platform to advocate for increased MoH allocation to the reproductive health commodities budget to meet Zambia’s FP2020 commitment of increasing expenditure on FP commodities from the annual average of $1million to $1.5million.
.
Abt Associates Component

Key cost drivers for the technical assistance package of support through Abt associates are staff salaries, programme administration and management costs and costs associated with trainings and other programmatic activities.

Economy

Staff costs: The total percentage of Abt staff costs is high at approximately 72% as is expected from a largely technical assistance (TA) programme providing TA at all levels. The ratio of national to international TA days has declined to a ratio of 9:1, a marginal improvement on the 2017 AR performance.

Unit cost of training: Unit cost per training per participant is £65 against a target of £60, representing no further reduction from the unit cost obtained in the 2017 AR period. Comparatively, this unit cost is lower than the baseline of £79 in 2016 and suggests no further innovation to reduce training costs without compromising on the quality of the training.

Administration and management costs: The Abt Associates administration and management costs as a proportion of total expenditure is significantly off track at 28% against a target of 20%. This result, although off track, shows an improvement over the previous AR period during which administration and management costs were 40% of overall spend. Steps taken to reduce costs during this AR reporting period included a greater volume of programme activities generated by two newly recruited technical staff (an adolescent health specialist and a central province advisor); and reducing the number of administrative staff. In addition, all but one milestone for the AR period has been approved, decreasing the percentage of administrative and management costs relative to programme costs for the period under review.

Efficiency

Unit cost of providing services to each additional user (£): The unit cost of providing services to each additional user in the year under review through Abt Associates was moderately below target at £19 against a target of £15 but at par with the baseline of £19 per additional user. The indicator new FP users was used as a proxy for additional users. Abt continued during the AR period to make long-term investments that have high initial costs, for example training, but do not necessarily result in immediate increases in FP acceptors. While some training may have more immediate impacts, such as training CBDs, the impact on the new FP users’ metric of training district health information officers, trainers and peer educators for adolescents will only be realized in the medium term. These long-term initiatives will help ensure ownership by the MOH and promote sustainability.

Unit Cost of training per participant per day (£): A new efficiency metric was agreed between Abt and DFID to be added to measure quality of training as evidenced by pre and post training. In the AR period, all trainings recorded an average improvement in scores as evidenced by the scores at 85%, just below the July 2018 target of 87%.

Effectiveness

Cost per Couple Year of Protection (CYP): SUFPII met its target in terms of Cost/CYP with an overall Cost/CYP during the AR period of £16 against a planned target of £18, based on 312,000 CYPs achieved nationally through UNFPA and Abt Associates programme activities.

 It is noteworthy that Abt Associates component achieved a Cost/CYP of £12 for Western province against the target of £18. The Abt CYP calculation is limited to Abt inputs and excludes the cost of FP commodities attributable to SUFPII through UNFPA. This figure however is a significant improvement over the Abt Cost/CYP of £30 reported for 2017 AR period for the province that reflected less than 6 months of programme implementation at the start of SUFPII. The challenges with health facilities’ interpretation of a ‘new FP user’ that may have inflated programme achievement and the mitigation actions taken by SUFPII are outlined under Output 1.

The underlying drivers of Cost/CYP are expected to be further examined in the end line report of SUFPI expected in August 2018.

Number and percentage of CBDs that receive full or partial “refills” of commodities in the last reporting period: All 115 active CBDs (97% of those trained) received refills of commodities (Depo Provera, Pills, Male Condoms, and Female Condoms) during the period under review, indicating government ownership and support to CBDs at this initial stage of scaling up the CBD model.

The review has attested that the second year of SUFPII is building capacity and strengthened working relationships with MoH towards increasing sustained ownership of FP services at national, provincial and district levels which are good measures of programme effectiveness.

Equity

The programme, by focusing on Western and Central province at scale, is meeting the equity VFM criteria by targeting the most underserved and hard to reach populations in the two provinces which have the worst indicators for teenage pregnancies and total fertility rate. Additionally, by increasing the focus on adolescents and poor rural households, the programme is demonstrating its commitment to leave no one behind. The programme also makes deliberate efforts to ensure gender considerations are taken into account in selection of CBDs, peer educators and health workers for training. In the year under review, 56% of trainees were female against a target of 58%.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The programme continues to represent good VfM achieving an overall Cost/CYP of £16 during the AR period, which compares favorably with the £15/CYP achieved in the final year of SUFPI and lower than the overall £20/CYP achieved over the four years of SUFPI. The cost Cost/CYP of £16 is however higher than the Cost/CYP of £10.43 achieved in Kenya and £11.03 anticipated in Malawi[2]. The SUFP business case anticipated, and experience through SUFPI[3] confirmed, that the Cost/CYP in rural Zambia is high compared to the regional average due to high staff costs and allowances and logistical challenges associated with expanding services to more remote unserved areas (the last mile) with dispersed populations. It is however expected that the increase in costs will be compensated by the fact that the SUFP programme would be providing services to the poorest households, adolescents and hard to reach communities.
[2] 2018 Annual Review of DFID Kenya’s Delivering Increased Family Planning Across Rural Kenya Programme and DFID Malawi’s ‘Tsogolo Langa’: Expanding Access to Family Planning Services and Sexual and Reproductive Health and Rights in Malawi Programme Business Case
[3] SUFP 2016 Annual Review
The programme continues to respond to the high unmet need for family planning particularly in underserved provinces and provide opportunities for learning to inform national FP services implementation. Several best practices and lessons emerging from the programme, including the Centres of Excellence for Family Planning and the roll out of CBDs at scale and strengthening the supply chain systems are innovations that seek to sustainably build FP capacity in public health facilities and communities. In order to maximize VFM, SUFP works with and through existing public health structures and is able to leverage on resources of existing partners and districts to implement activities in the two provinces. For example, they do not pay CBDs and peer educators and build on the technical expertise of PATH to support roll out of the self-administered injectable, Sayana Press through CBDs.
Family planning is a key priority for the UK and additional family planning users achieved by the programme will contribute to the UK FP2020 target of 24 million additional users by 2020 and strengthen the foundations for universal access to SRHR services by 2030, in line with the Agenda 2030 for the Global Goals, and the commitment to leave no one behind. SUFPII was designed as a forerunner to the ZHSSP, to ensure DFID investments through SUFPI were consolidated and bridge the gap between ZHSSP programme start up.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Moderate and increasing

Overview of programme risk

Programme risk is currently rated moderate. Regular reviews of the risks and risk mitigation strategies are carried at DFID during quarterly review meetings with all SUFPII partners.

SUFPII continues to place additional emphasis on GRZ ownership and leadership, with no change in the risk rating as assessed in the last annual review. DFID and programme implementing partners will however need to keep a close eye on this risk as the success of this phase of the programme is highly dependent on government prioritizing FP and increasing its resources to meet the programme targets and contribute effectively to overall family planning objectives and commitments. This will require continued high level engagement with MoH at national level (DFID and partners) and at district and provincial level (partners) to advocate for FP, support GRZ to keep to and if possible improve on its renewed commitments at the London 2017 Summit. The ZHSSP programme funds through districts in Western and Central provinces provide an opportunity for districts to ensure FP remains a priority during the MTEF planning and budgeting process.

The risk of community opposition to FP for unmarried adolescents is decreasing in target provinces and may be attributed to the programme’s intensive focus on community sensitisation activities that actively promotes and includes community leaders as partners in increasing demand for and delivery of FP services.

The fiduciary residual risk on expiry and theft/loss of family planning products is on the increase. The Global Fund Office of the Inspector General identified pharmaceutical and non-pharmaceutical inventory losses of $ 1,064 million delivered to the Medical Stores Limited (MSL) between 2014-2016. There is some evidence of theft of at least some of the health goods. Family planning commodities however were not implicated and UNFPA’s robust monitoring and control systems for procured FP commodities distributed through Medical Stores Limited have been reviewed and strengthened. Measures in place include quarterly inventory spot-checks and audits conducted at service delivery points; reconciliation of receipt and distribution reports with UNFPA’s records and period audits by UNFPA headquarters audit teams to track selected commodities from central level to recipient facilities. In addition, UNFPA’s annual RH commodity security survey reviews availability of commodities at service delivery points and assesses stock-outs regardless of the source of commodities and triangulates the information with commodity status at national level. The surveys have consistently informed SUFP activities strengthening the logistics management systems for RH commodities at national, provincial and district levels.

The dependence on weak HMIS data to track additional users of FP remains a challenge in determining programme outcome and some output indicators. SUFPII is addressing this risk through trainings in target provinces data however this issue cannot be fully solved under this programme and therefore a risk to be tolerated knowing that results can be verified using the preliminary DHS 2018/19 report expected in May 2019.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

The programme is implemented by Abt Associates and the United Nations Population Fund (UNFPA).

Overall, the relationships with all partners including Ministry of Health are positive. DFID chairs the quarterly meetings with Abt, UNFPA and a representative of the MoH. The implementing partners are part of the Technical Working Groups (TWG) on Family Planning and Adolescent, a multi-stakeholder forum providing advice and support to the Ministry of Health. Narrative progress and financial reports are submitted quarterly, matching the schedule for quarterly meetings. The reports summarise programme performance in relation to the achievements of activities and outputs, as well as implementation challenges, risk mitigation and lessons learnt. In addition to above, for both partners, there are regular discussions on forecasts.

During the year under review, performance of both partners has been acceptable. It is to be noted however the quality of initial milestone submissions by Abt Associates during the AR period have in several cases been sub optimal and required revisions before acceptance by DFID. This has in the main delayed payment of milestones. It should be noted however that Abt Associates have been responsive to DFID’s comments and improved the quality of the milestones accordingly.

UNFPA agreement with DFID is governed by a Memorandum of Understanding (MoU). UNFPA have adhered to expectation in procurement of FP commodities, the main stay of their programme component but experienced delays in delivery of several programme activities notably the SUFPI end line survey.

Both Abt Associates and UNFPA have robust financial management systems. The payments for Abt Associates are milestone based monthly reimbursable. Forecast for FY2017/8 was £2,388,408 against spend of £2,083,543.79 with a variance of 13%. Abt Associates accounts are audited regularly by their Internal Audit Department and they also conduct annual external independent audits. The last annual audited accounts were unqualified.

UNFPA’s payments are quarterly advance payments. Forecast for FY 2017/18 was £1,884,866 against disbursement of £1,884,865.40, the majority of which is spent on FP commodities (79%). UNFPA provides annual certified statements.

Abt Associates maintains an updated assets register in line with its own operations manual that is aligned with DFID requirements.

Date of last narrative financial report	April 2018
Date of last audited annual statement	June 2017

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Besides routine tracking of family planning data, SUFPII started several innovative activities in the area of M&E during the period under review. Most notably, SUFP designed and implemented a rapid cycle learning (RCL) activity to observe SUFP’ s progress in achieving its objectives, led by Abt Associates Senior M&E Advisor. Throughout the process, SUFPII engaged the Senior Health Information Officers and District Health Information Officers (DHIOs). As part of the rapid cycle learning exercise, SUFP also conducted a mapping exercise of all partners involved in FP activities for use by the provinces in their FP coordinating activities. During the annual review field visits, the provincial and district staff in the Western Province were able to articulate how the RCL activity has helped them monitor progress towards FP uptake goals and take necessary actions to improve implementation. Additionally, at the request of the MOH, SUFPII conducted training in routine data quality assessments (RDQA).

The FP national annual review meetings are mainly funded by UNFPA to review progress on FP plans and develop plans for the next year. This forum is important for increasing collaboration across the public health system with provincial, district, and health information officers and pharmacists in attendance. The review team confirmed the strong cordial working relationships between SUFP and UNFPA as the two main implementing partners. Oversight of the programme by senior MoH management is still a challenge because of the frequent changes in the ministry senior officials. The review found out that the current strong MoH involvement was ttributed to the proactive engagement and knowledge of government systems by the SUFPII Abt Associates and UNFPA teams. As such, although MoH staff and stakeholders interviewed during the review indicated that MoH is taking a leading role on the programme, fears were expressed as to whether MoH has the capacity to take over the SUFP model within the programme timeframe.

DFID Monitoring of SUFP Programme
DFID conducted quarterly field visits during the AR period and an additional visit by the Human Development Team leader and Head of Office to SUFP sites.

In December 2017 and February 2018, DFID participated in the ZHSSP Reproductive, maternal, newborn, child and adolescent health planning and budgeting workshop in Western province to advocate for integration of FP activities in provincial and district health plans. The opportunity was used to also review performance of the Abt Associate field coordinator with the provincial maternal and child health coordinator and districts targeted for SUFP activities in Western. DFID also participated in the Abt work plan development process with UNFPA in attendance and pressed home the urgency of the need for a seamless transition between the SUFP programme and Zambia Health Systems Strengthening Programme service delivery component implemented by UNFPA as the lead UN partner.

The SUFP annual review was conducted by DFID Malawi Health Adviser, supported by the SUFP programme SRO and programme management team. Field visits were conducted to districts in Western and Central province in April 2017.

Milestone achievements
The year under review had 15 milestones of which all milestones with the exception of one (Supply Chain Mobile Phone Pilot Report) for the AR period have been approved.

Evidence

As part of generating evidence, learning and documentation, SUFPII conducted a Rapid Cycle Learning study to assess family planning implementation to improve programme performance. A summary of the results are as follows:
1. The study clearly shows increases in average new FP users in twelve of the sixteen districts in Western Province (except in Sioma and Sesheke). Inconsistencies in data collection were noted and shared with reporting districts for further investigation.
2. There are positive average increases in long acting methods ( Depo Provera) in every intervention district except Nalolo, Senanga, and Sioma.
3. Family Planning clients are generally satisfied with the family planning services they received at health facilities (of the 252 FP clients surveyed, 98% reported being happy with the services)
4. At community level, myths and misconceptions still exist and there is still unmet need for FP.

During the year under review, DFID supported Population Council, through UNFPA, to conduct the end line review of SUFP1. The execution of the review has been severely delayed and although it will be difficult to assess real impact long after the close of SUFPI, it is expected that the report will reveal important lessons on programme implementation.

From the Pilot on supply chain SMS mobile technology
During the period under review, SUFP piloted a mobile phone technology pilot project in eight health facilities in the Western and Central provinces to demonstrate how mobile phone technology can be used to report on essential data elements such as stock status, losses and adjustments to better manage FP commodities almost in real time using supply chain data.

Recommendations
- UNFPA to expedite the finalisation of the SUFP1 End line report and disseminate findings by September 2018.
- SUFP II partners to disseminate findings from the SMS phone technology pilot to MoH and Family Planning technical working group and collectively agree, with the MoH and with DFID approval, on follow on actions after the Abt Associates component of SUFPII ends in October 2018. This might possibly include expansion of the pilot to additional sites under the ZHSSP but must be based on a thorough assessment of the added value of expanding the pilot.

Progress on recommendations from previous reviews

DFID Health Adviser and Social Development Adviser (SDA) to ensure SUFP implementing partners are engaged in the new HSS programme to maximise learning and leverage additional resources in the health sector through inviting them to key inception meetings (September 2017)
Done.  SUFP participated in the ZHSSP Province programme planning meeting week long meeting with provincial and district health staff in December 2017.  ZHSPS MOU with UNFPA was not signed until October 2017 hence the delay in implementing this recommendation.  In addition, UNFPA, in their capacity as the ZHSSP lead UN programme implementer, participated in the SUFP work plan exercise in February 2018.. Activities designed to maximize learning and leveraging  total DFID investments in FP and RMNCAH&N have been incorporated into SUFP work plans going forward (e.g. joint visits, meetings etc.)
UNFPA and Abt to agree a mechanism for supporting provincial redistribution of commodities to manage stock outs in Western (by August 2017) and ensure feedback from facility, district and provincial Essential Medicines Logistics Improvement Plan (EMLIP) users feeds into national policy engagement with MSL and MoH.
Done: UNFPA met with MOH Principal Pharmacist in Lusaka and briefed him on the issue and plans to work with provincial counterparts to devise mechanism redistribute commodities. They also convened meetings (in each province) with Provincial Pharmacists MSL representatives and other stakeholders to design districts-specific plans for addressing communication and transport support for redistribution. As a result of this the districts compiled redistribution plans and supported health facilities to restock based on need.
UNFPA to assess the stock out status within hospitals and identify root causes of the drop in performance (July 2017)
Done: RHCS SDP Survey data was critically analysed, with specific recommendations made which saw the implementation of activities such as the support to strengthening of eLMIS to help strengthen the monitoring of commodities for hospitals and primary health facilities
UNFPA and Abt to work with MoH to promote consistent interpretation of how new users are measured (by integrating this into all training sessions with HMIS users)
Ongoing: Advocated that MoH shift to “additional user” indicator as this is one of the key indicators for FP2020. To this effect SUFPII conducted a training in Track 20 in Central and Western Province to start modelling family planning data using existing survey data. SUFPII will also take advantage of other meetings to reinforce the correct interpretation
DFID SDA and Abt to redefine indicator 1.3 on capacity building of district staff to capture activities that occur outside the Centre of Excellence (August 2017)
Done: see revised log frame
Greater attention to adolescents should be informed by the work of other stakeholders in Zambia, in particular those active in Western Province. Restless Development, Concern Worldwide and Marie Stopes International have all adopted different models for provision of information and service delivery. UNFPA should convene the relevant partners to learn what models have worked well, and where, to support SUFP to advocate for the most effective set of interventions at district level
Ongoing: SUFPII recruited an Adolescent Specialist to spearhead adolescent activities. Held consultations with other partners implementing adolescent activities to understand which approaches have succeeded in engaging young people effectively. Abt worked closely with the Adolescent health specialist at UNFPA and undertook joint activities and developed complementary actions.
DFID Health Adviser and SDA, UNFPA and Abt to review the communication and advocacy strategy and agree what activities to prioritise under this programme (August 2017)
Ongoing: This national document has not been finalized and therefore recommendation not acted on.  Programme influencing strategy has focussed on ensuring lessons learned from FP review feeds into planning, advocacy to raise profile of RH in health sector budget, disaggregation of FP data to detail work on adolescents and appropriate and increased FP2020 revised commitments.
DFID SDA and Programme Manager, UNFPA and Abt to build upon the engagement with the Litunga to increase access to community structures and increase community acceptance of family planning (agree an action plan by September 2017)
Ongoing: UNFPA work on sensitizing parliamentarians on FP issues, using province specific data on FP and guiding parliamentarians as to the appropriate community response.  Likewise Abt support district and provincial MoH in planning outreach services and in implementing the ‘camping approach’ as appropriate.

DFID SDA and Abt to agree a disaggregated target for output 3.2 (August 2017) and move this indicator to output 2, as this deals more with access than community acceptance.
Done: Indicator is now under Output 2 and 2.4.

DFID SDA and Abt to agree an additional indicator related to community acceptance of adolescent family planning, incorporating aspects of peer education or adolescent action plans (August 2017)
Done: Added an indicator related to community acceptance under output 3
DFID Health Adviser and SDA, UNFPA and Abt to agree 2018 targets for indicators 4.1 and 4.2 with a greater focus on policy influencing objectives and quality assurance and less on the completion of GRZ documents (August 2017)
Done: See latest Log frame

UNFPA to prioritise more timely production and dissemination of evidence products to inform planning processes
Ongoing: UNFPA has planned for monthly bulletins, national/sub-national critical thinking fora, production of policy briefs all to support the timely production and dissemination of evidence based products

DFID Health Adviser, UNFPA and Abt to meet with MoH officials following the London family planning summit to agree a mechanism to maintain momentum and develop an accountability framework to back up any new commitments, and to agree how this programme can support such activities (September 2017)
Ongoing: Work has been undertaken through the FP technical working group. Senior leadership involvement from MoH has been limited and as such, new commitments including commitment to increase government allocation to FP commodities have not been implicit in the 2018 Health Sector Budget.  Overall, RH line item in the health sector budget has reduced from 2017 level.    During the Annual Consultative Meeting with Partners in March 2018, the government committed to allocating more funds to RH commodities procurement.  This was reiterated in the Health CPs meeting with MoH.  DFID and FP TWG will need to monitor to ensure that the promised increases in RH funding are commensurate with commitments made during the FP2020 second meeting in London.
1. DFID and Abt to agree a new VFM framework to better capture VfM along the results chain (September 2017).Done
2. DFID and Abt to further analyse administration and management costs and agree a plan to reduce this as a proportion of spend in the 2016/17 financial year (September 2017). Ongoing, administration and management fee reduced.
3. Further embed VfM in regular programme monitoring with quarterly reporting by the Abt team on the VfM matrix to begin in October 2017. Done