UK AID LOGO TO BE ADDED TOP RIGHT

Annual Review of DFID’s Support to the Kyrgyz Republic Health SWAp

Adrienne Chattoe-Brown

October 2011

Contents

# Acronyms
AIDS	Acquired immune deficiency syndrome
AR	Annual review
ARV	Antiretroviral drugs
CARHAP	Central Asia Regional HIV/AIDS Project
CDC	Centre for Disease Control
DFID	UK Department for International Development
DP	Development Partner
DS	Den Sooluk
EMOC	Emergency Obstetric Care
HIV	Human immunodeficiency virus
IMCI	Integrated management of childhood illnesses
JANS	Joint Assessment of National Strategy
JAR	Joint Annual review
KfW	Kreditanstalt für Wiederaufbau (German Development Bank)
KR	Kyrgyz Republic
M&E	Monitoring and evaluation
MDG	Millennium development goal
MDR	Multi-Drug Resistant
MHIF	Mandatory Health Insurance Fund
MICS	Multi indicator cluster survey
MoF	Ministry of Finance
MoH	Ministry of Health
MSM	Men who have sex with men
MT	Manas Taalimi
NGO	Non governmental organisation
PEPC	Promotion of Effective Perinatal Care
PHC	Primary Health Care
PLHIV	People living with HIV
RBF	Results based funding
RMIC	Republican Medical Information Centre
SDC	Swiss Agency for Development and Cooperation
SGBP	State Guaranteed Benefit Package
SIDA	Swedish International Development Agency
STD	Sexually transmitted diseases
SWAp	Sector-Wide Approach
TB	Tuberculosis
UN	United Nations
UNICEF	United Nations International Children's Fund
USAID	United States Agency for International Development
VCT	Voluntary counselling and testing
VHC	Village Health Committees
WB	World Bank

# Introduction
## This mission
The purpose of this mission was to undertake an Annual Review (AR) of DFID’s support to the Kyrgyz Republic Health SWAp. Terms of Reference are at Annex 1.

The consultant visited Kyrgyz Republic from 7th to 15th October. The purpose of the mission was to undertake an Annual Review of the Kyrgyz Health SWAp, assessing the extent to which the goal and purpose have been achieved through the planned outputs.

The specific tasks for the mission were to:

- Participate in the multi-donor/government health SWAp joint annual review and discuss progress directly with Development Partners, Joint Financiers, the Kyrgyz Government and Civil Society;
- Assess progress in achieving the outputs and purpose specifically improved health status especially maternal and child health and progress towards the MDG priorities;
- Assess progress of the UNICEF nutrition programme implementation;
- Assess progress of WB/DFID Result Based Funding programme pilot
- Assess progress towards finalising the new Health Strategy ‘Den Sooluk’ for 2012-2016 including the indicative plan of work, implementation arrangements and costing for Den Sooluk proposed by MoH; the monitoring framework; and the fiduciary risk assessment.

The consultant attended the 1 week Joint Annual Review during which side conversations and meetings of various lengths were conducted with WB, SDC, KFW, UNICEF, USAID and the Global Fund consultant, and members of Ministry of Health. There was also a pre-briefing and debrief with DFID. Due to a programme change the consultant was also able to join a field visit to some of the CARHAP funded NGOs which gave a useful insight into the health status of some of the most vulnerable members of the population, and the health systems barriers they face.

An annual review report for 2010 using DFID’s AR format has been completed and submitted separately. This addresses how the goal and purpose have been achieved through the planned outputs and gives some assessment of the project’s achievements against its log frame. Lessons learnt and recommendations for the final period of project implementation have also been identified. This short narrative report deals in more detail with the specific tasks above.
## DFID support to the health SWAp
DFID has been involved in the health sector in the Kyrgyz Republic since 1997. It has provided technical assistance to health reforms from 2000 – 2010 and since 2006 has also utilised the WB managed trust fund to channel un-earmarked sector budget support to MoH (via MoF) for the ‘Manas Taalimi’ (MT) Health Care Reform Programme 2006 – 2011. Other development partners using this route are WB, SDC and SIDA. KFW support goes direct to MoF, and other partners operate in parallel (USAID, UNICEF, GAVI, WHO and the Global Fund are the most significant).

DFID has provided £7m for the first five years of MT (2006-10), plus an additional £1m for the one year extension (2011) agreed between MoH and development partners. An additional £2m was approved for a further six months until July 2012 to act as bridging money for an anticipated funding gap whilst the next health strategy is being finalised. This includes £1m to be directed to UNICEF in support of scale up of the national nutrition programme.

Additional DFID funds are also being spent on a results based funding pilot supported by the WB multi-donor Health Results Innovation Trust Fund to which DFID has centrally pledged £114m.

DFID bilateral funding to the health sector (i.e. apart from the results based funding programme) will finish in July 2012. From about January to July the DFID inputs will be run from Dushanbe as the DFID Bishkek office is closing in March 2012.
# Progress in improving health status
The specific task of the consultant was to assess progress in improving health status, especially maternal and child health and progress towards the MDG priorities.

The relevant targets and the latest UN progress assessment are as follows:

Table 1 Progress against MDG targets
MDG target	UN assessment of progress
5.A. Reduce by three quarters, between 1990 and 2015, the maternal mortality ratio.	Off track (a)
4.A: Reduce by two-thirds, between 1990 and 2015, the under-five mortality rate.	Insufficient information
6A. Have halted by 2015 and begun to reverse the spread of HIV/AIDS	Possible to achieve if some changes are made (c)
6B. Achieve, by 2010, universal access to treatment for HIV/AIDS for all those who need it.	Not achieved (consultant’s assessment)
6C. Have halted by 2015 and begun to reverse the incidence of malaria and other major diseases (TB)	Possible to achieve if some changes are made (b)

Source: UN monitor, based on latest available data from the United Nations Statistics Division as follow: (a) 2005; (b) 2006; (c) 2007.
## Maternal mortality, child and infant mortality
Maternal, infant and child mortality are addressed in an integrated way in Manas Taalimi, and so are reported on together here. This section is an expansion of the comments made in the Annual Report, submitted separately.

### Progress in addressing maternal mortality

Table 2 Maternal Mortality Ratio per 100,000 live births (DFID goal indicator 2)
	2004	2005	2006	2007	2008	2009	2010 target	2010 / outturn
Maternal mortality	46.4	61.0	53.0	62.5	58.9	75.3	55.0	50.6

Source: Republican Medical Information Centre
Kyrgyzstan is not on track to meet the MDG target for maternal mortality. Although there has been a decline in the rate between 2009 and 2010 there continues to be an overall upward trend since the baseline of 46.4 in 2004. The scale of the apparent growth in maternal mortality may in part be due to problems with the official figures under representing the true situation in the early part of the period followed by more accurate reporting in 2009 and 2010. For example the MICS of 2006 stated a rate of 104 cases per live births[1], considerably higher than the official 53. Subsequent activities by MoH to improve detection and registration of maternal deaths and an end to penalising doctors who record maternal deaths, then led to an official figure of 75.3 in 2009 which may be more accurate as it is closer to survey estimates. The apparent major downturn in 2010 to 50.6 may be the result of improved categorisation, as it is highly unlikely that there was this enormous improvement in such a short period.
[1] Multiple indicator cluster survey, 2006.

In consequence it is difficult to assess, without further survey work, whether maternal health has significantly changed either way during Manas Taalimi. However it has been suggested that “there are encouraging indicators that are expected to improve mortality rates over time (Ministry of Health, 2008; Bhutta & Khan, 2009; Ibraimov et al., 2009). These include economic, social and cultural aspects and the state of the public health system, as well as the demographic structure and behaviour of the population.”[2]
[2] Ibraimova A, Akkazieva B, Ibraimov A, Manzhieva E, Rechel B. Kyrgyzstan: Health system review. Health Systems in Transition, 2011; 13(3):1–152. p8.

Regardless of the discrepancies in the figures, and even taking the best of them, maternal mortality is clearly a serious and persistent problem in Kyrgyzstan. In 2009 the main causes of maternal death were obstetric bleeding (52.3%), hypertensive disorders during pregnancy (22.4%), and septic complications (10.4%)[3]. These complications require prompt access to good quality obstetric services which are adequately equipped with drugs, antibiotics and transfusions, and which can perform caesarean sections and other surgical interventions. These skills and facilities are lacking at the level of primary hospitals with the result that maternal mortality is 1.5 – 2 times higher at this level[4]. The majority of pregnant women who die in childbirth do so without getting further up the system to better quality care. Moreover the rate of appropriate hospitalisation is poor (e.g. for women with hypertensive disorders it was recently reported to be 64.7%) so that many women who should be in hospital are not, and many of those who are admitted are there without appropriate indications.
[3] Republican Medical Information Centre 2010
[4] Maternal and Newborn Health in Chiu Province and Kyrgyzstan: assessment and implications for interventions. UNICEF, 2009

Poor maternal health has been exacerbated by the political unrest of 2010. Rapid assessments carried out then indicated a growing number of deaths at home, worsening access to essential medical services problems related to availability of basic food supplies.

### Progress in addressing infant and child mortality

Table 3 Infant and Child Mortality Rates (per 1,000 live births) (DFID goal indicators 1 and 2)
	2004	2005	2006	2007	2008	2009	2010 target (a)	2010 target
Infant mortality rate (infants under 1 year old per 1,000 live-births)	25.6	29.7 / (58)	29.2 / (38)	29.8 / (33)	27.1	25.0	0.6% annual decline from 2004 baseline	22.8
Mortality rate of children under 5 years old (per 1,000 live births)	31.8	35.2 / (45)	34.6 / (44)	36.6 / (42)	31.5	29.3	0.8% annual decline from 2004 baseline	26.3

Source: RMIC, and MICS (in brackets)
Note: (a) targets based on routine data.
The UN monitor assessment is that there is insufficient data to assess progress to the MDG target. Although both infant and child mortality rates show an improvement in 2010 on 2004 Manas Taalimi baselines, both figures have risen above the baseline in the interim. The later official figures are probably more reliable than those for maternal health as changes to the registration and categorisation system were last made in 2004 and 2005 and penalties for health workers in areas showing increased infant mortality rates were lifted in 2003. MICS figures are noted in brackets on the table above and show a narrowing of the discrepancy between them. However for both data sets, mortality indicators remain high, especially for boys. There has also been an increased mortality rate among infants at home or immediately after admission to hospital, suggesting a lack of funds of parents and / or health facilities to provide appropriate care for children.

Under-five child mortality in the perinatal period accounts for the majority of deaths (61% in 2006). Causes include respiratory diseases, congenital abnormalities, infectious diseases and parasites, and there are also links with undiagnosed problems during pregnancy, a lack of prenatal and post natal care, a lack of qualified staff and too few resuscitation services for newborn children.
### Manas Taalimi contribution to reducing maternal, child and infant mortality
Manas Taalimi has focussed on two main approaches to improving mother and child health: (a) improving access to health services through development and implementation of new legislation, expansion of the state guarantees benefit package, and structural adjustments to service delivery; (b) improving the quality of health services through the introduction and expansion of comprehensive programs and activities.

Access initiatives have included the following:

- Antenatal care and deliveries are now provided free of charge within the SGBP and the expanded Additional Drug Benefit Package. Also included in the ADBP are drugs recommended by the IMCI programme, and medications for children with micro-nutrient deficiencies.
- There have been improvements in the basic infrastructure of some maternity hospitals and more equipment has been provided.
- The national nutrition programme is being expanded.
- A Mother and Child Health Unit has been established in the Department of Health Care Organization in the MOH and a National MCH Centre has been set up.

Quality initiatives have included the following:

- IMCI has been implemented nationwide to address the primary causes of child death.
- Immunisation rates, whilst at 96.4% not quite meeting the 2010 target of 97%, do show high rates of coverage.
- At primary level there has been a focus on upgrading the skills of primary health care health personnel with regard to family planning, delivery management, timely detection of complications and appropriate referrals, and there has been an emphasis on improving the integration of child health services.
- The 2011 evaluation of MT reported that the WHO Making Pregnancy Safer/PEPC approach had been introduced in 60% of all obstetric health organizations and that 47% of all deliveries were taking place in health care facilities that have a certificate of a Child Friendly Hospital.
- Some clinical protocols are starting to be developed and implemented.

These initiatives have been supported by wider health system changes such as efforts to reduce the financial burden on the poor, some rationalisation of health infrastructure, reductions in informal payments, and adherence to the ‘SWAp rules’ which have retained levels of spending on health as a proportion of national state expenditure, and minimised deviation from the budget.
### Future challenges
Despite the efforts above, quality of care remains a major issue. Referral systems remain poor for both pregnant mothers and children so that serious conditions are not treated swiftly enough. EMOC services still need to be scaled up nationwide, and failure to implement standard protocols means that life saving, cost effective interventions are being missed. A UNICEF assessment carried out in 2009 recommended, among other things, an expansion of the ante-natal package to include calcium supplementation (to reduce the risk of high blood pressure and pre-eclampsia), improved oxytocic use with clear criteria for referral of patients, and use of magnesium sulphate at primary level (to prevent and manage pre-eclampsia). The current draft of Den Sooluk (Sept 12th 2011) addresses these issues in broad terms, but without more detailed plans it is difficult to establish the possible rate of expansion of interventions.

## Communicable diseases
### Progress in addressing TB

Table 4 TB incidence rate per 100,000 general population (excluding prison population)
	2004	2005	2006	2007	2008	2009	2010 target	2010 outturn
Tuberculosis morbidity rate	113.6	115.7	110.9	108.8	101.6	100.9	103.2	97.4

Source: RMIC

The TB incidence rate since 2004 shows some improvement, but the level remains higher than the threshold set by WHO for a high-level epidemic. Again these official figures would seem to be inaccurate: in 2009, WHO estimated that the incidence of TB (all forms) was 160/100,000[5]. Within these figures, there is a high and growing rate of multi-drug resistant (MDR) TB among new and re-treatment cases in the country. Efforts have been made since 2010 to collect more accurate data about this as that available is known to be unreliable.
[5] Report of the monitoring visit to Kyrgyzstan on behalf of the Green Light Committee, July 2011, p15

The conclusion of the partners annual joint review mission in June of this year was that the growth of MDR TB was an indication that the TB programme as a whole is not working. This was attributed not only to factors outside the control of the programme such as poverty and the living and working conditions of illegal migrants, but also to “insufficient stewardship and ineffective overall management of personnel, infection control, equipment maintenance, transportation and communication”. The health system barriers were identified as financing issues (such as exclusion of prisoners from the MHIF, informal payments and low salaries); ineffective service delivery and a lack of multi-sector and integrated approaches especially for prisoners; a shortage of resources; and fragmented public health services.
### Manas Taalimi contribution to addressing TB
Despite the problems above, under Manas Taalimi progress has been made including: some integration of the vertical TB service with the general health service; an uninterrupted drug supply which has been funded by KFW, World Bank, and Global Fund; expanded detection of MDR TB; capacity building through provision of equipment and training; some improvement in coordination between the civil and prison health services; and improvements in detection and tracking.
### Future challenges
Major challenges that will need to be addressed under Den Sooluk include improved stewardship; integration of TB services into SGBP/MHIF with appropriate levels of funding; greater integration of services both across sectors (civil and prison) and within the health sector itself; and upgrading care standards and more effective fostering of adherence to treatment. The challenge of MRD TB also means that MoH and the national TB programme will have to make greater efforts to curtail access to first and second line drugs in pharmacies and improve infection control in all TB facilities. A recent report on behalf of the Green Light Committee identified these as areas where little progress had been made but where the need for action was urgent.
### Progress in addressing HIV

	2004	2005	2006	2007	2008	2009
Newly registered HIV cases	153	165	233	388	532	671

Table 5 Newly registered HIV cases, 2004 - 2009
Source: RMIC, cited in Evaluation of Manas Taalimi, April 2011

The Kyrgyz Republic is showing signs of the HIV epidemic moving from a concentrated stage of high prevalence among the high risk population (prisoners, injecting drug users, sex workers) to a more generalised spread among the wider population. The infection is increasingly sexually transmitted, creating a bridge from one population to another, with high rates of STDs contributing to this. Although the incidence of syphilis in the general population has fallen since 2005 (40.4 per 100,000 to 22.2 per 100,000 in 2008) less than 60% of cases are estimated to be registered, and risky sexual behaviours persist. Similarly, risky behaviour among injecting drug users continues so that despite prevention efforts, it is the most common route for transmission. Prisons have emerged as a major site for transmission, because of high rates of drug use.

While most people living with HIV are male, the proportion of infected women is growing. Whereas in 2001 they accounted for 9.5% of PLHIV, in 2009 this has risen to 26%. This has clear implications for maternal and child health and presents particular challenges to service delivery. There is an increase in mother to child transmission and on 1st January 2010 95 pregnant women were living with HIV and 23 children born to HIV+ mothers were diagnosed with the infection.
### Manas Taalimi contribution to addressing HIV
Manas Taalimi has supported a number of interventions. These include improvements in the infrastructure of some laboratories and undertaking epidemiological and HIV sentinel surveillance among vulnerable groups. All pregnant women now have to be tested for HIV (with informed consent), and ARVs are being provided to most of those in need. In 2010 84% of pregnant women were counselled and tested (meeting the target of 80%), and 88% of those infected received ARVs (again meeting the target). 2010 indicators also show improved coverage of adults and children with advanced HIV infection receiving HAART (83.4%) and continuation rates (82% of adults and children with HIV-infection continue to receive ARVT for longer than 12 months). However services for PLHIV still need further development. Also a key high risk group, prisoners, are still very poorly protected whilst they are incarcerated, and once they have been released there is limited continuity of care.

The impact of MT on behaviour change among high risk populations has been more limited. Although harm reduction programmes have expanded (e.g. to include needle exchange points and methadone substitution therapy), use of sterile needles among drug users and condoms among MSM has not reached 2010 targets.

Institutionalisation of appropriate HIV testing and care has made some progress in terms of staff training and development of protocols, but case detection of AIDS as a percentage of PLHIV suggests that HIV is being diagnosed late. Service delivery capacity and geographic distribution are also poor. Although there have been efforts made to learn from the HIV outbreak through intra-hospital transmission in children’s hospitals in Osh oblast in 2007, infection prevention and control measures still remain inadequate.
### Future challenges
Despite the signs of change from a concentrated pattern of HIV infection to a more generalised one, it will still be essential for interventions under Den Sooluk to tackle the needs of the high risk groups, making harm reduction more accessible and more cost effective. Coordination between MoH, the CCM and the non-governmental sector in HIV prevention has been lacking. This will need to improve so that the needs of these hard to reach groups can be effectively addressed by the most appropriate stakeholder. Attitudes of health workers towards most at risk populations will also need to change as they are a barrier for these groups to seek VCT, treatment and care. Laboratory services still need further attention in terms of availability and quality. Monitoring and evaluation of the programme could be made more effective so that there is a greater use of up to date and accurate data to inform programme direction and implementation.
# Progress of the UNICEF nutrition programme implementation
## Outline of the programme
Poor nutrition in Kyrgyzstan among women and young children makes a contribution to high mortality rates, as well as morbidity. In 2010 44% of deliveries were complicated by anaemia in the mother, leading to greater risk of maternal death. 22% of children under 5 who die do so because they are undernourished. Latest available figures from 2006 suggest that 14% of children were stunted, and in three provinces this extended to more than 20% of the under five population. However stunting can be treated and even reversed through improvement in nutrition, brought about by a combination of behaviour change and strengthening and scale up of existing programmes.

To this end DFID has agreed to earmark £1 million of the additional £2m SWAp funds approved in 2010, to contribute to the scale up of the national nutrition programme led by MoH and supported by UNICEF, WB, Swiss Red Cross and the Soros Foundation. The scaled up national programme has also been informed by a pilot in Talas province on micronutrient supplementation which showed a 26% reduction in anaemia among children 6-24 months in one year. The scaled up programme will provide ‘sprinkles’, a micronutrient supplement branded as Gulazyk, to all children 6-24 months old, and include national training of health care providers including health promotion specialists at PHC level. They in turn will support new and existing Village Health Committees to inform and educate mothers about Gulazyk in addition to diet during pregnancy, exclusive breastfeeding, and improved complementary feeding. Early childhood development activities will be incorporated into the communications materials as these proved very popular in the Talas pilot and are expected, in line with past research, to demonstrate an additive effect on cognitive development and long term productivity.
## Progress of implementation
A baseline survey was carried out in 2009 with the help of CDC; results are expected very shortly. Implementation has begun in Issyk Kul, Batken and Chuy provinces. DFID funds will support the procurement of Gulazyk, the expansion of VHCs and thereby the full package of nutritional services in under served provinces (Osh and Jalal Abad) and the continuation of the programme in Talas province.

At the time of meeting with UNICEF to discuss progress however, funds had not yet been released from the World Bank because a new administrative agreement had to be reached between WB and MoH. An exchange of letters was expected imminently which would allow funds to flow and DFID funded activities to commence. The funds are unlikely to be available in time for international procurement of Gulazyk, but UNICEF will advance their own resources until DFID’s become available.
# Progress of WB/DFID result based funding programme pilot
## Outline of the programme pilot
The purpose of the pilot is to improve the quality of maternal and child health care outcomes in the KR through a pay for performance mechanism for rayon level maternity hospitals and eventually primary health care facilities. This is in response to ongoing problems with widespread poor quality of care which is a key barrier to better health outcomes for these target groups (see above). The rationale is that quality of care can be improved through the use of incentives to health providers; the incentives will be set so that both individuals and their institutions will benefit from achievement of higher quality standards. Assessment will be done on a peer to peer basis so that those participating both assess other facilities and are themselves assessed. Design is based on lessons learned from a similar initiative in Rwanda and other RBF pilots in Latin America, Africa and South East Asia. The initial proposal included Village Health Committees but these were dropped as they made the programme too complicated.

The pilot is based on a research approach with three groups that will participate in different ways: (i) intensive monitoring plus performance-based payments; (ii) intensive monitoring alone; and (iii) a control group which will have neither. There will be approximately 20 hospitals in each group. A baseline will be set at the beginning of the three years, and an impact evaluation after the first year will inform full roll out to all participating oblasts.

The pay for performance mechanisms to be used by the pilot will be added on top of the existing established and well functioning provider payment system which matches SGBP services with corresponding financial and information systems. The following facility spending rules have been agreed:

- 15% must go towards a staff performance-based bonus system, which is not a salary top-up but rather a quarterly lump sum payment given to top performers who contributed most to the achievement of results in the preceding quarter, as appraised by facility management using the labour participation passport;
- Up to 40% of total facility performance payment can be used for rehabilitation;
- At least 5% of total facility performance payment should be allocated to training;
- Performance-based payments cannot be used to pay for arrears, utilities, or procurement of vehicles (negative list).

Funding to the pilot ($10m + 1m for evaluation) comes through the World Bank’s multi-donor Health Results Innovation Trust Fund to which DFID has centrally pledged £114m.
## Progress of implementation
The pilot programme was due to start in 2010 but was delayed by political events. Since then discussions around detailed implementation issues have continued between WB and MoH but commencement is now delayed by the WB 2009 SWAp audit which is still outstanding. This is expected to be completed by the end of 2011, and then the RBF grant can be finalised. The pre-pilot should then start in January 2012 which suggests that completion will be due in October 2014.

During pre-appraisal in June 2011 WB and MoH agreed on implementation issues around: size & structure of performance-based payments, institutional responsibilities, financial management and funds flow, and procurement

As of mid October outstanding issues still to be to agreed with MoH included:

- The location of the secretariat – either in MoH or MHIF
- The final choice of the pre-pilot hospitals. WB and MHIF have given their feedback on the MoH shortlist of two and a final decision is expected soon.
- Whether MoH staff involved in peer evaluation and procurement for the pilot should also benefit from incentive payments.
- The balanced scorecard is also being finalised and the Working Group is drafting a user manual
- Terms of reference for the four key TA positions: (i) RBF Manager; (ii) MCH Technical Lead; (iii) RBF Technical Lead and (iv) M&E Specialist.

MoH has requested that six “regional” oblast-level hospitals, be included in the pilot. There are insufficient funds for this and the Bank is exploring the possibility of additional funding from the Health Results Based Financing Innovation Trust Fund, or failing that from alternative sources.
# Progress towards finalising the new health strategy
## Background to the current strategy
The new Health Strategy ‘Den Sooluk’, is now expected to start around May 2012 and to run until 2016. MoH started developing the strategy in June 2010, supported by WHO. Six experts, competitively selected, supported working groups which analysed Manas Taalimi, set the agenda for Den Sooluk and took the views of some health care providers, members of civil society and other stakeholders. Development partners had the opportunity to comment on various versions until the JAR in May 2011 when the version presented had “significant departures in its objectives, structure, and content from the previously seen and discussed versions”[6]. Significant omissions included the previous orientation to measurable and achievable results, and identification and removal of key health system barriers that have undermined previous programme implementation. Wider consultation on this version had also been more limited. At the request of representatives of parliament who attended the JAR, and Development Partners, MoH agreed to return to the earlier version and submit another draft by the end of July. The Minister of Health also committed to conducting a Parliamentary Roundtable in September and agreed that the MOH would work on the monitoring framework, a five-year indicative plan of work, and costing to be presented at the October Joint Annual Review.
[6] Joint Summary Note Kyrgyz Health SWAp Joint Annual Review, May 30-June 4, 2011, p3.

Just before the October JAR, a Joint Assessment of the new Den Sooluk draft was carried out in line with the Joint Assessment of National Strategies approach designed by International Health Partnership and related initiatives. This was a very useful exercise for the JAR participants as it enabled a degree of scrutiny that may otherwise not have been possible.
## Current status of Den Sooluk
### Assessment of the current strategy
The consultant was not able to review earlier versions of the Den Sooluk strategy document (including the problematic one of May), but understands from other DPs that the current version (12th Sept 2011) is a progression of the earlier, more acceptable one. The document provides a summary assessment of MT, outlines the lessons learnt and the unfinished agenda that should be picked up by DS and makes some brief statements on ‘mission, principles, strategic approach, and political commitment’. The remainder of the document is split roughly 50/50 between section 3: ‘expected results and core services for priority health programmes’ (cardiovascular diseases, maternal and new born health, child health, TB and HIV), and section 4: ‘overcoming systemic barriers through strengthening all functions of the health system’ (grouped under public health, provision of individual medical services, financing, stewardship and resources for the health care system[7]). There is also a very brief section on M&E.
[7] i.e. HR, pharmaceuticals, information and modern technologies

At the time of the JANS the planned on the monitoring framework, the five-year indicative plan of work, and costing of the whole package had not progress as far as expected so they could not be reviewed by the team. Based on the material that it had however the JANS, concluded that Den Sooluk is essentially a sound strategy but with some missing elements, especially around financial management. Also the proposal to increase provider autonomy had not been matched with a re-balancing of oversight and management capacity. The JAR recommended that further work be done especially on implementation arrangements around the plan of work and strengthening institutional set up and tools

The JANS exercise was however generally very helpful as it gave a systemic assessment of DS and concrete recommendations on how to progress it. The exercise is to be revisited when MoH has made various adjustments to implementation arrangements etc and when the team has had the opportunity to review the material presented at the JAR, the report will be finalised.

Comment by consultant:
 In terms of the content of DS, whilst the priority programme elements of Den Sooluk are important, they are still being considered too much in isolation from the health systems issues. Whilst health systems barriers have been identified for each core programme and drawn together at the end they are not prioritised or linked with each other, and there is insufficient analysis of how common fundamental barriers might be addressed. It is therefore not clear why these efforts should be more successful than previous ones. In general Den Sooluk is weak on identifying priority areas and strategising on how they might be addressed. It is also not clear where strategic leadership of the sector sits at levels below the Minister.

Some key issues arising out of MT are mentioned in DS but not given the strategic priority that could be expected. These include ensuring financial protection and access in the face of fast growing out of pocket expenditures (including informal user fees), achieving further efficiency gains in light of the persistent funding gap in the SGBP, addressing the remaining irrational distribution and management of infrastructure in large urban areas and the unfinished agenda on hospital autonomy and the role of MoH.

### Costing Den Sooluk
Progress in the costing of DS has been limited. The costing is expressed in two ways. The ‘micro costing’ is essentially that part of the donor contribution (25% in MT) which is not spent on the SGBP (50%) or procurement (25%); it is mostly used for training, workshops, capacity building etc. The ‘macro costing’ appears to be the overall resource envelope. So far MoH has carried out a micro costing exercise supported by USAID which attached budgets to each of the general activities (or rather broad work areas) listed in DS under ‘core programmes’ or ‘health systems barriers’. This was reported to cover the full five years of DS. A WB consultant had made an initial attempt at projecting the government contribution to the sector as a whole, but had not been able to get indicative funding amounts from the development partners so was not able to assess the overall resource envelope. His findings were presented to the JAR and helped to focus on the need for efficiency savings. The final statement by the DPs emphasised the need to further rationalize hospital network including specialty hospitals and Bishkek; focus on and invest in a further shift to PHC; continue provider autonomy; and adopt a multi-faceted approach to pharmaceuticals including pricing, rational drug use, etc.

Comments by consultant:
In general there is a lack of strategic economic analysis of Den Sooluk. There was no suggestion by the government that their budget details for the health sector should become available for scrutiny, nor did the Development Partners push for this. As a result the current financing landscape of Den Sooluk is of great detail in one small corner of a largely uncharted wilderness. Progress under Manas Taalimi in some key programme outcomes and outputs around reduced financial burden for the poorest, increased efficiency, and equalisation of resources were not addressed at any strategic level in the JAR. Nor does the current draft of Den Sooluk commit itself to concrete progress indicators in these areas as the monitoring framework is not yet ready. The final statement by the DPs did however state that budget targets will remain important during Den Sooluk, namely that health expenditures as % of total government budget should not decline; budget execution should remain no less than 95%; and a proposed new rule that non-salary expenditures should not decline. This last is a response to the increase in public sector salaries announced in 2010. The DPs also emphasized that the revised costing of Den Sooluk should reflect local as well as expected external resources, principles for prioritization should be made clear, and there should be prioritization of capital investment.

The DPs should seek further detail on the MoH budget than is available at the moment, although it is unlikely to be structured in a way which is easy for in-depth analysis of different areas of DS. DPs should also encourage greater consistency and transparency in the budget figures that are presented by MoH. Those presented in the JAR were difficult to understand as some tables had not been translated and some figures were inconsistent. This did not help the quality of the discussion around this important issue. The lack of financial information for the JANS exercise also undermined its ability to provide adequate analysis.

Remarks by some government officials give rise to questions about the perceived scope of DS. Most development partners seem to think of DS being synonymous with whole of the health sector, i.e. the overall budget for DS is that of the health sector, to which Kyrgyz Republic contributes the greater part. Statements by some KR officials rather suggested that they saw as DS being essentially a DP funded exercise which had some intersections with the wider health sector. These individuals were in the minority, but at least one is prominent enough to influence implementation.

The micro-costing exercise may have been positively unhelpful. Ideally DS needs more work as a strategy document, there then needs to be a good deal more work on elaborating the different sub-strategies, and there needs to be a better grasp of the overall resource envelope and there also needs to be agreement between DPs and MoH on the proportions of the budget to be assigned to these activities, procurement and SGBP, before the details of the micro-costing are finalised. Meanwhile a degree of ownership has been generated for this corner of the budget which may not be realised.

### Fiduciary risks
Both MoH (with MoF) and WB presented their assessment of fiduciary risks. This was supplemented by a review of the 2011 procurement plan by a consultant. The two assessments were broadly similar in terms of the areas covered: low staff capacities exacerbated by high turnover especially in procurement, lack of alignment between the procurement plan and the financing plan so that DP disbursements were not based on need, and weaknesses in transparency and accountability. An ongoing concern is the delay in carrying out the 2010 audit which was brought about by contractual disputes between WB and the international auditor. This was expected to start shortly and for the field work to be completed by the end of 2011.

Comment by consultant:
Leadership of the fiduciary risk assessment by WB gives confidence in the exercise. Much remains to be done in this area, but the impression gained is that some improvements have been made and will continue. However fundamental issues of how to retain trained staff are not being addressed by MoH adequately. Also follow up of MoH’s audit plan by WB is weak; more proactive engagement needs to be encouraged by other DPs.

### Implementation arrangements
The indicative five year plans of work (POW) need more development. It was proposed by DPs that a detailed Year 1 POW and procurement plan be developed by the end of October and plans for the full five years be reviewed at the May 2012 JAR.

An outline approach to monitoring and evaluation was given in the JAR, which emphasised a new approach in strengthening the role and capacity in M&E at the levels of the oblasts and the tertiary health organizations. This package of indicators will be supplemented by the coverage studies, health systems studies, and large scale surveys which have proved most valuable under MT. DPs generally considered that this was sound and appropriate. However funding to M&E will need further discussion as it was generally agreed that it was better supported through parallel financing at this stage because this reduced uncertainty around procurement through government systems which would occur if government funds / pooled budget support funds were used. Costs are due to be discussed at the ‘mini JAR’ proposed for November. At this stage no indicators have been formulated; these are due to be developed by 30 November.
### Next steps
With regard to next steps it was proposed by DPs that the DS strategy documents be finalised, based on the JAR dialogue, by the end of November so that government approval can be given by the end of the year. A World Bank fiduciary risk assessment is expected to take place around December of this year. GFATM and GAVI may also join this exercise. Meanwhile a consultant is preparing a joint statement and MoU for consideration by government and partners; this is due to be done by the end of November. DPs will also continue their considerations around possible future financing modalities. The recommendation from the consultant is for direct pooled financing to Kyrgyz Treasury, provided the necessary conditions are put in place to manage the risks involved. New funding will take a while to put into place but delays in disbursements and a new Joint Statement will enable unspent funds to roll over into 2012. DFID additional SWAp funds will help to ensure that there are no financing gaps.

# Annex 1: Terms of Reference

Terms of Reference for the Annual Review of Kyrgyz Republic Health Sector Wide Approach (SWAp) October 2011

Objective
The Objective is to undertake an Annual Review (AR) of our support to the Kyrgyz Republic Health SWAp

The Recipient
The work is primarily for DFID use. However, we will share the findings with Ministry of Health and multi-donor partners.

Scope
To undertake an Annual Review of the Kyrgyz Health SWAp, assessing the extent to which the goal and purpose have been achieved through the planned outputs. This will involve evaluating the project’s achievements against its log frame and identifying lessons learnt and recommendations for the final period of project implementation.

The specific tasks will be to:
- undertake a 2 day desk-based review of relevant materials to get familiar with the Kyrgyz Health SWAp programme prior to arrival in country;
- participate in the Multi– Donor/Government Health SWAp Joint Annual Review (JAR) and discuss progress directly with Development Partners, Joint Financiers, the Kyrgyz Government and Civil Society
- assess progress in achieving the outputs and purpose specifically improved health status especially maternal and child health and progress towards the MDG priorities:
- assess progress of the UNICEF nutrition programme implementation;
- assess progress of WB/DFID Result Based Funding programme pilot
- assess progress towards finalising the new Health Strategy ‘Den Sooluk’ for 2012-2016 including the indicative plan of work, implementation arrangements and costing for Den Sooluk proposed by MoH; the monitoring framework; and the fiduciary risk assessment.

 Methodology
The work will be undertaken through a mixture of desk and fieldwork. DFID will make available to the consultant a range of recent materials and contacts.

The consultant should seek to gather information from a wide range of interlocutors including other donors; key government officials and CSOs.

 Deliverables
A Short narrative report (up to 15 pages) summarising the main findings, impact, success stories, innovations and lessons learned and a Completed DFID Annual Review Report using DFID’s AAR format.

Timeframe
The consultant will travel to Bishkek in October to participate in the Multi-Donor/Government Joint Annual Review (dates to be confirmed)

The first draft of the short narrative report and the DFID ARR form submitted to DFID Kyrgyz Republic within 2 weeks of completing the country visit.

Any revisions incorporated and the final narrative report and AAR form submitted within 1 week of receiving the comments from DFID.

The final reports expected on or before 15th November 2011.

Reporting
The consultant will report to the DFID Kyrgyz Head of Office in Bishkek and the DFID programme manager for health.

Background
At independence, the Kyrgyz Republic inherited a centrally planned health system with a vast infrastructure of hospitals and clinics. There was good access to health services, but the system was unaffordable without the heavy subsidies from Moscow. Reacting to these difficulties, the government began a series of reforms aimed at a) improving the efficiency of the health sector; and b) establishing the government as a policy maker rather than an implementer of policies made in Moscow.
The Ministry of Health (MoH) and donors have worked together in a highly successful Sector Wide Approach (SWAp) since 1995. There have been many achievements to date in financial protection, equity, and efficiency. Many difficult health reforms have been undertaken. These include increasing the national allocation to health; establishing a completely new primary health care sector; rationalising the infrastructure; introducing both a State Guaranteed Benefit Package (SGBP) and a Mandatory Health Insurance (MHI) with a flat payroll tax of 2% deducted from salaries.
The current health strategy, referred to as the ‘Manas Taalimi’ Health Care Reform Programme, was developed during 2005 by a team led by MoH. The strategy aims to improve the health of the population, continue the ambitious previous programme of health reforms, and to reduce the financial barriers in accessing health services, particularly for the poor and socially vulnerable. It builds on the achievements of an earlier Kyrgyz health sector reform project, which won the World Bank Independent Evaluation Group’s (IEG) prestigious Project Award in 2009.
Donors supported the previous health strategy in a very coherent fashion and transited to a formal SWAp in support of the current one. In addition, to the World Bank and DFID, the Swiss Development Corporation (SDC), KFW (both of whom also provide parallel funding) and Swedish Aid jointly pool their funding to the SWAp. USAID provides separate parallel financing but its projects are very well integrated. Support through the SWAp accounted for 11.6% of total government health budget over the period of 2006-2009.
Despite the success of the SWAp, under nutrition, is a major public health problem in the Kyrgyz Republic causing preventable deaths of mothers and children and delaying the physical and cognitive development of girls and boys, sometimes beyond repair. Despite improvements since the 1990s, 22% of all deaths of under-fives in the country are still caused by under-nutrition. In 2006, some 14% of children in the age group were stunted, with stunting rates in three provinces of over 20 per cent. Nutrition is a key priority for MoH and efforts are underway to fast track the up scaling of much needed support to nutrition
Monitoring and Evaluation
There is a robust monitoring framework built into the design with joint government and partner reviews (JARs) twice a year. The JARs are well organised and managed by government.
All SWAp donors use the ‘Manas Taalimi’ Health Reform Programme indicator framework for monitoring progress. This is updated twice a year by MoH in consultation with partners as part of the JAR process (last updated June 2011).

Disclaimer

The DFID Human Development Resource Centre (HDRC) provides technical assistance and information to the British Government’s Department for International Development (DFID) and its partners in support of pro-poor programmes in education and health including nutrition and AIDS. The HDRC services are provided by three organisations: HLSP, Cambridge Education (both part of Mott MacDonald Group) and the Institute of Development Studies.

This document is issued for the party which commissioned it and for specific purposes connected with the captioned project only. It should not be relied upon by any other party or used for any other purpose.
We accept no responsibility for the consequences of this document being relied upon by any other party, or being used for any other purpose, or containing any error or omission which is due to an error or omission in data supplied to us by other parties.