# Executive Summary
This report presents the findings of the Mid-Term Evaluation (MTE) of the DFID Responsible Accountable and Transparent Enterprise (RATE) programme. RATE is a five-year, £27 million, programme which aims to improve the safety and well-being of poor women and men affected by business in developing and middle-income countries. It provides support to twelve responsible business initiatives (RBIs) which work to improve the way in which businesses manage and account for the social and environmental implications of their actions. RATE started in August 2014 and will end in March 2019 (2.1-5)[1].
[1] Figures in brackets refer to the relevant sections in the report.
List of current RATE grantees
The ISEAL Alliance (ISEAL)
Global Reporting Initiative (GRI)
UN Global Compact (UNGC)
Ethical Trading Initiative (ETI)
B-Lab
Shift
ShareAction
Fairtrade
UN Foundation - World Benchmarking Alliance
UK National Contact Point (NCP) for the OECD Guidelines for Multinational Enterprises
Humanity United
British Academy

The main causal steps in the Theory of Change (TOC) are that RATE funding strengthens and scales up the RBIs, which deploy a variety of influencing strategies to build corporate capacity. This leads to changes in corporate behaviours, particularly those that have positive impacts on poor workers, communities and the environment in developing and middle-income countries (3.1-3).
Evaluation methodology
1. The MTE covers the period up to October 2017 and eight of the twelve RBIs. The three most recent grants, and the UK National Contact Point, were not reviewed. The main objectives of the MTE are to assess programme progress and to identify key lessons to date (4.1-4).
2. The methodology is outlined in Section 4 with additional details in Annex 2. The evaluation analyses the evidence available against each of the evaluation questions in the Evaluation Framework (Annex 3), including evidence on the TOC and impact pathways where available. A simple scoring system has been used for each of the main evaluation questions (4.5-8).
3. The general evidence base for responsible business is limited. Most of the RATE-supported RBIs are at an early stage of their DFID funding and therefore have limited evidence. This assessment recognises both that the programme is at the mid-term stage, and that half of the initiatives funded are relatively new. Three main evidence streams have been used for this report:

(a) RATE RBI organisational analyses - which themselves draw upon RATE partner data, interviews, workshops, and relevant literature and statistics, and which were analysed against partner logframes and theories of change - discussed and agreed with RATE partners (4.9-17);
(b) Wider evidence in the secondary literature on RATE RBIs, non-RATE RBIs, and responsible business in general relevant to the programme theory of change (including comprehensive reviews of secondary evidence on corporate reporting and product standards);
(c) a sector study of the ready-made garment industry in Bangalore.
The RATE logical framework has been assessed using RATE RBI M&E data for the output and outcome indicators, and secondary data for the impact indicators. An assessment against all the indicators in the logical framework is contained in Annex 7.
Context
Some aspects of the operating context for RATE RBIs and for responsible business are becoming more supportive, with greater incentives for some types of companies to address social and environmental issues. However, there are still some major barriers to responsible business behaviour, and significant incentives for irresponsible business. There also are important social, political and economic uncertainties that could have significant implications for RBIs, responsible business, and outcomes for poor people (5.1-4).
Relevance and targeting
1. All the initiatives funded under the RATE programme are highly relevant to the challenges of responsible business, and to DFID policies (6.2 & 6.5). However, while all the RBIs supported are generally relevant to the problems faced by poor people affected by business in developing and emerging economies, most are not well targeted at workers in global supply chains, or poor communities affected by business (6.3 & 6.10). Most of the RATE grants have a relatively undifferentiated approach regarding women and disadvantaged socio-economic groups (6.11).
2. Positive membership trends, and uptake of the tools and guidance by companies, suggest that RATE-supported initiatives are relevant to some businesses, even though coverage and reach may be limited (6.4). RATE is working with appropriate RBIs and companies. It is more difficult to assess whether RATE is working with the most appropriate RBIs and companies. RATE does not target small and medium enterprises (SMEs) which make up the bulk of business activity (6.7-9).
Outputs
Output-level performance of the RATE programme, and of all the constituent initiatives except the UK NCP, is on or above target for most of the indicators in the revised RATE logical framework (7.2-7.8). The programme is above-target for two of the three indicators relating to business outreach and networks. It is on target for around half of the indicators relating to improved standards, guidance, tools, reporting systems and innovation. It is on target to meet two of the three indicators for impact evidence.

Outcomes

Building the capacity of business (the short-term outcome in the Theory of Change) is a significant component of all the RBIs supported by RATE, but it is too early to assess this for most of the RBIs (8.9-12). In terms of uptake (the medium-term outcome in the Theory of Change), evidence suggests that there has been increased uptake of the tools, guidance and standards recorded by some RATE-supported RBIs (8.13-14). At present, the available evidence on business behaviour change (the longer-term outcome in the TOC) resulting from RBIs is limited. Collecting and reporting on this evidence needs to be a RATE priority in the future (8.15-20).

Progress against the outcome indicators in the logical framework has been positive for the two of the three indicators for which data is currently available (8.2-8). However, overall outcome achievement is rated as uncertain due to the limited evidence currently available from the RATE-supported RBIs on business behaviour change, and the lack of data on two of the five outcome indicators in the logical framework. Additional evidence from the latter part of the programme should allow a more definitive assessment in the final evaluation.
Impact
1. Likely impact achievement is rated as uncertain due to the limited evidence currently available. It would be unrealistic to expect impacts at this stage in the programme, and arguably unrealistic to expect such impacts to be easily identified and attributable even in the longer term. While there are some improving trends in the impact indicators tracked in the logical framework, the scale of negative business-related impacts remains substantial (9.2-5). Certain contextual trends are positive, and there is a definite increase in the attention given by some businesses to social and environmental issues. However, the balance of the evidence relevant to the Theory of Change from all three evidence streams suggests that achieving positive impacts for poor women and men is likely to remain challenging (9.16). Likely impacts by gender and social group are uncertain (9.14).
2. The RATE portfolio comprises a range of RBIs employing diverse strategies to engage and influence companies. Most of the influencing strategies supported by RATE are led by intermediary organisations with global remits which rely upon their influence ‘trickling down’ through complex and extended global value chains to subsidiaries, suppliers and producers (9.7-8).
3. It is not yet possible, based on the available evidence from RATE and non-RATE sources, to determine the relative effectiveness of all the different impact pathways (9.9), or to judge the overall validity of the Theory of Change for RATE (9.17). Despite the rapid growth in corporate reporting, there is limited evidence on its quality and impact (9.11). The impact evidence on product and supply chain standards is mixed, but on balance positive, although additional measures are necessary (9.10).

Value for money

Available evidence suggests that the RATE programme is both economic and efficient (10.2). Evidence is currently both limited and uncertain on the extent to which RATE will prove to be effective and cost-effective (10.3).

DFID has employed several measures to maximise value for money (VFM). Three further measures are suggested: (i) prioritise the impact data that matters (i.e. evidence of changes in the behaviour of business as it directly affects poor women and men, and the environment, in developing and middle-income countries); (ii) give greater emphasis during the identification and appraisal of RBIs to the plausibility of the programme theory of change and of the specific impact pathway in question; and (iii) develop a systematic framework for appraising and selecting RBIs to be supported in any future phase (10.5).
Sustainability
Questions on sustainability, scaling and systematic change are difficult to answer at this stage of the programme. Sustainability is a challenge for almost all the RATE RBIs. Some, such as the UN Global Compact and the UK National Contact Point, receive relatively secure public funding. Most of the other initiatives, and some of the organisations, are unsustainable in the absence of continued grant funding. The sustainability of the outputs, outcomes and impacts of the programme is closely, but not entirely, tied to the financial sustainability of the initiatives (11.2-4).
Scaling and Systemic Impact
1. Most of the initiatives have ambitions to substantially scale up their work and will need to do so to achieve more significant impact. However, most of the RBIs supported by RATE aim to achieve incremental improvements in business capacity and behaviour, and most are very small scale compared to the overall size of the corporate sector. Few RATE RBIs present clear impact pathways leading to transformative change (11.5-8).
2. The initial findings of the sector study of the ready-made garment sector in Bangalore (based upon in-depth secondary evidence analysis) are as follows: social performance is rated as low with no significant improvement over the past five years; environmental performance is also rated as low, but with some improvement over the past five years; some improvement in levels of support by brands for community CSR projects; and low, but improving, levels of supply chain transparency (11.12-15).
3. Overall, based on evidence currently available from the three evidence streams, the likelihood that current RBIs supported by RATE could lead to systemic change in any sector or location is judged to be uncertain. These findings are consistent with a large body of research on the RMG sector in India and elsewhere, as well as with more general research on labour standards in global supply chains (11.6). Developing the MEL capacity of RATE partners is therefore a priority. Further sector studies, including primary data collection, will be carried out prior to the final evaluation, although the inherent challenges (e.g. reputational concerns, legal constraints) of accessing private sector data to assess levels of responsibility and actual outcomes will remain.
Initial Lessons
1. The main lessons to be drawn from programme implementation to date is the need for improved logical frameworks at the outset for the RBI programmes supported by RATE, and for increased emphasis on monitoring and evaluation (including theory of change development) within these programmes as a condition of DFID support. Lessons from the design and appraisal of RATE and the various RBIs supported will be produced by the final evaluation in 2019.
2. Several wider lessons can be drawn from the organisational analyses and partner engagement, sector study, and secondary statistics, plus wider literature that is relevant to the RATE theory of change (12.2-3). The over-riding lesson is that DFID and other donors need to be cognisant of the scale and depth of the challenge presented by irresponsible business, and realistic about the potential of responsible business to tackle poverty. Unfortunately, it cannot be assumed that general progress on corporate responsibility, and any RBI, will necessarily generate significant benefits for poor people in developing/emerging economies within a reasonable timeframe or tackle the significant harms caused by irresponsible business (12.4).
Summary Assessment
RELEVANCE AND TARGETING	Reasonable
OUTPUTS	Good
OUTCOMES	Uncertain
IMPACT	Uncertain
VALUE FOR MONEY	Reasonable
SUSTAINABILITY, SCALING AND SYSTEMIC IMPACT	Uncertain

Conclusions
1. Evidence suggests that there is strong case for supporting this type of programme, and that RATE is a relevant, efficient and - at output level - effective programme (13.2-3). However, while RATE is on track to achieve its outputs, to date there is limited evidence to draw conclusions about contribution to its intended outcome and impact (13.5). Half of the initiatives funded under RATE are relatively new, and there is limited evidence currently available on many of the evaluation questions (13.1), especially the outcomes and impacts (13.4). Additional evaluation work planned by the programme evaluators and the RBIs should allow for more definitive conclusions at the end of RATE in 2019.
2. The programme faces two main risks: (1) that it will not significantly improve the evidence base; and (2) that it will not significantly impact on poor people affected by business. The first risk can be addressed by improving RBI MEL systems, especially prioritising evidence on the key step in the RATE theory of change – material changes in business behaviour that are likely to impact on poor people (women and men) and environments affected by business. The second risk is more difficult to address at this stage, although the report suggests a set of measures that could be considered in any future programme (13.8-11).
Recommendations
RATE until 2019
1. DFID should require RATE partners to improve their Monitoring, Evaluation and Learning (MEL) systems in three ways: (i) Develop more robust theories of change; (ii) Generate and publish evidence on outcomes and impacts, specifically evidence of changes in the behaviour of business as it directly affects poor people and the environment; and (iii) Commission robust independent organization-level impact assessments where recent assessments are not available.
2. DFID should commission synthesis studies by the EM team or others on priority issues and alternative mechanisms to guide future investment and research.
DFID funding post-2019 on responsible business
DFID should continue to consider alternative options that deliver change ‘closer to-the-ground’, ensuring coverage of issues at the key business-worker/community/environment interface in developing and emerging economies, if it decides to fund additional work in this area, which compliments work that is being carried out around promoting responsible business practices across DFID’s country office network.
Acknowledgements
We would like to thank all the RATE Partners for their participation in several learning events organised by the Evaluation Management (EM) team, and for their comments and contributions to the MTE. We would also like to thank DFID for their constructive inputs on the MTE. We are also grateful to earlier NRI team members for their contributions to early design and analytical work.
Acronyms
EM	Evaluation Manager
ESG	Environmental, Social, Governance
ETI	Ethical Trading Initiative
FSC	Forest Stewardship Council
GRI	Global Reporting Initiative
ICI	International Cocoa Initiative
IFC	International Finance Corporation
ITUC	International Trade Union Confederation
MSI	Multi-Stakeholder Initiative
MTE	Mid-Term Evaluation
RATE	Responsible, Accountable and Transparent Enterprise
RBI	Responsible Business Initiative
RMG	Ready Made Garment
SME	Small- and Medium-Sized Enterprise
SRI	Socially Responsible Investment
TOC	Theory of Change
UNGP	United Nations Guiding Principles on Business and Human Rights.
UNGC	United Nations Global Compact
VfM	Value for Money
WDI	Workforce Disclosure Initiative
WWF	World Wide Fund for Nature

Contents

Annexes
Annex 1: MTE Terms of Reference	40
Annex 2: MTE Methodology – additional information	45
Annex 3: MTE Evaluation Framework	69
Annex 4: The RATE Portfolio	72
Annex 5: Programme Assumptions	74
Annex 6: Detailed Context Analysis	75
Annex 7: Assessment of RATE against Programme Logical Framework	84
Annex 8: Individual Organisational Assessment Summaries	88
Annex 9: Bibliography	92
Annex 10: Mapping Exercise Findings	94
Annex 11: Summary of NRI MEL engagements and achievements with RATE partners	105

Tables
Table 1 : List of current RATE grantees and grant details	2
Table 2: Evaluation Framework	7
Table 3: Evidence Workstreams	9
Table 4: Summary by Impact Pathway	24
Table 5: Summary of Sector Study Findings	33

Figures
 Figure 1 Rate Theory of Change	4
 Figure 2 RATE Impact Pathways	5

1. Introduction
  1. This report presents the findings of the Mid-Term Evaluation (MTE) of the DFID Responsible Accountable and Transparent Enterprise (RATE) programme. RATE is a five-year, £27 million, programme which aims to improve the safety and well-being of poor women and men affected by business in developing and middle-income countries. It provides support to twelve responsible business initiatives (RBIs) which work to improve the way in which businesses manage and account for the social and environmental implications of their actions.

  1. RATE started in August 2014 and will end in March 2019. This MTE covers the period up to October 2017. Its main objective is to assess programme progress and to identify key lessons to date.

  1. The structure of the report is as follows: Section 2 includes an introduction to the RATE Programme, and Section 3 outlines its Theory of Change. Section 4 explains the methodology used by the MTE. Section 5 provides a summary analysis of the context within which RATE operates. Sections 6 to 11 present an assessment of the programme against the main evaluation questions and criteria: relevance, effectiveness, outcomes, impact, efficiency, sustainability, scaling, and systemic impact. Section 12 identifies initial lessons to date. Section 13 contains the conclusions and recommendations.
The RATE Programme

  1. Globalisation has created millions of jobs in developing and middle-income countries and contributed to a reduction in extreme poverty. However, global supply chains involving these countries have also been characterised by serious and widespread social and environmental problems: poor occupational health and safety, insecure employment, low wages, sexual harassment, child labour, modern slavery, severe environmental pollution and natural resources degradation, plus negative impacts on communities (e.g. dispossession of land and property, impacts on social cohesion, human rights abuses) etc. These social and environmental impacts have tended to be treated as externalities giving rise to questions about the sustainability of global supply chains. In the absence of effective government regulation in supplier and/or consumer countries, a plethora of voluntary Responsible Business Initiatives (RBIs)[2] have been developed to partly fill this governance gap. Examples include sustainability standards and Fairtrade certification; multi-stakeholder commodity and industry initiatives; corporate codes of conduct; supplier audits; investment standards; corporate benchmarks; and guidelines for business reporting on social and environmental issues. International organisations such as the United Nations and the OECD have also developed initiatives and guidelines aimed at reducing the negative impacts of business and increasing its positive contribution to the Sustainable Development Goals (SDGs).
    [2] This is a term developed by the RATE MEL team and refers to non-governmental organisations or initiatives seeking to influence business behaviour through voluntary means. Many work at the transnational, global level.

  1. RATE is a programme of support to selected RBIs to encourage responsible business behaviour, with the objective of improving the safety and well-being of poor women and men in developing and emerging economies. The five-year programme started in August 2014 and now has a budget of £26.8 million providing support to a diverse range of RBIs covering improved standards and reporting for business; new technologies to increase transparency and accountability within global supply chains; emerging levers for increasing responsible business behaviour (e.g. new legal forms and benchmarks); and a government-led redress mechanism (the UK National Contact Point).

  1. As stated in the current logical framework (Annex 5) the intended impact and outcome of the RATE programme are as follows:

IMPACT	Where business activity affects their lives and the environment, the safety and well-being of poor women and men in developing and middle-income countries, and the impact on the local and global environment, is improved.
OUTCOME	Businesses are diligent in managing the social and environmental implications of their actions and are accountable for the consequences for poor women and men in developing and middle-income countries.

  1. Starting from four RBIs, grant support is now provided to the following 12 partners (Table 1)[3]. The most recent of these – British Academy – is receiving a grant to support a research programme on child labour and modern slavery rather than being a RBI as such. Summary details for each partner are contained at Annex 4.
    [3] Only the first eight of these grants are covered by this MTE. See para. 4.4 below.

Table 1 : List of current RATE grantees and grant details
Grantee	Grant period	Grant amount (£’000)
The ISEAL Alliance (ISEAL)	2014-18	£3,693,187
Global Reporting Initiative (GRI)	2015 - 19	£2,000,000
UN Global Compact (UNGC)	2014-18	£755,000
Ethical Trading Initiative (ETI)	2015-19	£5,034,100
B-Lab	2016-19	£3,155,737
Shift	2016 - 19	£1,402,183
ShareAction	2016-19	£969,314
Fairtrade (Fairtrace Grant)	2016 - 18	£208,424
UN Foundation - World Benchmarking Alliance	2017 - 18	£1,008,379
UK National Contact Point (NCP) for the OECD Guidelines for Multinational Enterprises	2014-18	£478,000
Humanity United	2017 - 19	£2,514,061
British Academy	2017 - 19	£2,000,000

  1. These grants are managed centrally by DFID’s Private Sector Department. A further grant has been made to an Evaluation Manager[4] to support monitoring, evaluation and learning (MEL) within the programme, including this MTE. The main objectives of the MEL element are to provide internal and external learning to DFID and other organisations; to increase the evidence base around ’what works’ in terms of end results for poor women and men; and to contribute to the business case for corporate responsibility.
    [4] Natural Resources Institute (NRI)

1. The RATE Theory of Change
  1. The connections between initiatives that are working to increase the responsibility of business, and the intended positive impact on the safety and well-being of the poor women and men in developing and middle-income countries affected by business, are lengthy, complex, non-linear, and context-sensitive. Understanding and evidence for how and why businesses are changing, and for the impacts on poor people, is limited and/or contested. Any RATE inputs are tiny compared to the resources being deployed by business and the other Responsible Business Initiatives that are not being supported by RATE. The definition of a theory of change that attempts to clarify how RBIs will lead or contribute to the intended impact is key to evaluating RATE, given the complexity of the interventions, the multiplicity of actors involved and the influence of contextual factors.

  1. An overall theory of change (ToC) for the programme has been developed by the Evaluation Manager (EM) in discussion with RATE partners. Further clarification and elaboration will be required after the MTE, especially for the nested impact pathways. The development of the ToC and impact pathways is a key part of the learning process for RATE and its partners, having already contributed to theory of change development for many of the partners. The most recent RATE ToC is presented in Figure 1 below, but we note that it is a living interpretation of the programme and so will evolve through further consultations with partners and stakeholders (more details on the TOC assumptions are included as part of the Evaluation Framework in Annex 3 and, also in Annex 5). We have drawn upon and extended a framework employed by Said Business School,[5] to identify seven impact pathways used by RATE RBIs. Figure 2 presents the specific impact pathways. Analysis of effectiveness across the impact pathway (from inputs to impacts) helps to unpack how RBIs work and whether the assumptions in the theory of change are correct or not.
    [5] ‘State & Direction of Inclusive Capitalism’ Said Business School/Univ. of Oxford 2016

  1. The main causal steps in the RATE theory of change are as follows. RATE funding strengthens and scales RBIs, including new and existing initiatives. These initiatives deploy a variety of influencing strategies to change corporate capacity (attitudes, knowledge, skills, plus opportunity/motivation) towards greater responsibility. In turn, this leads to changes in corporate commitments, policies, and practices, including those that have significant impacts upon poor workers (female, male), communities and the environment in emerging economies and developing countries. Pioneer or leading companies would act first, followed by a process of mainstreaming as competitor companies crowd in and public agencies respond (e.g. by changing procurement policies, by reforming policies) so that sector or industry becomes more sustainable. Multiple contextual factors shape will determine change in any specific context. RATE partners may also potentially influence that context by changing societal expectations or government policy.

Figure 1: Rate Theory of Change
Figure 2: RATE Impact Pathways
Impact
Behaviour change
Capacity change
	Impact Pathways
1	Thought leadership, Convening Leaders, Movement Building
2	Influencing investors
3	Standards and Tools for corporate reporting
4	Business & Industry Capacity Strengthening
5	Supply chain transparency, accountability and traceability tools
6	Creating new legal forms
7	Product and supply chain sustainability standards

1. Evaluation Methodology
  1. The terms of reference (ToR) for the MTE are attached at Annex 1. The main purpose of the independent MTE was ‘to assess programme progress with respect to the achievement of desired outcomes’, and to distil ‘key lessons to inform and improve programme design’. The ToR included a set of evaluation questions and an outline of the methods, timetable and report. The remainder of this section outlines the methodology used in the MTE. Further details on the evaluation methodology are contained in Annex 2.

Definitions and coverage

  1. There are many definitions of responsible business or corporate responsibility, but all share the belief that companies have a responsibility for the public good[6]. The magnitude and type of this responsibility varies with corporate size, country, and industrial sector. Unless otherwise stated, this report uses the DFID Business Case[7] definition of ‘responsibility’ in business as meaning an approach to business that is diligent, transparent and accountable with respect to the social and environmental impacts and implications of its direct operations and supply chains[8].
    [6] M. Blowfield and A. Murray (2014)
    [7] DFID (2014) - Responsible, Accountable and Transparent Enterprise (RATE). Business Case and Intervention Summary. Private Sector Department (Business Engagement Hub).
    [8] See Annex 2, Table 2.2 for more details on the definitions.

  1. The MTE has used OECD DAC definitions for the main evaluation criteria: relevance, effectiveness, efficiency, outcome, impact and sustainability[9]. The MTE combines this with the specific evaluation questions as set out in the MTE ToR and agreed with DFID in 2017. The report also includes theory-based evaluation analysis (see the Evaluation Framework below and Annex 3 for the full Evaluation Framework).
    [9] Glossary of Key terms in Evaluation and Results Based Management, OECD DAC

Table 2: Evaluation Framework
CRITERIA	MTE QUESTIONS	EVIDENCE
		O.A.*	W.E.**	S.S. ***
CONTEXT	How supportive is the context within which RATE is operating?	X	X	X
RELEVANCE	How relevant is RATE to DFID, business, and beneficiaries?	X	X	X
TARGETING	Are RBIs, particularly RATE RBIs, reaching companies of different kinds? Are these the most appropriate companies in terms of impact potential?	X	X	X
	Are RBIs, particularly RATE RBIs, reaching affected workers (female, male), communities and environment? Are these the most affected groups and areas?	X	X	X
EFFECTIVENESS	How effective is the RATE programme to date? Is it on target for delivering its outputs?	X
	How effective are the different impact pathways, i.e. in delivering outcomes and impacts?	X	X
OUTCOMES	What progress has been made on RATE outcomes?	X	X
	To what extent has RATE built the capacity for responsible behaviour amongst businesses and other stakeholders?	X	X
	What is the contribution of RBIs to corporate behaviour change (nature of changes in corporate decision-making, scale of changes vis-à-vis other corporate behaviour and vis-à-vis likelihood of achieving goals of RATE?	X	X
IMPACT	What is the likely impact of RATE on poor women and men workers, communities affected by business?	X	X	X
	How plausible is the overall theory of change for RATE? What is the evidence regarding the key assumptions (eg. the business case)?	X	X	X
	How effective are the different impact pathways [and individual interventions] with respect to gender and social difference?	X	X	X
VALUE FOR MONEY	Have resources been used efficiently in order to provide value for money and achieve results?	X
	To what extent is RATE likely to be an economic, effective and cost-effective investment?	X
	What could be done differently to improve implementation and value for money?	X
SUSTAINABILITY / AND SCALING	To what extent are the outputs, outcomes and impacts of the programme likely to be sustainable?	X	X	X
	What factors constrain or enhance sustainability?	X	X	X
	What is the likelihood of business building on and scaling up the work of the programme?	X	X	X
SYSTEMIC IMPACT	What is the systemic impact of RBIs, especially RATE RBIs? Can RBIs bring about a transformation of individual companies and sectors and under what conditions?	X	X	X
LESSONS	What are the key factors determining success? What are the major factors constraining or enhancing progress towards the intended outputs, outcomes and impacts?	X	X
	What could be done differently to improve programme relevance, implementation, output achievement, contribution to outcomes and impacts, systemic impact and with respect to the Sustainable Development Goals?	X	X	X
	What are the main lessons for DFID, governments, companies and civil society in relation to responsible business affecting developing countries?	X	X	X

Notes:
Shaded questions are additional or different to those listed in the MTE Terms of Reference.
*OA = evidence on the eight RATE Responsible Business Initiatives covered by the MTE drawn from interviews, partner M&E reports, workshop, secondary evidence in literature, all of which was triangulated and used to assess organisational performance and impact against their logframe and against their theory of change.
**WE = secondary evidence from the wider literature on RATE RBIs, non-RATE RBIs and responsible business more generally. This evidence is used to analyse the effectiveness and impact of key mechanisms employed by RATE partners and other non-RATE RBIs in changing business behaviour.
*** SS = evidence from the sector study, which draws on in-depth secondary data relating to the RMG sector.

  1. The MTE covers the period from August 2014 to October 2017, and 8 of the 12 grantees. It was agreed with DFID that the MTE would not cover the three most recently approved grants (UN Foundation, Humanity United, and British Academy). The UK NCP is being peer reviewed in 2018 and so was also not covered by this MTE.
Overall approach
  1. The ToR envisaged that the MTE would use a theory-based evaluation approach to test and refine the programme theory of change using evidence generated by the RATE partners and the Evaluation Manager (EM). The justification for this approach was contained in the EM Inception Report agreed by DFID.

  1. We have assessed the programme against the revised programme logical framework, but also assembled the available evidence to test the overall theory of change, focusing upon the relevant assumptions at each stage of the causal pathway. We have explored the effectiveness of the different mechanisms employed by the RATE partners and other RBIs through the impact pathway analysis, to support learning. Available evidence on the three main outcome stages of the ToC, and on the seven impact pathways, has been analysed.

  1. An evaluation framework detailing the criteria, questions, evidence sources and methods is attached at Annex 3. This uses the evaluation criteria as required by the ToR, but with specific questions that are more appropriate to the mid-term nature of this evaluation and the evidence likely to be available at this stage. These and other divergences from the ToR are detailed and justified in Annex 2.

  1. Based upon the evidence available, each evaluation question has been scored using a simple four-category scoring system[10]: good, reasonable, poor or uncertain. The latter category is used where there is insufficient evidence at this stage. Positive and negative findings have also been summarised for each criterion. Key MTE findings have been identified in bold type through the report.
    [10] This scoring system is adapted from the DFID project scoring system – Reviewing and Scoring Projects, How to Note, DFID (2011)
Evidence
  1. The general challenge faced by any evaluation of responsible business is the combination of an enormous universe of activity (global business); the multiple factors shaping corporate behaviour (including major global political-economy forces); and the very limited impact evidence publicly available. In addition to this general challenge, the specific challenge faced by this MTE was the combination of a significant number of grantees, each working with tens or even thousands of companies; the diversity of the RBIs supported; the fact that most of the RATE RBIs were at an early stage of their DFID funding; and the limited resources available for the MTE relative to the intended reach of the programme.

  1. The evidence challenge was addressed in four ways. First, it was agreed with DFID that greater emphasis would be placed on the larger, more mature RBIs for which more information was likely to be available: ISEAL, GRI, UNGC and ETI. Second, primary reliance was placed on the MEL information and reports produced by the eight RBIs themselves, rather than on primary research by the MTE team[11]. Third, in view of the likely scarcity of outcome and impact information from most of the RBIs, wider evidence on similar initiatives was consulted to the extent feasible. And fourth, a sectoral approach focussing on a single sector (ready-made garments) in two locations was planned as a manageable approach to testing the overall plausibility of the RBI approach (i.e. that significant positive impacts for poor women and men are likely to result).
    [11] It was agreed with DFID at an early stage that the focus would be on the evidence from partners and secondary evidence. Given the limited evaluation resources, making maximum use of evidence from partners and secondary evidence was judged to be the most cost-effective approach for the MTE.

  1. Three main evidence streams have been used for this report (Table 3). The findings presented for each evaluation question are based on the combination of available evidence from these three streams.

Table 3: Evidence Workstreams
Evidence Workstream	Details
RBI organisational analyses	A review of the monitoring and evaluation reports produced by the eight selected RBIs / Review of secondary evidence in literature related to the eight RBIs. / Individual interviews with the eight RBIs. / A series of learning workshops has been held with RATE partners to explore the theory of change, the importance of evaluation evidence and in 2017, a one–day workshop was held with RATE RBIs, two external participants, and DFID to discuss the interim MTE findings[12]. / All of the above has been triangulated and analysed against a theory of change, and upon which the partners have been consulted and the analyses approved.
Wider Evidence on RATE and non-RATE RBIs and on responsible business more generally	A literature review of corporate sustainability reporting. / A review of literature on sustainability standards; the business case for responsibility; Issues and initiatives in the ready-made garment sector; other types of RBI approaches (beyond standards) corporate responsibility in general. / Analysis of secondary data related to the RATE impact indicators.
Sector Study	An in-depth, structured review of secondary information on the ready-made garment sector in Bangalore, India.
[12] Earlier learning workshops involving RATE grantees and DFID were held in June 2015 and in 2016.

  1. An MTE organisational analysis based on the RATE RBI evidence stream was produced for each of the eight RBIs, each employing a theory of change approach. As agreed with DFID, these analytical summaries have not been published, but they are referenced in this report using the grantee acronym where appropriate.

  1. The literature review on corporate sustainability reporting followed a formal and systematic methodology, and again sought to test the theory of change. The other documents in the wider literature evidence stream – and those used in the sector study - were identified from RATE partners, RBI websites, personal communications, internet searches, and reference lists. References from the wider literature are detailed in footnotes and/or the bibliography (Annex 9).

  1. As originally planned, the sector study was to involve a structured document review by an in-country researcher in two ready-made garment locations (Bangalore and Dhaka); a field visit by the EM team and stakeholder interviews in Bangalore; and key informant interviews in the UK garment supply chain (Annex 2). Only the first part of this work in one location was completed in time for the MTE. Fieldwork is planned prior to the final evaluation.

  1. Evidence relating to responsible business has a high risk of bias. The evaluators have sought to counter this by triangulating the information provided by RATE-supported RBIs with secondary documentary evidence from a wide variety of business, NGO and academic sources. Further discussion of evidence quality can be found in Annex 2, which also contains a section on research ethics and principles followed in this study.
Process
  1. The theory of change was developed in consultation with RATE partners and DFID. The MTE TOR was developed and agreed with DFID and shared with the RATE partners. The MTE was conducted by a two-person EM team, with review provided by a third NRI staff member. The garment sector study was supported by a researcher based in India. The planned involvement of an additional consultant was curtailed by illness. The literature review on reporting and on product/supply chain standards, plus the mapping exercise and earlier analysis on which this MTE draws, was produced with the assistance of other NRI research assistants. Organisational analyses[13] were drafted and shared for comment with each of the RATE partners and revised to take account of the comments received. These organisational analyses provide the main part of the RBI evidence stream in the MTE findings that follow. This draft report has been prepared by the EM team. It will be circulated to RATE grantees for comment and then revised prior to publication.
    [13] The organisational summaries contained sections on relevance; project outputs, outcomes and impacts; contributions to programme outcomes (capacity change and business behaviour change); contribution to programme impacts; sustainability, scaling and systemic impact; monitoring and evaluation; and conclusions.

  1. A one-day UK workshop with grantees, two external participants, and DFID was held in October 2017 to discuss interim MTE findings. Earlier learning partners’ meetings and engagements with the RATE partners had included discussion of the theory of change and of the MTE purpose and the nature of and need for good quality evidence. A list of attendees is contained in Annex 2. Individual interviews were arranged with each of the RBIs covered to discuss progress since the Annual Review in August 2017; to identify further evidence relating to the RBI; and to discuss specific gaps or uncertainties relating to the evaluation questions. A list of the number and level of staff consulted in each of the RBI is contained in Annex 2.
Limitations
  1. The MTE has two main limitations. The first limitation was the limited resources available to the EM relative to the size of the programme and the ambition of the ToR for the programme evaluation. Some of the questions are over-ambitious and need to be reviewed prior to the final evaluation. Completing the sector study proved to be a larger task than envisaged. As a result, it only covers one location. Further work is planned involving stakeholder interviews in India and key informant interviews in the garment supply chain to inform the final evaluation.

  1. The second limitation is the limited evidence available. This is partly due to the mid-term nature of the evaluation (some of the RATE-supported projects are at an early stage and none are complete); weaknesses in some of the RATE RBI MEL systems; and a general lack of wider evidence on the outcomes and impacts of RATE and other RBIs. Many of the evaluation questions are scored as ‘uncertain’ at this stage due to this lack of evidence.

The Context

Evaluation Question: How supportive is the context within which RATE is operating?

  1. While the enabling environment for responsible business has generally become more supportive in recent years, this is against a backdrop of increased corporate power resulting from processes of economic globalization, a growing public disquiet with globalization and rising inequality, and a worsening global ecological crisis. We analyse this context in more detail in Annex 6. Some examples of supporting and non-supporting factors are presented below.

  1. Some aspects of the operating context for RATE RBIs and for responsible business are becoming more supportive. Responsible business activity has gone from the periphery to the mainstream in the last three decades. The costs of ignoring social and environmental externalities have increased, as have the benefits of addressing them (or at least being seen to do so). Supportive factors include (Annex 6.1):

- Continued evidence of global negative social and environmental trends[14], and the imperative for business to respond to these.
  [14] http://www.stockholmresilience.org/research/planetary-boundaries/planetary-boundaries/about-the-research/the-nine-planetary-boundaries.html
- Increasing recognition of the governance gaps created by a combination of inadequate laws / regulations and weak enforcement in both consumer and producer countries.
- Rapid growth in the number and coverage of private voluntary standards, codes, and tools available to address ethical and environmental issues in global business operations and supply chains.
- Growing business awareness of resource constraints and environmental risks to their supply chains.
- New regulations and normative frameworks. Examples include the Modern Slavery Act, the EU Timber Regulation, or the SDGs.
- Increasing institutional investor engagement on environmental and social issues.
- Evidence of the business benefits to market leaders from responsible behaviour.
- Growing public/consumer expectations in certain markets for more ethical corporate behaviour, as well as negative perceptions of corporate capitalism and standards of corporate governance.
- Public pressure created by major social and environmental disasters, or media/NGO campaigns (e.g. Rana Plaza and single-use plastics).
- Support for alternative corporate models (e.g. shared value) and for alternative legal organisational forms (e.g. B Corp).
- Technological developments support increased supply chain transparency (e.g. mobile phones and blockchain) and make companies more vulnerable to consumer comments and NGO campaigns (e.g. social media).

  1. Despite these supporting contextual trends, there are still some significant barriers to responsible business behaviour, and significant incentives for continued irresponsible business behaviour. Some of these are the same factors that are encouraging some companies to become more responsible. For example, the governance gaps that some RBIs are trying to fill also provide profitable opportunities for exploitation. Unsupportive factors include (Annex 6.2):

- The size of the negative social and environmental impacts associated with global business and the fact that these impacts are fundamentally the result of current business models, which makes them very difficult for companies to address.
- With processes of globalization and the creation of global production networks, a governance gap developed, created by a combination of inadequate laws / regulations and their weak enforcement – a gap which private governance initiatives (e.g. RBIs) have attempted to fill, primarily on a voluntary basis[15]. However, there remain ample opportunities for business to profit from the existence of weak environmental, labour and social regulation and enforcement.
  [15] Although in agriculture, hybrid public-private governance arrangements are being tested, including jurisdictional approaches.
- The length, complexity and frequent reconfiguration of global value chains makes it easy for negative business impacts to remain hidden, and more difficult for more responsible companies to identify and address issues in their operations, subsidiaries and supply chains. An increasingly informal labour force means that reaching casual workers, particularly female casual workers, may be becoming even harder for RBIs.
- The profitability of irresponsible business. For as long as poor behaviour is hidden or accepted, companies can profit from exploiting the opportunities created by weak standards and weak governance. The lack of a level playing field with respect to responsibility in business is therefore a major challenge in terms of mainstreaming.
- The challenge of making a sufficiently strong business case for responsible business, i.e. with benefits outweighing costs in the face of global drivers of competition (Annex 6.3). Extremely competitive and price-sensitive markets. Competitive consumer markets force price pressures down the supply chain, for example, with consequences for pay and conditions among suppliers.
- The shareholder corporation as the dominant legal form. The primary obligation of corporate executives is serve the interest of shareholders rather than wider stakeholders. Alternative legal organisational forms are in the minority.
- Financial markets encourage a short-term focus on profits, dividends and share prices. This puts pressure on executives to focus on financial returns and threatens the existence of under-performing companies.
- While corporations are increasingly powerful and politically influential, some trends in workers’ rights and civil society are negative. Trade unions are in decline.
- The lack of information on social and environmental impacts made available to the public and investors. This allows irresponsible behaviour to continue and encourages ‘green washing’ (companies claiming to be more responsible than they are). Corporate sustainability commitments can have significant reputational benefits and are far cheaper than actions.[16]
  [16] RBIs also pay insufficient attention to the robustness of claims made by individual companies and the overall levels of progress, not just for individual companies but for whole sectors and industries, and for which there is some evidence vis-à-vis the scope of business impacts.

  1. There are major social, political and economic uncertainties that could have significant implications for RBIs, responsible business, and outcomes for poor people in the near future. Globally, there are several major risks, challenges and uncertainties that will shape how far and how fast business becomes more (or less) responsible. The next economic crisis will force companies to focus on financial survival, and consumers to focus on price. Social and environmental issues become lower priorities during a recession. Longer term, there is growing discontent with the global economic system, which will have political and economic ramifications. Inequality, the stagnation of wages, a growth in precarious work and informality, and the shift of global economic power to Asia are all clear trends. In all economies, large numbers of jobs of different types are potentially threatened by automation and artificial intelligence. Companies may find it preferable to automate and/or ‘re-shore’ production rather than deal with the human rights risks inherent in off-shore supply chains. Environmental risks – notably those associated with climate change – have grown in prominence[17]. These and other uncertainties will impact on the context for global business, and on the poor people affected by it.
    [17] World Economic Forum (2018) – The Global Risks Report. 13thEdition.

  1. There are challenges in generating evidence, and in learning what works, in a business context. Unlike public activities, where there is an expectation of transparency and accountability, business activities tend to be relatively opaque for commercial and reputational reasons. Positive experience is more likely to be publicised than negative experience. This makes it more difficult to learn what works and to make balanced assessments of performance and impact. Corporate decision-making and behaviour can also be difficult to understand for outsiders – particularly those without a business background - which makes it more difficult for RBIs to exert influence.
Relevance and Targeting

Evaluation Questions:
How relevant is RATE to business, beneficiaries, and DFID?
Are RBIs, particularly RATE RBIs, reaching companies of different kinds? Are these the most appropriate companies in terms of impact potential?
Are RBIs, particularly RATE RBIs, reaching affected workers (female, male), communities and environment? Are these the most affected groups and areas?

Relevance
  1. This section considers the extent to which the objectives of RATE, and of the RBIs supported, are consistent with beneficiaries’ requirements, business priorities, and DFID policies. One of the RATE Theory of Change assumptions is that the combination of interventions is appropriate to meet desired goals (Annex 5). The evidence for this section is largely drawn from the RBI organisational analyses and the wider literature.

  1. All the initiatives funded under the RATE programme are highly relevant to the challenges of responsible business. Some of the RATE RBIs address more specific issues, such as human rights, but others are all-encompassing addressing a broad and evolving range of social and environmental issues. The RATE portfolio is wide-ranging in terms of the approaches employed, but includes a diversity of strategies for influencing business, such as convening corporate leaders, mobilizing investor pressure, creating new legal forms for business and offering corporate reporting and product standards and tools. The effectiveness of these different approaches currently employed within RATE are analysed in more detail in Section 9.6-13.

  1. RATE RBIs are generally relevant to the problems faced by poor people affected by business in developing and emerging economies. All the RBIs cover companies with a presence or supply chains in emerging/developing economies. For example, ETI’s 90 corporate members have an estimated 10 million workers in their supply chains. All the RBIs also cover sectors or commodities with persistent and widespread social and environmental problems as documented in the wider literature and the sector study. However, it is difficult to judge the extent to which the initiatives supported by RATE are relevant to specific beneficiaries’ requirements because of the general nature of the targeting. All the organisations supported by RATE are effectively global in coverage, albeit with RATE funding focused upon specific regions, commodities or responsible business issues in some cases. All the RATE RBIs are essentially intermediaries, working through businesses to achieve intended benefits in direct and indirect ways.

  1. Positive membership trends, and uptake of the tools and guidance by companies, suggest that RATE-supported initiatives are relevant to some businesses. GRI, ISEAL, B Lab, ETI and UNGC all have increasing numbers of business members and users[18], although there are indications that the coverage/influence of many RBIs may be limited in terms of reaching beyond headquarters, beyond pioneer companies and beyond tier one suppliers.
    [18] While indicative of relevance, rising membership does not necessarily mean that RBIs are meeting the most important needs of business. The MTE did not collect evidence on this point.

  1. RATE is relevant to DFID policies. At the centre of DFID’s new Economic Development Strategy[19] is a commitment to achieving inclusive growth that transforms economies; creating productive jobs and private sector investment that spread benefits and opportunities right across society. RATE is also relevant to wider UK Government action on business and human rights, notably The Modern Slavery Act 2015 and the UK National Action Plan[20].
    [19] Economic Development Strategy: prosperity, poverty and meeting global challenges. DFID (2017)
    [20] Good Business: Implementing the UN Guiding Principles on Business and Human Rights. Updated May 2016, Foreign and Commonwealth Office.
Targeting
  1. One of the assumptions in the Theory of Change is that RATE is effectively targeted at the most appropriate RBIs and companies in order achieve the maximum positive impact for poor people and that the RBIs and companies are willing to respond and participate. The evidence in this sub-section is drawn from the RBI organisational analyses[21] and the evidence in the wider literature.
    [21] Including collaborative work with GRI mapping corporate reporting in 4 key sectors.

  1. RATE is working with appropriate RBIs and companies. As mentioned above, all the RBIs are relevant to the social and environmental problems faced by poor people affected by business. The RBIs work with companies and sectors involving large numbers of poor people, and because of the voluntary nature of these initiatives, the companies involved are those that are sensitive to the issues and see some value in participation. This self-selection makes positive change more likely. However, as discussed later, it does not guarantee the extent of change within individual companies (i.e. how comprehensive the changes may be and the extent of implementation of practices, including beyond headquarters to suppliers and subsidiaries), and it remains true that only a small minority of companies are participating with RBIs. For the RATE RBIs it is important to understand the extent to which they are reaching leading companies, but also what prospects there are for reaching mainstream actors i.e. the extent to which the latter are willing to participate. A mapping exercise of GRI reach across four selected sectors found that the food, beverage and tobacco industry had the highest proportion (29%) of companies reporting (annex 10). The percentage of reports that have external assurance varies across the industry groups.[22] A recent KPMG report finds that corporate reporting is becoming more mainstream, but there are still companies and sectors where reporting is not yet mainstreamed[23] and there are issues regarding what is reported..
    [22] Starting with the Dow Jones Sustainability Index (DJSI), the leading index of sustainability-driven companies globally, we have identified a starting universe of 3450 Multi-National Companies (MNCs). This list was taken as the sample for the study, against which we have focused upon four sectors, agriculture, electronics, extractives and textiles, identified through stakeholder discussions as likely to have some of the most direct impacts in developing countries through production, service provision and contracting. The mapping exercise has established the proportion of companies reporting against the most recent version of the guidelines (G4). The food, beverage & tobacco industry group has the highest proportion (29%) of companies reporting. The percentage of reports that have external assurance varies across the industry groups. The semiconductor sector stands out with a low percentage of 20%, while for other industry groups this varies from 45% to 67%
    [23] Corporate sustainability reporting is now ‘standard practice for large and mid-cap companies around the world’ with around three quarters of the 4,900 companies studied issuing CR reports and two thirds of reports analysed in this survey applying the GRI G4 Guidelines or Standards’ (KPMG, ‘The Road Ahead’, 2017). However, while reporting rates amongst the G250 have been stable over the past four surveys (at 90-95%), for the N100 companies that has been higher levels of growth in reporting, largely due to new regulation (KPMG, 2017, p9). However, this means that one quarter of the N100 companies are not currently reporting on their sustainability. At the sector level, the KPMG survey finds that 60% of companies across all industry sectors are reporting on CR, which means that 40% are still not reporting.

  1. It is more difficult to assess whether RATE is working with the most appropriate RBIs and companies. This would require an assessment of the RBIs and companies that are not involved with RATE, which would be an enormous task. Not all the companies involved with RATE RBIs have a significant presence or supply chains in emerging/developing countries, but most do. DFID has ensured that the global RBIs such as B Lab, GRI, ShareAction, Shift and ISEAL have some focus in their RATE-supported work on priority regions or countries.

  1. RATE does not target small and medium enterprises (SMEs) which make up the bulk of business activity. According to the ILO, SMEs constitute 80-90% of employment in developing countries and generate a large part of the employment in the lower tiers of global supply chains. These tiers are generally characterised by the worst working conditions.[24]
    [24] Decent work in global supply chains. ILO (2016, p. 7)

  1. Most of the RATE RBIs are not specifically targeted at workers in global supply chains and poor communities affected by business. RATE supports RBIs that work with issues, companies, sectors and commodities that are generally relevant to poor people affected by business, rather being specifically targeted at defined groups of beneficiaries. While general targeting is an inevitable characteristic of a global programme and of the global RBIs supported, the theories of change for many of the RATE RBIs (and non-RATE RBIs) are long and top-down, with many causal steps between inputs and ultimate impacts and many inherent assumptions, for which past evidence is not that supportive. It is possible that a more selective focus on specific supply chains or geographies, or on initiatives with shorter causal chains, might achieve a better focus on poor people. There is limited evidence available that the RATE RBIs can reach the poorest of the poor.

  1. Most of the RATE grants have a relatively undifferentiated approach regarding women and disadvantaged socio-economic groups. Four of the eight grants have some focus on women and/or gender specific logframe indicators: B Lab, ETI, ShareAction and UNGC. The other four grants make little or no mention of women. The ETI and B Lab projects display the best appreciation of the existence of minority, excluded and disadvantaged groups.
SUMMARY ASSESSMENT – RELEVANCE AND TARGETING
OVERALL	Reasonable
POSITIVES	Relevant to the challenges of responsible business, to the problems faced by poor people affected by business, and to business itself. The programme is working with appropriate RBIs and companies.
NEGATIVES	Many RBIs are not yet reaching the mainstream of companies, except in corporate reporting where there are signs of more extensive uptake of reporting, but variable quality. / Most RBIs include a general focus on workers in global supply chains and poor communities affected by business, rather than specifically targeting them, and a relatively undifferentiated approach to gender and social difference. Some companies covered do not have a significant presence in or direct links to emerging/developing countries.

Outputs

Evaluation Questions: How effective is the RATE programme? Is it on target for delivering its outputs?

  1. This section presents an assessment of the programme’s effectiveness by output. Outcomes and impact are covered in Sections 8 and 9 respectively.

  1. Output-level performance of the RATE programme, and of all the constituent initiatives (except the UK NCP), are on, or above target for most of the indicators in the revised RATE logical framework. Effectiveness is assessed against the latest version of the RATE logical framework (October 2017). A summary of progress by RATE indicator and milestone is contained in Annex 7. A summary of progress for each individual initiative on their RATE grant is contained in Annex 8.

  1. Output 1: Increased business outreach and networks. The programme is above-target for two of the three indicators. The cumulative total of business leaders engaged with ISEAL since 2014 has been exceeded: 6,563 compared to the RATE August 2017 milestone of 5,482. The number of businesses involved with GRI in South Africa, and with B Lab in East Africa, also exceeds targets. ETI’s original objective of establishing 5 country-based multi-stakeholder ethical trade platforms by 2020 has encountered significant in-country challenges. A first meeting of the Bangladesh platform was held in July 2017, and work is underway in India, Pakistan and South Africa which may lead to multi-stakeholder platforms. However, ETI is now aiming for ‘increased dialogue between relevant local stakeholders’ rather than platforms per se, which is a less concrete but more realistic objective.

  1. Some of the other initiatives are also working to increase business outreach and networks. UNGC has 76 Local Networks. ShareAction has exceeded its targets for the number of companies and institutional investors engaged with its Workforce Disclosure Initiative (WDI). ISEAL slightly under-achieved its Communities of Practice targets, but still involved an online community of almost 2,000 users.

  1. Output 2: Improved standards, guidance, tools, reporting systems and innovation. RATE is on target for around half of the indicators for this output. Work on new GRI Reporting Guidelines has started on schedule. Work on updating existing reporting guidelines is slightly behind schedule but should still meet the end of project target in 2019. Shift has exceeded its milestone of the number of companies on its human rights reporting database, but the number of users is significantly below target, partly due to website and database technology issues that have now been resolved. B Lab has convened its East Africa Regional Advisory Group to begin the process of revising the B Impact Guidelines.

  1. Other initiatives are contributing to this output. ETI has produced several guides and tools to help its company members advocate for, and improve, workers’ rights. Guidance on ETI’s Human Rights Due Diligence Framework has been produced, and work on creating guidance materials on freedom of association is in process. Fairtrade has produced four visual supply chain maps for cocoa, coffee, tea and sugar.

  1. Output 3: Impact evidence generated and shared. The programme is on target to meet two of the three indicators for impact evidence. The number of new reports addressing sustainability impacts and performance of standards listed on the ISEAL website exceeded the target. ShareAction has published one of the two case studies[25] planned to date (Myanmar), and aims to produce three more case studies (Tanzania, India and Turkey) with a focus on modern slavery and child labour where feasible. The third indicator refers to the new British Academy research fund which has only just issued its research call. This research also focuses on modern slavery and child labour. This research programme is not covered by this evaluation.
    [25] It should be noted that these are situational analyses rather than impact studies as such.

  1. Output 4: Government-led interventions demonstrate that they extend responsible business practice. The initiative that contributes to this output – the UK National Contact Point (UK NCP) for the OECD’s guidelines for multinational enterprises – is not covered by this MTE. A peer assessment of the performance of the UK NCP is scheduled for late 2018.

  1. There is, as yet, limited evidence from the RATE RBIs on the causal links between the programme outputs and outcome. The Theory of Change includes a short-term outcome for this reason: ‘Capacity strengthened amongst companies (and other actors) on responsible business issues’. The contribution to this short-term outcome is assessed in the next section.

SUMMARY ASSESSMENT – OUTPUTS
OVERALL	Good
POSITIVES	Output-level performance is on or above target for most of the logframe indicators.
NEGATIVES	As yet, limited evidence on the causal links between programme outputs and outcome.

Outcomes

Evaluation Questions:
What progress has been made on RATE outcomes?
To what extent has RATE built the capacity for responsible behaviour amongst businesses and other stakeholders?
What is the contribution of RBIs to corporate behaviour change (nature of changes in corporate decision-making, scale of changes vis-à-vis other corporate behaviour and vis-à-vis likelihood of achieving goals of RATE?

  1. This section presents an assessment of the programme’s actual and likely outcomes. It assesses progress against the programme-level outcome indicators in the RATE logframe, as well as the contribution of RATE-supported RBIs to the short-term and longer-term outcomes in the theory of change: Capacity-strengthening and behaviour change respectively. The evidence for this section is primarily drawn from the eight RBI organisational analyses, which themselves employed theory-based evaluation and contribution analysis.

  1. The assessment recognises both that the programme is at the mid-term stage, and that half of the initiatives funded are relatively new. Four of the initiatives are both established initiatives and their DFID grants are at a medium or relatively advanced stage of implementation (ETI, GRI, ISEAL, and UNGC) while the other four (B Lab, Fairtrade, ShareAction and Shift) have only received DFID funding for a little over a year, although as organisations there is variation in their level of maturity. The likely contribution of the latter grants to RATE outcomes and impacts is inevitably more tentative than it is for the more advanced initiatives.
Programme outcome indicators
  1. The intended programme outcome is that ‘businesses are diligent in managing the social and environmental implications of their actions and are accountable for the consequences for poor women and men in developing and middle-income countries’. Most of the logical framework indicators for this outcome are uptake measures. As such, this outcome is effectively equivalent to the medium-term outcome in the RATE theory of change (Figure 1 above), although some of the indicators attempt to measure the longer-term outcome of behaviour change.

  1. Overall, progress against the selected logical framework outcome indicators has been positive, although data are not available for all the indicators. Data are currently available for three of the five indicators in the revised logical framework. As stressed elsewhere in this report, estimating the extent to which businesses are diligent and accountable, and the extent to which this has changed over time, is extremely difficult. The five outcome indicators in the programme logframe provide just one of many alternative snapshots. Other evidence on business behaviour change available from the RBIs supported, as well as wider evidence, is limited. There are some positive general trends in some business behaviours for certain types of business (see below), but the evidence linking these either to specific RATE (or non-RATE) RBIs or to impacts is limited. Although challenging, better evidence on the contribution of RATE-supported RBIs to business behaviour change RBIs has been identified as a priority by this MTE and should be made available by the RATE partner organisations for the final evaluation.

  1. One indicator of business responsibility is the number of production/management sites and chain of custody certificates issued by ISEAL members. Global figures for these certificates have continued to grow strongly – 65,484 in June 2017 against target of 65,000 and a baseline in 2014 of 46,553 – albeit at a slightly lower rate in 2017 for a complex set of reasons. The number of certificates issued in the emerging markets of Brazil, India and China have also increased by 50% since 2014 (see Annex 7). Because certification by ISEAL members is accompanied by third party certification, and in view of the available evidence on the outcomes/impacts of adoption, it is plausible that credible product and supply chain standards are an effective mechanism. Nevertheless, there are limits to the reach and depth of their impact which means that complementary and/or alternative measures may be needed to tackle development and environment challenges in specific production geographies.

  1. The number of sustainability reports submitted by businesses is also growing strongly. Over 5,900 2015 sustainability reports were registered in GRI’s Sustainability Disclosure Database by the end of 2016, compared to a target of 4,718 and a 2013 baseline of 4,150. The number submitted by businesses in Africa, Asia and Latin America & the Caribbean is above target and over 50% higher than the 2013 figure. As discussed elsewhere in this report, the number of sustainability reports is not necessarily indicative of more responsible behaviour.

  1. The fourth outcome indicator measures the level of progress in companies’ ethical trade performance as reported by ETI corporate members. As part of their 2020 Strategy, which RATE is supporting, ETI have committed to improve the transparency and accountability of the initiative. A revised ETI reporting framework for their 89 company members has recently been agreed, and pilot reports have been submitted and reviewed. However, the form and extent to which the data is made public has not yet been decided. If sufficiently detailed, publication may allow an independent assessment to be made of the extent to which corporate members are improving their performance with respect to workers’ rights. Although not yet available, this data should be available to the RATE MEL team in time for the final evaluation.

  1. The final measure of outcome progress in the logical framework is the quality of human rights reporting[26]. SHIFT will be measuring the maturity of corporate reporting on human rights over the course of their grant, but SHIFT cannot yet identify the improvement expected. SHIFT recognises that expecting to see improvement at the end of year 1 was over-optimistic.
    [26] Outcome Indicator #5: percentage of reporting companies whose disclosure maturity reporting improves by more than one level.
Short-term outcome: business capacity
  1. The short-term outcome in the RATE theory of change is that capacity[27] is strengthened amongst companies (and other actors) on responsible business issues and how to respond. This section summarises the evidence available to date from the RATE-supported RBIs.
    [27] Capacity is defined as new knowledge and skills, as well as motivation and opportunity.

  1. Building the capacity of business is a significant component of all the RBIs supported by RATE. For example, the Shift project is intended to contribute to capacity change. Building the capacity of companies – including small and medium-sized companies - to report more effectively on their human rights performance, and to improve that performance, is one of the main components of the project. The B Lab impact assessment tool aims to build the capacity of participating companies to measure and improve upon their social and environmental outcomes and provides improvement resources such as best practice guides. A large part of the ETI 2020 strategy is aimed at increasing the capacity of members to ensure that workers enjoy their rights at work as described in the ETI Base Code. ETI continues to be active in providing tools, guidance and training for its members. The Fairtrace tool of Fairtrade is intended to enable commercial partners to better understand the risks in their supply chains; to report more transparently; and to collaborate with producer groups on supply chain challenges. A major objective of the UNGC is to build the capacity of businesses everywhere to align their operations and strategies with ten universally accepted principles in the areas of human rights, labour, environment and anti-corruption.

  1. It is too early to assess the change in business capacity for most of the RBIs. This applies particularly to the more recent grants and/or less mature initiatives: Fairtrace, Shift, ShareAction and B Lab. In the case of Fairtrace, the initial feedback from companies has been positive, but it is too early to assess capacity change. It is too early to assess the growth and reach of the B Lab East African hub. Investor engagement under ShareAction, and company engagement under Shift are also at an early stage. There is little direct evidence available from the more mature initiatives on capacity strengthening. All RATE RBIs have been asked to provide more robust evidence for the final evaluation on corporate (and other stakeholder) capacity strengthening as a key link in the theory of change and to test the associated assumptions (e.g. that companies have the internal resources to respond to the services offered by RATE RBIs).

  1. An independent evaluation of ETI in 2015 concluded that the ‘professional capacity of members was being built’ but provided little actual evidence. ISEAL is using a comparison of baseline and final surveys of business leaders to assess whether it has substantially increased understanding and acceptance of the impacts and business case for using sustainable standards. Comparative data will not be available until after the final survey by ISEAL in May 2018. In the case of the UNGC, direct evidence on the extent to which the Compact has built capacity is limited, although an Annual Implementation Survey provides some information. For example, the 2017 Progress Report stated that 47% of respondent companies agreed that the UNGC had ‘guided their sustainability reporting’ and 19% strongly agreed. The 2015 impact assessment concluded that, ‘by producing ground-breaking best practice resources across a range of area … these tools have helped companies improve their performance … hundreds of participants are actively involved in the many business leadership platforms’[28].
    [28] UNGC, 2015, p.168
Medium-term outcome: uptake
  1. If corporate capacity has been strengthened (i.e. there is greater understanding of RBI issues, and motivation/opportunity to act) then the next step in the theory of change is uptake by companies. Uptake requires companies to have sufficient internal capacity to respond, for the capacity strengthening to have been effective (e.g. in sufficiently increasing understanding of relevant RBI issues and how to respond and offering types of tools, standards, and innovations that are of priority relevance to companies to help them address responsible business initiatives) and for pressure to have increased for uptake (e.g. methods such as engaging corporate leaders and using peer or investor pressure or supporting civil society accountability mechanisms have sufficient influence to create a strong enough business case, moral drive or regulatory demand).

  1. Evidence suggests that there has been increased uptake of the tools, guidance and standards recorded by RATE-supported RBIs. For example, there has been rapid global growth in the uptake of responsibility reporting by large companies, with GRI by far the most popular standard being used. According to a recent survey ‘GRI remains the most popular framework for corporate responsibility reporting. Around two thirds of reports analysed in this survey apply the GRI G4 Guidelines or Standards’ (KPMG, 2017, p4)[29]. In the case of ISEAL, the number of certificates issued and the market penetration of sustainability standards, continue to grow (albeit with variation by sector). In both cases it is reasonable to conclude that the increased uptake is indicative of increased understanding within companies of the value of sustainability reporting and standards.
    [29] KPMG, 2017, p.4
Longer-term outcome: corporate behaviour change
  1. Corporate behaviour change in the direction of greater responsibility involves a hierarchy of commitments, policies and practices, which may or may not occur in a chronological sequence in practice[30]. It is the changes in actual business practices which are the key to translating increased business capacity into real improvements for poor people. While public commitments and policies are important, ultimately implementation is critical. It is corporate-wide business practice that needs to change if responsible business is to be achieved. In some cases, achieving meaningful responsibility in corporate behaviour may involve changes in underlying business models (i.e. going beyond incremental changes).
    [30] Indeed, quite often it does not as corporate decision-making is not necessarily linear. As with governmental policy-making it can be messy and non-linear in nature.

  1. Evidence on the business behaviour change resulting from RBIs is currently limited. Collecting and reporting on this evidence needs to be a RATE priority. The lack of evidence from more recent initiatives such as ShareAction and Shift is understandable. The limited evidence from more mature initiatives is of greater concern.

  1. In the case of ETI, available evidence base on the extent and significance of behaviour change among ETI member companies to date is very limited. This is largely due to the limited amount of evaluation evidence – the last major ETI organisational impact assessment was published in 2006 - as well as the limited external transparency and accountability of ETI as an organisation afforded by the previous reporting system. A new reporting system is being rolled out. The degree of external transparency has yet to be decided and it remains to be seen how much evidence this will reveal on changes in corporate members’ behaviour.

  1. GRI has made very good progress on its DFID project and clearly provides a very useful reporting standard for businesses around the world and across industry sectors. However, more evidence is urgently needed that that the central mechanism for influencing corporate behaviour - corporate responsibility reporting - is indeed effective. The NRI literature review on corporate reporting found that there was little academic research, and little evidence from that research, of a positive causal relationship between reporting and behaviour change. More research is needed, but access to evidence from inside business (which is necessary for an analysis of contribution and lesson learning) is likely to remain a challenge.

  1. The extent to which UNGC has helped change business behaviour was assessed in a major UNGC-commissioned report in 2015. This concluded that the Compact had ‘undoubtedly played an important role in spreading sustainable practices around the world, most notably to markets where corporate sustainability was low on the corporate agenda prior to the launch of the initiative’[31]. The changes in corporate practices included helping legitimize a wider range of sustainability topics on the corporate agenda, helping to expand the boundaries of responsibility, fostering cross-sector collaboration, and advancing a set of global values reflected in the ten principles.
    [31] UNGC (2015, p.168)

  1. A combination of the slow improvement in self-reported practices, and a significant percentage of respondents saying that the UNGC has supported that improvement, provides circumstantial evidence that the UNGC has contributed to business behaviour change. However, even if reliable in themselves, these two sets of statistics do not indicate the extent to which UNGC has contributed to the reported change in behaviour. This remains uncertain. There remain ‘almost no empirical insights on the implementation of the ten principles in corporations … the impact of the Compact on existing business practices … for instance, whether and how participating firms have changed existing routines (e.g. with regard to supplier relations)’ [32]. This gap in the evidence applies more generally to all the RBIs supported by RATE, except for ISEAL.
    [32] Rasche, A. (2009, p.31)
SUMMARY ASSESSMENT – OUTCOMES
OVERALL	Uncertain (limited evidence)
POSITIVES	Strong RBI focus on building the capacity of business to change its behaviour. Significant increases in the uptake of tools, guides and standards by business. Achievement is above target for two of the outcome indicators.
NEGATIVES	Data not yet available on two of the outcome indicators. Available evidence on the improvements in business behaviour resulting from RBIs (including RATE RBIs) is very limited. Addressing this gap needs to be a RATE priority in the future.

Impact

Evaluation Questions:
What is the likely impact of RATE on poor women and men workers, communities affected by business?
How plausible is the overall theory of change for RATE? What is the evidence regarding the key assumptions (e.g. the business case)?
How effective are the different impact pathways?
How effective are the different impact pathways [and individual interventions] with respect to gender and social difference?

  1. This section presents an assessment of the programme’s likely impact as tracked by the impact indicators in the logframe. It also provides an initial assessment of the plausibility of the RATE theory of change (i.e. the likelihood that RATE will lead to positive impacts for poor women and men affected by business) and the potential differentiation of any impacts by gender and social group.
Programme impact indicators
  1. The impact statement for the RATE programme is ‘where business activity affects their lives and the environment, the safety and well-being of poor women and men in developing and middle-income countries, and the impact on the local and global environment, is improved’. As already mentioned above, wider evidence on the overall trend in business-related impacts, and the influence of RBIs on those trends, is limited. The three indicators selected for the RATE logical framework provide a partial measure of a larger, uncertain and contested picture. However, they confirm two general observations. First, that there are some improving trends. But second, that the scale of negative business-related impacts remains huge. As is to be expected, there is no evidence at this stage of RATE contributions to any of these indicators.

  1. The International Trade Union Confederation (ITUC) Global Rights Index is an annual assessment of workers’ rights violations around the world[33]. It rates 139 countries on a scale from 1-5 based on the degree of respect for workers’ rights. A large and increasing percentage of low income and lower middle-income countries are rated 5+ (no guarantee of rights due to the breakdown of the rule of law), 5 (no guarantee of rights), or 4 (systematic violation of rights). 84% of low income countries were rated 4 or above in 2017 compared with 56% in 2014. The equivalent figures for lower middle-income countries were 76% and 68%.
    [33] ITUC (2017)

  1. Estimates of the number of forced labourers and child labourers show different trends depending on the period in question. The latest ILO report estimates 40 million people were victims of modern slavery in 2016 (25 million in forced labour and 15 million in forced marriage), up from 17 million. The apparent increase may be the result of better data. 25% of victims of modern slavery are children, 71% are women or girls[34]. 152 million children, aged between 5 and 17, are subject to child labour, almost half in hazardous child labour. Since 2000, total child labour has reduced by 38%, hazardous child labour by 58%, although the pace of reduction has significantly slowed since 2012[35]. Some sector specific data suggests that any improvement is not necessarily permanent. For example, a 2015 study of cocoa production commissioned by the U.S. Department for Labour estimated that almost 96 % of the 2.12 million child labourers in Cote d’Ivoire were involved in hazardous work in the 2013/14 harvest season, representing a 13 % increase from the 2008/09 season. Certification agencies UTZ and ICI warned that more children were at risk of child labour due to falling cocoa prices[36].
    [34] ILO – Global Estimates of Modern Slavery 2017
    [35] ILO Alliance 8.7 – 2016 Global Estimates of Child Labour
    [36] Risk Averse? Company reporting on raw material and sector-specific risks under the Transparency in Supply Chains clause in the UK MSA 2015. CORE (2017)

  1. An annual estimate of the natural capital impacts of 1,600 companies worldwide shows a slight fall from 2014 to 2015, from USD 3,712 billion to USD 3,447 billion. It is too soon to say whether this represents a turning point[37]. After three years of stability, global carbon dioxide emissions will rise by 2% in 2017[38]. Most importantly, natural capital costs in 2015 were still more than double corporate profits for the largest 1,200 companies globally. Most of these costs are not direct and are concealed within the supply chain.
    [37] State of Green Business 2017. Greenbiz and Trucost (2017)
    [38] World Meteorological Organization
Impact pathways

  1. This section draws upon the evidence provided by RATE partners, plus wider literature and comparison with other types of initiatives, to present key insights on how RATE RBIs work.

  1. The RATE portfolio comprises a range of RBIs employing diverse strategies to engage and influence companies. In other words, there are different impact pathways that are nested within the overall programme theory of change and which capture these different strategies/mechanisms, the causal steps to impact, and the associated assumptions for each step. The RATE RBI strategies are anticipated as leading to capacity and behaviour change (commitments, policies and practices) and can be more-or-less direct or indirect in nature and may vary in their focal target actors. Each RATE partner uses one or more strategies in its DFID grant and/or more widely as an organization.

  1. An important feature of RATE is that most of the influencing strategies supported by RATE are voluntary and led by global intermediary organisations with global remits. Apart from UK NCP, all the RATE-supported RBIs are seeking to influence companies through voluntary approaches. Many are physically located in Europe, USA or the UN, emerging in these markets as sustainability concerns grew, but also intentionally close to the global companies that they are targeting. Most of the RATE RBIs work on a global basis and do not have strong territorial focus in developing countries/emerging markets. Further, and critically, the RATE RBIs are largely voluntary in nature – they offer tools, standards, etc, but there is no obligation upon companies to adopt and implement[39]. Instead, the intermediary organisations rely on influence ‘trickling down’ the global value chain to subsidiaries, suppliers and producers. A minority of the influencing strategies[40] employed by RATE RBIs are focused upon specific developing/emerging markets and seeking to directly build local business and wider stakeholder capacity, although these also vary in the extent to which they are top down or can make claim to be locally driven. As will be discussed later, this has significant implications for the cost-effectiveness and impact of the programme.
    [39] There is a growing effort to align public and private governance in some instances for a ‘smart-mix’ approach e.g. in jurisdictional approaches to sustainable oil palm sourcing in Indonesia, but it is still early days to judge their effectiveness.
    [40] B Lab East African hub; ETI local stakeholder dialogues and supply chain programmes; UNGC Local Networks; Shift capacity building workshops.

  1. It is not yet possible, based upon the available evidence from RATE and non-RATE sources, to determine the relative effectiveness of all the different impact pathways. Initial insights by impact pathway are summarised in Table 4 below. It is also not possible to say whether impact pathways not currently addressed in the RATE programme would be comparatively more or less effective. The final RATE evaluation will include a systematic theory-based analysis of different impact pathways, with some (limited) comparison with such alternative and complementary approaches.
Table 4: Summary by Impact Pathway
Impact Pathway	Analysis based upon evidence available
Thought leadership, Convening Leaders, Movement Building	Not clear how far RATE RBIs engage in thought leadership and this could be further explored, especially deeper learning on how to achieve transformative change. / Use of convening power, but unclear how peer effect leads to change beyond commitments. / Sharing business benefits evidence is important as a kind of marketing tool for RBIs, but business case assessments might be less conclusive. Impact evidence is lacking for many RBIs.
Influencing investors	Many causal steps in the theory of change with respect to poverty and environmental impact. / Limited evidence to date that investors are changing, or will change their decisions due to RBI activity, especially for challenging issues such as Human Rights, although there are some precedents. / Changes in corporate ownership and investment trends may reduce scope for RBIs to influence companies on their responsibility performance.
Corporate reporting Standards & Tools	More and better tools are being provided. More reporting, by more companies, but still gaps, and major quality issues. Limited evidence that corporate reporting is driving positive change in practices. Potential for masking business as usual. Hard to make the longer-term strategic business case compared with short-term pressures on margins in supply chains etc. / Newer approaches to managing corporate impact do not yet provide evaluative evidence on effectiveness, but could potentially be transformative if adopted, but the challenge is reaching the mainstream for scaling. Some suggest the business case is changing in the resource constrained economy. / Some, more learning-oriented initiatives offer codes and principles to guide reporting, but these are more aspirational in nature and have not demonstrated impact to external audiences).
Business & Industry Capacity Strengthening	Plausible that targeted work by RBIs is strengthening corporate capacity to understand, measure and report upon specific issues. Undoubtedly many RBIs provide important and useful guidance for companies and on a growing range of issues. The most effective approaches, and whether more understanding and more reporting equates with change in behaviour, is not yet clear. / Some initiatives seek to engage multiple actors to create momentum for change in specific sectors, but more evidence is needed on effectiveness. / Sector programming may be more effective to mobilize, identify norms, but needs to go beyond a few pilot companies. There are only a few cases of sector-wide, legally binding agreements between brands and trade unions. / More evaluation is desirable on local fora, networks and communities of practice as potential important mechanisms for donors seeking to tackle extreme poverty.
Supply chain transparency, accountability & traceability	There is a range of such initiatives, with many companies already moving ahead with technology-enabled systems for transparency in supply chains, but also potential risks. Only one RATE initiative funded specifically on this. Requires further analysis in the final evaluation.
New legal forms	It is too early to know if this can be achieved in East Africa. It takes time to achieve legislative change (e.g. only a few states in the USA have so far done so). Potentially transformative though.
Product & Supply chain standards	Evidence on product / supply chain standards that are credible on balance have positive benefits at production level, and range of benefits beyond this level. But business case needs strengthening for some types of companies and contexts. Increase in trade in emerging economies not requiring sustainability standards. Possible slowing of growth seen. Already recognition of need for complementary interventions, and standards are beginning to respond, but potential threat from trust-based, collaborative forms of programming and assurance. The latter has accountability risks. More research needed.

  1. The impact evidence on product and supply chain standards is mixed, but on balance positive. Compared with most other types of RBI mechanisms, product and supply chain standards have been more widely evaluated. The evidence on impacts is mixed, especially in the peer-reviewed literature, but the general finding is that standards have positive net results. However, outcomes are highly context-specific. Many factors shape the outcomes of such sustainability standards, including how standards are implemented, the geographic context in which they are adopted, the nature of the commodity and value chain and market conditions etc. Evaluation work has gaps (e.g. it is still more focused on particular commodities) and varies in methodological quality, but the work to date has already shown that there are limits to the reach and depth of impact of sustainability standards with respect to poverty impacts compared with initial expectations. For example, the costs associated with third party certification mean that they cannot reach less organized and capitalized producers, particularly women in situations where they do not hold land title and may not have sufficient depth of impact to raise producers and workers out of poverty.

  1. Despite the rapid growth in corporate reporting, there is limited evidence on its quality and impact. While there are instances of improved quality, there is limited evidence that the quality of mainstream corporate reporting is significantly improving. An academic literature review carried out by the EM team suggests that the quality of reporting remains poor, with a lack of standardization, completeness, accuracy and comparability. Overall, there is little academic research, and little evidence from that research, of a positive causal relationship between reporting and impacts on workers, communities and the environment. There are cases where reporting and practices are more aligned in terms of positive responsible behaviour, but it is not clear that the former has caused the latter.

  1. Two other impact pathways currently unsupported by RATE warrant consideration. First, more support for accountability mechanisms, including strengthening worker/producer and community organisation and voice should be considered. Greater support for accountability is necessary to counter-balance the vested interests within companies and RBIs, and the relative under-funding of initiatives that can hold business to account. Current initiatives enabling worker voice in supply chains may be useful to scale, but evaluation is still needed to understand whether they are effective in leading to business behaviour change, including issues of priority importance to workers. More innovation is needed in facilitating worker, producer, community and environmental empowerment vis-à-vis corporate power.

  1. Second, a strategic pillar around engaging governments could be important as a necessary complement to voluntary initiatives. Governments can play diverse roles in shaping sustainable production, consumption and trade, and the emerging interactions between existing public and private governance approaches. For example, jurisdictional approaches are emerging within the agriculture and forestry sectors, which mix public and private governance of sustainability in specific territories or landscapes. Relatedly, there are a growing number of multi-stakeholder initiatives at different scales being established to tackle issues of responsible business. These appear to vary in terms of scope and effectiveness. Particularly, the more grounded, country-sector initiatives, (such as Malawi 2020, which is showing some signs of progress on living wages) merit more research in terms of their effectiveness and success factors. This type of more targeted, closer to the ground type of initiative could be supported by donors, and their potential should be assessed for support for scaling. There are major opportunities (as well as barriers) in the adoption of responsible procurement policies. For donors, there is the potential to systematically review government policy coherence with respect to responsible business and to build on current initiatives in country programmes[41].
    [41] N.B. It is important to also recognize that in a globalizing economy, raising national or local standards in one country or region could merely displace the industry and investment to other countries or regions with lower standards, costs and scrutiny, and this would affect the total jobs supported and the economies relying upon these industries.

  1. Likely impacts differentiated by gender and other forms of social identity are uncertain. Evidence is rarely available by RBI or impact pathway. Available evidence on the impacts of product and supply chain standards suggests that reaching the poorest in rural societies and reaching women is more difficult due to their lack of land title and resources. However, the predominance of women in low-skilled jobs in global supply chains means that any positive impacts from RBIs may disproportionately benefit women, but more analysis is needed. That said, much of the work generated in the lower tiers of global supply chains is sub-contracted to SMEs[42] and/or informal enterprises. These are much less touched by RBIs than Tier 1 suppliers. Forced and child labour also tends to be more hidden and therefore more difficult to address, as well as being strongly associated with socially discriminated groups[43]. The extent to which different RBIs impact on different social groups is therefore likely to be complex and context-specific. Information on this is unlikely to be available from the RATE grantees. The final RATE evaluation will therefore need to base its assessment on specific sector studies.
    [42] Decent work in global supply chains, ILO (2016, p.7).
    [43] Confronting root causes: forced labour in global supply chains. LeBaron, G. et al (2018, p.26).
Overall Theory of Change Analysis

  1. The overall theory of change for RATE is that support for selected RBIs will lead to changes in corporate capacity; that improvements in capacity will lead to positive changes in business practices (corporate behaviour change); and that this behaviour change will then lead to positive impacts for poor women and men affected by business in emerging and developing economies. Assessing the plausibility of the theory of change at this stage of the programme is made more difficult by the diversity of responsible business issues, the diversity within and between companies (ownership, location, size etc) and by the limited evidence on responsible business outcomes and impacts, as well as in the types of RBIs and their impact pathways. This context-specificity is combined with a lack of data, or conflicting data, which makes it very hard to draw clear conclusions. In general, the evidence base for knowing what works in responsible business is thin.

  1. Despite the thin and sometimes conflicting evidence base, there is sufficient wider evidence to suggest that achieving positive impacts for poor women and men is likely to be a slow and difficult process. Drawing upon the logframe analysis and evidence assembled to test the theory of change and impact pathways we find that while certain trends within the context for responsible business are becoming more supportive (5.2), and there is a definite increase in the attention given by some businesses to social and environmental issues[44], there are still significant barriers to responsible business behaviour, especially in term of mainstreaming, and significant incentives for irresponsible business behaviour (5.3). Wider experience confirms this (11.2-3 below).
    [44] Impact. Transforming Business. Changing the World. UNGC DNV (2015)

  1. There is currently insufficient evidence available to judge the overall theory of change for RATE. The key question is the extent to which the RBIs that are currently supported within the RATE portfolio lead to material changes in business behaviours that in turn demonstrably lead to improvements for poor people in developing and middle-income countries. The assumption that any general progress on corporate responsibility, and any RBI, will necessarily generate significant benefits for poor people in developing/emerging economies within a reasonable timeframe can be questioned. Collecting the evidence on the key step in the RATE theory of change – material, poverty-impacting changes in business practice – is thus a key priority going forward.

SUMMARY ASSESSMENT – IMPACTS
OVERALL	Uncertain (limited evidence)
POSITIVES	Some improving global indicators. Evidence on product and supply chain sustainability standards is mixed but on balance positive.
NEGATIVES	Substantial negative business-related impacts remain. Wider evidence suggests achieving positive impacts for poor women and men is likely to be a slow and difficult process. Overall, better evidence is needed for material, poverty-impacting changes in business behaviours. Insufficient evidence to judge the relative effectiveness of all the different impact pathways, or likely impacts by gender and social group.

Value for money
Evaluation Questions:
Have resources been used efficiently in order to provide value for money and achieve results?
To what extent is RATE likely to be an economic, effective and cost-effective investment?
What could be done differently to improve implementation and value for money?

  1. This section presents a mid-term assessment of the efficiency of the RATE programme. It uses the DFID definition of value for money (VFM) – maximising the value of each pound spent to improve poor people’s lives[45]; the 3E framework – economy, efficiency and effectiveness - summarised in Box 1 below; and the VFM assessment in the latest Annual Review[46].
    [45] DFID’s Approach to Value for Money (VFM). DFID (2011)
    [46] See RATE Annual Review 2017 on DFID DevTracker for more information.

Box 1: The 3E’s VFM Framework
 Economy: Are we or our agents buying inputs of the appropriate quality at the right price? (Inputs are things such as staff, consultants, raw materials and capital that are used to produce outputs) /  Efficiency: How well do we or our agents convert inputs into outputs? (outputs are results delivered by us or our agents to an external party. We or our agents exercise strong control over the quality and quantity of outputs) / • Effectiveness: How well are the outputs from an intervention achieving the desired outcome on poverty reduction? (Note that in contrast to outputs, we or our agents do not exercise direct control over outcomes) / • Cost-effectiveness: How much impact on poverty reduction does an intervention achieve relative to the inputs that we or our agents invest in it?

Source DFID (2011)
  1. Available evidence suggests that the RATE programme is economic and efficient. There are no obvious ways in which costs could have been contained without affecting delivery. As reported in the most recent Annual Review, all proposals from new partners are subject to significant VFM scrutiny by DFID. Costs are benchmarked to ensure they represent VFM and are in line with DFID guidance (e.g. on travel). All excessive costs are negotiated down. Existing partners are encouraged to improve and report on their VFM. For example, GRI has revised the format and structure of the Standards to facilitate easier updating and has economised on the way in which it creates e-learning modules. ISEAL has submitted a first VFM report to DFID and has used the report to institute several measures to reduce the cost of hosting events. The quality of financial management was assessed to be good.[47] Apart from encouraging grantees to follow a more explicit approach to VFM – as has been well displayed by ISEAL[48] – it is difficult to see how economy and efficiency could be significantly improved.
    [47] RATE Annual Review, September 2017 (DFID, 2017)
    [48] Ensuring VFM: ISEAL’s Approach to managing its DFID Funded Project (ISEAL, 2015)

  1. Evidence is both limited and uncertain on the extent to which RATE will prove to be effective and cost-effective. Effectiveness measures how well outputs are contributing to the desired outcome, which in this case is better business behaviour as it affects poor people and the environment. As mentioned above, output-level performance of the programme has been good (Section 7). Progress at outcome level has also been positive by some measures, but evidence linking the RBIs and behaviour change that is likely to impact on poor people and the environment in the short term, is limited. In some cases, such as ISEAL, this is because the evidence for the type of business change intended is due to be collected before the end of the project, but this data is not yet available. In other cases, such as the more recent initiatives, it is premature to expect this evidence. But in some cases - such as GRI, ETI and UNGC – there is almost no recent evidence available and no certainty that the evidence will be forthcoming.

  1. Cost-effectiveness measures the relationship between inputs and impacts: improvements in the safety and well-being of poor women and men in developing and middle-income countries, and in the local and global environment. It would be unrealistic to expect impacts at this stage in the programme, and arguably unrealistic to expect such impacts to be easily identified and attributable even in the longer term. That aside, it is reasonable to assess the likelihood that the RBIs supported will contribute to positive impacts for the poor within a reasonable time-frame to justify the investments being made by DFID and others. This depends on the plausibility of the theories of change linking the inputs to the impacts. As discussed elsewhere in this report, there is good reason to doubt whether the optimistic and extended theories of change that characterise most of the RBIs supported, combined with lack of evidence available, provide sufficient confidence in the cost-effectiveness of RATE as currently designed.

  1. DFID has employed several measures to maximise VFM. These include: supporting a mix of different initiatives, drawing on results and learning from other DFID-supported programmes, cost sharing with other donors, and avoiding duplication/ensuring complementarity. While these measures are effective to some extent, effectiveness and cost-effectiveness might be increased by three further measures:

  1. prioritise the impact data that matters, specifically evidence of changes in the behaviour of business as it directly affects poor people and the environment in developing and middle-income countries. Improvements in commitments, policies and reporting are positive and may be necessary conditions for achieving desired impacts. But experience strongly suggests that such changes may not be sufficient to effect substantive change on the ground in the factories and farms of developing/emerging economies. Hence the need for better evidence on the business behaviour that matters, such as transparently responding to, and effectively remedying, reported human rights abuses.

  1. give greater emphasis during the identification and appraisal of RBIs to the plausibility of the entire theory of change, especially the inherent assumptions involved. The causal linkage to the safety and wellbeing of poor women and men, and the local and global environment requires particular scrutiny. While a mix of initiative types may be important (established, new and less tested, etc.), the most important criteria for selection should whether the RBI has a plausible theory of change that extends directly to poor men, women and children in developing/emerging economies. Further analysis of effective strategies and impact pathways is therefore important.

  1. develop a systematic framework for appraising and selecting RBIs to be supported in any future phase. Given the limited evidence currently and likely to be available, and the wide range of potential initiatives, selecting the RBIs that are most likely to have a positive impact on poor people will always be a challenge. As mentioned elsewhere in this report, voluntary RBIs may only be able to mitigate some of the business-related impacts on poor people and the environment, and some RB strategies that have not received RATE support may have potential. A wider and systematic appraisal of all the available RBIs and levers should be carried out prior to a possible second phase of RATE.

SUMMARY ASSESSMENT – VALUE FOR MONEY
OVERALL	Reasonable
POSITIVES	Available evidence suggests that RATE is economic and efficient. DFID has employed several measures to maximise VFM.
NEGATIVES	Evidence is limited and uncertain on the extent to which RATE will prove to be effective and cost-effective.

Sustainability, Scaling and Systemic Impact

Evaluation Questions:
To what extent are the outputs, outcomes and impacts of the programme likely to be sustainable?
What factors constrain or enhance sustainability?
What is the likelihood of business building on and scaling up the work of the programme?
What is the systemic impact of RBIs, especially RATE RBIs? Can RBIs bring about a transformation of individual companies and sectors and under what conditions?

  1. Questions on sustainability, scaling and systematic impact are difficult to answer at this stage of the programme. However, some indication of the likely systemic impact of RATE-supported RBIs can be provided by an assessment of the individual initiatives, and by an initial study of one sector, the ready-made garment (RMG) sector in Bangalore, India.
## Sustainability

  1. Most of the initiatives, and some of the organisations, are unsustainable in the absence of continued grant funding. UNGC, ShareAction, Shift, Fairtrade, and ETI recognise this and are working on sustainable funding models. In the case of UNGC, higher mandatory fees are being introduced for business participants. Fairtrade has RATE funding for a pilot project, but it has built funding requests into all its propositions to business partners and has already exceeded its co-funding target. ShareAction will explore options to make the annual survey self-sustaining, drawing on the experiences of the Carbon Disclosure Project. ETI’s 2020 Strategy includes working on a sustainable business model, but as an organisation is currently very dependent on DFID funding.

  1. Sustainability is a challenge for almost all RBIs. Most are inevitably dependent on two primary sources: donor grants and corporate grants or fees. Grants from donors have the advantage of being independent of business interests, but they are vulnerable to changes in donor policies and priorities. Grants and fees from businesses are potentially more sustainable, but these carry the risk (real or perceived) of reduced independence and credibility. NGOs whose purpose is to hold business to account are less likely to be funded by business and may be under-funded as a result, compared with companies’ resources and with multi-stakeholder organisations. Given the weak level of accountability that characterises the responsible business sector, and the importance of increasing accountability, this type of organisation might warrant more public funding.

  1. The sustainability of the outputs, outcomes and impacts of the programme is closely, but not entirely, tied to the financial sustainability of the initiatives. The results of the funding to the mature initiatives such as ETI, ISEAL and GRI will continue to be beneficial regardless of future funding. The results of the early/pilot initiatives such as ShareAction, Shift, Fairtrade and the B Lab East African hub are much more dependent on continued funding.
## Scaling and Systemic change

  1. Most of the initiatives have ambitions to substantially scale up their work and will need to do so to achieve more significant impact. The extent to which the initiatives will succeed in scaling up their work is largely dependent on obtaining future grant funding and/or developing sustainable funding models. However, even if scaled up, these initiatives may only cover a small fraction of business activity and there are potential limitations inherent in many RBIs as mechanisms for creating change (e.g. relatively long theories of change reliant on voluntary measures and often remote connections to DFID target beneficiaries). If the changes in business practices that occur as result of the initiatives are too limited - because of weak standards/benchmarks and/or weak uptake and implementation - or if the changes fail to trickle down sufficiently to lead to substantive improvements for poor people in developing/emerging economies, simply increasing the number of companies covered will not be effective.

  1. Most of the RBIs supported by RATE aim to achieve incremental improvements in business capacity and behaviour and are very small scale compared to the size of the corporate sector. One of the largest RBIs – UNGC – only covers 2% of listed companies and global GDP. It is judged unlikely that initiatives with an impact pathway that enables incremental changes and/or has such limited reach will substantially contribute to sector transformation. This may change as and when coverage increases. A recent KPMG report reviewing the adoption of corporate reporting (KPMG, 2017)[49] finds that this practice is becoming much more widespread, with GRI being the most adopted standard globally. This suggests that it is starting to or has achieved scale, but evidence is needed to demonstrate that GRI standards’ adoption has made a difference on the ground in terms of poverty and sustainability impacts.
    [49] KPMG (2017) ‘The Road Ahead: The KPMG Survey of Corporate Responsibility Reporting 2017’

  1. Beyond incremental improvements in individual companies, transformative change in sectors and industries – i.e. in specific markets – requires sustained benefits from mainstreaming within individual companies, but also wider scaling to reach the mainstream of companies and responsible business practices that are resilient to market shocks and stresses (e.g. financial crises). Thus, in the RATE context, systemic and transformative change would mean that the benefits from RBIs, would change not only the behaviour of some pioneer, leading companies, but would essentially lead to wider changes in country-sectors and, eventually, in global industries. As well as scaling of initiatives (involving crowding in amongst competing companies, and responses from public agencies e.g. in the adoption of responsible procurement policies or jurisdictional approaches), it is also important that the changes in practices include not just the relatively easy to address issues such as health and safety, but also more fundamental issues (i.e. enabling rights such as collective bargaining and freedom of association). The extent to which RATE RBIs are reaching the mainstream was discussed in the earlier section on relevance and targeting. The evidence suggests that more progress is being made on more straightforward issues such as health and safety (see Annex 6.4)

  1. Two RATE RBIs – ISEAL and B Lab - present possible exceptions in terms of the impact pathways they employ and with respect to transformative change. Some ISEAL members are supporting dialogue in sector transformation approaches, which may lead to wider changes where standards are mainstreamed and become part of the licence to operate, although it is not clear if they are fully successful in driving systemic change (e.g. achieving a magnitude of benefits for smallholders to lift them out of poverty). Market penetration rates suggest that a few sectors are moving towards mainstreaming in terms of coverage, although for many others the proportions covered are lower and currently product and supply chain standards are available only for certain products/supply chains. But more evidence is needed to demonstrate that, even with mainstreaming, this equates with transformative change on the ground on key sustainability and poverty indicators. Nonetheless, to the extent that ISEAL is effective in supporting its members, it is plausible that there will be a contribution to wider change and there is growing recognition that standards organisations can play a role in addition to their direct production impact in convening and coordinating sector dialogue and change processes. More research is needed on sector-success factors and the effectiveness of multi-stakeholder initiatives. There is also a category of emerging, more locally grounded sector initiatives (e.g. Malawi Tea 2020, ACT[50]), which often involve but go beyond individual standards organisations, for which impact evidence is not yet available.
    [50] Malawi Tea 2020 partnership http://www.malawitea2020.com/ Action Collaboration Transformation (ACT) https://actonlivingwages.com/

  1. B Lab has clear ambitions to transform business at a global scale. Its emphasis on a wider pursuit of social and environmental impact alongside financial returns could potentially transform individual companies and could possibly be scaled up and out. It combines work to influence norms and institutions by rewriting the rules for corporate accountability. Legal innovation is a key component of the B Lab approach. As a supported group, a collective of B Corporations could have a potential role as market disruptors, which could influence traditional private sector actors more widely (Sistema B blog[51]).
    [51] http://blog.academiab.org/2017/06/04/sistema-b-pioneers-affecting-systemic-change-in-latin-america/
## Sector Study – initial findings

  1. The sector study of the RMG sector in Bangalore provides insights into current conditions in a specific sector, to inform our analysis of the impact of RBIs (RATE and non-RATE) in achieving more systemic change. The aim of the study is to pilot a methodology for identifying the contribution of RBIs, particularly those supported by RATE, on workers and the environment. Further work may be conducted to extend the analysis to more clearly explore possible connections between RATE RBIs and conditions in the sector (and in other sectors), but this rapid survey provides a useful ground-truthing of current business practice, albeit in only one specific location. This uses the same headings as used in the Higg Facility Tools developed by the Sustainable Apparel Coalition (SAC).[52] The Higg Facility Tools measure the social and environmental performance at individual factories.
    [52] https://apparelcoalition.org/the-sac/

  1. Bangalore is one of five major garment producing cities in India, producing 15% of exported garments by value. Textiles and garments account for 15% of India’s merchandise exports and employs 10% of the workforce. A large proportion of the RMG workers are first generation industrial workers, many of whom are internal migrants and women[53].
    [53] Fashion Focus. India Annex. The Circle (2017, p.111)

  1. Table 5 below provides a summary of the findings by major heading. These findings are preliminary and may be followed by further fieldwork prior to the final evaluation, particularly to explore RATE RBI contribution. It is recognised that there are, of course, many factors which shape outcomes in a specific sector or location, but none of the wider evidence suggests that these findings are atypical.
Table 5: Summary of Sector Study Findings
	Performance	Change over past 5 years
Social	Low	No significant change
Environmental	Low	Some improvement
Community impact	Low	Some improvement
Transparency, public disclosure and ethics	<25% companies	Some improvement
Brand/buyer responsible behaviour	Low	No significant change

  1. Social performance is rated as low with no significant improvement over the past five years. While recruitment procedures have improved somewhat, recruitment practices still lead to worker exploitation. Despite the implementation of large numbers of brand-supported, sustainability initiatives, average wages are less than half of a living wage, involuntary overtime is common, and trade union activity is restricted. There are significant worker well-being issues: most women workers are anaemic, physical and sexual harassment is routine and ignored by management, and there is a high level of gender discrimination. More positively, most Tier 1 RMG factories are well-lit, mostly clean, with well-marked emergency exits and some type of fire detection system.

  1. Environmental performance is also rated as low, but with some improvement over the past five years, in part due to the focus of international brands and buyers on environmental issues related to cotton, polyester, renewable energy, factory discharges, and water use. While environmental laws are well articulated, compliance tends to be low and enforcement ineffective. However, action was taken to close many of the illegal dyeing units that were polluting a lake, and more effluent treatment plants have been installed. Problems remain with the low energy efficiency of factories; high levels of micro-plastics in drinking water believed to be related to the garments and textiles sector; and unhealthy levels of air pollution.

  1. Other findings include improving levels of support by brands for community CSR projects and low, but improving, levels of supply chain transparency. The standard of brand/buyer behaviour is rated as low and substantially unchanged. CSR and buying departments are often separate and may have conflicting goals. Regular audits conducted by brands have been ineffective at addressing the problems of low wages, sexual harassment, excessive and unpaid overtime, and limited freedom of association. Brand-supported programmes have had limited impacts on the ground, in part because of the limited leverage of individual brands with suppliers. As a result, more collaborative approaches have begun to emerge, but these have also had limited impact to date.

  1. These findings are consistent with a large body of research on the RMG sector in India and elsewhere, as well as with more general research on labour standards in global supply chains. An emphasis on auditing and compliance has led to some improvements in working conditions (e.g. health and safety) in some factories. However, working conditions have failed to improve, or have even deteriorated, in other factories. Improvements tend to be unstable. Alternative capability-building initiatives have had some success, but they have also tended to avoid more difficult issues such as living wages and enabling rights, and the upstream business practices that are driving many of the unfair labour practices among suppliers[54]. Given this history and context, based upon the evidence currently available from within and outside the programme, the likelihood that most of the current RBIs supported by RATE will lead to systemic change in any sector or location is judged to be low.
    [54] Locke (2013) ‘The Promise and Limits of Private Power: Promoting Labor Standards in a Global Economy’. Cambridge University Press.

SUMMARY ASSESSMENT – SUSTAINABILITY, SCALING AND SYSTEMIC IMPACT
OVERALL	Uncertain (limited evidence)
POSITIVES	Two of the RATE RBIs could possibly contribute to transformative change.
NEGATIVES	Sustainability is a challenge for almost all RBIs. Most RBIs aim to achieve incremental improvements in business capacity and behaviour, and most are very small scale compared to the size of the corporate sector. Likelihood that most of the current RATE RBIs will lead to systemic change is judged to be low.

Initial Lessons

Evaluation Questions:
What are the key factors determining success? What are the major factors constraining or enhancing progress towards the intended outputs, outcomes and impacts?
What could be done differently to improve programme relevance, implementation, output achievement, contribution to outcomes and impacts, systemic impact and with respect to the Sustainable Development Goals?
What are the main lessons for DFID, governments, companies and civil society in relation to responsible business affecting developing countries?

  1. The purpose of this section is to identify some of the initial lessons from RATE for DFID and other responsible business stakeholders. It is recognised both that RATE as a programme is only at its mid-term point, and that the challenge of improving the lives and environment of poor people through responsible business initiatives is immense. It is hard to identify clear success factors at this stage given the paucity of robust evidence. Success or otherwise, and the key factors responsible, will be more evident at the end of the programme than now. There is also limited scope to do things differently at this stage of the programme. The initial lessons that follow are based on the combined MTE evidence base: the experience of RATE-supported RBIs to date; initial findings from the sector study; and wider literature.

  1. The significant financial allocation for programme level lesson learning and evaluation within RATE reflected the need to generate better evidence about how support via RBIs to responsible business practices can have a positive impact on poor people. However, in a programme of this type, most of this better evidence needs to be produced by the various partner organisations. These vary in terms of their monitoring, evaluation and learning (MEL) experience and expertise, in the quality of the MEL framework within the grant proposal submitted to DFID, and in the level of resources allocated to MEL activities by each partner organisation. Assisting some of the partners with their logical frameworks has absorbed more resources from the NRI team, and taken longer, than envisaged. One of the lessons of RATE is that better appraisal of the MEL component of grant proposals, and more front-loaded support for grantees with less MEL capacity, is required. The NRI MEL team has been working with the RATE partners to raise understanding and action on improving organisational MEL systems, with various organisations increasing their investment in creating more robust MEL systems, but this will take time to bear fruit and implementation depends upon the partners. For example, UNGC is currently developing an organisational theory of change and a MEL system.

  1. The second lesson relates to the focus of the MEL effort within the programme. Gathering evidence on the contribution of programme outputs to the outcome (improved business diligence and accountability), and on the contribution of the outcome to impacts for poor people, is a particular challenge for this type of programme. RBIs are just one of many influences on business behaviour, and businesses are understandably reluctant to provide access to evidence that may be of commercial value or impact on their reputation. Gathering evidence on outcome-to-impact contributions is inherently challenging, not least because of the time-lag and causal steps between RBI activities, outputs, outcomes and eventual impacts. Gathering evidence on output-to-outcome contributions is more feasible and warrants greater emphasis within grantee MEL programmes. One of the lessons of the programme to date is that the collection of evidence on the extent to which RBI outputs have led to material changes in business practice that are likely to impact on poor people and their environment needs greater priority.

  1. There are general lessons emerging from the Theory of Change analysis and from experience beyond RATE. First, the business case for RB is variable and uncertain. It should not be assumed that responsibility makes business sense, at least in the short term (see Annex 6.3). Second, progress towards responsibility in business has been heavily concentrated in a small minority of reputation-sensitive companies and sectors. UNGC, the world’s largest corporate sustainability initiative with over 9,500 business members, covers just 2% of global GDP, 2% of listed companies, and 4% of people working in the private sector[55]. Evidence focused upon the market penetration and impact of product and supply chain standards also indicates that in some sectors the standard bodies may have hit a ceiling. Third, many international supply chains have developed into being extremely long, evolving, complex and opaque. Just understanding their supply chains, let alone acting to improve conditions within them, has proved to be a huge undertaking for the most committed of companies. If companies do not know what is going on – or do not want to – achieving impact is virtually impossible[56]. Fourth, there tends to be a sharp fall-off from commitments to action, particularly action in distant supply chains or beyond Tier 1 suppliers. A much higher percentage of companies have policies on human rights than carry out impact assessments, monitor or evaluate performance, or disclose information on policies and practices[57]. Fifth, such improvements as have been achieved in supply chains seem to have been focused on issues that are more straightforward to deal with: e.g. ‘basic improvements have been achieved in some areas such as occupational health and safety, but not in others (e.g. freedom of association, excessive working hours)’[58]. An impact evaluation of ETI in 2003-2006 found a similar picture[59]. Problems such as purchasing practices and living wages in supply chains that were correctly identified over ten years ago are still being discussed[60].
    [55] UNGC (2015, p.60)
    [56] World Employment Social Outlook, ILO (2015, p.145)
    [57] 2017 UNGC Progress Report. UNGC (2017, p. 47)
    [58] Locke (2013, p.174).
    [59] ETI IDS (2006)
    [60] Purchasing Practices: marrying the commercial with the ethical. ETI (2004). Purchasing practices and working conditions in global supply chains: global survey results. INWORK Issue Brief No. 10. ILO (2017). Action Collaboration Transformation (ACT) https://actonlivingwages.com/

  1. Finally, and related to the fifth point, much of the persistence of poor working conditions and labour rights, and negative community and environmental impacts are a systemic and structural feature of the current business and economic model, and the competitive drivers and risk environment of the global economy (see Annex 6.4). This, and the related points about the lack of a universal or sufficiently strong business case for the adoption of voluntary measures, limited RBI coverage of business, and poor governance in supplier countries, goes a long way to explain why the extent of improvements in global supply chains have been so limited and slow, and why much less progress has been made on fundamental issues such as freedom of association and living wages/incomes. Progress on these issues may require more fundamental changes to the business model.

  1. The overall lesson is therefore as follows: DFID and other donors need to be cognisant of the scale and depth of the challenge represented by irresponsible business, and realistic about the potential of more responsible business to tackle poverty. It cannot be assumed that any general progress on corporate responsibility, and any RBI, will necessarily generate significant benefits for poor people in developing/emerging economies within a reasonable timeframe or tackle the significant harms caused by irresponsible business. This may point to the need for a wider and more critical appraisal and selection process for the RBIs to be supported.

Conclusions and recommendations

  1. The RATE programme is funding a diverse portfolio of responsible business initiatives (RBIs). While employing a range of different influencing mechanisms, the common objective is to encourage and support more responsible business behaviour. The goal of the programme is to improve the well-being, safety and environment of poor women and men affected by business in developing and middle-income countries. The Mid-Term evaluation includes an analysis of programme performance against the revised programme logical framework and the theory of change, recognizing that the programme is at a mid-term stage, and that half of the initiatives funded are relatively new. Limited evidence is currently available on many of the evaluation questions.

  1. There is a strong case for supporting a programme on responsible business. The social and environmental costs associated with irresponsible business are huge, and the incentives for businesses to pay attention to these costs are increasing. However, there is huge diversity within business and wide-ranging responsibility issues to be addressed, as well as diverse responses from RBIs and companies. Outcomes are likely to be context specific, and the wider, non-programme evidence base for knowing what works in responsible business is limited, although there are exceptions (e.g. product standards). The business case, at least in the short term, is variable and uncertain. Much of the persistence of poor working conditions is a systemic and structural feature of global business and economic models. These models, combined with poor governance and weak labour rights in supplier countries explain the limited mainstream business case for action and limited progress (5.3, 12.3).

  1. RATE is a relevant, efficient and - at output level – effective programme (6.2, 7.2, 10.2). It is working with a good mix of appropriate RBIs (6.7). However, it is not clear that the programme is strongly enough targeted to maximizing impact on poor people in developing and emerging economies. The mechanisms or impact pathways employed by many of the RATE RBIs (and non-RATE RBIs) and their overall theories of change are long and extended, with many causal steps and major assumptions, for which past evidence is not that supportive. Most of the RATE grants have a relatively undifferentiated approach regarding women and marginalised social groups (6.10-11).

  1. The programme’s intended outputs are: Increased business outreach and networks; Improved standards, guidance, tools, reporting systems and innovation; Impact evidence generated and shared; and Government-led interventions demonstrate that they extend responsible business practice. An analysis of the programme against the logical framework suggests that at the output level, all the constituent initiatives (except for the UK NCP), are on or above target for most of the indicators in the new RATE logical framework. Output achievement is rated as good.

  1. There is currently limited evidence from RATE RBIs on outcomes and impacts. Overall, progress against the selected outcome indicators in the logical framework for which data is available has been positive (8.4). Other evidence on business behaviour change available from the RATE RBIs, as well as wider evidence on corporate behaviour change from the literature, is currently limited (8.16). Wider impact trends are mixed, and there is no evidence at this mid-term stage of RATE contributions to any of the impact-level indicators (9.2). It would be unrealistic to expect impacts at this stage in the programme, and arguably unrealistic to expect such impacts to be easily identified and attributable even in the longer term. RBIs are small scale compared to the scale of global business and its impacts. Based upon the evidence currently available from within and outside the programme, the likelihood that the current RBIs supported by RATE, with a few possible exceptions (11.8), will lead to systemic change is judged to be low (11.16).

  1. The overall lesson of the programme to date is that DFID and other donors need to be cognisant of the scale and depth of the challenge represented by irresponsible business, and realistic about the potential of responsible business to tackle poverty (12.4). While RATE is on track to achieve its outputs, the extent to which it will make a significant contribution to its intended outcome and impact is uncertain.

  1. In the case of the longer-term outcome – corporate behaviour change – this may partly be a function of the mid-term stage of the programme and/or the fact that more behaviour change has happened or is happening than has so far been documented. Either way, measuring and reporting the RBI contribution to corporate behaviour change needs to be prioritised. Identifying that change, and the contribution of the RBI to that change, is not easy, which is one reason why it is unlikely to happen if it is not prioritised (8.16).

  1. In the case of the intended impact – the safety and well-being of poor women and men in developing and middle-income countries – the uncertainty around the likely achievement of the programme is less a factor of time or measurement, although both are still real challenges. The more fundamental factor may be that some of the RBIs are unlikely to result in significant positive social and environmental impacts for poor people affected by business within a reasonable timeframe, for two main reasons. First, the theory of change linking outputs to impacts for poor people may not work effectively for all the RBIs. Businesses can become more responsible, accountable and transparent in many ways without this necessarily resulting in significant positive impacts for poor people in distant and extended supply chains. Second, even where the theory of change is reasonably robust, the depth and the scale of the social and environmental challenges associated with business, and the nature of the underlying causes, may limit what can be achieved through voluntary responsible business initiatives alone. Unfortunately, it cannot be assumed that general progress on corporate responsibility, and any RBI, will necessarily generate significant benefits for poor people in developing/emerging economies within a reasonable timeframe.

  1. The programme faces two main risks: (1) that it will not significantly improve the evidence base; and (2) that it will not significantly impact on poor people affected by business. The first risk can be addressed. Measuring and reporting on the contribution to corporate behaviour change needs to be prioritised in RBI monitoring and evaluation. In particular, the collection of evidence on the key step in the RATE theory of change – material changes in business practice that are likely to impact on poor people and environments affected by business – is the priority.

  1. The second risk is more difficult to address at this stage of the programme. All the funds have been committed and there is little scope or merit in changing the projects as designed. Looking forward, one conclusion is that a wider, more critical and systematic approach to the selection of RBIs may be required for any future phase. It is recognised that, even after RATE, there will be limited evidence to make that selection. However, for a donor such as DFID that is seeking to achieve and demonstrate positive impacts for poor people in developing and middle-income countries, any future programme should consider:

1. engaging closer to the locations of desired impact and/or with more thematically focused and targeted initiatives (e.g. sector, commodity, or issue);
2. selecting interventions, initiatives and organisations based on a clear analysis of the mechanisms being employed and actors targeted, with a plausible (or evidenced) theory of change linking RBI activities to impacts for poor people;
3. for mature RBIs, making recent and robust independent organizational impact assessments a requirement prior to any future funding decision.
4. targeting some of the more fundamental, difficult and long-standing issues such as living wages/incomes and enabling rights – and the connection between those issues and business practices - not only general RB initiatives or issues that have proved easier to tackle and are already well funded;
5. supporting more research and reflective learning on business-society-environment relationships, which underpin all efforts to influence corporate behaviour, and more in-depth analysis of changing trends within business and investment. The recent addition of the modern slavery and child labour research fund to RATE is a welcome example.

  1. Two other impact pathways currently unsupported by RATE may warrant consideration in any future programme. First, more support for accountability mechanisms, including strengthening worker/producer and community organisation and voice. Second, a more strategic pillar around engaging governments could be important as a necessary complement to voluntary initiatives (9.12-13).

  1. These are only suggestions at this stage. Further research and critical appraisal would be necessary for all future DFID-supported responsible business initiatives. Where new approaches are supported it is essential that DFID requires of grantees that strong monitoring, evaluation and learning systems are in place and provides funding for this where necessary. The most important selection criteria should be whether the RBI has a robust and plausible theory of change that extends directly and reliably to poor men, women and children in developing/emerging economies within a reasonable time frame. Any support also needs to be conditional on agreed outcome targets and acceptable levels of external transparency and accountability, including full corporate cooperation and access for evaluation and learning.
## Recommendations

  1. There are two sets of recommendations arising from the MTE: for RATE until the end of the current programme in March 2019, and for future DFID funding of responsible business post-2019. References to the relevant conclusions are given in parenthesis
RATE until 2019
The following recommendations are proposed for the remaining implementation period of the RATE programme until March 2019:
DFID should require RATE partners to improve their Monitoring, Evaluation and Learning (MEL) systems in three ways:

1. develop more robust organizational theories of change that extend down to poor people in developing/emerging economies, including associated assumptions, where these are not already in place (13.3, 13.7, 13.9).
2. generate and publish evidence on outcomes and impacts, specifically evidence of changes in the behaviour of business as it directly affects poor people and the environment associated with subsidiaries and supply chains (13.4, 13.8).
3. more mature RATE partners (ETI, ISEAL, GRI, UNGC) should commission robust independent organizational impact assessments where recent assessments are not available. This should be a requirement prior to any future funding decision (13.4, 13.7, 13.9)

DFID should commission synthesis studies by the EM team or others on priority issues and alternative mechanisms to guide future investment and research. The list of studies should be agreed in consultation with the EM and the RATE partners (13.9, 13.10, 13.11)

DFID funding post-2019 on responsible business
Given the immense scale of impacts of business on people and the environment – positive and negative – it is important that DFID continues to learn about and invest in responsible business initiatives (13.2). The following recommendation is designed to provide DFID with greater confidence in the outcomes and impacts of the investments made in this area.
DFID should continue to consider alternative options that deliver change ‘closer to-the-ground’, ensuring coverage of issues at the key business-worker/community/environment interface in developing and emerging economies, if it decides to fund additional work in this area, which compliments work that is being carried out around promoting responsible business practices across DFID’s country office network.

Annex 1: MTE Terms of Reference
Terms of Reference for RATE Mid-Term evaluation - Evaluation Manager
September 2017
Introduction
The Responsible, Accountable and Transparent Enterprise (RATE) programme focuses on businesses’ social and environmental risk management, and transparency and accountability of private sector companies. It is a portfolio programme, with DFID providing support to a range of partner organisations or Responsible Business Initiatives (RBIs). DFID is investing £21.8 million in the RATE programme (2014-2019) with nine partners receiving funding to date.
The programme has been underway since 2014 and the Evaluative Learning Manager was contracted in 2015. A Mid-Term Evaluation is now due and should be completed by the end of December 2017. The users of the findings of the MTR will be DFID, PMU, the grantees and implementing partners, and external stakeholders including developing country beneficiaries. These terms of reference set out the scope of the Mid-Term Evaluation.
The three key overarching objectives of the evaluation and learning are: a) Provision of internal and external learning to DFID and other organisations supporting business environmental and social risk management and transparency and accountability; b) Contribute to the evidence base on the end results for poor women and men of implementation of such mechanisms and practices by the private sector; c) Contribute to the evidence base on why private sector companies should engage in more responsible practices.
Purpose, Objectives and Evaluation Questions
The main purpose of the Mid-Term Evaluation (MTE) is to assess programme progress with respect to the achievement of desired outcomes, distilling key lessons to inform and improve programme design. The MTE covers the period since the inception of the RATE programme until October 2017.
The evaluation of the RATE programme will assess its impact, effectiveness, sustainability, relevance, efficiency and coverage according to the OECD DAC criteria and the assessment is employing theory based evaluation as it primary design.
The objective of the MTE is to provide an independent mid-term evaluation of the RATE Programme.

Table 1. Revised Evaluation Questions
Evaluation Questions
Relevance / What is the relevance of Responsible Business Initiatives (RBIs), especially RATE RBIs, to achieving sustainable development? Are there alternative approaches which are as or more relevant to sustainable development, which involve different types of corporation or non-corporate economic development?
Targeting / Are RBIs, particularly RATE RBIs, reaching companies of different kinds? Are these the most appropriate companies in terms of impact potential? / Are RBIs, particularly RATE RBIs, reaching affected workers (female, male), communities and environment? Are these the most affected groups and areas?
Programme effectiveness / How effective has the programme been in demonstrating how business (large and SMEs) can benefit, directly and indirectly, from better management of social and environmental risks and increased transparency and accountability? / To what extent has RATE built the capacity of and ownership for responsible practices amongst businesses and other stakeholders? / What are the major factors constraining or enhancing progress towards the intended outputs, outcomes and impacts?
Evidence of outcomes and impact / What are the outcomes of RBIs? What is the contribution of RBIs to corporate behaviour change (nature of changes in corporate decision-making, scale of changes vis-à-vis other corporate behaviour and vis-à-vis likelihood of achieving goals of RATE? / What are the impacts (positive, negative, expected and unexpected) of RBIs, particularly RATE RBIs, on poor women and men workers, communities and businesses affected by business in terms of securing and improving the wellbeing, safety and lives of poor women and men workers, communities and environments affected by business activity? / How effective are RBIs in achieving their intended impacts? / Which types of RBI interventions are most effective in achieving outcomes and impacts? / How effective are the different impact pathways [and individual interventions] with respect to gender and social difference?
Efficiency / Have resources been used efficiently in order to provide value for money and achieve results? / What could be done differently to improve implementation? Has this been a cost effective and cost-efficient investment? / How could value for money have been improved in the programme and costs contained without affecting delivery?
Sustainability and Scaling / To what extent are the outputs, outcomes and impacts of the programme likely to be sustainable? / What factors constrain or enhance sustainability? / What is the likelihood of business building on and scaling up the work of the programme?
Systemic impact / What is the systemic impact of Responsible Business Initiatives (RBIs), especially RATE RBIs? Can RBIs bring about a transformation of individual companies and sectors and under what conditions? / How do companies learn about RBIs? What are the incentives and disincentives for pre-competitive collaboration? How much alignment is there among companies, in particular sectors, with respect to sustainability issues? How does the nature of the industry itself influence responsible business performance at a sectoral level?
Learning Questions / What could be done differently to improve programme relevance, implementation, output achievement, contribution to outcomes and impacts, systemic impact and with respect to the Sustainable Development Goals? / What are the key factors determining success? / What are the main lessons for DFID, governments, companies and civil society in relation to responsible business affecting developing countries?

Methods
#### 3.1 Overall approach and methodology
The evaluative learning approach is based upon refining and testing the programme theory of change using evidence generated by the RATE learning partners, as well as by the Evaluation Manager. The EM will use different sources of evidence to test the theory of change and will use this evidence to analyse processes of change and the contribution of the RATE programme to it (Contribution Analysis). Specific sources of data include:
Key activities
- Gathering and analysing M&E data from partners
- Literature review (grey and academic literature) on key topics such as business case and development case for different types of interventions
- Secondary data analysis
- Sector review – development of a methodology to analyse sustainability in a sector and application in one test case, including stakeholder consultation
- Developing organisational summaries of evidence for grantees to comment upon (*extent of coverage to be proportionate e.g. with the funding received and the extent of progress of the RATE partner).
- Synthesis of overall programme evidence in draft report
- RATE Learning Partner workshop to present the draft findings of the MTE and gather learning partner inputs
- Submission of draft report to DFID and RATE partners and responding to comments
- Dissemination of report
In analysing evidence, we will pay attention to the quality of evidence and the evidence findings (extent outcomes achieved, conditions for success).
Key sources of data include: i) Partner M&E documents ii) Secondary Data; iii) EM sector studies iv) Literature Review.
Risks and challenges
The challenges outlined in the MTE TOR relate to the ability of RATE partners to access and share data from private sector companies as well as the broad ranging scope of the partner organisations, meaning that impacts are hard to capture and quantify.
Proposed process and timeline
Planning	August-Sept 2017
Literature Review	Sept 2017
Secondary Data Analysis	Sept 2017
Sector analysis and fieldwork	Sept-Oct. 2017
Meetings/skype calls with grantees	Mid-Sept – end Sept 2017
Organisational summaries shared with grantees for comment (For priority selection – to be agreed with DFID)	By mid Oct
Comments received from grantees	By end Oct
Evidence Review and Contribution Analysis against Theory of Change	By mid-Oct 2017
RATE learning partner workshop	18th October
Draft report submitted to DFID and learning partners	11.11.2017
Comments from DFID and RATE partners	21.11.2017
Final report submission	31.12.2017

Reporting, Deliverables and Roles
The MTE will be guided by the Terms of Reference and the Evaluative Learning Design (2016). A proposed outline for the MTE report is included in annex 1.
All data will be reported in a confidential fashion with data anonymized. A process has been set out for sharing findings with the grantees at both organisational and draft report stage, which will give them significant opportunities. The draft report will be shared with DFID as well as the learning partners for review.
The MTE will present the findings of the evaluation team. It is DFID’s intention that the MTE will be published, and it will be made publicly available on DFID websites and through other electronic means. Stakeholder workshops will be held as part of the MTE process and will involve sharing of preliminary findings. A briefing of findings for DFID is also envisaged.
The Evaluation Manager (EM) is responsible for conducting the MTE. The EM is contracted to provide DFID with an independent report and is accountable to DFID for the work.

## Report Outline

The draft outline for the MTE is set out in table 1. However, there may be minor modifications during the report writing stage.
The main report will be approximately 40 pages long, with limited additional information included in annexes as appropriate.
Element	Approximate lengths
Executive Summary	2 pages
Main report
Introduction	1 pages
Purpose, Scope and Objectives	1 page
Methodology	3 (including TOC)
Contextual Analysis	3
Findings	25 pages responding to Theory of Change
Conclusions	5 pages
Recommendations	2 pages / Recommendations / Wider insights for responsible business community of practice
References
Annex 1: Terms of Reference
Annex 2: List of Persons Consulted

Annex 2: MTE Methodology – additional information
Evaluation Design and Framework
An Evaluation and Learning Design Document was submitted to and agreed with DFID in 2016. This set out the key elements of the Evaluation Framework, namely the OECD DAC criteria (relevance, effectiveness, efficiency, outcome, impact and sustainability) and Evaluation Questions and the Theory of Change, including the associated assumptions and sources of evidence and data collection and analytical methods. This MTE report is organized against the Evaluation Questions and OECD DAC criteria, with the relationship between these and the theory of change laid out in the Evaluation Framework (Annex 3). The impact pathways have been identified and this represents a contribution to the understanding of how RBIs work – i.e. what are their mechanisms and how do they seek to influence change (either as an organisation or in terms of their specific activities funded by RATE), as well as to the assessment of their contribution to change.
Evaluation Questions
The Evaluation Manager (EM) drafted the Terms of Reference (ToR) for the Mid-term Evaluation in 2017 and these were approved by DFID (Annex 1). The evaluation questions in the ToR were taken from the Evaluation and Learning Design produced by the EM in late 2016 and were intended to cover the entire programme period. During the process of elaborating the MTE TOR it became apparent that some of the evaluations questions could not be answered at this mid-term stage, and that some additional questions would be more appropriate. The evaluation questions that differ from those in the ToR have been shaded in the Evaluation Framework (Annex 3). The Evaluation Questions cover issues of context, relevance, targeting, effectiveness, outcomes, impact, efficiency, sustainability and scaling, systemic impact and lessons.
Theory Based Evaluation
Theory Based Evaluation (TBE) underpins the evaluation of RATE, guiding the framing of a theory of change, data collection strategies and tools, and analytical strategies. TBE is relevant in situations of complexity (Stern et al, 2012) – for example, interventions that involve multiple components and variable modes of delivery or cover diverse contexts of implementation. TBE tests the hypothesis or theory of an intervention against the reality. The theory of change (combined with the evaluation questions) provides the framework for data collection and analysis. Evidence is collected for each causal stage of the theory of change and the evidence combined to test if each causal step holds true through scrutiny of the associated assumptions.
In the case of RATE, intermediary organisations are being funded to provide companies with principles, guidelines, tools and standards for responsible business. Thousands of companies worldwide use these principles, guidelines and standards, covering operations and sourcing from many different countries. Each company may have a variable structure and engagement in developing countries (operations, sourcing, acquisitions), and operate in diverse governance, institutional and environmental contexts. Each multi-national company may only adopt some of the principles, guidelines, standards and tools offered by Responsible Business Initiatives (RBIs). Many factors shape corporate decision-making other than environmental and social drivers. Experience has shown that access to private sector data on responsible business issues tends to be highly challenging for external evaluators. This complexity lends weight to the use of TBE as a means of validating the contribution of RBIs to plausible outcomes and impacts.
Additional notes on definitions
Key terms for the RATE programme evaluation include responsible business, transparency, and accountability. Responsible business (or corporate responsibility) definitions all share the belief that companies have a responsibility for the public good (Blowfield & Murray, 2014[61]). Corporate responsibility is voluntary and self-regulatory in nature. Corporate responsibility begins where the law ends (Davis, 1973[62]). Companies voluntarily accept responsibility for their actions, earning a licence to operate and thus creating value for stakeholders, including shareholders and society (Blowfield and Murray, 2014). The magnitude and type of responsibilities vary with corporate size and industrial sector and each sector faces different opportunities and threats. Corporate responsibility includes being consistent with ethical principles and conduct such as honesty, integrity and respect for others (Blowfield and Murray, 2014. Some definitions include environmental impacts.[63] Unless otherwise stated, this report uses ‘responsibility’ as meaning an approach to business that is diligent, transparent and accountable with respect to the social and environmental impacts and implications of its direct operations and supply chains[64]. A responsible business will be consistent with the UN Guiding Principles (UNGP) on Business and Human Rights.
[61] M. Blowfield and A. Murray (2014) ‘Corporate Responsibility’ Oxford University Press.
[62] Davis, K. (1973). The case for and against business assumption of social responsibilities. Academy of Management Journal 16, 312-322
[63] E.g. http://www.businessdictionary.com/definition/corporate-social-responsibility.html
[64] The term ‘sustainability’ is sometimes employed in the same way, but more commonly focuses on environmental issues.
There is a wide range of potential responsibility issues that may or may not be material to a company’s impacts: materiality to companies depends upon the nature of corporate activities and their impacts. Responsibility issues are not only social, environmental and economic, but include questions of inter-generational justice and sustainable development.[65] Tackling poverty may be perceived as an essential component for success or treated as a separate normative goal, even though poverty is intertwined with other social, environmental and economic sustainability issues and despite the obvious moral and instrumental rationale for corporate action and responsibilities (see Blowfield, 2013, p49[66]). Environmental sustainability challenges may be met, with richer people benefitting and poorer people remaining trapped in poverty, although not tackling poverty could amplify other sustainability challenges (Blowfield, 2013, p49-50). Corporate poverty impact (e.g. (Oxfam, 2009,[67] adopted by UNGC) covers five poverty dimensions of relevance, such as worker health[68] and five areas of corporate practice, such as value chains and institutions/policies.[69][70]
[65] Brundtland’s definition from the World Commission on Environment and Development, 1987) logically means that companies should also consider their historical responsibilities, stakeholder expectations and the rights / interests of next generations (Blowfield, M. (2013)’Business and Sustainability’ Oxford University Press, p6).
[66] Blowfield, M (2013)’Business and Sustainability’ Oxford University Press.
[67] https://www.oxfam.org/sites/www.oxfam.org/files/oxfam-poverty-footprint.pdf
[68] Standard of Living; Health and Well-being; Diversity and Gender equality; Stability and Security; Empowerment.
[69] i) Value chains, i.e. How corporate value chains affect poor people’s access to decent work, living wages and ability to sustain a business; Macro-economy issues; Institutions and Policy; Social implications of environmental practices; Product development and marketing.
[70] https://www.unglobalcompact.org/docs/issues_doc/human_rights/PovertyFootprintIndicator.pdf
Table 1: Key Terms
Diligence is defined as: businesses’ acceptance of their responsibility to understand the social and environmental risks they can pose to others; their approach to managing potential risks; how they monitor their performance in relation to relevant risks; and their transparency about that performance.
Transparency is a pre-condition for accountability. One definition is: the “lack of hidden agendas and conditions, accompanied by the availability of full information required for collaboration, cooperation, and collective decision making.”[71] In current business initiatives transparency is demonstrated through sustainability reporting (e.g. by measuring and reporting on material impacts).
Earlier definitions of accountability focused upon the learning process for companies, but did not reference what the company has taken responsibility for.[72] More recent definitions include corporate acceptance of responsibility, including disclosure and transparency[73]. The DFID RATE Business Case reflects recent changes in the normative frameworks on Business and Human Rights[74], by defining accountability as ‘how businesses take people’s views into account; how they identify and communicate the social, environmental and human rights responsibilities they accept; and how they address their obligation to provide remedy’.
[71] http://www.businessdictionary.com/definition/transparency.html
[72] Stakeholder engagement and is about ‘learning and change: ‘learning about the organization itself, about those who have a relationship with it, and learning about its place in the larger scheme of things.” (AccountAbility, 2002: 5).
[73] “The obligation of an individual or organization to account for its activities, accept responsibility for them, and to disclose the results in a transparent manner. It also includes the responsibility for money or other entrusted property.” http://www.businessdictionary.com/definition/accountability.html
[74] In the UN Guiding Principles on Business and Human Rights there are three key pillars – the State duty to protect human rights, the corporate responsibility to respect human rights and the need for greater access to effective remedy.

Safety includes workplace safety (e.g. fire, buildings) and safety in the local environment where people live (e.g. water pollution). Well-being encompasses the outcomes of businesses’ social and environmental risk management (e.g. working conditions) as well as access to remedy (eg. compensation, complaints mechanisms).
Mid-Term Evaluation Process
The Terms of Reference for the MTE were developed by the Evaluation Manager in 2017, drawing upon the Evaluation and Learning Design Document (2016) (Annex 1). The MTE covers the period up to October 2017, and eight of the twelve RBIs. The three most recent grants, and the UK National Contact Point, were not reviewed. The main objectives of the MTE are to assess programme progress and identify key lessons to date. The MTE TOR include the amended evaluation questions (i.e. the questions set out in the original TOR for the Evaluation Manager MEL contract, but amended in agreement with DFID for the MTE). The evaluation employs the programme logframe and evidence assembled on the theory of change, nested impact pathways and associated assumptions. A simple scoring system has been developed for each of the main evaluation questions.
Developing a Baseline
It was proposed in the Evaluation and Learning (EL) Design Document that a baseline would be developed. However, the EM later agreed with DFID that a conventional baseline would not be appropriate in the RATE context, particularly as a steady stream of new grantees was being funded (each requiring support in logframe development or refinement). This meant significant variation in the timing of when organisations first received funding. At the time of writing the EL Design Document, it was already clear that a staggered baseline would be required (covering 2014 and 2015 start dates), but as new grantees were funded the stretching of this period, essentially meant that a conventional baseline became less feasible and not value for money. Instead, the EM efforts would focus upon the Mid-Term Evaluation in terms of gathering evidence to test the theory of change and to answer the evaluation questions. Baseline plans also included a proposed sector study. This was rolled forward from baseline to MTE, with additional work added to year 3 for updating the evidence from the wider literature and for final evaluation.

Figure 1: Plans for Baseline (which became part of the MTE)

Literature review
Draft methodology
Review proposed methodology and identify literature with partners
Review of literature (staggered i.e. year one focus on corporate reporting; year 2 on sustainability standards, year 3 on Multi-stakeholder learning)
Share/discuss findings with RATE partners

Global & Sector-Country Studies
Review conditions in one global sector using secondary data
Develop sector analysis framework
Select one or two country cases for situation analysis using secondary data

Empirical case study
Sector case study in one country to gather data on corporate practices in operations & supply chain & impacts
Engaging stakeholders to validate findings
(Resource dependent)

Sampling and Selection Strategy

Selection of RATE RBIs
It was agreed with DFID that greater emphasis would be placed on the larger, more mature RBIs for which more information was likely to be available: ISEAL, GRI, UNGC and ETI. Evidence was still sought for the other RATE RBIs, but it was agreed with DFID that the MTE would not cover the three most recently approved grants (UN Foundation, Humanity United, and British Academy). The UK NCP is being peer reviewed in 2018 and so was also not covered by this MTE.
Mapping exercise
The Dow Jones Sustainability Index (DJSI) is the leading index of sustainability-driven companies worldwide. Companies are invited to join based on largest companies by market capitalisation. The 2016 starting universe of companies comprised 3450 companies. This list was taken as the sample for this study, as it is an extensive publicly available database of more than 3000 of the largest global Multi-National Companies (MNCs). The DJSI uses the Global Industry Classification Standard (GICS), the most commonly used company categorisation tool that was originally developed by MSCI and Standard & Poor. The GICS has a typology of industry groups[75]:
[75] Energy, Materials, Capital Goods, Commercial & Professional Services, Transportation, Automobiles & Components; Consumer Durables & Apparel, Consumer Services, Media, Retailing, Food & Staples Retailing, Household & Personal Products, Health Care Equipment & Services, Pharmaceuticals, Biotechnology & Life Sciences, Banks, Diversified Financials, Insurance, Real Estate, Software & Services, Technology Hardware & Equipment, Telecommunication Service, Utilities.
Four sectors were identified to be more likely to have direct impacts in least developed countries (based on consultations with the RATE partners, particularly GRI), through production, service provision, and contracting, and therefore more likely to involve companies participating in RATE funded initiatives to compare with performance of companies not participating in RATE funded initiatives but operating in the same sector. The sectors selected were: Agriculture; Textiles; Electronics; and Extractives. Table gives an overview of the GICS industry groups that were selected for the baseline study following these four sectors.

Table 2 Overview of GICS industry groups studied
RATE sector	GICS industry group(s)	Number of companies in DJSI starting universe 2016
Agriculture	Food & Staples Retailing	67
	Food, Beverage & Tobacco	157
Textiles	Consumer Durables & Apparel	110
	Retailing	115
Electronics	Technology Hardware & Equipment	119
	Semiconductors & Semiconductor Equipment	68
Extractives	Materials	282
Across these four sectors	Transportation	136

Note that the GICS industry groups are very broad, so that Consumer Durables & Apparel also includes categories such as home furnishings, consumer electronics and leisure products. However, using GICS industry groups is the only way to capture all the companies on the DJSI. The full list of industries included in each industry group can be found online. In three industry groups, Food Beverage & Tobacco, Technology hardware & Equipment and Transportation, companies were added from other benchmark lists:
Table 3: Other Benchmarks Used
Industry group	Companies added	Retrieved from benchmark
Food, Beverage & Tobacco	Mars	Oxfam Behind the Brands
	Koninklijke FrieslandCampina	Access to Nutrition Index
	Ferrero	Access to Nutrition Index
	Arla foods	Access to Nutrition Index
Technology Hardware & Equipment	Celestica	Corporate Knights
Transportation	Aeroports de Paris (ADP)	Corporate Knights

Sector Study Selection
The selection of sector for a sector study was influenced by the earlier discussions with GRI and decisions on priority sectors for the mapping exercise (see above). All the four chosen sectors – agriculture, textiles, electronics, extractives – are judged to have significant poverty impact. Significant sector transformation work has already been undertaken on agriculture and forestry sectors (see Molenaar et al, 2015) and so was deemed less of a priority. The Evaluation Manager selected the apparel sector, to draw upon pre-existing knowledge of the apparel sector in Asia (based upon a recently completed, three-year evaluation of the Trade and Global Value Chains Initiative, which include the Bangladesh ready-made garment sector), as well as the in-depth knowledge of an in-country researcher on both Dhaka and Bangalore apparel sectors. This selection was discussed with DFID as part of the contracting process for the in-country researcher.
Development of Indicators
A programme logframe had been developed prior to the engagement of the EM, but the EM was responsible for reviewing and refining the overall logframe in discussion with DFID. This process was an extended exercise, because of the new grantees that were funded during this period. Each grantee has a RATE project or partner logframe. The EM has worked with each grantee to develop these from scratch or to refine their existing logframes. These logframes nest or cascade within the overall programme logframe: there is variation in terms of the level that they reach vis-à-vis the programme logframe (short, medium or longer-term outcomes and impacts) and it has not been possible for the EM to completely redevelop the partner logframes given the contracting that had already occurred.
The EM has employed the logframe in this MTE, as well as the use of theory-based evaluation, because of the scale and scope of the work of the intermediary partners. As stated in the main report, the logframe indicators represent just one slice of what is a highly complex reality - It has been challenging to identify a common set of indicators for the overall theory of change of the programme, because the partners are seeking to influence global business impacts in developing /middle income countries. Many of the RATE partners have developed metrics and indicators within their standards, codes and tools. There is limited consensus internationally on what a limited set of metrics are that could represent business poverty and sustainability impact. Thus, to assess programme performance we have referred to the programme logframe, but have also sought to integrate within this assessment of contribution, an analysis of the theory of change assumptions through the application of relevant evidence, including a specific sector study in which indicators have been delineated. The final evaluation will include a more detailed contribution analysis.
In the sector study (Bangalore Apparel), a draft set of indicators were proposed drawing upon the Oxfam Poverty Impact Framework and with some additional indicators relating to sector level changes. In designing the study for the MTE work, the Evaluation Manager reviewed a set of indicators used to analyse Sector Transformation using scorecards by Molenaar et al (2015) and the indicators used by the FutureFit Benchmarking organisation for individual corporate success on sustainability. Ultimately, it was decided that the most appropriate set of indicators to use for the apparel sector could be taken from the Higgs Facility Tools, which are employed within the apparel industry and were developed by the Sustainable Apparel Coalition (SAC)[76]. The Higg Facility Tools measure the social and environmental performance at individual factories, but the Evaluation Manager adapted them to make a sector-level assessment. This framework could be adapted to use in other types of sectors beyond apparel, and the Evaluation Manager emphasizes the importance of sector-wide performance evaluation, not only individual corporate analyses, to gain a better idea of the overall progress of RBIs with respect to responsible business. More work is planned to unpack the contribution of RBIs, drawing upon stakeholder perspectives, but particularly, to explore the potential footprint of RATE RBIs.
[76] https://apparelcoalition.org/the-sac/
Data Collection Methods
The Evaluation and Learning Design Document agreed with DFID set out the planned key methods for data collection. These included:
- Synthesis and analysis of existing evidence to identify lessons and gaps
- Use of evidence and lessons from RATE partner organisations
- Sector Study
- Secondary Data Gathering and Analysis (including mapping of GRI against Dow Jones Sustainability Index; mapping of indices and benchmarks).
More detail is provided on each of these data collection methods below. The EL Design Document explained that primary empirical evidence would not be collected by the Evaluation Manager, due to the scale and scope of the RBI partners and the length of their theories of change, which meant that any primary data collection with beneficiaries could not be representative and that applying the available resources to analysis of partners’ evidence, evidence within the secondary literature and from one sector study would represent an approach most likely to generate evidence and the greatest value for money.
Please note: Additional funds were requested for two additional global sector study and a RATE case study, but funds were not available. The EM did explore the possibility with one of the RATE partners that has a more targeted, geographical focus (methodologically offering a stronger possibility of primary data collection and analysis), but the partner could not participate due to a lack of resources/funds and their participation was essential to enable access to the participating companies.
Synthesis and analysis of existing evidence
A comprehensive review of the literature was planned. Drawing upon the EM team’s knowledge of the field it was decided to focus upon the areas where it is known that there is more evidence available, mainly because the impact pathways in question are more mature. As well as the focused evidence reviews (on corporate reporting/product standards) the Evaluation Manager also collated and analysed a large amount of grey and academic literature, employing a snowball approach (e.g. conducting web searches, gathering studies from the RATE partners, stakeholders, academics, list servers and practitioner networks, and business and industry magazines (e.g. Ethical Corporation). The topics are wide-ranging and include general material on corporate responsibility, but also on the RATE grantees themselves, and on specific issues (e.g. landscape approaches, Multi-Stakeholder Initiatives, Global Production Networks and Global Value Chains, labour rights, living wages, living income, modern slavery, child labour, climate change, poverty impacts etc. The most systematic reviews conducted by the Evaluation Manager focused upon a) corporate sustainability reporting, b) evidence on product and supply chain sustainability standards. These are explained in more detail below:
Corporate Reporting Literature review
A literature review on one of the most widespread and important tools used by RBIs – corporate reporting – was planned and implemented and the findings shared with the RATE partners (at a learning event). The research questions, drawn from the programme theory of change, guiding the literature review were:
What is the quality and availability of the evidence base on corporate reporting initiatives?

What is the effectiveness and impact of corporate reporting on poor workers and communities, and the environment affected by business?
The methodology employed in the literature review involved an initial search of Corporate Reporting and Transparency in the literature using the following search terms: responsible OR sustainable* AND business OR corporate AND reporting OR disclosure. This provided the authors with an idea of the size of the literature available. A refined search was then conducted using eighteen specific search terms to narrow the focus. Four databases were searched, namely Scopus, Science Direct, Business Source Premier, and Web of Science. The eighteen search terms were: effectiveness, social, environment, poverty, impact, “supply chain”, “human rights”, audit, evidence, “business case”, “financial performance”, transparent*, effectiveness, “social performance”, community, worker, “competitive advantage”, “firm value”. This search produced approximately 2,000 articles per database with a total of 7,496 articles. A preliminary assessment of these articles for retention was conducted by simply reading the titles; those that had relevance to the topic – the effectiveness or Impact on business, workers, communities and the environment - were retained for further assessment. A total of 676 articles were retained. A double-blind review of all the abstracts (676 in total) was then conducted by two researchers who selected relevant abstracts according to three different categories: a) generic literature; b) literature on business benefits with the potential of empirical data; c) benefits to workers, communities, local and global environment with the potential of empirical data. In cases where there was no consensus, the reviewers discussed and agreed whether and where to include the abstract. This article presents the findings of the review of c) only. This category included 66 articles (two were eventually excluded for non-relevance). A tabulation of key findings was undertaken, before the drafting of the literature review. Limitations with this study are discussed under the relevant section below.
Product and Supply Chain Sustainability Standards Literature Review
A comprehensive review of the literature has been undertaken by the Evaluation Manager, drawing upon the following sources of evidence and activities:
Detailed, critical analysis of two recent systematic reviews, including analysis of the methodology employed and the findings:
  - Oya, C., F. Schaefer, D. Skalidou, C. McCosker, L. Langer (2017) Effects of certification schemes for agricultural production on socio-economic outcomes in low-and middle-income countries: a systematic review’
  - DeFries, R.S. J.Fanzo, P. Mondal, R. Remans and S. A.Wood (2017) ‘Is voluntary certification of tropical agricultural commodities achieving sustainability goals for small-scale producers?
- Review of a number of reports from ISEAL impacts webpage and telephone interview with ISEAL
- Review of key grey literature: e.g. the latest State of Sustainability Initiatives report (Lernoud et al, 2017); A DFID funded three-year theory-based evaluation on the poverty impact of sustainability standards, which itself includes a review of the latest evidence (Nelson and Martin, 2013); Theoretical and empirical work on sector transformation theory (Molenaar et al, 2015) etc.
- Drawing upon the longstanding engagement of Evaluation Manager team members with ISEAL and with various sustainability standards, including Fairtrade, Rainforest Alliance, Utz Certified etc and an academic track record on the topic of the effectiveness and impact of sustainability standards (see https://www.nri.org/development-programmes/equitable-trade-and-responsible-business/publications).

Use of evidence and lessons from RATE partner organisations
The Evaluation and Learning Design Document indicated that the EM would encourage the RATE partners to strengthen their MEL systems and would draw as far as possible upon the evidence generated by the partners, but also recognized the limits to the evidence likely to be available.
Evaluation data and reports were requested from each of the RATE partners. All the studies and data made available by the partners were collated and systematically analysed. Summary organisational analyses were drafted using the basic programme theory of change as a guide and drafts were shared with each of the grantees. The drafts were revised (sometimes more than once) to achieve agreement on the analysis. These organisational analyses represent the first step in the contribution analysis of the programme theory of change by the EM, which was followed by an assembling of the evidence against the theory of change and an initial exploration of the impact pathways to draw lessons.
Sector Study
The sector study seeks to test the overall programme theory of change in a specific sector or set of sectors. The aim was to explore the current situation on responsibility in business practices in the ready-made garment sector in two specific locations (Bangalore and Dhaka); to determine whether there has been discernible change over the past five years towards more responsible business practices at the sharp end of the value chain; and to identify the contribution of RBIs in general, and RATE-supported RBIs to that change.
Because of the complexity and length of the programme theory of change a sector study and the challenges of gaining access to data on changes in corporate behaviour (so much of which is kept confidential for reasons of commercial sensitivity), while it is quite feasible to gather evidence on programme outputs, it is harder to gain comprehensive and reliable information on the middle part of the theory of change. It was judged feasible to gain a picture of the ground level situation in one or two selected industries to shed light on overall trends (e.g. Are things improving or worsening for target beneficiaries and environments?).
The Evaluation and Learning Design Document envisaged the sector study comprising two stages: Firstly, reviewing conditions in one global sector using secondary data, developing a sector analysis framework and selecting one or two countries for situation analysis; Secondly, conducting a sector case study in one country to gather data on corporate practices in operations/supply chains and impacts, and engaging stakeholders to validate findings. In planning the MTE, the Evaluation Manager was keen to cover the empirical stage, but this was not feasible during the implementation, but it will be completed during 2018 as part of an annual cycle of analysis, fitting with the more staggered approach agreed with DFID as being more appropriate to the programme than conventional, less complex programme evaluation approaches (i.e. baseline, MTE and final evaluation). A planned field visit by the EM team and stakeholder interviews in Bangalore, further document review for Dhaka apparel sector and key informant interviews in the UK garment supply chain are now planned for 2018.
The sector study included a detailed structured document review by an in-country researcher covering Bangalore ready-made garment industry.
Key steps included:
- Study Design
- Selection of sectors for case study (see Sampling and Selection, section 3 above)
- Development of the framework (based upon the Higgs Facility Tool Indicators). The framework uses the same headings as used in the Higg Facility Tools developed by the Sustainable Apparel Coalition (SAC)[77]. The Higg Facility Tools measure the social and environmental performance at individual factories.
  [77] https://apparelcoalition.org/the-sac/
- Identification and collation of key reports and data (see data sources in Table 4 below)
- Analysis of the key reports against the agreed framework
- Production of a detailed analysis
- Production of a synthesis report of findings, including bibliography.
66 reports and articles were included in the sector document review and analysed. A summary of key data sources employed in the sector study are as follows:
Table 4: Data sources (2012-2017) used in the sector study
	Indicators	Identified Sources
1	Social	NGO reports on RMG sector (BBA, Cividep, etc.) / Issues highlighted by international organisations (FLA, FWF, ILO, SAI, UN Women, CARE, C&A foundation, BSR, Business & Human Rights Resource Centre, CCC, Solidaridad, etc.) / Worker union reports or campaigns (GLU, GATU, etc.) / Government- AEPC, Textile ministry, Labour ministry / Impact reports by standards and capacity building organisations (SAI, FWF, Impactt, etc.) / Articles, Journals and news reports / RATE grantees website (only for references to projects and possible links to South India)
2	Environmental	NGO reports on RMG sector (TERI, etc.) / Issues highlighted by International organisations (Greenpeace, BCI, UNEP, World Bank, Business & Human Rights Resource Centre, etc.) / Articles, Journals and news reports / Worker union reports or campaigns (GLU, GATU, etc.) / Impact reports by standards organisations (ISO14001, REACH, Eco-Textile Certification, ZDHC, etc.) / Government: / Pollution prevention law in India, especially Bangalore (Pollution prevention board) / Government (AEPC) / RATE grantees website (only for references to projects and possible links to South India)
3	Community impact	NGO reports on community issues and impacts / CSR spend reports of brands (only top 5 to 10) and suppliers linked to RATE projects. / Review sustainability reports of brands (only top 5 to 10) and suppliers linked to RATE projects.
4	Transparency, public disclosure & ethics	Annual corporate and financial reports- available on websites / News reports on ethical issues in Indian companies / Local initiatives
5	Brand/buyer responsible business behaviour	Brand sustainability reports (top 5 to 10) and initiatives (i.e. implementation of standards, projects and disclosures) / Review of responsible business initiatives in India

Secondary Data Gathering and Analysis
The Evaluation and Learning Design Document set out some of the key secondary statistics that would be collected to answer the evaluation questions. Data was collected on the key indicators encapsulated within the programme logframe – see programme logframe summary in Annex 7 for more details.
It was also planned that the reach of RATE RBIs in four sectors would be mapped as a contribution to the evidence to be used to test the reach and response assumptions in the programme theory of change. The purpose of this mapping exercise would be to establish what proportion of companies are using RATE RBIs and the proportion of companies which are not. Four sectors were selected – agriculture, textiles, electronics and extractives (see Sampling and Selection discussion above). The mapping would give an idea of the coverage of the RBIs in the bigger global business context. The initial focus was on GRI, who made a major contribution to this exercise in a collaborative effort with the EM. GRI is the most widely used standard used for corporate sustainability reporting worldwide. The mapping would analyse the four selected sectors and the proportion of companies participating in GRI. It would also analyse the level at which GRI participants are reporting, e.g. are they providing third party assurance of their corporate reporting or not.
Starting with the Dow Jones Sustainability Index (DJSI), the leading index of sustainability-driven companies globally, we have identified a starting universe of 3450 Multi-National Companies (MNCs). This list was taken as the sample for the study, against which we have focused upon four sectors, agriculture, electronics, extractives and textiles, identified through stakeholder discussions as likely to have some of the most direct impacts in developing countries through production, service provision and contracting. The mapping exercise has established the proportion of companies reporting against the most recent version of the guidelines (G4). The food, beverage and tobacco industry group had the highest proportion (29%) of companies reporting. The percentage of reports that have external assurance varies across the industry groups. to the M&E team will map the list against the other RATE initiatives to establish the reach of individual RATE initiatives and combined.
The sampling strategy is explained above. The data sources for the mapping exercise are as follows: The GRI Reports List was used (version of 1 June 2016) This document contains all centrally collected data points presented in GRI’s Sustainability Disclosure Database for reports published from 1999 until present. The Sustainability Disclosure Database includes sustainability and integrated reports that GRI is aware of. Some reports may be omitted, particularly those in non-Latin scripts or those not published online. From this file, the database for 2015 was used. Reports based on the GRI Guidelines, which include a GRI Content Index are classified as "GRI Reports". Reports, which refer to the GRI Guidelines without having a GRI Content Index are included as “GRI - Referenced” reports in the Sustainability Disclosure Database and are not considered to be GRI Reports. Sustainability/Integrated Reports, which do not refer to the GRI Guidelines, are classified as "Non-GRI" Reports. These last two categories are not counted as reporting against GRI guidelines. The DJSI 2016 starting universe was downloaded from www.sustainability-indices.com/images/invited-universe-djsi-2016.xlsx.The companies from the DJSI list were compared with the GRI Reports List to see which companies have reported against GRI guidelines in 2015. This was done through various MS Excel functions[78]. The findings of the mapping exercise are included in Annex 10.
[78] VLOOKUP() exact; VLOOKUP() approximate, supplemented with case by case manual checking of company names; MATCH() the result to the row number in the GRI Reports List and INDIRECT(CONCATENATE()) to retrieve additional fields for the company.
Analysis of indices and ratings of corporate performance
A mapping of key indices and ratings was conducted in the early stages of the MEL work by the EM and initially it was envisaged that further tracking and analysis of corporate performance in these indices might give an indication of their trajectories (improving or worsening) on different topics and that potentially this could be traced back along the theory of change to the uptake of RATE RBI initiatives. However, there is a large and growing number of such indices and ratings and many do not publish the criteria employed to rate companies. The strongest contenders for inclusion and analysis were judged to be the Dow Jones Sustainability Index, Corporate Knights (general sustainability performance focus), Corporate Human Rights Benchmark (human rights focus), Know the Chain (forced labour focus), Carbon Disclosure (climate mitigation), and agriculture, food and beverage sectoral indices (sectoral). A preliminary analysis has been undertaken, but it is planned that a follow up analysis will be undertaken by the final evaluation to provide time for changes in corporate position to become clear – and given the scale of this task potentially only for specific sectors.
Recognizing the inherent challenges with many of these benchmarks and indices, one RATE partner has successfully sought DFID funding through RATE to do a more detailed qualitative assessment of corporate reporting on human rights impacts. Their work has been reviewed as part of the wider RATE evaluation work. Further, DFID has recently funded the World Benchmarking Initiative (WBA) which aims to ‘develop, fund, house and safeguard free, publicly available corporate sustainability benchmarks aligned with the SDGs. It is therefore envisaged that the WBA may be able to provide more comprehensive analysis for the final evaluation report on corporate performance.
Gender and Social Difference
The target groups for the RATE programme are principally workers in global supply chains, but also local communities and smallholders in agricultural supply chains. These groups can be further differentiated. Among workers there is variation in work position (permanent, seasonal, contract, homeworker etc.), as well as along lines of identity (gender). In wider communities, various lines of differentiation exist (age, gender, caste, class, spatial location etc.). In terms of the evaluation, the wider challenges relating to the generation of, or access to evidence also represent barriers to disaggregation along the lines of gender and social difference. Further, empirical work in the sector study will ensure that the perspectives of women and marginalized groups are obtained. Differentiation of impact by social group will be analysed and integrated into the study of the ready-made garment sector.
Information from the sector study, and such information as is available from the RBI MEL systems, will inform the final RATE evaluation. Very limited information is available at this stage on outcomes and impacts in relation to gender, poverty, human rights and other cross-cutting issues.
Analytical Methods and Approaches
Evaluation questions, appropriate designs and methods and programme attributes all need to be reconciled when designing impact evaluation approaches (Stern et al, 2012[79]). The RATE programme exhibits aspects of complexity[80]. In other words, some aspects of the programme and the contexts in which RBIs and target companies operate have emergent properties, where multiple agents and processes influence each other in unforeseeable ways. This can result in non-linear change. Contribution Analysis is particularly relevant in the case of P4F as it is a theory-based approach that aims to confirm that an intervention is a contributory cause to a given outcome (Stern et al, 2012). Contribution claims are based upon a theory of change verified through evidence which can also account for the role of other relevant causal factors[81]. Thus, evidence can be drawn from both the data or results generated by a specific programme and from external research or academic literature available to provide wider contextual evidence. Once the contribution claim has been tested against available evidence, further evidence can be sought, and the claim can be revised and strengthened. While there are a variety of tools that can be used, at the core, contribution analysis relies on six key steps, described below in Table 5 below, including its application with the RATE programme[82].
[79] Stern, E., N. Stame, J. Mayne, K. Forss, R. Davies, B. Befani (2012) ‘Broadening the Range of Designs and Methods for Impact Evaluation’. DFID Working Paper No. 38. https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/67427/design-method-impact-eval.pdf
[80] – e.g. long timeframes for impact to occur, elements of non-linearity, diversity amongst the impact pathways and strategies employed by the partner organisations (some are more standardized, while others are more customized, many are comprehensive in nature while some are more targeted) etc.
[81] Mayne, J. (2012). Contribution analysis: Coming of age?. Evaluation, 18(3), 270-280.
[82] As described in Mayne, J. (2008) Contribution Analysis: An approach to exploring cause and effect, ILAC methodological brief, available at http://www.cgiar-ilac.org/files/ILAC_Brief16_Contribution_Analysis_0.pdf

Table 5: Key steps in Contribution Analysis and the approach in the RATE evaluation
Contribution Analysis Steps (after Mayne, 2011)	Approach in RATE Evaluation
1: Set out the attribution problem to be addressed	Evaluation Questions; OECD DAC Criteria
2: Develop a theory of change and identify risks to it	Programme theory of change developed through consultation with RATE partners, although still requires further development and consultation prior to final evaluation.
3: Gather the existing evidence on the theory of change	Evidence gathered from diverse sources of data (e.g. extended literature reviews, RATE partners’ evaluation evidence, sector study etc).
4: Assemble and assess the contribution story, or performance story, and challenges to it	Data gathered assembled in the MTE to assess progress against the logframe (a relatively limited set of indicators against outputs, outcomes and impact) and against the theory of change (which includes more causal steps especially at outcome level, e.g. short, medium and longer-term outcomes) plus associated assumptions and nested impact pathways.
5: Seek out additional evidence	Further evidence will be collected during 2018 and 2019 to expand the analysis and to test contribution claims further. Consultations with RATE partners and stakeholders will continue, with particular efforts to extend discussions with a wider set of stakeholders. More detailed work is planned on the sector study, including in-country visit and interviews with stakeholders.
6: Revise and, where the additional evidence permits, strengthen the contribution story	Conducting the final evaluation and strengthening the contribution story.

At this MTE stage it is challenging to conduct a Contribution Analysis, because of the early stage of implementation of several of the grantees. In the final year, the EM will apply Contribution Analysis to draw conclusions on P4F contribution to any observed changes. A range of hypotheses explaining why changes have occurred will be generated and then evidence will be mapped against them to understand how and why these changes have occurred. Contribution Tracing (i.e. quantitative assessment of contribution claims) is not, however, planned for the final evaluation, given the complexity of the programme/context and limitations on evidence anticipated.
Please note: Due to the timescales of implementation and anticipated impact for some of the RATE partners, it is likely that evidence collected to date in this MTE and that will be assembled and analysed for the final evaluation will not be generalisable to the entire programme and so it may only be possible to assess contribution of specific impact pathways (e.g. corporate reporting, product standards) and for some of the more mature initiatives. However, the RATE Evaluation Manager will continue to support the RATE partners in strengthening their MEL systems to ensure that the partner organisations deliver improved evidence and lessons in the future. One of the key recommendations of this report is also that improved MEL systems are prioritized by the RATE programme and DFID going forwards.
Limitations
Overall, there are aspects of the RATE programme in terms of its inherent attributes which present challenges for evaluation. The RATE programme is funding a diverse group of intermediary organisations. These tend to work on a global scale with large numbers of companies on a range of sustainability issues, and through a variety of influencing strategies. Some of the partners receive funding for small projects, and others for their entire strategy. This internal variation, the scale of operation of global businesses, the multiple factors shaping corporate behaviour (including major global political-economy forces) and the challenge of accessing relevant global measures and accessing private sector data, means that it is therefore extremely challenging to evaluate RATE as a programme in terms of its contribution to outcomes and impacts. Due to these challenges, the general evidence base for responsible business is limited. Most of the RATE-supported RBIs are at an early stage of their DFID funding and therefore have limited evidence.
Specific limitations associated with individual methods employed within the evaluation are as follows:
Literature Review: Because the theory of change is relatively complex and due to the scale/scope of the RBI target (i.e. essentially global business and its impact in developing and middle-income countries) it is not easy to isolate literature streams for analysis. There is a vast literature, for example, on both Corporate Social Responsibility (CSR) and on sustainable supply chain management, which could not be covered here. We focused our analysis upon two areas which are fairly mature impact pathways and for which some evidence would potentially be available: Corporate reporting as a specific instrument, seeking empirical evidence of the relationship between corporate sustainability reporting and corporate behaviour and impacts and product/supply chain standards.
On corporate sustainability reporting, we have only analysed the academic literature, which includes a natural time lag and may not represent current practice in responsible business. An analysis of the grey literature is needed to complement this literature review, given that it could be more reflective of current practice and/or may present more empirical evidence, although attention is required with respect to the quality of evidence presented. Exploration of stakeholder expectations with regard to the potential contribution of RBIs is also important, particularly with respect to social sustainability goals. The Evaluation Manager did request studies known to the RATE partners, and also interviewed key informants in our own research and practitioner networks to identify potential grey literature, as well as conducting web searches. However, the quality of the evidence in the grey literature is often weak, methodologically speaking and with potentially high levels of bias given the self-reporting nature of the work. The commercial sensitivity of much of the evidence from within companies means that it is very difficult to obtain and publish such evidence (M. Blowfield, pers. comm).
In the field of product/supply chain standards, there is a wider set of consultancy documents available, of variable methodological quality and academic work is limited, but growing.
Sector Study: The sector study drew upon secondary evidence. Empirical work is planned to extend this study in 2018 and 2019 to support the final evaluation.
Secondary Statistics: There is no international consensus on one set of indicators for responsible business impact. The statistics included in the programme logframe are influenced by a multitude of contextual factors.
Mapping: Only conducted for four sectors and with one RATE RBI (although the most widely adopted by companies). No specific inherent limitations.
Overall Evaluation Process
The anticipated evaluation process, as included in the Evaluation and Learning Design Document is outlined in table 6 below. The final column indicates how the evaluation implementation has varied from the anticipated workplan.

Table 6: Evaluation Plan and Implementation Process
Date	Activity	Main Planned Methods/Activities	Implementation
Early 2017	Baseline	Existing resources: / Literature Review (corporate reporting & sustainability standards) / Global sector study and possible fieldwork in one country / Mapping RATE RBI reach against four sectors and GRI coverage / Analysis of partner M&E evidence / Secondary data collection and analysis / Review of indices / If additional resources: Further global sector studies and empirical case studies. B Lab case study (resources allowing)	As agreed with DFID, baseline activities were rolled into the MTE for reasons explained in main text.
2017	Mid-Term Review	Updates of literature review, global sector study, mapping of RATE reach against GRI, analysis of partner evidence, secondary statistics, indices.	Extensive literature review √ / Sector study √ / Mapping √ (partial) / Analysis of partner evidence √ / Secondary statistics √ / Indices (parked until final evaluation)
2018	Additional annual assessment (light touch)	Updates of literature review, global sector study, mapping of RATE reach against GRI, analysis of partner evidence, secondary statistics, indices.
2019	Final Evaluation	Updates of literature review, global sector study, mapping of RATE reach against GRI, analysis of partner evidence, secondary statistics, indices.

Mid-Term Evaluation Implementation
Three main evidence streams have been used for the MTE: RATE RBI information (reports, interviews and a workshop); wider literature (including literature reviews on corporate reporting and product standards); and a sector study of the ready-made garment industry in Bangalore. An organisational analysis was produced for each RBI covered – following a theory of change approach - and reviewed by the partner. Figure 2 summarizes the MTE evaluation process as implemented by the Evaluation Manager.

Figure 2: Mid-Term Evaluation Process

Preparatory
  - Developing Terms of Reference
  - Refining EL questions
Develop Theory of Change
  - Theory of Change - consultation with partners since 2017 on evolving versions (all include same basic causal steps) including a series of learning partner meetings (2015, 2016, 2017)
  - Selection of a simplified ToC at Mid-Term Evaluation
Initial Data Collection
  - RATE partner evaluation evidence requested, collated, analysed and telephone interviews held
  - Wider Literature Analysis (extensive review, including two comprehensive evidence reviews on mature impact pathways)
  - Sector Study - Framework developed, Evidence Identified and Documentary Analysis completed (60+ reports)
Initial findings shared
  - Initial findings on programme evaluation shared with RATE grantees and a limited number of stakeholders
Organisational Analyses
  - Organisational analyses produced for each RATE partner using theory of change and contribution analysis. Consultation with RATE partners and refinement.
Logframe Review and Contribution Assessment
  - Assembling of evidence to assess performance vis-a-vis the logframe and to assess contribution (as far as evidence is available)
  - Production of draft report, review by DFID and EQUALS, sharing with RATE grantees

The programme theory of change has been widely discussed and developed with the RATE partners since the beginning of the Evaluation Manager contract. The most recent version used in the MTE is a simplified version, as comments received during the MTE Process from partners (e.g. at the RATE partners meeting and in individual telephone interviews) suggested that this would be necessary. Further consultations with RATE partners and a wider set of stakeholders is planned for 2018 and 2019.
The corporate sustainability reporting literature review study was conducted in 2016 and the findings presented at a RATE learning partner meeting. The study of the impacts of voluntary sustainability product and supply chain standards was conducted in 2017, drawing upon the evaluation team’s own research, but also detailed critical review of two new systematic reviews of the evidence. The sector study was conducted in late 2017 by the evaluation team in collaboration with an in-country research partner. An engagement with an internationally recognized academic who is a leading light on business and corporate responsibility, was set up, but unfortunately could not be completed for personal reasons.
Telephone interviews were requested with each of the RATE partners, as well as documentary evidence on their own organisational outcomes and impacts (this request had been explained much earlier as well during initial discussions with each RATE partner as they were contracted), and also any available studies on the impact of responsible business more generally. The telephone interviews were carried out with each of the RATE partner organisations during September and October of 2017 to discuss progress since the 2017 Annual Review and questions relating to the organisational analyses. The telephone interviews carried out for this MTE are summarised in the table below. The participants at the MTE partners event are listed at the end of this annex.

Table 7: Mid-Term Evaluation Interview Details
Date	Partner	Number of staff involved
22/9/17	B Lab	3
12/10/17	ETI	3
27/9/17	Fairtrade	2
12/10/17	GRI	2
9/10/17	ISEAL	2
13/10/17	ShareAction	1
10/10/17	UNGC	1

The Evaluation Manager collated data and reports from all the partners. Draft organisational analyses were prepared for each of the eight RBIs covered by the MTE based on documentary reviews and interviews. Each of these employed the same structure – following the basic causal steps of the programme theory of change[83] – and included an analysis of the relative contribution of each organisation to intended outcomes and impacts, as far as the evidence allows. These draft analyses were reviewed by each partner organisation. Comments and suggestions received were responded to by the EM, and a revised version produced (sometimes several iterations were needed). As agreed with DFID, these organisational summaries will not be published.
[83] It is also important to note that only a handful of the RATE partners have explicitly set out their theory of change and the Evaluation Manager has encouraged all since the outset to further advance this work prior to the final evaluation as a means of improving their own MEL systems as well as to inform the programme level evaluation. The programme evaluation does not seek to evaluate the impact of the individual organisations, but it is focused upon the evaluation of the combined effects of the RATE programme and to learn lessons with respect to what works. For this reason, it is also intended that there will be further elaboration of impact pathways as nested within the overall theory of change with the RATE partners and key informants prior to the final evaluation.
In terms of collecting evidence, as well as the sector study and the corporate reporting literature review, the EM also reviewed academic databases and conducted web searches on the participating RATE RBIs, and extensive web searches and grey literature review on corporate responsibility in general, on non-RATE RBIs and new innovations, and on key issues. There is a vast amount of grey literature and initiatives underway on responsible business. The Evaluation Manager has also identified key reports through relevant list servers (e.g. Business and Human Rights Resource Centre). Particular literature sets were collated on the effectiveness of landscape approaches in agriculture, of multi-stakeholder initiatives, of living wage and living income issues etc. The Evaluation Manager also attended a three-day GRI global conference in 2016 to capture current discussions on responsible business.
The evidence was assembled by the Evaluation Manager team, drawing upon the three evidence workstreams, to test the theory of change. This analysis is woven into the report, which is organized for the sake of clarity against the evaluation questions, but there is also a specific section on the theory of change and impact pathways.
A RATE partners meeting was held in October 2017 to discuss initial findings from the evidence review (Box 1 below). The draft report was produced and submitted to DFID in December 2017. Following feedback from DFID and the EQUALS reviewers a revised draft has been developed and will be shared with grantees for their comment. A final version will respond to these comments, for final review by DFID and publication on DFID’s DevTracker website.
Box 1: RATE PARTNERS EVENT – 18 OCTOBER 2017 – LIST OF ATTENDEE ORGANISATIONS (including Non-RATE stakeholder invitees/presenters*) / ETI / ShareAction / NRI / Oxfam* / Independent Consultation/Evaluation Colleague / Shift / UNGC / Fairtrade / DFID / ICAEW* / ISEAL / Index Initiative / GRI / Humanity United

List of Consultees
The list of those consulted specifically during the MTE process is provided below. Each of these consultees/organisations engaged in a meeting to discuss the evaluation and available evidence and provided in-depth comment on the organisational analyses produced by the MEL team.
- ISEAL
- GRI
- UNGC
- Ethical Trading Initiative
- B Lab
- Shift
- ShareAction
- IIED
- Fairtrade Foundation
- ICAEW Chartered Accountants
- Oxfam
Additional interactions occurred in the preceding two years, with researchers and NGOs, during the learning partner workshops, partner skype calls and individual interviews.
Quality Assurance, Principles and Ethics
Research ethics
NRI is committed to operating all aspects of their work in an ethical manner, including respecting the rights of employees, promoting non-discriminatory practices and acting in accordance with the laws of the countries we work in. We observe the following principles, given the particular sensitivities relating to responsible business engagement and issues: a) Maintaining anonymity/confidentiality, b) Individual responsibilities, c) Participation / privacy: Evaluators should provide maximum notice, minimise demands on time, and respect people’s right to privacy, d) Respect of cultural values, e) Integrity: Evaluators have an overriding responsibility to ensure that the evaluation is independent, impartial, and accurate. This principle should not be compromised, f) Omissions and wrongdoing: The evaluation team should consult with DFID when there is any doubt about if and how issues, such as evidence of wrongdoing, should be reported, g) DFID has zero tolerance on Fraud, Bribery and Corruption (FBC) any instances of, or threats of, FBC against DFID funds must be reported to DFID immediately, h) Disclosure: Responsibility for distribution of published material normally rests with DFID or its delegated agent.
All NRI research involving staff and students is covered by the NRI Research Ethics work instruction and the University of Greenwich Research Ethics Policy[84]. NRI has a “Code of Practice” on Research with People” which is guided by the requirements of the University of Greenwich Research Ethics Policy. It covers all research carried out by NRI staff or sub-contractors, or on projects led by NRI, that involve interaction with people, particularly poor, vulnerable or marginalised people. People are hereafter referred to as the “participants” in or of the research.
[84] https://docs.gre.ac.uk/__data/assets/pdf_file/0004/1550470/University-Research-Ethics-Policy-January-2018.pdf
The Code of Practice on Working with People refers to item ii of section 3.1 (Definition of Human-Related Research) of the Research Ethics Policy, ‘Direct involvement through non-invasive procedures, such as laboratory-based experiments, interviews, questionnaires, surveys, observation’. For the remaining items in section 3.1, the research must be referred to the University Research Ethics Committee. The following Codes of Practice covered by these policies are of particular relevance to RATE and the approach adopted is explained below:
Voluntary Informed Consent
The telephone/skype interviews for the MTE were requested in a formal email written to all the RATE partners and written agreement was obtained in email responses to the request. The request email set out the purpose of the MTE and the main topics/questions to be covered, plus it explained how the data to be collected would be used. The TOR were shared with the grantees (attachment to email). These issues have also been discussed at several of the RATE partner learning events and during introductory and monitoring interviews. Grantees were able to comment upon the theory of change, on the organisational analyses, and will be shown the final report for comment.

Confidentiality, anonymity and acknowledgement of participants’ contributions
Reports and data shared in the public domain have not attributed views to individual, named grantees (except with the individual’s permission). Data is held securely according to the University of Greenwich guidelines on data protection. The contribution of the grantees is recognized in the acknowledgements.

Overall Conduct of research
Following the University and NRI policies, researchers seek to conduct their work in a respectful manner. Researchers avoid undue intrusiveness: “the advancement of knowledge and the pursuit of information are not themselves justifications for overriding other social and cultural values” - Social Research Association Ethical Guidelines 2003:26. For example researchers avoid raising expectations where it is not likely that these will be met, seek to avoid exacerbating conflicts etc. Where appropriate, research findings are shared with participants as a key part of the research processes and partners. Attention is paid to issues of safety, harm and risk to participants, research assistants, researchers and future researchers in the same locality. NRI researchers are also expected to observe the highest ethical standards in their dealings with co-workers, sponsors, funders and users of the research and the wider public in the UK and in developing countries, and in their analysis, interpretation and dissemination of findings. Where personal data and videos, recordings and photos are collected this is handled according to University guidelines. See further information on conflict of interest, impartiality, and evidence principles in the RATE context.

Conflicts of Interest and Impartiality:
NRI is extremely careful to identify where conflicts of interests may arise within our own work portfolio (or for subcontracted consultants) and where necessary we raise this with potential or actual clients. There are no known conflicts of interest in this case. NRI consultants are committed to conducting impartial analyses. Quality assurance processes also help to identify any sources of bias. In RATE, as well as providing RATE partners with opportunity to comment, the practice leader for NRI on Monitoring and Evaluation has reviewed the report. The MTE report also details and is transparent about data availability and reliability, providing a clear scoring system.

Evidence Principles
NRI and the Evaluation Manager for RATE seeks to follow the BOND principles for evidence[85]. Table 8 below summarizes the key principles, the overall approach within the RATE evaluation and the specific approach taken in this Mid-Term Evaluation.
[85] https://www.bond.org.uk/data/files/Effectiveness_Programme/120828Full_Bond_checklist_and_guide.pdf

Table 8: Evidence Principles and Evaluation Manager approach

BOND Principles	Details	EM approach
Voice and Inclusion	Perspectives of beneficiaries and most excluded groups included and integrated, and the active participation of beneficiaries facilitated. Disaggregation of findings.	The RATE partners (intermediaries) have been consulted and engaged via learning partner meetings. The MTE has largely relied upon secondary evidence and RATE partner evidence because of the scope/scale of the programme RBIs and the comprehensive nature of their interventions (rather than targeted on specific social groups in specific localities). There are challenges therefore in identifying representative groups for beneficiary feedback, qualitative research and active participation. One case study was explored with a RATE partner with a geographical focus, but the RATE partner lacked the capacity to participate. A small number of evaluation reports collected by RATE partners (e.g. ETI) include beneficiary perspectives. The impact evidence on product/supply chain standards includes substantial feedback from beneficiaries and perspectives from the most excluded. The EM sector study document review includes studies which report beneficiary perspectives and further stakeholder and beneficiary fieldwork is planned for the final evaluation. Relevant secondary statistics have been disaggregated for gender and social difference, but the same challenges apply. See next section for more information on gender and social difference issues and analysis.
Appropriateness	Appropriate data collection methods, appropriate sampling, team skills for data collection/analysis, systematic data analysis leading to convincing	The design (theory-based evaluation, contribution analysis, etc) has been developed based upon a programme that demonstrates dimensions of complexity (e.g. in its inherent attributes and in the context of implementation). The focus upon secondary data collection, as opposed to primary data collection is explained above. The specific choice of methods is explained in the main text, but they are appropriate for the attributes of the programme evaluation. The sampling and selection strategy is detailed in an earlier section. The report structure follows the evaluation questions and integrates the theory of change and logframe analysis within those answers. The analysis follows a clear evaluation framework and theory of change and there is cross-referencing in the text to indicate how the analysis leads to conclusions and recommendations.
Triangulation	Use of different data collection methods and different types of data. Comparison of different stakeholder perspectives. Explanation of areas of conflicting findings and divergent perspectives. Validation of findings by a range of key stakeholders.	A range of data collection methods and types of data have been employed. For example, data collected from the RATE partners has been compared with available wider literature and evidence. The sector study is part of this process of triangulation as well – providing a kind of ground-truthing with respect to conditions on the ground. The sector study focuses upon only locality – Bangalore – and so the extent of generalization of findings is somewhat limited, but the evaluators have drawn upon their wider knowledge and practical experience in apparel and other industries in developing countries, plus a comprehensive review of wider literature and these indicate often similar findings at least in terms of challenges and trends. The perspectives of the RATE partners have been fully explored through learning partner meetings and consultations on the organisational summaries. Conflicting and divergent perspectives and evidence have been highlighted throughout the report.
Contribution	Points of comparison, exploration of how an intervention contributes to change, alternative factors considered, unintended and unexpected changes considered.	For each organisational analysis, the specific temporal point of comparison is firstly when they received the RATE grant, but we have also taken into consideration evidence that explores their effectiveness as an organisation which may pre-date RATE. This is because of the paucity of evidence available, but also because the MTE focuses mostly upon the more mature initiatives which have had more time to create impact. Each organisational analysis has considered the extent to which evidence demonstrates a causal contribution by the organisation and the extent to which other factors may have played a role and unexpected changes. These summaries have formed a key part of the overall Mid-Term Evaluation, but they will not be published.
Transparency	Size and composition of group from which data collected, adequate explanation of methodology including limitations, potential biases addressed and made explicit, clear link between data and conclusions.	Sampling and selection strategies explained in the section above. A detailed methodology is provided in this annex, including limitations. The evidence in this area has a high risk of bias. Companies have a commercial incentive to underplay negative social and environmental impacts, and to exaggerate the positive impact of their own or associated RBIs. RBIs for their part also have an incentive to exaggerate their actual or potential positive impacts on company behaviour, as do NGOs working with RBIs and companies. Independent, advocacy NGOs have the opposite incentive: to over-play the negative social and environmental impacts of business, and to under-play the positive progress made by RBIs. Academic literature should be less prone to bias, but it may still be influenced by ideology and funding. The MTE has sought to balance the bias in these different sources by drawing on evidence from a wide range of documentary sources. Evidence obtained from the RBIs themselves has been triangulated with other sources where available. The evidence from the RATE partners did include a small number of independent studies (of variable methodological quality). The literature review on corporate reporting employed a highly transparent approach and can be replicated. The literature review on product / supply chain standards is less comprehensive, but it includes two major recent systematic reviews which have high levels of methodological rigour and the quality of evidence in additional studies has been taken into account by the Evaluation Manager. Clear linkages are made between the conclusions presented and the data (including cross-referencing in the report).

Communications
A detailed communications plan was set out in the evaluation design document. However, after its approval, DFID decided that the focus of the learning would be the RATE partners and DFID itself, with key lessons shared externally at a later date. This has affected communications activities, which have been adapted as follows:
Internal Audiences
- RATE partners were invited to learning events in each year – 2015, 2016, 2017 to explore issues of evidence, monitoring and evaluation approaches and tools, theories of change, draft MTE findings. Further events are planned for 2018 and 2019 to discuss how to improve M&E approaches and systems. At the 2016 and 2017 events, RATE partners were asked to share their experiences with M&E and lessons learned, with several providing presentations (e.g. ETI presented on outcome mapping).
- Regular skype calls enabled the MEL team to discuss with the RATE partners their M&E plans periodically. Further discussions are anticipated for 2018 and 2019 based on the findings of the MTE.
- A summary of the literature review and a briefing on corporate reporting and evidence were shared with DFID and GRI. Key findings were also presented at the RATE partners meeting in 2016.
- Communications with DFID have been regular, with face to face meetings and telephone conference calls arranged on a regular basis. DFID staff have attended all of the RATE partner meetings as well, providing an opportunity for lesson sharing and learning. A DFID representative presented the RATE programme at the 2015 and 2016 events and presented the DFID Economic Development Strategy at the 2017 meeting to inform RATE partners.
- The MEL team have offered to support DFID in assessing their own engagement across DFID, particularly with country offices.
External Audiences
- A project website was proposed in the evaluation design to enable the sharing of information externally, with key outputs shared on the site. However, DFID decided that an external website was not desirable and so this has not been implemented.
- Various plans were set out in the evaluation design in terms of collaborating with the RATE partners to disseminate lessons emerging from the programme. The RATE MTE will be shared with the partners and they will be asked to disseminate the link to the report, when it is available on DevTracker.
- Key outputs will be disseminated via external listservers (e.g. Business and Human Rights Resource Centre). The MTE, when it is approved, will be shared in this way.
- No media events are planned, in accordance with DFID guidance.

#### 13. Independence

Differences of opinion
There were no differences of opinion on the final report within the evaluation team, or with the RATE partners on the final versions of the organisational analyses. All the RATE partners were consulted on the relevant organisational analysis. Each RATE partner provided comments to the RATE MEL team, who then made revisions. Several iterations were undertaken where needed until the RATE partner approved the final analysis. Extensive stakeholder consultations were not conducted due to the exceedingly large number of stakeholders that exist for the RATE RBIs – essentially stakeholders for global business. However, a sector study has been initiated and the RATE MEL team will conduct stakeholder interviews for this study and for an additional sector study – this provides an opportunity to assess stakeholder perspectives in a more bounded, practicable manner. Any differences of opinion will be reported in the final evaluation.
Conflicts of interest
No conflicts of interest were identified.
Evaluation team’s freedom to operate
The evaluation team was able to work freely and without interference. The evaluation was commissioned by DFID and required agreement prior to publication.
Information sources and their contributions were independent of other parties with an interest in the evaluation
The RATE MEL team have drawn upon evidence from the RATE Partners, but they have also reviewed secondary evidence from the literature on the impact of RATE RBIs, non-RATE RBIs and responsible business in general. Efforts were made to identify independent studies wherever these were available and to draw upon these. It is also important to note that whether independent or not, all non-corporate actors face challenges in extracting information from companies that can be published due to commercial sensitivity concerns – this is an inherent challenge in the field of responsible business for both RBIs and for evaluators.
Annex 3: MTE Evaluation Framework
CRITERIA	MTE QUESTIONS	THEORY OF CHANGE ASSUMPTIONS	EVIDENCE			METHODS
			O.A.	W.E.	S.S.
CONTEXT	How supportive is the context within which RATE is operating?	The combination of interventions (scaling, new levers, evidence, remedy) is appropriate to meet desired goals & is relevant to DFID, business & beneficiaries / RATE RBIs more effective than comparative approaches	X	X	X	Document review; workshop; interviews.
RELEVANCE	How relevant is RATE to DFID, business, and beneficiaries?		X	X	X	Document review; workshop; interviews.
TARGETING	Are RBIs, particularly RATE RBIs, reaching companies of different kinds? Are these the most appropriate companies in terms of impact potential?	Targeting is effective by DFID (combination of RBIs selected) & RATE RBIs are willing to participate: / Targeting is effective by RATE RBIs & companies are willing to participate;	X	X	X	Document review
	Are RBIs, particularly RATE RBIs, reaching affected workers (female, male), communities and environment? Are these the most affected groups and areas?	RATE RBIs are effectively targeting poor people (women and men), communities and environments in developing/middle income countries	X	X	X	Document review
EFFECTIVENESS	How effective is the RATE programme to date? Is it on target for delivering its outputs?	Entire Theory of Change & the nested Impact Pathway assumptions	X			Document and logframe review; workshop; interviews.
	How effective are the different impact pathways?		X	X		Document review; workshop; interviews.
OUTCOMES	What progress has been made on RATE outcomes?	See outcome assumptions below	X	X		Document and logframe review; workshop; interviews.
	To what extent has RATE built the capacity for responsible behaviour amongst businesses and other stakeholders?	RATE RBI services effectively promoted. Companies & other stakeholders have capacity to respond. RBI services are relevant to corporate needs.	X	X		Document review; workshop; interviews.
	What is the contribution of RBIs to corporate behaviour change (nature of changes in corporate decision-making, scale of changes vis-à-vis other corporate behaviour and vis-à-vis likelihood of achieving goals of RATE?	Drivers of uptake are effective (e.g. strong business case; moral/regulatory imperative). Accountability mechanisms /actors sufficiently strong to exert adequate pressure. / Drivers are sufficient for public adoption of tools, guidance, standards, and innovations & translates into meaningful behaviour change within companies & sectors. Civil society has sufficient capacity to ensure implementation	X	X		Document review; workshop; interviews.
IMPACT	What is the likely impact of RATE on poor women and men workers, communities affected by business?	Approaches adopted are effective in delivering benefits to workers, communities & environments. Benefits outweigh harms of business impacts (including unexpected and unintended impacts) and can be sustained. Contextual factors are supportive.	X	X	X	Document and logframe review; workshop; interviews.
	How plausible is the overall theory of change for RATE? What is the evidence regarding the key assumptions (e.g. the business case)?	All assumptions of the ToC (and of nested impact pathways)	X	X	X	Document review; workshop; interviews.
	How effective are the different impact pathways [and individual interventions] with respect to gender and social difference?	Impact pathway assumptions	X	X	X	Document review; workshop; interviews.
EFFICIENCY	Have resources been used efficiently, in order to, provide value for money and achieve results?	Data available on resource use and outcomes accessible and transparent for assessment of vfm. / RBIs monitoring systems adequate to track outputs and outcomes	X			Document review; workshop; interviews.
	To what extent is RATE likely to be an economic, effective and cost-effective investment?		X			Document review; workshop; interviews.
	What could be done differently to improve implementation and value for money?		X			Document review; workshop; interviews.
SUSTAINABILITY / AND SCALING	To what extent are the outputs, outcomes and impacts of the programme likely to be sustainable?	Business case for non-pioneers is strong enough to encourage adoption. Dissemination of RBIs effectively reaches mainstream companies and laggards	X	X	X	Document review; workshop; interviews.
	What factors constrain or enhance sustainability?		X	X	X	Document review; interviews.
	What is the likelihood of business building on and scaling up the work of the programme?		X	X	X	Document review; interviews.
SYSTEMIC IMPACT	What is the systemic impact of RBIs, especially RATE RBIs? Can RBIs bring about a transformation of individual companies and sectors and under what conditions?	RBI mechanisms and approaches are relevant to the mainstream of companies (not just pioneers) and external pressure, regulation and incentives sufficient to create level playing field and motivation to act / Adequate clarity and consensus amongst key actors on industry targets and specific responsibilities of companies and/other stakeholders / Supportive enabling environment	X	X	X	Document review; workshop; interviews.
LESSONS	What are the key factors determining success? What are the major factors constraining or enhancing progress towards the intended outputs, outcomes and impacts?	Lessons drawn from the analysis of the theory of change and associated assumptions	X	X		Document review; workshop; interviews.
	What could be done differently to improve programme relevance, implementation, output achievement, contribution to outcomes and impacts, systemic impact and with respect to the Sustainable Development Goals?		X	X	X	Document review; workshop; interviews
	What are the main lessons for DFID, governments, companies and civil society in relation to responsible business affecting developing countries?		X	X	X	Document review; workshop; interviews.

Notes:
 Shaded questions are additional or different to those listed in the MTE Terms of Reference.
*OA = evidence on the eight RATE Responsible Business Initiatives covered by the MTE drawn from interviews, partner M&E reports, workshop, secondary evidence in literature, all of which was triangulated and used to assess organisational performance and impact against their logframe and against their theory of change.
**WE = secondary evidence from the wider literature on RATE RBIs, non-RATE RBIs and responsible business more generally. This evidence is used to analyse the effectiveness and impact of key mechanisms employed by RATE partners and other non-RATE RBIs in changing business behaviour.
*** SS = evidence from the sector study, which draws on in-depth secondary data relating to the RMG sector.
Annex 4: The RATE Portfolio
Partner	Maturity of Initiative	Stage of Implementation of DFID grant	Organisational Approach	Type of organisation	Corporate Membership/ participation	Themes & Sectors covered	DFID Funding (Scale; Type; Relative importance to grantee)
Core Partners
Global Reporting Initiative (GRI)	High maturity (1997)	Apr 2015 – Mar 2019 [Advanced]	Corporate reporting sustainability standard; Focal Hubs; Gold Membership Network	Not for profit organisation.	Global – GRI reports produced in 100+ countries.[86]	Multiple themes. Multiple sectors	Large grant (£2m) / Core funding (deliver standards, outreach via focal hubs, M&E) / Limited (as one of many donors)
Ethical Trading Initiative	High maturity (1998)	Jan 2016-Mar 2019 [Medium]	Stakeholder learning & dialogue on meeting the base code.	Tripartite MSI (Corporate members, Trade Unions, NGOs)	Membership is 89 companies, mainly UK HQ, plus NGOs and unions -	Ethical trade (especially human rights) across three sectors	Very large grant (£5m) / Core funding (ETI 5-year organisational strategy)
United Nations Global Compact (UNGC)	High maturity / (2000)	Aug 2014 – Dec. 2018 [Advanced]	Corporate reporting principles (& some guidelines). Voluntary initiative based on CEO commitments	UN organization – uses convening power to	Global / 9,500 companies and 3,000 non-business signatories	10 principles (broad coverage)	Organisational Core Funding / [Limited Influence – DFID funding goes into donor pot. Donor funding much less than corporate member funding. Some influence via donor group]
ISEAL	High maturity (2002)	Dec 2014 – May 2018 [Advanced]	Sustainability standards & assurance processes of products, audited & documented changes in production, supply chains, & business practices	Umbrella body for credible multi-stakeholder voluntary sustainability standards	Global	Certain sectors covered only.	Large grant (£3.6m). / Project funding (identify /disseminate evidence on business and impacts case and to engage business leaders.) / Specific focus on certain sectors/emerging markets in DFID grant
B Lab	Medium maturity / (2006) (\project - new East Africa hub)	July 2016 – Mar 2019 [Medium]	Social & environmental impact standards & support for pioneer companies to measure/improve. New legal forms also identified & promoted.	Non-profit organisation established seeking to build a global movement for responsible business	Global / (40K companies using B Lab standard)	Diverse ESG themes/ impacts. All sectors	Global. DFID grant focuses on regional hub in East Africa / Funding for the development of a regional hub in East Africa
Shift	Medium / (2011)	Jul 2016 – Mar 2019 / [Medium]	Strengthening corporate capacity to measure their human rights impact and driving improved performance through pilot reporting database.	Centre of expertise on the UN Guiding Principles on Business and Human Rights. Founded in 2011.	Works globally with businesses/ stakeholders to embed Guiding Principles into practice.	Human Rights. All sectors.	Global. / Project based. Online database on companies’ human rights reporting, plus corporate capacity strengthening
ShareAction	Medium (2005)	Sep 2016 – Mar 2019 [Medium]	Influencing investors		UK, Canada etc.		Small - £970 K / Project-based
Fairtrade	High maturity / (1997)	Oct 2016 – Mar 2017 [Medium]	Alternative approach to conventional trade, offering standard, certification & label.	Sustainability standard (ISEAL member)	Global.		Very small - £150K / Project funding – transparency initiative focused on tea, coffee and cocoa
Non-Core Partners
UK National Contact Point for the OECD Guidelines (UKNCP)	-	Aug. 2014 – Mar 2018 [On-going]	Grievance mechanism. Civil society organisations or individuals can file a complaint where they think a company is breaching OECD guidelines.[87]	Government (Dept. for International Trade), overseen by a steering board with government & external representatives	Global	Broad range (e.g. due diligence in supply chains, Human rights, employment & industrial relations, environment etc	Small - £500k / Partially funded by DFID
[86] https://www.globalreporting.org/information/about-gri/Pages/default.aspx
[87] The NCP then follows a procedure and decides whether to accept a case brought under the guidelines. The first objective of the complaint process is to find a solution through conciliation or mediation. The NCP only undertakes a full examination of the complaint if mediation fails to find a resolution. The NCP decision is made public

Legend: Level of Maturity of Organisation: High maturity – Pre-2003; Medium maturity – 2003 – 2014; Newly emerging – 2014 – to date. Stage of Implementation of DFID grant: Advanced; Medium; Recent. Size of Grant: Very large (£3m+); Large (£3m+); Medium (£1m to £2m); Small (£100 k to ≥ £1m); Very small (≥£100K)
Annex 5: Programme Assumptions
Rationale	The combination of interventions (scaling, new levers, evidence, remedy) is appropriate to meet desired goals.
Reach & response	RATE (DFID) can identify appropriate (combination of) RBIs, who are willing to participate. RBIs can identify & engage relevant business actors/other stakeholders & they are willing to participate.
Capacity & Practices -Pioneer Companies	Services and engagement strategies offered by RBIs are attractive, relevant and affordable for pioneer companies. / Pioneer companies & other stakeholders, such as investors, civil society actors, have sufficient capacity to absorb, understand and apply new information, tools, systems, innovations and learning processes & adequate motivation/opportunity to use them / Sufficient public, consumer & business understanding of & pressure for increased responsibility in business conduct/impact, plus understanding of the risks of inaction. / Sufficient benefits/incentives (business case; regulatory requirements) for companies to make public commitments & to develop policies and to translate these into practices & impact. / External pressure/rewards (i.e. from investors, NGOs, financiers, other business clients, media, citizen activists, governments), and/or internal drivers for the adoption of new commitments (benefits exceed costs, i.e. the business case is clear) & of their implementation. / Civil society & governments have adequate capacity to hold companies to account e.g. to use reports. / Assurance processes are of sufficient quality & can be enforced. / Local, national & international rules & legislations provide level playing field (e.g. there is legislation in place requiring corporate disclosure). / Pioneers have sufficient motivation to mainstream RB practices in organisations & share lessons with others.
Direct benefits for pioneers & those affected	Changes in business practices are sufficient in scope, scale, targeting, appropriateness and cover all relevant issues to workers, communities, environment. / Companies can capture the value of their improved impact upon workers, communities, environment. / Benefits to workers, communities and environments outweigh harms of business impact & contextual factors.
Scaling	Business case for non-pioneers is strong enough for adoption & dissemination of RBIs effectively reaches mainstream companies and laggards. There is adequate clarity and consensus amongst key actors on industry targets and the specific responsibilities of companies/other stakeholders. / Knowledge of more responsible business practices is sufficient incentive for other companies to adopt. / The enabling environment is supportive. There are adequate perceived political benefits for public agencies to support responsible business.

Annex 6: Detailed Context Analysis
Trends in the Global Context Affecting Responsible Business
6.1 Supporting trends
There is growing awareness of resource constraints amongst global businesses, new regulations and normative frameworks have been established, there is growing public/consumer expectations in certain markets for ethical corporate behaviour, new RBIs emerging, and technological developments which can support supply chain transparency etc.
There has been a major growth in the power of Multi-National Companies (MNCs) with globalization processes. To fill the governance gap of insufficient labour and environmental legislation and enforcement in production locations (ref), there has been a growth in private governance. Different standards, norms, principles, codes and frameworks have been developed, some led by civil society, others by industry[88]. This entry into areas of regulation previously the responsibility of the state is noteworthy, although there is an important interaction between public and private governance with respect to global value chains.
[88] Standards for products and value chains, corporate codes & auditing, own brand initiatives, reporting for corporate performance, public-private collaborations and sectoral initiatives, multi-stakeholder initiatives to promote compliance and learning, ratings and indices (increasingly with stock exchanges using), impact investing, plus national and international regulations, sustainable procurement guidelines etc.
Key developments include the formation and global agreement on the United Nations Sustainable Development Goals (SDGs), which provide the new set of global aspirations and against which companies have rapidly aligned (KPMG, 2017). With respect to human rights
On forced labour in business and supply chains, governments committed to a new international agreement in 2014 (ILO Forced Labour Protocol), and various jurisdictions are not implementing or revising their legislation accordingly, such as the California Transparency in Supply Chains Act (2010), the UK’s Modern Slavery Act (2015) and the EU Non- Financial Reporting Directive (2014) (ShareAction, 2016[89]). These legislative advances demand greater transparency from companies with respect to their actions to tackle supply chain forced labour issues, but real progress on the ground will depend upon a) enforcement by governments; b) willingness of businesses to comply new laws and regulations (ShareAction, ibid).
[89] ShareAction ‘Forced Labour: What Investors Need to Know’. Forced Labour: Investor Briefing, June 2016’.
Human Rights Impact Reporting is increasing following the the unanimous endorsement by UN Human Rights Council of the Guiding Principles on Business and Human Rights. A Reporting Framework has also recently been produced, which provides a framework for companies to report on their human rights performance in line with the UN Guiding Principles (Shift and Mazars, 2015). HRIAs assess the potential and actual human rights impacts of a corporate project and recommends how to prevent, mitigate and/or address these impacts[90]. An Oxfam analysis suggests that rights-holders should be central to the process of indicator selection, that the assessments should raise awareness on human rights amongst companies, but also local communities (building capacity for follow-on action, and importantly, they should lead to real action (Damiano de Felice, Oxfam)[91]. Community-based HRIAs are being tested, either as parallel or hybrid approaches, to help prevent adverse impacts on communities, achieve corporate buy-in and further embedding meaningful human rights due diligence processes within companies or local governments.’[92] Such approaches are more likely to be able to ‘redress power imbalances to include legitimate mediation, from ensuring independent funding to empowering communities to say no to harmful projects’ (Oxfam America, ibid).
[90] HRIAs are different from Environmental Impact Assessments because of their holistic approach. Based on the inter-relatedness and indivisibility of human rights, they cover both environmental and social issues. HRIAs are different from Social Impact Assessments because their standards are anchored in binding national and international legal frameworks. This is important because these frameworks clearly identify duty-bearers and rights-holders (http://www.huffingtonpost.com/damiano-de-felice/who-is-in-charge-a-key-qu_b_9220244.html).
[91] http://www.huffingtonpost.com/damiano-de-felice/who-is-in-charge-a-key-qu_b_9220244.html
[92] The Canadian organization Rights and Democracy developed ‘Getting It Right’ in 2004 – a community-based HRIA tool. The International Federation for Human Rights (FIDH), Oxfam, the Project on Organizing, Development, Education, and Research (PODER), and the Carter Center have more recently been promoting active leadership from local communities in measuring the human rights impacts of business projects. (Oxfam America ‘Community Voice in Human Rights Impact Assessments’ 2015. http://www.oxfamamerica.org/static/media/files/COHBRA_formatted_07-15_Final.pdf
There are specific technological developments which may help to increase transparency in global supply chains (e.g. there is growing interest in the application of blockchain technologies to act as a digital ledger) (Niforos et al, 2017).[93]
[93] Niforos, M., V. Ramachandran, T. Rehermann (2017) ‘Blockchain: Opportunities for Private Enterprises in Emerging Markets’. International Finance Corporation.
6.2 Non-supporting trends
The global social and environmental context in which global business operates (and to which it contributes) is highly challenging, with intertwined sustainability challenges facing humanity. There is a worsening global ecological crisis in terms of climate change, but also in terms of biodiversity loss and extinctions, ocean acidification, nitrogen and phosphorus flows to the biosphere and oceans, etc[94].There is a worsening ecological crisis and resource constrained environment, with many companies recognizing the imperative for action and sometimes leading where governments do not. For example, many US companies have called for climate action even as their government withdraws from the US Paris Climate Agreement. Some suggest that a post-growth economic system is the only way to deliver prosperity: While Gross Domestic Product (GDP) increased threefold since 1950, there has been a negative trajectory if social and environmental externalities are considered and there is an urgent need to create a more effective key measure[95]. The latter must integrate environmental externalities and human wellbeing measures and be used to guide policy-making and investment, not GDP.
[94] http://www.stockholmresilience.org/research/planetary-boundaries/planetary-boundaries/about-the-research/the-nine-planetary-boundaries.html
[95] There was a decrease on a Genuine Progress Indicator (GPI) which integrates social and environmental externalities, since 1978 [Kubiszewski et al, 2013 ‘Beyond GDP: Measuring and achieving global genuine progress.
There are major risks and uncertainties (political-economic, and technological etc.) that may affect how far and how fast business becomes more responsible. Hyper-inequality is increasingly seen as a problem created by economic globalization processes. Growing wealth inequality, the stagnation of wages in developed economies, and increasing threats from automation for certain categories of jobs, a declining bargaining power of workers and growth in precarious work are all serious trends around the world. These trends have contributed to the rise of the far right, and a growing mistrust of governments, and multi-national corporations. A recent OECD report finds that just 42% of people in 2016 have trust in the institutions of government and that there is a ‘common thread…a growing sense that the global economy is rigged to work in favour of the few and not the many and that governments are not able to respond to challenges that open trade raises...’, including the highly unequal outcomes for different social groups (OECD, date, p3).[96] There is increased calls for recognition of the limits to economic globalization processes, because of their inherent unfairness, but some argue that the emerging backlash presents opportunities for change as well as challenges for those seeking more responsible and inclusive business.[97]
[96] http://www.oecd.org/inclusive-growth/Policy_Brief_Time_to_Act.pdf
[97] Organisations emphasised how often a call for ‘high road’ business may be viewed as superfluous in the face of pressure to emphasise relationships with consumers, employees, or capital in order to survive. While economic systems are in flux, organisations such as those interviewed…nevertheless face an opening to instigate new approaches to the way business is done’ (Said Business School/University of Oxford, 2016, p1).
The civil society network, Civicus, monitors the space for civil society[98] or ‘civic space’ and report that this space is closing: ‘Updated ratings released on 4th October by CIVICUS, the global civil society alliance, provide further evidence that the space for civil society - civic space - continues to close around the world[99]’ and with 108 countries now rated as being ‘obstructed’, ‘repressed’ and ‘closed’ (on a five point scale) indicating ‘serious restrictions of civic space’ and with a discernible downward trend in recent months[100]. This has implications with respect to voluntary approaches to responsible business influencing, which rely upon journalists, NGOs and human rights defenders to play a key role in holding companies to account. The analysis shows a decline both in known offenders, but also a decline in civic freedoms in countries that had been positive beacons, indicating that such freedoms cannot be taken for granted[101]. Further, some commentators would suggest that there is a link between the growing wealth of individuals and companies, and a ‘thinning of democracy’, as the former use their wealth to influence and penetrate governments (Standing, 2016[102]). Not unrelatedly, globally, labour rights are under pressure, with employer’s organisations contesting the right to strike in countries where this right is not provided for in the constitution (Bernard Thibault, ILO,[103]).
[98] ‘Civic space is the bedrock of any open and democratic society. When civic space is open, citizens and civil society organisations are able to organise, participate and communicate without hindrance. In doing so, they are able to claim their rights and influence the political and social structures around them. This can only happen when a state holds by its duty to protect its citizens and respects and facilitates their fundamental rights to associate, assemble peacefully and freely express views and opinions. These are the three key rights that civil society depends upon. The CIVICUS Monitor analyses the extent to which the three civil society rights are being respected and upheld, and the degree to which states are protecting civil society. https://monitor.civicus.org/globalfindings0417/
[99] 3% of people on the planet live in countries with open civic space. By contrast, almost one in ten people live in a country with closed civic space and over a third of people live in countries with repressed civic space’ https://monitor.civicus.org/globalfindings0417/
[100] https://monitor.civicus.org/Ratingsupdatesept17/
[101] https://monitor.civicus.org/Ratingsupdatesept17/
[102] Guy Standing (2016) ‘The corruption of capitalism: Why rentiers thrive and work does not pay’ Biteback Publishing.
[103] http://column.global-labour-university.org/2016/02/ilo-is-sole-shield-for-millions-of.html?utm_campaign=announcements&utm_content=6533&utm_medium=email&utm_source=platform#more
There are major trends in terms of the way global businesses are developing and how they are making profits, responding to political-economic imperatives, including technological developments and the rise of the information economy. These processes are ‘remaking business’: Large companies are having to increasingly compete on ‘voice, innovative approaches to markets, and purpose’, because competitive advantages relating to physical distribution networks relied upon by consumer companies have been eroded by the internet, but also because start-ups can access efficiencies of scale through accessing sourcing and manufacturing as a service[104]. The largest consumer companies earned their power by consolidating and optimizing their access to commodities, manufacturing and distribution, but cannot now compete only on price. These changes in corporate business models and the rapid process of disruptive innovation have implications for workers in the gig economy, for example.
[104] https://www.linkedin.com/pulse/bigcos-newcos-nine-trends-remaking-business-john-battelle?trk=eml-b2_content_ecosystem_digest-hero-14-null&midToken=AQFCUi-3a-3HHg&fromEmail=fromEmail&ut=21zY8Rq5ZHd781
There is a growth in precarious work, as more people have an increasingly tenuous relationship to work, are not part of organised labour and are characterized by chronic uncertainty and insecurity (Standing, 2011). Thibault from the ILO (ibid) suggests that globally work is deteriorating: ‘Today, unemployment stands at 215 million. One in every two workers does not have an employment contract; only 1 in 4 has a stable employment relationship; 21 million people are subjected to forced labour; up to 168 million children are known to be working; and 23 million workers die every year due to work-related illnesses or accidents’.
6.3 Lessons from the literature
Drivers of responsible corporate decision-making include ‘values’ motivation (‘conscious desire to achieve and be accountable for societally beneficial outcomes by means of operating a profitable business’) and a ‘materiality’ motivation (‘recognition that a successful business can seek out and address societal challenges with resultant material benefits’) (Blowfield and Murray, 2014). However, some argue that some corporate responsibility strategies, such as corporate reporting, are legitimization strategies, masking inaction and allowing business as usual to continue and in worst case scenarios such strategies can slow progress by deflecting stakeholder pressure[105].
[105] Braam, G.J.M. et al., 2016. Determinants of corporate environmental reporting: the importance of environmental performance and assurance. Journal of Cleaner Production, 129. Available at: http://linkinghub.elsevier.com/retrieve/pii/S0959652616301068
One key motivation of corporate behaviour is the business case. The International Finance Corporation (IFC) states that ‘companies that do good by the environment, their labour force, and communities do well financially’[106]. However, the literature on the overall business case for responsibility is more conflicting than the IFC suggests. Some studies show a positive correlation between corporate social responsibility (CSR) and financial profitability[107]. Some do not[108]. One study found higher investment returns for ‘sin stocks’[109]. A later paper did not[110]. Overall, the comprehensive literature shows that the relationship is complex and heterogeneous, and that the direction of causation remains unanswered[111]. A recent meta-review of the benefits of using sustainability standards concluded that ‘many studies investigating the business case of using standards come up with inconclusive outcomes on the identified benefits, which are often difficult to quantify and highly context dependent’[112].
[106] http://www.ifc.org/wps/wcm/connect/topics_ext_content/ifc_external_corporate_site/sustainability-at-ifc/business-case
[107] Carroll and Shabana (2011); Orlitzky e l (2003); Beurden and Gossling (2008); Thorpe and Prakash-Mani (2003); Wang, Dou and Jia (2015).
[108] Mulyadi and Anwar (2012); Aras, Aybars and Kutlu (2010); Nelling and Webb (2009).
[109] Hong and Kacperczyk (2009)
[110] Blitz and Fabozzi (2017)
[111] The financial and commercial impact of responsible and sustainable business practice. HEART for DFID (2017) unpublished
[112] The business benefits of using standards – a meta review. Aidenvironment for ISEAL (2017)
It is important to stress that there can be a business case for responsibility. A recent WWF study on the economic impacts of FSC certification found a ‘strong positive business case overall for the decision to pursue FSC’[113]. There can also be a longer term, more strategic business case. ETI believe that ethical can improve supply chain efficiency, protect a company’s reputation, protect and increase sales, increase access to capital, and motivate employees[114]. Shift reports that a growing body of research illustrates how severe impacts on human rights can represent, in the medium to long term at least, considerable risk to companies: operational risk, reputational risk, financial/investment risk, judicial and non-judicial risk, and staff recruitment and retention risk[115]. A recent report on the sustainable economy concluded that ‘for all companies, failing to deliver the SDGs is likely to result in severe disruption and missed opportunities…[and that]…moving towards the SDGs will create commercial benefits for forward-looking companies’[116].
[113] WWW (2017) ‘Profitability and Sustainability in Responsible Forestry: Economic impacts of FSC certification on forest operators’. http://wwf.panda.org/about_our_earth/deforestation/forest_publications_news_and_reports/forest_reports/?299850/Responsible%2Dsourcing%2Dof%2Dforest%2Dproducts%2Dbeneficial%2Dfor%2Dbusinesses%2Dnew%2Dreport
[114] www.ethicaltrade.org/join-eti/business-case
[115] Risk to Human Rights as Risk to Business. Shift (2017) unpublished draft
[116] Towards a sustainable economy. The commercial imperative to deliver the UN Sustainable Development Goals. Cambridge Institute for Sustainability Leadership (2017).
The problem with this type of longer term, strategic business case is that it can be difficult to make and may conflict with shorter term business realities. According to a UNGC study in 2013, business leaders felt they were ‘constrained by market expectations and are struggling to quantify and capture the business value of sustainability … struggling to deliver the business case for action at scale; and see market failure hindering business efforts to tackle global challenges’[117]. Greater responsibility can conflict with highly profitable business models. This can make it difficult to convince ‘factory managers (let alone company directors) that it is their own self-interest (i.e. the business case) to pay workers higher wages and embrace independent unions’[118]. The need to maintain profit margins can directly contribute to, and make it more difficult to address, poor labour practices in global supply chains[119]. Or, as one interviewee in the HEART study for DFID put it more bluntly: “a lot of firms accused of human rights abuses are extremely profitable and have been for a long time”[120].
[117] Architects of a Better World. UNGC Accenture (2013)
[118] The promise and limits of private power. Promoting labour standards in a global economy. Locke, R.M. (2013, p.177).
[119] Negotiated Solutions to Human Rights Violations in Global Supply Chains, Corporate Accountability Research (2016). The Promise and Limits of Private Power – promoting labor standards in a global economy. Locke, R.M. (2013)
[120] HEART (2017, p.8)
The assumption that there is a business case for companies to improve their behaviour is key to many RBIs, as well as to voluntary approaches more generally. If responsibility is in the enlightened self-interest of business, the necessity for government regulation is reduced, and the case for investing in [121]RBIs as a vehicle for win:win business and society gains is enhanced. However, while it may be right that ‘a commitment to ethical principles should outweigh financial justification’[122], if the financial justification is hard to make, or even runs contrary to ethics, this suggests that there is a limit to what voluntary RBIs can achieve. That there is a general business case (and increasing regulatory pressure) which would support some improvements in business behaviour for some companies, does not mean that there is a universal business case for improving all business behaviour for all companies.
[122] Beyond Supply Chains. Empowering Responsible Value Chains. World Economic Forum (2015, p.4).
Corporate decision-making processes are often non-linear and messy in practice. In terms of shifting towards sustainability, being ‘on a journey’ is part of the responsible business language for corporate progress. Reason et al (2009, p112-113) identify six levels of organisational responsibility to sustainability on a spectrum from non-responsiveness (level 1), compliant (level 2), efficient management (level 3), breakthrough projects (level 4), strategic resilience (level 5), and champion organisations (level 6). Such an evaluative scale could provide a useful tracking tool for companies or RBIs seeking to track change in individual companies. Blowfield (2013) describes a common trajectory for corporate transformation as companies move from defensive strategies (the management of risk and the protection of reputations) to offensive strategies (identifying business opportunities and enhancing reputation) to integrated approaches (Blowfield, 2013). Offensive approaches can improve reputations, and identify opportunities, but alone cannot protect the organisation’s reputation. Thus, both types are needed, and should be integrated into corporate strategy, across all aspects, including in the company’s own products and operations, but also throughout the value chain (Blowfield, 2013, pp120-121).
It is important to clearly analyse the extent to which sustainability is integrated across a company – i.e. has it achieved corporate transformation? Given the marketing which companies invest in, it is not always possible for external actors to know, because reporting does not allow for proper comparison of the data. Some recent systematic analysis on MNEs in the ASEAN region, maps the extent to which companies are making commitments and adopting policies and management systems according to international conventions, standards and guidelines. The authors (Topple et al, ref[123]) find that has sustainability requirements have not percolated to subsidiaries to nearly the same extent as in headquarters, with a similar fall off noted in global supply chains.
[123] Topple, C., Donovan, J. D., Masli, E. K. Borgert, T. (2017) ‘Corporate sustainability assessments: MNE engagement with sustainable development and the SDGs’, Transnational Corporations, Vol. 24, no. 3 (2017), pp. 61-72
It is unclear how easily incumbent companies can change to become fully responsible (i.e. integrating sustainability issues). Porter and Kramer (2011[124]) argue that business contributes to sustainable development through the creation of benefits both for firms and society (‘shared value’ approaches). Profitable activities also ‘benefit consumers, producers, employees or in wider society, both directly and through complex value chains’ (ref). Several ‘hard-nosed’ companies have already embarked on such initiatives, including GE, Wal-Mart, Nestlé, Johnson & Johnson, and Unilever, according to these authors[125]. Critics suggest that ‘win-win’ projects may still leave an ‘ocean of unsolved environmental and social conflicts’ untouched (Crane et al, 2014, p139[126]). ‘While CSV might be a good way of integrating various activities into one social strategy, it fails to deliver orientation for a responsible corporate-wide strategy’ and thus fails to do what CSV proponents suggest, which is to ‘redefine the purpose of the corporation’ (Crane et al, ibid). CSV presumes that compliance with the law and ethical standards are already achieved, as well as mitigating any harm caused by the business. CSV also fails to capture the messy, trade-offs that occur in the real world, yet these challenges need to be integral to any business response (Crane et al, ibid). This critique is important with respect to RBIs more generally – to what extent can they drive the development of responsible corporate-wide strategies and does this require the re-definition of the purpose and business model of the company?
[124] Porter, M. E. and M. R. Kramer (2011) ‘Creating Shared Value’. Harvard Business Review, Jan-Feb. Issue.
[125] E.g. Nestlé redesigned its coffee procurement processes, working intensively with small farmers in impoverished areas who were trapped in a cycle of low productivity, poor quality, and environmental degradation. Nestlé provided advice on farming practices; helped growers secure plant stock, fertilizers, and pesticides; and began directly paying them a premium for better beans. Higher yields and quality increased the growers’ incomes, the environmental impact of farms shrank, and Nestlé’s reliable supply of good coffee grew significantly. Shared value was created’.
[126] A. Crane, G. Palazzo, L.J. Spence, D. Matten (2014) ‘Contesting the Value of ‘Creating Shared Value’. UNIVERSITY OF CALIFORNIA, BERKELEY VOL. 56, NO. 2 WINTER 2014. California Management Review.
Beyond the corporate-centric gaze, industry transformations are needed to achieve the Sustainable Development Goals. This means considering what progress has been achieved beyond leading companies within a specific country-sector levels and, understanding the global dynamics involved – a focus which is too often lacking in debates on responsible business circles. A new Corporate and Human Rights Benchmark database has been launched[127] to rate corporate progress on human rights. It finds that ‘there are some clear leaders, but improvements can still be made’, ‘the results skewer significantly to the lower bands’, ‘lowest performing companies must improve urgently’, and ‘commitments must be followed through’, ‘engagement with those potentially affected is lacking’ and ‘there is a gap between responding publicly to serious allegations and taking appropriate action[128]’ (CHRB, 2017, p2-3). This type of analysis demonstrates the major gap between rhetoric and practice which exists in relation to many responsible business topics.
[127] https://www.corporatebenchmark.org/
[128] https://www.corporatebenchmark.org/sites/default/files/2017-03/CHRB_Findings_web_pages.pdf
The vision for and process of industry transformation needs to be better articulated and monitored. Work on sector transformation in export agriculture sectors provides insights on the key phases of change (Molenaar et al, 2015)[129], but may have limits of applicability for some sectors, where companies can more easily switch sourcing locations in a search for cheap labour. A model of systemic change in market systems suggests scaling, sustainable benefits and resilience are all required, with new practices being adopted by partner companies, adapted/mainstreamed across organisations, expansion (crowding in by competitive actors) and responses (institutionalization by governments) (DCED, Kessler, 2014)[130]. A key mechanism being increasingly widely used to facilitate stakeholder dialogue and coordination in sectors and at other scales, are multi-stakeholder initiatives (MSIs). There are now 45 transnational MSIs setting standards (ref), but a much larger number when including legality and governance MSIs, REDD+ and jurisdictional approaches (WWF ref). Despite this growth there are questions on their effectiveness beginning to emerge, particularly relating to the quality of participation for more marginal groups (Nelson/Tall ref; MSI-Integrity)
[129] Stage 1: civil society raise awareness of challenges; first movers support pilots and benefit reputationally, as new standards and tools are developed. In stage 3, the sector transformation model suggests that competitors crowd-in and adopt similar practices, and in stage 4 there is a process of institutionalization with government creating a level playing field and all companies required to meet sustainable practices. In Molenaar, J.W., Dallinger, J., Gorter, J., Heilbron, L., Simons, L., Blackmore, E., Vorley, B. (2015). The role of VSS in scaling sustainability in smallholder dominated agricultural sectors. White Paper 4. Commissioned by IFC
[130] Kessler, A (2014, links updated 2016) ‘Assessing Systemic Change: Implementation Guidelines for the DCED standard’
A less corporate-centric approach is needed in which efforts are not targeted solely at changing firm level behaviour but focus on societal responsibility ‘in a broader sense’ and ‘manifest in industry-wider solutions and multi-stakeholder initiatives where corporations would perceive themselves as a stakeholder of the problem rather than as the centre of a stakeholder network’ (Crane et al, 2014). Businesses are social actors with an economic purpose, but the degree to which their goals are moderated by certain opportunities or constraints depends on the specific social reality in which business operates’ (Crane et al, ibid).
Related to both individual corporate transformation prospects and that of whole sectors and global industries is achieving better understanding of success (and failure) factors. Corporate ownership and business models clearly influence outcomes, but it is not easy to draw hard and fast rules. The current focus of many responsible business initiatives is on large MNEs (although increasingly RBIs are looking to meet the needs of SMEs). But there is emerging evidence that it may easier for start-up companies to adopt new sustainable business models that for incumbents to adapt incrementally – ‘modular architecture’ in companies is less easy to change compared with ‘integral architectures’ (Blowfield, pers. comm). Increasingly the responsible business debate suggests that companies will need to integrate sustainability into business purpose and models because of the resource constrained economy and changing public expectations of business (Blowfield, 2013[131]). There remain questions about how far and how fast incumbent companies can go in achieving responsible business in the global economic context which puts downward pressure on margins and labour conditions etc.
[131] Blowfield, M. (2013)’Business and Sustainability’ Oxford University Press
Bottom of the Pyramid (BoP) business models are lauded for delivering services to poor rural and urban consumers. However, critics of bottom of the pyramid approaches suggest that the business case is not necessarily in place to ensure profitability. The OECD notes that in many industries leading companies are making greater productivity gains, leaving ‘poorer performing counterparts struggling in their trail’ (OECD, 2017)[132]. Leading companies, because they operate often as part of an MNE group, can take advantage of being inter-connected with suppliers and customers from different countries to capture gains from global value chains, and greater international tax competition etc. Such economic forces of corporate concentration represent major challenges for responsible business.
[132] OECD (2017) ‘Time to Act: Making Inclusive Growth Happen’. OECD Policy Brief.
6.4 Plausibility of the Theory of the Change
What can be learned from the achievements of responsible business to date to test the plausibility of the RATE theory of change in the future? The potential for RBIs to effectively contribute to improvements in the safety and wellbeing of the poor, and of the environment, can be informed by an analysis of progress to date on the ground in developing countries and emerging markets.
Firstly, to note: There are two major obstacles to such a retrospective analysis. Firstly, the diversity and scope of global business and investment, and secondly, the wide-ranging nature of responsibility issues. Global business covers small farmers, SMEs, to global firms with differing ownership models. Global business includes a diversity of corporate ownership models and the literature is mixed on how such models influence responsible business performance. [Significant amounts of global business are conducted by SMEs, not large companies and increasingly trade is south-south]. Similarly, investors (asset owners and managers) range in type with rapid changes afoot. Responsibility can cover a multitude of issues (and the level of responses from companies vary in strengthen and significance (from incremental changes such as weak commitments to not knowingly using cotton from Uzbekistan to far reaching changes in actual sourcing practices). It is thus difficult to generalize about whether RBIs have been effective – it is highly context specific. The lack of data on effectiveness and impact of RBIs is not surprising, given the challenges of accessing private sector data. In some areas, such as product standards, there is comparatively good data. In other areas, there is a lot of data, but no clear answers (e.g. on the business case there is conflicting evidence). In some areas there is a clear lack of evidence (e.g. on corporate reporting, purchasing practice changes). On the purchasing practices there is almost no data (partly due to commercial confidentiality) and no easy answers[133]. In general, the evidence base for knowing what works in responsible business is thin.
[133] Purchasing practices and working conditions in global supply chains: global survey results. INWORK Issue Brief No. 10. ILO (2017)
What is clear is that there has been a definite increase in the attention given by business to social and environmental issues[134]. However, existing evidence and trends on the ground in emerging economics and developing countries suggest that later assumptions in the theory of change may not hold true. This has implications for the design of programmes and interventions on responsible business. The key points are as follows:
[134] Impact. Transforming Business. Changing the World. UNGC DNV (2015)
- The business case for RB is variable and uncertain. It should not be assumed that responsibility makes business-sense, at least in the short term.
- Progress towards responsibility in business has been heavily concentrated in a small minority of reputation-sensitive companies and sectors, and in a very small minority of companies. UNGC, the world’s largest corporate sustainability initiative with over 9,500 business members, covers just 2% of global GDP, 2% of listed companies, and 4% of people working in the private sector[135].
  [135] UNGC (2015, p.60)
- Many international supply chains have evolved to be extremely long, complex and opaque. Just understanding their supply chains, let alone acting to improve conditions within them, has proved to be a huge undertaking for the most committed of companies. If companies do not know what is going on – or do not want to – achieving impact is virtually impossible.
- There tends to be a sharp fall-off from commitments to action, particularly action in distant subsidiaries, supply chains or beyond Tier 1 suppliers. A much higher percentage of companies have policies on human rights than carry out impact assessments, monitor or evaluate performance, or disclose information on policies and practices[136].
  [136] 2017 UNGC Progress Report. UNGC (2017, p. 47)
- Such improvements as have been achieved in supply chains may be confined to easy to address issues: ‘basic improvements have been achieved in some areas (e.g. health and safety), but not in others (e.g. freedom of association, excessive working hours)’[137]. Early research on the poverty impact of corporate codes of practice found this to be the case (Nelson, Martin and Ewert, 2007[138]) An impact assessment of ETI in 2003-2006 found a similar picture[139], as have meta-analyses of product standards. Problems relating to working conditions, such as purchasing practices and living wages that were correctly identified over ten years ago are still being discussed[140].
  [137] R. M. Locke (2013, p.174).
  [138] Nelson, V., A. Martin, J. Ewert (2007) ‘The Impacts of Codes of Practice on Worker Livelihoods: Empirical Evidence from the South African Wine and Kenyan Cut Flower Industries’. The Journal of Corporate Citizenship, Winter, 28: 61.
  [139] ETI IDS (2006)
  [140] Purchasing Practices: marrying the commercial with the ethical. ETI (2004). Purchasing practices and working conditions in global supply chains: global survey results. INWORK Issue Brief No. 10. ILO (2017). Action Collaboration Transformation (ACT) https://actonlivingwages.com/
More fundamentally, much of the persistence of poor working conditions and labour rights, and negative community and environmental impacts are the result of the ‘causal drivers of global production networks in terms of the competitive dynamics (optimizing cost-capability ratios, market imperatives, and financial discipline) and risk environments’[141]. Poor working conditions and insecure labour rights, for example, are a systemic and structural feature of a business and economic model that links large retailers and global brands in highly unequal and price-sensitive relationships with a mass of, generally small, competing suppliers in countries with weak governance and poor labour rights. ‘Upstream’ business practices have major ‘downstream’ effects on suppliers and their workers[142]. ‘When supplier firm margins are squeezed by the asymmetry of market structure in global value chains, these firms in turn are under enormous pressure to keep wages and labour standards low’[143]. This model combined with the poor governance in supplier countries causes the lack of a universal business case, which in turns explains the limited RBI coverage, and combined goes a long way to explaining why the extent of improvements in global supply chains have been so limited and slow, and why much less progress has been made on fundamental issues such as freedom of association and living wages/incomes. This history and reality has significant implications for programmes such as RATE.
[141] Yeung, H.W., N. M. Coe, (2014) ‘Toward a Dynamic Theory of Global Production Networks’. Journal of Economic Geography. 91 (1) pp29-59.
[142] Locke (2013, p.175).
[143] Outsourcing Economics. Global Value Chains in Capitalist Development. Milberg, W. and Winkler, D. (2013, p.304)

Annex 7: Assessment of RATE against Programme Logical Framework
			Baseline / (Aug 14)	Milestone 3 / (Aug 17)	Target / (Dec 18)	Comment
IMPACT
Where business activity affects their lives and the environment, the safety and well-being of poor women and men in developing and middle-income countries, and the impact on the local and global environment, is improved.	Percentage of (a) developing and (b) emerging countries rated as 4 or above on the ITUC Global Rights Index	Planned	Low Income Country (LIC) - 56%;[144] / Lower Middle-Income Country (LMIC) - 68%	To be defined	To be defined	The ITUC Global Rights Index rates 139 countries on a scale from 1-5 based on the degree of respect for workers’ rights. A large and increasing percentage of low income and lower middle-income countries are rated 5+ (no guarantee of rights due to the breakdown of the rule of law), 5 (no guarantee or rights), or 4 (systematic violation of rights).
		Achieved		LIC – 84% / LMIC – 76%
		Source	ITUC Global Rights Index annual reports. Scale 1 (irregular violations) to 5+ (no guarantee of rights due to breakdown in rule of law).
	Number of forced labourers and child labourers in Africa, Asia & the Pacific, and Latin America & the Caribbean	Planned	Forced labour - 17 million; Child labour - 108 million.	To be defined	To be defined	The latest ILO report estimates 40 million people were victims of modern slavery in 2016 (25 million in forced labour and 15 million in forced marriage). 25% of victims of modern slavery are children, 71% are women or girls[145]. 152 million children, aged between 5 and 17, are subject to child labour, almost half in hazardous child labour. Since 2000, total child labour has reduced by 38%, hazardous child labour by 58%, although the pace of reduction has significantly slowed since 2012.[146]
		Achieved		Forced labour – 25 million; Child labour – 152 million
		Source	Global Estimate of Forced Labour (ILO, 2013); Global Child Labour Trends (ILO,2012)
	Cost of corporate natural capital impacts (million USD)	Planned	2,871,000	To be defined	To be defined	3,447,000 in 2015 compared to revised 2014 figure of 3,712,000. Although suggesting a slight fall since 2014, natural capital costs were still more than double corporate profits for the largest 1,200 companies globally. Most of these costs are not direct, but concealed in the supply chain[147]
		Achieved		3,447,000
		Source	Global Trucost data (State of Green Business report)
OUTCOME
Businesses are diligent in managing the social and environmental implications of their actions and are accountable for the consequences for poor women and men in developing and middle-income countries.	Number of certificates issued by ISEAL members (a) globally, and (b) in Brazil, India and China.	Planned	46,553 / 8,079	65,000	(a) 71,000	Number of certificates includes production certificates and chain of custody certificates (or nearest proxy). The June 2017 figures do not include the most recent numbers on production certificates from the Global Coffee Platform
		Achieved		June 2017: / 65,484 / 12,816
		Source	Data from implementing partner (ISEAL)
	Number of businesses (cumulative) submitting sustainability reports (a) globally, and (b) in Africa, Asia, and LAC	Planned	2013 Baseline: / 4,150 / 1852	End 2016: / 4,718 / 2,234	Mar 2019: / 7,000 / 3,670	5,906 2015 sustainability reports were registered in GRIs Sustainability Disclosure Database. 6,254 2016 sustainability reports have been received so far.
		Achieved		5,906 / 2,878
		Source	Data from implementing partner (GRI)
	Number and percentage of UNGC signatories to the Women's Empowerment Principles submitting gender-specific Communication on Progress reports.	Planned		To be defined	To be defined	Data on this indicator is not available from UNGC. A new UNGC logframe will be produced in early 2018. / As at December 2016, the number of UNGC signatories supporting the WEP’s CEO statement was 1,500 against a target of 1,050.
		Achieved
		Source	Data from implementing partner (UNGC)
	Level of progress in company's ethical trade performance reported by ETI corporate members	Planned	2016 Baseline: / Leader =11; Achiever=14; Improver=49; Foundation=12	System under development	L=15; / A=19; / I=42; / F=9	The revised ETI reporting framework for company members has been agreed, and pilot reports have been submitted and reviewed. A transparency roadmap is under development.
		Achieved
		Source	ETI feedback on member reports and grading of members at Leader, Achiever, Improver and Foundation levels
	Percentage of reporting companies whose disclosure maturity reporting improves by more than one level.	Planned	2016 Baseline: / 0	5%	30%	SHIFT now recognise that trying to gather data at the end of year 1 was premature. Developments are expected to be more visible at the end of the second year
		Achieved		0%
		Source	Data from implementing partner (SHIFT Reporting Database)
OUTPUT 1
Increased business outreach and networks	Number of business leaders engaged with ISEAL (cumulative)	Planned	782	5482	5482	These are cumulative figures. ISEAL reports annual figures.
		Achieved		6563
		Source	Data from implementing partners' annual reports
	Number of businesses involved with (a) Global Reporting Initiative focal point in South Africa; (b) B Lab hub in East Africa.	Planned	769 / 117	1080 / 215	1160 / 600	The number of businesses involved with B Lab refers to the number of total registered users of the Impact Assessment tool. / Only half of the revised target of 10 certified B Corps in East Africa has been achieved, but more are in the pipeline.
		Achieved		1246 / 256
		Source	Data from implementing partner (B Lab)
	Number of country-based multi-stakeholder ethical trade platforms focused on increasing the rights of workers in supply chains	Planned	0		2020: 5	Significant delays due to in-country challenges in 2016. First Bangladesh platform meeting held in July 2017. Work in India, Pakistan and South Africa may lead to multi-stakeholder platforms. ETI now aiming for ‘increased dialogue between relevant local stakeholders’ rather than platforms per se.
		Achieved		1
		Source	Data from implementing partner (ETI)
OUTPUT 2
Improved standards, guidance, tools, reporting systems and innovations generated and shared	Number of (a) updated and (b) new GRI Reporting Guidelines produced and disseminated.	Planned	(a) 0 of existing 46 issue-level reporting guidances being updated, (b) 0 new issue-level guidances in development.	Dec 2016: / 6 / 2	Mar 2019: / 9 / 3	Updates of two guidances started in January. The annual milestone for issue level reporting guidances was not achieved, but GRI is confident that the 2019 target of 9 will be achieved.
		Achieved		2
		Source	Data from implementing partner (GRI)
	Number of (a) companies on and (b) users of, human rights reporting database	Planned	2016 Baseline: / 40 / 0	2017: / 120 / 4,000	2019: / 300 / 7,000	The number of users is measured by the number of database searches. As at July 2017, Shift was not on track for the target of 4,000 by the end of the year.
		Achieved		94 / 644
		Source	Data from implementing partner (SHIFT)
	B Lab standards for emerging markets reviewed and improved	Planned	Version 5 of B Impact Assessment (BIA)	7/2017: East Africa Regional Advisory Group convened	7/2019: E African companies certifying on version 6 of BIA	New drafts of Version 6 of the BIA will be ready for initial testing in mid-2018, with an anticipated launch in January 2019.
		Achieved		Group convened
		Source	Data from implementing partner (B Lab)
OUTPUT 3
Impact evidence generated and shared	Number of published externally reviewed reports/case studies addressing the business, social or environmental impacts of responsible business initiatives.	Planned	June 2014 baseline: / 0	June 2017: / 135		Data refers to the number of new reports addressing sustainability impacts and performance of standards listed on the ISEAL website.
		Achieved		150
		Source	Data from ISEAL database
	Number of published externally reviewed research reports addressing modern slavery issues	Planned				New research fund managed by British Academy. Research call issued. Fund manager recently appointed.
		Achieved
		Source	Data from RATE research partner (British Academy)
	Case studies published of company and investor awareness of working practices in target countries	Planned	2016 baseline: / 0	2	3	Second case study due to be published shortly. Three further case studies are planned to be completed by September 2018.
		Achieved		1
		Source	Data from ShareAction and OXFAM
OUTPUT 4
Government-led interventions demonstrate that they extend responsible business practices	Proportion of complaints concluding in agreement between parties or recommendation by the UK NCP	Planned	March 2015: / 50% (total number of cases = 2)	August 2017: / 80% (total number of cases = ?)	December 2018: / 80% (total number of cases = ?)	A small and declining number of cases are handled by the UK NCP each year. Since 2015, 5 of the 6 published Initial Assessments have rejected the complaint at this stage, and 4 Final Statements have recorded agreement or made recommendations.
		Achieved		50%
		Source	UK National Contact Point (NCP) reports to Steering Committee
	Peer assessment of performance of UK NCP compared with other NCPs	Planned	UK NCP is top-performing G7 member NCP and amongst top three NCPs	UK NCP maintains its leading position amongst all NCPs	UK NCP maintains its leading position amongst all NCPs	A peer assessment of the performance of the UK NCP is scheduled for late 2018.
		Achieved
		Source	Commentary by the OECD and other interested stakeholders
[144] DAC List of ODA Recipients (2014). Percentage of countries rated in each group in each ITUC survey year (2014 and 2016 data).
[145] ILO – Global Estimates of Modern Slavery 2017
[146] ILO Alliance 8.7 – 2016 Global Estimates of Child Labour
[147] Greenbiz and Trucost – State of Green Business 2017

Annex 8: Individual Organisational Assessment Summaries
Name	Approach	Maturity level	RATE project performance	Last major impact assessment	Likely or actual contribution to corporate behaviour change	Likely or actual contribution to impact on poor people	Strengths of the RBI approach in influencing corporate behaviour and achieving impact	Weaknesses of the RBI approach in influencing corporate behaviour and achieving impact	Key Recommendations
GRI	Standard for corporate reporting on sustainability performance to increase transparency	H / [Major grant for core activities & tailored deliverables]	On track	-	Limited evidence to date	Limited evidence to date.	Globally, most commonly used corporate RB performance reporting standard, covering wide range of sustainability issues. In-country fora being established. Respected initiative.	Lack of evidence that there is a business case for change in corporate practices. Not clear that corporate reporting drives change in business responsibility.	Rapid improvement in M&E system within current grant. / Organisational impact assessment needed. / In future, if funding provided could shift to earmarked funding.
ETI	Multi-stakeholder learning and improvement initiative	H / [Core funding]	On track for all except one outcome indicator	2003 / External organisational review in 20015.	No evidence	Limited or dated evidence of some positive easier-issue impacts	Tripartite membership. Respected initiative and Base Code. 2020 Strategy includes action of transparency and accountability, plus three country-based platforms. Good tools and guidance for business.	Very limited external transparency and accountability. Extent of improvement against Base Code unknown. May provide more reputational cover for business than incentive for change. Heavily dependent on DFID support.	Provide robust evidence on changes in material company behaviour due to ETI. Commission independent impact assessment in final year of RATE grant. Future funding should be conditional on this and increased external transparency and accountability. And/or consider shift to earmarked funding.
UNGC	Business-focussed learning and improvement initiative.	High / [Core funding]	On track	2015, but without attention to impacts on people	Uncertain.	Unknown	Universal consensus on 10 Principles. World’s largest corporate sustainability initiative. Accessible for almost all businesses. Global convening power potential and wide coverage, especially in Africa, Asia and Latin America 76 Local Networks. Tools and guidance for business, especially relating to SDGs	Vague and general principles. Covers 2% of global listed companies and GDP only. Communication on Progress provides limited accountability. Limited evidence that UNGC is improving business behaviour. No evidence of UNGC- derived business impacts on poor people or environment.	Limited DFID influence as funds are part of donor stream & private funding is much higher. Use influence to press for increased accountability, improved impact assessment, and evaluation of Local Networks. Or consider shift to earmarked funding for these priorities.
ISEAL	Enhancing the impact of credible sustainability standards for products and value chains	High / [Business & Impacts Case project]	Meeting most output targets	None? / Participatory review (2017)	ISEAL impact on business behaviour (adoption of standards) from this particular DFID project not known. Standards themselves show continuing growth in market penetration & Chain of Custody, but may have hit a ceiling. Variable performance by sector.	Comparatively good evidence base for the impact of standards once adopted, but also gaps. On balance net benefits, but more needs to be done to realize increased benefits for individual producers and workers.	Standards have a direct influence on corporate practice, where standards adopted. Standard development helps define sustainable production in new sectors. Support for sector dialogues for mainstreaming. ISEAL is supporting innovation & addressing challenging issues e.g. living wage. Good emphasis and support for MEL, impact assessment and business benefits analysis.	Impact of standards more limited than anticipated. Growth may be slowing. Driving change in supply chains requires complementary/alternative measures. Standards also responding). Business case work needs to focus as much on costs as benefits.	Continue support subject to better evidence of ISEAL impact on business behaviour relating to ISEAL standards. DFID should continue to encourage ISEAL to facilitate innovation. / Impact research needed on the ‘alternative’ approaches and business case (not just business benefits).
B Lab		M / [E Africa hub project]	Good progress.	None available	Little robust evidence of causal link between B Lab participation and change in corporate behaviour /impacts on the ground.	As for previous. Very little evidence of impacts.	May help define sustainability impact for companies. / New legal forms offer could be transformative. More outcome oriented than other standards & requires continuous improvement.	Length of time to achieve new legal forms? Reporting mainly self-assessment. Standards are not very stringent, but do require continual improvement. Relies mainly on self-assessment (only random auditing). Unclear business case for less responsible companies that require a big change in business models	Continue subject to evidence of relevant changes in business practices directly affecting poor people and the environment in developing/emerging countries.
Shift	Building capacity and incentives for improved HR reporting	M / [x yr project]	Good progress on outputs. Too early for outcomes and impacts	None available	Likely to be variable. Depends on strength of link between HR reporting and HR behaviour. No universal business case for improving all HR behaviour in all companies.	Uncertain. Depends on type and extent of business behaviour change, and trickle down to poor people/environment in developing/emerging economies.	Shift is leading centre of expertise on UNGP. Good early progress on outputs. Commitment to obtaining evidence on the theory of change.	Uncertain theory of change connecting HR reporting – business HR behaviours – impacts on the ground. Impacts will take a long time to trickle time or may not.	M&E priority → evidence of impacts on business Human Rights practices most directly connected with poor people, and the actual impact of changes in practices. →
ShareAction		M / [Specific project]	Good progress.		Many steps in causal chain. Depends on type and extent of investor pressure. No evidence that investor pressure on human rights will lead to sufficient change in the business behaviour that matters.	Uncertain. Depends on type and extent of business behaviour change, and trickle down to poor people/environment in developing/ emerging economies.	Aims to harness potential influence of an important stakeholder (investors), so increasing incentive for companies to take HR seriously.	Uncertain theory of change connecting investor pressure – business HR behaviours – impacts on the ground.	M&E priority → evidence of impacts on business HR practices most directly connected with poor people, and the actual impact of changes in practices.
Fairtrade	Providing innovative tool for greater supply chain transparency	H / [Short pilot]	Good progress	n/a	Positive reaction from companies. Not yet clear whether this will be translated into business behaviour change	Depends on type and extent of business behaviour change. Assumes that increased clarity will have benefits for businesses in the supply chain, and will shift business case towards responsibility.	Innovative approach to using increased transparency to generate shared learning and action	Unproven theory of change linking greater supply chain transparency with substantive business behaviour change that benefits farmers.	Await evaluation of pilot. Stress need for evidence that mapping tool shifts business case and likely to lead to substantive change in business behaviour.

Legend: Organisational Maturity: H = High; M = Medium; NE = Newly Emerging.

Annex 9: Bibliography
Action Collaboration Transformation (ACT) https://actonlivingwages.com/
Barrientos, S. and Smith, S. (2006) The ETI code of labour practice: do workers really benefit? Independent Assessment for ETI. IDS
Blowfield, M. and Murray, A. (2014) – Corporate Social Responsibility
Brown, J.A. et al (2016) – The UN Global Compact: engaging implicit and explicit CSR in global governance.
CORE (2017) - Risk Averse? Company reporting on raw material and sector-specific risks under the Transparency in Supply Chains clause in the UK MSA 2015.
Corporate Accountability Research (2016) - Negotiated Solutions to Human Rights Violations in Global Supply Chains
Corporate Human Rights Benchmark (2017) - Key Findings 2017
Danish Business Authority (2015) – A comparison of 4 international guidelines for CSR
DFID (2011) - DFID’s Approach to Value for Money
DFID (2014) - Responsible, Accountable and Transparent Enterprise (RATE). Business Case and Intervention Summary. Private Sector Department (Business Engagement Hub).
DFID (2017) – Economic Development Strategy: prosperity, poverty and meeting global challenges
DFID (2017) - RATE Annual Review, September 2017
El Blog Academia B - http://blog.academiab.org/2017/06/04/sistema-b-pioneers-affecting-systemic-change-in-latin-america/
ETI (2004) - Purchasing Practices: marrying the commercial with the ethical
FCO (2016) – Good Business: implementing the UN Guiding Principles on Business and Human Rights
Friede, G. et al (2015) ‘ESG and financial performance: aggregated evidence from more than 2000 empirical studies’. Journal of Sustainable Finance and Investment. Vol. 5, 2015 – Issue 4.
Greenbiz and Trucost (2017) State of Green Business 2017
ILO (2015) World Employment Social Outlook
ILO (2016) – Decent work in global supply chains
ILO (2017) – Global estimates of modern slavery 2017
ILO (2017) – 2016 global estimates of child labour
ILO (2017) - Purchasing practices and working conditions in global supply chains: global survey results. INWORK Issue Brief No. 10.
ISEAL (2015) - Ensuring VFM: ISEAL’s Approach to managing its DFID Funded Project
ISEAL - www.isealalliance.org/our-work/improving-effectiveness/global-living-wage-coalition
International Trade Union Confederation (ITUC) - Global Rights Index 2017
KPMG (2017) – The Road Ahead - survey of corporate responsibility reporting 2017
LeBaron, G. et al (2018) - Confronting root causes: forced labour in global supply chains
Locke, R.M. (2013) – The promise and limits of private power – promoting labor standards in a global economy
Milberg, W. and Winkler, D. (2013) - Outsourcing Economics. Global Value Chains in Capitalist Development.
New York University Stern (2017) - Putting the ‘S’ in ESG: measuring human rights performance for investors
OECD DAC (2002) – Glossary of key terms in evaluation and results based management
OECD (2005) – The UN Global Compact and the OECD Guidelines for Multinational Enterprises: complementarities and distinctive contributions.
Rasche, A. (2009) – “A Necessary Supplement” – What the UN Global Compact Is and Is Not.
Rasche, A. and Waddock, S. ( ) – Global Sustainability Governance and the UN Global Compact: a rejoinder to critics
Ruggie, J.G (2017) – Acceptance Speech, A.SK Social Science Award 2017, Harvard Kennedy School
Said Business School/Univ. of Oxford (2016) - State & Direction of Inclusive Capitalism
Sethi, S. and Schepers, D. (2014) – UN Global Compact: The Promise-Performance Gap
Shift (2017) - Human Rights Reporting: Are Companies Telling Investors What They Need To Know?
SOMO (2013) – Corporate responsibility instruments. A comparison of the OECD Guidelines, ISO 26000 & the UN Global Compact
State of Sustainability Initiatives (2014) – Review 2014: standards and the green economy
Stockholm Resilience Centre - http://www.stockholmresilience.org/research/planetary-boundaries/planetary-boundaries/about-the-research/the-nine-planetary-boundaries.html
Sustainable Apparel Coalition - https://apparelcoalition.org/the-sac/
The Circle (2017) - Fashion Focus. India Annex
UNGC (2017) – UNGC Progress Report 2017
UNGC (2015) - Impact. Transforming Business. Changing the World. UNGC and DNV GL
UNGC (2013) Architects of a better world: Building the post-2015 business engagement architecture (https://www.unglobalcompact.org/library/441
UNGC (2011) – A response from the Global Compact Office to the JIU report
UNGC (2016) – UN Global Compact. 2020 Global Strategy
UN Joint Inspection Unit (2010) – United Nations Partnerships: the role and functioning of the Global Compact
World Economic Forum (2018) – The Global Risks Report. 13thEdition.
Yeung, H.W., N. M. Coe, (2014) ‘Toward a Dynamic Theory of Global Production Networks’. Journal of Economic Geography. 91 (1) pp29-59.
Annex 10: Mapping Exercise Findings
Table 10.1 shows the percentage of companies from each industry group that is reporting against GRI guidelines. This ranges from 10% to 29%. Most of the companies in the sample are reporting against G4 guidelines, which is the most recent version of the guidelines:
“Launched in 2006, the G3 Guidelines feature sustainability disclosures that organizations can adopt flexibly and incrementally, enabling them to be transparent about their performance in key sustainability areas. In 2011, the G3.1 Guidelines were released. This update completed the content of G3, with expanded guidance on local community impacts, human rights and gender. It also introduced the Technical Protocol – Applying the Report Content Principles offering process guidance on how to define the content of a sustainability report. In May 2013, GRI launched the fourth generation of Guidelines, the G4.”[148]
[148] https://www.globalreporting.org/standards/G3andG3-1/Pages/default.aspx
The food, beverage & tobacco industry group has the highest proportion (29%) of companies reporting.
Table 10.1 Number of companies in DJSI 2016 starting universe who reported against GRI guidelines in 2015
	Industry group	Total number of companies	Companies reporting	%		Guidelines used
						G3	G3.1	G4
Agriculture	Food & Staples Retailing	67	8	12%				8
	Food, Beverage & Tobacco	157	46	29%				46
Textiles	Consumer Durables & Apparel	110	13	12%			1	12
	Retailing	115	11	10%				11
Electronics	Technology Hardware & Equipment	120	23	19%				23
	Semiconductors & Semiconductor Equipment	68	15	22%		1		14
Extractives	Materials	282	63	22%			3	60
Across sectors	Transportation	136	26	19%			3	23

The percentage of reports that have external assurance varies across the industry groups. The semiconductor sector stands out with a low percentage of 20%, while for other industry groups this varies from 45% to 67% (see Table 10.2). Assurance is mostly given by accountants such as Pricewaterhouse Coopers, KPMG and Ernst & Young.
Table 10.2 Number of companies with external assurance for their GRI report
	Industry group	Companies reporting	External assurance	% with external assurance
Agriculture	Food & Staples Retailing	8	5	63%
	Food, Beverage & Tobacco	46	22	48%
Textiles	Consumer Durables & Apparel	13	8	62%
	Retailing	11	5	45%
Electronics	Technology Hardware & Equipment	23	14	61%
	Semiconductors & Semiconductor Equipment	15	3	20%
Extractives	Materials	63	42	67%
Across sectors	Transportation	26	15	58%

Taking into account the extra companies that were encountered from other benchmark lists slightly changes the proportions, as shown in Table 10.3.
Table 10.3: Industry groups where proportions of companies reporting changes after adding extra companies to sample
	Industry group	Total number of companies	Companies reporting	%		Guidelines used
						G3	G3.1	G4
Agriculture	Food, Beverage & Tobacco	161	46	29%				46
Electronics	Technology Hardware & Equipment	121	24	20%				24
Across sectors	Transportation	137	26	19%			3	23

Table 10.4: All companies reporting against GRI guidelines
GICS industry group	Company	GRI industry	External assurance	Type of assurance provider	Assurance provider
Food Retailing	Aeon Co Ltd	Retailers	No	0	0
Food Retailing	Carrefour SA	Retailers	No	0	0
Food Retailing	CVS Health Corporation	Healthcare Products	No	0	0
Food Retailing	Delhaize Group	Retailers	Yes	Accountant	Ernst & Young
Food Retailing	ICA Gruppen AB	Retailers	Yes	Accountant	Ernst & Young
Food Retailing	Kesko Oyj A	Retailers	Yes	Accountant	PricewaterhouseCoopers
Food Retailing	Kesko Oyj B	Retailers	Yes	Accountant	PricewaterhouseCoopers
Food Retailing	Seven & I Holdings Co Ltd	Retailers	Yes	Engineering firm	Bureau Veritas
Food, Beverage & Tobacco	Alicorp SA	Other	No	0	0
Food, Beverage & Tobacco	Arca Continental, SAB de CV	Food and Beverage Products	Yes	Accountant	PricewaterhouseCoopers
Food, Beverage & Tobacco	Asahi Group Holdings Ltd	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	AVI Ltd	Other	No	0	0
Food, Beverage & Tobacco	BRF S.A.	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	British American Tobacco Malaysia Bhd	Tobacco	Yes	Accountant	Ernst & Young
Food, Beverage & Tobacco	Bunge Ltd	Agriculture	Yes	Accountant	Other
Food, Beverage & Tobacco	Charoen Pokphand Foods	Food and Beverage Products	Yes	Accountant	PricewaterhouseCoopers
Food, Beverage & Tobacco	Charoen Pokphand Indonesia Tbk PT	Food and Beverage Products	Yes	Accountant	Lloyds
Food, Beverage & Tobacco	Coca-Cola Amatil Ltd	Food and Beverage Products	Yes	Accountant	Ernst & Young
Food, Beverage & Tobacco	Coca-Cola Co	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Coca-Cola Embonor SA B	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Coca-Cola Enterprises	Food and Beverage Products	Yes	Engineering firm	DNV
Food, Beverage & Tobacco	Coca-Cola Femsa SAB de CV L	Food and Beverage Products	Yes	Accountant	Deloitte
Food, Beverage & Tobacco	Coca-Cola HBC AG	Food and Beverage Products	Yes	Accountant	Deloitte
Food, Beverage & Tobacco	Coca-Cola Icecek Uretim AS	Food and Beverage Products	Yes	Accountant	Ernst & Young
Food, Beverage & Tobacco	Coca-Cola West Japan Co	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	ConAgra Foods Inc	Food and Beverage Products	Yes	Engineering firm	Bureau Veritas
Food, Beverage & Tobacco	Diageo Plc	Food and Beverage Products	Yes	Accountant	KPMG
Food, Beverage & Tobacco	Embotelladora Andina SA A	Consumer Durables	No	0	0
Food, Beverage & Tobacco	Embotelladora Andina SA B	Consumer Durables	No	0	0
Food, Beverage & Tobacco	General Mills Inc	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Graincorp Ltd A	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Grupo Bimbo S.A.B.	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Grupo Nutresa S.A.	Food and Beverage Products	Yes	Accountant	KPMG
Food, Beverage & Tobacco	Heineken NV	Food and Beverage Products	Yes	Accountant	KPMG
Food, Beverage & Tobacco	Hormel Foods Corp	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Imperial Pacific International Holdings Ltd	Logistics	No	0	0
Food, Beverage & Tobacco	Imperial Tobacco	Tobacco	No	0	0
Food, Beverage & Tobacco	Indofood CBP Sukses Makmur TBK PT	Agriculture	No	0	0
Food, Beverage & Tobacco	Indofood Sukses Makmur Tbk PT	Agriculture	No	0	0
Food, Beverage & Tobacco	Japan Tobacco Inc	Tobacco	No	0	0
Food, Beverage & Tobacco	JBS SA	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Kikkoman Corp	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Kirin Holdings Co Ltd	Food and Beverage Products	Yes	Accountant	KPMG
Food, Beverage & Tobacco	Lindt & Sprungli AG Ptg	Textiles and Apparel	No	0	0
Food, Beverage & Tobacco	Lindt & Sprungli AG Reg	Textiles and Apparel	No	0	0
Food, Beverage & Tobacco	Lotte Chilsung Beverage	Chemicals	Yes	Small consultancy/ boutique firm	Other
Food, Beverage & Tobacco	Lotte Confectionery Co	Chemicals	Yes	Small consultancy/ boutique firm	Other
Food, Beverage & Tobacco	Lotte Food Co Ltd	Construction	Yes	Engineering firm	DNV
Food, Beverage & Tobacco	Marine Harvest ASA	Food and Beverage Products	Yes	Accountant	Ernst & Young
Food, Beverage & Tobacco	MEIJI Holdings Co Ltd	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	Nestle SA Reg	Food and Beverage Products	No	0	0
Food, Beverage & Tobacco	PepsiCo Inc	Food and Beverage Products	Yes	Engineering firm	Bureau Veritas
Food, Beverage & Tobacco	SABMILLER PLC	Food and Beverage Products	Yes	Accountant	PricewaterhouseCoopers
Consumer Durables & Apparel	Amer Sports Oyj-A Shs	Equipment	No	0	0
Consumer Durables & Apparel	Arcelik Co	Consumer Durables	Yes	Engineering firm	Other
Consumer Durables & Apparel	Asics Corp	Textiles and Apparel	Yes	Accountant	Deloitte
Consumer Durables & Apparel	Coway Co Ltd	Household and Personal Products	No	0	0
Consumer Durables & Apparel	Formosa Taffeta Co Ltd	Technology Hardware	No	0	0
Consumer Durables & Apparel	Gildan Activewear Inc A	Textiles and Apparel	No	0	0
Consumer Durables & Apparel	Hugo Boss AG	Textiles and Apparel	Yes	Accountant	Ernst & Young
Consumer Durables & Apparel	JM AB	Real Estate	No	0	0
Consumer Durables & Apparel	LG Electronics Inc	Consumer Durables	Yes	Small consultancy/ boutique firm	Other
Consumer Durables & Apparel	Ruentex Industries	Other	Yes	Accountant	PricewaterhouseCoopers
Consumer Durables & Apparel	SEB SA	Financial Services	Yes	Accountant	PricewaterhouseCoopers
Consumer Durables & Apparel	Sekisui Chemical Co	Chemicals	Yes	Accountant	Deloitte
Consumer Durables & Apparel	Sekisui House	Real Estate	Yes	Small consultancy/ boutique firm	Other
Retailing	Gap Inc	Retailers	No	0	0
Retailing	Inditex SA	Retailers	No	0	0
Retailing	Kingfisher	Retailers	Yes	Engineering firm	SGS
Retailing	Lojas Renner SA	Retailers	No	0	0
Retailing	LOTTE Himart	Textiles and Apparel	Yes	Accountant	PricewaterhouseCoopers
Retailing	Lotte Shopping	Construction	Yes	Engineering firm	DNV
Retailing	Lowe's Cos Inc	Construction	Yes	Engineering firm	DNV
Retailing	Marks & Spencer Group	Retailers	No	0	0
Retailing	Marui Group Co Ltd	Retailers	Yes	Accountant	Ernst & Young
Retailing	Myer Holdings Ltd	Retailers	No	0	0
Technology Hardware & Equipment	Advantech Co Ltd	Computers	Yes	Engineering firm	SGS
Technology Hardware & Equipment	Alcatel-Lucent SA	Telecommunications	Yes	Accountant	Ernst & Young
Technology Hardware & Equipment	Asustek Computer Inc	Computers	Yes	Engineering firm	SGS
Technology Hardware & Equipment	Brother Industries	Technology Hardware	No	0	0
Technology Hardware & Equipment	Compal Electronics Inc	Computers	Yes	Engineering firm	SGS
Technology Hardware & Equipment	Delta Electronics Thai PCL	Technology Hardware	Yes	Engineering firm	SGS
Technology Hardware & Equipment	Flextronics Intl Ltd	Technology Hardware	No	0	0
Technology Hardware & Equipment	Foxconn Technology Co Ltd	Technology Hardware	No	0	0
Technology Hardware & Equipment	Fujifilm Holdings Corp	Technology Hardware	No	0	0
Technology Hardware & Equipment	Hitachi	Technology Hardware	Yes	Accountant	KPMG
Technology Hardware & Equipment	Hon Hai Precision Industry Co Ltd	Technology Hardware	No	0	0
Technology Hardware & Equipment	HP Inc	Computers	Yes	Accountant	Ernst & Young
Technology Hardware & Equipment	HTC Corporation	Automotive	Yes	Engineering firm	SGS
Technology Hardware & Equipment	Ibiden Co	Equipment	No	0	0
Technology Hardware & Equipment	Inventec Corp	Computers	Yes	Engineering firm	SGS
Technology Hardware & Equipment	Kyocera Corp	Equipment	No	0	0
Technology Hardware & Equipment	Lenovo Group Ltd.	Computers	No	0	0
Technology Hardware & Equipment	LG Display Co Ltd	Technology Hardware	Yes	Small consultancy/ boutique firm	Other
Technology Hardware & Equipment	Nokia OYJ	Consumer Durables	Yes	Accountant	PricewaterhouseCoopers
Technology Hardware & Equipment	Pegatron Corporation	Computers	Yes	Engineering firm	Bureau Veritas
Technology Hardware & Equipment	Ricoh Co	Technology Hardware	Yes	Engineering firm	Bureau Veritas
Technology Hardware & Equipment	Samsung SDI Co	Equipment	Yes	Engineering firm	DNV
Technology Hardware & Equipment	Seagate Technology	Technology Hardware	No	0	0
Technology Hardware & Equipment	Celestica	Equipment	No	0	0
Semiconductors & Semiconductor Equipment	ARM Holdings	Technology Hardware	No	0	0
Semiconductors & Semiconductor Equipment	ASML Holding NV	Technology Hardware	No	0	0
Semiconductors & Semiconductor Equipment	Epistar Corp	Technology Hardware	Yes	Engineering firm	Other
Semiconductors & Semiconductor Equipment	First Solar Inc	Energy	No	0	0
Semiconductors & Semiconductor Equipment	Infineon Technologies AG	Technology Hardware	No	0	0
Semiconductors & Semiconductor Equipment	Inotera Memories	Technology Hardware	No	0	0
Semiconductors & Semiconductor Equipment	KLA-Tencor Corporation	Other	No	0	0
Semiconductors & Semiconductor Equipment	Lam Research Corp	Other	No	0	0
Semiconductors & Semiconductor Equipment	Mediatek Inc	Computers	Yes	Accountant	Ernst & Young
Semiconductors & Semiconductor Equipment	Microchip Technology Inc	Technology Hardware	No	0	0
Semiconductors & Semiconductor Equipment	Novatek Microelectronics Corp	Energy	No	0	0
Semiconductors & Semiconductor Equipment	Nvidia Corp	Technology Hardware	Yes	Small consultancy/ boutique firm	Other
Semiconductors & Semiconductor Equipment	Phison Electronics	Technology Hardware	No	0	0
Semiconductors & Semiconductor Equipment	Tokyo Electron	Technology Hardware	No	0	0
Semiconductors & Semiconductor Equipment	Xilinx Inc	Technology Hardware	No	0	0
Materials	Akzo Nobel NV	Chemicals	Yes	Accountant	KPMG
Materials	Alrosa PJSC	Mining	Yes	Accountant	PricewaterhouseCoopers
Materials	Alumina Ltd	Mining	Yes	Accountant	PricewaterhouseCoopers
Materials	Ambuja Cements Ltd	Construction Materials	Yes	Engineering firm	Bureau Veritas
Materials	Amcor Ltd	Other	Yes	Accountant	Ernst & Young
Materials	Anglo American Plc	Mining	Yes	Accountant	PricewaterhouseCoopers
Materials	AngloGold Ashanti Ltd	Mining	Yes	Accountant	Ernst & Young
Materials	AptarGroup Inc	Household and Personal Products	Yes	Engineering firm	ERM
Materials	ArcelorMittal Inc	Metals Products	Yes	Accountant	Deloitte
Materials	Asahi Kasei Corporation	Food and Beverage Products	No	0	0
Materials	Ashland Inc	Chemicals	No	0	0
Materials	Avery Dennison Corp	Equipment	No	0	0
Materials	Barrick Gold Corp	Mining	No	0	0
Materials	BASF SE	Chemicals	No	0	0
Materials	BHP Billiton Ltd	Mining	Yes	Accountant	KPMG
Materials	BHP Billiton Plc	Mining	Yes	Accountant	KPMG
Materials	BillerudKorsnas AB	Forest and Paper Products	Yes	Accountant	Ernst & Young
Materials	Boliden AB	Mining	No	0	0
Materials	Braskem SA Prf A	Chemicals	Yes	Accountant	KPMG
Materials	Cementos Argos S.A. Pref	Conglomerates	Yes	Accountant	Deloitte
Materials	Cementos Argos SA	Conglomerates	Yes	Accountant	Deloitte
Materials	Cemex SA CPO	Construction	Yes	Accountant	Deloitte
Materials	China Steel Corp	Chemicals	No	0	0
Materials	Clariant AG Reg	Chemicals	Yes	Accountant	PricewaterhouseCoopers
Materials	Compass Minerals Intl	Mining	Yes	Small consultancy/ boutique firm	Other
Materials	CRH Plc	Construction Materials	Yes	Engineering firm	DNV
Materials	Croda Intl	Chemicals	No	0	0
Materials	Denki Kagaku Kogyo KK	Chemicals	No	0	0
Materials	Dow Chemical	Chemicals	Yes	Engineering firm	ERM
Materials	Ecolab Inc	Chemicals	No	0	0
Materials	Evonik Industries	Chemicals	Yes	Accountant	PricewaterhouseCoopers
Materials	Fibria Celulose S.A.	Forest and Paper Products	No	0	0
Materials	Formosa Plastics Corp	Energy	Yes	Engineering firm	Other
Materials	Gold Fields Ltd	Mining	Yes	Engineering firm	SGS
Materials	Grasim Industries Ltd	Textiles and Apparel	Yes	Engineering firm	Bureau Veritas
Materials	Grupo Argos S.A.	Construction Materials	Yes	Accountant	Deloitte
Materials	Grupo Argos S.A. Preferred	Construction Materials	Yes	Accountant	Deloitte
Materials	HeidelbergCement AG	Construction Materials	No	0	0
Materials	Hexpol AB	Chemicals	No	0	0
Materials	Hitachi Chemical Co	Chemicals	No	0	0
Materials	Hitachi Metals	Metals Products	Yes	Small consultancy/ boutique firm	Other
Materials	Hudbay Minerals	Mining	No	0	0
Materials	Huhtamaki Oyj	Equipment	No	0	0
Materials	Hyundai Steel Co	Metals Products	Yes	Engineering firm	DNV
Materials	Indocement Tunggal Prakarsa Tbk PT	Construction	No	0	0
Materials	Italcementi SpA	Construction Materials	Yes	Accountant	Ernst & Young
Materials	JFE Holdings Inc	Conglomerates	No	0	0
Materials	Klabin SA Unit	Forest and Paper Products	Yes	Small consultancy/ boutique firm	Other
Materials	Lanxess AG	Chemicals	Yes	Accountant	PricewaterhouseCoopers
Materials	LG Chem Ltd	Chemicals	Yes	Engineering firm	DNV
Materials	LG Chem Ltd Prf	Chemicals	Yes	Engineering firm	DNV
Materials	POSCO	Metals Products	Yes	Accountant	PricewaterhouseCoopers
Materials	PTT Global Chemical PCL	Energy	Yes	Accountant	Lloyds
Materials	Randgold Resources Ltd	Mining	Yes	Small consultancy/ boutique firm	Other
Materials	Sandfire Resources NL	Mining	No	0	0
Materials	Semen Indonesia Persero Tbk PT	Mining	No	0	0
Materials	Siam Cement Public Co.	Conglomerates	Yes	Accountant	Deloitte
Materials	Sibanye Gold Limited	Mining	Yes	Accountant	KPMG
Materials	Sika Finanz AG Br	Chemicals	No	0	0
Materials	Sinopec Shanghai Petrochemical Co Ltd H Shares	Energy	Yes	Small consultancy/ boutique firm	Other
Materials	Symrise AG	Chemicals	Yes	Engineering firm	Other
Materials	Toray Industries Inc	Textiles and Apparel	Yes	Accountant	Lloyds
Materials	Umicore	Metals Products	Yes	Accountant	PricewaterhouseCoopers
Transportation	Aena SA	Aviation	Yes	Small consultancy/ boutique firm	AENOR
Transportation	Air China Ltd H Shares	Aviation	No	0	0
Transportation	Airports of Thailand PCL	Aviation	No	0	0
Transportation	Alaska Air Group Inc	Aviation	No	0	0
Transportation	American Airlines Group Inc.	Aviation	No	0	0
Transportation	Asciano Ltd	Logistics	Yes	Accountant	KPMG
Transportation	Asiana Airlines	Aviation	Yes	Small consultancy/ boutique firm	Other
Transportation	Atlantia SpA	Other	Yes	Accountant	Deloitte
Transportation	Aurizon Holdings Limited	Railroad	Yes	Accountant	PricewaterhouseCoopers
Transportation	China Airlines Co	Aviation	Yes	Engineering firm	SGS
Transportation	China Merchants Holdings (International) Co. Ltd.	Financial Services	Yes	Engineering firm	Bureau Veritas
Transportation	COSCO Pacific Ltd.	Logistics	No	0	0
Transportation	CSX Corporation	Railroad	Yes	Small consultancy/ boutique firm	Other
Transportation	Delta Air Lines	Aviation	No	0	0
Transportation	East Japan Railway Co	Railroad	Yes	Accountant	KPMG
Transportation	Fraport AG	Aviation	Yes	Small consultancy/ boutique firm	Other
Transportation	Grupo Aeromexico SAB de CV	Aviation	No	0	0
Transportation	Hyundai Glovis Co Ltd	Logistics	Yes	Engineering firm	DNV
Transportation	Korean Air Lines Co	Aviation	Yes	Small consultancy/ boutique firm	Other
Transportation	LATAM Airlines Group S.A.	Aviation	Yes	Accountant	Deloitte
Transportation	Mitsui OSK Lines Ltd	Logistics	No	0	0
Transportation	MTR Corporation Ltd.	Railroad	No	0	0
Transportation	PostNL NV	Logistics	Yes	Accountant	PricewaterhouseCoopers
Transportation	Royal Mail plc	Logistics	Yes	Accountant	Ernst & Young
Transportation	Sinotrans Ltd. - H Shares	Logistics	No	0	0
Transportation	Sydney Airport	Aviation	No	0	0

Annex 11: Summary of NRI MEL engagements and achievements with RATE partners
- 3 learning events (workshops) for partners – 2015; 2016; 2017 at which evidence on outcomes and impacts and approaches to monitoring and evaluation were discussed (see information below)
- Review of logical frameworks (for some partners this meant a very light touch review, for others logframes were constructed from scratch). This process generated understanding amongst the partners on how to measure outcomes and impacts.
- Regular interactions with the RATE partners (largely by skype, but also some face-to-face sessions) at which MEL approaches have been discussed.
In addition, please see Table 1 below.

Table 1 Summary of achievements – MEL engagement with RATE partners
Partners	Progress achieved
The ISEAL Alliance (ISEAL)	ISEAL already has strong MEL systems and there is significant external work assessing impact of members. The organisational summary explored the overall theory of change evidence and included a review of two recent systematic reviews of available evidence, including the MEL team’s critique of the these. All of this informs ISEAL as it reviews its work on demonstrating and improving impact.
Global Reporting Initiative (GRI)	The MEL team has worked with GRI to analyse coverage (in 4 sectors) which shed light on targeting and which could be used as a partial baseline. / GRI has encountered some challenges in establishing its MEL capability and system, but it has completed a study on poverty impact. The MEL team have highlighted how the latter study is useful (in mapping out how GRI may have a poverty impact), but also noted its limits (with respect to generating evidence on casual linkages. / NRI has consistently encouraged GRI to strengthen its M&E system, drafting a theory of change to help GRI articulate how it anticipates having an impact. GRI provided comments on a draft TOC, but it is anticipated that GRI would develop its own theory of change and has employed consultants to do this. / NRI has also discussed with GRI the importance for GRI of tracking change over time and producing more robust evidence. GRI have said that this will take them some time as they need to start with companies who have not yet adopted the GRI standard and then they will track behaviour change over a period of time (e.g. 10 to 20 years). Some case studies are already underway, but NRI has commented on the TOR which indicates that these are not designed to generate robust evidence.
UN Global Compact (UNGC)	NRI has encouraged UNGC to develop its M&E system. The current ‘impact’ study is limited in nature. The RATE MEL team requested that DFID use its influence in the donor group to encourage UNGC to develop a theory of change and robust M&E system. DFID did lever its influence in this way and UNGC are now developing a theory of change and an M&E system, including indicators. NRI requested/offered to comment, but nothing has been shared so far.
Ethical Trading Initiative (ETI)	NRI has encouraged the ETI to develop a more robust MEL system and provided advice on the indicators in the logical framework. / ETI contracted consultants to work on improving the MEL system / The MTE review highlighted two M&E priorities for the remainder of the programme. The first is to provide robust evidence of how, and to what extent, company behaviour with a demonstrable impact on workers’ rights has changed as a result of ETI. The second M&E priority is to commission a comprehensive and independent impact assessment of ETI similar to the one last carried out in 2003. This assessment will also contribute to the development of ETI’s new post-2020 strategy.
B-Lab	The RATE MEL team suggested to B Lab a collaboration in terms of conducting a study on the East Africa B Lab hub. However, B Lab responded that they did not have the resources to collaborate on such a study, although they are looking for funding from donors in order to do this. B Lab offered various other sources of data which were analysed by the MEL team in the organisational analyses, which included comments upon the quality of the information available.
Shift	Provided advice on the logical framework. / The RATE MEL team have emphasised that identifying the impact of the project on human rights practices that are most directly connected with poor and vulnerable people should be the M&E priority.
ShareAction	Provided advice on the logical framework. / MTE review emphasised the importance of Shareaction being able to demonstrate a causal relationship to positive impact for poor people in a reasonable timeframe.
Fairtrade	Provided advice on the logical framework.
UN Foundation - World Benchmarking Alliance	Initial discussions held and the partner participated in the learning event on evidence and MTE emerging findings.
Humanity United	Initial discussions held and the partner participated in the learning event on evidence and MTE emerging findings.