Annual Review

Title: Neglected Tropical Diseases Implementation Research Programme (COUNTDOWN)
Programme Value £ (full life): £8,014,091		Review Date: June 2018
Programme Code: 203089	Start Date: 1 November 2014	End Date: / 31 October 2019

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	A	A	A+	A+
Risk Rating	Medium	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4111293.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/28320935.odt

A. Summary and Overview

Description of programme

DFID’s Research and Evidence Department (RED) commissioned a programme of Implementation Research that will directly contribute to the achievement of the 2020 Neglected Tropical Diseases (NTDs) elimination and eradication goals through providing a greater understanding of how best to cost-effectively and sustainably deliver integrated NTD Control Programmes at scale. This is linked to DFID’s wider work on tackling NTDs, including £245 million to support the control of NTDs over the period 2011-15.

The main pillar of Integrated NTD Control Initiatives is delivery of Mass Drug Administration (MDA) programmes to treat and control up to 7 NTDs (schistosomiasis, lymphatic filariasis, onchocerciasis, trachoma and three soil transmitted helminths) simultaneously.

Liverpool School of Tropical Medicine (LSTM) was initially awarded a contract of £7,012,587, which was then increased to £8,014,091 for delivering this research programme. The increased figure has allowed the programme to upscale its work in Nigeria, a country with one of the greatest NTD burdens globally.

Summary supporting narrative for the overall score in this review

COUNTDOWN has continued to perform well and has scored an A+ across all of its outputs. Research is well underway in all four countries (Ghana, Cameroon, Nigeria and Liberia) and is aligned with the implementation landscape for scale up and acceleration towards WHO 2020 targets and DFID investments in health. There is good evidence of stakeholder participation to achieve research uptake and policy influencing, with emerging findings disseminated effectively by country teams. Networks in each country have also expanded into other sectors, such as education and WASH, which is critical in the drive to address NTDs.

Recommendations for the year ahead

1. COUNTDOWN to provide DFID with location details of all implementation sites to allow DFID to monitor the security situation and provide advice as needed – by August 2018.
2. COUNTDOWN to develop a case study on the integration of mental health and healthcare for NTDs – by May 2019.
3. COUNTDOWN to diversify its geographic focus of policy briefs – by May 2019.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	COUNTDOWN generates research evidence to respond to priority information needs of NTD policy makers and programme managers
Output number per LF		1	Output Score	A+
Impact weighting (%):		60%	Impact weighting % revised since last AR?	Y (new output)

Indicator(s)	Milestone(s) for this review	Progress
1.1 NTD implementation research gaps identified	Implementation research conducted to address 5 knowledge gaps for NTD policy makers and programmes	Met expectations: 6 knowledge gaps addressed
1.2 Number of approved research projects	i) Design: 4; ii) Implementation: 8; iii) Analysis/Dissemination: 2; iv) Completed: 1; Total: 15	Met expectations: 15 approved projects
1.3. Open access research publications: / - Peer reviewed journal articles / - lead or co-author with home institution in LMIC / - female lead/co-author / - female lead/co-author with home institution in LMIC	16 peer reviewed articles cumulatively	Met expectations: 17 peer reviewed articles in total, 6 from the review period (4 of these with a female lead author, 2 of whom are from a home institution in an LMIC)
1.4. Open access knowledge products (presentations, blogs, briefs) produced and disseminated	150 knowledge products, including 5 policy briefs, developed and geographic dissemination mapped, including through website download and page views	Moderately exceeded expectations: 179 knowledge products, 5 policy briefs, 108,041 unique page views of website/blog

Provide supporting narrative for the score
COUNTDOWN has moderately exceeded expectations for Output 1. Six out of an expected 5 knowledge gaps in NTD programming were identified for implementation research, to influence the work of NTD policymakers and programmes. These were: (i) timing of MDA distribution and how this affects attendance by men and women; (ii) community-based treatments in Ghana and Cameroon on schistosomiasis and how this reduces infections and morbidity; (iii) the extent to which MDA delivery and awareness can improve through both awareness programmes for community members and effective training for healthcare providers; (iv) how co-implementation of MDA programmes by communities and health providers supports community drug distributor motivation; (v) how precision mapping of disease distribution can provide disease “hot spots” in endemic communities so that people migrating are covered; and finally (vi) the cost-effectiveness of the MDA approach.

COUNTDOWN reached the target, 15 research projects at various stages. One of these, on soil transmitted helminths and schistosomiasis monitoring in Ghana, is completed. The 17 peer reviewed articles are also open access, and 6 are from the review period. COUNTDOWN exceeded expectations for open access knowledge products overall, with 179 available against a target of 150. This includes publications, book chapters, blogs, presentations and posters, articles and policy briefs. This year COUNTDOWN published their first policy briefs, all five of which focus on Nigeria.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lessons: Given that NTDs are shaped by the social determinants of health, there is a need to build multi-sectoral teams and partnerships. COUNTDOWN is well placed to do this, engaging with multiple Ministries.

Recommendation: COUNTDOWN to diversify its geographical focus of policy briefs – by May 2019.

Output Title	COUNTDOWN supports incorporation of evidence to improve policies and operational plans and practices for scale-up of NTD control
Output number per LF		2	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	Y (new output)

Indicator(s)	Milestone(s) for this review	Progress
2.1. Involvement of key stakeholders at national, state and district level in developing linkages, partnerships, across disciplines, sectors and countries to enhance evidence-based NTD policymaking and programming	COUNTDOWN expands stakeholder network into 2 COUNTDOWN countries to advocate and manage multi-disciplinary research at national, state and district levels	Moderately exceeded expectations: completed in all 4 COUNTDOWN countries
2.2. COUNTDOWN undertakes research uptake and dissemination activities effectively	5 effective activities which led to research uptake/ dissemination	Met expectations: 5 new activities

Briefly describe the output and provide supporting narrative for the score

COUNTDOWN moderately exceeded expectations for Output 2. COUNTDOWN works collaboratively with policymakers and NTD programmes, to ensure that evidence generated by the programme is used. Multidisciplinary networks have been formed across all four countries, exceeding the target of 2. In Cameroon, for example, NTD coordinators from 10 regions were brought together to discuss results from COUNTDOWN research, with members of civil society, to plan for moving from control to elimination in the control of schistosomiasis. In Ghana, district and regional health directors have engaged with the COUNTDOWN research teams on their work. Engaging a broad range of stakeholders at all stages of the research cycle, from planning and implementation to revision and dissemination, has enabled COUNTDOWN research to remain relevant to policy makers’ needs and utilise the broad networks that are needed to address these complex diseases.

Research dissemination overall has been positive. COUNTDOWN has worked with the WHO NTD Working Group on Monitoring and Evaluation to modify their toolkit on preventive chemotherapy for NTDs. COUNTDOWN co-supported the launch of the Liberian Integrated Case Management Plan during the review period. National steering committee meetings across the four countries have included dissemination of COUNTDOWN’s findings to date. COUNTDOWN has influenced and encouraged awareness within Cameroon on female genital schistosomiasis in particular. This has directly helped to expand national interest in the disease and enable buy-in of outside donor support and in-country infrastructure development, which led to the refurbishment of a gynaecological ward.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons Learnt: Engaging journalists through getting them to understand field realities and experiences of community drug distributors is an effective mechanism for raising awareness on NTDs publically.

Recommendations: None

Output Title	COUNTDOWN strengthens capacity for evidence-based decision making and planning through learning by doing amongst its staff, associated partners and country based research communities
Output number per LF		3	Output Score	A+
Impact weighting (%):		15%	Impact weighting % revised since last AR?	Y (new output)

Indicator(s)	Milestone(s) for this review	Progress
3.1. COUNTDOWN stakeholders engaged in implementation research training	Institutions in at least 3 COUNTDOWN countries demonstrate the impact of improved research capacity through new knowledge, skills, networks, collaborations, funding	Moderately exceeded expectations: Met in all 4 COUNTDOWN countries

Provide supporting narrative for the score

COUNTDOWN moderately exceeded expectations for Output 3. All 4 countries have benefited from capacity building in research skills from the programme. LSTM delivered paper writing workshops to its partners. Training has also been delivered on data collection and analysis, lab-based training and the training of healthcare workers. In Ghana, the team worked with training institutions and alliances of doctors and healthcare workers to ensure that female genital schistosomiasis stays on the agenda. In Nigeria policymakers have been trained on how to use evidence. COUNTDOWN’s capacity building efforts of southern researchers led to several having their abstracts accepted for the highly competitive Health Systems Global conference, to take place in Liverpool in 2018.

Capacity building efforts overall have resulted in greater collaboration. For example, the Liberian team used the COUNTDOWN research and support to collaborate with the Ministry of Health National Health Promotion team to develop a draft communications strategy for the NTD programme. The strategy aligns with and informs Liberia’s National Health Promotion Strategic Plan.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons: Capacity building of researchers should not be limited to preparation for field research but should be an evolving process across the lifetime of the programme for which appropriate resources need to be invested.

Recommendations: None

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The COUNTDOWN theory of change was not changed in the review period.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)
The programme is on track to meet its outcomes. It continues to produce evidence on the obstacles to NTD services and the populations most affected by inequitable coverage. Decision-makers are engaged throughout the process. COUNTDOWN is also generating evidence on how health workers often lack capacity for effectively diagnosing female genital schistosomiasis, thereby not referring women to appropriate services. Research has shown that young women who seek care for female genital schistosomiasis are chastised by health workers who think they have a sexually transmitted infection.

Important to COUNTDOWN’s work is research aimed at improving the cost-effectiveness and affordability of NTD programming. Household surveys are assessing the economic burden of NTDs. The programme is also testing innovations designed to achieve greater impact than traditional NTD interventions and areas that need improvement. This includes community drug distributor training, supervision and incentives; drug management; and the effectiveness of information, education and communication strategies and materials.

COUNTDOWN is identifying aspects of NTD programmes that need to be adapted to improve intervention acceptability. This includes adherence to praziquantel due to fears of side effects, for example, which requires greater investment in awareness raising.

Explain major changes to the logframe in the past year (1/2 page)
The logframe has been adapted in the review period to align with the Health Research team’s Results Framework. This includes a revision of milestones but has not affected the essence of the programme, which still aligns with the above theory of change. Weightings have also been amended accordingly.

Describe any planned changes to the logframe as a result of this review (1/2 page)
The current logframe was updated in the last 6 months, no further changes are planned, as a result of this review.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

COUNTDOWN continues to represent good value for money and has been adaptive through its research on NTDs. The programme has developed expertise in building evidence to address priority issues for NTD control programmes, that change due to broader changes in the landscape. It remains focused on identifying the most effective strategies for scale up that include reaching the hardest to reach and identifying factors that influence acceptance, accessibility and affordability amongst different populations. Financial management has been robust.

Economy: In the past year COUNTDOWN has continued to secure cost-savings when travelling and procuring consumables to conduct and support research implementation and dissemination. These costs are only approved if the COUNTDOWN Programme Management Team believe that they are justified and in line with existing budget allocations. Travel is avoided if alternative arrangements can be made using technology. Quotes for consumables are sought to ensure cost-effectiveness. Free conference attendance is mostly attained through the LSTM NTD network of memberships.

Efficiency: The direct costs of multi-disciplinary activities are planned, budgeted and charged appropriately on agreements between partners. Teams working on different research activities share resources. Planning for the utilisation of programme equipment is managed effectively - COUNTDOWN has been able to achieve more output for less cost by working this way when sharing equipment, vehicles, fuel costs and reducing the number of field staff across the teams. A booking system for each field visit is monitored to ensure costs and usage remain within acceptable limits. COUNTDOWN has secured open access waivers which saves publication costs.

Effectiveness: COUNTDOWN’s implementation research portfolio is exploring innovations designed to achieve greater impact than traditional NTD interventions. Having selected health systems challenges identified by key stakeholders, COUNTDOWN continues to test improvements needed for the delivery of NTD programmes while engaging stakeholders at all levels via implementation research uptake plans. COUNTDOWN research findings have been effectively shared at national, district and community levels to influence uptake. A further element of COUNTDOWN’s work is to strengthen capacity for quality research and synthesis of findings.

Cost Effectiveness/ Equity: COUNTDOWN is examining NTD intervention effectiveness from a cost perspective in various settings. Household surveys are used to assess the cost of both mass drug administration. Data collection and analysis is ongoing with plans for dissemination of these findings planned in 2018 and 2019. COUNTDOWN is working to identify and deliver alternative strategies to improve equity of NTD programmes, prioritising those who are left behind. The programme addresses how social determinants of health (such as age, gender, sexuality and income) are central to NTD health service delivery as well as how collaboration and participation can improve outcomes of accessibility to treatment and social wellbeing.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme is delivering good quality research in an area that is a policy priority for DFID. The work complements other NTD programmes, currently supported by DFID, and the results will inform future research themes. The work is innovative and is having a significant influence in the direction of travel within the NTD research community, including at national, district and community level.

COUNTDOWN has recently submitted a 2 year extension proposal which is intended to enhance the work that is being conducted, particularly in Nigeria (which began later than the other sites). This is supported by the Research and Evidence Division (RED) and will be submitted shortly though Commercial and Procurement Department (PCD) for further scrutiny on the contractual terms and the financial aspects.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

COUNTDOWN’s risk rating continues to be Major. This is largely due to the security situation within its 4 operating countries. In Cameroon there is unrest in the south west region so work needs to be carefully planned to avoid disruption and to ensure that staff working in affected sites are not placed at risk. Northern Nigeria has some security concerns which are closely monitored by partner, Sightsavers, in-country. The main mitigation measure for security risks is ongoing monitoring. Another risk is ineffective financial systems amongst partners. LSTM has measures in place to ensure due diligence checks are undertaken, as well as spot checks. Financial reports undergo thorough levels of scrutiny. In turn, DFID further scrutinises financial reports that are submitted by the consortium.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)

COUNTDOWN has continued to demonstrate good financial acumen. Forecasting has been regularly updated to ensure accuracy and invoices are submitted within acceptable timescales along with financial narrative reports that provide details of how the money is being spent and the impact it is having. In the period April 2017 to March 2018 COUNTDOWN hit their spend target and in addition (with the agreement of DFID), brought funds forward from 2018/19 to begin some Liberian activities early. COUNTDOWN has DFID approval to advance payments to some country partners; these advances are managed effectively, based on need and maintained at an appropriate level. The most recent Audit Report on Liverpool School of Tropical Medicine (LSTM) covering the period to July 2017 is unqualified and provides assurance that systems and procedures continue to work effectively.

COUNTDOWN continues to respond quickly to requests for ad-hoc information often required urgently to respond to public enquiries/parliamentary questions. The requirement for ad-hoc information has grown over the last few years and COUNTDOWN has been an excellent partner in providing succinct and relevant returns.

During 2017/18 the DFID health research team introduced a new results framework which will be used to enhance the logframe and to make output targets more meaningful. COUNTDOWN has now aligned their activities to the framework and the final version has been agreed. The team appreciate that this has taken up significant time to conclude. COUNTDOWN has indicated that the exercise provided a welcome opportunity to refine their priorities.

The COUNTDOWN assets register is kept up to date and submitted to DFID annually as part of the Annual Report documentation. No spot checks have taken place to date, but there is confidence that the register is managed appropriately and is accessible for inspection as required.

DFID and LSTM have built a good working relationship which helps resolve any issues quickly. The Senior Responsible Owner (SRO) attended the COUNTDOWN annual meeting in 2017 and, together with other DFID programme team members, has continued to have regular dialogue on a wide range of topics.

Date of last narrative financial report(s)	3 May 2018
Date of last audited annual statement (s)	5 November 2017

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
The annual review was carried out by members of the Health Research Team in RED. Members of the review team had ongoing dialogue with the COUNTDOWN team throughout the year. This included a visit by the Senior Responsible Officer to LSTM in March 2018, to meet with consortium partners and the senior programme team. In June 2018, at the time of the review, COUNTDOWN visited DFID to present to Health Advisors at a ‘Lunch and Learn’ event and also met with the Health Research Team. Extensive discussions also took place with COUNTDOWN, on their request, to extend the programme by two years.

Evidence (1/2 page)
COUNTDOWN continued to generate high quality evidence in the review period. For example, there have been several studies to assess the status of lymphatic filariasis disease elimination and to understand the adherence to interventions, including MDA and insecticide treated beds. This work is crucial to better understand potential gaps and pitfalls in current NTD programmes. Another example is the COUNTDOWN team in Cameroon advancing the concept of precision mapping for schistosomiasis, by demonstrating its significance and impact for equitable scale-up of preventive chemotherapy. Community drug distributors and their motivation levels has been a key focus, with a greater understanding on how community fatigue makes their work challenging. As they are a critical vehicle for mass drug administration, understanding how to improve their engagement is highly important.

Evidence collected by the programme is age and gender disaggregated, with the programme sharing outputs related to gender and equity with the wider NTD sector, aligning with the Leave No-one Behind agenda. No evaluation is planned for the programme.

Learning (1/2 page)
COUNTDOWN used quarterly reports, reflection meetings with partners, case studies and an annual meeting to share lessons, new evidence and know how. LSTM coordinates this amongst partners. Key lessons throughout the year have been noted under each output. More broadly the consortium recognises that policy influencing takes time – evidence generated by COUNTDOWN is just one component in a complex set of factors influencing decision making.

Future learning will include generating evidence on how NTD programming needs to be adapted for different geographical contexts, including urban/rural areas. Equity issues will be further pursued, as well as the need to address, not only elimination of NTDs, but also responses to morbidity. Mental health impacts will also be explored, as case studies with patients in Liberia have shown that it may be important to integrate psychosocial support into health care, which COUNTDOWN will bring stakeholders together to explore.

Progress on recommendations from previous reviews (1/2 page)
COUNTDOWN have developed case studies on gender and equity issues for three countries and are still analysing data for the final case study, for Liberia.

COUNTDOWN now report on strategies to disseminate findings to populations at risk of NTDs in indicator 2 of the logframe, where they have moderately exceeded expectations.

The COUNTDOWN forecast variance was 13%, not 5% as recommended. This was to enable advance payments for the next financial period and for some activities to be brought forward, all with DFID agreement.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Neglected Tropical Diseases Implementation Research Programme (COUNTDOWN)
Programme Value: £8,014,091		Review Date: June 2017
Programme Code: 203089	Start Date: / 1 November 2014	End Date: 31 October 2019

Summary of Programme Performance
Year	2015	2016	2017	2018	2019	2020
Programme Score	A	A	A+
Risk Rating	Medium	Major	Major

Summary of progress and lessons learnt since last review

COUNTDOWN is a research consortium dedicated to investigating cost-effective, scale-up and sustainable solutions, necessary to control and eliminate the seven most common Neglected Tropical Diseases by 2020. It is operational in 4 countries – Ghana, Cameroon, Liberia and Nigeria. Operations in Nigeria commenced in early 2017.

COUNTDOWN has moderately exceeded expectations during the review period. It continues to engage well with national governments, resulting in effective policy influencing across multiple sectors. Collaborative efforts include with the Government of Ghana to improve access and timings of interventions for Lymphatic Filarisis, as well as work on female genital schistosomiasis. WHO has cited COUNTDOWN research in its fourth NTD report, ‘Integrating neglected tropical diseases in global health and development’ demonstrating the increasing influence of COUNTDOWN’s work in global NTD policy and control.

Eleven peer-reviewed articles have been published by COUNTDOWN in the review period, including in The Lancet, PLOS Neglected Tropical Diseases, Infectious Diseases of Poverty, International Journal of Parasitology and Parasitology Open.

COUNTDOWN has demonstrated a good focus on gender and equity. It is important that key learning on gender and equity in NTD policy and control programmes continues to be drawn out throughout the course of the programme.

Summary of recommendations for the next year

1. Research to draw out learning on gender and equity issues through a case study per country – by May 2018
2. COUNTDOWN to report on effective strategies for disseminating its findings to populations at risk of NTDs (as per the request from Ministries of Health) in the next annual report – by May 2018.
3. COUNTDOWN should improve forecasting over the next year and aim to have a variance (between budget and spend) in the region of 5%.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Neglected Tropical Diseases Implementation Research Programme (COUNTDOWN)
Programme Value: £8,014,091		Review Date: 1 July 2016
Programme Code: 203089	Start Date: / 1 November 2014	End Date: 31 October 2019

Summary of Programme Performance
Year	2015	2016
Programme Score	A	A
Risk Rating	Medium	Major

Summary of progress and lessons learnt since last review

COUNTDOWN is a research consortium dedicated to investigating cost-effective, scale-up and sustainable solutions, necessary to control and eliminate the seven most common Neglected Tropical Diseases by 2020. COUNTDOWN has made good progress in the past year, with all milestones met or partially exceeded. It has established its research programme in Ghana and Cameroon, and following the approval to expand the research in Nigeria, and re-establish activities in Liberia, progress has been also been made establishing research in these countries as well.

There has been positive engagement with key policy makers in the targeted countries, including the Minister of Health in Cameroon involved in the in-country launch and an opportunity to engage with the World Health Organisation (WHO) African Regional Program Review Group for Neglected Tropical Diseases (NTDs) at COUNTDOWN’s partner meeting in Accra.

Publications have included four submissions of articles to peer reviewed journals, including Lancet Infectious Diseases and International Health, and COUNTDOWN staff co-authoring a book chapter on the Social and Economic Impact of Neglected Tropical Diseases in Sub-Saharan Africa.

As the programmes are developed, COUNTDOWN should remain focused on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD control programmes at scale. DFID has also spoken to COUNTDOWN regarding tightening up its financial accounting, with accurate budgeting, and only claiming for expenditure that has already been spent.

Summary of recommendations for the next year
1. COUNTDOWN should ensure that its submissions to peer-reviewed journals and knowledge products; presentations/ blogs/ briefs are as operationally relevant as possible, and be targeted to key policy makers in affected countries and implementing organisations (ACTION: COUNTDOWN – ongoing)
2. COUNTDOWN should increase its collaboration with the range of DFID funded NTD programmes involving mass drug administration, both at a global and country level. DFID will ensure that COUNTDOWN is involved in NTD partner meetings whenever these take place. (ACTION: COUNTDOWN & DFID – immediate and ongoing)
3. COUNTDOWN should remain focused on its core priority of building evidence on how best to cost-effectively and sustainably deliver integrated NTD control programmes at scale. (ACTION: COUNTDOWN – immediate and ongoing)
4. COUNTDOWN should reconsider its proposed work on products (particularly diagnostics), following discussion with DFID, and ensure this work is complementary to the work of the DFID funded Product Development Partnerships in this area. (ACTION: COUNTDOWN – November 2016)
5. DFID has discussed with COUNTDOWN regarding improving the financial management, with accurate budgeting, and only claiming for expenditure that has already been spent. (COUNTDOWN – already actioned, following meeting with DFID)
Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Neglected Tropical Diseases Implementation Research Programme.
Programme Value: £7,012,587 (currently under review)		Review Date: 24 June 2015
Programme Code: 203089	Start Date: 1 November 2014	End Date: 31 October 2019

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating	N/A

Summary of progress and lessons learnt since last review

At the time of the last review the programme had not yet begun and the review was “light touch” and based predominantly on the procurement cycle/ process. This year the review will not be able to look at the programme in depth as the inception phase started on 1 October and has been running for approximately 6 months.

COUNTDOWN has used the initial period of the contract to interact with partners and to agree a workplan for rolling out the research. The Ebola outbreak in Liberia (one of the anticipated partner countries) has resulted in a change to the original focus and work in Liberia has been put on hold for the time being, with the potential for a minimal programme of research to take at a later stage (much smaller than originally planned). Initiation of any activities in Liberia would be subject to approval by DFID, and based on DFID guidance on working in Liberia.

As an alternative to Liberia, COUNTDOWN was asked by DFID to consider scaling-up the implementation research in Nigeria which has one of the highest burdens of Neglected Tropical Diseases(NTDs) in the world. COUNTDOWN produced an informal concept note, proposing the potential focus on the research in Nigeria. Following feedback from DFID, COUNTDOWN has developed a proposal for additional funding with a revised workplan, which is currently under consideration.