ADDENDUM TO BUSINESS CASE, INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Health Partnership Scheme (HPS)
Country or region targeted	Africa and Asia
Type of cost extension (if applicable)	Bridge funding
Original project budget	£30.2m
Original project start and end dates	July 2011 to June 2017
Cost extension value (if applicable)	Up to £2.1m
New project end date (if applicable)	28 February 2019
Business Case Quest Document No.	2841615

INFORMATION
What is the project’s purpose?
The purpose of the Health Partnership Scheme (HPS) is to contribute to strengthening developing country health systems, with an emphasis on the performance of the health workforce. This is done through supporting partnerships between UK health institutions (e.g. NHS Trusts, universities, Royal Colleges and professional associations) and those in developing countries, building health worker capacity and sharing skills. The HPS provides grant funding, with accompanying advice and sharing of expertise, for these partnerships. / This also benefits the UK health sector: the recent HPS evaluation found that partnerships contribute to improved health professional competencies, motivation, health service innovations and global influence.
What is the objective of the cost extension or other changes?
Bridge funding is required to sustain delivery of results during a period of transition. Options for potential future support are being considered and will be put to Ministers for decision. The existing HPS is due to end in June 2017. Bridge funding to February 2019 will enable ongoing support of UK health partnerships. / There is a long and rich history of partnerships between UK health institutions and their counterparts in low income countries, and of UK government support. DFID has funded the current Health Partnerships Scheme since 2011 (and prior to that funded a similar health ‘Links’ programme). UK and global experience demonstrate that partnerships and volunteering are effective to support DFID’s overall health goals and work to strengthen health systems, and health workers’ capacity in particular – with benefits also to the UK health system. The recent (2016) independent evaluation of the HPS showed that the scheme has successfully strengthened partnerships and contributed to building human resources capacity at country level.[1] / An immediate end to current UK support risks losing both momentum and valuable knowledge and skills. Drawing on recommendations from the evaluation, the bridge funding will mitigate these risks, and ensure continuity for the most effective health partnerships. / This bridge funding will contribute to implementation of the 2015 UK Aid Strategy, particularly strategic objectives 2 (Strengthening resilience and response to crises) and 4 (Tackling extreme poverty and helping the world’s most vulnerable). It will help enable UK health institutions to support the development of health systems overseas as part of ‘Global Britain’. Within DFID’s Human Development Department’s operational plan objectives, the programme contributes to improving access to basic services.
What is the additional and total support the UK will provide?
Up to £2.1 million additional (June 2017 to February 2019); making a total of up to £32.3m (2011-2019).
What are the expected results?
In addition to sustaining results, bridge funding will build on successes to date and main learnings from the evaluation to further improve the development effectiveness of partnerships work. / The expected outcome is improved health worker and health service performance for poor and vulnerable populations in targeted areas. This would be accomplished through the following outputs: / At least 20-25 strong and strategically targeted health partnerships supported (through grant awards) in selected low income countries - addressing health systems constraints and fostering innovative approaches. The evaluation highlighted that partnerships focused on a few countries and coordinated with other health work are likely to be more effective at addressing systemic constraints, whereas smaller partnerships offer scope for innovation and approaches with potential for scale up. All grants will ensure a robust monitoring and evaluation component to continue to build the evidence base of health partnership work. / Preliminary expected additional results for the bridging period include[2]: / 7,000 training course places and other educational opportunities / 95% of tested trainees showing improved skills or performance immediately after training / 12 developing country institutions have improved medical equipment, ICT or health information management systems.
What is the approach to implementation?
The bridge funding will be provided through an Accountable Grant with the Tropical Health and Education Trust (THET), the UK NGO that manages the current HPS. It will provide support for further health partnership grants which will aim to embed and replicate successes. It will also generate further learning on what makes partnerships most effective, and the best ways to support such partnerships in the future. / Building on the findings of the evaluation, grants will be provided to: / a selection of large health partnerships in a few priority countries, to sustain the benefits to the health institutions and embed good practice in national systems; / a selection of smaller health partnerships which have proved successful in strengthening the performance of health workers for specific tasks and which offer models with the potential to scale up (e.g. in developing whole-facility approaches to quality improvement, leadership and management, and Health Technology Management). / This proposed mix of grants will enable partnerships from the current HPS to bid for further support, giving continuity, and will also allow flexibility to support partnerships that have not been previously supported by the HPS. Building on the evaluation findings, focused support in a few countries will foster even greater impact through stronger alignment with national strategies and coordination with other health partners – with the aim that partnerships in a country deliver more than the sum of their parts. / THET will agree final criteria and process for award of grants with DFID, following consultation with the NHS International Group and DFID central and country office teams. This will include agreement of 4-5 priority countries (based on need, existing partnerships, and THET and partners’ capacity), plus other selection criteria such as track record, potential for scalability and sustainability, likely impact on health facilities and services, and likely ability to influence the wider health system. THET will identify and agree with DFID a transparent granting process that both maximises funding opportunities for the best performing partnerships and allows for innovative approaches (e.g. through earmarking an allocation to previous grant holders and/or running a two-stage grant process, one for existing grant holders and one for new grantees). / Gender Equity and Gender Equality Act compliance / Gender is a key factor to consider in health workforce interventions. Women make up 67% of health and social sector employment but gender biases persist within the health workforce. For example, health systems rely heavily on unpaid and informal work that disproportionately fall on women and girls. Girls and women also have unique needs and barriers when accessing healthcare which strong health systems and workforces must cater for. In accordance with the 2014 International Development (Gender Equality) Act, this project will ensure any institutional partnerships supported and established under its remit consider impact on gender equality, and how the issues identified above can be addressed. They will also include disaggregation of data by gender and the inclusion of gender-based targets in results measurement. / In addition, THET are currently finalising a gender analysis study which will provide guidance for partnerships on gender equality and social inclusion requirements and how to integrate these into project design (including for the selection of health institutions, health partnership management and planning, volunteer recruitment and management). / Disability compliance / In line with new guidance, the programme will also consider how partnerships can ensure that people with disabilities are being reached and benefit from the programme. Following a recommendation from the evaluation, THET is currently conducting a study on populations served by a sample of health partnerships (rural / urban, gender, ethnicity, disability and sexual orientation) and this will help to inform how future health partnerships can best support disadvantaged populations. / VFM and budget / The independent evaluation of the HPS found that the volunteering and partnership approaches used by the HPS represent good value for money. The use of expert volunteers enables provision of specialist expertise to developing country partners at a relatively low cost. Volunteers also demonstrated commitment to delivering high quality work and innovation. All the projects reviewed demonstrated a high level of awareness of and commitment to delivering economy, efficiency and effectiveness as well as sustainability. / Systematic measurement of Value for Money will be integrated into the new activities from the outset and will be underpinned by an Economy, Efficiency, and Effectiveness approach. The following table lists proposed VFM indicators for the extension period. / VfM E Draft indicator suggestions Notes / Economy Cost per consultancy Unit cost benchmarked against type, skill set, country and sector average rates / Cost per staff per month Unit costs benchmarked against the sector / Cost per monitoring visit Unit costs benchmarked for each country context and a set number of people / Cost per workshop Unit costs benchmarked for each country context and size of workshop / Cost per training per person Unit costs benchmarked for each country context and size of training / Value of UK volunteers’ contributions in kind, as a percentage of grant funding to health partnerships *= Volunteer days x daily rate by cadre; Note: Does not include the value of other contributions such as institutional support; May create incentive for using highly paid health professionals as volunteers. / Efficiency Percentage of grants completed on time, and amount spent against budget forecast by grant holders / Percentage of training participants who show improved knowledge or capability immediately after training / Percentage of policies, protocols and curricula approved and signed off, as a percentage of those to which health partnerships contributed / Number of participating institutions using and maintaining improved equipment, ICT or health information management systems, 12 months after delivery, as a percentage of those which improved them / Percentage of training participants who successfully completed training as trainer of trainers Trainer of trainers is considered a VfM measure as it helps ensure a standardised training approach / Effectiveness Percentage of those health workers with improved capability immediately after training who show improved performance 12 months after training Reflects both the local support for health workers to apply their new skills, and the appropriateness of the training for that level of local support. / Percentage of policies, protocols and curricula implemented, as a percentage of those approved and signed off Number of policies, protocols and curricula implemented, a figure not otherwise recorded in the logframe. / Percentage of UK volunteers who report or demonstrate improved clinical and leadership skills Number of UK volunteers, a figure not otherwise recorded in the logframe. / Equity % female training participants and/or participants from other marginalised groups / % of services benefitting the poorest and marginalised / % of local consultancies used to deliver activities / % distribution of resources between priority countries / THET’s budget for the bridging activities is in the table below. DFID has worked closely with THET to ensure VFM, e.g. minimising levels of staffing and other overheads to deliver expected results. Up to £2.1m is required to support at least 20/25 strong partnerships. The larger grants are expected to be up to £250,000 each and the smaller grants up to £60,000 each. / Staff inputs and costs are judged to be reasonable and to offer VFM on the following grounds: / THET will provide more intensive support to partnerships during the bridge funding, especially the new ‘larger’ grants. This responds to the evaluation recommendations that partnerships can have greatest impact through stronger alignment with national strategies and priorities and coordination with work of other health partners, and to ensure that lessons are learned and good practices are shared. / The implementation period for grants awarded under the bridging period is significantly shorter than for the existing HPS. This will require more intensive inputs from THET – including more direct support to those awarded grants to ensure rapid and high quality project design, delivery, and monitoring and evaluation. / Our assessment is therefore that the budget represents value for money and that the management costs are justifiable given the intensive inputs needed to deliver the bridging activities. / Budget redacted / Logframe / The current logframe will be amended once the Accountable Grant is signed to reflect the revised approach and the recommendations of the programme’s annual review due in July 2017. / Risk / As for the current programme, overall risk for the bridge funding is considered to be moderate. The main programme risks and mitigation measures, as updated in the most recent HPS Annual Review (June 2016), and regularly reviewed by DFID with THET, are outlined in Annex 1. / THET has demonstrated sound leadership and financial management of significant DFID funds, with over 200 health partnership grants awarded and managed. DFID conducted a due diligence assessment of THET’s capacity and capability to deliver the current £30.2 m programme in 2014, prior to a cost-extension to the original HPS contract. High level mapping of THET’s delivery chains (and any associated risks) will be included in the Accountable Grant and updated as partnership grants are awarded. / Terrorism and financing / The overall risk of programme funds being diverted for terrorist related activities is minor. Most of the financing goes to supporting volunteers’ travel and costs which will be managed directly by UK Health Institutions with THET oversight. DFID will ensure that appropriate steps are followed and checks are undertaken in line with the Counter-terrorism Financing guidance to mitigate the risks of aid funding being diverted to terrorist organisations. In addition, DFID will make decisions and judgments in consultation with THET on when it is appropriate to suspend or withdraw funding for any given project.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work? / The programme rationale and objectives in the original HPS Project Memorandum still hold. / The independent evaluation of the HPS, completed October 2016, found that; / HPS partnership projects have contributed to health system strengthening by strengthening health worker capacity; / the volunteering and partnership approaches used by the HPS represent good value for money / the HPS benefits both volunteers and UK health systems. / A revised Theory of Change (ToC) was developed in consultation with key UK health stakeholders as part of the independent evaluation. It identifies three pathways by which health partnerships contribute to the intended outcome (stronger health systems, especially health workforce) and impact (health service provision and contribution to the health SDG). The proposed approach for bridge funding, is consistent with this theory of change. See ToC diagram below[3]. / (i) The Partnership change pathway describes how partnerships evolve and develop through support from the HPS. The expectation is that partners with a longer term relationship and with more experience of working together in the country will develop projects that will more strategically address health system constraints. / (ii) The Volunteer and UK Health system change pathway describes how volunteering opportunities are expected to enhance UK health workers’ attitudes, skills and behaviour so that they bring new ways of working back to the UK, positively influence the UK health system and improve services. It is expected that the positive experience of the UK health workers will encourage more volunteering and a better supply of volunteers, and might help with recruitment and retention of health workers in the UK. / (iii) Host country health system change pathway shows how the HPS projects, partnerships and volunteers enhance the knowledge, skills, attitudes and behaviour of host country health workers and this should result in a strengthened health workforce, delivering higher quality health services. Training curricula and certification, system inputs such as support for equipment management and infection prevention and control, leadership and HR management approaches are likely to lead to sustainable changes in the partnering institution. Over time, this will likely affect the health system and reach more health workers. An improvement of health workforce capability and status should lead to a strengthened health workforce if the overall management and funding of human resources is improved. / Assumptions / Health workers and institutional partners are able to address a range of health / system constraints in order to improve service delivery. / Health workers use new skills to improve the quality of care and inclusiveness of services they deliver to men, women and children. / Activities are delivered in cost effective ways to maximise the outcomes for the investment. / Monitoring and evaluation are used at project and programme level to inform / learning and improve effectiveness.
[1] Health Partnership Scheme independent evaluation, published December 2016; WHO Global Health Strategy on Human Resources for Health: Workforce 2030
[2] Results will be refined once grant selection criteria have been finalised
[3] The ToC will be updated during the design for any potential future support for health partnerships programme, including updating to reflect the Global Goals instead of the MDGs.

Annex 1: Risk Matrix

Risk	Impact	Mitigation	Residual Impact
External Context
Validity of programme 'assumptions' / - that health services are accessible and appropriate to target populations - that UK volunteers are able to make use of their experiences when returning - that health workers support change and have capacity to adopt improved practices	Major	THET selection process for grants include a review of project need, voluntary contributions and potential barriers to project delivery.	Minor
Projects suffer threats from raised security levels	Moderate	Grantees are required to undertake risk assessments and apply robust policies/procedures to addressing security issues.	Minor
Operational
Changes in DFID resources to support the programme or change in policy priorities	Major	Ensure proactive management of any impact on grantees, including stakeholder, political and media management	Moderate
Reputational
Perceived or actual detrimental impact of volunteering on NHS health service delivery	Major	There is little evidence that this is the case but the scoping studies to be commissioned separately will assess these issues in detail and identify how to address them if needed.	Minor
Delivery
Projects are not effective due to: level of UK partner's project management experience, lack of LMIC partner engagement or other contextual factors	Major	THET will select grants based on previous performance and will continue to provide advice and support on project design, budgeting and monitoring and evaluation. Progress and spending will be reviewed quarterly and funds withheld or redeployed if necessary	Minor
Safeguards
The programme activities have unintentionally detrimental impact on developing countries (programmes, priorities, etc)	High	THET will monitor and evaluate activities against a transparent framework and ensure close engagement with national governments. If necessary, THET will be able to terminate relevant activities/ or funding
Fiduciary
Grants do not meet adequate financial and project management standards. Multi-partnership arrangements and complex governance structures create challenges in effectively accounting for DFID funds	Major	THET will select grantees based on previous performance and ensure they have robust financial and control policies/systems in place. THET will also build capacity in this area as necessary. Payments are dependent on performance and adherence to robust financial reporting requirements, and THET will conduct regular adhoc audits	Minor