    Annual Review
Title: Building Disaster Resilience in Pakistan (BDRP)
Programme Value £ (full life): £40.8 million		Review Date: 15 July 2018
Programme Code: 203264	Start Date: 20-7-2014	End Date: 31-03-2020

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	B	B	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5573566.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/30264263.xls

A. Summary and Overview

Description of programme
Pakistan is one of the most disaster prone countries in the world. In the 2017[1] Global Climate Risk Index, Pakistan ranked 7th on the list of 10 countries most vulnerable to natural disasters, with more than 130 million people at risk. The Building Disaster Resilience in Pakistan Programme (BDRP) aims to increase Pakistan’s capability to reduce disaster risk through better planning, preparedness and response at the government and community levels. BDRP focuses on two main delivery areas: (a) Community Based Disaster Risk Management (CBDRM); and (b) Strengthening Disaster Management bodies at the federal, provincial, district and community levels. BDRP is delivered by two consortia:
[1] https://germanwatch.org/en/download/16411.pdf

- CBDRM consortium of international and local Non-Governmental Organisations (INGOs and NGOs) led by Concern Worldwide and including ACTED, Welthunger Hilfe (WHH), and the International Rescue Committee (IRC);
- Government-strengthening consortium led by the United Nations (UN) Food and Agriculture Organisation (FAO) and includes the United National Development Programme (UNDP) and the UN’s World Food Programme (WFP).

BDRP has three main outputs:
- Output 1: Evidence of effective community/village resilience building measures (led by Concern worldwide consortium);
- Output 2: Improved skills for government for better disaster management (led by FAO);
- Output 3: Sustainable livelihoods and environmental management practices providing greater community resilience (led by both Concern and FAO).

The programme started in September 2016[2] with an eight-month inception period. Phase I implementation work started on 1st May 2017. It has focused on piloting resilience-building activities in four districts: two in southern Punjab (Rajanpur and Muzaffargarh) and two in Northern Sindh (Ghotki, Kashmore). The programme is in line with the Gender Equality Act. Programme interventions are strongly focused on how they will contribute to reducing gender inequality. One of the programme’s aims is to target women and female headed households who are amongst the most vulnerable to natural disasters and data is disaggregated by sex.
[2] The business case was approved in July 2014. However, procurement was delayed because of staffing gaps and the need for further design work. In addition, the programme budget was reviewed through the Bilateral Aid Review (BAR) and Spending Review of DFID programmes, which resulted in a reduction in the overall programme budget from £76.3 million to £40.8 million.

This Annual Review has used evidence and results data as of June 2018 to assess progress towards meeting milestones for August 2018 (i.e the end of Phase I).

The programme steering committee, chaired by the National Disaster Management Authority (NDMA) meets every six months. It includes representatives from the NDMA, Provincial Disaster Management Authorities (PDMAs), other provincial government department and line ministries, the UN and INGO/NGO consortia and DFID. BDRP is a part of DFID Pakistan’s International Climate Fund (ICF)[3] offer.
[3] https://www.gov.uk/government/publications/international-climate-fund/international-climate-fund

Phase II is due to start in September 2018 pending Ministerial and other approval processes.

Summary supporting narrative for the overall score in this review
The programme has been awarded an ‘A’ rating. Whilst not all of the milestones have been met yet, the team assesses that they will be met by the end of Phase I based on progress to date and plans for the remaining quarter.

Since the last AR (2017) partners’ performance has shown an upward trend with them meeting most of their milestones. Some key achievements include:

- Supporting an estimated 0.5 million individuals (approximately 49% women), to cope with extreme weather events through a range of approaches, such as providing timely agricultural advice to sustain livelihoods;
- The development of baseline village and district risk profiles and capacity needs assessments to inform design of practical and context- appropriate programme interventions;
- Piloting agricultural resilience building and conservation practices at the community level;
- Establishment of emergency response teams at the Union Council level in both Punjab and Sindh;
- Ecological zoning for Punjab and Sindh last conducted in 1980s has been updated and an agriculture stress index system to improve drought monitoring has been piloted.
All three outputs are on track to achieve their targets[4] and therefore have been awarded A. The DFID team has maintained regular engagement and close coordination with the implementing partners to ensure implementation remains on track given the tight implementation timeline over 18 months.
[4] Phase I targets are for August 2018 which is later than this review. The team therefore made the assessment based on progress to date and plans/evidence of likelihood of meeting the overall Phase I target.

Recommendations for the year ahead
The recommendations below are not specific to any one output, but relate to the overall programme. Specific output recommendations can be found in the detailed output scoring section:

Programme governance structure and coordination with government: Through concerted efforts, governance and management arrangements are working well in Punjab. Similar efforts are required in Sindh. Implementing partners should regularly engage with government counterparts/key stakeholders in Sindh to seek the right support for programme implementation. It is recommended that DFID submit final progress reports for Phase I to relevant stakeholders including NDMA, PDMAs and DDMAs. Partners need to strengthen engagement with local and provincial governments to promote mainstreaming of resilience into annual development plans and processes. This will ensure scale up and replication of best practices implemented under BDRP.

Engagement with other DFID programmes: Multi Year Humanitarian Programme (MYHP) and BDRP should work more closely together, including joint visits – drawing on lessons and using the next two years to identify key areas for interventions for future programming. DFID should seek ways to improve coordination between BDRP and the Inclusion, Accountability and Preventing Modern Slavery (AAWAZ II) and Sub National Governance (SNG II) programmes. For this, the DFID team should sit together to jointly map out areas of overlap to identify how to better utilize existing community mechanisms/platforms and undertake joint field visits. Broader linkages could also be sought with other programmes (Sub National Governance (SNG) II, Sustainable Energy and Economic Development (SEED) , AWAAZ) on better integrating disaster management.

Cross-consortia learning: DFID should work with partners to strengthen coordination and communication between the two BDRP consortia to ensure complementarity between the activities. Work is needed to ensure shared objectives and approaches – and also a shared Monitoring and Evaluation plan to promote synergies across the two consortia.

Refresh political economy analysis: Partners need to improve their understanding of the political economy analysis, particularly who benefits and who loses from the status quo. DFID and partners should refresh political economy analysis this year for the programme.

Evidence gathering: Partners need to increase focus on gathering evidence of impact on the drought-affected communities. This should include how to ensure effective mobilization to mitigate drought.

Coherent project timelines: DFID team need to ensure annual review timelines are consistent with the milestones timelines in Phase II of the programme to enable accurate assessment of performance based on the latest data.

Acronyms
AR	Annual Review
ARBIs	Agriculture Resilience Building Initiatives
BDRP	Building Disaster Resilience Programme
CDMC	Community Disaster Management Committee
CBDRM	Community Based Disaster Risk Management
DDMAs	District Disaster Management Authorities
DFID	Department for International Development
DRM	Disaster Risk Management
DRR	Disaster Risk Reduction
FAO	Food and Agriculture Organisation of the United Nations
GoP	Government of Pakistan
(I)NGO	(International) Non-Governmental Organisation
LFA	Logical Framework Agreement or Log Frame
MYHP	Multi Year Humanitarian Programme
NDMA	National Disaster Management Authority
O&M	Operation and Management
PCD	Procurement and Commercial Department
PELP	Pakistan Evidence and Learning Platform
PDMAs	Provincial Disaster Management Authorities (Punjab and Sindh)
PMD	Pakistan Meteorological Department
PWDs	People with disabilities
SIMEX	Emergency response simulation trainings and exercises
SEED	Sustainable Energy and Economic Development
SNG II	Sub National Governance Programme
SOPs	Standard Operating Procedures
TPM	Third party monitor
UC	Union Council
UERT	Union Council Emergency Response Teams
UCRF	Union council response forums
UCDRF	Union Council Disaster Resilience Fund
UN	United Nations
UNDP	United Nations Development Programme
VfM	Value for Money
VERT	Village Emergency Response Team
WASH	Water, Sanitation and Hygiene
WFP	World Food Programme
WHH	Welthungerhilfe

## B: DETAILED OUTPUT SCORING

Output Title	Target stakeholders have resilience building measures in place (disaggregated by community, households, institutions)
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review (August 2018)	Progress (As of June 30, 2018)
1.1.Number of community based disaster risk management structures established and functioning effectively	300 Community Disaster Management Committees (CDMCs) have been formed and 28 Union Council Emergency Response Teams (UERTs) are established and functioning.	300 CDMCs have been formed and 28 UERTs are established and functioning. / A (met expectations)
1.2.Number of people who have benefitted from improved Water, Sanitation and Hygiene (WASH)	315,000 (Male: 51% Female: 49% of which 8% are People with disabilities [PWD]) are triggered for safe defecation. This also includes including 25,200 individuals who have been provided hand pumps for safe drinking water.	315,000 (Male: 51%; Female: 49% of which 8% are PWD). This includes over 19,000 individuals who have been provided with hand pumps for safe drinking water. / A (met expectations) - On track to meet August milestones.
1.3.Number of people who have benefitted from improved Disaster Risk Reduction (DRR) infrastructure (bunds, embankments, protection/retaining walls, raised bed platforms, evacuation routes, water harvesting structures)	63,000 individuals have benefited from improved DRR infrastructure (Male 51% Female: 49% of which 0.05% are PWD)	49,980 individuals have benefited from improved DRR infrastructure. (Male: 51%; Female : 49% of which 0.05% are PWD) persons / B (Moderately did not meet expectations) – Target may get delayed if there is heavy rains/flood as monsoon season starts in July.
1.4.Number of people who have benefitted from disaster resilient shelters	2,100 persons benefitted from disaster resilient shelters	1,512 persons benefited from disaster resilient shelters. / A (met expectations) - On track to meet August milestones.

This output aims to establish community structures and to demonstrate how communities are leading on resilience activities. All the targets under Output 1 are on track for completion by the end of August 2018 (end of Phase 1).

Output 1.1: 300 Community Based Disaster Risk Management structures (CDMCs) and 28 Union Council Emergency Response Teams (UERTs) have been established in the target districts. The members of these structures and teams are effectively facilitating, planning, implementing and monitoring resilience activities. The formation of CDMCs in each village started with initial consultations and rapport building with communities followed by detailed orientation. Formation requires representation of women, elderly, PWD, religious and ethnic minorities and other vulnerable groups. Overall, the composition of CDMCs comprises 69 % men, 31% women, and 2% PWDs and elderly. These structures have managed identification of community members for different trainings, identification of sites for small to medium scale infrastructures and identification of beneficiaries for livelihood activities. UERTs have been trained on relevant subjects such as search and rescue, first aid and firefighting with the involvement of relevant line departments such as Rescue 1122.

Output 1.2: Mass awareness campaigns were launched both at community and school level regarding health, hygiene, safe water and sanitation. Activities included: triggering exercises at village level, interactive street theatres for hygiene promotion; school hygiene club formation; celebration of global water, sanitation and hygiene (WASH) days; information, education and communication (IEC) materials developed and disseminated. Communal hand pumps with raised platforms were installed in 70% of the target villages for provision of safe water to communities and the remaining communities will receive hand pumps before the end of August 2018. To make facilities accessible for PWDs, ramps and side grills are provided on hand pumps in those communities where there is a presence of PWDs. Pre and post construction water testing was done to ensure the quality of water. Operation and Maintenance (OandM) kits were handed over to the CDMCs to ensure future operation and maintenance of the newly constructed hand pumps[5].
[5] The constructed hand pumps are large in size and can extract water from 50ft to 80ft as compared to traditionally used hand pumps which pump water from 30ft to 50ft only.

Output 1.3: Small to medium scale disaster risk reduction (DRR) and livelihood infrastructure schemes were constructed/ rehabilitated. These included access roads, medium size culverts, drainage schemes, raised platforms and irrigation channels. Community members and CDMCs ensured that the identified schemes were communal and would build the resilience of considerable numbers of households, especially the most vulnerable in the village. Programme trained masons and local labourers were involved through cash for work. This helped in generating livelihood opportunities. The completed schemes were handed over to relevant CDMCs for operation and maintenance. There have been delays in the procurement of supplies which could have been avoided with earlier decisions on procurement policies between consortium members.

Output 1.4: Household level disaster resilient shelters were constructed for the most vulnerable members of the community (including those with disabilities). The shelters with raised platforms will help secure lives and assets of vulnerable families in case of floods. Local masons trained by the programme were involved in the construction of shelters.

Lessons Learnt:
- Community empowerment takes time and requires continued consultations and facilitation. Dialogue with government line departments needs constant follow-up, time and energy to ensure the sustainability of the programme.
- Multiple committees at village and union council (UC) level will probably create complexities during a real time emergency. A single and simplified structure with a clear hierarchy would perform better in times of disaster.
- Training of qualified government officials and rolling out training through them at the field level will ensure the ownership of interventions by government. This will ensure sustainability of interventions in the long run.

Recommendations:
- It is important that formal handing over of infrastructure schemes happens with records/data given to respective district disaster management authorities (DDMAs) and relevant authorities. Partners need to ensure this by the end of August 2018.
- Advocacy and lobbying efforts with district governments need to be prioritised to ensure the replication of resilience activities. Partners need to lobby with district governments to have resources dedicated for DRR schemes and capacity building to ensure sustainability. The DFID team will work with the SNG II programme to seek synergies around public finance planning and budgeting.
- It is important to ensure sustainability of community structures. This might be achieved by linking community forums established under DFID’s AAWAZ II[6] with CDMCs.
  [6] AAWAZ II - a successor programme of AAWAZ I focuses on strengthening voice and inclusion of marginalised communities especially women and young people. The programme has established community forums which could be utilised for BDRP.

Output Title	Target stakeholders have improved skills and systems to develop, plan and apply DRM and DRR strategies and Standard Operating Procedures (SOPs)
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1. Standard Operating Procedures (SOPs) established for how to integrate, develop, implement and evaluate disaster management element at sectoral levels	Sectoral plans and phase 1 implementation plans acknowledged by key stakeholders (NDMA, PDMAs, implementing partners) / Number of agricultural, governance, health and education disaster management SOPs established	Phase I plans have been shared and acknowledged by key stakeholders / 8 Standard Operating Procedures (SOPs) have been developed / A (met expectations)
2.2. Number of DRM/DRR plans and strategies developed and adopted by target stakeholders	At least 12 DRM/DRR plans and strategies at national, provincial and districts levels will be developed and adopted by stakeholders.	12 DRM/DRR plans and strategies at national, provincial and district levels have been developed and adopted by stakeholders / A (met expectations)
2.3. Number of people trained with new DRR/DRM Skills. Number of master trainers trained.	2,750 people trained with new DRR/DRM Skills	2,195 people trained with new DRR/DRM Skills / A (met expectations) - On track to meet August milestones.
2.4. Number of new dialogues or forums established between communities and government	Identification of members and formation of 28 UCRF (Union council response forums)	28 UCRF have been established / A (met expectations)

This output is about the level of knowledge among government and disaster management practitioners, i.e. the right skills and adequate resources to plan, prepare and respond to a disaster. Overall, the output has met expectations.

Output 2.1: A total of eight SOPs have been developed on agriculture, education and disaster management with active participation of key stakeholders including NMDA, PDMAs and relevant government departments. Their purpose is to ensure that DRR is mainstreamed in education and agriculture. SOPs have been developed for multi-hazard vulnerability risk assessments (MHVRAs) and mainstreaming DRR in rehabilitation and development planning. A Multi Hazard and Vulnerability Risk Assessment study has been conducted in targeted districts of Sindh. SOPs have been formed on updating the data. Designing and printing of the maps are in process which is expected to be completed and launched later this year. In Phase II focus will be on monitoring and implementation of SOPs.

Output 2.2: A number of key outputs have been delivered, including:

Four district level Agriculture Disaster Management plans for target districts developed with extensive consultations and ownership of agriculture department. District Agriculture Technical Advisory Groups have been formed to enhance linkages and promote regular and smooth interaction with stakeholders at the district level;
- Preparation of two provincial Agriculture Disaster Management plans has been initiated. The plans will support provincial agriculture departments to mainstream disaster risk management into agriculture development plans and set operational modalities;
- Sindh Drought Mitigation Policy has been reviewed and finalized;
- Development of the Punjab Provincial Strategy on Public Private Partnership has been started, to target the private sector as a potential source of support for disaster and climate risk management;
- All four district level Disaster Risk Management plans have been drafted with engagement of the DDMAs and PDMAs. Two have been endorsed by the respective authorities and the remaining two are in the final stages;
- UNDP has supported the strengthening of District Emergency Operation Centres (DEOCs) of Kashmore and Ghotki (Sindh) to perform their prescribed roles effectively. UNDP worked with various tiers of disaster management authorities from federal to district level on the National Action Plan for the Sendai Framework for DRR

Output 2.3: This output captures the beneficiaries of various technical trainings. The trainings are outlined as below:

Training	No. of Participants trained
Emergency response simulation trainings and exercises (SIMEX)	180
Village disaster management planning and hazard, livelihood vulnerability assessments	100
Agriculture stress index systems and tools	35
Agro-ecological zoning	55
Farmer field schools, women open schools and livestock farmer field schools	1,825

35 participants of the Pakistan Meteorological Department (PMD) have been trained on Agriculture stress index systems and tools to improve drought monitoring at provincial level, 55 participants have been trained in agro-ecological zoning on Punjab and Sindh. The baseline study done under the project indicated that previous agro-ecological zones of Pakistan were too broad for provincial and district-level planning and thus needed an update for better planning and decision making processes. FAO engaged an international consultant to lead the training for PMD. FAO locally trained staff are working closely with PMD trained staff and the irrigation department for the monitoring of drought. Similarly for the agro-ecological zoning, FAO collaborated with agriculture universities in Punjab and Sindh and trained students on data collection and analysis. The collected data was used for modelling which resulted in changes in the zones.

Output 2.4: 28 Union Council Response Forums (UCRF) have been trained on organisational development, leadership, proposal writing, monitoring and record keeping. This will help them in advocating for additional resources from government and other organisations for funding their unmet needs, as identified in the Village Disaster Management Plans) and Union Council Disaster Management Plans Emergency equipment has been provided to the UCRF to support UERTs in emergency response. Originally the forums were also responsible for managing the funds for identified DRR schemes through the Union Council Disaster Resilience Funds (UCDRF). However, partners are unable to register the forums to date because of a lack of clarity among different departments at district level which caused delays. As an alternative, partners have implemented the DRR schemes through a procurement process in close coordination and with the participation of the UCRFs.

Lessons Learnt:
- Female participation particularly in UCRFs was challenging due to mobility issues. However involvement of female councillors, teachers and Lady Health Workers proved helpful in ensuring the participation of women;
- UN agencies need to ensure coordination between them to ensure complementarity within proposed activities.

Recommendations:
- UN partners should ensure timely dissemination of reports to share key lessons and initiate dialogue with government on forward implementation;
- The work under this output has potential to link up with community structures and capacity building work done under Output 1. It is recommended to harmonise them where possible for greater impact through joint meetings and monitoring visits;
- It is important that DFID strengthens relationships with the top leadership of PDMA in Punjab and the DFID Lahore office can support this. This would improve ownership from government and accountability to DFID for its investment;
- FAO needs to focus on evaluation of their activities to understand better what has worked, what has not worked and why, particularly to feed into Phase II;
- Considering the engagement with two PDMAs, an institutional review of Punjab and Sindh PDMAs may be undertaken by FAO in the next phase. This will help in designing context specific activities and possible learnings across two institutions.

Output Title	Target stakeholders are introduced to sustainable livelihoods and environmental management practices for resilience building
Output number per LF		3	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of community level on farm and off farm agricultural resilience building initiatives and new improved environmental management practices adopted which support resilience and sustainable livelihoods	10-12 (both on farm and off farm) resilience building measures in place and operating	11 (both on farm and off farm) resilience building measures in place and operating / A (met expectations)
3.2. Number of households in targeted areas (most vulnerable 20%) that have benefitted from resilient livelihood related field interventions	60,148 Households or communities	20,152 Households. One major activity Information and Communication Technologies (based weather forecasting for farmers (approx. 38,000) is planned for July-August. / B (Moderately did not meet expectations)
3.3. Number of demonstration plots developed for promotion of flood tolerant crops and fodder	1,408 plots (352 per district - 200 Wheat plots, 120 fodder plots and 32 high value crops plots/district). / FAO to establish 32 sites for the demonstration of Agriculture Resilience Building Initiatives (ARBIs)	1,651 plot (922 Wheat plots, 601 fodder plots and 128 high value crops plots in four districts). / 54 sites established sites for the demonstration of Agriculture Resilience Building Initiatives (ARBIs) / A+ (Outputs moderately exceeded expectation)

This output is about sustainable livelihoods and environmental management practices and has moderately exceeded expectations. Good progress has been made in implementing agro-forestry related activities along with agriculture resilience building initiatives.

Output 3.1: In 2017, both on farm and off farm resilience building measures were introduced. These resilience building initiatives were identified through comprehensive risk and resilience profiling, consultation with FAO and relevant government departments during the inception phase of the BDRP programme. 32 Agriculture Resilience Building Initiatives (ARBIs) have been identified and documented by means of a comprehensive study. These ARBIs present a set of best agricultural practice options considering hazards and with climate smart elements. 11 ARBIs have been demonstrated which are being adopted and replicated by communities. The ARBIs primarily include, for example, laser land levelling, zero tillage, mulching, multiple cropping, crop rotation and use of integrated pest management techniques.

In-addition, livelihoods diversification through vocational skill trainings was identified under the off farm livelihood work.

Output 3.2: Approximately 20,152 households have benefitted from on farm and off farm livelihood activities in targeted districts. The review team is of the view that based on current progress and plans, the full target will be met by August 2018.

The following table depicts livelihood packages with respective targets.

On farm livelihood packages
Capacity building of farmers on climate smart agriculture and conservation agriculture based technologies and practices	4,651
Community based quality seed production and multiplication and storage facility	922
Promotion of improved household nutrition through vegetable production and training	7,125
Introduction and promotion of flood/drought tolerant crops	601
Promotion of high value crops	128
Promotion of home based poultry / turkeys and ducks and training	1,500
Improved community capacity in livestock management through Community Livestock Extension Workers workforce development	259
Community based nurseries for quality seedling and plants production	26
Plantation of agro‐forestry and multipurpose hedgerows/wind breaks and farm boundary markers	4,500
Off farm livelihood packages
Electrician, UPS repair and solar mechanics training	44
Motor cycle repair mechanic	45
Tailoring and embroidery	290
Small engine[7] repair and maintenance	40
Mobile repairing	21
Total	20,152
[7] Petrol/Diesel engines

Promotion of improved household nutrition through vegetable production and training was specifically designed for women. The packages comprised seeds and a toolkit, and trainings were provided to women to establish kitchen gardens. Women have reported selling surplus produce from kitchen gardens, thus increasing their income.[8]
[8] Mid-term survey conducted by Concern

Output 3.3: Under this output 300 seed production plots for crops, 179 for fodder and 128 for high value crops have been piloted in four districts to enhance agriculture resilience of targeted communities. The beneficiary farmers were identified in consultation with CDMCs based on agreed criteria. 128 packages of high value crops have been distributed based on the recommendations made by a market assessment and value chain analysis study. Practical demonstration of installation of tunnels and orientation on vegetable cultivation were also conducted. FAO has exceeded its target and has established 54 sites for the demonstration of Agriculture Resilience Building Initiatives (ARBIs)

Lessons Learnt:
- Joint planning and collaboration among FAO and Concern on agriculture provided an opportunity for joint learning in Sindh and a similar practice could be beneficial in Punjab.
- Wider initiatives taken by Punjab and Sindh governments on agriculture and skills development offered opportunities for creating synergies and complementarities. This has resulted in targeted beneficiaries getting the full benefit from the government schemes and better value for money.
Recommendations:
- The demonstration of agriculture resilience building initiatives has been replicated by farmers. There is a need to document the evidence and to use it for wider adoption by government and other developmental organisations. FAO should share the economic analysis of climate smart agriculture plots with provincial agriculture departments;
- Non-traditional livelihood packages could be designed for women to allow for greater livelihood diversification. This will help in building the social resilience of women. Implementing partners may consider piloting these packages in Phase II.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The programme’s theory of change (ToC) was revised during the inception phase of the programme in April 2017. Under the new ToC, the outputs now follow a different sequence starting with formation and empowerment of CBDRM structures followed by capacity building of CBDRM structures and resilient livelihood interventions. Finally, the theory of change now elaborates targeting, key thematic areas of change as well as the stakeholders the programme will be working with. The revised theory of change is depicted below:

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and what action is planned as a result in the year ahead

Outcome: The overall outcome for BDRP is ‘Resilience of crisis-affected communities improved through risk assessment, planning, mitigation and preparedness measures and emergency response’. There are two outcome indicators. Progress is on track. A brief summary of progress is provided below.

Outcome Indicator	Progress
Number of people whose resilience has improved as a result of project support	The Concern-led consortium did a mid-term survey to measure resilience in the targeted population. 792 randomly selected households from the targeted households were interviewed using a questionnaire to calculate the resilience score of a household. / In the baseline, 19% of the selected households were deemed as ‘resilient’. A comparison between our mid-term survey data against our baseline data reveals that now 52% of the selected households are ‘resilient’ i.e. already transitioned from low to higher level of resilience.
Number of quality DDMA contingency plans developed, financed and implemented, that reflect the environmental context and priorities of village committees	The programme has extended its support to the National Disaster Management Authority in developing the district disaster management plans. It has completed district level consultative processes for developing district DRM plans in all four project districts and disseminated drafts among stakeholders for review and finalization. Four district level validation workshops were also held to verify content.

Impact: The programme contributes to the following impact - ‘Crisis-affected populations in Pakistan are better able to anticipate, cope with, adapt and recover from shocks and stresses’. It is difficult to gauge progress at impact level at this stage as there has been no major disaster in the targeted communities.

Given the impact of disasters in Pakistan, increase in resilience at the community level is expected to result in fewer losses in terms of livelihoods and lives following a natural disaster. So a CBDRM treated village hit by a disaster will require reduced emergency assistance compared to a non-treated village because of its ability to cope and to recover quickly.

The mid-term survey conducted by Concern showed that the resilience of communities has increased based on indicators/criteria decided during the inception phase of the programme. However the actual ability of communities to cope and recover from disasters can only be assessed in times of disaster.

Explain major changes to the log frame in the past year
The log frame was reviewed in September 2017 taking into account baseline figures from the inception phase work. The major changes are:

- All outcome and output indicators are now based on the baseline studies carried out under the programme;
- Milestones and overall targets were updated for 2018;
- Targets for indicators were revised based on the revised scope of some activities;
- Disaggregated numbers, on sex and disability, have been provided.

Recognising what is attributable to this programme, and what is not in the control of this programme, a change was made to Output 3 in April 2018. Output indicator 3.4 relating to improved coordination and technical design of humanitarian and resilience project was removed as it was felt it was more appropriate for the Multi-Year Humanitarian Programme.

Describe any planned changes to the log frame as a result of this review
The log frame should be revised after this annual review and when the decision on moving to Phase II of CBDRM is finalised (due August 2018). The following changes are planned in the log frame as a result of this review.

- Output indicator 2.1 ‘SOPs for health’ is no longer valid and needs to be removed, as it been already done by another organization;
- Clearer milestones need to be developed under output 2;
- The log frame may include an indicator linking up output 2 with output 1.

By the end of the implementation of Phase I, Concern will conduct an evaluation of their CBDRM component, as per their contract, by hiring an independent third party. The proposal for Phase II will have a revised log frame if and when the CBDRM component is approved.

## D: VALUE FOR MONEY

Key cost drivers and performance
The existing budget for BDRP is less than originally planned (see 2016 Annual Review). The total programme budget is £ 40.8 million and is allocated as follows:
- CBDRM : £35.8m
- Institutional strengthening : £5m

Reduced budgets directly impact the scale of the programme; however, key cost drivers identified in the business case remain unchanged. For example, the deployment of technical experts on a full and part time basis was identified as a key cost driver which remains valid post budget reductions. The unit cost of these experts was reviewed during the competitive bidding process. The DFID team continues to monitor unit cost through implementation with an aim to achieve efficiency savings where possible.

Assess VfM compared to the proposition in the Business Case, based on the past year
Given the high costs of emergency assistance and frequency of disasters in Pakistan, increases in resilience at the community level are expected to result in reductions in both the immediate impacts, and in the cost of recovery following a natural disaster. A 2012 study[9] from Ethiopia, Kenya and Bangladesh suggests that wider benefits of building resilience in a drought hit area will significantly outweigh its costs leading to the conclusion that investment in resilience is value for money. The VfM case made at the business case stage still holds i.e. a CBDRM treated village hit by a disaster will require reduced emergency assistance compared to a non-treated village.
[9] Cabot Venton, Courtenay. 2012. ‘Economics of Early Response and Disaster Resilience: Lessons from Kenya and Ethiopia’ and https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/226156/TEERR_Bangladesh_Report.pdf

Through the inception and implementation period DFID has been in discussions with the CBDRM supplier around costs per village in the context of their vulnerability profiling which pinpointed the needs of the communities. This has helped to determine and refine the scale and scope of interventions in each village and district. Based on these vulnerability profiles and costs per district, a set of VfM indicators has been finalised. Progress on these indicators is being monitored on a quarterly basis providing assurance that broadly all unit costs have remained within the agreed benchmarks. [10]
[10] On average, major outputs were delivered at 7.7% higher than the negotiated baseline unit costs in 2016 – which when compared with the cumulative inflation in Pakistan during 2016-2018 at 10.9% seems reasonable.

Recommendation: Drawing on the data from inception and implementation phase activities DFID and partners should review and update the VfM template to ensure its usefulness.

Explain whether and why the programme should continue from a VFM perspective, based on its own merits and in the context of the wider portfolio

Pakistan remains prone to natural hazards and disasters, including floods, earthquakes, and drought. The Global Facility for Disaster Reduction and Recovery (GFDRR) reports that 9% of the national territory is at risk from two or more hazards, representing almost half the country's population.[11] During 2002-2012 more than 80% of the country’s 124 districts have been hit by natural disasters, with some 33 million people affected. Conflict, insecurity and violence across Pakistan compounds vulnerability, undermining coping mechanisms and challenging effective response. In turn, natural disasters can erode fragile peace and security gains. Poor people are the most widely exposed, and disasters increase their vulnerability to malnutrition, disease, increased debt and exploitation.
[11] GFDRR Natural Hotspots Study: A Global Risk Analysis 2005. As per this Risk Assessment, Pakistan is prone to two or more hazards (including floods, earthquakes and droughts). Although the floods will only affect 9% of the national territory, the areas affected (Indus delta and Karachi) are densely populated putting 40.1% of the population at risk.

In addition to human suffering, most recent natural disasters have caused US$17.1 billion of losses to the economy. In 2010 alone, the monsoon flooding of the Indus River in Pakistan led to a humanitarian disaster affecting approximately 20 million people, destroyed homes, crops, and infrastructure and left millions vulnerable to malnutrition and waterborne disease. Estimates of the total number of people killed ranged from 1,200 to 2,200, while approximately 1.6 million houses were damaged or destroyed, leaving an estimated 14 million people without homes. The damage caused by floods in 2010 and 2011 was estimated at US$10billion and $3.7billion respectively.

In a disaster prone country, investing in resilience which continues to reduce people’s vulnerability, and enable better and more appropriate responses to emergencies remains VfM. This investment does not negate the need to support people who have been affected by humanitarian disasters in the short to mid-term. DFID Pakistan continues to deliver through a complementary Multi-Year Humanitarian Programme allowing for a more strategic response to humanitarian emergencies. Where there are opportunities to ‘build back better’, the humanitarian programme seeks to ensure that options (whether house-building or similar) are as resilient as possible.

E: RISK

Overall risk rating: Moderate. There has been little change during the year as the programme moved from inception to implementation. Risk mitigation measures include:
- A risk register has been established and is updated on a regular basis;
- A third party monitoring firm has been hired by DFID to verify CBDRM milestones and conduct asset spot checks every two months;
- A programme delivery plan is being used to monitor programme performance and procurement risks.
- Additional support has been sought through the DFID Pakistan Portfolio Risk Assurance Programme II [12] led by Price Waterhouse Coopers (PWC). PRAP will review the governance structure and cash flow tracking of the Union Council Disaster Resilience Funds (UCDRF)[13]. Please see output 2.4 for more details.
  [12] PRAP II is designed to strengthen DFID Pakistan’s ability to identify, understand, address and manage programme level risks, by assessing the ways in which implementing partners mitigate such risks in their governance, management and financial approaches and control environments
  [13] The UCDRF is an entity responsible for financing medium to large scale UC level Disaster Risk Reduction and Livelihood Infrastructure schemes.

As Phase I moves into the final stage of implementation, the following risks must be monitored:

Context: Monsoon flooding is likely in Punjab and Sindh in July/August each year. If serious flooding occurs, the government will prioritise a response effort over resilience building measures. This will also give a chance to see and test the contribution of this programme to the resilience of communities.

Governance: The programme effectiveness and sustainability depends on the ownership of the NDMA, PDMAs and DDMAs. Regular steering meetings have been chaired by NDMA at the national level and similarly provincial meetings have been done on a quarterly basis chaired by the respective PDMAs. It is important that regular coordination and communication is kept with the District, Provincial and Federal Governments (including DMAs) throughout programme implementation that will assist in ensuring their sustained engagement and support for the programme.

Safeguarding and accountability: Given the programme targets addressing vulnerability, gender and disability, safeguarding actions to prevent abuse and exploitation are a priority for the team. DFID in consultation with implementing partners has also undertaken a thorough safeguarding risk analysis which maps out key risks being faced by programme beneficiaries, impact, risk score and the mitigation in place. Prioritisation of villages and targeted beneficiaries under the current budget[14] may mean that some of the neediest communities are unable to access the programme during Phase I. This may be viewed unfavourably by some of the communities. This risk has been managed by using participatory and conflict sensitive approaches with clear communication, ensuring community involvement, ownership and satisfaction. An accountability framework (Beneficiary feedback and accountability to target population) has also been developed for the programme and put in place.
[14] In January 2016, the programme budget was reviewed through the Bilateral Aid Review (BAR), and reduced down by 47% which impacted the geographical coverage in the first phase of the programme.

Delivery: One key risk to delivery in Pakistan is the permission from government to INGOs to operate in certain districts and regions of the country. The Ministry of Interior (MOI) is leading the registration process for all INGOs. Under the CBDRM consortium, Concern Worldwide, WHH and Help Age have had their registrations renewed. However, the registration status of IRC and ACTED is under consideration which could cause delays in programme implementation. Thus it is important that members of the consortium have regular coordination and sharing of programme information with relevant government departments. In parallel, updates need to be shared with DFID on a regular basis.

General Elections 2018: General elections are scheduled for late July 2018. This may divert the attention of government partners at the Federal but particularly at the provincial level. There is likelihood that post-election, we may see Government turnover which could cause delays in decision making, implementation and programme handover. At the moment, all implementing partners have planned to maximise completion of core activities before elections.

Reputational: DFID’s commitment to building disaster resilience has been discussed widely with key stakeholders including the Government of Pakistan. If Phase II is not approved by the ministers, this may pose a reputational risk for DFID Pakistan not only at the community level but with the partners and the government as well. The team should work with partners and develop an appropriate exit strategy/ plan in case Phase II approval does not come through.

Update on partnership principles

The Partnership Principles Assessment (PPA) is regularly discussed with the Economic Affairs Division, Government of Pakistan at the federal level. The PPA was last discussed in March 2018 during our Bilateral Assistance Talks. The PPA sets out DFID’s assessment of the Government of Pakistan’s commitment to the four partnership principles, as demonstrated through its policies and action for reducing poverty and achieving the Sustainable Development Goals (SDGs). These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability.

BDRP aims to target the poorest and the most vulnerable communities based on need. It is being directly implemented through NGOs, INGOs and the UN. It supports the Government of Pakistan (GoP) priorities in reducing disaster risk and is in line with their national policies and plans. Even though there is no budget support or financial aid, the Government remains our primary strategic partner for the programme. The programme activities are being executed in partnership and through the endorsement of the NDMA, PDMAs and DDMAs.

The programme is part of the wider aid relationship between the UK and Pakistan, which is based on an assessment of the Pakistan Government’s commitment to our partnership principles. Although the Partnership Principles do not need to play a role in management and monitoring the programme, the future sustainability of NGO operations depends on government buy-in, collaboration, policy and financial support, and to demonstrate greater commitment to the principles, the government will need to work more with non-state actors.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of Partners: The partnership has helped achieve the programme objectives effectively, through contractual arrangements between DFID and Concern Worldwide, and a framework agreement between DFID and FAO. The performance of partners under BDRP is on an upward positive trend: a) both FAO and Concern Worldwide have gradually improved their reporting and communication with DFID; b) progress review meetings were held on a regular basis with partners to discuss work plans, risk registers and addressing challenges; c) performance management was also reviewed through a quarterly management committee (chaired by PDMAs Sindh and Punjab) and d) a six-monthly strategic and technical review committee was held, chaired by NDMA which provides strategic direction, oversight and ensures information-sharing and coordination between the different components. Third party monitors – GLOW – were hired through a competitive process to monitor the CBDRM component.

Performance on commercial and financial issues:

Concern Worldwide – CBDRM component: For Phase I, a total of £8.5m is allocated for the CBDRM component of which £5.9 has been spent as of May 2018. The CBDRM consortium has a hybrid payment model with 90 percent on milestones and 10% as actuals. The quarterly milestone targets are set on the basis of expected programme delivery timelines. The achievement of these targets is reported through quarterly progress reports. These targets are further subject to verification by DFID through desk review of documents and on verification by the third party monitoring firm, appointed by DFID. Under each activity, the consortium members are expected to produce evidence to show the completion of the activity.

An underspend has been noticed in invoices which demonstrates poor forecasting and planning from Concern Worldwide. Some of the key reasons behind this continuous underspend are delays in procurement by the downstream partners, government permission to implement a scheme, and staff turnover among the consortium members. Going forward (in Phase II), Concern Worldwide should revisit the agreements they currently have with partners, to disburse a minimum mobilization fee and then reimburse them on actuals. With a revised agreement suggested, it will incentivise downstream partners to spend and deliver at a faster rate.

FAO - Institutional Strengthening component: DFID has contributed £2 million for this component for phase I, of which £1 million was disbursed for the inception period and the remaining £1 million has been allocated for the implementation. FAO submits six monthly financial reports to DFID including a breakdown of expenses from UNDP and WFP.

Regular monthly meetings on finances are held with partners by DFID. The company GLOW has been hired as third party monitors with a contract value of £16,700.

The financial progress of the programme is on track. As of 31st March 2018, the programme has utilised 75% of the total budget for FY17-18. The budget break down between Concern and FAO is summarised in the below table:

Implementing partner	Contract Value for Phase I
Concern	£ 8,500,000
FAO	£ 2,000,000
Total Budget	£ 10,500,000

Asset monitoring and control
Concern Worldwide and FAO have adopted DFID’s asset policy (as set out in DFID’s ‘Smart Rules’). An asset register to record all assets purchased using programme funds has been submitted to DFID and is updated quarterly. GLOW Consultants have carried out the asset spot checks in partners’ field offices (including downstream partners) on behalf of DFID. The team will continue to follow up on the asset spot checks through the regular field visits.

Date of last narrative financial report(s)	31st March 2018 for FAO and April 30, 2018 for Concern
Date of last audited annual statement (s)	31st December, 2017 for Concern and FAO is pending (the team is following up)

G: MONITORING, EVIDENCE & LEARNING
Monitoring
The programme team has been using the delivery plan as a tool for tracking progress. DFID has agreed arrangements regarding tracking progress against the log frame and its milestones with BDRP partners. In addition to the overarching programme logframe, the team has worked with partners in developing their individual logical frameworks that capture disaggregated data on disability, age and sex. BDRP contributes to both the Single Departmental Plan and International Climate Fund (ICF) returns on results, and provides support in engaging with BDRP partners in reporting against these indicators.

Quarterly progress reports by partners are a way of reviewing and gathering evidence on the achieved milestones. The DFID team also conduct regular review meetings with partners to discuss ongoing progress, challenges, risks and real time solutions. Since the inception phase, the team has conducted four field visits to the targeted districts, when DFID staff was able to see the real time results of the BDRP interventions. Local people referred to the positive changes the investments have made. The DFID team also conducted monthly meetings with the Punjab PDMA for coordination and sharing of programme updates along with implementing partners.

GLOW Consultants (TPM) provides assurance to DFID Pakistan that the CBDRM activities under the BDRP programme have been delivered in an efficient manner and the agreed milestones are achieved to the required quality standards and contractual requirements. The TPM conducted two field visits covering all four districts. DFID will meet with partners to discuss the TPM findings. The TPM reports will help DFID to collect evidence on suppliers’ performance and take necessary measures for course correction. It will also help in recording lessons learned from the implementation of Phase I.

As part of our Government coordination, BDRP provided the beneficiary database and work plans to the Planning and Development Department (P&D) Punjab. P&D is using this portal as a monitoring tool to assess the ongoing resilience work in Punjab. The programme info can be found here: http://pcupiupnd.info/ppms
At the partner level as part of performance monitoring, a mid-term survey was carried out, with a statistically representative sample (792) taken from targeted households. This survey provided realistic baseline values for outcome as well as output level indicators.

This Annual review was led by DFID Pakistan’s Resilience Adviser with inputs, comments and reviews provided by the implementing partners, DFID Pakistan’s Social Development Adviser, Governance Adviser and Deputy Programme Manager. The review was quality assured by the Senior Responsible Owner for BDRP, Team Leader (Conflict, Humanitarian and Resilience Team) and reviewed by the Deputy and Head of Governance Group DFID Pakistan.

Evidence
The Concern led consortium did a mid-term survey to measure resilience in the targeted population. 792 randomly selected households from the targeted group were interviewed using a questionnaire to calculate the resilience score of a household. Results show that, as compared to the baseline, the overall resilience of targeted households in the three identified categories of low, medium and high resilience has improved.

Learning
At partner-level: It took some time to fully engage government partners in project activities but once it happened, it proved useful and paved the way for exploring linkages with on-going government programmes. Gender trainings were conducted for partner staff and downstream partners to ensure the participation of women in activities. Context specific strategies like provision of transportation and separate men/women meetings proved useful.

DFID-level: Partners need to invest time in innovative approaches to allow wider impact and overall cost savings. DFID will prioritise this as one of the key areas of focus in the coming year. Certain levels of flexibility might be given to partners to change activities based on socio-environmental changes. The DFID team need to work closely with MYHP to map out synergies among activities for Phase II of BDRP and collect evidence and data for a future combined programme.

Progress on recommendations from previous reviews

Recommendation	Progress
DFID and the implementing partners should meet every 2-3 months to ensure that implementation is coordinated and complementary. A quarterly stocktake will be helpful in reviewing the governance and management arrangements of BDRP and keeping track of progress against annual review recommendations;	BDRP team is regularly conducting: / Monthly catch ups with Concern and FAO to discuss programme progress, challenges etc. / Monthly meetings with PDMA Punjab, Agriculture department and Planning & Development (P&D) to discuss ongoing resilience work / Regularly conducting quarterly project management committee and six monthly project steering committee meetings
DFID should develop practical measures to bring the BDRP closer together with DFID’s Multi Year Humanitarian Programme (MYHP) and DFID’s Pakistan Evidence and Learning Platform (PELP)[15]. This can be achieved through joint meetings and/or joint field missions, MYHP sitting on the BDRP steering committee as well as bringing MYHP colleagues into BDRP monitoring and evaluation discussions;	MYHP consultants have recently conducted field visits including BDRP sites. They also monitored activities which are similar in both BDRP and MYHP i.e., shelters etc. and provided recommendations accordingly.
BDRP partners and the DFID team should focus on gathering evidence of impact from the implementation phase to support any submission to Ministers to scale up to Phase 2;	For implementation phase I, DFID has hired a TPM firm to monitor and provide evidence on the CBDRM activities. / DFID receives quarterly narrative reports from Concern and FAO and / DFID team field visits ensure gathering of evidence. / Concern Worldwide will also conduct an evaluation study in July/ Aug 2018 to capture impact/ outcome level info for the BDRP programme
DFID and partners should review and update the Value for Money (VfM) analysis given the change in scope for the programme (by end 2017)	A detailed VFM framework has been developed. This framework has been regularly updated during Phase I. Based on the learning from Phase I the framework will be refined in the scale up Phase.
During implementation, DFID and partners will make it a priority to review the approach to gender throughout the programme – building on the work underway by the Concern consortium to finalise a gender strategy and associated indicators. This should include how to maximise female participation at all levels of the governance structure, ensuring women are targeted effectively and improving data collection of gender sensitive outcomes. Disability and youth will also be more systematically considered following this review;	At programme level, at least 30% representation of vulnerable groups including women, PWD and elderly is ensured in CDMCs and other structures. Beneficiary data collection is gender, disability and age sensitive. / Concern has finalized the Gender strategy and Action Plan for the programme which provides detailed guidelines for gender integration in all proposed CBDRM activities.
Following the inception period, a modified log-frame was agreed by partners in April 2017. The indicators should be kept under review – with regular meetings with partners to assess progress and ensure consistency in approach to measurement (ongoing/quarterly). This will also support the earlier recommendation on building a robust evidence base.	The log frame agreement (LFA) was reviewed and updated in September 2017. Targets/ milestones were updated in consultation with partners.
[15] The Pakistan Evidence and Learning Platform (PELP) aims to establish a knowledge hub for the Humanitarian sector. It will gather evidence, generate and disseminate best practice, support innovation and develop the capability of Pakistan’s humanitarian sector.