## Logframe (hidden)
correct as of June 2016
PROJECT NAME | Improving UK Private Sector Engagement in Humanitarian Response
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
The private sector is better harnessed to reduce human suffering in humanitarian disasters | Level of business in the UK support in humanitarian disaster response - through cash, skills, expertise, products and services | Planned |  |  |  |  | 2018-06-01
Achieved
Source
BITC to measure current levels of business engagement
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
The private sector operating in the UK is better prepared to respond quickly, effectively and appropriately to humanitarian crises | Routine use of private sector in humanitarian disaster response. Milestone 2 to be repeated annually. | Planned |  | Baseline survey and review completed May 2014 | Survey completed by September 2015 |  | 15% increase on key metrics against the 2014 baseline: May 2018 | That there are international disasters that warrant business engagement and response. That there is an appetite amongst NGOs and businesses to increase the level of business engagement in humanitarian response.
|  | Achieved |  | 2014-09-01
Source
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
| 755,000 - 30,000 dedicated to monitoring and evaluation. 60,000 contingency |  |  |  |  | 755000 | 100%
INPUTS (HR) | DFID (FTEs)
DFID CHASE HRG programme staff
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumption
Increased insight and understanding for business on how they can best assist during humanitarian emergencies | Development and delivery of annual BITC International Disaster Relief Award (Award) as part of the BITC International Disaster Relief programme (IDRP). | Planned | 0 | IDRP Launch supported with senior DfID representation, Announcement of Award at launch: December 2013 | Workshop for business on engagement in programme and award application process: January 2014 | IDR award winners announced and profiled in July 2014 (following support to applicants, webinars, assessment and judging panel) | International Disaster Relief Awards held annually from 2014-2018. | That there are international disasters that warrant business engagement and response. That the International Disaster Relief Award will gather significant interest from the private sector.
|  | Achieved |  | 2013-12-01 | 2014-01-01 | 2014-07-01
Source
BITC
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Numbers of best practice case studies identified | Planned | 0 | First set of case studies published: May 2014 (5) | Second set of case studies published: June 2015 (10 new) | Third set of case studies published: June 2016 (15 new) | 50 case studies available: June 2018
|  | Achieved |  | 5
Source
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Insight papers articulating the business case for business engagement in disaster relief. | Planned |  | First Insight Paper produced December 2015 | Second Insight Paper produced December 2016 | Third Insight Paper produced December 2017 | Compiled document articulating business case for action produced by January 2018
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Online guidance for business on engagement with humanitarian community on BITC website (also relates to Output 3). | Planned | Number of users accessing guidance in 2014. | Develop new IDRP web pages and add revised guidance material: May 2015 | Refresh and populate BITC website with Award winners and case studies: Annually July 2014, 2015, 2016, 2017 | Review and evaluate website content and online guidance: February 2017 | 15% increase in average monthly users accessing online guidance by May 2017, against 2014 figures.
30% |  | Achieved |  |  | 2014-07-01
|  | Source | [5 empty] | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
Partnerships between NGOs and businesses are created | Number of new partnerships between NGOs and business established supported by the "Matching Tool" | Planned | 0 | "Matching Tool" concept drafted by June 2015 | Pilot testing of "Matching Tool" concept by December 2015 | "Matching Tool" first iteration developed and rolled out by June 2016. | 15 new partnerships by May 2018 | That there are international disasters that warrant business engagement and response. That there is an appetite amongst NGOs and businesses to develop strategic partnerships.
Achieved
Source
Records of partnerships established on BITC database. Depending on where the Matching Tool is on the spectrum from an IT system to active brokering will have implications on how much this will be database build in Year 3 and maintenance thereafter or staff time Year 3-5
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Number of forums and increase in dialogue around importance of engagement and partnerships between NGOs and business. Milestones 2 and 3 to be repeated annually. | Planned | Data on corporate engagement in key humanitarian forums and non BITC dialogue events during 2014 to be gathered by June 2015 | IDRP launch, supported by senior DIFD representative: December 2013 | 4 meetings with NGOs on engaging with business held by December 2015. | After action review of role of business in major disaster response held with businesses and humanitarian partners: September 2015 | 15% increase against 2014 baseline in corporate engagement in humanitarian forums and non BITC organised dialogue: May 2018
|  | Achieved |  | 2013-12-01
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
40% |  | Planned
Achieved
|  | Source | [5 empty] | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response | Capacity building for business to identify their unique contribution and better understand how it can be used. Milestones 1 , 2 and 3 to be repeated annually. | Planned | 0 | Disaster simulation exercise April 2015 | Seminar/webinar series on key aspects on business unique contribution established by September 2015 | Training for business on key aspects of the online guidance by December 2015. | 120 business leaders engaged in seminars, simulations and training by July 2018 | That there are international disasters that warrant business engagement and response. That businesses have an interest in furthering their engagament in humanitarain response.
|  | Achieved |  | 2015-04-01
Source
BITC database
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Number of face to face meetings with business targets | Planned | 0 | 20 Meetings: September 2014 | 50 Meetings: May 2015 | 125 Meetings: May 2017 | 200 Meetings: May 2018
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
30% | Recommendations on role of business in disaster relief put forward to DFID to inform World Humanitarian Summit 2016 preparations (Note: this is additional work not currently included in the project budget) | Planned | 0 | Europe consultation with business held in May 2015 | Paper submitted to DFID with recommendations for WHS agenda planning meeting by end June 2015. | Business leaders encouraged to attend WHS in May 2016. | Recommendations based on business consultation are provided by June 2015 to inform WHS preparations.
Achieved
Source
| Output Indicator 3.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date)
| Number of businesses showcasing their International Disaster Relief programme in their corporate communications. Milestone 1 will be repeated annually | Planned | Baseline established on number of BITC members showcasing IDR in corporate communications in 2014, by June 2015. | Review of number of BITC companies showcasing IDR in corporate communications in 2015 (June 2016) |  |  | 15% increase against 2014 baseline in businesses showcasing international disaster relief programmes in corporate communications: May 2018
Achieved
|  | Source | [5 empty] | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## logframe revised 2018
PROJECT NAME | Improving UK Private Sector Engagement in Humanitarian Response
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | N/A | Target
The private sector is better harnessed to reduce human suffering in humanitarian disasters | Routine strategic use of private sector in humanitarian disaster response. | Planned | 59% of business have a policy or process in place for activation | Baseline survey and review completed May 2014 - 59% of business have a policy or process in place for activation | A 5% point increase on baseline | A 10% point incraese on the baseline | A 15 % point increase on baseline | N/A | 15% increase on key metrics against the 2014 baseline: May 2018
|  | Achieved |  | 2014-09-01 | 01/09/2016 - 64.2% | 01/05/2017 - 69% | 2018-05-01
Source
BITC Survey
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | N/A | Target (date)
Planned
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | N/A | Target (date) | Assumptions
The private sector operating in the UK demonstrates stronger engagement in disaster response at a corporate level | Number of businesses showcasing their International Disaster Relief programme in their corporate communications. Milestone 1 will be repeated annually | Planned | Baseline established on number of BITC members showcasing IDR in corporate communications in 2014, by June 2015. (baseline = 24%) | 24% of Businesses showcasing IDR in corporate communication, 2014 | 30% of Businesses showcasing IDR in corporate communication, 2015 | 37.5% of Businesses showcasing IDR in corporate communication, 2016 | 46.8% number of Businesses showcasing IDR in corporate communication, 2017 | N/A | 58.5% showcasing international disaster relief programmes in corporate communications demonstrating a 25% increase year on year against 2014 baseline in businesses: May 2018 | That there are international disasters that warrant business engagement and response. That there is an appetite amongst NGOs and businesses to increase the level of business engagement in humanitarian response.
|  | Achieved |  | 2014-09-01 | 1/5/15 - 43% | 1/5/16 - 57%
Source
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | N/A | Target (date)
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 755,000 - 30,000 dedicated to monitoring and evaluation. 60,000 contingency |  |  |  |  | 755000 |  | 100%
INPUTS (HR) | DFID (FTEs)
DFID CHASE HRG programme staff
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5 | Assumption
Increased insight and understanding for business on how they can best assist during humanitarian emergencies | Development and delivery of annual BITC International Disaster Relief Award (Award) as part of the BITC International Disaster Relief programme (IDRP). | Planned | 0 | IDRP Launch supported with senior DfID representation, Announcement of Award at launch: December 2013 | Workshop for business on engagement in programme and award application process: January 2014 | IDR award winners announced and profiled in July 2014 (following support to applicants, webinars, assessment and judging panel) | 2017 International Disaster Relief Awards held | International Disaster Relief Awards held annually and show a 15% incraease in submissions between 2014-2018. | N/A | That there are international disasters that warrant business engagement and response. That the International Disaster Relief Award will gather significant interest from the private sector.
|  | Achieved |  | 2013-12-01 | 2014-01-01 | 2014-07-01
Source
BITC
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5
| Numbers of best practice case studies identified | Planned | 0 | First set of case studies published: May 2014 (5) | Second set of case studies published: June 2015 (10 new) | Third set of case studies published: June 2016 (15 new) | Fouth set of case studies published: June 2017 (15 new) | 50 case studies available: June 2018 | Publish 15 case studies from awards finalists and BUCIII research
|  | Achieved |  | 5
Source
| Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5
| Publications referencing the business case for business engagement in disaster relief. | Planned | Baseline data from web analyitics reports produced after releases. 2015 baseline - 137 visits | First Insight Paper produced December 2015 and baseline captured | Second Insight Paper produced December 2016 with 150 views by May 2017 | Third Insight Paper produced May 2018 | 167 views of third insight paper | 10% increase in the number of site visits to publications, research and insight papers by June 2018 | 50 site visits to Business Unique Contribution III during the first few months after its launch
|  | Achieved |  | 2014 | 2016-12-06
Source
BITC
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5
| Online guidance for business on engagement with humanitarian community on BITC website (also relates to Output 3). | Planned | Number of users accessing guidance in 2014. - 4 users/month | Develop new IDRP web pages and add revised guidance material: May 2015 | Refresh and populate BITC website with Award winners and case studies: Annually July 2014, 2015, 2016, 2017 | Review and evaluate website content and online guidance: February 2017 |  | 15% increase users accessing online guidance by May 2017, against 2014 figures. | N/A
30% |  | Achieved |  |  | 2014-07-01
|  | Source | [7 empty] | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5 | Assumptions
Partnerships between NGOs and businesses are created | Number of new partnerships between NGOs and business established facilitated by BITC and supported by the "Matching Tool" | Planned | 0 | "Matching Tool" concept drafted by June 2015 | Pilot testing of "Matching Tool" concept by December 2015 | "Matching Tool" first iteration developed and rolled out by June 2016. | Live test (beta testing) of "Matching Tool" in 2017 | 15 new partnerships by May 2018 | N/A | That there are international disasters that warrant business engagement and response. That there is an appetite amongst NGOs and businesses to develop strategic partnerships.
Achieved
Source
Records of partnerships established on BITC database. Depending on where the Matching Tool is on the spectrum from an IT system to active brokering will have implications on how much this will be database build in Year 3 and maintenance thereafter or staff time Year 3-5
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5
| Number of forums and increase in dialogue around importance of engagement and partnerships between NGOs and business. Milestones 2 and 3 to be repeated annually. | Planned | Data on corporate engagement in key humanitarian forums and non BITC dialogue events during 2014 to be gathered by June 2015. | IDRP launch, supported by senior DIFD representative: December 2013 | 4 meetings with NGOs on engaging with business held by December 2015. | After action review of role of business in major disaster response held with businesses and humanitarian partners: September 2015 | Collaboation "roundable" with businesses and their partner NGO's on strategic responses to disasters. April 2017 | Increase corporate engagement and commitment to humanitarian forums and non BITC organised dialogue: May 2018 | Plan 1 event on IDR.
|  | Achieved |  | 2013-12-01
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5
40% |  | Planned
Achieved
|  | Source | [7 empty] | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5 | Assumptions
Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response | Capacity building for business to identify their unique contribution and better understand how it can be used. Milestones 1 , 2 and 3 to be repeated annually. | Planned | 0 | Disaster simulation exercise April 2015 | Seminar/webinar series on key aspects on business unique contribution established by September 2015 | Training for business on key aspects of the online guidance by December 2017. |  | 200 senior practitioners and business leaders engaged in seminars, simulations and training by July 2018 | Start planing BITC blueprint for once the DFID programme ends | That there are international disasters that warrant business engagement and response. That businesses have an interest in furthering their engagament in humanitarain response.
|  | Achieved |  | 2015-04-01
Source
BITC database
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5
30% | Recommendations on role of business in disaster relief put forward to DFID to inform World Humanitarian Summit 2016 preparations (Note: this is additional work not currently included in the project budget) | Planned | 0 | Europe consultation with business held in May 2015 | Paper submitted to DFID with recommendations for WHS agenda planning meeting by end June 2015. | Business leaders encouraged to attend WHS in May 2016. | WHS follow up Workshop with business on the breadth of scope for priviate sector involvement in IDR by end of June 2017 | Recommendations based on business consultation are provided by June 2015 to inform WHS preparations leading to an Incraesed understanding of additional business contributions | N/A
Achieved
Source
|  |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Target (date) | Milestone 5
Achieved
|  | Source | [7 empty] | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)