## Summary page
Part A - Project Data
This section allows you to provide basic information about the project
Project Title/ Description | Beyond WTO Support Programme
Benefiting Country | Vietnam
ARIES ID | 108994
Current Project Officer Name | Tu Thu Hien
Approved Commitment/ Revised Budget (figs only-auto formats) | 4140000
Actual Start Date (dd/mm/yyyy) | 2007-03-15
Planned End Date (dd/mm/yyyy) | 2013-12-31
Spend To Date (figs only - auto formats) | 2025714
Date of Review (dd/mm/yyyy) (final day of the review mission) | 2010-02-03
Joint Funding Organisations (if relevant): | AusAID

## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 108994
ARIES Project Description | Beyond WTO Support Programme (BWTO)
A1: Goal, Purpose, Risk
Goal
Goal statement | To strengthen the government's capacity to manage the economic integration of Vietnam into the global economy & the transition of Vietnam to a socialist oriented market economy
Indicator 1 | Economic growth rate
Milestone for this review (if any) | 6% for 2011
What progress has been made in the period covered by this review? | The GDP growth rate of 2011 was 5.9%, against 6.8% in 2010. This was not a negative outcome as this was mainly due to Government's tightening monetary and fiscal policies set out in Resolution 11, which were necessary in order to reduce inflation, and high trade and fiscal deficits. Government's weak macro-economic management capacity were revealed with inflation souring to 23% in August. They continued to use a number of administrative measures for example in controlling prices, the foreign exchange market (ban of foreign currency trading in black markets), and labour market (decision 46 limiting the use of expatriate labourers). However painful enforcement of Resolution 11, particularly in monetary policies, brought inflation down to 18.13% in December year-on-year, and the trade deficit below 10% of GDP, the lowest in several years. Beyond WTO continued to support Vietnam in improving economic management in the areas of land, State-Owned-Enterprises (SOEs), and price management by making key Government agencies aware of the weaknesses of the current system and recommending certain changes.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Growth was still 5.9% amid severe global economic difficulties and tightening measures. In addition, Government realised the need to improve economic management and has adopted restructuring in three areas: SOEs, public investment and banking as top priorities for 2012 and the medium term. Government has announced that they will continue implementing Resolution 11 to restore fully macro-economic stability.
Goal Recommendation 1 | Continue to monitor macro economic situation, and to link project support to wider policy discussion, e.g DFID's Development Partnership Arrangement annual discussion, the World Bank-led Economic Management and Competitiveness Credit, and the Consultative Group Meetings.
Goal Action Point 1 | Project Officer to monitor growth rate, inflation rate and other macro-economic indicators and Government's economic management policies and signal concerns, if any to the wider DFID and Embassy team for discussion with Government.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Implementation of priority policy actions from Ministerial and Provincial Action Plan to implement Resolution 16 of the Government on sustainable growth post WTO accession.
Indicator 1 | Number of Government priority policy actions within the Ministerial and Provincial Action Plans (PAPs) for integration implemented, monitored and evaluated.
Milestone for this review (if any) | 2 actions implemented in 2011 compared with no actions implemented (baseline)
What progress has been made in the period covered by this review? | A large number of policy actions of ministries and provinces were implemented during 2011, exceeding the milestone of 2 actions. For example WTO centers were established in Ho Chi Minh City and Da Nang, responsibilities for economic integration within Ho Chi Minh City were clarified. A study on WTO impacts was undertaken and a report on the effectiveness of integration focal points was prepared and submitted to Government to inform the formulation of a new Government resolution on integration. In terms of monitoring and evaluation, studies on indexes of integration (assessing the performance of provinces in supporting integration) were undertaken and widely discussed in policy and media. This will help improve provincial support to businesses and in turn contribute to better trade and investment.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Percentage of sex workers in participating provinces reporting consistent condom use with their casual clients in the last month
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | The external economic environment continued to be extremely challenging in 2011. New difficulties emerged in large economies such as the US and Eurozone, making it more difficult for Vietnam to access international markets and maintain high exports and achieve strong Foreign Direct Investment (FDI). In that context, the programme is very important in helping Vietnam to review key economic management mechanisms and develop more market oriented ones.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | The programme independent review which concluded in November 2011 rated all 19 projects supported by Beyond WTO in the first round as strong or satisfactory and contributing actively to building capacity of ministries and provinces in managing economic integration. Vietnam's Global Competitiveness Index increased to 4.27 in 2010 from 4.03 in 2009. It dropped slightly in 2011 to 4.24 but remained well above the target set by the programme monitoring and evaluation framework.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | The programme independent review and institutional review confirmed all 19 projects supported by the programme and delivered under different programme components (captured in Outputs 1 to 5) were highly relevant to Government's priorities set in Resolution 16 on integration.
Purpose Recommendation 1 | Work with AusAid and the Steering Committee to ensure projects supported under round 2 are implemented effectively to support economic integration and market economy orientation.
Purpose Action Point 1 | Project Officer to take stock of progress in first quarter of 2012, identify and then implement measures for ensuring project effective implementation.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 2 | 1.5
Purpose Justification | Policy actions implemented exceed the milestone, so project could have scored 1. However some actions to deal with macro-economic instability were judged as going against market-economy orientation, and we need to see stronger policy uptake from programmme support and recommendation, in key areas such as SOE reform. Government partner needs to inject more pace into project implementation. Hence a score 2.
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1 | Monitor any changes in Government commitment to market orientation
Risk Action Point 1 | Project Officer to monitor and inform DFID and Embassy team for discussion with Government if necessary.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Log frame, DSOs, Cross-Cutting Markers
Log frame revised/needs revision? | Yes
If Yes, why was/is this? | The BWTO was designed to support the Government to implement the Government Action Plan in accordance with Resolution 16. Resolution 16 is going to be replaced with a new Resolution, being drafted with the support from the BWTO. Government plan will likely change accordingly to reflect new priorities and challenges. Hence the programme needs to revise its directions and targets, hence logframe needs revising to reflect new results.
Logframe Recommendation 1 | The logframe needs revising after the new Resolution and Action Plan are in place to ensure the BWTO consistently support Government actions.
Log frame Action Point 1 | Monitor the completion of the new resolution and revise the logframe
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Log frame Recommendation 2
Log frame Recommendation 3
Log frame Action Point 2
Log frame Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Strengthening the institutions of a market economy to help Vietnam attain the recognition as a market economy by trading partners
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 35%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.35
DFID Share revised/needs revision?
If Yes, why was/is this? |  | 1
Original or Revised DFID Share | 42% | 2
3
Indicator 1 | Number of laws, decrees, circulars, decisions and other regulations drafted and adopted to strengthen market economy institutions, particularly in 6 priority areas: (i) Price controls; (ii) Interest rate policy; (iii) Subsidies to State Owned Enterprises (SOEs); (iv) SOE reforms; (v) Land policy and management; (vi) Socialisation of public services. | 4
Is this a Standard Indicator? | No | 5
Milestone for this review (if any) | 2 papers (regulations, decrees…) drafted in 2011. | 0
What progress has been made in the period covered by this review? | Milestone achieved. 19 projects have been successfully implemented, sigfinicantly contributing to the formulation of policies and regulations in the areas of prices, competition, SOE, SME, land management and public services. Key results include: (1) Completion of the report to justify the market economy status of Vietnam in 2010, resulting in recognition of market economy status by South Africa and Belarus and - most importantly - Japan, and significantly bringing Vietnam closer to recognition by the EU and US; (2) study on competitiveness in 10 sectors, providing inputs to improve competition policy framework; and (3) study on land policy in SOE equitisation, directly feeding in to 3 Decrees, on land use fees, on land and water rent, and on transforming SOEs into joint stock companies. All projects have provided good inputs and recommendations, accepted and adopted by the Government in five out of six priority areas. There is no project yet identified on interest rate policy.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 1 | 1 | 1
Impact Weighted Score | 35 | 0.35
Justification for the Score | This output has been achieved. Independent assessment of the first year annual workplan (AWP1) indicated that the expected outputs have been completed. All supported projects under this output produced good results, which are policy recommendations adopted by the Government to feed into new policies and regulations in 5 out of 6 priority areas.
Output 1 Recommendation 1 | Follow up the official issuance of new Laws and policies supported under AWP1 to identify areas for continuous support. Closely monitor the issuance of the new Resolution in Economic Integration to identify priority areas for support in the next work plans.
Output 1 Action Point 1 | Project Officer to invite the Senior Technical Adviser to DFID to discuss programme contribution to policies and priority areas going forward in 2012 in the first quarter of 2012.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | Monitor the implementation of the insitutional review to ensure effective programme operation
Ouput 1 Action Point 2 | Project Officer to work with AusAid and the Steering Committee to ensure effective management and quick delivery of the programme in 2012
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Addressing social and economic consequences of integration for the rural sector
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.3
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share | 42%
Indicator 1 | Number of reports and research papers conducted; databases and information system developed on impacts of integration on labour, gender, environment, poverty and recommendations on measures to mitigate negative impacts adopted
Is this a Standard Indicator? | No
Milestone for this review (if any) | 2 papers conducted compared with no papers conducted in 2009 (baseline)
What progress has been made in the period covered by this review? | Milestone achieved. Several studies have been conducted, including • a study by the Central Insitute for Economic Management assessing the impact of integration including general impacts on rural economy and the poor. • methodology prepared by Ministry of Agriculture and Rural Development (MARD) for applied research on rural development, and its implementation started. The related diagnostic work and dialogue contributed to policies on rural development policy. • Preparation for a study on migration of rural workers to industrial zones and urban areas by Ministry of Labour, Invalids and Social Affairs (MOLISA). BWTO was able to mobilise additional resources from the EC funded project on trade and Australian National University to help improve the project proposal. This study started in late 2011. • Developed a database of regulations on food safety and trade partners of EU, Japan, USA, China, Korea and some ASEAN countries. Now available via sanitary and phytosantiary (SPS) office website.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 2 | 2 | 0.75
Impact Weighted Score | 11.25 | 0.1125
Justification for the Score | This output has been largely achieved. For a score 1, more specific policy recommendations need to be generated and then implemented to generate tangible results for rural communities.
Output 2 Recommendation 1 | Monitor the follow up research by MOLISA and MARD, especially the policy recommendations and how they will be reflected in future policy.
Output 2 Action Point 1 | Project Officer to monitor MOLISA and MARD research, policy recommendations and their implementation, involving the Social Development Advisor
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Strengthening the government capacity for management and coordination of integration
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.3
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share | 42%
Indicator 1 | Number of mechanisms for management and coordination of integration strengthened, evidenced by improved organizational structure in Government agencies, staff trained and improved management systems
Is this a Standard Indicator? | No
Milestone for this review (if any) | Mechanism in 2 agencies improved
What progress has been made in the period covered by this review? | Milestone achieved. BWTO supported projects have delivered concrete results in improving Government capacity on integration management. Key results include • Report on impact of 3 years of WTO informing new resolution on integration. • Report on the effectiveness of international integration focal points prepared and submitted to government informing on-going discussion about restructuring institutional arrangements for managing integration. • Recommendations on restructuring OOG (Office of Government) and clarifying roles and responsibilities of different departments. OOG staff have received related training. • Integration issues developed for inclusion in public administration training courses. Trainers have been trained, and curriculum developed, to sustain training via the National Institute for Public Administration, SME association and some provinces. • Integration index is basis for prioritizing actions to support integration. • Provincial integration index helps planning for provincial level integration reforms.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 3 | 1 | 1
Impact Weighted Score | 15 | 0.15
Justification for the Score | This output has been achieved. There has been good progress in terms of capacity building, awareness raising and training. BWTO supported studies have attracted considerable attention by policy makers and the mass media. Recommendations from these studies are being reflected in proposals to reform the institutional framework for integration. In particular, recommended reform options from BWTO support are expected to be reflected in a new resolution on integration.
Output 3 Recommendation 1 | Monitor the issuance of the new Resolution on integration, focusing on improving the capacity and authority of the agency that will be mandated to coordinate and manage the integration process (now NCIEC)
Output 3 Action Point 1 | Project Officer to contribute to the consultation on the new Resolution.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Prioritised activities in Provincial Action Plans of at least 4 provinces (PAP) implemented
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.15
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share | 40%
Indicator 1 | Number of prioritised activities on provincial integration action plans of at least 4 provinces implemented
Is this a Standard Indicator? | No
Milestone for this review (if any) | 8 activities implemented in 2011 compared with no activity implemented in 2009 (baseline)
What progress has been made in the period covered by this review? | Milestone achieved • BWTO studies produced policy recommendations to address integration issues in provincial level development plans. • Increased awareness and capacity of private sector and officials in selected provinces (HCMC, An Giang and Da Nang) to benefit from integration (achieved via provincial and central level projects). • WTO centres have been established in HCMC and Da Nang, with interest in their services by local businesses and neighbouring provinces (and as a vehicle for support activities by other donors, e.g. EU's MUTRAP). Increased awareness and capacity of private sector and officials in selected provinces to benefit from integration.Initial linkages developed with Le Kuan Yew Institute in Singapore. • Responsibilities for integration within HCMC Peoples Committee have been clarified. • Studies on retail and wholesale distribution in Da Nang as input to report on planning for the sector.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 4 | 2 | 0.75
Impact Weighted Score | 11.25 | 0.1125
Justification for the Score | This output has been largely achieved. Support under BWTO to provinces even goes further than the Provincial Action Plan and expanded to address integration issues of the new 5 year provincial development plan. Some projects have strong and potential sustainable impacts, i.e.. WTO centres, which provides significant services to business and helps increase awareness on integration issues for the community. However, although the result is very positive, only 3 provinces were supported instead of 4 provincies as expected and it is still too early to see successful examples be replicated elsewhere.
Output 4 Recommendation 1 | Make sure examples of successful provincial activities, (i.e. WTO centres) are shared widely to allow replication. Support provinces to develop quality proposals and increase the number of provinces supported under 2012 workplan.
Output 4 Action Point 1 | Integrate success stories and lessons learnt into communication strategy of BWTO.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5 | Multi-donor Trust Fund effectively supports the programme
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share | 42%
Indicator 1 | Key Government seconded officials and recruited staff in place by August 2009 and throughout project implementation period
Is this a Standard Indicator? | No
Milestone for this review (if any) | No
What progress has been made in the period covered by this review? | The project management team has been in place in late August 2009 and continues to support project implementation. There were certain delays in approving sub-projects due to lengthy procedures and other Government beaureaucracy. The Operational Manual has been revised to simplify procedures, and institutional arrangements streamlined.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | Compliance with the financial management and reporting requirements
Is this a Standard Indicator? | No
Milestone for this review (if any) | 70% in 2010 compared with 60% in 2010
What progress has been made in the period covered by this review? | The financial management compliance has been improved through the reduced number of audit recommendations (from 46 in 2007 to 10 in 2008 to 9 in 2009). Among the 9 audit recommendations in 2009, 2 recommendations have been fully implemented in 2010 and remaining 7 recommendations have been largely implemented. After 1 year of operation, the Operation Manual (OM) has shown some weaknesses. Actions have been initiated to revise the OM in 2011 to ensure more efficient and effective monitoring and reporting. The project has developed a draft monitoring and evaluation system and organised periodic monitoring of project activities. The project has also organised a review of BWTO institutional arrangement to address short comings in BWTO management. |  | t
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 5 | 2 | 0.75
Impact Weighted Score | 15 | 0.15
Justification for the Score | This output has been largely achieved. OSC (Office of the Sterring Comittee) is fully staffed and trained. The Operation Manual (OM) has been revised, to reflect necessary changes to facilitate the implementation of the programme, drawing lessons from previous years. The institutional review has been completed, resulting in eliminating the Management Board of the Multi donor Trust Fund, as recommended in the last review. Members of the Steering Committee are also reduced, streamlining the SC structure - which is very welcome. However, the programme is still waiting for an official decision by the Prime Minister to approve these institutional changes.
Output 5 Recommendation 1 | Monitor the Prime Minister's decision on BWTO Steering Committee structure.
Output 5 Action Point 1 | Project Officer to keep an eye on PM's decision and work with AusAid to ensure more effective arrangement in place by mid 2012 at the latest.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3

## A2 Outputs 6-10 N.A
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | December 28, 2011
Impact Weighting (must = 100) | 100%
Total Impact Score | 87.5 | 0.875
Output Risk | High | 1.5
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review | X
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners | X
DFID staff | X
Donor partners | AusAID
Comment here on the Method of Scoring and Scoring Responsibility.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | AusAID and the Government
Working with Partners Recommendation 1 | Ausaid and DFID maintain a very strong partnership, with AusAID acting as the lead donor and DFID closely engaging and providing timely advice. The institutional review has suggested changes to the management structure, but there is a serious delay in making changes happen, mainly due to a major Governtment reshuffle in 2011. Donors must be flexible but persistent in trouble-shooting problems occuring during implementation and pressing for the institutional changes needed.
Working with Partners Action Point 1 | Monitor closely the implementation of the recommendations of the institutional review.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | After major difficulties, the institutional review has recommended streamlining the Steering Committee and abolishing the Management Board of the Multi-donor Trust Fund. This will simplify the management structure and potentially accelerate the decision-making process. The role of the advisory board is enhanced to improve the neutrality and transparency of decision making as well as the quality of projects chosen.
Best Practice / Innovation Recommendation 1 | The Advisory Board should be expanded to include technical and policy experts in various areas to ensure all areas of BWTO will receive technical advice.
Best Practice / Innovation Action Point 1 | Monitor the expansion of the Advisory Board.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Ausaid is the lead donor and Government manages and owns the project. DFID's involvement will now focuss on results-based management. This is timely as the programme has finished the start-up process requiring intensive work. DFID worked closely with the programme in the beginning of the project cycle to agree the results and will focus on monitoring mid-term, detecting problems, helping with implementation where helpful, influecing at senior level where necessary and assessing results (at project end).
Project Management Recommendation 1 | Continue with results-based and strategic management.
Project Management Action Point 1 | Revise the Log Frame to reflect results that are better aligned with Government's new integration resolution and the programme results matrix.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | Government leadership is important, especially in programmes relating to policy reforms as it ensures Government's buy-in. However, the institutional setting is important to ensure there is room for getting inputs and ideas from various other stakeholders to increase the quality of programme results.
Key issues, points of information or additional comments that may be useful for this or other project teams. | The current institutional arrangement of BWTO is still not effective, hence the decision making procedure is very lengthy. The delay in approving the first annual workplan (AWP1) is being repeated in the AWP2. 3 months have passed since the Steering Committee received the project proposals, hence the final list of AWP2 has not been approved. This will result in a foreseeable delay in implementing AWP2.
Other Recommendation 1 | Monitor closely programme progress and raise issues in a timely manner. If programme implementation does not pick up, consider not approving a third round of sub-projects in order to focus on ensuring good implementation and completion of projects in the second round.
Other Action Point 1 | Project Officer to monitor and advise DFID management
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
3355164 | Programme results report, November 2011
3357147 | Evaluation report on Annual Work Plan 1, October 2011
Government's reports on General Statistics Office Website
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | The programme supports policy formulation and reforms and capacity building. Hence it is likely the impacts will be sustainable. For example, improved capacity of the Competition Department will increase the quality of policies and regulations in the area of competition.
Sustainability Recommendation 1
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | Continue to monitor macro economic situation, and to link project support to wider policy discussion, e.g DFID's Development Partnership Arrangement annual discussion, the World Bank-led Economic Management and Competitiveness Credit, and the Consultative Group Meetings. | Project Officer
R2 | 0
R3 | 0
A1: Purpose
R1 | Work with AusAid and the Steering Committee to ensure projects supported under round 2 are implemented effectively to support economic integration and market economy orientation. | Project Officer
R2 | 0
R3 | 0
A1: Risk
R1 | Monitor any changes in Government commitment to market orientation | Project Officer
R2 | 0
R3 | 0
A1: Logframe
R1 | #REF!
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Follow up the official issuance of new Laws and policies supported under AWP1 to identify areas for continuous support. Closely monitor the issuance of the new Resolution in Economic Integration to identify priority areas for support in the next work plans. | Project Officer
R1.2 | #REF!
R1.3 | #REF!
R2.1 | Monitor the follow up research by MOLISA and MARD, especially the policy recommendations and how they will be reflected in future policy. | Project Officer
R2.2 | 0
R2.3 | 0
R3.1 | Monitor the issuance of the new Resolution on integration, focusing on improving the capacity and authority of the agency that will be mandated to coordinate and manage the integration process (now NCIEC) | Project Officer
R3.2 | 0
R3.3 | 0
R4.1 | Make sure examples of successful provincial activities, (i.e. WTO centres) are shared widely to allow replication. Support provinces to develop quality proposals and increase the number of provinces supported under 2012 workplan. | Project Officer
R4.2 | 0
R4.3 | 0
R5.1 | Monitor the Prime Minister's decision on BWTO Steering Committee structure. | Project Officer
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Ausaid and DFID maintain a very strong partnership, with AusAID acting as the lead donor and DFID closely engaging and providing timely advice. The institutional review has suggested changes to the management structure, but there is a serious delay in making changes happen, mainly due to a major Governtment reshuffle in 2011. Donors must be flexible but persistent in trouble-shooting problems occuring during implementation and pressing for the institutional changes needed. | Project Officer
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | The Advisory Board should be expanded to include technical and policy experts in various areas to ensure all areas of BWTO will receive technical advice.
R2 | 0
R3 | 0
Project Management
R1 | Continue with results-based and strategic management. | Project Officer
R2 | 0
R3 | 0
C: Other Comments
R1 | Monitor closely programme progress and raise issues in a timely manner. If programme implementation does not pick up, consider not approving a third round of sub-projects in order to focus on ensuring good implementation and completion of projects in the second round.
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | Project Officer to monitor growth rate, inflation rate and other macro-economic indicators and Government's economic management policies and signal concerns, if any to the wider DFID and Embassy team for discussion with Government. | Project Officer
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | Project Officer to take stock of progress in first quarter of 2012, identify and then implement measures for ensuring project effective implementation. | Project Officer
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | Project Officer to monitor and inform DFID and Embassy team for discussion with Government if necessary. | Project Officer
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | The logframe needs revising after the new Resolution and Action Plan are in place to ensure the BWTO consistently support Government actions.
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Project Officer to invite the Senior Technical Adviser to DFID to discuss programme contribution to policies and priority areas going forward in 2012 in the first quarter of 2012. | Project Officer
AP1.2 | #REF!
AP1.3 | #REF!
AP2.1 | Project Officer to monitor MOLISA and MARD research, policy recommendations and their implementation, involving the Social Development Advisor | Project Officer
AP2.2 | 0
AP2.3 | 0
AP3.1 | Project Officer to contribute to the consultation on the new Resolution. | Project Officer
AP3.2 | 0
AP3.3 | 0
AP4.1 | Integrate success stories and lessons learnt into communication strategy of BWTO.
AP4.2 | 0
AP4.3 | 0
AP5.1 | Project Officer to keep an eye on PM's decision and work with AusAid to ensure more effective arrangement in place by mid 2012 at the latest. | Project staff
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Monitor closely the implementation of the recommendations of the institutional review. | Project Officer
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | Monitor the expansion of the Advisory Board.
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | Revise the Log Frame to reflect results that are better aligned with Government's new integration resolution and the programme results matrix.
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | Project Officer to monitor and advise DFID management
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3