## A1 Goal, Purpose, Risk
Annual Review (reviewed September 2011)
ARIES Project Code | 200274
ARIES Project Description | Deepening Democracy in Nigeria
A1: Goal, Purpose, Risk
Goal
Goal statement | Strengthen Democratic Governance in Nigeria
Indicator 1 | Rule of Law, Transparency
Milestone for this review (if any) | Ibrahim Index for 2011 is 52 for Nigeria
What progress has been made in the period covered by this review? | Index reached 41.1 in 2010, still below the baseline from 2008 of 48.2. Figure for 2011 not available at time of Review, but likely to be much higher. Elections held in April 2011 regarded by Nigerian and international observers (e.g. EU Observation Mission) as the most free and fair Nigeria has ever had (in marked contrast to the worst in 2007). This in large part due to political context, improved performance by INEC led by its highly respected Chairman, Prof. Jega appointed in June 2010, coupled with well targeted support from the international community led by DFID through DDIN and the USAID/DFID Partnership.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Participation and Human Rights
Milestone for this review (if any) | Similar Ibrahim index targets+ OECD SIGI Targets
What progress has been made in the period covered by this review? | Though more women voted in 2011, little progress has been made in increasing female participation as candidates and successful election as legislative members -in fact numbers have declined. Female participation has improved at lower levels.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | The evidence is in the verdict on the April 2011 Parliamentary and Presidential elections-the most democratic Nigeria has ever had and a huge contrast to one of the most corrupt elections ever held in 2007. While democratic gains are still fragile, if the progress made can be strengthened and consolidated during the remaining life span of DDIN until 2015, then there may be grounds for the assessment that democracy in Nigeria has acquired irreversible momentum.
Goal Recommendation 1 | Support to deepening democracy through DDIN must be continued until 2015, focussing on capacity development in key institutions for democracy: INEC; NASS; Civil Society; Political Parties;The Judiciary and Election Disputes; and the print and electronic media.The cross -cutting issue of women's participation must also be tackled successfully
Goal Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Advance key political governance processes and structures
Indicator 1 | Quality of elections
Milestone for this review (if any) | "Mediocre (General elections)" in 2011
What progress has been made in the period covered by this review? | Milestone much more than exceeded. Elections in April 2011, assessed very positively and the "best" Nigeria has ever had (with thepossible exception of those in 1993).This is admittedly starting from the very low base that was the legacy of 2007 elections, but genuine progress was made .
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | %satisfaction with democracy (fairly or very satisfied)
Milestone for this review (if any) | 38% fairly or very satisfied in the Afrobarometer assessments.
What progress has been made in the period covered by this review? | Afrobarometer assessment for 2010 is still not available. There are very strong indications that satisfaction has increased substantially.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | % women in Parliament
Milestone for this review (if any) | 9% for 2011
What progress has been made in the period covered by this review? | No progess -in fact there has been marginal regression. The percentage of women in the National Assembly has dropped from 7% to 6%.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | There is no visible threat to constitutional democracy in formal legal terms.However the riots in the North after the election results were announced, though suppressed, do constitute a potentially recurring threat to peace and stability.The impact on the Project is to underline its importance in strengthening democracy, especially through voter education about how a democratic system works and the reality that there have to be winners and losers.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | The evidence in the acceptance of the genuineness and credibility of the elections by the vast majority of citizens, on the basis that INEC in particular peformed independently ,objectively and fairly. But this achievement remains fragile and could be reversed. Much more development work is required to ensure the Purpose is lastingly achieved.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | A good start has been made over the 15 months effective life of DDIN (June 2010-September 2011). Significant initial progress has been made in four of the five ourputs-the exception being Output 3-political parties and women's representation.
Purpose Recommendation 1 | The imperative need to continue development work over the remaining three years of DDIN.The suggested pattern of activities is already defined and has been clarified in the Report accompanying this Review.
Purpose Action Point 1 | Continuing DDIN implementation
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 1 | 1.2
Purpose Justification | Overall, the purpose level indicators as well as the consolidated output scores point towards 1. Democracy has made a step-change during the review period and DDIN has contributed strongly. Looking ahead strengthening key institutions in the emerging democratic process in Nigeria-the central focus of DDIN-is the main priority over the period until the next national elections in 2015.If these are as free and fair as 2011, then there will be strong grounds for accepting that democracy in Nigeria had acquired "irreversible momentum".
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | No
If Yes, why was/is this?
Logframe Recommendation 1
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision?
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Strengthen the capacity and independence of INEC
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | There is a mistake in the logframe - the total adds up to more than 100%. The weight for output 1 should be 25%
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.25
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share | 28% | 2
3
Indicator 1 (leave blank if standard indicator) | % commissioners and %senior management in INEC substantively appointed | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 80% of Commissioners and 75% of Senior Management substantively appointed | 0
Progress made in the period covered by this review, including numbers. | Overachieved. 100% of commissioner are in place.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | % Implementation of recommendations from UK/US independent mission report
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 50% of recommendations implemented
Progress made in the period covered by this review, including numbers | Overachieved. 70% of recommendations implemented timely, and importantly, the top seven recommendations were all implemented (credible chair, funding, transparency, voter register update, parallel vote tabulation, improved judiciary process, police impartiality)
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Quality and effectiveness of relationship between INEC and political parties and CSOs (proxi, scale 1-5 where 1 is poor and 5 is excellent)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 milestone=2
Progress made in the period covered by this review, including numbers | Overachieved. Consolidated score 3. Doubtful if this has been achieved for political parties where much improvement is required and changes in the membership of IPAC-probably only 1.By contrast, relationships with CSOs have markedly improved eg.NDI for PVT and CSOs running the Situation Room-mark 4.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 1 | 1
Impact Weighted Score | 25 | 0.25
Justification for the Score
Output 1 Recommendation 1 | Continue to support INEC for the remaining three years of DDIN in its efforts to reform all aspects of its organisation,staffing and general performance
Output 1 Action Point 1 | Make sure the DDIN support is aligned with INEC's three year Strategic Plan 2012- 2015. Coordinate closely with other donor support and carefully consider DFID's particular comparative advantages.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Better functioning National Assembly
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | There is a mistake in the logframe - the total adds up to more than 100%. The weight for output 2 should be 20%
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 32%
Indicator 1 (leave blank if standard indicator) | Number of Parliamentary Committees with approved strategic plans
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 six committees have strategic plans
Progress made in the period covered by this review, including numbers | Achieved. The House leadership has a strategic plan (the Speaker's legislative agenda) and 4 committees have strategic plans. In total 24 committees across the House and the Senate have basic strategic plans (which still need work before they are really operational and useful. Constitutional affairs Health; Education;Women and Youth;Agriculture;Finance;Apporpriations;MDGsand Poverty Alleviation;Justice and Human Rights;and the House of Representatives Impementation Committee are amongst the committees DFID supports.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of substantive legislation passed by the NASS (same bill, both Chambers)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 - 5 "substantive pieces of legislation"
Progress made in the period covered by this review, including numbers | Over-achieved. There was a real surge in legislation coming through in late 2010 up to June 2011. The Constitution was changed twice and the election act twice. Importantly, the Freedom of Information Act came through. In total more than 10 substantive pieces of legislation came through.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Quality and effectiveness of interactions between NASS and CSOs/public/Media
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011=2(1=poor;5=excellent)
Progress made in the period covered by this review, including numbers | Score=3. NASS has set up a Civil Society Liaison Office, but there is still potential for considerable improvement in the next three years.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 1 | 1
Impact Weighted Score | 20 | 0.2
Justification for the Score
Output 2 Recommendation 1
Output 2 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Better functioning Political Parties, incl. women representation
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | There is a mistake in the logframe - the total adds up to more than 100%. The weight for output 3 should be 20%
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 40%
Indicator 1 (leave blank if standard indicator) | Number of political parties with approved manifestos, code of conduct and audited accounts
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | There is no numerical target for number of parties with these characteristics in the log frame milestones for 2011.
Progress made in the period covered by this review, including numbers | All the main 5 parties have manifestos and codes of conduct, but none of them have audited accounts. Comparatively, manifestos and behaviour played a bigger role in the 2011 elections, but improve political parties remain a serious challenge in Nigeria.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of IPAC/ PPRRC sessions undertaken (with participation from at least 80% of the 5 major parties)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 Target= 10 sessions
Progress made in the period covered by this review, including numbers | Technically, the target was met, IPAC has held several meetings, but fundamentally IPAC is still not a real forum for discussing strategic inter-party issues. Yet, the role of IPAC in helping INEC to get parties to sign up to the INEC code of conduct was important.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | {
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 2 | 0.75
Impact Weighted Score | 15 | 0.15
Justification for the Score | Party behaviour is changing. For the first time, party primaries were largely non-violent. There were signs of issues-based campaigning and largely, parties and candidates accepted election results (the number of election petitions dropped to less than half. Yet, one of the root-causes of of poor democracy in Nigeria still relate to political parties. Godfatherism still matters INEC is only begining to establish a constructive dialogue with the parties and suffers from not being a member of IPAC and women's representation in NASS appears to have declined between 2007 and 2011.
Output 3 Recommendation 1 | The smaller JDBF recommended should concentrate on political party reform. UNDP should have a comparative advantage among external partners in this sensitive and delicate area, not being identified with any particular country's interests.
Output 3 Action Point 1 | Update logframe milestones on indicator 3.1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Strengthen the role of civil society organisations and Media in promoting and protecting democratic processes
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 43%
Indicator 1 (leave blank if standard indicator) | Number of professionally executed opinion surveys published
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 =9
Progress made in the period covered by this review, including numbers | 10 (6 from NoI polls, 4 from IRI). A range of other surveys were publish. Mostly of reasonable quality.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of community radio stations licensed and operational
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011=4
Progress made in the period covered by this review, including numbers | 6 are operational. Importantly, the Broadcasting act has been revised and now allows community radio stations to operate. The number should increase significantly in the coming years.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Number of people trained/sensitised on elections, rights and responsibilities
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No figure given in the DDIN log frame available
Progress made in the period covered by this review, including numbers | A large number of people were sensitised through the UNDP basket, the IRI youth work and Wangonet's social media networks. Civic Education assessed as having a differential impact.Grass roots CSO opinion in the North thought it inadequate in the election preparatory period and in part blamed this inadequacy for the misunderstanding of the electoral process that led to the riots after the April results were announced. Others felt that civic education had produced a more sophisticated electorate that judged candidates on their merits rather than by the money they paid for votes.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | Quality and effectiveness of CSO work to promote democratic processes (scale 1-5, 1=bad, 5=excellent)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011=3(1==poor;5=excellent)
Progress made in the period covered by this review, including numbers | Score=4. CSOs have undoubtedly made a major impact already on key aspects of the electoral process through DDIN support The "Situation Room" and The "PVT"system played influential roles, run by CSOs.Civic education was enhanced by CSO involvement.
No
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 1 | 1
Impact Weighted Score | 25 | 0.25
Justification for the Score
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5 | Policy support and coordination maximised
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 10%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.2
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 100%
Indicator 1 (leave blank if standard indicator) | Quality and effectiveness of international community and donor messages on elections and deepening democracy issues (score 1=bad, 5=excellent).
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011= 4
Progress made in the period covered by this review, including numbers | Score=4. The donor community undoubtedly were very influential in the elections.Influence came from a combination of financial and technical support , united public statements by donors and diplomats on key election issues and the creation of general awareness in Nigeria amomg politicians that the world was intently watching Nigeria and its elections for freedom and equity
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Debate on international and African perspectives on best elections and deepening democracy practices
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 "2-3 events organised and led by senior researcher,elder statesman or other dignitary".
Progress made in the period covered by this review, including numbers | 2 DFID funded events. There was limited time in the truncated run-up to the elections that only really started with Professor Jega's appointment as INEC Chairman in June 2010 for the appropriate meetings to be organised and the results digested. September 2011 was still too early after the elections for a full range of such international meetings to be held.Nonetheless two international events had been held:Prof Jega had addressed a conference organised by the Malaysian Commonwelath Studies Foundation in Cambridge UK on"The 2011 Elections and the Consolidation of Democracy in Nigeria in August 2011;and INEC was beginning to conduct its own comprehensive review of the 2011 election process with a view to identifying the detailed reforms required before 2015. Within Nigeria, a number of senior politicians (incl. a former Canadian Prime Minister and a range of retired African presidents visited and had events in various fora). Two were funded by DFID (implemented by NDI).
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 | 1 | 1
Impact Weighted Score | 10 | 0.1
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-12-19
Impact Weighting (must = 100) | 100%
Total Impact Score | 95 | 0.95
Output Risk | Medium | 1.75
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review | X
DFID staff review
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner | X
National non-Government partner | X
Independent consultant | X
Donor partners | X
DFID staff | X
Donor partners | USAID, UNDP, EC, Canada
Comment here on the Method of Scoring and Scoring Responsibility. | Most data is publicly available. Where proxi indicators or qualitative data has been used, the scoring assessment has been in consultation with relevant stakeholders and independent experts.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | The need to be flexible and adjust to the evidence of performance and non-performance by partners. This accounted for the decision to switch £16m of the DDIN budget from the UNDP JDBF to the USAID/DFID Partnership. The JDBF could not overcome its management difficulties., nor agree to concentrate on areas where it had a comparative advantage.
B
Working with Partners Recommendation 1 | Partners should be realistic about their advantages in support and comparative weaknesses.
Working with Partners Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | The provision of a comparatively small Startegic Fund to fund experimental inovations was invaluable and will continue to be vital in the next three years of DDIN
Best Practice / Innovation Recommendation 1
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Intensive hands on management by the DFID Governance Adviser, supported by the DFID Programme Officer for DDIN proved essential in providing appropriate support at the right times.This project management provision should be continued. In the remaining Programme life -span
Project Management Recommendation 1
Project Management Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | It is far too early to judge the sustainability as DDIN still has three years to run. Evidence so far however is encouraging. What is required is a period of stability with the leadership of INEC to be continued by the current Chairman so that the reform programme required can be implemented and consolidated.
Sustainability Recommendation 1 | DDIN to continue at its present scale and with the same broad objectives.
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | Support to deepening democracy through DDIN must be continued until 2015, focussing on capacity development in key institutions for democracy: INEC; NASS; Civil Society; Political Parties;The Judiciary and Election Disputes; and the print and electronic media.The cross -cutting issue of women's participation must also be tackled successfully
R2 | 0
R3 | 0
A1: Purpose
R1 | The imperative need to continue development work over the remaining three years of DDIN.The suggested pattern of activities is already defined and has been clarified in the Report accompanying this Review.
R2 | 0
R3 | 0
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Continue to support INEC for the remaining three years of DDIN in its efforts to reform all aspects of its organisation,staffing and general performance
R1.2 | 0
R1.3 | 0
R2.1 | 0
R2.2 | 0
R2.3 | 0
R3.1 | The smaller JDBF recommended should concentrate on political party reform. UNDP should have a comparative advantage among external partners in this sensitive and delicate area, not being identified with any particular country's interests.
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Partners should be realistic about their advantages in support and comparative weaknesses.
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | 0
R2 | 0
R3 | 0
Project Management
R1 | 0
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | DDIN to continue at its present scale and with the same broad objectives.
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | Continuing DDIN implementation
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Make sure the DDIN support is aligned with INEC's three year Strategic Plan 2012- 2015. Coordinate closely with other donor support and carefully consider DFID's particular comparative advantages.
AP1.2 | 0
AP1.3 | 0
AP2.1 | 0
AP2.2 | 0
AP2.3 | 0
AP3.1 | Update logframe milestones on indicator 3.1
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3