DEEPENING DEMOCRACY IN NIGERIA
(DDIN: 2010-2015)

Annual Review 2010-2011
and
SUGGESTIONS ON PRIORITIES AND PROGRAMMES
For
2012-2015

REPORT OF A REVIEW

16 – 27 SEPTEMBER 2011

Dr GARTH GLENTWORTH
Dr KWADKO AFARI-GYAN
ABUJA
20th December 2011

CONTENTS Pages
EXECUTIVE SUMMARY		2-5
1 / 2.	INTRODUCTION / DDIN IMPACT SO FAR / 2.1 Purpose / 2.2-2.6 Outputs 1-5	6 / 7-10
3.	CONTEXT AND CHALLENGE	11
4.	INDEPENDENT NATIONAL ELECTORAL COMMISSION / 4.1 Background / 4.2 Possibilities	11
5.	NATIONAL ASSEMBLY / 5.1 Background / 5.2 Priorities	13
6	CIVIL SOCIETY / 6.1 Background / 6.2 Priorities	14-16
7.	POLITICAL PARTIES / 7.1 Background / 7.2 Priorities	16-17
8.	ELECTION TRIBUNALS AND THE JUDICIARY / 8.1 Background / 8.2 Reform Possibilities	17-18
9.	MEDIA	18
10.	WOMEN’S ADVANCEMENT AND PARTICIPATION / 10.1 Background / 10.2 Possibilities	18
11.	DELIVERY MECHANISMS / 11.1 Background / 11.2 UK Strategic Fund / 11.3 US/UK Partnership Agreement / 11.4 UNDP Joint Donor Basket Fund / 11.5 Conclusions	18-20
12.	RISKS	21
APPENDICES:
1.	VFM OBSERVATIONS	23
2.	TOR: ANNUAL REVIEW OF DDIN	24-27
3.	ITINERARY AND CONTACTS	28-30
4.	ABBREVIATIONS	31

 EXECUTIVE SUMMARY

DDIN impact so far

(i)Progress made towards the DDIN Purpose “Advance key political governance processes and structures” has been considerable but is stilll fragile. DDIN has been one of the major contributory elements in the successful run up and holding of the 2011 elections, supporting the key element in that success-the appointment of Professor Jega as Chairman of the Independent National Electoral Commission in June 2010. Professor Jega provided INEC with independence respect and credibility that were very damagingly absent before.

(ii) DDIN’s “process” characteristics-the ability to be flexible in activities while retaining the commitment to Goal and Purpose was well served by movement of funds between DDIN’s three funding mechanisms: the UNDP managed Joint Donor Basket Fund; the USAID/DFID Partnership Arrangement; and the DFID Strategic Fund. INEC have built-up a clear picture of the different strengths of the three mechanisms and would wish to retain them in future.

(iii) Evidence of progress in DDIN’s Output 1 “Strengthen the capacity and independence of INEC” was Professor Jega’s decison to postpone the date of the elections, in turn based on reports from the Strategic Fund supported CSO initiative “The Situation Room”. Similarly, confidence in INEC’s impartial reporting of election results was strengthened by the results produced by the “Parallel Vote Tabulation” System funded by the USAID/DFID Partnership.

(iv) INEC now has the confidence and capacity to conduct its own comprehensive review of the electoral process and reform requirements in the future. Two areas where progress has not been made by INEC are in its relationships with political parties and with the Judiciary in electoral disputes.

(v) The Strategic Fund’s support for the “Policy and Advisory Centre’s”(PLAC) work with the National Assembly(NASS) under Output 2 “Better Functioning National Assembly” has produced plans for a Constitutional Review, advice on the formation and work programmes of new parliamentary committees and a number of training and induction programmes.
.
(vi) Limited progress has been made so far by DDIN in its Output 3 “Better functioning political parties including women’s representation”. Parties have are only gradually changing their closed elitist self-serving memberships and modes of operation. More women voted in 2011 but for fewer women candidate successful elected. Deep seated problems remain: traditional views of women’s roles in society; male dominated political behaviour patterns ; lack of party sponsorship and funding.

(vii) DDIN has had a variety of impacts on the huge and diversified CSO Sector under its Output 4 “Strengthen{ing} the role of CSOs and Media in promoting and protecting democratic processes”. Civic education programmes seem to have had different impacts on different groups and parts of the country ranging for inadequacy to raising voter levels of sophistication in assessing candidates, Strategic Fund support for two CSOs “Enough is Enough “and “Wangonet” has made progess in mobilising young middle class Nigerians to take an active interest in politics. Very substantial JDBF funding was judged by several leading Nigerian CSOs to be too restrictive in Terms of Reference to be properly utilised.

(viii) This Review Team did not fully assess the impact of press, radio and television on the electoral process. Social Media (SMS, Facebook and Twitter) are beginning to have an impact but only on a small scale when compared above all with radio.Generally the media role has benefitted from INEC’s greater openness encouraged by the Strategic Fund.

(ix) The different strengths and weaknesses of the three funding mechanisms under DDIN (JDBF;USAID/DFID Partnership.DFID Strategic Fund) have had to be utilised flexibly to improve effectiveness and VFM under Output 5 “Policy support and coordination maximised”. The JDBF proved to have major limitations in its management-most notably an absence of strategy and work plan and an unquestioning, purely reactive pattern of activity. This had two results: major switching of DDIN resources to the USAID/DFID Partnership (£4m. instead of £20m through the JBTF with £16m.spent through the Partnership); but retention of INEC confidence in the JBTF because of UNDP’s willingness to respond without question to the Commission’s requests.

Context and Challenge

(x) Over the four years to the next Federal Elections in 2015, the key challenge for Deepening Democracy in Nigeria (DDIN) is to maintain and consolidate the popular belief that, in Nigerian democracy, individual votes count and electoral participation is essential. If faith in democracy is not strengthened, Nigeria will see increased levels of fragility and tension along ethnic and religious faultlines.

Future Priorities

(xi)The Independent National Election Commission (INEC) is the most important focus of support. DDIN will need to wait to be asked by INEC but could offer a range of support: in electoral process and design factors; in election legislation and constitutional reform particularly designed to strengthen the independence of the Commission and its Chairman’s control over personnel at central, regional and local levels; for capacity building in INEC itself; in creating the new bodies recommended by the 2009 Uwais Commission- in particular the Political Parties Registration and Regulation Commission and the Election Malpractices Commission; in building-up training and research capacity in the Commission’s Electoral Institute; expanding INEC’s efforts to develop appropriate civic education throughout the country; to improving INEC’s own capacity to prosecute electoral offenders if it chooses to do so; to strengthening election security ;over the longer term revising electoral boundaries; and generally in improving relationships with other key actors in the election cycle.

(Ixii) DDIN should maintain its connection with the National Assembly. There should be three main areas of potential support: Constitutional and electoral legislative reform, particularly focussed on building up the legal independence of INEC; increasing the Assembly’s capacity to hold the Executive to account, especially through the work of the two chambers (Senate and House of Representatives) committees; and strengthening Assembly interaction with CSOs through the functioning of the Assembly CSO Liaison Office and a variety of means of communication including the rapidly growing “Social Media”.

(xiii) The major role played by Civil Society in the 2011 elections creates a strong case for continuing and expanding DDIN support. Two categories of CSOs should be considered :
---strategic CSOs which play and will play vital roles in institutional capacity building and in major issues in the elections, such as PLAC with the National Assembly and NDI in Parallel Vote Tabulation;
---a large and growing range of state and local CSOs with variety of functional roles, but all with the capacity to play a part in the electoral process and represent citizen concerns and problems to the executive and legislative branches of government.

With the first category, DDIN should enter into three year contracts with strategic CSOs covering a range of potential capacity building activities: institutional restructuring and innovation; training of key cadres and officials; drafting of key documents such as electoral reform legislation; and pilot activities designed to implement innovations. Whenever possible in the next three years of DDIN, Nigerian CSOs should be engaged as they now have the capacity to play most though not all the roles previously played by their international counterparts. There are still a few areas such as reporting on votes and results where an international presence may be necessary to prevent allegations of manipulation and bias.

There are two pre-requirements before supporting the second category of CSOs: more information about the numbers and capabilities of CSOs in remote areas; and an answer to the question which the Review Team could not answer-should CSO support from DDIN be concentrated in the least developed regions where the needs are greatest but the impact most problematic?

Where this type of CSO exists in sufficient numbers with real capacity, they should be supported in: increasing involvement in basic civic education; monitoring the performance of key official actors in the electoral process; spreading the message of ”value orientation ”;and generally improving communications between governed and governments.

(xiv) Nigerian political parties are probably the most difficult area in which to achieve reform and also the most sensitive and controversial for external involvement such as DDIN. They are vitally important for the future of democracy in Nigeria. There are three priorities which seem now to be possibilities for DDIN support:assistance in establishing a clear legal framework for the organisation and conduct of political parties; helping INEC and political parties create and successfully maintain a forum for dialogue in both the national capital and in the states; and funding activities designed to build up understanding of the requirements of genuine party democracy.

(xv) The fact that the number of electoral cases has come down between 2007 and 2011 from 2600 to 1000 does not disguise the fact that there are major reform needs in Election Tribunals and the Judiciary, when the latter deals with electoral complaints. Reform possibilities that could be supported by DDIN are: the creation of the Election Malpractices Commission recommended by the Uwais Commission; broadening the legal definition of ‘admissible evidence’ in election petitions ; funding the use of ADR techniques; and generally encouraging CSOs to exert pressure for the resolution of cases. (NB: DDIN may not be the appropriate DFID programme to be involved here; J4A may be more suitable.)

(xvi) With the exception of the Social Media, this review did not really cover the Media though their role was noted as markedly ‘improved’ between 2007 and 2011. One area for DDIN may be to encourage the use by the media of the recently passed Nigerian Freedom of Information Act which is not currently being utilised.

(xvii) Women’s Advancement and Participation has been a disappointing story in both 2007 and 2011 elections, with numbers of both candidates and successful elections down. There are a large number of formidable obstacles to overcome in reversing this trend and the Review Team has not come up with any promising new initiatives for DDIN Seminars should be continued to encourage and train women candidates, as should the body “Gender for Affirmative Action” but neither has produced the results hoped for so far.

(xviii) During the course of the Review, it became clear that the right Delivery Mechanisms - the right method and timing of support delivery-was as important as the technical content. There are three alternatives in supplying support through DDIN: the UK Strategic Fund; US/UK Partnership Agreement; and the UNDP Joint Donor Basket Fund (JDBF). Each as its advantages and disadvantages, not least the fact that the Chairman and Staff of INEC like the range of choice available.

The conclusions of the Review are the following:

---The Strategic Fund should be enlarged, managed directly by DFID Nigeria and not through a service provider and used for comparatively small project funding (eg of the strategic CSOs such as PLAC and CDD),even though collectively the expenditure may be considerable.
--- The Partnership Agreement should be much smaller than it was in the run- up to 2011 and used to fund continuing International NGOs ie IFES,IRI and NDI, but on condition much more effort is made to transfer expertise to Nigerian counterparts.
--- The JDBF should both be much smaller and more targeted, the UK contribution no more than £3 million over the three years and focussed on Basket Fund support to the reform of political parties.

(xviv) The following is the Review Team’s assessment of Key Risks in the continuation of DDIN: departure of Prof. Jega from the Chairmanship of INEC, currently almost a killer risk; reversion of the National Assembly to its old discredited ways of working, losing respect and credibility; growth of violence to an extent that at worst threatens the integrity of the state or destroys popular belief in democracy; failure to develop effective delivery mechanisms for DDIN and its components; competition between donors becoming disruptive of each other’s efforts; and a backlash against donor interference in the democratic sector is whipped up by sections of the Media or political parties and causes programmes to have to be curtailed or stopped.

1.	INTRODUCTION

  1. The Deepening Democracy in Nigeria (DDIN) Programme was approved in 2009 with a budget of £35 million and approved in April 2010 in the run-up to the Nigerian Federal Presidential and National Assembly elections in April 2011. What can be called Phase 1 of DDIN lasted until the elections and substantially contributed to the general verdict that these elections were the “best” that Nigeria had had under civilian rule[1]. DDIN lasts until 2015 (a five-year period) and it was felt by DFID Abuja that a review of what had happened so far and an effort to identify priorities for at least the next three years (2012 – 2014) would be useful. Obviously, the nature of activities would change after the Federal elections, even though there are to be a sequence of governorship elections over the intervening years until the next Federal elections in 2015.
    [1] With the possible exception apparently of the 1993 elections.

  1. In this context, DFID Nigeria engaged Electoral Reform Internal Services (ERIS) to provide a two-person consultancy team to conduct a review of DDIN: Dr Afari-Gyan, long-serving Chairman of the Ghana Electoral Commission and Dr Glentworth, an experienced retired Senior Governance Adviser in DFID who had been involved in a number of democracy projects in different countries. They visited Nigeria in mid-September 2011 to conduct a range of interviews with stakeholders in DDIN: the Independent National Electoral Commission (INEC); members of the National Assembly a large range of civil society organisations; British diplomats and DFID officials; other aid agencies involved in democracy strengthening; and complementary aid projects such as “Justice for All” (J4A) focusing on strengthening the Judiciary and Police in Nigeria. Most contacts were in Abuja but visits were paid to Kaduna and Lagos to add regional perspectives to the Federal level. The Review Team would like to thank all their interlocutors for the time devoted to discussions and for the full and frank nature of these meetings– which obviously are not quoted verbatim here.

  1. This Report contains the findings and suggestions of the DFID Review Team. However, late 2011 seems to be the season for reviews of democracy in Nigeria! This Review will have to be considered with the conclusion of several reviews of post-election priorities and possible activities being conducted by other aid agencies. INEC is itself conducting a comprehensive review which maybe available by the end of October 2011; UNDP is embarking on a series of reviews of its “Democratic Governance for Development” (DGD) Programme financed by the Joint Donor Basket Fund (JDBF); USAID is expecting a review team in Nigeria in October to look at its programme; and the National Democratic Institute in Nigeria, one of the principal contractors used by the USAID/DFID Partnership in the run-up to the elections is also reviewing its work programme. Obviously, eventual priorities for the three years in the lead up to the 2015 elections and specific activities will have to take into account the results of this range of reviews. Donor coordination is essential in aid to democracy strengthening and elections.[2].
    [2] The assumption has been made that the three years 2012 to 2014 are effectively Phase 2 of DDIN. Phase 3, if there is one, will consist of the immediate preparatory support activities in 2014/15 for the 2015 Federal Elections.

  1. The first section of the Report reviews progress made in the run-up to the April 2011 Elections and in particular the impact made by DDIN in terms of the Outputs defined in its Log Frame. The Report then concentrates on future priorities for support in the three years from 2012 to 2014. A summary of the key challenges to democracy in Nigeria, leads into consideration of capacity development needs that should be supported in the key institutions in the Nigerian elections: INEC; National Assembly; Civil Society ; Political Parties; and Election Tribunals and the Judiciary. Finally, a number of key issues involved are tackled separately: women’s advancement and participation in the democratic process; the management and delivery of support to the various institutions; and the risks involved in the continuation of DDIN.

2 DDIN IMPACT SO FAR

2.1 DDIN Purpose “Advance key political governance processes and structures”

2.1.1 Progress made towards the Purpose has been considerable but is still fragile and cannot be considered yet as having “irreversible momentum” as some protagonists claim in Nigeria.The election process was immeasurably better in 2011 than in 2007 or 2003.[3] Since its launch in June 2010,DDIN on its own and as the largest support component in the Joint Donor Basket Fund(JBTF) funding for the UNDP managed “Democratic Governance for Development”(DGD) Programme was a major contributory element in the successful run-up and holding of the elections, supporting the key to tah success-the appointment of Professor Attahiru Jega as Chairman of the Independent National Electoral Commission(INEC) in June 2010.Professor Jega provided INEC with independence, respect and credibility sadly lacking previously and began the process of Commission reform by bringing in a small number of very able external advisers.DFID support had three components: the Joint Donor Basket Fund through DDIN: involvement in DGD; a bilateral funding partnership with USAID; and its own Strategic Fund. The two latter components became increasingly important and influential as limitations in UNDPs management of the JDBFand the deployment of its funds became clearer.in the run up to the elections.[4]
[3] However,the Mo Ibrahim Index for Nigeria used as a milestone in the DDIN Log frame was targeted as 50 for 2010(the 2011 figures are not yet available) but was 41.1 and 41st in the ranking of African countries.The verdict on the 2011 elections should have markedly improved this ranking...
[4] £20 million for the JBTF and £1 million for the DFID Strategic Fund in June 2009 eventually became by April 2010 £4 million for the JBTF,£16 million for the partnership withUSAID and £1 million for the DFID Strategic Fund.

2.1.2 This ability to be flexible and exploit the “process“ characteristics built into DDIN proved invaluable. DFID was able to respond quickly and effectively to both preliminary and well thought out requests from INEC.The time devoted to supporting the election process by the Governance Adviser involved in the DFID Abuja Office was a further key in the successful impact, allowing the development of in depth knowledge of the politics and personalities involved and the establishment of close personal relationships with the the INEC Chairman’s key advisers..

2.2 Output1: “Strengthen the capacity and independence of INEC”

2.2.1 The impact of Professor Jega personally on the election process cannot be over estimated. But his effectiveness also depended vitally on his ability to call up support and expertise from the US/UK Partnership and the DFID Strategic Fund. What consolidated his vitally important reputation for guaranteeing INEC independence in the elections was his decision on postponing the election date because the practical arrangements were not in place.INEC’s assessment of preparedness was to a considerable extent based on the reports of the “Situation Room” –a CSO entity funded by the Open Society Initiative for West Africa(OSIWA) and the DFID Strategic Fund, setting up a monitoring system on elections and their preparations throughout the country.

2.2.2 Similarly, the credibility of INEC’s impartial reporting of election results was improved by checking against the results being reported by the “Swift count” or “ Parallel Vote Tabulation”(PVT) system, organised by NDI and funded by the USAID/DFID Partneship. This was a comparatively small initiative when compared with eg.the massive voter education programme but played a vitally important role.

2.2.3 Initial capacity development and improvements in efficiency in INEC brought about by a combination of the new Chairman and his advisers and external support built sufficient confidence and expertise for INEC to hold it own comprehensive review of the whole electoral process in late 2011.This was to cover fundamentals: reforms required in electoral legislation; changes in the powers and reporting arrangements for the INEC Secretary; decentralisation-INEC’s relationship with the Regional Electoral Commissioners(RECs).and Local Government Authorities’ Election Teams..

2.2.4 INEC itself built up a clear ideas about the relative strengths of the JDBF and the British Strategic Fund.The former was very useful for immediate logistic support eg.the training needs that emerged unexpectedly in the new voter registration system.The latter was more useful strategically eg.in introducing innovations from other electoral systems.

2.2.5 There are two areas where progress has not been made.One was in INEC’s relationships with political parties.The Inter Party Advisory Committee (IPAC) bringing the main parties together still does not include INEC representation.The second is the continued politicisation of the Judiciary and its poor relationship with INEC in resolving electoral disputes.

2.3 Output 2: “Better functioning National Assembly(NASS)”

2.3.1 Eighty per cent of the Assembly members were new after the April 2011 Elections so some of the earlier work with MPs has not born fruit. However, DFID’s Strategic Fund has made some high impact interventions .Chief among these has been the funding of the Policy and Advisory Centre (PLAC) led by its Executive Director in its work with the Assembly.This has a number of facets: helping plan and begin a Constitutional Review covering such vital issues as citizenship and indigenes,state creation and presidential terms ;advising on the formation of new parliamentary committees and defining their agendas;training committee clerks; creating committee research capacity; and holding induction seminars for new elected members on committee functions.

2.3.2 The new NASS undoubtedly will have a better relationship with Civil Society, as DDIN has helped the Assembly set up a Civil Society Liaison Office. Efforts have also been made to change the image of MPs among the public –not millionaire funders of school fees, wedding and funeral expenses but actual representatives of constituent interests.These have still to bear fruit and are not helped by public knowledge of the huge salaries and expense accounts Assembly Members and Senators vote themselves.

2..4 Output 3:”Better functioning political parties Including womens’ representation”

2.4.1 In spite of party development having been a major focus of NDI/IRI activity, supported by the DFID/USAID Partnership,this is the element of DDIN where least progress has been made. Apart from the sensitivity of foreign involvement in this area, it has to be recognised that the DDIN operational life -span from mid 2010 has been far too short to change deeply entrenched patterns of party behaviour and the extent of women’s representation in Parliament. Much more time is required.

2.4.2 .Other than cosmetically,political parties have not changed their patterns of membership and operations.They remain predominantly closed cliques dominated by small elites.There is little evidence of policy debate and its influence on votes. Support is generated by personalities and their followers,payments for votes and especially .in the North in the 2011 elections, religion(PDP for Christians and CPC for Moslems). ‘Win at all costs’ is still the dominant behaviour pattern so great are the rewards of political office. Codes of conduct exist on paper but are not being observed An Inter- Party Advisory Council(IPAC) has been created to foster inter- party dialogue but has not modified party behaviour and suffers from not including INEC in its meetings.There are still too many small parties without any real membership base even at elite level. INEC is trying to apply standards in party registration, but not yet with very much effect.

2.4.3 Women voted in much greater numbers in 2011 but this was not reflected in female candidates and their success in getting elected.Fewer women came forward and were elected in 2011 than in 2007.The reasons are complex and unclear: traditional views of women’s roles ;the dominance of aggressive male behaviour in electioneering ; decision-making dominated by closed ‘smoke filled rooms’; lack of financial support and sponsorship by dominant political parties; and women’s disinclination to get involved in Nigeria’s type of political environment.DDIN has not had much success yet in this environment.

2.5 Output 4: “Strengthen the role of CSOs and Media in promoting and protecting democratic processes”

2.5.1 DDIN has had a variety of impacts in the huge and diversified CSO sector in Nigeria.
.The record of CSOs in civic and voter education in the run-up to the elections was assessed very differently by different groups contacted by the Review Team.. Grass roots CSOs in Kaduna felt that civic education(not differentiating between INEC supported programmes and those of DDIN [5]) had been patchy and inadequate, contributing by omission to the riots after the election results were announced.An alternative reaction was that civic education had made voters much more sophisticated in 2011, in that they took the money from candidates but did not feel any obligation to vote for them; instead assessing candidates much more on their merits.. The considerable CSO funding (grants of $200000 to $6million) offered by the JBTF for civic education and womes’ involvement was felt by several Nigerian national CSO leaders to be too rigid and restrictive in its terms of reference to be adapted and useful in different areas, but views were divided..
[5] It needs to be born in mind that in INEC’s own estimate, only 15% of INEC funding for the elections came from aid sources.

2.5.2 The DFID Strategic Fund was able to fund three initiatives involving social media and CSOs that had a relatively limited impact but show great promise for the future.The “Situation Room” has already been discussed under Output 1 above. Apart from its direct contribution in reporting, it also pioneered a pattern of cooperation among CSOs that had not really been in existence before. DFID supplemented the initial funding from the Macarthur Foundation for “Enough is Enough”, a small CSO based in Lagos and Abuja using not only seminars but SMS, Twitter and Facebook to involve essentially young middle -class Nigerians in the election process. A second CSO “Wangonet” produced a CD presentation designed to alert Nigerians to the malpractices involved in election rigging, such as manipulating the location of voter registration centres and voting stations to favour supporters of incumbents.

2.5.3 The impact of conventional media(press radio and television) on the elections was not really assessed by the Review Team.. Therefore only two comments. the spread of Social Media.is rapid but still limited even with mobile phones and SMS; radio above all remains the main method of information gatheriing for the mass of the population.There is considerable evidence that media coverage of the elections improved significantly because of INEC’s greater openness, encouraged by DFID’s Strategic Fund.

2.6 Output 5:”Policy support and coordination maximised”

2.6.1 The three components of DDIN had different strengths and weaknesses and Phase 1 up to the elections saw a considerable shift in resources between them..The in –depth involvement in the planning, management and evaluation of activities by the DFID Adviser was invaluable in creating these transfers to maximise combined impact and VFM. As mentioned earlier(footnote p. ), initial allocations of £20m. to the JBTF and £1m.to the DFID Strategic Fund had become by April 2011 £ 4m. to the JBTF, £16m. to the DFID/USAID Partnership and £1m. to the Strategic Fund.

2.6.2 The JDBF had limitations which could not be overcome:lack of a strategy and work plan ; ad hoc purely reactive decision-making; gaps in the staffing of its management team; and poor communications with other aid donors leading to a break down in trust and coordination. This set of characteristics had very different results .It accounted for the main shift in resources in DDIN -to the DFID/USAID Partnership and CEPPS-the combination of NDI,IRI and IFES..It made the innovation and experimental funding available in the Strategic Fund even more important.But at the same time, the willingness of UNDP and JBTF to respond unconditionally on a short term basis to INEC’s requests allowed them to retain the confidence and good will of the Commission.

2.6.3 INEC came to see itself benefitting from the contrasting strengths of the three funding mechanisms and to be loath to lose any of them which it could use in different ways for different needs.

3.	CONTEXT AND CHALLENGE

3.1 In this context,,the challenge involved in democratic consolidation in Nigeria in the future should be clear. Nigerians have just experienced the “best” election ever in the popular view after the “worst” election ever in 2007. There is as a result some measure of euphoria and of self-satisfaction and a feeling that a corner may have been turned.

3.2 The challenge is to keep up this positive momentum over the next four years. The danger is that optimism transforms into frustrations, cynicism and even anger with the democratic process and `government’ if `things’ do not improve. Ideally, improvements will be tangible – much enhanced youth employment opportunities and an increase in living standards for the majority of the population. But even if these are not forthcoming ,the continuing belief that votes mean something important must be maintained– that the President and National Assembly are listening to citizen demands and doing something about it, that political parties are actually taking into account the interests of rank and file support.
3.3 Maintaining faith in the democratic process is the priority for DDIN in the period up to the 2015 elections. These will be the real test. If expectations are not met, Nigeria may lose faith with democratic government, at worst possibly slipping into anarchy and violence – signs of which are already there, or dividing in practice if not in law along the growing North-South divide, or being subjected to another military takeover on the grounds of the incompetence of civilian democratic government.

4. FUTURE PRIORITIES: INDEPENDENT NATIONAL ELECTORAL COMMISSION

4.1 Background

4.1.1 It is generally agreed in Nigeria that INEC’s reputation and to a lesser extent performance have been transformed since the appointment of Professor Atahiru Jega as Chairman in June 2010. Prior to Jega’s chairmanship, INEC had lost the confidence of the Nigerian people, believed to be a tool of the Presidency and subject to allegations of corruption. Professor Jega has fundamentally improved the image of INEC among the public and to a lesser extent its performance by bringing in highly competent advisers and new reputable commissioners, but above all by the reputation and respect attributed to him personally. He is regarded as very much his own man, not subject to Presidential pressure and able, for example, to postpone the timing of the elections when he decided that effective arrangements were not in place. This personalisation has of course both advantages and disadvantages: advantages in his ability to take decisions and force reforms through; dangers of demoralisation and institutional collapse if he were to be incapacitated or removed (by resignation or dismissal) from the Chairmanship.

4.1.2 A strong and effective INEC institution is the response required and this will take at least the three years of DDIN to achieve if not longer. INEC has been in existence for many years without fundamental reforms and the task is immense. A start has been made under Professor Jega’s leadership and will be carried forward by the comprehensive review of INEC due to be finished by the end of October 2011 and the development of an INEC Strategic Development Plan until 2015.

4.1.3 While DDIN must support the process of reform in the interests of consolidating democracy in Nigeria generally, DFID must first of all wait to be asked for assistance. Professor Jega and his team have clear ideas of the relative merits of UNDP and the JBTF vis-à-vis bilateral support from DFID and for example USAID. They see both sources of support as important but with different characteristics and they wish to utilise both when they deem them appropriate.

4.2 Possibilities

4.2.1 The potential range of UK support set out below is very wide, but a comprehensive or open-ended request is unlikely. In some cases there will be a need for a quick response; but in others reforms will be spread over a considerable period of years. Many reforms will be tested in the gubernatorial elections due over the next few years between Federal elections. The positions of governors are arguably more powerful than they have ever been. The legislative framework defining their powers and responsibilities is unclear and not enforced, so that as free and fair elections as possible are the main limiting influence on their powers and performance.

There is first a range of `process and design’ factors where DDIN might be called in. These range from updating, cleaning and refining the biometric voters register, clarifying the criteria for locating registration and polling stations, through ballot paper design, arrangements for accreditation and voting on election day to the counting, collation and announcements of results.

Election legislation and constitutional reform: Amendments to the 2011 Electoral Act and the Constitution, designed to strengthen the independence of INEC and the Chairman’s control over personnel led by the Secretary and including the appointment and activities of Regional Electoral Commissioners and electoral teams at Local Government Authority level. Reorganisation and streamlining of the candidate nomination process would be a further priority, imposing clear standards for the qualifications required of candidates and time deadlines for their nomination while prohibiting the substitution of candidates once registered.

Capacity building in INEC itself: Reorganisation and restructuring; increased professionalism through recruitment, training, mentoring and better incentives for performance; improved use of IT (especially social media); and – perhaps - measures to rely more on volunteers (calling on their sense of “civic duty”) than paid staff on polling days.

Creation of the new bodies recommended in the 2009 Uwais Report – particularly the Political Parties Registration and Regulation Commission and the Election Malpractices Commission – if the new National Assembly sees fit to pass the necessary legislation required.

Building up the training and research programmes of the INEC Electoral Institute: seconding researchers from Nigerian universities; studying such topics as regional and local voting patterns and the reasons for them and preparing case studies of the problems in the electoral process that create the propensity to resort to violence.

Supporting INEC efforts to stimulate civic education throughout the country, tailored to particular regional needs.

Improving INEC’s ability to prosecute electoral offenders or help in the creation of separate efficient electoral offences tribunals.[6]
[6] This may be more in the sphere of the new DFID J4A Programme which has recently been launched.

In the longer term, providing support for the revised delimitation of constituency boundaries to reflect population changes.

Improving election security, working with the Nigerian police force and the J4A Programme.

Generally supporting efforts to improve relationships with other key actors in the election cycle, including the private sector.

5 FUTURE PRIORITIES: NATIONAL ASSEMBLY

5.1 Background

Following `good’ elections, there is now a new National Assembly – 72 freshly elected senators out of 109 and 260 first time MPs out of 360. They are of course as yet an unknown quantity, but there are encouraging signs in the priority given to constitutional electoral reform in both chambers’ legislative programmes. Both Senate and House of Representatives have INEC Committees which will consider both the reform of INEC and the reform of the electoral process. [7]
[7] A meeting with the Senate President produced a number of positive statements and commitments. INEC he stated is not the only institutional responsible for free and fair elections – a sound democracy required everybody to get involved and this requires massive voter education. The judiciary and the media need to be strengthened. Legislative institutions also need strengthening through training reinforced by lessons from comparative experience elsewhere. The Inter-Parliamentary Committee will coordinate the National Assembly Chambers in passing legislation that will make elections more transparent and empower INEC to lead the way forward.

5.2	Priorities

5.1.1	DFID should maintain its focus on the National Assembly, if the public are to continue to strengthen their belief in improved democracy and the value of the National Assembly to their interests. There should be three main areas:

(I)	Constitutional and electoral reform: above all designed to strengthen the independence of INEC but also covering such issues as the creation of new states which are vital to peace and stability in a growing number of areas of the country as are voting rights for settlers and indigenes.

(ii)	Strengthening the Assembly’s collective capacity to hold the Executive to account, especially through the work of the two Chambers’ Committees. Selection of committees on which to concentrate will be the first task. One cross -section that suggests itself is the following: Health; Education; Women and Youth; Agriculture; Finance; Appropriations; MDGs and Poverty Alleviation; Justice and Human Rights – and in the House of Representatives the Implementation Committee.

What is required is straightforward: Training of staff as clerks and researchers; improving the use of IT; making sure all staff understand and can apply Senate and House rules and procedures. And for elected members of committees: induction into the role and purpose of committees and their responsibilities within these bodies; and how to work constructively with committee staff to make committees effective.

(iii)	Strengthening Assembly interaction with CSOs and members of the public: various forms of communication (meeting and seminars; publicity and the media). Paying particular attention to the new electronic media (“Social Media”). Making sure that the recently created National Assembly Liaison Office for contacts with CSOs works effectively. Trying to change public perceptions of Assembly members – not millionaires or bankers but servants of the public’s interests.[8]
[8] The salaries of members do not helping this change of image as they receive some of the highest salaries in the world - $1 million equivalent each year plus very lavish expenses.

6.	FUTURE PRIORITIES:CIVIL SOCIETY

6.1	Background

6.1.1	Though not uniformly positive in its impact,one of the more encouraging developments in the2011 elections was the contribution made by Nigerian and international CSOs to the mobilisation of the population to vote and to the understanding of the electoral process. While there is a long way to go, the patterns established need to be expanded and consolidated. CSOs appear willing to partner with INEC to deal with perceived deficiencies in the electoral system and generally to create an environment conducive to the conduct of free and fair elections.

6.1.2	Some of the programmes and activities carried out by CSOs – like the “Situation Room”, “Parallel Vote Tabulation”(PVT) and the use of Social Media to mobilise youth to play a positive role in the political process – were innovative and extremely effective. Though it is very difficult to quantify the impact of these innovations in terms of numbers or percentages and specific timeframes of months and years, they represent a pattern of activity which should be expanded and consolidated.

6.1.3	Two categories of CSOs stood out and should be supported by DDIN in the next few years:

(i)	Strategic CSOs which play and will play vital roles in institutional capacity building, for example: the Policy and Legal Advocacy Centre (PLAC) with the National Assembly; The Centre for Democracy and Development with political parties; the National Democratic Institute and Parallel Vote Tabulation; and WANGONET and Enough is Enough in developing Social Media and civic education. The Centre for Law Enforcement Education in Nigeria (CLEEN) also plays a vital role but with the Nigerian Police Force and Election Security, supported by the DFID funded J4A Programme.

(ii)	A large and growing range of state and local CSOs with a variety of roles stretching from service provision and economic empowerment to care for the disabled. They all have the capacity to play a part in the election process and represent citizen concerns and problems to executive and legislative branches of government at different levels. These CSOs are likely to be potentially more effective at state and Federal levels. Though they should be effective at local government level, most LGAs are not given the resources by governors to provide services of any significance so there is little on which to impact.

6.1.4	These are also the CSOs with the potential to make contributions to the massive voter education programme required at grassroots level. They are able to adapt to local culture and environments and at the same time explain to ordinary citizens in local languages what democracy and elections are about in practice.

6.2	Priorities

6.2.1	The first category – strategic CSOs with roles in international capacity building – are fairly straightforward. What are required are individually designed and funded programmes over three to four years to develop capacity in key institutions such as the National Assembly and political parties. Activities within such programmes will include: institutional restructuring and innovation; training of key cadres and officials; drafting of key documents such as electoral reform legislation and party constitutions; and pilot programmes embodying innovations. DDIN should enter into contractual agreements with the CSOs involved over at least a three year period with sufficient funds to allow this range of activities to take place.

6.2.2	One issue for the DDIN lifespan is how much to use Nigerian and international CSOs. In the run-up to the 2011 elections, heavy reliance was placed by the DFID/USAID Partnership Agreement on NDI, IRI and IFES. These huge US based organisations played a very valuable part in preparation and election delivery and to a lesser extent are continuing to do so. They exhibit high standards of professionalism and are vastly experienced.[9] The question now is to what extent the Nigerian CSO sector has developed and can take over the role played by these three organisations.. The Review Team’s assessment is that Nigerian NGOs can and should in the run-up to 2015. There are still areas such as PVT where external expertise (in this case from NDI) is still required but programmes need to be carefully designed to ensure the transfer of expertise to Nigerian counterparts as soon as possible. Otherwise, contracts should be given to Nigerian organisations with the objective of capacity building in the national sector as well as democracy development.
[9] Unfortunately the UK simply has no equivalents. The Westminster Foundation for Democracy is useful but for the specific purpose of deploying British politicians and party managers. Electoral Reform International Services has an unrivalled reservoir of election specialists but does not have the management capacity to deliver large programmes.

6.2.3	Specific programmes that are particularly worthy of support and replication or expansion are: the “Situation Room” at state level in the sequence of gubernatorial elections; the development of the whole range of Social Media (not forgetting SMS) for their potential in communication and ability to mobilise the political interest and involvement of the 70% of the Nigerian population under the age of 35;[10] and developments in conventional media programme- making especially for radio.
[10] But their potential impact should not be over-estimated or at least not yet. 3 million Nigerians are estimated to be on Facebook and Twitter, but this is out of a total registered electorate of 74 million.

6.2.4 In the second category of state and local level CSOs, there are two prerequisites. One is greater knowledge of the capacity of CSOs in some of the less developed states in the North-West and North-East of Nigeria. A survey may be required to find out what CSOs actually exist and what they actually do . A second preliminary is a question: while DDN support should of course be spread geographically, should it be concentrated in the least developed regions where the needs are greatest but the impact most problematic? This is an issue that the Review Team did not have the information to answer and further consideration by DFID Nigeria is required.

6.2.5	Where CSOs exist in sufficient numbers and with practical capacity, there are three main roles which should be supported:

-	Increasing involvement of CSOs in elections, not just in 2015 but in the intervening years: civic education (not neglecting the basics of explaining democracy and the part elections play in it); monitoring performance of key official agencies on and before election day; monitoring the actions and performance of governors after they have been elected; monitoring the behaviour of political parties; and above all mobilising citizens to vote.

-	In the decision to vote, spreading the message of “value orientation” – voting for `good’ candidates, on the basis of character, honesty, interest in service and not self-enrichment. Encouraging voters to reject choices on the primary basis of tribe and religion or because payments are involved. CSOs combining with religious leaders and tribal enders would be a very important combination in this particular role.

-	Generally improving communications in the democratic process not just in elections; making sure messages on for example needs, abuses and preferences get through to executive authorities and legislators at various levels.

7	FUTURE PRIORITIES:POLITICAL PARTIES

7.1	Background

7.1.1	Nigerian political parties have become notorious for what appear to be the guiding principles of their existence.. They are conceived essentially as alliances of small elite groups, drawn from big business and current and ex-military officers. Once elected and in power, their central objective is to to utilise the resources at their disposal for their own ends. Such are the rewards of success in elections that all means are used – bribery on a large scale, political violence including assassinations, pressure on election authorities and judicial tribunals to produce favourable results, manipulation of the press, radio and television and the making of exaggerated and unrealisable promises to secure support. These characteristics probably diminished at Federal level in 2011, having reached their zenith in 2007. But governorship elections still exhibit these characteristics among competing political parties as the resources available to elected governors are so vast and discretionary.

7..2	Priorities

7.2.1	Political parties are probably the most difficult area to reform and also the most sensitive and controversial for potential external involvement. Though there were few signs in the run-up to the 2011 elections,that parties were becoming more aware of the need to generate genuine popular support by paying attention to the interests of ordinary citizens, PDP losses in the elections seem to have had a salutary effect on developing this awareness.

7.2.2	There are three priority areas in which reform is required before parties can transform themselves. The Review Team believe that these will not be achieved without pressure: first from the growing effectiveness of civil society in favour of representation and accountability; and secondly from diplomats and development partners.[11]
[11] There was considerable evidence in the2011 elections that external pressure did have an effect.

(i)	The first requirement is to establish a clear legal framework for the organisation and conduct of political parties. There are four key elements: defining the legal requirements for the formation and continued operation of a political party( eg. constitution, membership, internal decision making institutions); setting out candidate nomination requirements in terms of process and procedures under INEC supervision; developing a legally binding code of conduct for parties; and defining both the consequences for any offences against the law and the legal institutions that will handle such offences.

(ii)	The second requirement is that INEC and political parties create a really effective IPAC in which issues relevant to the creation of a level playing field for political competition can be discussed and resolved. This means an inter-party/INEC dialogue first in the national capital and then in states between the Regional Election Commissioners and parties at state level.. These committees should meet regularly and be attended personally by senior INEC officials and party leaders if they are to have any real credibility and influence.

(iii)	The third requirement is the building up of understanding of the need for genuine votes and the capacity to generate that kind of support among voters. Such exercises should also deal with the downside of rigging and the ways it can be stopped. The contents of such workshops are straightforward an have already been mentioned:: democratic party organisation; membership mobilisation; the nomination process for candidates and offences against the law . Subject matter should also include the advantages of internal democracy, the need for transparency in party and campaign finances and the particular issue of improved women’s participation and representation.

(iv)	DDIN could be invited to help in these reforms, but it may be preferable for political reasons to make the JDBF the lead provider of such external assistance (see below-Section 10.5).

8.	FUTURE PRIORITIES:ELECTION TRIBUNALS AND THE JUDICIARY

8..1	Background

8.1.1	The record of judicial involvement in election tribunals, especially after 2007, has had considerable problems. There has been a high incidence of corrupt decisions where judges have been paid by politicians. There has been huge pressure and intimidation of honest tribunals, sometimes necessitating special police protection and as a consequence there has been great reluctance amongst judges to take part in such tribunals due to the physical dangers, the vilification and the very lengthy times taken to consider cases. (One by-product has also been the disruption of normal judicial case schedules by lengthy absences on tribunals in other parts of the country).

8.1.2	More positively, though numbers are still very large 2600 electoral cases in 2007 had become 1000 in 2011 after the deadline for filing complaints had past.

8.2	Reform Possibilities

8.2.1 Creation of the Election Malpractices Commission recommended by the UWAIS Commission. However, this depends on the new National Assembly passing the necessary legislation and that requires a marked change in the attitude of its previous members who saw the Commission as a threat.

8.2.2	Broadening the definition of what consists of `admissible evidence’ in election petitions, many of which are currently decided unfairly on the basis of inclusion or exclusion of relevant evidence.

8.2.3	Use of Alternate Dispute Resolution techniques (ADR) with judges sitting informally. This is potentially useful if the problems of enforcement of decisions can be overcome.

8.2.4 Generally encouraging pressure from CSOs to improve performance and equity in the resolution of election cases.

DDIN should reserve judgement on whether to be involved. On the UK side, J4A is the more likely DFID partner, but foreign inputs have not been welcomed so far by the Judiciary.

9.	MEDIA

9.1	The role of the print and broadcasting media in the electoral process was not a primary focus of the review – in contrast to the Social Media which were exhaustively discussed and analysed. It is worth noting that relationships between the media and INEC were much better in 2011 than previously. Measures should be taken to improve this trend. One particular aspect may be seminars/workshops to encourage media to use the recently passed Nigerian Freedom of Information Act which so far has been under- utilised.

10.	FUTURE PRIORITIES:WOMEN’S ADVANCEMENT AND PARTICIPATION

10.1	Background

This has been a disappointing story. Female participation has declined from 2007 to 2011 both in terms of fewer candidates and fewer elected, even though women are believed to have voted in greater numbers than ever before. There are a whole range of obstacles: culture and history; lack of legislation on affirmative action[12]; finance available to female candidates in the elections; party membership and structures – only nominal targets (PDP 15%) for numbers of women but no real action; popular attitudes to female politicians; and the attitudes of women themselves to both participation and voting for female candidates.
[12] Nigerian electoral law forbids political parties to create separate women’s and youth wings.

10 .2	Possibilities

10 .2.1	The Review Team has not come up with any major new initiatives:

(i)	There must be a continuation of the seminars/workshops and publicity exercises on national gender policy and on encouraging women candidates through training and public speaking, use of the media and campaigning. But the trouble is that these have been going on for some time and have not produced a significant impact.

(ii)	There may be a case for the creation with DDIN sponsorship of a Nigerian equivalent of the UK “300 Club” picking out a range of likely women candidates for 2015 and intensively developing their capacities: self-confidence; motivation; political expertise; and even financial backing. However there is already an almost equivalent body in Nigeria – “Gender for Affirmative Action” – which has not produced the expected result of more female candidates being successful.

11.	DELIVERY MECHANISMS

11.1	Background

11.1.1	During the course of the Review, it became clear to the Consultants that the right method and timing of delivery of support was as important as the technical content – in an assessment that applied to the main DDIN institutional targets – INEC, National Assembly, Civil Society and Political Parties.
11.1.2 Currently, there are three alternatives in delivery: a UK “Strategic Fund” – used bilaterally; a joint US/UK Partnership Agreement regulated by a Memorandum of Understanding; and a UNDP managed Joint Donor Basket Fund (JDBF). The run- up to the April 2011 elections saw a dramatic shift in the allocation of resources between the three alternatives in delivery and the task in the next three years will be to use the different possibilities to maximise their positive impacts..

11.2	UK Strategic Fund

11.2.1	This was used on a comparatively small scale for specific innovatory projects relevant to the elections. It was based on the assessment that the UK comparative advantage lay in specialist technical and (occasionally) political inputs, provided in the right form at the right time. These were of varying size, but usually involved comparatively small financial amounts even if they added up to a significant total.

11.2.2	The suggestion here is that the Strategic Fund be enlarged and used during the next three years of DDIN. The challenge will be its management. In the Review Team’s view, this can only really be provided internally in DFID Nigeria, not by the engagement of an external service provider. In the latter case, the contract and its amendment(s), the process of approval (individual consultancies, consultants and sub-projects) and the need for time-bound comprehensive work plans would make the response too slow and inflexible. It would also be difficult to provide a service provider that could cover the range of potential technical assistance required. What would be most desirable as an alternative would be for a DFID Governance Adviser on a full-time or nearly full-time basis to be appointed with one or two Programme Officers in DFID Abuja to manage the Strategic Fund as well as DDIN in its entirely. Costs could be met from the DDIN budget – there are precedents for this already in DFID Nigeria. Only in this way will close contacts and the specially tailored support that will make for success be developed.

11.2.3	In making this suggestion, the Team are well aware that problems could be created in terms of staffing levels in DFID Nigeria. Enough has been said about the importance of further successful elections in Nigeria to make this a problem worth solving.

11.3	US/UK Partnership Agreement

11.3.1	This proved extremely useful in 2011allowing considerable expenditure on the vital roles of NDI, IFES and IRI in the run-up to and the conduct of the elections. These expert and professional bodies were jointly funded by USAID and DFID and made very valuable contributions.

11.3.2	The standing question is whether these three bodies should go on being utilised in Nigeria in the aftermath of the elections. It has already been argued in this Report(Above paras.6.2.1-6.2.3) that more priority should be given to the employment and development of Nigerian CSOs with the international bodies concentrating more on the transfer of expertise (for example in “Parallel Vote Tabulation”). A further factor is that USAID is unlikely to have anything like the same level of funding available for electoral support as it had up to April 2011. This points to a smaller Partnership with the main focus on developing Nigerian CSO capacity in the electoral process.

11.4	UNDP Joint Donor Basket Fund

11.4.1	Originally in the run-up to 2011, this was to be the main vehicle for the delivery of donor support to elections. However the Fund came to exhibit a number of serious problems in its management and delivery: lack of an overall strategy and of basic documentation; immediate and ill-thought reactions to requests from Nigerian partners involving more finance than technical assistance, or alternatively overly rigid project proposals that stifled particularly Nigerian initiatives; failure to fill key staff management posts; poor and non-transparent relations with other donors and particularly DFID Nigeria. Eventually, these problems necessitated the transfer of a large amount of DFID funding from the Fund to the Partnership in order to get the money spent effectively in time.

11.4.2	Though these problems might create a case for withdrawal from the JBTF, there are complicating factors. Professor Jega and INEC like the JDBF for its rapid and responsive method of operations and its “flexibility”. It is also useful for its political neutrality not being identified with `interfering’ bilateral partners. Additionally, the recent bombing of UN Abuja would make it very difficult if not impossible for the UK to withdraw from the JDBF in the near future.

11.4.3	Perhaps the best compromise is for DFID to continue to support the Fund but on a much more limited basis (£3 million over three years would be a suitable figure). Funding would be earmarked and perhaps political party strengthening would be the subject area in which UNDP would have the most comparative advantage. UNDP will not in any case be short of funding. The EU feel they have no alternative method of delivery for their prospective €20million programme of electoral support and CIDA will continue to make available the balance of their $7 million contribution and there maybe other small supporters. At the same time as earmarking the British contribution, efforts should continue to get the Fund management satisfactorily staffed and to see the production of a realistic plan and set of priorities for the utilisation of the Fund over the next three years. The current review sequence in which UNDP are involved may produce these benefits, but discussions with the head of UNDP indicated yet another time estimate of six months before staffing would be complete (interviews had not yet taken place in September 2011),

11.5	Conclusions

11.5.1	DFID Nigeria should continue to use the three alternative delivery modes: Strategic Fund; Partnership Agreement; and JDBF. But the advantages and disadvantages of these should be clearly understood and acted upon:

(i)	The Strategic Fund should be for comparatively small targeted support to INEC and other institutions when required, as well as to enter into contract agreements with key Nigerian CSOs (PLAC, CDD, EisE and WANGONET for example) over three year periods.

(ii)	The Partnership Agreement should continue support to NDI, IFES and IRI (subject to the USAID review findings in October 2011). But on a significantly smaller scale and with much greater emphasis placed on the transfer of expertise to Nigerian counterparts over the next three years.

(iii)	The JDBF contribution should be both smaller and more targeted. An initial priority could well be JDBF support for the development and reform of Nigerian political parties, where their political neutrality is an advantage.

12.	RISKS

12.1	The risk analysis in the original 2009 DDIN Memorandum does need updating, though the core risks are there. The following is the Review Team’s list in approximate order of priority:

(i)	The departure of Professor Jega from the INEC Chairmanship: currently, this would be a strong contender for the status of killer risk, so dominant has the Professor’s personality and image become! Fortunately, there is no evidence that this is about to happen, though Nigerian politics is not exactly a predictable business.

(ii)	National Assembly reverts to old priorities and ways of working and loses respect and confidence amongst citizens: this is a real possibility, given the pressure on elected members to reward the supporters on which they depend. However, the declarations of intentions involved in planning legislative programmes and the belief that new members are aware of the responsibilities to constituents may make this less likely.

(iii)	Violence in Nigeria, (exemplified but hopefully not typified by Boko Haram) grows to such an extent that democracy in its present form is threatened by anarchy or martial law and/or the restoration of military rule: this does not seem likely but anxieties over violence are high and could easily tip popular attitudes into loss of confidence in the civilian government’s ability to maintain law and order.

(iv)	Efficient and effective delivery mechanisms for DDIN, DGD and the Partnership Agreement cannot be set up: this only seems likely in the case of the JDBF which funds DGD, but optimistically, the reviews that UNDP are undertaking during the last few months of 2011 and the Strategic Plan they are drawing up to cover the period to 2015 should solve delivery problems.

Competition between donors is disruptive of each other’s efforts: this is recognising that there will be reduced opportunities for donor support to the electoral process in the next three years and that donors may get in each other’s way. There are two components in improving the situation: better donor coordination and attitudes of cooperation rather than competition.; and greater clarity in UNDP on where they have a comparative advantage and an unwillingness to become involved outside these areas.

(vi)	A backlash against donors’ “interference” is whipped up by the media and political parties: this could happen if some political parties feel that they are being disadvantaged in receiving external support. Even-handedness is the obvious solution, but may be hard to achieve with so many formally registered political parties. Donor relations with the media are an area where improvements may be possible .
Appendix 1

Value-for-Money proposals
Appendix 2

Terms of Reference:

Annual Review of
Deepening Democracy in Nigeria (DDIN)

Background
1.	The Deepening Democracy in Nigeria programme was approved in April 2010. It was designed to help Nigeria break the negative trend in election credibility since 1999 and more broadly to deepen democratic processes and institutions.

The design of DDIN carefully considered the lessons of mixed success in election support from 2003 and 2007. Flexibility, strategic focus, impact and value-for-money were the main guiding principles. DDiN is founded on the 2008 Electoral Reform Commission report recommendations.

The goal of DDiN is to strengthen democratic governance in Nigeria. The purpose is to advance key political governance processes and structures.

The programme was designed with a deliberate “high risk – high return” strategy in mind. There was a major investment in the 2011 elections, supported by long-term deepening democracy focus towards the 2015 elections and beyond. Around 60% of the programme spend relates to the 2011 elections. As a result of VfM focus and flexibility, substantial amounts were shifted between implementation channels compared to the original intentions.

Overall, the strategy is to maintain momentum and work alongside the reformers, while putting pressure on negative forces. DDIN has three implementation channels:

- US/UK joint work: Political areas focusing on the 2011 elections, such as INEC independence and credibility, voter registration and parallel voter counting system, led by the civil society.
- UNDP basket: Focusing on technical deepening democracy work (Elections, Media, Civil Society, National Assembly, Parties), balanced focus between 2011 and medium/long-term work.
- HMG strategic/innovative component: to deepen democracy and improve strategic coordination and dialogue. Focus on flexible and innovative ways to promote democracy (such as social media).

A HMG Programme Board provides strategic oversight and direction as well as ensures coordination with other HMG efforts on political governance. The Board consists of the UK high commissioner, the DFID head of office, the GSD team leader, head of Chancery and the DDIN leader adviser.

Review Objectives
7.	The objective of the review is to assess project progress and performance since the start-up in mid-2010 and recommend future strategic focus, partners and other implementation modalities.

8.	The review takes place amidst other reviews and stock-takings, including:
  - The Independent National Election Commission (INEC) is planning a review of the election process (July).
  - UNDP is planning a review of the UN-led basket on Democracy for Governance and Development (scheduled for October)
  - NDI is presently undertaking a review of their main component, Project Swift Count”.
  - DFID-N is planning a wider piece of research and analysis on Nigeria’s “democratic transition” later in 2011; likely in collaboration with INEC, international universities and selected Nigerian civil society and private sector individuals.
9.	Within this context, the review team will be expected to make a recommendation on the performance score to be given to the project (according to the DFID ARIES project scoring system). The review report will be used by DFID-Nigeria to decide upon the final project score which will be entered into the ARIES system.

Recipient
10.	The primary recipient of this review is DFID Nigeria. Secondary recipients are implementing partners and key Nigerian stakeholders.

Aspects to be covered by the review
The Review Team will carry-out the below three equally important tasks:

I.	REGULAR REVIEW TASKS

Conduct a review of the performance of the project to-date in terms of:
  1. Progress made in the implementation of the DDIN, together with the reasons for the level of progress made.
  2. Progress made in achieving the project logframe outputs Progress made towards achieving the project’s purpose.
  3. Review the programme’s current logframe and make recommendations on required improvements. If a revised logframe is being proposed the reviewers should also review this.
  4. Assess whether assumptions are still holding and relevant.
  5. The appropriateness of DDIN’s approach, strategic direction, and risk mitigation strategies (pre-elections, during- and the immediate post-election period)
  6. Identify the main lessons – what have we learnt, Nigeria-specific and generically.

II.	VALUE FOR MONEY (VfM):
### Review economic, financial and budget processes; in particular, assess the Value for Money (VfM) – based on results and achievement - of DDIN and make recommendations as suggested below:
#### Assess availability of cost and forecasts broken down by input and output to show how money is being spent,
  1. Assess availability of information to understand effectiveness of outputs to deliver results
  2. Compared costs to planned and achieved results, to assess economy, efficiency and effectiveness of DDIN,
  3. Set out specific recommendations on improving VfM, including transactions costs (DFID staff time, identifying programmatic and administrative savings by implementation partners and other ways to adjust the programme to maximise impact). What to cut? What to do more of?
  4. If/where possible, set out recommendations for improving the ability of DDIN to measure VFM, including improved cost information and VFM metrics

III.	LOOKING AHEAD - STRATEGIC DIRECTION:
This part of the review should suggestions for strategic focus and future implementation partners and arrangements towards 2015. Key considerations would include:
  1. Issues; the “what”: What are the substantive needs and priorities, what’s DFID/HMG’s strategic interests, focus and what’s our comparative advantage – what’s the best division of labour given available staff time?
  2. Institutional and administrative arrangements: Provide options and recommendations on future implementation partners (basket, US, own service provider) and administrative setup

Organisation and Coordination
11.	The review team will be led by a senior international independent democratic governance expert supported by an election specialist. A DFID VFM/commercial adviser will support the team and a DFID governance adviser from another DFID-country may join the team as appropriate. DFID-Nigeria will lead on organizing the logistics of the review.
12.	The team may be accompanied in some of its meetings by members of the DFID Nigeria Governance team and the DFID-N Results Adviser.
13.	The lead DFID Governance Adviser for DDIN (Jens-Peter Dyrbak) will be responsible for coordinating the review on DFID’s side. He will be supported by Odumu Ebengonye, Programme Officer, Governance and Social Development Team (DFID Nigeria) who will cover logistics and planning aspects on DFID’s side.
14.	The consultants will be responsible for preparing the review report and submit the draft report to DFID-Nigeria (lead adviser, Jens-Peter Dyrbak).

Methodology
15.	The review team will review performance evidence for all of the components. Performance will be assessed based on existing evidence and reports, verified by interviews with key interlocutors. Unless strong reasons are identified, the team is not expected to review individual activities within the main components (UN basket and US partners).
16.	The review will consist of pre-mission document review, meetings with DFID, FCO and implementing partners, together with meetings with a number of representatives of CSOs, INEC and political parties. The main review will take place in Abuja with visits to Lagos (Wangonet and wider social media scene) and Kaduna or Kano (conflict/violence).
17.	The main findings and recommendations of the review will be presented to a meeting and relevant partners the completion of the mission, in order to elicit initial reactions and to correct any factual errors. There will also be a final wrap up meeting / presentation with DFID and the DDIN Board.

Consultant Inputs

Skill Area	Category	No of days
Democratic governance expert	International, team leader
Election expert	International/local
VFM expert	DFID staff

Reporting
18.	The team will produce the following reports:
- A short report (max. 20 pages) responding to the requirements outlined above.
- A completed Aries Annual Report Excel spread-sheet, including recommended scores (where possible).
Timing
19.	The consultants’ report and spread-sheet will be supplied to DFID within two weeks of the completion of the mission.
20.	Where relevant DFID will share the draft review report with its principal counterparts for comments – which will be expected to be provided within one week.
21.	The schedule for the conduct of field work and report submission is presented in the table below:

Stage/Activity	Timing
Conduct of in-country review	Start August –end September 2011
Submission of draft report to DFID.
Submission by DFID of comments on draft report.
Submission of final report

 Pre-review required background reading
1. The “Afari-Gyan” report, February 2010. EDRM.
2. Electoral Reform Commission recommendations, 2009 (www)
3. DDIN approved Logframe April 2010. EDRM
4. DDIN programme memorandum, April 2010. EDRM
5. INEC review report, available July/August 2011
6. Election violence hotspots report + updates Feb+Oct 2010,
7. Project Swift Count press releases, March-May 2011 (www)
8. Project Swift Count review documents, available July 2011
9. Situation Room grant agreement, progress reports and press releases, March-May 2011
10. UNDP basket programme, progress reports and minutes, EDRM
11. US partner (IFES, IRI, NDI) workplans and progress reports, EDRM
12. WANGONET grant agreement and progress reports. EDRM
13. PLAC grant agreement and progress reports (NASS). EDRM

Appendix 3
Deepening Democracy Annual Review 16 -27 September 2011
Itinerary and Contacts
Dr Kwadko Afari-Gyan
Dr Garth Glentworth
Date and Time	Contacts	Venue
Friday 16 September	Abuja
1200	Meeting with British High Commissioner, Deputy High Commissioner with Jens-Peter Dyrbak (JPD) [13]	High Commissioners / Residence
2-3 pm	Meeting with Acting INEC Chair, INEC Advisers, Commissioners and Senior Staff	INEC Office
Saturday 17 September
10.30	Meeting with Richard Montgomery, Julius Court (DFID)	RM’s House
1200	Meeting with PLAC : Clement Nwankwo & Omolara Akinyeye	PIAC Office
Sunday 18 September
1400	Travel to Kaduna
1900	Political Dinner: Festus Okoye, Director Nigeria Human Rights Watch, Safya Ibu Garba, Director, Kaduna Women’s NGO
Monday 19 September	Kaduna
11.30	Meeting with selected religious leaders / ( 6 attending)	SAVI Office, / Kaduna
13.30	Meeting with selected CSO’s (10 attending)	SAVI Office Kaduna
1500	Meeting with Deputy Police Commissioner (IC2),Kaduna State	Police HQ Kaduna
PM	Travel back to Abuja
Tuesday 20 September	Abuja
9-10.30	Meeting with J4A (Bob Arnott, Police Major Junaid Bakar)	British Council Office,Abuja
1200-1300	Meeting with Amara Nwankpa, Enough is Enough	DFID Office
1330-1500	Lunch with Prof .Okey Ibeanu, Principal Adviser to the / INEC Chairman	Restaurant
1600-1700	Meeting with CIDA ( David Rose) and EU ( Alan Munday and Laolu Olawumi)	DFID Office
Wednesday 21 September
9-10	Meeting with USAID -Minnie Wright & Diana Arnaudova	USAID Office
10-12	Meeting with CEEPS Partners : NDI (Carlo Binda), IFFS (Carl Dundas) and IRI (Wahirat Aliyu))	USAID Office
1600-1700	Meeting with UNDP Basket Fund :G. Dehoux, J Hiemstra, S.Ekwoo	DFID Office
1930	Political Dinner-High Commissioner: Montgomery, Court, Ibrahim, Ibeanu, Nwankwo. Mangwe, Ikenze	High Commissioner’s Residence
Thursday 22 September
1000	Situation Room Partners- Clement Nwankwo, Dan Nagel, Uchenia Arisukwu	DFID Office
1230	Meeting with Senate- Senator David Mark- Senate Speaker +Six Senators	National Assembly
1730	Travel to Lagos [14]
Friday 23 September	Lagos
9	DFID Lagos – Director Sina Fagbeno , Margaret Fagboyo, Programme Officer
10-11	Meeting with Enough is Enough, Yemi Abamoleken, Mercy Aban	12B Ezekiel St, Toyin, Ikeja-Lagos
1430-1600	Meeting with WANGONET- Tunji Lardner, Peter Egbale	7 Raymond Street, Sabo-Yaba, Lagos
2000	Dinner: Innocent Chukwuma & Josephine Chukwuma -CLEEN	Best Western Hotel,Lagos
Saturday 24 September	Travel Back to Abuja
Sunday 25 September	Abuja
1430	Review Team and Jens Peter Dyrbak discussed conclusions and worked on presentation to DFID	Sheraton Hotel
Monday 26 September
9-10	Meeting on “Hot Spots”- Sam Unom -Consultant	DFID Office
11-12	Centre for Democracy and Development- Director Dr Jibril Ibrahim	DFID Office
1430	UNDP, Country Director- Ade Leboetje	DFID Office
Tuesday 27 September
1100	Presentation to DFID – R Montgomery, J Court, Odumu Egbonye	DFID Office
Wednesday 28 September	Consultants Depart Nigeria
[13] Unless otherwise stated meetings were held with the Consultants and Jens Peter Dyrbak, DFID Governance Adviser in charge of DDIN
[14] Jens Peter-Dyrbak did not visit Lagos with the Consultants

Appendix 4 Abbreviations

ADR	Alternative Dispute Resolution
CDD	Centre for Democracy and Development
CEPPS	Consortium for Elections and Political Process Strengthening
CIDA	Canadian International Development Agency
CPC	Congress for Progressive Change
CSO’s	Civil Society Organisations
DDIN	Deepening Democracy in Nigeria
DFID	Department for International Development
DGD	Democratic Governance for Development (UNDP)
ERIS	Electoral Reform International Services
E is E	Enough is Enough
EU	European Union
IFES	International Foundation for Electoral Systems
INEC	Independent National Election Commission
IPAC	Inter Party Advisory Committee
IRI	International Republic Institute
J4A	Justice For All (DFID Programme)
JDBF	Joint Donor Basket Fund
LGA	Local Government Authority
MDG’s	Millennium Development Goals
MOU	Memorandum of Understanding
NASS	National Assembly
NDI	National Democratic Assembly
OSWA	Open Society Initiative in West Africa
PDP	People’s Democratic Party
PLAC	Policy and Advisory Centre
PVT	Parallel Vote Tabulation (System)
REC	Regional Election Commissioner
UNDP	United Nations development Programme
VfM	Value for Money