## A1 Goal, Purpose, Risk
Mid Term Review (reviewed November 2011 - revised January 2012)
ARIES Project Code | 114230-101
ARIES Project Description | State Accountability and Voice Initiative (SAVI)
A1: Goal, Purpose, Risk
Goal
Goal statement | The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced. NB this is referred to as 'impact' in SAVI's logframe.
Indicator 1 | G1. Quality of governance of State & Local Government in terms of their accountability and responsiveness. Source: SAVI Governance Baseline
Milestone for this review (if any) | Early 2010 baseline: aggregate governance score across the 5 states: 2 out of 5, with a maximum score of 2.5 in 1 state (Jigawa). No change was expected for 2011. Milestone end 2012: 3 states improve their quality of governance score to 2.5 out of 5 or above, of which 2 states improve their score to 3 out of 5 or above.
What progress has been made in the period covered by this review? | The Governance Baseline will not be updated and peer reviewed until 2012. Hence, it is too early to make a full assessment of progress against this indicator. However, SAVI have undertaken an internal assessment (not peer reviewed) using the 2010 baseline methodology, which suggests progress has been made in 4 states, and deterioration has occurred in one state (Kaduna). Late 2011 internal assessment scores (2010 baseline scores in brackets): Enugu 3.4 (2.2); Jigawa 3.2 (2.5); Kaduna 1.5 (1.8); Kano 2.3 (2.0); Lagos 3.9 (2.0). If these scores are confirmed in the 2012 Governance Baseline update SAVI will have achieved its milestones for 2011 and 2012.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | G2. Citizen’s satisfaction (including that of normally excluded groups) with their ability to claim rights and hold government to account through democratic channels. Source: Citizens Perceptions Survey
Milestone for this review (if any) | None
What progress has been made in the period covered by this review? | Citizen's Perception Survey (CPS) data exists for 2010, but will not be repeated until 2012. It is therefore too early to assess progress against this indicator.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | G3. Passage of key legislation relating to good governance – i.e. fiscal responsibility bill (frb), public procurement bill (ppb), freedom of information bill (foib), house service commission bill (hscb).
Milestone for this review (if any) | (Mid 2011 target) On a scale of 0 to 15 of key stages in the process of passage and implementation: Enugu – frb: 1, ppb: 9, foib: 0, hscb: 2. Jigawa – frb: 12, ppb: 12, foib: 1, hscb: 12. Kaduna – frb: 11, ppb: 6, foib: 0, hscb: 13. Kano – frb: 2, ppb: 2, foib: 1, hscb: 11. Lagos – frb: 7, ppb: 11, foib: 1, hscb: 13.
What progress has been made in the period covered by this review? | Current status reported by SAVI: Enugu - frb: 1, ppb: 12, foib: 12, hscb: 14-15. Jigawa - frb: 12-13, ppb: 12, foib: 0, hscb: 12-13. Kaduna - frb: 10, ppb: 3, foib: 1, hscb: 10. Kano - frb: 3, ppb: 3, foib: 1, hscb: 10. Lagos - frb: 14-15, ppb: 10, foib: 5, hscb: 13. Most of the bills in most states appear to have proceeded beyond or to the point of the mid 2011 milestone with the exception of Kaduna where there has been slippage.
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Indicators point to improvements in budget and policy processes in most SAVI states, in particular in relation to civil society policy advocacy and budget tracking, media coverage of the State House of Assembly, public access to information and the greater engagement of the State House of Assembly in the policy and budget process.
Goal Recommendation 1 | 2012 SAVI Annual Review should be completed after the completion of the 2012 Governance Baseline and 2012 Citizen's Perception Survey to allow thorough assessment of achievement of goal level indicators.
Goal Action Point 1 | Agree timing of 2012 Governance Baseline update, 2012 Citizen's Perception Survey and 2012 Annual Review by end March 2012. IMEP to plan data validation exercise including coverage of 2012 Governance Baseline update.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Civil society, State Houses of Assembly and Government improve their voice and accountability processes. NB This is referred to 'outcome' in SAVI's logframe.
Indicator 1 | P1. Functionality of state houses of assembly as agents of voice and accountability. Source: SAVI Governance Baseline (questions relating to quality of governance of State House of Assembly).
Milestone for this review (if any) | Governance baseline early 2010: 4 states score of 2 out of 5 while 1 state (Lagos) has a score of 2.5 out of 5. Mid 2011 milestone: One state improves its score to 3 out 5. Late 2012 milestone: 2 states improve their score to 3 out of 5, of which one state scores 3.5 out of 5.
What progress has been made in the period covered by this review? | The Governance Baseline will not be updated and peer reviewed until 2012. Hence, it is too early to make a full assessment of progress against this indicator. However, SAVI have undertaken an internal assessment (not peer reviewed) using the 2010 baseline methodology. This indicates progress in 4 states and deterioration in one state (Kaduna), and suggests that the mid 2011 milestone has been achieved. The finding will need to be confirmed through the 2012 Governance Baseline Assessment. Late 2011 internal assessment scores (2010 baseline scores in brackets): Enugu 2.8 (2.0); Jigawa 2.4 (2.2); Kaduna 2.0 (2.2); Kano 2.1 (1.9); Lagos 3.2 (2.2). The MTR review team found additional evidence of SHoAs in several states developing their staff capacity, taking more responsibility in budget oversight, conducting more public hearings, enabling greater access by CS groups, and publishing or broadcasting their proceedings.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | P2. Functionality of civil society (including the media) as agents of voice and accountability. Source: SAVI Governance Baseline (questions relating to the quality of governance in Civil Society and the Media).
Milestone for this review (if any) | Baseline early 2010: 3 states have a quality of governance score of 2 out of 5 while 2 states (Jigawa & Lagos) have a score of 2.5 out of 5. Milestone mid 2011: 2 states improve their quality of governance score to 3 out of 5 or above. Milestone end 2012: 3 states improve their quality of governance score to 3 out of 5 or above.
What progress has been made in the period covered by this review? | The Governance Baseline will not be updated and peer reviewed until 2012. Hence, it is too early to make a full assessment of progress against this indicator. However, SAVI have undertaken an internal assessment (not peer reviewed) using the 2010 baseline methodology. This indicates progress in 3 states (Lagos, Jigawa and Enugu) and little or no change in 2 states (Enugu and Kano). The preliminary assessment of the MTR is that the mid 2011 milestone has broadly been achieved. Late 2011 internal assessment scores (2010 baseline scores in brackets): Enugu 2.9 (1.8); Jigawa 3.3 (2.4); Kaduna 2.3 (2.2); Kano 2.0(2.0); Lagos 2.8 (2.3). The MTR review team found additional evidence of improved functionality of civil society in the context of SAVI's Advocacy Partnerships (see outputs 1 and 2 below) and their closer engagement with State Houses of Assembly (see output 3 below). SAVI has been effective in promoting the use of the media by civil society and the State Houses of Assembly. However, its contribution to strengthening the capacity of media houses and media personnel has been limited.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | P3. Demonstrable change in policy and implementation where there is evidence of attribution to SAVI.
Milestone for this review (if any) | At least 5 examples from across the programme directly attributable to SAVI (resulting from improved approaches demonstrated by civil society partnerships and SHoA with SAVI support).
What progress has been made in the period covered by this review? | The MTR Review Team finds that this target has been met. The following 11 changes in policy and implementation are judged to be in part attributable to SAVI's work. Kaduna: Moving towards greater budget realism, start up of primary health care and drug management agency. Lagos: Passage of Special People’s Bill and House Service Commission Bill, agreement to establish a Legislative Budget and Research Office. Enugu: Deployment of more staff to primary health centres following policy dialogue. Kano. New legislation for decentralised water management, Establishment of Legislative Budget and Research Office, and Civil Society Liaison Desk in State House of Assembly. Jigawa: Free Maternal and Child Health Bill at Second Reading. Response to shortage of female personnel in health and education.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Purpose level assumptions appear to have held. SPARC, PATHS2 and ESSPIN have been providing supply side inputs on planning, budget and policy at the central and sector MDA levels, and have been working with civil society and State Houses of Assembly on MTSS/budget training. There does appear to be "space for plural political views in the States where SAVI works" and the "2011 elections [were] sufficiently free and fair that citizens maintain faith in democratic process." The impact of social instability following the elections had a limited impact on SAVI's work in northern states. There is a serious and growing security risk associated with the Boko Haram threat in the north and intercommuncal tensions (see risk heading below).
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | SAVI's theory of change is based on the reasonable assumption that strengthened voice and accountability in civil society, the media and State Houses of Assembly (SAVI's purpose/outcome statement) will lead to more effective and efficient use of resources by state level governments (SAVI's goal/impact statement). There is only limited evidence that state governments are changing their allocation of resources based on civil society advocacy. However, a few examples were found including the deployment of more primary health workers in Enugu and the increase in health and education budgets in Jigawa. The Special People's Law in Lagos should soon result in additional spending on access to buildings and other disability rights.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | There is increasing evidence of results in the five output areas which are contributing to the effectiveness of civil society advocacy and the oversight roles of the media and State Houses of Assembly. Taken together this amount to an improvement in voice and accountability processes as envisaged by the purpose statement.
Purpose Recommendation 1 | Step up work in the additional northern states in partnership with PRRINN-MNCH and SPARC, but take careful account of the risks identified in section 2.6 and security issues discussed in section 2.8 of the report.
Purpose Action Point 1 | SAVI in discussion with DFID needs to present a plan for human resource deployment in the new states, and explain how the risk of spreading human resources too thinly will be mitigated. The problem of insecurity in Yobe is an additional concern that requires a decision to be taken in the near term about the feasibility of beginning work in this state.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2 | Review purpose statement according to logframe recommendation 1 below.
Purpose Recommendation 3
Purpose Action Point 2 | Review logframe and seek DFID approval by end March 2012
Purpose Action Point 3
Project Purpose Score | 3 | 2.7
Purpose Justification | The ARIES template generates the above score automatically generated from the output scores. However, the MTR has witnessed numerous examples of State Houses of Assembly, government and CS groups behaving in new ways that act to strengthen voice and accountability. The achievements are relatively modest, but encouraging in view of the scale of governance weaknesses in Nigerian states. While scoring a 3, the progress against purpose is in line with reasonable expectations of what a medium-sized donor governance programme can achieve in the Nigerian political economy context.
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1 | There is an increasing security risk posed by Boko Haram attacks and associated intercommunal tension. Recommendations: (1) SAVI requires external support to review and cost security arrangements for operations in northern Nigeria. (2) DFID needs to strengthen its capacity and support for providing ongoing security-related information and support to its projects operating in northern Nigeria. (3) With rising inter-communal tensions SAVI needs to develop in affected states an explicit and documented conflict strategy (see section 2.8 of report for more discussion).
Risk Action Point 1 | In view of the urgency of the issue action to be taken on the above three recommendations by end March 2012.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2 | SAVI is exposed to a high risk that its actions will be perceived as interference in local politics (a scenario that has already played out in Kaduna). This risk is heightened by the programme's weak connections to state government. SAVI should give urgent attention to revamping its oversight and advisory functions. The aim should be to restore the functions provided by the State Advisory Panel or Technical Executive Committee, but probably through different and less formal arrangements. SAVI should give urgent attention to revamping its oversight and advisory functions. The aim should be to restore the functions provided by the State Advisory Panel or Technical Executive Committee, but probably through different and less formal arrangements. The types of functions that need to be ensured include: (1) a representational function (via influential and well-respected persons of the state) to give visibility and certain level of credibility and local ownership, (2) a hands-on function via individuals who offer strong expertise in the key areas of SAVI’s work and, hence, can play a proactive role in overseeing programme management, and (3) an oversight function geared towards ensuring that SAVI pursues its work in a manner that is consistent with its own mission, local development policies and broader aspects of UK-Nigeria cooperation.
Risk Recommendation 3
Risk Action Point 2 | Revamped Oversight/advisory bodies to be in place by July 2012
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | SAVI have proposed some changes in wording and changes in the indicators following the 2011 Annual Review. Due to the late approval of the IMEP inception report IMEP was not able to review these changes with SAVI before the MTR, but finds the changes to be generally satisfactory.
Logframe Recommendation 1 | IMEP proposes a final round of logframe revisions in discussion with SAVI to remove remaining inconsistencies to be completed and endorsed by DFID by end March 2012. preliminary recommendations on logframe adjustments discussed in accompanying report, but subject to confirmation through the logframe review.
Logframe Action Point 1 | Revisions to logframe before end March 2012
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy & monitoring.
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 (leave blank if standard indicator) | 1.1 Strength of civil society partnerships for policy advocacy and monitoring. | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone mid 2011: 4 out 10 advocacy partnerships have sufficient linkages and combined skills and resources to achieve their planned objectives for 2010/11. Milestone end 2012: 6 out of 10 advocacy partnerships have sufficient linkages and combined skills and resources to achieve their planned objectives for 2011/12. | 0
Progress made in the period covered by this review, including numbers. | Based on the MTR's own assessment SAVI have already progressed beyond the 2012 milestone. 7 out 10 advocacy partnerships are achieving their planned objectives. (Enugu: MNCH yes, Incl. Educ. no, WATSAN n/a; Jigawa: MNCH yes, School Health yes; Kaduna: MNCH yes, Gender Working Group no; Kano: MNCH yes; Wudil yes; Lagos: Climate Change no, People With Disabilities yes)
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | 1.2 Dependency on / independence from SAVI support.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone for mid 2011: 8 out of 10 advocacy partnerships progressed from incubation to call-down support; of which 2 are progressing from call-down support to SAVI community of practice. Milestone end 2012: 8 out of 10 advocacy partnerships progressed from incubation to call-down support; of which 4 have progressed from call-down support to SAVI community of practice.
Progress made in the period covered by this review, including numbers | MTR agrees with SAVI's assessment (see SAVI's quarterly progress reports July-Sept 2011) that 8 out 10 advocacy partnerships are at the call down stage with one on the cusp of becoming a community of practice (Jigawa MNCH). Two groups are still at incubation (Enugu Inclusive Education and MNCH - WATSAN was not counted for the purpose of this review).
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | 1.3 Civil society partners active support of replication of the approach.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | SAVI are reformulating this indicator based on existing data fitted to a new set of milestones and scoring matrix for each state showing connections between Advocacy Partnerships and other stakeholders.
Progress made in the period covered by this review, including numbers | This indicator will be scored early in 2012. The MTR found many examples of lessons being learned and shared within APs and their member organisation. There is evidence of replication of ideas between APs in the same state or between different states (exchange visits between Enugu and Kaduna). SAVI's CS partners are also increasingly becoming engaged in voice and accountability activities promoted by other SLPs.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 2 | 0.75
Impact Weighted Score | 15 | 0.15
Justification for the Score | Indicators 1 and 2 are on or ahead of track. Based on the project's own milestones the targets will be largely (or even completely achieved). There are questions about whether SAVI has done enough to ensure the sustainability and replicability of the approach (see recommendation 3 below). This should become clearer once indicator 3 has been scored. If the ARIES system allowed intermediate scores it would be appropriate to provide a rating of 1.5 for this output.
Output 1 Recommendation 1 | Within the next 3-6 months SAVI needs to decide whether it will take on any new advocacy partnerships. Beyond this point there is too little time remaining to achieve a sustainable result within the project lifetime. The broad recommendation of the MTR is to consolidate progress made with the existing APs, but a few changes and additions may be needed. There is an opportunity in Lagos to step up work on health and education (through LACSOP, PaGG or other groups) and so strengthen synergies with PATHS2 and ESSPIN. The MTR review is concerned that the proposed approach to building a WATSAN AP in Enugu is too localised in scale to fit with SAVI’s model of long-route accountability. The review also suggests considering narrowing the focus of the Climate Change partnership in Lagos around flood prevention and management
Output 1 Action Point 1 | Final decisions on new APs or changes to AP focus by mid 2012.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | As the Advocacy Partnerships mature they need more technical, research, policy and scientific support to engage credibly in state policy processes. SAVI has been effective in providing support on advocacy skills and organisational development, but needs to be able to make available to the APs more technical expertise on policy content, and to work to develop local TA capacity.
Output 1 Recommendation 3 | SAVI needs to do more to ensure the sustainability and replicability of the work of its Advocacy Partnerships. This requires working more with APs and individual members on organisational development, external communications and the mobilisation and management of funds (see also points on Worksheet D).
Output 1 Action Point 2 | Proposal on new SAVI recruitment or mobilisation of locally available, external TA by March/April 2012.
Output 1 Action Point 3 | For those Advocacy Partnerships with demonstrated readiness make available a package of additional support during the first half of 2012. Evidence of the usefulness of this support will be tracked by the 2012 Annual Review.
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.2
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | 2.1 Strength of civil society partnerships for engagement in government budget and planning:
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone mid 2011: 2 out of 5 advocacy partnerships have sufficient linkages and combined skills and resources to achieve their planned objectives for 2010/11. Milestone end 2012: 3 out of 5 of advocacy partnerships have sufficient linkages and combined skills and resources to achieve their planned objectives for 2011/12.
Progress made in the period covered by this review, including numbers | Based on the MTR's own assessment 2 out 5 APs are achieving their planned objectives (Enugu: no; Jigawa: no; Kaduna: no (previously had been an effective group, but no longer meeting on its own initiative); Kano: yes; Lagos: LACSOP yes, PaGG no, but overall for Lagos state - yes)
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | 2.2 Dependency on / independence from SAVI support.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone mid 2011: 3 out of 5 advocacy partnerships progressed from incubation to call-down support; none progressed from call-down support to SAVI community of practice. Milestone end 2012: 3 out of 5 advocacy partnerships progressed from incubation to call-down support; of which 1 progressed from call-down support to SAVI community of practice.
Progress made in the period covered by this review, including numbers | SAVI is well behind track on this milestone. The MTR concurs with SAVI's assessment (see quarterly progress reports July-Sept 2011) that only 1 out of 5 of the budget tracking groups (Lagos LACSOP) has reached the call down stage. SAVI consider that the Kaduna Know Your Budget (KYB) partnership has slipped back from call down to incubation since the 2011 Annual Review. The MTR's assessment is that this group is developing independently of SAVI, but more in the form of a professional association rathe than SAVI's model of an Advocacy Partnership.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | 2.3 Civil society partners active support of replication of the approach.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | SAVI are reformulating this indicator based on existing data fitted to a new set of milestones and scoring matrix for each state showing connections between Advocacy Partnerships and other stakeholders.
Progress made in the period covered by this review, including numbers | This indicator will be scored early in 2012. The MTR found several examples of the budget tracking (output 2) Advocacy Partnerships extending their skills and findings to the issues based (output 1) Advocacy Partnerships.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 3 | 0.5
Impact Weighted Score | 10 | 0.1
Justification for the Score | Although several of the budget tracking APs are newly established, the lack of development of the groups beyond the incubation stage (with the exception of LACSOP, and possibly Kano, which is on the cusp of call down) suggests that there are problems with SAVI's mode of engagement and this output will only be partly achieved.
Output 2 Recommendation 1 | Focus on addressing the problems of the less well performing Advocacy Partnerships under output 2 (particularly Kaduna and Enugu). On a case by case basis consider options of: 1) forming a broader and probably looser network of CSOs interested in budget/MTSS work that can be linked to the work of all of the SLPs, 2) encouraging some output 2 APs or individual members of APs to become professional service providers, 3) further strengthening links between output 2 and output 1 Advocacy Partnerships, and 4) transferring budget tracking/MTSS work to the output 1 APs.
Output 2 Action Point 1 | Finalise state-by-state proposals on strengthening output 2 work in coordination with other SLPs during first half of 2012.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | An enabling environment for policy advocacy & monitoring, and engagement in government budget & planning processes.
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | Given the central importance of output 3, and recommendations to expand media work we recommend the weighting is increased from 10% to 20%
Original or Revised Impact Weight (%) | 10%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.2
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | 3.1 Support from leadership in civil society, the media and state houses of assembly for voice and accountability initiatives actively supported by SAVI and its state partners.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Scoring matrix shown in main report.
Progress made in the period covered by this review, including numbers | The matrix has not yet been compiled, although narrative evidence from quarterly reports indicates that most leadership of civil society, the media and SHoAs are supportive of SAVI sponsored voice and accountability initiative. The milestone has been achieved.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | 3.2 Public understanding of the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Scoring matrix shown in main report
Progress made in the period covered by this review, including numbers | Not yet established. Previously SAVI had proposed to measure this indicator using the Citizen's Perception Survey, but are now suggesting that the indicator is collected by media partners as part of their assessment of the effectiveness of their civic education work. MTR found several good examples of SAVI supported media work that is seeking to strengthen citizens' understanding of and engagement with governance systems.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Level of demand side activity amongst SAVI partners on strengthening the governance related gender-enabling environment
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Proportion of partners working on strengthening the governance related gender-enabling environment (a new indicator based on DFID’s (2011) strategic vision for girls and women. Baseline currently being established. Milestones not yet establised.
Progress made in the period covered by this review, including numbers | Not yet established.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 2 | 0.75
Impact Weighted Score | 7.5 | 0.075
Justification for the Score | Because the proposed indicators have not yet been adequately developed or measured, this score is rather tentative, and is provided on the basis of the MTR team's impression of the progress made by SAVI against this output. SAVI has proven to be effective in brokering links between civil society, the media and State Houses of Assembly. In most states there does appear to be improved communication, understanding and willingness to interact between civil society, the media, State Houses of Assembly and the Executive. SAVI has been effective bringing about this change.
Output 3 Recommendation 1 | SAVI needs to give working with the media as much emphasis as its work with civil society and the State House of Assembly. Stepping up engagement with the media should include a focus on media development and building journalist's capacity to report on policy processes and public accountability.
Output 3 Action Point 1 | Implement contract amendment 3 provisions as soon as possible. Prepare a complete strategy and budget for additional scaling up work with the media by March 2012.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2 | Where conditions allow SAVI should scale up broader efforts to bring together civil society organisations, the media and State Houses of Assembly by replicating successful models such as the V&A platform in Kano, LACSOP in Lagos and the civil society group that engages with the Enugu State House of Assembly.
Output 3 Recommendation 3
Output 3 Action Point 2 | Scale up this work over next year where conditions allow.
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Improved state houses of assembly systems for transparency, public engagement and financial oversight.
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | In order to enable an increased weighting for output 3 it is recommended to reduce the output 4 weighting to 30%. This also reflects the MTR's view that engagement in the State House of Assembly is a long-term, high risk activity that will not generate the same dividends as SAVI's other outputs over the life of the programme. The MTR advises retaining a strong (30%) weighting to reflect the strategic importance of this output, but recommends a reallocation to output 3, which offers greater potential to deliver more immediate results.
Original or Revised Impact Weight (%) | 35%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.35
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | 4.1 Quality of systems for public access to information and processes in the house and representation of public interests by members (based on 2009 Organisational Capacity Assessment updated in 2011).
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 4 states score at least 2 out of 5 by mid to late 2011 (post elections), of which 1 state scores 3 out of 5.
Progress made in the period covered by this review, including numbers | Definite improvements have been recorded. The MTR review noted that in several states there is a change in attitude towards more openness, increased transparency and accountability of State House of Assembly and their members. However, according to the 2011 Organisational Capacity Assessment scores the milestone has not been reached. 2011 Organisational Capacity Assessment scores (2009 baseline in brackets): Enugu 1.5 (1); Jigawa 1.5 (1); Kaduna 1.5*(1); Kano 2 (1); Lagos 3* (1). Note that the Kaduna and Lagos scores are preliminary assessment based on SAVI internal review rather than a full State House of Assembly self-assessment, which will be completed shortly. The reason for the failure to meet this milestone may relate to the turnover in House members and the disruption caused by the elections.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | 4.2 Quality of systems for recruitment and retention of house support staff and aides (based on 2009 Organisational Capacity Assessment updated in 2011).
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 4 states score at least 2 out of 5 by mid 2011 (post elections), of which 1 state scores 3 out of 5.
Progress made in the period covered by this review, including numbers | Good progress has been made, but the mid 2011 milestone has not quite been reached. 2011 Organisational Capacity Assessment scores (2009 baseline in brackets): Enugu 1.5 (1); Jigawa 1.5 (2); Kaduna 2*(1); Kano 2 (2); Lagos 3* (2). Note that the Kaduna and Lagos scores are preliminary assessment based on SAVI internal review rather than a full State House of Assembly self-assessment, which will be completed shortly. Much of the improvement in this indicator is explained by the progress made in establishing and legislating for House Service Commissions.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | 4.3 Quality of systems for induction and monitoring of compliance with house rules & procedures (based on 2009 Organisational Capacity Assessment updated in 2011).
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 3 states score at least 2 out of 5 by mid to late 2011 (post elections), of which 1 state scores 3 out of 5.
Progress made in the period covered by this review, including numbers | The mid 2011 milestone has been reached. 2011 Organisational Capacity Assessment scores (2009 baseline in brackets): Enugu 1.5 (1); Jigawa 3.5 (1); Kaduna 1.5*(1); Kano 2 (2); Lagos 3* (1). Note that the Kaduna and Lagos scores are preliminary assessment based on SAVI internal review rather than a full State House of Assembly self-assessment, which will be completed shortly. SAVI notes that the scores are slightly higher than expected at this stage because of the success of the induction process for new SHoA members
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | 4.4 Quality of systems for scrutinizing public financial documents in the house (based on 2009 Organisational Capacity Assessment updated in 2011)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 4 states score at least 2 out of 5 by mid to late 2011 (post elections), of which 2 states score 3 out of 5.
Progress made in the period covered by this review, including numbers | There has been some improvement, but the mid 2011 milestone has not been reached. 2011 Organisational Capacity Assessment scores (2009 baseline in brackets): Enugu 2 (2); Jigawa 2 (1); Kaduna 1.5*(1); Kano 2 (1); Lagos 2* (1). Note that the Kaduna and Lagos scores are preliminary assessment based on SAVI internal review rather than a full State House of Assembly self-assessment, which will be completed shortly. SAVI notes that all 5 states have improved on scrutiny, procedure and timing of the appropriation bill, but scored low on audit & query and member's capacity for financial and performance analysis. Scores are not likely to improve in late 2011 because of the turnover in House members.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 3 | 0.5
Impact Weighted Score | 17.5 | 0.175
Justification for the Score | On the basis of a strict reading of progress against the output 4 indicators and milestones, the assessment is that targets are being 'partly achieved' meriting a rating of 3. However, SAVI has achieved significant results in a difficult context, particularly in relation to human resource management for house staff and induction processes for new members. Less progress has been made in strengthening financial oversight mechanisms and improving access to information. If the ARIES system allowed intermediate scores it would be appropriate to provide a rating of 2.5 for this output.
Output 4 Recommendation 1 | Following the 2011 elections there is a significant opportunity to step up engagement with new members of the State Houses of Assembly. This should focus particularly on building capacity in public financial oversight, constituency relations and strengthening committees working on issues relevant to SAVI's Advocacy Partnerships.
Output 4 Action Point 1 | Develop further the global strategy and priorities for each state for working with State Houses of Assembly. This should focus in particular on opportunities to work with members of the House, strengthening constituency relations, options for supporting Committee work, and actions to enable greater transparency and accountability in the House. Consider appointing a dedicated SHoA officer for each SAVI state office.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2 | SAVI's partnerships with State Houses of Assembly need to be placed on a more formal footing with a jointly agreed programme of support and commitments from both sides on resources to be applied building in the need for flexibility in timing.
Output 4 Recommendation 3 | Identify ways to embed the experience gained by SAVI of working with State Houses of Assembly within Nigerian organisations (National Assembly and/or others).
Output 4 Action Point 2 | Develop and agree work programmes with three out of five State Houses of Assembly by end of first quarter of 2012.
Output 4 Action Point 3 | For consideration during 2012
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5 | Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches.
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | Some of the work under output 5 covers internal project responsibilities, which are part of everyday management rather than an external deliverable. Reducing the weighting for this output to 10% will enable a greater weighting for the critical output 3.
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.3
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | 5.1 Accessibility of lessons learnt which are relevant and useful to other development partners.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Systems in place for routine capture of key learning, frameworks in place for interpreting lessons for a wide range of partners needs, with 25% of documentation focused on meeting external communication needs compared to 75% on internal programme M&E and planning.
Progress made in the period covered by this review, including numbers | There is a strong emphasis on self reflection and lesson learning processes within SAVI state teams and in SAVI's work with partners. Lessons are learned and shared internally and extended to civil society and SHoA partners. Different state teams report that between 5% and 60% of their documentation is focussed on meeting external communication needs. The MTR's assessment is that SAVI's internal lesson learning is working well, but external communication is still relatively weak. SAVI's approach, lessons learned, and evidence of change needs to be presented in a simpler, non technical and more accessible format suited to different types of audience.
from the pere
Indicator 2 (leave blank if standard indicator) | 5.2 Commitment of other development partners to replicate key aspects of SAVI and its state partners' approaches.
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | 3 other development partners in each SAVI state express interest in learning from SAVI through invitation to knowledge sharing events, joint working on advocacy partnerships or active promotion of a key aspect of SAVI and its state partners’ approaches by mid-2011.
Progress made in the period covered by this review, including numbers | SAVI reports that all 5 SAVI state teams now have at least 3 joint working relationships or other formal means of sharing lessons with development partners in their own states. Enugu: joint working with ESSPIN & PATHS2, interest from UNICEF, J4A (V&A), Living Earth Foundation and Water Aid. Jigawa: joint working with PATHS2 (MNCH), ESSPIN (SHP) & EU-SRIP (PMP), invitation from PRRINN-MNCH (V&A). Kaduna: joint working with ESSPIN (GWG-MTSS) & PATHS2 (MNCH), invitation by SPARC (GWG-MTSS), invitation from PRRINN-MNCH (V&A). Kano: joint working with PATHS2 (MNCH) and SPARC, invitations from ESSPIN & PRRINN-MNCH (V&A). Lagos: active promotion by ESSPIN & PATHS2, invitation from UNICEF (LACSOP). The MTR review concurs with this assessment, but finds that other SLPs have a rather mixed record in taking on board essential elements of SAVI's approach.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 5 | 3 | 0.5
Impact Weighted Score | 7.5 | 0.075
Justification for the Score | Due to the weakness of external communication and some remaining issues with cross SLP coordination Output 5 seems likely to be only partially achieved. Provided that human resources are available to SAVI there are good prospects to improve this score over the next year as SAVI steps up its external communication work.
Output 5 Recommendation 1 | Develop new external communication tools including succinct presentation of the SAVI approach, results achieved to date and stories of change. Develop tools to capture recent challenges and achievements for internal and external audiences (e.g. quarterly bulletin, development of extranet/ website). Step up communications efforts towards non SLP development partners. Increase SAVI's presence in national and state level CSO fora.
Output 5 Action Point 1 | SAVI to have revised external communication strategy in place by mid 2012
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2 | Revise external communication strategy during first quarter of 2012.
Output 5 Action Point 3 | Revise external communication strategy during first quarter of 2012.

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2012-01-18
Impact Weighting (must = 100) | 100%
Total Impact Score | 57.5 | 0.575
Output Risk | High | 1.45
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study
Government assessment
Joint donor review
Independent consultant review | X
DFID staff review
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant | X
Donor partners
DFID staff
Donor partners | SPARC, ESSPIN & PATHS2 in Abuja, Kaduna, Kano, Jigawa, Lagos and Enugu. GEMS 3 in Abuja and Lagos.
Comment here on the Method of Scoring and Scoring Responsibility. | The scoring is based on visits to all five states and detailed interviews with SAVI and partners engaging in each of the five output areas. SAVI's own indicators have been cross checked with the MTR team's own experience, but not subject to in depth data validation. The MTR team and IMEP are responsible for scoring.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | The MTR observed many good examples of coordination between SAVI and other SLPs, but these arise on an ad hoc basis mainly through good interpersonal relations. SAVI usually has a proactive attitude towards coordinating with other SLPs, but other SLPs are not always receptive. Several problematic cases were also encountered (ESSPIN Enugu, PATHS2 Kaduna, SPARC Kano – historically), which indicates systemic weaknesses in cross SLP coordination. Coordination structures like the SLP monthly meetings and DFID-SLP quarterly meetings generally seem to be weak and poorly managed. DFID regional/state coordinators need to play a stronger role in coordinating between SLPs, and should be empowered to enforce joint planning and implementation. There is no mechanism to address failures of coordination and to enforce a solution. SAVI is not well linked to government because it lacks a host ministry or institutional counterpart. SAVI's oversight bodies (and the State Steering Committee) could help to link SAVI more closely to government, but these bodies are not functioning well in most states.
Working with Partners Recommendation 1 | MTR finds that SAVI is sufficiently proactive in seeking to work with other SLPs. Weaknesses often arise due to shortage of SAVI staff time. Improved resourcing of SAVI state offices should help to address this, but receptiveness of other SLPs will also need to improve.
Working with Partners Action Point 1 | No SAVI specific action to follow from this review (see MTR suite review for cross SLP follow up)
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | SAVI is employing many elements of good practice in its civil society advocacy work, and undertaking innovative work, particularly in relation to the State Houses of Assembly. These lessons need to be documented in a way that is understandable and accessible to organisations working on voice and accountability elsewhere in Nigeria and internationally.
Best Practice / Innovation Recommendation 1 | Lessons learned from different DFID voice and accountability programmes are not being adequately shared between countries. However, some links developing between SAVI and STAR Ghana. A cross country review of good practice and establishment of an informal network of V&A projects should be considered by DFID.
Best Practice / Innovation Action Point 1 | DFID to consider recommendation for cross country review and network of V&A projects.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | SAVI's human resources at state level are overstretched, and this problem may worsen if staff are diverted to the new Northern states. The provisions for an additional State Programming Officer for each state under SAVI's contract amendment three will go some way in addressing this constraint, but scaling up work with the media and State Houses of Assembly will require additional resources.
Project Management Recommendation 1 | Recruit 1 additional SPO through contract amendment 3. Consider recruiting an additional State Programming Officer or advisor (for media or SHoA work) on the basis of a new contract amendment.
Project Management Action Point 1 | Present a proposal for increased human resources at state level by end of March 2012
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | See MTR report
Key issues, points of information or additional comments that may be useful for this or other project teams. | See MTR report
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
SAVI Project Memorandum
SAVI June 2009 inception review report
SAVI February 2010 mini review report
SAVI June 2010 output-to-purpose review report
SAVI June 2011 annual review
SAVI Logframes – programme and all 5 states
SAVI Workplans – programme and all 5 states
SAVI Quarterly Progress Reports (July 2010-September 2011) – programme and all 5 states
SAVI Governance Baseline 2010
SAVI State Drivers of Change Assessments
Political Economy Analysis updates for each state
Evidence Recommendation 1 | SAVI State Quarterly Progress Reports are overly long, presentation is complex and the process takes up too much staff time. In discussion with DFID and IMEP a simpler and shorter (max 10 pages) report format for state teams' quarterly reporting should be developed.
Evidence Action Point 1 | SAVI to propose simpler quarterly reporting format for state teams for implementation in the next reporting period. IMEP and DFID to offer guidance.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2 | SAVI to provide expenditure data on a sub-output basis to enable more sophisticated value analysis.
Evidence Recommendation 3 | A data validation exercise for the Governance Baseline and other sources of logframe evidence and indicators should be undertaken by IMEP prior to the 2012 Governance Baseline update.
Evidence Recommendation 4 | The 2012 Annual Review should be scheduled for the third quarter of 2012 to allow for time for finalising the logframe, completing scheduled CSO/SHoA assessments and public perception/awareness surveys, and to complete the data quality review. 2012 Annual Review to cover all of the logframe, but should focus particularly on progress in new northern states and implementation of key MTR recommendations.
Evidence Action Point 2 | SAVI to begin reporting by sub-output during first quarter of 2012
Evidence Action Point 3 | IMEP to validate Governance Baseline methodology and other data sources before 2012 update. Validation of results during and after 2012 update.
Evidence Action Point 4 | IMEP and DFID to agree timing of next Annual Review by March 2012

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | Many of the legislative, policy and institutional changes promoted through SAVI will remain after the project closes (though policy reversal is always possible). Capacity to engage in advocacy amongst CS groups members of APs will also remain. The sustainability of the current membership of Advocacy Partnerships is a less relevant consideration. It is to be expected that they will change with time as issues evolve: some APs will continue; others will disappear. Systems strengthening within the State Houses of Assembly should generate lasting benefits, but there is a high risk that such systems will decay following the closure of SAVI. SAVI's experience in working with State Houses of Assembly also risks being lost without a Nigerian counterpart organisation working closely with SAVI on SHoA programmes. The weakness of SAVI's oversight and advisory bodies is another obstacle to SAVI's experience being retained in Nigeria.
Continued.
Sustainability Recommendation 1 | See output recommendations 1.3, 2.1, 4.3 and risk recommendation 2
Sustainability Action Point 1 | See output actions points 1.3, 2.1, 4.3 and risk action point 2
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | 2012 SAVI Annual Review should be completed after the completion of the 2012 Governance Baseline and 2012 Citizen's Perception Survey to allow thorough assessment of achievement of goal level indicators. | IMEP
A1: Purpose
R1 | Step up work in the additional northern states in partnership with PRRINN-MNCH and SPARC, but take careful account of the risks identified in section 2.6 and security issues discussed in section 2.8 of the report. | SAVI in partnership with PRRINN-MNCH and SPARC
R2 | Review purpose statement according to logframe recommendation 1 below. | SAVI with IMEP support
A1: Risk
R1 | There is an increasing security risk posed by Boko Haram attacks and associated intercommunal tension. Recommendations: (1) SAVI requires external support to review and cost security arrangements for operations in northern Nigeria. (2) DFID needs to strengthen its capacity and support for providing ongoing security-related information and support to its projects operating in northern Nigeria. (3) With rising inter-communal tensions SAVI needs to develop in affected states an explicit and documented conflict strategy (see section 2.8 of report for more discussion). | SAVI/DFID
R2 | SAVI is exposed to a high risk that its actions will be perceived as interference in local politics (a scenario that has already played out in Kaduna). This risk is heightened by the programme's weak connections to state government. SAVI should give urgent attention to revamping its oversight and advisory functions. The aim should be to restore the functions provided by the State Advisory Panel or Technical Executive Committee, but probably through different and less formal arrangements. SAVI should give urgent attention to revamping its oversight and advisory functions. The aim should be to restore the functions provided by the State Advisory Panel or Technical Executive Committee, but probably through different and less formal arrangements. The types of functions that need to be ensured include: (1) a representational function (via influential and well-respected persons of the state) to give visibility and certain level of credibility and local ownership, (2) a hands-on function via individuals who offer strong expertise in the key areas of SAVI’s work and, hence, can play a proactive role in overseeing programme management, and (3) an oversight function geared towards ensuring that SAVI pursues its work in a manner that is consistent with its own mission, local development policies and broader aspects of UK-Nigeria cooperation. | SAVI
A1: Logframe
R1 | IMEP proposes a final round of logframe revisions in discussion with SAVI to remove remaining inconsistencies to be completed and endorsed by DFID by end March 2012. preliminary recommendations on logframe adjustments discussed in accompanying report, but subject to confirmation through the logframe review. | SAVI with IMEP support
R2 | 0 | SAVI with IMEP support
R3 | 0 | SAVI with IMEP support
A1: DSOs
R1 | 0
A1: Cross-Cutting Markers
R1 | 0
A2: Outputs
R1.1 | Within the next 3-6 months SAVI needs to decide whether it will take on any new advocacy partnerships. Beyond this point there is too little time remaining to achieve a sustainable result within the project lifetime. The broad recommendation of the MTR is to consolidate progress made with the existing APs, but a few changes and additions may be needed. There is an opportunity in Lagos to step up work on health and education (through LACSOP, PaGG or other groups) and so strengthen synergies with PATHS2 and ESSPIN. The MTR review is concerned that the proposed approach to building a WATSAN AP in Enugu is too localised in scale to fit with SAVI’s model of long-route accountability. The review also suggests considering narrowing the focus of the Climate Change partnership in Lagos around flood prevention and management | SAVI
R1.2 | As the Advocacy Partnerships mature they need more technical, research, policy and scientific support to engage credibly in state policy processes. SAVI has been effective in providing support on advocacy skills and organisational development, but needs to be able to make available to the APs more technical expertise on policy content, and to work to develop local TA capacity. | SAVI
R1.3 | SAVI needs to do more to ensure the sustainability and replicability of the work of its Advocacy Partnerships. This requires working more with APs and individual members on organisational development, external communications and the mobilisation and management of funds (see also points on Worksheet D). | SAVI
R2.1 | Focus on addressing the problems of the less well performing Advocacy Partnerships under output 2 (particularly Kaduna and Enugu). On a case by case basis consider options of: 1) forming a broader and probably looser network of CSOs interested in budget/MTSS work that can be linked to the work of all of the SLPs, 2) encouraging some output 2 APs or individual members of APs to become professional service providers, 3) further strengthening links between output 2 and output 1 Advocacy Partnerships, and 4) transferring budget tracking/MTSS work to the output 1 APs. | SAVI
R3.1 | SAVI needs to give working with the media as much emphasis as its work with civil society and the State House of Assembly. Stepping up engagement with the media should include a focus on media development and building journalist's capacity to report on policy processes and public accountability. | SAVI with IMEP support
R3.2 | Where conditions allow SAVI should scale up broader efforts to bring together civil society organisations, the media and State Houses of Assembly by replicating successful models such as the V&A platform in Kano, LACSOP in Lagos and the civil society group that engages with the Enugu State House of Assembly. | SAVI
R4.1 | Following the 2011 elections there is a significant opportunity to step up engagement with new members of the State Houses of Assembly. This should focus particularly on building capacity in public financial oversight, constituency relations and strengthening committees working on issues relevant to SAVI's Advocacy Partnerships. | SAVI
R4.2 | SAVI's partnerships with State Houses of Assembly need to be placed on a more formal footing with a jointly agreed programme of support and commitments from both sides on resources to be applied building in the need for flexibility in timing. | SAVI
R4.3 | Identify ways to embed the experience gained by SAVI of working with State Houses of Assembly within Nigerian organisations (National Assembly and/or others). | SAVI
R5.1 | Develop new external communication tools including succinct presentation of the SAVI approach, results achieved to date and stories of change. Develop tools to capture recent challenges and achievements for internal and external audiences (e.g. quarterly bulletin, development of extranet/ website). Step up communications efforts towards non SLP development partners. Increase SAVI's presence in national and state level CSO fora. | SAVI
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | MTR finds that SAVI is sufficiently proactive in seeking to work with other SLPs. Weaknesses often arise due to shortage of SAVI staff time. Improved resourcing of SAVI state offices should help to address this, but receptiveness of other SLPs will also need to improve.
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | Lessons learned from different DFID voice and accountability programmes are not being adequately shared between countries. However, some links developing between SAVI and STAR Ghana. A cross country review of good practice and establishment of an informal network of V&A projects should be considered by DFID. | SAVI/DFID
R3 | 0
Project Management
R1 | Recruit 1 additional SPO through contract amendment 3. Consider recruiting an additional State Programming Officer or advisor (for media or SHoA work) on the basis of a new contract amendment.
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | SAVI State Quarterly Progress Reports are overly long, presentation is complex and the process takes up too much staff time. In discussion with DFID and IMEP a simpler and shorter (max 10 pages) report format for state teams' quarterly reporting should be developed. | SAVI with IMEP support
R2 | SAVI to provide expenditure data on a sub-output basis to enable more sophisticated value analysis. | IMEP
R3 | A data validation exercise for the Governance Baseline and other sources of logframe evidence and indicators should be undertaken by IMEP prior to the 2012 Governance Baseline update. | IMEP
R4 | The 2012 Annual Review should be scheduled for the third quarter of 2012 to allow for time for finalising the logframe, completing scheduled CSO/SHoA assessments and public perception/awareness surveys, and to complete the data quality review. 2012 Annual Review to cover all of the logframe, but should focus particularly on progress in new northern states and implementation of key MTR recommendations. | IMEP
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | See output recommendations 1.3, 2.1, 4.3 and risk recommendation 2
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | Agree timing of 2012 Governance Baseline update, 2012 Citizen's Perception Survey and 2012 Annual Review by end March 2012. IMEP to plan data validation exercise including coverage of 2012 Governance Baseline update. | IMEP
A1: Purpose
AP1.1 | SAVI in discussion with DFID needs to present a plan for human resource deployment in the new states, and explain how the risk of spreading human resources too thinly will be mitigated. The problem of insecurity in Yobe is an additional concern that requires a decision to be taken in the near term about the feasibility of beginning work in this state. | SAVI and DFID
AP1.2 | Review logframe and seek DFID approval by end March 2012 | SAVI with support from IMEP
A1: Risk
AP1.1 | In view of the urgency of the issue action to be taken on the above three recommendations by end March 2012. | SAVI/DFID
AP1.2 | Revamped Oversight/advisory bodies to be in place by July 2012 | SAVI
A1: Logframe
AP1.1 | Revisions to logframe before end March 2012 | SAVI with support from IMEP
A1: DSOs
AP1.1 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
A2: Outputs
AP1.1 | Final decisions on new APs or changes to AP focus by mid 2012. | SAVI
AP1.2 | Proposal on new SAVI recruitment or mobilisation of locally available, external TA by March/April 2012. | SAVI
AP1.3 | For those Advocacy Partnerships with demonstrated readiness make available a package of additional support during the first half of 2012. Evidence of the usefulness of this support will be tracked by the 2012 Annual Review. | SAVI
AP2.1 | Finalise state-by-state proposals on strengthening output 2 work in coordination with other SLPs during first half of 2012. | SAVI
AP3.1 | Implement contract amendment 3 provisions as soon as possible. Prepare a complete strategy and budget for additional scaling up work with the media by March 2012. | SAVI with support from IMEP
AP3.2 | Scale up this work over next year where conditions allow. | SAVI
AP4.1 | Develop further the global strategy and priorities for each state for working with State Houses of Assembly. This should focus in particular on opportunities to work with members of the House, strengthening constituency relations, options for supporting Committee work, and actions to enable greater transparency and accountability in the House. Consider appointing a dedicated SHoA officer for each SAVI state office. | SAVI
AP4.2 | Develop and agree work programmes with three out of five State Houses of Assembly by end of first quarter of 2012.
AP4.3 | For consideration during 2012
AP5.1 | SAVI to have revised external communication strategy in place by mid 2012 | SAVI
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | No SAVI specific action to follow from this review (see MTR suite review for cross SLP follow up)
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.2 | DFID to consider recommendation for cross country review and network of V&A projects. | DFID
AP1.3 | 0
Project Management
AP1.1 | Present a proposal for increased human resources at state level by end of March 2012
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | SAVI to propose simpler quarterly reporting format for state teams for implementation in the next reporting period. IMEP and DFID to offer guidance. | SAVI with IMEP support
AP1.2 | SAVI to begin reporting by sub-output during first quarter of 2012 | IMEP
AP1.3 | IMEP to validate Governance Baseline methodology and other data sources before 2012 update. Validation of results during and after 2012 update. | IMEP
AP1.4 | IMEP and DFID to agree timing of next Annual Review by March 2012
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | See output actions points 1.3, 2.1, 4.3 and risk action point 2
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3