The Independent Monitoring and Evaluation Project for the State Level Programmes (IMEP)

Mid Term Review –
State Accountability and Voice Initiative (SAVI)

Client: UK Department for International Development (DFID)
Revised Draft
Abuja and Rotterdam, 18 January 2012

Funded by UKaid from the Department for International Development

Gareth Williams
Victor Adetula
Maisha Strozier
Dirk Van Esbroeck
David Hoole (value for money annex)

Abuja and Rotterdam, 18 January 2012

Table of Acronyms
AP	Advocacy Partnership
ESSPIN	Education Sector Support Programme in Nigeria
FMCH	Free Maternal and New-born Child Health
IE	Inclusive Education Advocacy Partnership (Enugu)
IMEP	Independent Monitoring and Evaluation Project
GWG	Gender Working Group (Kaduna AP)
J4A	Justice for All Programme
LACSOP	Lagos State Civil Society Partnership
LGA	Local Government Area
MDAs	Ministries, departments and agencies
MNCH	Maternal and New-born Child Health
MTR	Mid Term Review
MTSS	Medium Term Sectoral Strategy
SAVI	State Accountability and Voice Initiative
SH	School Health Advocacy Partnership (Jigawa)
PaGG	Partnership for Good Governance (Lagos AP)
PATHS2	Partnership for Transforming Health Systems Phase II
PRRINN-MNCH	Partnership for Reviving Routine Immunization in Northern Nigeria, Maternal Newborn and Child Health Initiative
PWD	People with Disabilities
SDoC	State level Drivers of Change analysis
SHoA	State House of Assembly
SLP	State Level Programme
TA	Technical Assistance
V&A	Voice and Accountability

Executive Summary
This report presents the results of the Mid Term Review of the DFID Nigeria State Accountability and Voice Initiative (SAVI). Key findings and recommendations are summarised below:

SAVI is performing well in contributing to its purpose of improving voice and accountability processes in civil society, State Houses of Assembly and government. Positive trends in the effectiveness of demand-side advocacy have been recorded in several states. SAVI is already able to demonstrate that it has contributed to around 11 improvements in policy and implementation at state level. In a few states there is evidence of changes in resource allocation following advocacy initiatives by SAVI partners.

SAVI is broadly on track to meet its output level milestones, although some outputs have only been partly achieved. ARIES scores for each output are shown below together with the derived total impact score.

Output	Current weighting	ARIES Score	MTR recommendation on future weighting
1 Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy & monitoring	20%	2 / Mostly achieved	20%
2 Civil society demonstrates a replicable and sustainable approach to engagement in government budget & planning processes	20%	3 / Partly achieved	20%
3 An enabling environment for policy advocacy & monitoring, and engagement in government budget & planning processes	10%	2 / Mostly achieved	20%
4 Improved state houses of assembly systems for transparency, public engagement and financial oversight	35%	3 / Partly achieved	30%
5 Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches	15%	3 / Partly achieved	10%
Total Impact Score		57.5%

SAVI has been particularly successful under output 1 in demonstrating a replicable and sustainable approach to issue based policy advocacy and monitoring. SAVI has succeeded in bringing together civil society organisations into partnerships that are increasingly capable of engaging in effective policy and advocacy and monitoring. The groups are mostly achieving the objectives they have set for themselves, and have in several cases succeeded in influencing policy and monitoring its implementation. SAVI has developed a viable model for promoting issue based policy advocacy and monitoring that avoids the risk of creating dependence on donor support and distorting civil society agendas. This demonstrates the value of SAVI’s work in behind-the-scenes brokering of networks and partnerships, and the nurturing of Advocacy Partnerships through the use of training, mentoring and selective funding of partners’ activities. Recommendations for the next phase of SAVI’s work under output 1 centre on the need to make available to the Advocacy Partnerships greater support on technical, policy and research issues, and strengthen their capacity in resource management and mobilisation.

While some of the output 2 Advocacy Partnerships working on budget and planning processes are performing well, several have not yet proven to be effective. It is recommended that SAVI explores alternative models for developing the less well performing output 2 Advocacy Partnerships.

Very promising results have been achieved under output 3 in particular the strengthening of communication and interaction between civil society, the media and State Houses of Assembly. There are also several good examples of SAVI supported media work (for example radio programmes in Jigawa and Enugu) that is seeking to strengthen citizens' understanding of and engagement with governance systems. In view of SAVI’s demonstrated effectiveness and the critical importance of output 3 it is recommended to increase the logframe weighting to 20% for this output. This should be accompanied by a stepping up of SAVI’s engagement with the media including media development work.

SAVI has achieved notable progress in strengthening State House of Assembly systems for transparency, public engagement and financial oversight. However, its targets have only partly been achieved. Over the second half of the SAVI programme there are good opportunities for SAVI to engage more closely with State Houses of Assembly. This will require a shift towards a more programmatic approach and greater focus on working with the Members of the House in addition to the legislative staff, who have been the main target of assistance so far. In spite of these opportunities it must be recognised that working with State Houses of Assembly carries risks and will require long term engagement across electoral cycles and beyond the lifespan of the SAVI programme.

SAVI’s external communication work under output 5 is beginning to yield results measured in terms of other development agencies and projects replicating elements of SAVI’s approach. However, there is still significant room for improvement in SAVI’s external communication work and there is a need to engage with a wider range of partners.

The Mid Term Review finds that SAVI offers good value for money at each of the three levels of economy, efficiency and effectiveness. A full assessment is not possible because of the absence of reliable expenditure data by sub-output. However, there are indications that SAVI has been able to deliver its outputs in an economical and cost-efficient manner. There is emerging case study evidence of very good value for money at the effectiveness level.

The SAVI programme is generally well managed and benefits from having highly committed and professional staff. One weakness that should be addressed in the near term is generally poor-functioning of SAVI’s oversight and advisory bodies at state level. The MTR also found that SAVI’s state teams are overstretched, and will not be able to take on new tasks without additional human resources. The calls for a modest increase in staffing at state level in order to step up areas of work recommended by this review. The value for money assessment has indicated that increasing staff resources at state level could be achieved at relatively low marginal cost and could potentially deliver much improved results.

The MTR has assessed SAVI’s plans for engaging in the three additional northern states. It finds the immediate proposal for joint working with PRRINN-MNCH to be workable, but warns that SAVI will need to adapt to a different model of working and more rapid delivery of results. The northern expansion carries particular risks if it results in a diversion of overstretched human resources away from SAVI’s existing states.

The worsening security situation in the north of Nigeria is a matter of great concern and points to the need for a review of security arrangements and practices.

# Introduction
## Structure of the report
This report presents the findings of the Mid Term Review of DFID Nigeria’s State Accountability and Voice Initiative (SAVI) following a three week mission in November 2012. The main part of the report is structured around standard OECD DAC evaluation criteria: Relevance, Effectiveness, Sustainability and Efficiency. Additional sections address programme oversight and management arrangements, issues surrounding the proposed expansion of the SAVI programme into three additional northern states and SAVI’s treatment of gender and social inclusion. Value for money issues have been addressed under sub-headings in the sections covering effectiveness and efficiency. A separate annex on value for money assessment is also provided. Conclusions, lessons and recommendations are presented in section 3.

## Characteristics of the SAVI programme
The State Accountability and Voice Initiative (SAVI) is one of five interlocking sector and governance State Level Programmes (SLPs) financed by the United Kingdom’s (UK) Department for International Development (DFID). It is a six year programme running from August 2008 to August 2014 with a total budget of £21.5 million. SAVI currently focuses on 5 states, (Enugu, Jigawa, Kaduna, Kano and Lagos with small scale activities starting in Ekiti). SAVI has expanded into 3 additional Northern states (Katsina, Yobe and Zamfara) from October 2011. The programme is implemented by a consortium of consulting companies led by GRM international. SAVI has offices in Abuja and in each of the 5 states, which operate separate programmes under decentralised management arrangements.

SAVI is a demand side programme that seeks to harness sources of pressure for improved governance. Its purpose statement is that “Civil society, State Houses of Assembly and government demonstrate improved voice and accountability processes”. SAVI has been conceived as a demonstration programme to test particular models for promoting voice and accountability and to encourage replication of these.

The programme aims to deliver the following 5 outputs (from October 2011 logframe):

1	Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy and monitoring;
2	Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes;
3	An enabling environment for policy advocacy and monitoring, and engagement in government budget and planning processes;
4	Improved state houses of assembly systems for transparency, public engagement and financial oversight;
5	Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches.

## Methodology
### Sources of evidence
This review was carried out by a four person, Nigerian and International team led by Gareth Williams. A Value for Money specialist was also attached to the team for part of the duration of the mission. The mission began with a briefing by DFID-Nigeria and initial meeting with SAVI and other SLPs. The team then began a series of 5 state visits each lasting up to four days and consisting of meetings with SAVI state teams, other SLPs in the state, DFID’s State or Regional Coordinator, members of SAVI’s advisory and oversight bodies, civil society organisations participating in SAVI’s Advocacy Partnerships, journalists, Members of the State Houses of Assembly and legislative staff. All of the MTR team members visited Kaduna together, and then split into two subgroups to cover the remaining four states. At the end of each state visit the MTR team conducted a short feedback session with SAVI’s state teams. Final debriefing sessions were held in Abuja with DFID and SAVI. In total the Mid Term Review team held more than 100 meetings (see Annex C). It also reviewed the project’s extensive literature and progress reports.

### Approach to assessing value for money
This review includes an assessment of whether SAVI is providing value for money. It provides some evidence on the economy, efficiency and effectiveness of the programme, but is not able to provide precise measures of these. A major constraint has been the absence of reliable financial data disaggregated by sub output, which was not foreseen as a requirement in SAVI’s original contract, but has been identified by this MTR as being an information gap that should be addressed. This makes it difficult to map expenditure to particular inputs and outputs. In spite of these limitations, it has been possible to provide some evidence on the following aspects of value for money:

To what extent are the programmes outputs delivering outcomes (effectiveness)? What are the costs and benefits of delivering particular outcomes?

What level of programme inputs is required to deliver a specified output (efficiency)?

What is the cost of the programme’s inputs (economy)?

Would value of money be increased by reallocating resources between states and between outputs?

# Main Findings
## Relevance
SAVI works to strengthen demand for better governance and to enhance engagement between state and non-state actors in policy, budget and planning processes. Studies of the Nigerian political economy have shown that both of these mechanisms are crucial drivers of improved governance. They are particularly relevant in the Nigerian context where pervasive patronage and easy access to oil revenues (which require no accountability towards taxpayers) have undermined public institutions and accountability, lowered citizen’s expectations of government and weakened relations between state and society.

Through its specific focus on the demand side of governance and enhancing state-society interaction, SAVI occupies a critical position in the suite of State Level Programmes. SAVI’s approach supports the other state level programmes working in health, education and public financial management, which act mainly on the supply side of governance reform. While PATHS2 and ESSPIN include demand-side activities, they work mainly to strengthen direct relations between groups of service users and service providers through so-called short route accountability. SAVI works exclusively on long route accountability, which concerns engagement in the policy process by organised civil society, the media and the State Houses of Assembly. Where programming is well coordinated, SAVI can operate in a complementary way to the other SLPs, and can bring important synergies by linking supply side reforms to demand side pressure.

SAVI has a well developed and coherent theory of change based on: (1) strengthening and mobilising sources of demand for improved governance, (2) facilitating links between key demand side actors (civil society, media and State Houses of Assembly), (3) encouraging interaction between demand side and supply side (government) actors, and (4) scaling up and replicating the model. SAVI refers to these steps as: (1) getting SAVI’s demand side partners’ respective houses in order, (2) breaking down barriers and building bridges between demand side actors (joint civil society, media and State House of Assembly action), (3) breaking down barriers between demand and supply side (joint civil society and government action), (4) leveraging more support (consolidating joint civil society/ government action) and (5) scaling up action, replication, critical mass for change. The theory is consistent with political economy understanding of how policy and institutional change occurs through the mobilisation of various sources of societal demand, as well as processes of state-society bargaining.

The SAVI programme aims to deliver five outputs, which target important elements of voice and accountability, including advocacy by civil society groups, creating an enabling environment for demand side governance and strengthening the State House of Assembly. These outputs and their logframe weightings are shown in table 1 below:

Table 2.1	The relative weighting of SAVI’s outputs
Output	Current weighting	MTR recommendation on future weighting
1 Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy & monitoring	20%	20%
2 Civil society demonstrates a replicable and sustainable approach to engagement in government budget & planning processes	20%	20%
3 An enabling environment for policy advocacy & monitoring, and engagement in government budget & planning processes	10%	20%
4 Improved state houses of assembly systems for transparency, public engagement and financial oversight	35%	30%
5 Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches	15%	10%

The current logframe weightings are used in SAVI reviews (including this MTR) to generate the total impact score. The weightings are also used by SAVI as a guide to the level of emphasis the programme should place on its different outputs. The MTR considers that the current weightings are generally appropriate, but that insufficient emphasis has been given to output 3, which is a factor that will substantially contribute to achieving results under other outputs and broader replication of SAVI’s approach. Output 3 also includes SAVI’s work with the media, which the MTR recommends should be scaled up. In order to increase the weighting for output 3 it is recommended to reduce slightly the weightings for outputs 4 and 5.

SAVI’s intervention logic is generally coherent and is based on a plausible results chain. The five outputs can be seen as individual parts of the outcome defined as “civil society, State Houses of Assembly and Government improving their voice and accountability processes.” In turn this is expected to contribute to enhancing the goal of increasing the “the efficiency and effectiveness of selected state level governments’ use of public resources”. While the MTR finds that SAVI’s logframe is generally sound, there are some presentational issues and problems with indicators and assumptions that need to be addressed (see section 3.4, suggested changes to the logframe).

The assumptions in the intervention framework at output, purpose and goal level are generally valid. However, some of the key risks exist at activity level and are not captured by the intervention framework assumptions because the logframe begins at output level. In practice SAVI’s activities are vulnerable to being disrupted by political events or changed relationships between SAVI and the state legislature or executive. The assumptions generally need to be brought up to date. For example, electioneering in 2011 is still regarded as a risk under the assumptions for outputs 1 and 2.

SAVI’s approach is consistent with analyses of Nigeria’s political economy, and has been tailored to the specific context of each state. Political Economy Analysis has been undertaken in 2009 and updated in 2011 as a cross-SLP exercise led by SAVI. Although there are some weaknesses in the political economy analysis methodology and the report presentation (to be addressed in the cross SLP review), these studies have generally proven to be useful to SAVI and its partners in helping to identify entry points and issues with political traction, understand risks and select partners to work with. SAVI has adapted to the different conditions and opportunities to engage with demand side actors, and has adjusted its approach in different states (see Annex A for state level reports).

There is some variation in the specific issues addressed by SAVI, although in practice most of SAVI’s state programmes are heavily tilted towards health and education. There are some exceptions, notably SAVI’s work on water and sanitation in Kano and Enugu, climate change in Lagos and People with Disabilities in Lagos (Table 2.2 lists the Advocacy Partnerships in the five states and the key issues they address). The selection of issues has been informed by state specific analyses (S-DoC studies), which in practice have identified similar issues in different states. It also appears that the issues have been selected on the basis of practicality, and a realisation that SAVI has limited resources and technical expertise and therefore needs to work in partnership with the other SLPs. While this has led to a certain narrowness and similarity in the issues addressed by SAVI, the Mid-Term Review finds that this focus has been appropriate given the resources available to SAVI and the logic of joint working through the suite of SLPs. This has presented opportunities to link SAVI’s advocacy expertise to the technical skills of the other SLPs, to draw on the expertise and data collected by other SLPs, and to make connections between long route accountability (promoted by SAVI) and short route accountability (promoted by PATHS2 and ESSPIN). These linkages need to be strengthened and should remain at the core of the SAVI programme. At the same time SAVI needs to be open opportunities to work on issues outside of health and education, particularly where there are opportunities to work in partnership with other DFID programmes, such as GEMS and ENABLE. The MTR team is concerned that there remains a certain vagueness about the issues which SAVI should address with different messages projected by DFID and SLP partners about the need to respond to local demand or to ensure complementarity with themes of the other SLPs. Stronger strategic steering by DFID is required to bring greater clarity to this issue.

Table 2.2	Issues Addressed by Advocacy Partnerships

State	Advocacy Partnerships and issues
Enugu	Maternal and New-born Child Healthcare MNCH (output 1) - conducts advocacy in favour of the adoption of a free MNCH care bill, but is also engaged in other issues related to the provision of basic health services. / Inclusive Education (output 1) – focussed on identifying and addressing issues that prevent children attending school / Water and Sanitation (output 1) – SAVI is considering engaging with a neighbourhood association that advocates on local water and sanitation issues / Participatory Budget and Planning Advocacy Partnership (output 2) – formed in Q1 2011
Jigawa	Maternal and New-born Child Healthcare MNCH (output 1) - conducts advocacy in favour of the adoption of a free MNCH care bill, but is also engaged in other issues related to the provision of basic health services / School Health Partnership (output 1) - deals both with issues related to education (provision of basis education, policy advocacy, education budget) and school health (school environment issues) / Project monitoring (output 2)- engaged in analysis budget compliance with the MTSS/ MTEP in 3 sectors – health, education, and water resources – group restarted in mid 2011
Kaduna	Maternal and New-born Child Healthcare MNCH (output 1) - conducts advocacy in favour of the adoption of a free MNCH care bill, but is also engaged in other issues related to the provision of basic health services. / Gender Working Group (output 1)– originally focussed on Gender and Education, but now takes a broader gender mainstreaming approach / Know Your Budget (output 2) – budget transparency and budget analysis
Kano	PPMNCH (Output 1) advocating for free maternal and new-born child healthcare / Wudil (Output 1) a regional water association advocating for the new water bill / COBTAK, the Coalition of Budget and Transparency Advocacy (Output 2)
Lagos	People with Disabilities (Output 1) focusing on the passage and implementation of the Special People’s Bill; / Climate Change (Output 1) working on a state policy framework for climate change adaptation and mitigation; / Lagos State Civil Society Partnership (LACSOP) (output 2) - a large civil society umbrella organisation which engages in MTSS and budget processes, as well as tracking the effectiveness of public policy and service delivery. / The Partnership on Good Governance (PaGG) (output 2) – undertaking similar work to LACSOP in three pilot LGAs

The Mid Term Review also finds that the issues selected by SAVI are particularly relevant to problems of gender and social inclusion. Seven out of ten of the output 1 Advocacy Partnerships are focused on issues that are highly relevant to gender and social inclusion. The strengths and limitations of SAVI’s approach to gender and social inclusion are discussed further in section 2.7.

## Effectiveness and impact
### Achievements against outputs

#### Output 1 – Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy and monitoring
This output concerns SAVI’s work in bringing together and strengthening the issue based Advocacy Partnerships (APs), raising the effectiveness of these groups in advocating for policy change and monitoring implementation, and demonstrating that the approach is sustainable and replicable. The logframe contains three indicators to assess progress against this output. For each of these the table below shows the present situation, the relevant milestones for the Mid Term Review and the MTR’s assessment of whether the milestones have been achieved.

Table 2.3	Progress in delivering output 1
Indicator	Present situation	Milestone mid 2011	Milestone end 2012
1.1 Strength of civil society partnerships for policy advocacy and monitoring.	According to MTR’s own assessment 7 out 10 advocacy partnerships are achieving their planned objectives. (Enugu: MNCH yes, IE no, WATSAN n/a; Jigawa: MNCH yes, SH yes; Kaduna: MNCH yes, GWG no; Kano: MNCH yes; Wudil yes; Lagos: Climate Change no, PWD yes)	4 out 10 advocacy partnerships have sufficient linkages and combined skills and resources to achieve their planned objectives for 2010/11 / Achieved	6 out of 10 advocacy partnerships have sufficient linkages and combined skills and resources to achieve their planned objectives for 2011/12. / Achieved
1.2 Dependency on / independence from SAVI support.	MTR agrees with SAVI's assessment (see SAVI's quarterly progress reports July-Sept 2011) that 8 out 10 advocacy partnerships are at the call down stage with one on the cusp of becoming a community of practice (Jigawa MNCH). Two groups are still at incubation (Enugu IE and MNCH - WATSAN was not counted for the purpose of this review).	8 out of 10 advocacy partnerships progressed from incubation to call-down support; of which 2 are progressing from call-down support to SAVI community of practice. / Target substantially met	Milestone end 2012: 8 out of 10 advocacy partnerships progressed from incubation to call-down support; of which 4 have progressed from call-down support to SAVI community of practice. / Not yet achieved
1.3 Civil society partners active support of replication of the approach.	SAVI are reformulating this indicator based on existing data fitted to a new set of milestones and scoring matrix for each state showing connections between Advocacy Partnerships and other stakeholders. / This indicator will be scored early in 2012.

The Mid Term Review finds that very good progress has been made against the first indicator. SAVI has been instrumental in bringing together civil society organisations into partnerships that are increasingly capable of engaging in effective policy and advocacy and monitoring. The groups are mostly achieving the objectives they have set for themselves, and have in several cases succeeded in influencing policy and monitoring its implementation (examples provided in section 2.2.2). SAVI’s support has been critical to the effectiveness of the advocacy partnerships, and has included various combinations of the following: (1) bringing the partnerships together, (2) advising and supporting the organisational development of the partnerships, (3) providing training on organisational and advocacy skills, (4) on-going mentoring, (5) selective financial support for specific activities, and (6) facilitating access of the Advocacy Partnerships to media, State Houses of Assembly, Ministries, Departments and Agencies.

As the Advocacy Partnerships mature and engage in more sophisticated advocacy work it is clear that there is an increasing need to provide the groups with technical support on policy, research and analytical issues. Technical capacity gaps are becoming increasingly evident, for example in the problems faced by Northern Advocacy Partnerships engaging in budget and MTSS processes and the lack of technical knowledge in Climate Change AP in Lagos. In the view of the Mid Term Review SAVI should already be doing more to address these gaps. SAVI’s approach has been to wait for the Advocacy Partnerships to identify their needs and to then broker links with sources of expertise according to expressions of demand. The problem is that the groups do not always recognise their needs and how to take their advocacy work to the next level. In practice this recognition tends arise from exposure to outside ideas and alternative ways of working. While SAVI has sometimes adopted such an approach (cross state visits have been particularly fruitful), the Mid-Term review recommends that SAVI should be doing more, particularly in the second half of the programme. SAVI needs to become more proactive in exposing the APs to outside ideas and more actively suggesting ways for groups to strengthen their technical skills. This should not detract from broad thrust of SAVI’s approach, which works with the groups’ internal dynamics and is demand led.

SAVI’s approach to forming and strengthening the Advocacy Partnerships has generally proven to be successful and draws on many lessons of good international practice in advocacy work and field experience in Nigeria. SAVI has played a behind the scenes role brokering networks and connections. It has been careful to avoid playing a directive role or to distort civil society agendas by offering grant funding for work on specified issues or projects. These practices have helped to limit the dependence of the Advocacy Partnerships on SAVI support, as measured by the second output 1 indicator. SAVI has substantially met its mid 2011 milestone that 8 out 10 of the Advocacy Partnerships should have entered the ‘call down’ stage, where they manage most of their work independently of SAVI, but are able to request support from SAVI for specific activities justified in their workplans. None of the partnerships have yet entered the final stage of becoming a ‘community of practice’ that can operate fully independently of SAVI, but one group (Jigawa MNCH) is judged to be close to this point.

Because SAVI has been designed as a demonstration project, its success will depend on the extent to which its advocacy approach can be replicated more widely. SAVI intends to measure the extent to which the Advocacy Partnerships are able to promote replication of their approach whether through their own members’ parent organisations or other similar forms of civil society partnerships. This will be assessed using a third indicator that will be scored on the basis of a matrix for each state showing connections between Advocacy Partnerships and other key stakeholders. Although the source data exists, the scoring against the matrix has not yet been carried out (due early 2012), so no definitive judgement can yet be made on the extent to which Advocacy Partnerships are able to promote replication of their approach. However, the MTR found many examples of lessons being learned and shared within the Advocacy Partnerships and their networks of member organisations. There is evidence of the replication of ideas and approaches to advocacy work between APs in the same state and between different states (several exchange visits between APs in Enugu and Kaduna have taken place). SAVI's civil society partner organisations are also increasingly becoming engaged in voice and accountability activities promoted by other SLPs. Members of Advocacy Partnerships also use the experience gained in working with SAVI in their other activities and networks.

Based on the evidence of this review, output one can be judged to have been mostly achieved thus meriting an ARIES score of 2. The score should in practice be somewhat better than 2, but ARIES requires a round number score, and the judgement of the MTR team is that the score is closer to 2 than 1.

Looking forward there are good prospects for the existing Advocacy Partnerships under output 1 to continue to work effectively and to become increasingly independent of SAVI. Future milestones are likely to be achieved. There are however, sustainability issues (see section 2.3) that may limit the number of Advocacy Partnerships reaching the ‘community of practice’ stage. As the Advocacy Partnerships mature a particular priority for the second half of the SAVI programme is to enable the Advocacy Partnerships to ensure their institutional sustainability by building their capacity in functions such as managing and mobilising funds.

#### Output 2 – Civil society demonstrates a replicable and sustainable approach to facilitating public involvement in government budget and planning processes.

This output concerns the work of the process-based Advocacy Partnerships that work on budget planning and monitoring, MTSS and the monitoring of government performance in disbursement. The indicators and milestones are similar to output 1 and are shown in the table below:

Table 2.4	Progress in delivering output 2
Indicator	Present situation	Milestone mid 2011	Milestone end 2012
2.1 Strength of civil society partnerships for engagement in government budget and planning:	Based on the MTR's own assessment 2 out 5 APs are achieving their planned objectives (Enugu: no; Jigawa: no; Kaduna: no (previously had been an effective group, but no longer meeting on its own initiative); Kano: yes; Lagos: LACSOP yes, PaGG no, but overall for Lagos state - yes)	2 out of 5 advocacy partnerships have sufficient linkages and combined skills and resources to achieve their planned objectives for 2010/11. / achieved	3 out of 5 of advocacy partnerships have sufficient linkages and combined skills and resources to achieve their planned objectives for 2011/12. / Not yet achieved
2.2 Dependency on / independence from SAVI support	The MTR concurs with SAVI's assessment (see quarterly progress reports July-Sept 2011) that only 1 of the APs (Lagos LACSOP) has reached the call down stage.	3 out of 5 advocacy partnerships progressed from incubation to call-down support; none progressed from call-down support to SAVI community of practice. / Not achieved	3 out of 5 advocacy partnerships progressed from incubation to call-down support; of which 1 progressed from call-down support to SAVI community of practice. / Not achieved
2.3 Civil society partners active support of replication of the approach.	SAVI are reformulating this indicator based on existing data fitted to a new set of milestones and scoring matrix for each state showing connections between Advocacy Partnerships and other stakeholders. / This indicator will be scored early in 2012.

SAVI’s progress in delivering output 2 has been more limited than for output 1. Only two of the Advocacy Partnerships are judged to be achieving their planned objectives. In part this reflects the fact that most of the non achieving APs have been newly formed or reconstituted in the past year. It has also proven more challenging than expected to form cohesive groups to work on budget tracking and planning processes and to develop the required technical skills. The issues based Advocacy Partnerships under output 1 tend to demonstrate much more commitment to their particular subject area. The more successful output 2 Advocacy Partnerships in Kano and Lagos have overcome this problem by combining issues based interests with budget tracking and planning work. The Kano budget tracking partnership is composed of a number of organisations with a varied background, predominantly in social sectors. These organisations are not primarily interested in budget and planning processes, but engage in these because of the key role they play in making available the necessary resources for their respective social sector activities. LACSOP in Lagos has a similarly broad membership, and has undertaken influential budget tracking work in the education and health sectors.

The difficulties encountered under output 2 are also reflected in the second indicator, which shows that only one (LACSOP) of the APs has reached the ‘call down’ stage. SAVI considers that the Kaduna Know Your Budget (KYB) partnership has slipped back from ‘call down’ to ‘incubation’ since the 2011 Annual Review. The MTR also found that this group is no longer functioning effectively, but that the impasse reflects a difference of understanding between SAVI and individual members of KYB on how the group should develop. Influential members of the group are keen to use their skills as a professional service provider rather than as part of a voluntary network. This could be viewed as a successful case of building professional TA capacity, but does not fit with SAVI’s model of partnership development. The experience again demonstrates the inherent difficulty of mobilising and sustaining advocacy work around budget analysis work.

The third indicator covering the promotion by Advocacy Partnerships of the replication of their approach has not yet been scored (although source data exists). However, the MTR found several examples of the output 2 Advocacy Partnerships (particularly in Lagos and Kano) extending their skills and insights to the issues based (output 1) Advocacy Partnerships. This is a promising approach that has been promoted by SAVI, and should also be applied to the other output 2 partnerships where possible. Output 2 Advocacy Partnerships have also been linked to other SLPs with varying degrees of success. For example, SPARC has had a strong relationship with LACSOP and KYB in Lagos and Kaduna, but relationships between SPARC and the output 2 partnerships in Jigawa and Kano have been slower to develop.

In view of the problems experienced, the assessment of the MTR is that planned results under output 2 have been ‘partly achieved’. This output therefore merits a score of 3. There is an urgent need to address the problems experienced with the less well performing output 2 Advocacy Partnerships in (Enugu and Kaduna particularly). Options and recommendations are discussed in section 3.3.

#### Output 3 – An enabling environment for policy advocacy and monitoring, and engagement in government budget and planning processes.

Output 3 covers SAVI’s work in improving communication and linkages between civil society organisations, the media and State Houses of Assembly, and improving understanding of the respective roles of these organisations. It includes SAVI’s work with the media on civic education. An additional indicator seeks to measure the extent to which SAVI partners are engaging with the gender dimensions of governance.

Table 2.5	Progress against output 3
Indicator	Present situation	Milestone mid 2011					Milestone end 2012
3.1 Support from leadership in civil society, the media and state houses of assembly for voice and accountability initiatives actively supported by SAVI and its state partners	The matrix has not yet been compiled, although narrative evidence from quarterly reports indicates that most leadership of civil society, the media and SHoAs are supportive of SAVI sponsored voice and accountability initiative. / The milestone has been achieved.		No Support	Permissive Support	Facilitative Support	Support to Institutionalise		No Support	Permissive Support	Facilitative Support	Support to Institutionalise
		En	2	3	0	0	En	0	4	1	1
		Jg	0	3	2	0	Jg	0	2	2	2
		Kd	0	1	3	0	Kd	0	3	2	1
		Kn	0	2	2	0	Kn	0	2	2	2
		Lg	1	2	2	0	Lg	0	1	3	3
3.2 Public understanding of the expected roles and responsibilities of civil society, the media, state houses of assembly, government and citizens in improving voice and accountability.	This is a new indicator. Not yet measured. New survey to be conducted by media partners.		Inactive on Civic Ed / V&A	Demanding for Civic Ed / V&A	Participating in Civic Ed / V&A	Involving Govt / Involved in P/Gov		Inactive on Civic Ed / V&A	Demanding for Civic Ed / V&A	Participating in Civic Ed / V&A	Involving Govt / Involved in P/Gov
		% partners	35	60	5	0		15	45	35	5
		% citizens	w	x	y	z		w+	x+	y+	z+
3.3 Level of demand side activity amongst SAVI partners on strengthening the governance related gender-enabling environment	This is a new indicator. Milestones to be based on proportion of partners working on strengthening the governance related gender-enabling environment. Baseline currently being established.

The major difficulty in assessing progress against output 3 is that scores for two of the three indicators are yet not available. However, the MTR has been able to reach a qualitative judgement about the contribution of SAVI to improving communication and cooperation between civil society, the media and State Houses of Assembly. The MTR observed much improved relations between these actors in several states including Kano (where the SAVI brokered Voice and Accountability platform has been influential), Lagos (where the LACSOP CSO network is working increasingly closely with the State House of Assembly), Enugu (where civil society and media access to the State House of Assembly has markedly improved) and Jigawa (where SAVI has been highly instrumental in developing media attention for the State House of Assembly). In relation to the second indicator the MTR found several good examples of SAVI supported media work (for example radio programmes in Jigawa and Enugu) that is seeking to strengthen citizens' understanding of and engagement with governance systems.

Based on this limited (but fairly striking) qualitative evidence, the assessment of the MTR team is that planned results under output 3 have been ‘mostly achieved’ meriting an ARIES score of 2. It remains to be seen whether the initial good results will be sustained. There are many additional challenges to address that go beyond the initial work in improving communication and links between demand side actors. These include enabling broader civic engagement with demand and supply side actors, building public understanding of their roles, and ensuring the flow of information on their performance. These are important challenges where progress is essential for SAVI’s other outputs to achieve results. Consequently, it is recommended to increase the output 3 logframe weighting from 10% to 20%.

A finding of the 2011 Annual Review, confirmed by this MTR, is that opportunities have been missed to work with the media as an agent of voice and accountability. SAVI’s present work with media mainly involves linking journalists and media organisations to the Advocacy Partnerships and State Houses of Assembly. There has been only limited attention to building the capacity of journalists and media houses to report on public policy questions and processes. The MTR recommends that SAVI should give working with the media as much emphasis as its work with civil society and the State House of Assembly, and should shift towards a stronger focus on media development.

#### Output 4 – Improved state houses of assembly systems for transparency, public engagement and financial oversight.
SAVI assesses its progress in working with State Houses of Assembly against 4 indicators based on aggregated ratings generated by the 2009 Organisational Capacity Self-Assessment (conducted by SHoAs). The ratings were reassessed by the new State Houses of Assembly following the legislative elections in 2011 and compared with the logframe milestones. The Kaduna and Lagos scores are preliminary assessments based on SAVI internal review rather than a full State House of Assembly self-assessment, which will be completed shortly.

Table 2.6	Progress against output 4
Indicator	Present situation	Milestone mid 2011
4.1 Quality of systems for public access to information and processes in the house and representation of public interests by members.	2011 Organisational Capacity Assessment scores (2009 baseline in brackets): Enugu 1.5 (1); Jigawa 1.5 (1); Kaduna 1.5 (1); Kano 2 (1); Lagos 3 (1)	4 states score at least 2 out of 5 by mid to late 2011 (post elections), of which 1 state scores 3 out of 5. / Some improvement, but milestone not achieved
4.2 Quality of systems for recruitment and retention of house support staff and aides.	2011 Organisational Capacity Assessment scores (2009 baseline in brackets): Enugu 1.5 (1); Jigawa 1.5 (2); Kaduna 2 (1); Kano 2 (2); Lagos 3 (2).	4 states score at least 2 out of 5 by mid 2011 (post elections), of which 1 state scores 3 out of 5. / Good progress, but milestone not achieved
4.3 Quality of systems for induction and monitoring of compliance with house rules & procedures	2011 Organisational Capacity Assessment scores (2009 baseline in brackets): Enugu 1.5 (1); Jigawa 3.5 (1); Kaduna 1.5 (1); Kano 2 (2); Lagos 3 (1).	3 states score at least 2 out of 5 by mid to late 2011 (post elections), of which 1 state scores 3 out of 5. / Achieved
4.4 Quality of systems for scrutinizing public financial documents in the house	2011 Organisational Capacity Assessment scores (2009 baseline in brackets): Enugu 2 (2); Jigawa 2 (1); Kaduna 1.5(1); Kano 2 (1); Lagos 2 (1).	4 states score at least 2 out of 5 by mid to late 2011 (post elections), of which 2 states score 3 out of 5. / Some improvement, but milestone not achieved

The Mid Term Review concurs with the results of the Organisational Capacity Assessments that significant progress has been made in strengthening State Houses of Assembly, but this has fallen somewhat short of the milestones established by SAVI. In interpreting this result it is important to draw attention to the 2011 elections and the disruption this caused to the regular work of State Houses of Assembly.

The best results have been achieved in terms of strengthening internal systems for inducting new members, ensuring compliance with house rules and strengthening systems for the recruitment and retention of house support staff (through the House Service Commissions). This reflects SAVI’s emphasis on internal systems strengthening as the first stage in its theory of change (‘getting houses in order’)

More limited results have been achieved in strengthening house systems for scrutinising public financial documents. Organisational Capacity Assessment scores show that all five states have improved on scrutiny, procedure and timing of the appropriation bill, but scored low on audit functions and members’ capacity for financial and performance analysis. The MTR’s assessment was that Members of State Houses of Assembly often had a limited or narrow understanding of their role in public financial oversight, but that this was stronger for House support staff.

The Organisational Capacity Assessment scores also indicate only limited improvement for other external functions of the State Houses of Assembly, including the quality of systems for public access to information and processes in the house and representation of public interests by members. However, following the elections there does appear to have been a change in attitude in several states towards more openness, increased transparency and accountability of State Houses of Assembly and their members. There are notable improvements in several states regarding the use of public hearings (Lagos, Kano and Enugu), the broadcasting of House proceedings and functioning (Enugu, Jigawa and Kano), liaison between State Houses of Assembly and civil society organisations (Lagos, Kano, Enugu and Jigawa) and the first cases of bills being sponsored by private members (Lagos).

On the basis of progress against the output 4 indicators and milestones, the MTR’s assessment is that targets are being 'partly achieved' meriting a rating of 3. There has generally been more progress in strengthen the houses’ internal systems that in strengthening external functions. Overall the results are encouraging given the starting point for SAVI’s intervention and the political context where many State Houses of Assembly are used more as an instrument of patronage and control rather than as an institution for policy deliberation and oversight. The interruption to the regular work of State Houses of Assembly and the turnover in Members caused by the 2011 elections has been an additional challenge. In view of these constraints SAVI deserves particular credit for its pioneering work with the State Houses of Assembly and the results already achieved. If ARIES permitted intermediate scores the MTR would have opted for a score somewhat better than 3 (but closer to 3 than 2).

There are good prospects for further improvements in the results of SAVI’s work State Houses of Assembly. This will require a shift towards a more programmatic approach, greater emphasis on strengthening the Houses’ external functions and more focus on working with the Members of the House in addition to the legislative staff, who have been the main targets of assistance so far. Better coordination and more joint working with other SLPs in their State House of Assembly related work is also required. However, it will be difficult to sustain the improvements brought by SAVI beyond the lifetime of the project unless SAVI’s experience can be transferred, retained and further developed by State Houses of Assembly and other Nigerian organisations working with the legislature. Realistically the State Houses of Assembly will require external support beyond the duration of the SAVI programme to ensure the benefits brought by SAVI’s intervention and further develop the quality of the legislature.

#### Output 5 – Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches.

Output 5 covers SAVI’s work on external communication and the wider uptake of the SAVI approach by other development partners. There are two indicators of progress under output 5 shown below:

Table 2.7	Progress against output 5
Indicator	Present situation	Milestone mid 2011
5.1 Accessibility of lessons learnt which are relevant and useful to other development partners.	Different state teams report that between 5% and 60% of their documentation is focussed on meeting external communication needs. The MTR's assessment is that SAVI's internal lesson learning is working well, but external communication is still relatively weak.	Systems in place for routine capture of key learning, frameworks in place for interpreting lessons for a wide range of partners needs, with 25% of documentation focused on meeting external communication needs compared to 75% on internal programme M&E and planning. / Partly achieved
5.2 Commitment of other development partners to replicate key aspects of SAVI and its state partners' approaches.	SAVI reports that all 5 SAVI state teams now have at least 3 joint working relationships or other formal means of sharing lessons with development partners in their own states. Enugu: joint working with ESSPIN & PATHS2, interest from UNICEF, J4A (V&A), Living Earth Foundation and Water Aid. Jigawa: joint working with PATHS2 (MNCH), ESSPIN (SHP) & EU-SRIP (PMP), invitation from PRRINN-MNCH (V&A). Kaduna: joint working with ESSPIN (GWG-MTSS) & PATHS2 (MNCH), invitation by SPARC (GWG-MTSS), invitation from PRRINN-MNCH (V&A). Kano: joint working with PATHS2 (MNCH) and SPARC, invitations from ESSPIN & PRRINN-MNCH (V&A). Lagos: active promotion by ESSPIN & PATHS2, invitation from UNICEF (LACSOP).	3 other development partners in each SAVI state express interest in learning from SAVI through invitation to knowledge sharing events, joint working on advocacy partnerships or active promotion of a key aspect of SAVI and its state partners’ approaches by mid-2011. / Achieved

In relation to the first indicator the MTR team noted the strong emphasis SAVI places on self reflection and lesson learning processes within SAVI state teams and in SAVI's work with partners. Lessons are learned and shared internally and extended to civil society and SHoA partners within and between states. However, the MTR finds that SAVI’s external communication is still relatively weak, and the programme is little known beyond its immediate partners. This finding is consistent with SAVI’s strategy of keeping a relatively low profile and acting as a behind-the-scenes broker of advocacy work. It also reflects time pressures on SAVI created by reporting and communications requirements towards DFID and IMEP (review requirements having been particularly heavy this year). SAVI recognises the need to communicate its approach more actively, but this has not yet resulted in substantially improved external communications products and approaches. SAVI's approach, lessons learned, and evidence of change needs to be presented in a simpler, non-technical and more accessible format suited to different types of audience. There is a particular need to complement SAVI’s presentation of conceptual ideas (which are sometimes rather heavy) with stories of change that illustrate SAVI’s working methods in a practical way. As SAVI gains more evidence on the results of its work the value of external communication will increase.

Against the second indicator there does appear to be evidence of other development partners becoming exposed to SAVI’s approach and showing signs of replicating aspects of this. However, the examples cited mainly refer to joint working with other SLPs and there is a need for greater communications efforts towards non-SLP partners. Some non-DFID programmes (e.g. UNICEF, EU SRIP and Water Aid) have entered in partnerships with SAVI, although the number is relatively modest. In some states SAVI is beginning to engage with broader groups of civil society organisations beyond its Advocacy Partnerships. There is scope to step up this approach as a low cost method of extending SAVI’s model to a broader range of organisations.

In the light of the progress achieved the assessment of the MTR is that planned results under output 5 have been ‘partly achieved’ meriting a score of 3. Provided that human resources are available to SAVI there are good prospects to improve this score over the next year as SAVI steps up its external communication work.

### Achievements against purpose
SAVI’s purpose statement (referred to as the outcome in SAVI’s logframe) is that “Civil society, State Houses of Assembly and Government improve their voice and accountability processes.” The relevant milestones and present situation for the three purpose level indicators are shown in the table below. The first two indicators are based on SAVI’s Governance Baseline scores, which were established in 2010, but will not be updated using external experts and peer review until 2012. The present scores indicated below are based on a recent SAVI internal assessment using the governance baseline methodology.

Table 2.8	Progress against purpose
Indicator	Present situation	Milestone mid 2011	Milestone end 2012
Functionality of state houses of assembly as agents of voice and accountability. Source: SAVI Governance Baseline (questions relating to quality of governance of State House of Assembly).	Late 2011 SAVI internal assessment scores (2010 baseline scores in brackets): Enugu 2.8 (2.0); Jigawa 2.4 (2.2); Kaduna 2.0 (2.2); Kano 2.1 (1.9); Lagos 3.2 (2.2).	One state improves its score to 3 out 5 / Milestone achieved	2 states improve their score to 3 out of 5, of which one state scores 3.5 out of 5 / Milestone not yet achieved
Functionality of civil society (including the media) as agents of voice and accountability. Source: SAVI Governance Baseline (questions relating to the quality of governance in Civil Society and the Media).	Late 2011 internal assessment scores (2010 baseline scores in brackets): Enugu 2.9 (1.8); Jigawa 3.3 (2.4); Kaduna 2.3 (2.2); Kano 2.0(2.0); Lagos 2.8 (2.3).	2 states improve their quality of governance score to 3 out of 5 or above. / Milestone substantially achieved	3 states improve their quality of governance score to 3 out of 5 or above. / Milestone not yet achieved
Demonstrable change in policy and implementation where there is evidence of attribution to SAVI.	10 changes in policy and implementation are judged to be in part attributable to SAVI's work (see below).	At least 5 examples from across the programme directly attributable to SAVI (resulting from improved approaches demonstrated by civil society partnerships and SHoA with SAVI support). / Milestone achieved	At least 10 examples from across the programme directly attributable to SAVI, and at least 5 indirectly attributable to SAVI (constituting ‘replication’ of improved approaches demonstrated with SAVI support). / Milestone partly achieved

The provisional Governance Baseline scores indicate an improvement in the functionality of State Houses of Assembly as agents of voice and accountability in all states except Kaduna. The mid-2011 milestone appears to have been achieved, although this will need to be confirmed when the Governance Baseline is updated. As discussed under output 4 in section 2.2.1 above, the MTR also found evidence of improved functionality in State Houses of Assembly, particularly in relation to the management of legislative staff and induction of new members, but also including some progress in strengthening budget oversight functions and increasing public access to information. It should be noted that the 2011 milestone for this indicator is a relatively modest target requiring substantial improvement in only one state. However, this should not detract from the general improvements noted. The negative trend in Kaduna should also be highlighted as an indication of the risks inherent in working in the politicised environment of State Houses of Assembly.

The provisional Governance Baseline scores also indicate improvement in the functionality of civil society (including media) as agents of voice and accountability. The mid 2011 milestone has been substantially achieved (one state has reached the target and two others are very close). The MTR review team found additional evidence of improved functionality of civil society and media in the context of SAVI's Advocacy Partnerships (see outputs 1 and 2 above) and their closer engagement with State Houses of Assembly (see output 3 above). SAVI has been effective in promoting the use of the media by civil society groups and the State Houses of Assembly, and the media attach more importance to reporting on the State House of Assembly’s role, functions and proceedings.

The third purpose level indicator is a new measure that was introduced following the 2011 Annual Review. This seeks to capture “demonstrable changes in policy and implementation where there is evidence of attribution to SAVI”. The MTR team observed the following changes, which met the criteria of being both substantial and in part attributable to SAVI’s work. These are described in the following table:

Table 2.9	Demonstrable change in policy and implementation where there is evidence of attribution to SAVI
State	Demonstrable change in policy and implementation	SAVI contribution to the change
Enugu	Deployment of more staff to primary health centres following the health policy dialogue	The dialogue was co-funded by SAVI and PATHS2. The MNCH AP played an active role in the dialogue and monitoring follow-up.
Jigawa	Free Maternal and Child Health Bill at Second Reading. Increase in budget allocation for free MNCH from N 140 million to N 170 million in 2011. / Response to shortage of female personnel in health and education.	Changes have followed advocacy work by SAVI APs
Kaduna	Moving towards greater budget realism	Advocacy by the Know Your Budget AP contributed to the reduction of the 2010/11 state budget.
	Start up of primary health care and drug management agency	The MNCH AP has been active in advocating for the establishment of this agency
Kano	New legislation for decentralised water management	This has followed the piloting and advocacy around alternative water management by the Wudil AP.
	Establishment of Legislative Budget and Research Office, / Establishment of a Civil Society Liaison Desk in State House of Assembly	This has followed SAVI’s engagement with the State House of Assembly
Lagos	Passage of the Special People’s Bill	The bill was drafted by the PWD AP and passed as a private members bill
	Passage of House Service Commission Bill / Agreement to establish a Legislative Budget and Research Office	SAVI’s behind the scenes advice and support to the SHoA has contributed to both of these changes.

On the basis of this evidence the MTR judges that SAVI has achieved its 2011 milestone of contributing to 5 demonstrable changes in policy and implementation. This indicator has proven useful to demonstrate where SAVI’s work has led to tangible results in terms of improved policy and implementation. It is recommended to continue using this indicator within the context of a reformulated purpose statement (see section 3.4), but with more thorough documentation to be provided by SAVI on the nature of the change, its cost (including partner contributions) and the contribution of SAVI’s work. There may also be scope to break this indicator down into subcategories to capture improvements in institutions, behaviour, policies and practices that embody greater voice and accountability.

SAVI is making strong progress against its purpose level milestones, which have all been mostly or fully achieved. On this basis SAVI’s performance would merit an ARIES score of 2 (mostly achieved). However, the automatic calculation of the purpose score using the ARIES spreadsheet is based on the weighted average of output scores. This yields a derived purpose score of 3 (partly achieved). IMEP understands that there are circumstances under which the automatic score can be overriden, but the criteria for taking this decision are not clear. DFID will need to take a judgement on scoring based on its interpretation of its own procedures. In the view of IMEP there would appear to be a strong case for using the score of 2 based on the direct assessment since there is evidence to back this up, and the purpose level indicators (particularly the third) have the merit of being more results focussed than some of the more process oriented output indicators. There are also conceptual difficulties with using the derived score of 3, which assumes that the purpose follows automatically from outputs, ignores the role of the assumptions column in the logframe, and indeed undermines the case for systematic monitoring at purpose level.

### Achievements against goal

SAVI’s goal statement (referred to as the impact in SAVI’s logframe) states that “the efficiency and effectiveness of selected state level governments’ use of public resources is enhanced”. Three indicators have been proposed at goal level, which measure overall changes in the quality of governance (Governance Baseline scores), changes in citizens’ perceptions and the passage of key legislation by State Houses of Assembly. These indicators do not measure the goal as such, but do assess improvements in governance that contribute to the goal. It might be advisable to ensure consistency by lowering the goal statement to the level of the indicators, although it is understood that the goal statement has been established as a link to other SLPs (SAVI’s goal statement is the same as SPARC’s purpose level statement). Progress against each indicator and relevant milestones are shown in the table below.

Table 2.10 Progress against goal

Indicator	Present situation					Milestone mid 2011					Milestone end 2012
Quality of governance of State and Local Government in terms of their accountability and responsiveness	Late 2011 internal assessment scores (2010 baseline scores in brackets): Enugu 3.4 (2.2); Jigawa 3.2 (2.5); Kaduna 1.5 (1.8); Kano 2.3 (2.0); Lagos 3.9 (2.0)					No change expected from 2010 baseline / achieved					3 states improve their quality of governance score to 2.5 out of 5 or above, of which 2 states improve their score to 3 out of 5 or above. / Achieved if internal assessment scores are confirmed by full governance baseline update
Citizen’s satisfaction (including that of normally excluded groups) with their ability to claim rights and hold government to account through democratic channels. Source: Citizens Perceptions Survey	Citizen's Perception Survey (CPS) data exists for 2010, but will not be repeated until 2012. It is therefore too early to assess progress against this indicator.
Passage of key legislation relating to good governance	15 point scale through passage and implementation. FRB=Fiscal Responsibility Bill, PPB=Public Procurement Bill, FOIB=Freedom of Information Bill, HSCB=House Service Commission Bill
		En	Jg	Kd	Kn	Lg			En	Jg	Kd	Kn	Lg	Mid 2011 milestones substantially achieved, except in Kaduna
	FRB	1	12-13	10	3	14-15		FRB	1	12	11	2	7
	PPB	12	12	3	3	10		PPB	9	12	6	2	11
	FOIB	12	0	1	1	5		FOIB	0	1	0	1	1
	HSCB	14-15	12-13	10	10	13		HSCB	2	12	13	11	13

On the basis of the above indicators, SAVI appears to have substantially achieved its goal level milestones. However, these indicators do not provide evidence of the achievement of the goal level statement itself. A few promising cases were noted by MTR team where there is evidence of state governments changing their allocation of resources based on demand side advocacy. Examples include the deployment of more primary health workers in Enugu and the increase in health and education budgets in Jigawa. If adequately implemented, the Special People's Law in Lagos should soon result in additional spending on access to buildings and other disability rights.

### Value for money at effectiveness level
At the level of effectiveness (translation of outputs into outcomes and goal) it is not possible within the resources of this MTR to provide a definitive measure of value for money. This would require an estimation of net present value of all observed changes in governance and policies adjusted according to the extent of SAVI’s contribution to the changes. A particular obstacle to calculation has been the absence of detailed financial data, which makes it impossible to assign costs accurately to sub-outputs. However, there is sufficient evidence for the Mid Term Review to make a broad assessment of value for money, which appears to be strong at the effectiveness level. Sections 2.2.2 and 2.2.3 have documented evidence of significant improvements in governance and demonstrable changes in policies and implementation where there is evidence of attribution to SAVI. Taken together, this amounts to an important result that has been achieved with relatively modest investment in the SAVI programme (£7.7 million to date). SAVI’s value for money will be further enhanced if it succeeds in creating conditions for the wider replication of its approach.

Value for money at effectiveness level can be demonstrated in more concrete terms on the basis of case study evidence of the results of particular outputs and sub-outputs. The examples below are drawn from VFM case studies prepared by SAVI and additional evidence collected by the MTR team.

In Lagos SAVI investment to date in the PWD Advocacy Partnership is roughly estimated at £60,000. This has already resulted in the passage of the ground-breaking Special People’s Law that if properly implemented will improve the lives and opportunities of tens of thousands of disabled people in Lagos state. The cost per beneficiary is extremely low;

In Kaduna SAVI has so far spent around £82,000 on output 2. One of the main results of this spending (jointly attributable to SAVI, SPARC and DFID N actions) was to bring about a revision in the 2010-11 state budget. The reduction in the proposed budget was around N30 billion (£120m). Although the finally approved budget was still unrealistic and subject to considerable waste, the reduction in the budget must have saved resources many times in excess of SAVI’s investment;

In Jigawa the 2011 Appropriation Bill submitted to the Jigawa State House of Assembly included an increase in the allocation for the free MNCH services from 140 million Naira to 170 million Naira annually. The FMCH Advocacy Partnership established by SAVI has been instrumental in demanding this budget increase. SAVI’s investment in the Advocacy Partnership has so far been in the region of £40,000-50,000. If the increased budgetary resources prove to be additional, and are spent and sustained over several years then DFID’s funding will have achieved significant leverage (£1 of DFID funding leverages £3 of Nigerian funding in the first budget cycle).

All of these estimates assume a counterfactual situation where the observed changes would not have occurred in the absence of SAVI support. If the situation would have improved or deteriorated irrespective of SAVI’s inputs then the above estimates would need be reduced or increased accordingly.

## Sustainability
In judging SAVI’s sustainability it is important to recognise that the programme is intended to act as a demonstration of the viability of models for engaging demand side actors in advocacy work which can be maintained and replicated without large scale external assistance. Consequently the key test of sustainability is whether the advocacy models are appropriate, viable and replicable, and that demand side actors will be in a position to use these models in the absence of SAVI support.

SAVI’s model of working with Advocacy Partnerships (under outputs 1 and 2) has many positive aspects that should contribute to long-term sustainability. SAVI has been careful to avoid creating dependency on the programme by limiting its funding to time bound and specified activities, and by supporting organisational development of the Advocacy Partnerships. Nevertheless the groups are dependent on SAVI to a certain extent for organisational support, funding of activities and access to key stakeholders. None of the partnerships have yet reached the ‘community of practice’ stage where they can operate independently of this support. Bringing a number of groups to this level will be a critical test of the viability and sustainability of SAVI’s approach. Reflecting the level of development of the Advocacy Partnerships, SAVI has not yet given much attention to the types of support required to create ‘communities of practice’, including partnership development and capacity building to manage and mobilise funds. For the second half of the programme these should be major priorities for SAVI support. Such assistance could be provided at the level of Advocacy Partnerships where they are likely to continue their work in the medium to long term. It could also be provided at the level of the Advocacy Partnership’s member organisations where the Partnership is less likely to be durable over time. Both types of capacity building should contribute to the sustainability of SAVI’s model of advocacy work.

SAVI’s work with State Houses of Assembly poses particular challenges for sustaining the benefits so far achieved by the project. The turnover of Members of the House between legislative terms makes it difficult to sustain capacities and justifies SAVI’s strategy of focussing on systems building and working with the legislative staff. Realistically it will take changes in the broader social and political climate as well as many years of external support (perhaps one or two decades) for improvements in House institutions and performance to become embedded. Some form of continued donor support will be needed to sustain the gains that have been achieved by the SAVI programme. An immediate priority is to ensure that the valuable experience gained by SAVI will not be lost when the programme closes. It would be desirable to deliver output 4 in partnership with a Nigerian organisation which should be in a position to maintain and further develop the experience gained by SAVI and to transfer this to future programmes. SAVI has already tried to engage national NGOs (AAN, CISLAC and PLAC) in the delivery of output 4, but the contribution of these partners was not felt to be satisfactory. This experience notwithstanding, it is recommended for SAVI to continue looking to develop new partnerships to support and sustain its work with State Houses of Assembly (SAVI’s partnership with the National Assembly looks promising in this regard).. More generally SAVI’s experience would be more likely to be retained within Nigeria if the programme’s oversight and advisory bodies could play a more active role.

## Efficiency
### Progress against plan
This Mid Term Review has not attempted a detailed comparison of the progress of SAVI’s activities against its workplans. Time did not permit an adequate assessment, and it was deemed to be more beneficial to focus on tracking the results of the programme. In addition, the nature of SAVI’s work makes it difficult to engage in detailed planning beyond the horizon of a few months. This is because SAVI needs to adapt flexibly to changing political circumstances and has to be responsive to changing demands from its partner organisations.

The assessment of the MTR is that SAVI has maintained an impressive pace of programme implementation and has been able to provide inputs on a timely basis on the basis of its workplans and in response to demand. There have been few programming interruptions, one exception being the sharp slowdown in work in Enugu in 2010 following the death of the former State Team Leader.

Overall expenditure has been less than planned expenditure during both the inception phase and implementation phase as shown in table 10 below. Mid way through the programme SAVI has spent about 36% of its total budget of £21.5 million. This compares with a planned level of expenditure at the mid-point of 42% of the total budget. The slower than expected rate of expenditure during implementation is understood to be due to the reorientation of the programme following the inception review (and in particular the decision not to provide sub-grants) and the underestimation of the time required to identify and establish effective working relationships with State Houses of Assembly and with the Advocacy Partnerships. The rate of expenditure has since increased as SAVI has established its way of working. This trend is likely to continue, and should reduce the underspend by programme completion. With the expansion in the North and additional activities recommended by this review it will be necessary to examine the question as whether the total budget needs to be increased.

Table 2.2 SAVI Budget vs. Actual Expenditure by location
	Enugu	Kano	Kaduna	Lagos	Jigawa	Abuja	Total
	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000
Inception
Budget	331	375	463	353	176	507	2,205
Actual	349	384	394	395	246	332	2,100
Diff.	6%	2%	-15%	12%	39%	-35%	-5%
Implementation
Budget	1,039	1,246	1,108	1,177	969	1,385	6,923
Actual	876	963	787	925	687	1,341	5,579
Diff. (%)	-16%	-23%	-29%	-21%	-29%	-3%	-19%

### Value for money at efficiency level
Value for money at efficiency level concerns the conversion of inputs to outputs, for example the increase in capacity of an Advocacy Partnership that results from a certain training input. As explained in Annex B it has not been possible to provide accurate data by sub-output because of the limitations of SAVI’s accounting methods. It is recommended to address this shortcoming in order to enable more complete value for money analysis in future. The table below indicates expenditure by output and by state.

Table 2.32	Total Expenditure by Output and Location
	Enugu	Kano	Kaduna	Lagos	Jigawa	Abuja	Total	% share
	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000
Output 1	104	85	89	121	83	35	518	7%
Output 2	101	81	83	115	79	35	494	6%
Output 3	93	112	96	102	59	69	532	7%
Output 4	280	334	236	294	209	101	1,454	19%
Output 5	73	110	107	151	65	70	575	7%
X-Cutting technical	205	208	235	185	150	163	1,146	15%
Abuja/State Offices	361	399	333	338	274	1,246	2,950	38%
Total	1,216	1,329	1,178	1,306	919	1,718	7,668	100%
% share	16%	17%	15%	17%	12%	22%	100%

This data does not provide a strict measure of efficiency, and simply indicates the cost of delivering outputs. Nevertheless, some remarks on value for money from an efficiency perspective can be made:

53% of total programme expenditure by location is accounted for by Abuja-based fees and costs and cross-cutting technical inputs. The Abuja office manages the overall programmes and acts as a technical and administrative service centre for the state-based programmes, so a significant portion of this expenditure relates directly to output delivery at state level.

- For each output SAVI’s contribution has often been matched by a financial or in kind contribution of the project partner (see examples in annex B). This makes it possible to deliver outputs at lower cost, thereby increasing value for money on efficiency grounds. SAVI has not measured the value of partners’ contributions, which makes it impossible to assess the scale of these leverage effects.
- Taking outputs one and two together the cost of establishing an issue based or budget tracking Advocacy Partnership has been in the range of £40-70,000 (there are typically 3 or 4 Advocacy Partnerships per state. This estimate does not include central costs in Abuja). For the output 1 Advocacy Partnerships this financial input has for the most part resulted in the formation of well functioning Advocacy Partnerships that are achieving their objectives. The value for money of the output 2 Advocacy Partnerships will tend to be weaker on efficiency grounds due to the more limited functionality of many of these groups.

Output 3 contains a rather diverse set of activities making a value for money assessment impossible without more disaggregated data. However, it appears that some of the most promising activities under output 3 including the funding of media programmes and the bringing together of civil society, State House of Assembly and media actors can be achieved at low cost representing good value for money in efficiency terms.

Output 4 has entailed much higher costs than any other outputs, in part because of the relatively heavy use of external consultants. In view of the more limited immediate results for this output, questions can be raised about its value for money. Further data disaggregated by sub-output will be needed to make the value for money case for working with the State House of Assembly. This assessment needs to take account of the long time scale required to deliver improvements in State Houses of Assembly, the high risks involved, but also the substantial benefits that would arise if State Houses of Assembly could act more effectively as agents of voice and accountability. The value for money case will need to be made in a forward looking sense on the basis of projections of the level of improvement in State Houses of Assembly that can reasonably be expected by the end of the SAVI programme and years following.

It is currently impossible to assess the value for money of output 5 as various types of expenditure have been budgeted under this output, including special activities such as SAVI’s engagement in Ekiti state.

### Value for money at economy level
Value for money at economy level describes the conversion of money into particular project inputs, for example the cost of a training programme. This has not been a major focus of the Mid Term Review because economy will for a large part be achieved by adhering to standard DFID practices for competitive procurement and cost control. There is evidence that SAVI has generally performed well in ensuring value for money on an economy basis. In particular it has succeeded in limiting technical assistance costs by employing only two expatriate staff and limiting the use of short term TA. As explained in Annex B the weighted average cost of long term TA, which represents 80% of total fees expenditure to date, is £138 per day. This compares well against other donor projects and suggests that the marginal costs of expanding SAVI’s work would be relatively low.

### Balance of expenditure between states and outputs – Allocative Efficiency
The Mid Term Review has considered the question of whether a reallocation of resources between outputs and states would result in increased value for money. Table 11 above shows the pattern of spending to date by output and by state. This is shown in percentage terms in table 12 below.

Table 2.4	Allocation of expenditure by Output and Location in percentage terms
	Enugu	Kano	Kaduna	Lagos	Jigawa	Abuja	Total
	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000
Output 1	8.6	6.4	7.6	9.3	9.0	2.0	6.8
Output 2	8.3	6.1	7.0	8.8	8.6	2.0	6.4
Output 3	7.6	8.4	8.1	7.8	6.4	4.0	6.9
Output 4	23.0	25.1	20.0	22.5	22.7	5.9	19.0
Output 5	6.0	8.3	9.1	11.6	7.1	4.1	7.5
X-Cutting technical	16.9	15.7	19.9	14.2	16.3	9.5	14.9
Abuja/State Offices	29.7	30.0	28.3	25.9	29.8	72.5	38.5
Total	15.9	17.3	15.4	17.0	12.0	22.4	100.0

The bottom row of the table indicates a relatively even pattern of spending between states with the exception of Jigawa where the SAVI operations began later than in the other states. The state level reviews (see Annex A) suggest that there have not been major differences in the performance of SAVI programmes in different states. While SAVI’s results are somewhat more limited in Kaduna and Enugu, this reflects the more challenging operating environment and disruption to programme implementation. SAVI appears to be able to deliver an effective programme in all states. Therefore there does not appear to be any efficiency justification for reallocating resources between states.

There is also a relatively consistent pattern of spending between the five outputs in different states. Greater differences might have been expected to be observed between states in view of the different opportunities to work with demand side actors. In practice SAVI has adopted different approaches to working with demand side actors in different states, but this does not appear to have had important expenditure consequences.

Output 4 has absorbed the largest proportion of expenditure. As discussed in section 2.4.2 the more limited results under this output raises the question as whether better value for money would be achieved by reallocating resources from output 4 to alternative uses. The Mid Term Review recommends that substantial spending on output 4 should be maintained in view of the long-term potential benefits. However, it also proposes a small reallocation on logframe weighting away from outputs 4 and 5 to output 3, which may result in management decisions to reduce slightly the share of the budget spent on output 4.

## Programme oversight and management
### General programme management issues
The Mid Term Review team were impressed with the quality, commitment and professionalism of SAVI staff. The SAVI Abuja office and all of the state teams benefit from strong leadership. SAVI staff have a firm understanding of the programme’s approach and are well informed about the local political context and opportunities for demand side engagement. The decentralised management structure is generally working well with state teams given considerable flexibility in shaping and implementing each state programme.

The MTR finds that SAVI’s state teams are thinly staffed with the result that human resources are sometimes overstretched. This has sometimes affected the quality of SAVI’s work. For example, several of SAVI’s Advocacy Partners commented that SAVI is often slow to respond to their requests, and other SLPs commented that SAVI staff are sometimes unavailable to attend joint events. The MTR finds that the SAVI programme is working at full capacity, and that an increase in human resources will be required if SAVI is expected to implement additional activities or to work in new states. The MTR recommends an increase in SAVI’s staffing levels at state level in particular to address weaknesses in work with the media and State Houses of Assembly. This would result in increased value for money because increased staffing is likely to generate significant benefits while imposing low marginal costs (see section 2.4.3).

### Monitoring and evaluation systems and reporting
SAVI has a well developed monitoring and evaluation system based on its logframe and indicators, regular reflection meetings at state and national level, state level workplans, quarterly and annual progress reports (at state and national level), and external reviews. The logframe indicators provide a good basis to assess progress against outputs, purpose and goal. SAVI has developed interesting monitoring tools including the Governance Baseline and State House of Assembly Organisational Capacity Assessments, which are of benefit to SAVI and its external partners.

The MTR finds that there are still some weaknesses with the indicator framework, which are discussed in section 3.4. The heavy reliance on the use of composite indicators collected once every two years makes it difficult to assess progress on a regular basis. For the purpose of regular monitoring and evaluation there is a need for simpler and more disaggregated measures that can be assessed by SAVI staff. In practice SAVI is already undertaking internal assessments of the Governance Baseline, which partly meet this need, but the process could be strengthened and built into regular reporting. The latest version of the logframe contains more results indicators which will be critical to demonstrating the changes that can be achieved through advocacy work. However, the indicators are still rather process oriented, and there needs to be a further shift towards the use of results indicators.

SAVI has developed an elaborate format for quarterly progress reporting at state and federal level. The MTR found that this process ties up a substantial amount of staff time, particularly in the overstretched state offices where completing the quarterly report typically takes up over two weeks of staff time. The length and complexity of the reports has increased over time making them difficult to read and to extract key information. It is recommended to simplify the quarterly reporting format focusing more on activities delivered and immediate results, and capturing high level results only when an important development has occurred and evidence of change can be provided. The MTR suggests experimenting with a 10 page quarterly report format for the state offices for the next reporting cycle. A more substantial document is required for annual (or possibly 6 monthly) progress reporting that would include a full assessment of progress against plan and logframe indicators.

### Oversight mechanisms
SAVI’s oversight arrangements at state level include the Technical Executive Committee and the State Advisory Panel, which are specific to SAVI, and the State Steering Committee, which covers all of the State Level Programmes. The general finding of the MTR is that these mechanisms are not working well in most states. The Technical Executive Committees are intended to provide a formal link to government. However, only one of these committees is operating (Kano), although a small, informal TEC has recently been established in Enugu. The State Advisory Panels are intended to make available to SAVI the advice, experience and political support of well informed and connected individuals. However, the SAPs are only functioning in Kaduna and Kano, and only to a limited extent.

The absence of effective oversight and advisory structures means that SAVI lacks an external platform for strategic reflection on its approach and programme, and a local forum SAVI can account for its performance, obtain legitimate feedback, expose itself to challenging views and seek buy in from local partners. SAVI is not well institutionally embedded in the states, which feeds perceptions that it is an externally driven initiative with limited Nigerian ownership. This has limited the extent to which the experience gained by SAVI can be retained in the state. Furthermore, it increases the risk that SAVI will be accused of interfering in local politics. This scenario has already occurred in Kaduna state and resulted in a period of limited access to the State House of Assembly. Resolving such crises depends on good communication with government and local power brokers, which is much easier where effective channels for communication and local diplomacy, have been established.

The MTR recommends that SAVI should give urgent attention to clarifying and revamping its oversight and advisory functions. The types of functions that need to be ensured include: (1) a representational function (via influential and well-respected persons of the state) to give visibility and certain level of credibility and local ownership, (2) a hands-on function via individuals who offer strong expertise in the key areas of SAVI’s work and, hence, can play a proactive role in overseeing programme management, and (3) an oversight function geared towards ensuring that SAVI pursues its work in a manner that is consistent with its own mission, local development policies and broader aspects of UK-Nigeria cooperation. To provide all of these functions SAVI will need to revamp and reconstituting the State Advisory Panels and Technical Executive Committees, but it will also be worth considering different and less formal arrangements. SAVI will need to identify new members and maintain their interest and commitment. In discussion with DFID it may be worth revisiting the difficult issue of paying a per diem or honorarium for the professional service provided.

### Coordination between SAVI and other State Level Programmes
The Mid Term Review observed many good examples of coordination and joint working between SAVI and other SLPs. These are detailed in the state reports in annex A, and include the following illustrative cases:

In Enugu SAVI and PATHS2 co-funded the influential state health policy dialogue. PATHS2 is contracting members of SAVI’s Advocacy Partnerships to provide training to Facility Health Committees. CSOs working with SAVI were also closely involved in fact finding for the production of a hard hitting documentary funded by PATHS2 on the state of primary health services in Enugu.

In Lagos SAVI and SPARC work jointly to implementation of training activities for the State House of Assembly. SPARC has supported capacity building of the LACSOP and PaGG Advocacy Partnerships.

In Kaduna ESSPIN has linked SAVI’s Gender Working Group AP to the SUBEB, ensured its participation in the Annual School Census, and brought the group into the State Steering Committee on Inclusive Education.

However, the overall results of coordination between SAVI and other SLPs have been rather mixed, and several problematic cases were encountered by the MTR. These include:

In Enugu ESSPIN has engaged to a very limited extent with SAVI’s Inclusive Education Advocacy Partnership, and has established an alternative CSO network under the umbrella of CSACEFA.

In Kaduna PATHS2 (through its centralised management in Abuja) contracted Action Aid to manage a grant programme to support CSO engagement in the MTSS process. This threatened to undermine SAVI’s approach to encourage CSO engagement without using external resources. The dispute took some time to resolve, but PATHS2 have now suspended the Action Aid contract pending a review. This has negatively affected SAVI’s relationship with Action Aid Nigeria.

In Kano SAVI’s relationship with SPARC had been much weaker than in other states. SPARC was initially reluctant to engage CSOs in budget and MTSS processes, although the relationship is now much improved.

The MTR’s observed that there is no general pattern to the quality of coordination, and that good and bad cases exist in each state and for each SLP partner. Good coordination appears to arise on an ad hoc basis where strong interpersonal relations exist and SLP staff appreciates the value of advocacy work. Because of its smaller size in relation to other SLPs and its dependence on generating results through leverage and replication, SAVI has generally been proactive in seeking opportunities for joint working with other SLPs. However, the other SLPs have not always been receptive to its proposals. There is some evidence that attitudes towards SAVI are beginning to change and that other SLPs are more actively seeking to work jointly with SAVI.

The MTR found evidence of systemic weaknesses in cross SLP coordination. The SLP monthly coordination meetings are often poorly managed with an absence of minuting, action points and agreed follow-up. DFID’s regional and state coordinators are intended to play an important role in coordinating SLPs, but have not been empowered to enforce joint planning and implementation. Where failures in coordination arise there does not appear to be a mechanism to resolve disputes and enforce a solution.

Cross SLP coordination issues will be covered in greater depth in the parallel SLP suite review. Consequently this MTR will not offer any specific recommendations on strengthening coordination. SAVI has been found to be sufficiently proactive in looking for opportunities for coordination and joint working, and does not need to take specific action on its own. The problems that have arisen affect all of the SLPs and need to be addressed at this level.

## Expansion into northern states
At the request of DFID SAVI has initiated work in three additional northern states (Katsina, Yobe and Zamfara). The proposed model is to work jointly with the PRRINN-MNCH project and SPARC. PRRINN-MNCH, SAVI and SPARC have recently discussed the modalities of joint working in the North for the remaining two years of PRRINN-MNCH’s operations. Joint working with SAVI will be focussed on the following areas: (1) promoting an integrated public health system (against the present situation of fragmentation), (2) ensuring better functioning of community primary health services, (3) advocating for more adequate provision of human resources and the deployment of qualified women staff in primary health, (4) strengthening links between short route accountability at the point of service delivery and long route accountability through the state policy process (in particular through links to the State Houses of Assembly and media), and (5) performance monitoring towards MDAs and Primary Health Care Agencies.

Because of the short two year window for engagement, PRRINN-MNCH is anxious that SAVI should begin operations in support of PRRINN-MNCH’s programme as soon as possible. SAVI has expressed a preference to start up its work through its standard approach starting with a comprehensive political economy analysis, actor mapping and other baseline studies.

It clear that DFID Nigeria is planning a larger scale and more ambitious programme in the new Northern states that will extend beyond the SAVI-PRRINN-MNCH-SPARC partnership as currently planned. However, the shape and timing of this programme is not yet clear making it very difficult for SAVI to plan for a larger scale engagement. In view of these uncertainties it is difficult to make firm recommendations on SAVI’s engagement in the new Northern states, but the following suggestions can be made:

DFID Nigeria needs to develop and explain its strategy for engaging in the new northern states as soon as possible in order for SAVI to start considering broader options for promoting voice and accountability beyond the proposed partnership with PRRINN-MNCH.

SAVI will need to adopt an approach that is both strategic and opportunistic responding to variable circumstances in different states including: PRRINN-MNCH’s presence and legacy in the State, variations in socio-economic conditions, the local political agenda, the strength of demand side actors, and other planned DFID initiatives and projects.

Gender and Social Inclusion issues should be built into the design of SAVI’s work in the new northern states from the outset. There are useful lessons to be learned from SAVI’s experience in Jigawa which presents similar socio-cultural conditions. The focus should be on looking for ways for women’s voice to be aggregated and heard, and to ensure increased women’s representation in local CSOs.

SAVI should go ahead with the proposed partnership with PRRINN-MNCH. The proposed model of embedding SAVI staff in PRRINN-MNCH offices requires a different mode and engagement to SAVI’s established way of working. SAVI needs to take full account of the risk, but on balance the approach appears feasible and offers an opportunity for a rapid start up and implementation. The areas for joint working listed above provide a suitable focus for SAVI’s activities. However, it must be recognised that these can only be partially addressed within the lifetime of the PRRINN-MNCH programme. The priority should be to ensure a rapid start up using PRRINN-MNCH’s knowledge and experience as a starting point and initiating advocacy activities while conducting political economy and S-DoC studies in parallel.

The Mid Term Review supports the proposed approach to engaging in the additional northern states, but does remain concerned that rushed and under-resourced implementation could prove to be counterproductive. There is a particular risk that SAVI’s engagement in the new northern states will divert overstretched human resources from the existing states. SAVI in discussion with DFID needs to present a plan to for human resource deployment in the new states, and explain how the identified risks will be mitigated. Growing security risks are also very concerning and are discussed in section 2.8.

## Gender and social inclusion
Despite the many challenges to advancing voice and accountability frameworks for women and other socially excluded groups in the five SLP states, the SAVI MTR found strong evidence of commitment and progress to integrating issues of gender and social inclusion (GSI) in key aspects of the project.

In the northern states, the project operates within a socially conservative context where religion, low literacy, and traditional leadership structures limit opportunities for girls and women to play significant roles and decision-making or benefit from government services. The problem is compounded by the generally weak governance structures and service delivery agencies. It is therefore necessary to engage more broadly at the level of enabling environment for GSI issues.

Advocacy Parternships are addressing issues affecting women, girls, and other socially excluded groups. SAVI’s Advocacy Partnerships are working effectively to create an enabling environment for reducing discrimination against girls and women, and increasing investment in social and economic problems that improve the quality of life. APs and their member CSOs are advocating on issues that directly affect girls and women. This includes policies such as free maternal and child health (FMCH) in Enugu, Kano, Kaduna, and Jigawa, and girls’ education in all five states through formal advocacy or through coordination with other SLPs. Efforts to codify longstanding FMCH policies in legislation have been faced many challenges, with no state yet passing new legislation; SAVI’s advocacy partnerships have registered significant achievements in increasing budgets and expanding services relevant to women (Kaduna, Enugu, Jigawa and Kano). Equally important, health and women’s groups have gained confidence and credibility as strong, organized voices with the MDAs and the SHoAs.

In the education sector, Advocacy Partnerships in Jigawa, Kaduna, and Enugu have a girls’ enrollment and retention focus. In Jigawa, the School Health Advocacy Partnership has influenced the new policies on free basic education for girls and improvements in school water supply and separate toilets to encourage families to send and keep their daughters in school.

The Advocacy Partnerships have gone beyond focus on issues affecting women and girls to include other excluded groups, especially People with Disabilities (PWD). In Lagos, SAVI’s support to the People with Disabilities AP contributed to broadening the advocacy, awareness, and support for the Special People’s Bill that was signed into law in July 2011.

Advocacy Partnerships are expanding voice of women and socially excluded groups. Most of the education and health Advocacy Partnerships include women in leadership positions. They have been able to engage effectively with more male dominated institutions, such as the education MDAs, SHoA and the media to advance their advocacy agendas. Some of the Advocacy Partnerships are moving towards a more strategic view of gender needs. In Kaduna, the Gender in Education AP evolved to become the Gender Working Group that has mainstreamed gender into the MTSS and budget processes in health, education, agriculture, and water resources.

While acknowledging the gender focus and composition of the Advocacy Partnerships as a positive feature of the SAVI programme, it is also important to pay attention to the internal dynamics operating within the partnerships. A few of the Advocacy Partnerships met by the MTR team were clearly dominated by male individuals in spite of their inclusion of many female members. It may be worth studying from a gender and social inclusion perspective whose voice is heard within the Advocacy Partnerships and whose voice is projected into the policy process.

Peoples with Disability are also finding voice in Advocacy Partnerships, most importantly in the PWD group in Lagos, but also in several other APs in Kano and Jigawa that have begun to advocate on disability issues relating to health and education policy.

SAVI has increased staff and partners’ capacity for Gender Assessment and Budget Processes. State team members have been trained in basic gender analysis approaches and are using basic gender frameworks to identify and assess the levels of empowerment of women in their Advocacy Partnerships. Advocacy Partnerships in Enugu and Kaduna States have also received similar gender training on gender concepts and frameworks including strategies for engaging with the MTSS process in each state. In Kaduna, there have been some preliminary discussions on providing more support to the Women Affairs Committee on gender budgeting and monitoring MDAs around budget execution and service delivery.

SAVI’s Staff and Capacity for Gender Programming. Since the inception phase, SAVI has continued to strengthen capacity to mainstream GSI issues into programme planning, logframes, workplans and state team personnel profiles. SAVI has conducted a review of HR and financial policies to look at hiring, position descriptions, and salaries through a gender lens. Each state office has a Gender Focal Person while maintaining a clear policy that mainstreaming is the responsibility of all staff.

SAVI has an impressive record on hiring women in leadership positions in the state offices. In four of the five states the State Team Leaders are women – Kano, Kaduna, Enugu, and Jigawa. The SAVI MTR and prior reviews suggests that the perspective and experiences of the STL affect the types of issues and approaches to partnering and advocacy reflected in the state programs, perhaps accounting somewhat for more GSI sensitive interventions.

Despite significant progress on GSI issues at the SAVI programme, AP, and SHoA levels, there is room for number of improvements in approach and interventions:

SAVI should consider engaging with the SHoA Women Affairs Committees and the Women Affairs MDAs to scale up capacity to address GSI related policy and resource issues.

There is a lack of gender specific indicators presented in the logframe (although for some indicators disaggregated source data does exist). This gap would partly be filled by SAVI’s proposal for an additional indicator under output three that would assess the ‘level of demand side activity amongst SAVI partners on strengthening the governance related gender-enabling environment.’ The MTR team would prefer the monitoring framework to take on a stronger results focus. One option would be to measure the policy and advocacy issues successfully advanced (and where change has been enacted) by SAVI partners reflecting voice of women and other socially excluded groups. This could be included as a sub-indicator to the tracking of policy and institutional change at purpose level (i.e. include as a component of purpose indicator 3).

SAVI should step up its support to APs and broader civil society on GSI related policy analysis, gender budgeting, and advocacy using trainers from appropriate civil society organisations, local policy centres and university departments.

SAVI should incorporate capacity building of media on GSI reporting. This is an essential element of building awareness and a more enabling environment for progress on GSI issues.
## Conflict and insecurity
Nigeria has always posed security problems for development projects. However, the security environment in the North has deteriorated over the past few years with the increasing frequency of Boko Haram attacks. This has intensified over the past two months since the MTR team conducted its fieldwork, and is likely to remain a major concern for the foreseeable future. SAVI’s work has not yet been significantly disrupted by insecurity. However, there is a clear risk, which demands a serious and proactive response. The MTR team is not well experienced in providing security advice, but would like to make the following observations:

- SAVI’s management appears to be security conscious and well equipped to meet the current challenges. However, at this point there would be merit in providing some external support to review and cost security arrangements for SAVI and other DFID projects operating in northern Nigeria. This would need to include an assessment of the circumstances under which SAVI’s operations can be continued or may need to be adjusted or suspended. An immediate concern is the security implications of SAVI’s start up in the additional three northern states. The safety and practicality of operating in Yobe state looks particularly doubtful at this point in time.
- DFID needs to strengthen its capacity and support for providing ongoing security-related information and support to its projects operating in northern Nigeria.

With rising inter-communal tensions SAVI needs to develop (preferably with other SLPs) in affected states an explicit and documented conflict strategy. This would strengthen SAVI’s: (1) understanding of the (conflict) context in which they operate, (2) understanding the interaction between SAVI’s operations and the (conflict) context, and (3) ability to act in ways that avoid negative impacts and maximise positive impacts on the (conflict) context. Conflict sensitivity goes further than ‘conflict awareness’ in the sense that it implies a proactive attitude with regard to the interaction between operations and (conflict) context. SAVI is already doing many of the right things in these areas, in particular by promoting inclusiveness and conflict sensitivity in its advocacy work. However, this would be an opportune moment for further reflection on developing these principles further and more explicitly building them into working practices.

The notions of ‘working around, in and on conflict’ (developed by Jonathan Goodhand) could provide some useful guidance in developing a conflict policy and strategy in affected states. Programmes should avoid considering the conflict solely as a ‘disruptive factor’, over which little influence can be exercised (working around conflict). They should recognise that they can be negatively affected by conflict, but may also have (if managed in an insensitive way) a negative impact on the dynamics of the conflict. This should lead, where needed, to reactive adjustments of the programme, a greater focus on positioning (neutrality, impartiality) and improved security management (working in conflict). If such an attitude is adopted there is the potential for development programmes to affect the dynamics of the conflict in a positive way. This does not necessarily require a refocusing of programmes onto addressing the root causes of the conflict or peacebuilding work (working on conflict).
# Conclusions, lessons and recommendations
## Conclusions
The Mid Term Review provides a favourable assessment of the results of the SAVI programme. SAVI is broadly on track to meet its output milestones, although some outputs have still only been partly achieved. SAVI has developed a viable model for issue based policy advocacy and monitoring that avoids the risk of creating dependence on donor support and distorting civil society agendas. This demonstrates the value of behind-the-scenes brokering of networks and partnerships, and the nurturing of Advocacy Partnerships through the use of training, mentoring and selective funding of partners’ activities. Another major achievement of SAVI has been to strengthen communication and interaction between civil society, the media and State Houses of Assembly resulting in much better prospects for demand side engagement in the policy process.

SAVI appears to be making an effective contribution to its project purpose. There is evidence of improvements in voice and accountability processes within civil society, State Houses of Assembly and Government. These improved processes are beginning to generate results. The Mid Term Review has documented 11 examples of changes in policy and implementation where there is evidence of attribution to SAVI.

The Mid Term Review has identified parts of the SAVI programme where progress has been slower than anticipated. This applies to output 2 (civil society engagement in government budget and planning processes) and output 4 (improved state houses of assembly systems for transparency, public engagement and financial oversight). While there are some examples under output 2 of successful Advocacy Partnerships working on budget tracking and MTSS processes, there is a need to rethink the approach to the other Advocacy Partnerships that are struggling to engage effectively. There has been significant progress in working with State Houses of Assembly, but SAVI’s milestones have only been partly achieved for this output. Over the second half of the SAVI programme there are good opportunities for SAVI to engage more closely with State Houses of Assembly particularly by working with Members on the oversight of public finances, constituency relations and committee work. However, bringing about lasting improvements will require long term engagement and carries high risks. The Mid Term Review has also highlighted the relative weakness of SAVI’s work with the media, and the need to scale up this engagement.

The Mid Term Review finds that SAVI offers good value for money at each of the three levels of economy, efficiency and effectiveness. A full assessment is not possible because of the absence of reliable expenditure data by sub-output. However, there are indications that SAVI has been able to deliver its outputs in an economical and cost-efficient manner. There is emerging case study evidence of very good value for money at the effectiveness level. The value for money assessment has also indicated that increasing staff resources at state level could be achieved at relatively low marginal cost. This would enable SAVI to scale up its activities significantly with the potential for delivering much improved results.

## Lessons
For the purposes of the Mid Term Review it is worth highlighting some general lessons learned from the set up and management of the SAVI programme:

DFID took a correct decision in designing SAVI as a standalone programme rather than as a component of SPARC. There is general agreement amongst informed stakeholders that it would have proven impossible for a single implementing agent to work simultaneously on the supply and demand side of governance. Creating a standalone programme has given SAVI the freedom to engage in sensitive issues. However, the drawback of SAVI’s separation is that it has often found itself operating in isolation and is regarded as a junior partner by the other SLPs.

The architecture of the SLPs has led to an unhelpful separation between short route and long route accountability. SAVI’s inception review led to a clear recommendation that SAVI should focus solely on long route accountability through the state policy process. Short route accountability at the point of service delivery has been taken up by PATHS2 and ESSPIN in their work with Facility Health Committees and School Based Management Committees. While this reorganisation has helped to focus SAVI’s work, it resulted in a gap emerging between the two routes to accountability. Effective advocacy through long route accountability depends on understanding service delivery at the local level as it is experienced through short route accountability. These links have not been sufficiently addressed in the architecture of the SLPs, and this has been detrimental to their effectiveness. However, there are examples of SAVI and other SLPs increasingly coordinating around activities that help to reconnect the short and long routes of accountability (see section 4.4). While these are promising developments, it has taken several years for these links to develop, and opportunities have already been missed.

Voice and accountability programmes can lead to rapid results. The examples of policy and institutional changes documented by this review provide encouraging evidence that significant results can be achieved by voice and accountability programmes in the near term. This should help to allay concerns that voice and accountability programmes do not fit with DFID’s results focus. It is worth emphasising the value of process improvements brought by these programmes, but it is also essential to be able to demonstrate value for money and results. SAVI is beginning to produce evidence of such results, and should be encouraged invest further in results based monitoring.

SAVI’s behind the scenes role in brokering partnerships and making connections has been very valuable. Much of SAVI’s value added has arisen from the programme’s ability to bring together civil society groups in Advocacy Partnerships and to make connections between civil society, the media and State Houses of Assembly. This brokering role implies a rather different way of working to traditional donor projects with a supply driven focus. Effective brokering requires a flexible approach, willingness to operate opportunistically and to depart from the workplan, sufficient space for experimentation and long term investment in relationship building. Fortunately SAVI has been able to operate under these conditions, which have contributed to the programme’s effectiveness.

It has been worthwhile supporting State Houses of Assembly. There is little donor experience in Nigeria of working with State Houses of Assembly. In this context SAVI’s focus on working with State Houses of Assembly presented a major risk, but there are sufficient signs of progress to justify the investment. Realistically, the benefits from this will only be sustained if DFID can commit to supporting State Houses of Assembly over the long term.

## Recommendations
The MTR recommendations for SAVI’s work under outputs 1 to 5 are presented below:

#### Output 1
Recommendation. Within the next 3-6 months SAVI needs to decide whether it will take on any new advocacy partnerships. Beyond this point there is too little time remaining to achieve a sustainable result within the project lifetime. The broad recommendation of the MTR is to consolidate progress made with the existing APs, but a few changes and additions may be needed. There is an opportunity in Lagos to step up work on health and education (through LACSOP, PaGG or other groups) and so strengthen synergies with PATHS2 and ESSPIN. The MTR review is concerned that the proposed approach to building a WATSAN AP in Enugu is too localised in scale to fit with SAVI’s model of long-route accountability. The review also suggests considering narrowing the focus of the Climate Change partnership in Lagos around flood prevention and management (see Annex A).
Action Point. Final decisions on new APs or changes to AP focus by mid 2012.

Recommendation. As the Advocacy Partnerships mature they need more technical, research, policy and scientific support to engage credibly in state policy processes. SAVI has been effective in providing support on advocacy skills and organisational development, but needs to be able to make available to the APs more technical expertise on policy content, and to work to develop local TA capacity.
Action Point. Proposal on new SAVI recruitment or mobilisation of locally available, external TA by March/April 2012.

Recommendation. SAVI needs to do more to ensure the sustainability and replicability of the work of its Advocacy Partnerships. This requires working more with APs and individual members on organisational development, external communications and the mobilisation and management of funds.
Action point. For those Advocacy Partnerships with demonstrated readiness make available a package of additional support during the first half of 2012. Evidence of the usefulness of this support will be tracked by the 2012 Annual Review.

#### Output 2
Recommendation. Focus on addressing the problems of the less well performing Advocacy Partnerships under output 2 (particularly Kaduna and Enugu). On a case by case basis consider options of: 1) forming a broader and probably looser network of CSOs interested in budget/MTSS work that can be linked to the work of all of the SLPs, 2) encouraging some output 2 APs or individual members of APs to become professional service providers, 3) further strengthening links between output 2 and output 1 Advocacy Partnerships, and 4) transferring budget tracking/MTSS work to the output 1 APs.
Action point. Finalise state-by-state proposals on strengthening output 2 work in coordination with other SLPs during first half of 2012.

#### Output 3
Recommendation. SAVI needs to give working with the media as much emphasis as its work with civil society and the State House of Assembly. Stepping up engagement with the media should include a focus on media development and building journalist's capacity to report on policy processes and public accountability.
Action Point. Implement contract amendment 3 provisions as soon as possible. Prepare a complete strategy and budget for additional scaling up work with the media by March 2012.

Recommendation. SAVI should scale up broader efforts to bring together civil society organisations, the media and State Houses of Assembly by replicating successful models such as the V&A platform in Kano, LACSOP in Lagos and the civil society group that engages with the Enugu State House of Assembly.
Action Point. Scale up this work over next year where conditions allow.

#### Output 4
Recommendation. Following the 2011 elections there is a significant opportunity to step up engagement with new members of the State Houses of Assembly. This should focus particularly on building capacity in public financial oversight, constituency relations and strengthening committees working on issues relevant to SAVI's Advocacy Partnerships.
Action Point. Develop further the global strategy and priorities for each state for working with State Houses of Assembly. This should focus in particular on opportunities to work with members of the House, strengthening constituency relations, options for supporting Committee work, and actions to enable greater transparency and accountability in the House. Consider appointing a dedicated SHoA officer for each SAVI state office.

Recommendation. SAVI's partnerships with State Houses of Assembly need to be placed on a more formal footing with a jointly agreed programme of support and commitments from both sides on resources to be applied building in the need for flexibility in timing.
Action Point. Develop and agree work programmes with three State Houses of Assembly by end of first quarter of 2012.

Recommendation. Identify ways to embed the experience gained by SAVI of working with State Houses of Assembly within Nigerian organisations (National Assembly and/or others).
Action Point. Idea for consideration during 2012. Decision by next Annual Review.

#### Output 5
Recommendation. Develop new external communication tools including succinct presentation of the SAVI approach, results achieved to date and stories of change. Develop tools to capture recent challenges and achievements for internal and external audiences (e.g. quarterly bulletin, development of extranet/ website). Step up communications efforts to non SLP development partners. Increase SAVI's presence in national and state level CSO fora.
Action Point. SAVI to have revised external communication strategy in place by mid 2012.

#### Additional recommendations
Recommendation. SAVI should give urgent attention to revamping its oversight and advisory functions. The aim should be to restore the functions provided by the State Advisory Panel or Technical Executive Committee, but probably through different and less formal arrangements. The types of functions that need to be ensured include: (1) a representational function (via influential and well-respected persons of the state) to give visibility and certain level of credibility and local ownership, (2) a hands-on function via individuals who offer strong expertise in the key areas of SAVI’s work and, hence, can play a proactive role in overseeing programme management, and (3) an oversight function geared towards ensuring that SAVI pursues its work in a manner that is consistent with its own mission, local development policies and broader aspects of UK-Nigeria cooperation
Action Point. Revamped Oversight/advisory bodies to be in place by July 2012

Recommendation. Recruit 1 additional State Programme Officer through contract amendment 3. Consider recruiting an additional State Programming Officer or advisor (for media or SHoA work) on the basis of a new contract amendment or budget reallocation.
Action Point. SAVI to present a proposal for increased human resources at state level by end of March 2012

Recommendation. Step up work in the additional northern states in partnership with PRRINN-MNCH, but take careful account of the risks identified in section 2.6 and security issues discussed in section 2.8.
Action Point. SAVI in discussion with DFID needs to present a plan for human resource deployment in the new states, and explain how the risk of spreading human resources too thinly will be mitigated. The problem of insecurity in Yobe is an additional concern that requires a decision to be taken in the near term about the feasibility of beginning work in this state.

Recommendation. SAVI to provide expenditure data on a sub-output basis to enable more sophisticated value analysis.
Action Point. SAVI to begin reporting by sub-output during first quarter of 2012

Recommendation. SAVI State Quarterly Progress Reports are overly long, presentation is complex and the process takes up too much staff time. In discussion with DFID and IMEP a simpler and shorter (max 10 pages) report format for state teams' quarterly reporting should be developed.
Action point. SAVI to propose simpler quarterly reporting format for state teams for implementation in the next reporting period. DFID and IMEP to provide guidance.

Recommendation. A data validation exercise for the Governance Baseline and other sources of logframe evidence and indicators should be undertaken by IMEP prior to the 2012 Governance Baseline update.
Action point. IMEP to validate Governance Baseline methodology and other data sources before 2012 update. Validation of results during and after 2012 update.

#### Gender and Social Inclusion Recommendations.
SAVI should consider engaging with the SHoA Women Affairs Committees and the Women Affairs MDAs to scale up capacity to address GSI related policy and resource issues.

Include more gender disaggregated information in the logframe where this can be derived from source data. Consider including within the third purpose indicator a measure of demonstrable changes in policy and implementation reflecting the voice of women and other socially excluded groups.

SAVI should step up its support to APs and broader civil society on GSI related policy analysis, gender budgeting, and advocacy using trainers from appropriate civil society organisations, local policy centres and university departments.

SAVI should incorporate capacity building of media on GSI reporting. This is an essential element of building awareness and a more enabling environment for progress on GSI issues.

Action points. Progress on above 4 gender and social inclusion recommendations to be reviewed at next annual review.

#### Conflict and Security Recommendations.

SAVI requires external support to review and cost security arrangements for operations in northern Nigeria.

DFID needs to strengthen its capacity and support for providing ongoing security-related information and support to its projects operating in northern Nigeria.

With rising inter-communal tensions SAVI needs to develop in affected states an explicit and documented conflict strategy (see section 2.8).

Action points. In view of the urgency of the issue action to be taken on the above three recommendation by end March 2012.

#### The next Annual Review.
Recommendation. The 2012 Annual Review should be scheduled for the third quarter of 2012 to allow for time for finalising the logframe, completing scheduled CSO/SHoA assessments and public perception/awareness surveys, and to complete the data quality review. 2012 Annual Review to cover all of the logframe, but should focus particularly on progress in new northern states and implementation of key MTR recommendations.

Action point. IMEP and DFID to agree timing of next Annual Review by March 2012.

## Suggested changes to the logframe
#### General recommendations
Many efforts have been undertaken to improve SAVI’s logical framework. These improvements have served two purposes: technical modifications to ensure compatibility with functional requirements (logframe theory) and improvements/additions to better reflect and communicate the reality and dynamics of SAVI. The logframe modifications have been globally appropriate and have improved the quality and relevance, as a management tool, of the logframe.

The flip side of this evolution is that the logframe has grown in length from 7 pages in January 2010 (already considerable) to 10 pages (clarifications not included) by October 2011, while the activity level is not yet included in the logframes. The rather qualitative nature of the project, and correspondingly, of the objectives at outcome and output levels, is a major explanation for this. The present long (and complicated) logframe reduces its usefulness for external communication and accountability. In addition, it makes internal monitoring more demanding. The frequent modifications of the logframe further complicate monitoring (both internal and external) and evaluation exercises that seek to assess project performance over a longer period of time.

The frequent modifications to the logframe over the last two years illustrate how and to which extent the logframe has been used as a learning tool and be adapted to the increasing level of understanding and the dynamics of SAVI. As such it seems to have been used as a tool for reflection on SAVI’s future rather than as a reference for internal evaluation and monitoring, and reporting. This can be understood in view of SAVI being a demonstration project that had to develop along largely unknown paths. However, now that the project seems to be on track and its theory of change more firmly established, it should be possible to diminish the frequency and depth of changes in the logframe and bring more balance in the various ways it is being used.

As part of IMEP deliverables under Output 2: "Appropriate Technical Advice provided on the design and functioning of individual SLP M&E systems", SAVI and DFID should jointly review and finalise the current SAVI logframe through a process facilitated by IMEP by end March 2012. The final logframe should reflect consideration of the MTR suggested changes at output and indicator levels, and reflect DFID's expectations around contributions to suite-level objectives at purpose level, as well as reasonable targets, milestones, data collection timeframes as the basis for periodic reporting, ARs, and evaluations. The final logframe should also incorporate DFID and SAVI’s expectations around GSI.

It addition SAVI should work on a short (and simplified) version of the logframe for external communication purposes in view of the increased importance attached to output 5 and the evolution to the community of practice stage within APs.

The following points are preliminary suggestions by the MTR team for discussion during the logframe review. It is envisaged that IMEP core team will have further suggestions to make.

#### Intervention logic

While SAVI’s intervention logic is generally coherent and its results chain plausible, there is some room for improvement:

- The present outcome/purpose statement is rather a summary of the five outputs than its effect. It is therefore recommended to reformulate the outcome/purpose statement in such a way that it indicates the envisaged effect of the outputs, i.e. changes in behaviour, practices and policies. A possible formulation could be: "SHoA, government and CSOs demonstrate improved behaviour, policies and practices that embody greater voice and accountability”;
- Output 5, as it stands now, is situated at a lower level than the other outputs. It is therefore recommended to either uplift the output (by changing its formulation) or to integrate it as a sub-output under outputs 1, 2 and 4, which would imply that the key actors involved in these outputs (APs, SHoA staff and members) would become co-responsible for replication. In view of the importance attached to the replication of SAVI’s approach (SAVI as a demonstration project), we recommend to alter its formulation, for instance as follows: “Development actors are able to replicate key aspects of SAVI and its partners’ voice and accountability approaches”. However, knowing that replication already takes place, one might wonder whether SAVI should not increase its ambition level and explicitly intend to achieve replicability. The output would then read: “Development actors replicate (or demonstrate a sustainable approach to replicate) key aspects of SAVI and its partners’ voice and accountability approaches”. At the minimum SAVI should set up a mechanism to inventory the replication efforts of its approach and address in that way the demand to provide evidence of its impact. These could then be captured in an indicator at purpose level.
It is recommended to include, preferably in an annex to the logframe, the main activities for each output so as to allow a better understanding of the approach followed for each output and an identification of the assumptions at activity level.

#### Assumptions
Overall, the assumptions are appropriate, but some minor corrections are recommended:
- The assumptions should be updated as some relate to events of the past (such as the 2011 elections).
- References to SPARC and other SLP should be avoided, while the actual content of the assumptions should be maintained (e.g. SPARC is able to deliver its outputs to a satisfactory degree, i.e. it improves the key functions of government in lead states; should become: key functions in lead states improved); the rationale behind this recommendation is that it is not important who realises the assumption (any other actor/factor than SPARC can do it also).
- The formulation of a few assumptions is too strong/demanding and should be softened; for instance:
- CS groups do not use their influence for personal or political gains; a better (less uncompromising) formulation would be : CS groups do not make substantial abuse of their influence for personal or political gains;
- Social instability and insecurity do not affect poverty reducing resource allocation; a better formulation: social instability and insecurity are not substantially affecting poverty reducing resource allocation.
Once the activity level will have been included in the logframe, assumptions at activity level are to be identified and also pre-conditions (= assumptions that need to be fulfilled before activities can actually start).

#### Indicators
Output 3 indicators need to capture more fully the key features of an enabling environment for policy advocacy and monitoring and the work of SAVI in brokering links between civil society, the media and State Houses of Assembly. The first output 3 indicator could be recast as 'Improved communication, understanding and willingness to interact between civil society, the media, State Houses of Assembly and the Executive.' An additional indicator measuring media coverage of state policy issues and processes could also be developed in case the recommendation to invest more in media development is adopted.

While most indicators are adequate from a methodological point of view, the indicators as a whole remain rather abstract and intangible, and, hence, cannot adequately address the increasing demands on SAVI to ‘demonstrate its outcomes’. Hence, overall efforts should be undertaken to come up with more tangible/easy-to-understand indicators. Further, the following is recommended:

- Overall, it is important to reduce reliance on composite indicators that are only measured once every two years. These indicators are needed, but for the purpose of regular monitoring and evaluation simpler and more disaggregated measures are also required.
- In case the recommendations to reformulate the purpose/outcome and output 5 are accepted, the indicators related to these objectives should be reviewed accordingly:
  - at outcome level, the indicators can be maintained, but it is recommended to modify the third indicator and ‘break it open’ in several sub-indicators that refer to ‘improved behaviour, policies and practices that embody greater voice and accountability’;
  - At output 5 level, indicators should be modified according to the formulation adopted to capture either the ability of partners to promote replication or actual evidence of replication.

## Implementation of 2011 Annual Review Recommendations
The 2011 Annual Review was a light touch review carried out in June 2011 based on a one week field visit and a self assessment document prepared by SAVI. As such it was not appropriate to make far reaching recommendations on the future orientation of the SAVI, and consideration of many issues was deferred until the Mid Term Review.

Most of the recommendations of the 2011 Annual Review related to suggested improvements in the logframe, many of which have been incorporated in the latest version. It had been intended for IMEP to provide technical support on logframe development prior to the Mid Term Review, but the later than expected approval of IMEP’s inception report prevented this activity from taking place. In the event SAVI has substantially improved its logframe, but there some outstanding issues to be resolved as discussed in section 4.4 above.

The 2011 Annual Review discussed in some depth the need to find ways to link short route and long route accountability, and options for engaging at LGA level. The Mid Term Review finds that some progress has been made in these areas, and there are good examples of members of SAVI’s Advocacy Partnerships strengthening their links to the community level and supporting short route accountability initiatives promoted by PATHS2 and ESSPIN. SAVI is also gearing up to engage at the LGA level in the context of the oversight of the Conditional Grants scheme. This could take place in partnership with other SLPs or with the new DFID programme M4M. The next Annual Review should look further into how these arrangements are developing, and whether they will prove effective.

The 2011 Annual Review identified the need for SAVI step up its work with media organisations. SAVI has since gained approval under contract amendment 3 for the recruitment of a media officer.

Annex A – State Level Reports
#### SAVI Mid-Term Review – Enugu State Report

1. Context
The political environment in Enugu is characterised by complete control of the People’s Democratic Party (PDP) and the concentration of power in the hands of the Governor Sullivan Chime. Other political parties have very little presence in the state and organised civil society is weak. The governance of Enugu State has generally been weak with major shortcomings in public financial management, budget realism and budget performance. Combined with a lack of transparency and accountability, this has greatly undermined the resourcing and quality of service delivery in the state.

The 2011 election campaign witnessed splits within the PDP and a power struggle between the incumbent Governor, Chime, and his predecessor. Governor Chime won the election and has since consolidated his power base. Seventeen of the 25 members of the State Executive Council are new members selected by the Governor. There has also been considerable turnover in the membership of the State House of Assembly (16/24 new members). No opposition parties are represented in the House, and all its members owe their position to the Governor’s patronage. In spite of this concentration of power, there have been some positive developments in the governance of the state. The new members of the Executive Council and the legislature are viewed as being more competent, professional and reform-minded than before. The new State House of Assembly has been much more assertive in using its powers, recently rejecting three Commissioners nominated by the Governor. The Governor speaks in terms of a developmental and service delivery agenda, and is credited with major improvements in urban road infrastructure during his last term.

Concerned at the manifest weaknesses in governance in the state DFID has indicated that its continued support will be dependent on measurable improvements in performance over the next six months. A review will be carried out in April 2012 based on the assessment of Key Performance Indicators jointly established between DFID and the state government.

2. Description of the SAVI Enugu programme
The SAVI programme in Enugu can be summarised as follows:

- Output 1: Formation and training of two Advocacy Partnerships covering Maternal and Newborn Child Health (MNCH) and Inclusive Education (IE). SAVI has recently established a nascent Advocacy Partnership for Water and Sanitation;
- Output 2: Provision of training on budget processes and MTSS to a wide range of civil society organisations. Formation and training of a Participatory Budget and Planning Advocacy Partnership in the first quarter of 2011;
- Output 3: SAVI has brought together a media platform that has launched a new radio phone-in programme, ‘Nigeria Go Better’. SAVI engages with a group of civil society organisations working with the State House of Assembly;
- Output 4: Training for staff and members of the State House of Assembly, focusing on budget control and oversight. Induction for new members. Technical support to the ad-hoc committee for development of legislative term agenda;
Output 5: Internal lesson learning, sharing of experience between Advocacy Partnerships (including exchange visits to Kaduna), communication of SAVI’s approach to other SLPs and donor projects.

3. Assessment of progress against outputs
#### Output 1:
The Maternal and Newborn Child Health (MNCH) Advocacy Partnership is well established, and benefits from a highly motivated and committed membership. It has a good working relationship with Paths2, who jointly with SAVI provide the group with technical advice and enable its participation in state level policy processes, including the health policy dialogue and MTSS. The group also has good relations with the Ministry of Health and plans to engage with the Health Committee in the new State House of Assembly. The group has been undertaking field research and fact finding spot checks on the state of health service delivery in the state. It plans to undertake a more comprehensive survey jointly with the staff of the Ministry of Health. It has undertaken exchange activities with the SAVI Kaduna MNCH group and plans a joint visit to Ondo state, which is regarded as model in the delivery of MNCH services.

The Inclusive Education Advocacy Partnership focuses broadly on the issues preventing children from attending school, including issues surrounding disability and gender. It has embarked on a state-wide survey of the numbers of out-of-school children and the reasons for their non-attendance. Initial returns have indicated serious data quality problems. The reliance on traditional leaders to complete the survey coupled with expectations that the survey will be linked to access to scholarships appears to have distorted results. The group is now proposing a data validation exercise. The Partnership is not enjoying a good relationship with ESSPIN, who they complain is dismissive of their work, and prefers to work with their own CSO partners. This is also reflected in the group’s marginal involvement in the education MTSS process. An exchange visit with the Kaduna Gender Working Group has been organised.

The Water and Sanitation Advocacy Partnership has been recently formed around a neighbourhood organisation that has organised street level security and engaged in advocacy on local water supply issues. From the perspective of the MTR review team this group does not appear to fit the SAVI model of an advocacy partnership. It is a single neighbourhood association - rather than a coalition - that is primarily involved in local service delivery and short-route accountability. The MTR doubts whether the structure and experience of the group lends itself to effective advocacy on state level water and sanitation policies and programmes. To support this initiative further a convincing case would have to be made explaining how it will be possible to scale up engagement beyond a single organisation to promote advocacy on state level water policy issues.

#### Output 2:
The Participatory Budget and Planning (PBP) Advocacy Partnership was only fully established in the first quarter of 2011, and does not appear to have yet developed a strong organisational structure and a clear understanding of its activities and strategy. The group has undertaken budget and MTSS training through SAVI and SPARC, but its participation in budget and MTSS processes has so far been limited (the group recently participated in the agriculture MTSS).

Beyond the PBP partnership SAVI, has supported the engagement of its Advocacy Partnerships - and civil society more broadly - in state budget and policy processes by providing training on budget monitoring and MTSS. Civil society and government have recently signed a communiqué on citizen’s inclusion in the state budget and policy process.

#### Output 3:
There have been incremental improvements in communication between civil society, the media, the State House of Assembly and the executive. A working group in the State House of Assembly is liaising with the executive on budget realism and fiscal responsibility outside of normal legislative processes. There is increased civil society engagement with the State House of Assembly, which has appointed a civil society liaison officer. SAVI’s financing of the ‘Nigeria Go Better’ radio phone-in programme is a promising initiative that has created a new and challenging form of interaction with politicians and officials in the state. With advice from SAVI, the Enugu State Broadcasting Corporation has started to televise the proceedings of the State House of Assembly.

#### Output 4:
Under the previous State House of Assembly, SAVI made rather limited progress building management systems and financial oversight capacity, although some training was delivered to the staff of the legislature. With the election of the new House, conditions now appear to be much better for SAVI to engage effectively. The induction training provided by SAVI was well received and took place this year for the first time before the inauguration of the House. The State House of Assembly has taken measures to increase openness and citizen access (see output 3 above). SAVI has organised a self assessment exercise in the State House of Assembly following the 2011 elections. The findings have been taken up by the ad hoc team for the legislative term agenda, who are preparing a comprehensive set of proposals covering the internal and external environment of the House, and its oversight function. These proposals may form the basis of a programme for further SAVI support to the State House of Assembly.

#### Output 5:
SAVI is well known to the other SLPs, who regularly draw on SAVI’s expertise in civil society advocacy work, its knowledge of local organisations and the political economy of the state. Beyond its advocacy partnerships SAVI has engaged with a wide set of civil society organisations across state to promote advocacy work.

4. Progress against outcomes
Progress has been made in passing key legislation, most notably the Public Procurement Law, which has been passed and assented. Disagreements remain between government and civil society groups over the implementation arrangements for this law, in particular the question of whether government should head the proposed Procurement Council.

The follow-up to the Health Policy Dialogue represents a change in policy and implementation where SAVI’s contribution can be demonstrated. There is evidence that government has responded to the dialogue by deploying more Primary Health Care (PHC) workers and repairing some damaged facilities. In one LGA studied by the MNCH Advocacy Partnership, it is reported that 65 additional ad hoc PHC workers have been employed. Given the good results of the Health Policy Dialogue it is proposed to repeat the event quarterly.

5. Cross-SLP coordination issues
The review mission found some good examples of coordination between SAVI and other SLPs, but also discovered some problematic cases and systematic weaknesses in the SLP coordination framework. Monthly SLP coordination meetings are taking place, but mainly for the purpose of exchanging information rather than joint planning. It has yet to be seen whether improvements will be driven by the recently established cross SLP thematic working groups (SAVI is leading on social mobilisation). All SLPs recently contributed to the Political Economy Analysis update (under SAVI’s lead), but the process was time consuming and imposed considerable transaction costs. A draft version of the report consulted by the MTR team suggests that there are still problems of inconsistency between different sections of the report.

The State Steering Committee (overseeing all SLPs) is reported to work quite effectively in Enugu. The SLPs have recently convened a three hour meeting with the Governor of the state, which is reported to have been a useful interaction, but was the first such meeting for several years.

SAVI enjoys a good working relationship with SPARC, and jointly implements capacity building activities for the State House of Assembly and Civil Society Organisations on budget and MTSS processes. The relationship with PATHS2 is also strong, and the co-funding of the Health Policy Dialogue appears to have been a particularly successful activity. Members of the FMCH Advocacy Partnership have provided training to the Facility Health Committees established with PATHS2 support. A forum linking community health groups to CSO groups advocated on health issues at state level has also been established. The FMCH Advocacy Partnership has also contributed to Paths2 fact-finding and the preparation of a hard hitting documentary on the state of heath facilities in Enugu. Paths2 have requested SAVI’s support to engage in the legislative agenda (e.g. Drug Management Agency Bill, Free Maternal and Newborn Child Health Bill, District Health Law).

SAVI’s relationship with ESSPIN has been more problematic with tensions arising around the limited use ESSPIN has made of SAVI’s Inclusive Education Advocacy Partnership. ESSPIN regards itself as the lead project in the education sector, and expects other projects to fit into its model as service providers. Effectively ESSPIN has developed its own voice and accountability programme led by CSACEFA the Civil Society Action Coalition on Education for All. ESSPIN have informed the Inclusive Education partnership that they should participate in its work under the CSACEFA umbrella. Some individual members of Inclusive Education Advocacy Partnership have been invited to participate in ESSPIN activities (including MTSS process), but not the group as whole.

6. Office management
The critical management issue facing SAVI in Enugu is the limited human resources available to the project. Staff are competent and highly committed, but struggle to cover the workload imposed by a broad ranging programme. Several of the Advocacy Partnerships indicated that SAVI is unable to respond in a timely manner to their requests and workplans. Following the illness and death of the previous State Team Leader there was a hiatus in SAVI operations in Enugu. The new team leader has only been in post for a year, but has made good progress in renewing the programme.

This year SAVI has reconstituted its Technical Executive Committee (TEC) around three individuals with close connections to government. Rather than providing an oversight role and formal link to government, the function of the TEC appears to be to provide advice and contacts with government. In other states these would be the functions provided by the State Advisory Panel. The members of the TEC appear to be committed and interested in SAVI, but so far their work has been rather low in intensity (2 meetings held so far).

7. Key issues
SAVI’s achievements in Enugu state so far appear to be rather modest, although much of this is explained by the political environment and the change in state team leadership. In view of these challenges progress appears satisfactory, and the recent increase in activity (particularly with the State House of Assembly) is encouraging.

It is clear to the review team that human resources in the SAVI office are highly stretched to the point where this is detrimental to the effectiveness of the programme. In view of these constraints, it is questionable whether the team is in a position to establish a third advocacy partnership for water and sanitation, especially given the limitations of the proposed group referred to above. The MTR review team suggests that SAVI carefully reviews the resource requirements of this work before going further with the Advocacy Partnership. The key test of the feasibility of going ahead will be to take a judgement on whether the group will be in a position within 1-2 years to engage in long-route accountability work. The opinion of the MTR team is that SAVI can make better use of resources by focusing on the existing advocacy partnerships and its expanding work with the State House of Assembly.

The review team has noted that there are particular challenges in cross SLP coordination in Enugu. The added value that has been gained from close cooperation between SAVI and PATHS2 contrasts sharply with the difficulties experienced in the relationship between SAVI and ESSPIN. Attempts to resolve this problem within existing coordination structures have not yielded much result, indicating that higher level intervention from DFID is required.

#### SAVI Mid-Term Review: Jigawa State report

1. Context
- Jigawa state is relatively young state, carved from Kano in 1991. Its proximity to Kano and traditional leadership structure characterized by emirate rivalry for political relevance and resources has affected economic and political development;
- There has been limited progress in making the state self-reliant. The State’s budget is predominantly from the federal allocation, with significant resources from DFID and other donor (EU, UNDP, UNICEF, IBRD, IFAD, ADF) funding. However, after many years of financial mismanagement, the current Governor, Sule Lamido, elected in 2007, has instituted political and governance reforms, including fiscal discipline, that has increased resources for health, education, and infrastructure. Since 2009, Jigawa has been able to access significant federal and donor funds for education, health, and infrastructure through counterpart funding;
- Traditional power structures (five emirates) continue to play an important role in State politics; the antagonism between the most influential (Hadejia) and the four other emirates determines to a major part the political dynamics. The emirs’ struggle clarifies the dispute related to the governor election result; recently the election tribunal decided in favour of the newly elected governor;
- CSOs are however rather hopeful that the newly elected governor and his Executive Council will be able to engage in an important reform agenda. The governor has also undertaken important reconciliation steps towards the Hadejia emirate (a.o. by granting representatives of the emirate key positions in his government);
- With massive road rehabilitation projects undertaken throughout the State during the last five years, efforts to improve electricity generation the independent power platforms, scale-up of investment in rice, fisheries, and dry season irrigated farming in the Hadejia-Nguru wetlands, the economic climate is improving;
- In 2007, Jigawa established the Gunduma Health System. Adapted from the WHO recommended “District Health System”, the Gundamas provide integrated health services to communities, which brings both primary and secondary care services under one management and accountability structure. In other states, secondary health services are managed at state level;
- Despite a more open environment for reforms and civic engagement, and signs of reforms at the MDA, decision-making is still largely centralized through the governor’s office, with suspicions between government and citizens still high. In early 2011, the governor banned the Daily Trust from all governor-attended events due to critical articles written in the influential northern-based daily;
- At the start of the programme, all key actors SAVI is supposed to work with (CSO, SHoA, media) disposed of limited capacities to take up their key roles in society;
- The SAVI Jigawa State programme was initially managed out of Kano, A full office was set up in mid-2010 after the first OPR.

2. Brief description of the programme
The programme supports three partnerships:

- the maternal and new-born child healthcare (MNCH) advocacy partnership (AP) consists of 11 member organisations and conducts advocacy in favour of the adoption of a free MNCH care bill, but is also engaged in other issues related to the provision of basic health services;
- the school health (SH) AP (12 member organisations) deals both with issues related to education (provision of basis education, policy advocacy, education budget) and school health (school environment issues);
- the project monitoring (PM) AP has presently 13 member organisations after a renewed start mid 2011 and among others engaged in an analysis of the 2011 budget compliance with the MTSS/MTEP in three sectors – health, education, and water resources.

A civil society Gender and Social Inclusion Focus Group supported by SAVI is evolving as a coalition. SAVI is evaluating the members and activities to determine whether to support the coalition as an Advocacy Partnership.

The work at SHoA level does not differ substantially from what is done in other states; efforts are undertaken to increase the transparency and accountability mechanisms of the House members, but also to improve the system and functioning of the House. So far, the program has worked well with the SHoA staff. There have been some challenges and delays in supporting the SHoA on induction of new members. Members wanted to participate in organizing the training. SHoA has identified and has engaged 3 SAVI Consultants to carry out the induction of new members using the SAVI produce training manual. Will also use House staff who completed a SAVI TOT. The induction has not yet been scheduled. SAVI’s work with SHoA has been largely at the staff and committee levels. With support from SPARC, ESSPIN and PATHS II, SAVI has supported capacity building around the MTSS/budget process at the appropriations, health and education committee level. Capacity building of staff has included improvement in committee reporting, oversight of cash releases, monitoring of expenditures of the House and MDAs using a template developed with support from SAVI. SAVI is supporting implementation of the new Service Commission Act.

While Jigawa is a state that in many ways lags behind the four other states, the SAVI program is quite similar to that in other states. The issues addressed by the AP and via the work with the SHoA are relevant in view of the challenges the state is confronted with.

3. Assessment of progress against outputs

#### 1. Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy & monitoring
The MNCH AP seems most advanced in developing a replicable and sustainable approach. It presently is engaged in state-wide advocacy for a free MNCH bill which is now in the second reading stage at the SHoA. The AP has further used evidence gathered by its members related to the provision of health services, which has contributed to the extension of health services to 10 more primary health facilities. It has also been successful in changing the composition of the budget in favour of its key advocacy issues (free MNCH care, recruitment of additional female health workers). The AP uses mainly its own resources and is able to mobilise additional resources where needed (e.g. lawyers to assist in legal drafting processes). More than the other APs it has gained the capacity and confidence to identify and liaise with other key stakeholders (SHoA, MDAs, media). It has also developed GSI sensitive tools to monitor service delivery and budget implementation, and has shared its approach with the similar AP in Kaduna and other actors active in the health sector.

The AP members feel that SAVI has created considerable added value in bringing them together in a coalition and guiding them behind the scene in their advocacy work, which has also impacted positively on the performance of the individual member organisations.

The SH AP is a looser network with members that are more spread across the state and focus on a broad range of issues related to education and school health. This broad approach poses challenges to the network to focus its action and ensure the necessary quality; more capacity building is needed to bring the partnership to the desired level of competence. The AP also still needs financial and logistical support from SAVI to ensure its bare functioning as a partnership. Its members show however a high level of commitment and passion for the issues taken up and manage to establish linkages with the community level. The AP has been successful in influencing key budget allocations (e.g. more attention for school renovation, teacher training and recurrent expenditure). It uses the national policy framework as a major reference and chooses carefully the issues it wants to advocate for, thereby assessing first what is realistically achievable at the level of the state. However, so far the AP’s efforts in terms of long-route accountability promotion have remained limited.

On the other hand, the AP membership has inspired its members to undertake new activities at the level of their respective organisations (e.g. radio broadcasts) and to intensify their efforts to further promote the inclusion of girls in basic education.

Overall, the MNCH AP seems to develop towards a sustainable partnership that is able to develop a replicable approach to health-related advocacy. The sustainability of the SH AP might be more challenging in view of the configuration and focus of the group but it is certain that the competences and skills acquired will be highly useful for the member organisations and lead to tangible improvements at the community level.

#### 2. Civil society demonstrates a replicable and sustainable approach to engagement in government budget & planning processes
The BM AP has experienced a difficult start, as many of the initial member organisations were headed by civil servants who considered the analysis of budgeting and planning processes as too delicate. After a few efforts to engage in in-depth work on these issues the AP came to an actual standstill to be revived by SAVI in the middle of 2011; only 13 from the initially 39 partners are ready to continue on a renewed basis. New members are however expected to join.

Since its renewed start, the AP has been very active and able to achieve important results. SAVI provided support for training on budget, project ad policy monitoring (in which the other APs also participated) and with the support of SPARC facilitated the AP in liaising with relevant institutions (three key ministries of Water and Sanitation, Environment and Education, and the Directorate of Budget and Economic Planning). These activities provided a good base allowing the AP to engage in an analysis of the 2011 budget compliance to the MTSS/MTEP in the three above-mentioned sectors. The AP is presently working with the MDAs concerned to review the MTSS/MTEF document.

The organisation, with SAVI support, of focus group discussions (FGDs) on service delivery in 9 LGAs was another important activity in which in total 405 participants representing men, women, youth and the socially excluded participated. The AP also works with the Ministry of Water Resources and with the Ministry of Agriculture to review and finalize their 2012-2014 MTSS plans.

The next steps will deal with the discussion of the results of the FGD via dialogue sessions.
As the AP is actually newly established, it is too early to assess its sustainability. So far, budget analysis and tracking work in the narrow sense has not been conducted; the AP is however expected to further develop its competence and outreach.

#### 3. An enabling environment for policy advocacy & monitoring and engagement in government and budget & planning processes
Working on improving the relations between CS, media and the SHoA has been a key issue for the Jigawa team as it was considered a vital condition to achieve the program’s major aims. Efforts have so far led to an increased mutual appreciation of each other’s roles and functions. In particular, the cooperation between the SHoA and the media has improved, the latter covering increasingly the activities of the House and featuring SHoA members on its programmes; the PR unit of the house, with SAVI’s support, also organised a one-day training for journalists.
Cooperation and understanding between CSOs and media also improved leading to increased coverage of CS activities on the radio, the granting of free or discounted airtime to CSOs, etc. Cooperation between CSOs and the SHoA remains however rather weak.

SAVI-supported radio programmes (such as a phone-in radio programme on the SHoA functions) increased the public’s understanding of the roles of media, CS and the SHoA. The SAVI initiative made the media to continue on their own similar programmes without SAVI support and to deal more explicitly with issues that involve government and CS, such as information resulting from monitoring of project implementation.

Various APs have promoted GSI issues (e.g. advocacy to increase enrolment and retention of girls in schools) and the media, CSO and SHoA improved understanding of GSI issues led to higher consideration of gender issues in radio programmes, featuring more women, children and marginalised groups. Increased attention to the problem of the limited number of female staff in health and education sectors has led to the introduction of a community birth extension workers course for women and, more broadly, to increased advocacy for more employment opportunities for women.

#### 4. Improved state houses of assembly systems for transparency, public engagement and financial oversight
So far SAVI’s engagement with the SHoA members has been relatively limited and has mainly dealt with improving the relations with the media (see above) and facilitating public access to information (portal of SHoA on government website, information campaign on functions of the House for public and SHoA members). Apparently these efforts have led to improved openness at the level of the house members towards CS and the media and to increased interaction between these groups. The induction of new the members of the house has been planned since quite long but so far has not taken place. Apparently the unstable political climate (disputed governor election results) and the frictions between old and newly elected members in the parliament are responsible for this delay.

The work of SAVI at the level of the SHoA staff has been more considerable and is much appreciated. An Organizational Capacity Assessment provided the basis for a broad support programme including budget analysis and tracking training, including the development of adequate templates, rules and a timeframe for the annual budgeting procedure, and the presentation of a budget review manual (developed by SAVI Kaduna) to the members. Further training was related to report writing, accounting procedures and improvement of the process of appropriation bills. SAVI support also included capacity building for 25 House committees and a TOT on induction training for the new members.

While the staff of the House very much appreciates SAVI’s support, they fear SAVI will be a ‘come and go project’ and insist mechanisms should be devised to ensure sustainability.

With over 50% new members after the May 2011 elections, SHoA is likely to continue to be isolated from the reforms process at the governor and MDA levels. Although the Service Commission Act of 2011 provides more authority around staffing, SHoA budget management, etc., SHoA has taken only small steps to loosen the grip of the governor’s office on its legislative agenda, MDA oversight activities, and resources.
SHoA has expressed some reluctance to engage civil society despite improvements in relationships, participation in radio and forums, and more outreach to their constituents. The members have welcomed support to strengthened their understanding MTSS, budgets, PFM, and emerging policy/legislative issues that will provide the knowledge and confidence needed to engage the public and MDAs. They have committed to public hearings and have begun to introduce private bills, mainly nuisance laws such as public smoking and cursing, but have not yet focused on policy matters such as health and education bills that remain the exclusive domain of the governor and MDAs.

#### 5. Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches
As is the case with the other SAVI state-level programmes, SAVI Jigawa consciously shares its approaches, strategies and key experiences with the other SLPs and via DFID quarterly meetings; also other international partners are informed on its approaches. The joint PE analysis has been a means to better coordinate certain strategies, among others on the way to address the lack of quality human resources in the State.

4. Progress against outcomes
When assessing the program’s progress against outcomes, it is important to realise that the programme only really took off in 2010 after the OPR mid-term review. The major programme outcomes can be summarized as follows:

- SAVI has significantly contributed to the on-going process of strengthening of a varied range of institutions – CSOs, media and the SHoA – that are all in the midst of a comprehensive learning process (skills, attitudes, processes and systems development) that is induced by several factors and create a favourable environment for an institutional strengthening project such as SAVI;
- The considerable improvement of the relationship between CSOs, the media and the SHoA is most probably the most important outcome so far. This improvement is obvious via changes in policies and practices at the level of these three types of institutions that liaise far more frequently with each other, involve each other in key initiatives undertaken, etc. This development undoubtedly contributes to improved voice and accountability processes in the State;
- At the level of the SHoA new practices are slowly taking shape with regard to the functions the House is supposed to assume: inclusion of CSO concerns in policy making and budget, follow up by the SHoA of project implementation monitoring results, better tracking of budget implementation, improved scrutiny of draft budget, openness of the House towards demands of the public and increased readiness to account, improving systems and procedures which eventually should substantially increase the performance of the House;
- It is claimed that the increased media coverage of issues related to the performance of the SHoA, MDAs and local government has led to an improved public understanding of the role and function of these institutions and to increased interest for governance issues and the implementation of development projects at the local level. It has been found that the type of demands emanating from local communities to SH Members and office bearers at large is changing from opportunistic requests to demands that address structural problems at the local level;
- The set-up of APs is expected to produce more tangible results at outcome level in the future (e.g. passage of the bill on free MNCH). However, already at this moment the simple fact of bringing CSOs together in APs has produced important outcomes in terms of the CSOs capacities to pursue their own objectives at the grassroots level. The members of the partnerships seem to have contributed significantly to improved service delivery in the health and education sectors, thereby paying adequate attention to gender and social inclusion issues. In this regard, it is hard to isolate the contribution of these CSOs from that of other actors (ESSPIN, PATHS2) and the effects of a globally favourable environment, but the positive role of the CSOs cannot be ignored.

5. Key issues
- Jigawa state is rather particular, with on the one hand deeply entrenched values and attitudes that are considerable constraints for SAVI’s V & A work, but, on the other hand, a mix of factors that create a surprisingly favourable environment for changes in the desired direction. The MTR team has not been able to analyse these factors in depth but has find out, for instance, that despite highly male-dominated formal and informal institutions, substantial progress is made in addressing gender imbalances;
- Work with the media (in particular radios) offers a big potential in Jigawa state that is not yet fully utilised by SAVI. While increased engagement of the media has already produced important effects, a more exhaustive media development strategy would allow multiplying their impact in a cost-effective way and contribute to addressing the constraint of limited outreach, in particular in hard-to-reach parts of the state;
- The initiative of the PM AP to conduct FGD at the level of nine LGAs in which carefully selected representatives could articulate their views and experience with local development seems an interesting model to bridge the gap between grassroots and higher-level work. At this same time, it could be an interesting model for SAVI to deal with its own lack of accountability and transparency;
- While the work of SAVI is much appreciated, there is a strong demand to ‘further wider its nets’ to include more actors in its work so that more issues can be addressed and a broader voice developed. It is felt that the present environment offers many opportunities for effective advocacy that presently cannot be addressed;
- The SAVI programme has in various ways successfully addressed GSI issues. These are prominently on the agendas of the F-MNCH and SH APs. In addition, in the composition of the APs, SAVI has carefully aimed at ensuring an adequate balance among the different religious and ethnic groups. At a certain moment a GSI group has been formed (with members from the different APs) to address a few specific issues related to gender, with support (training) from SAVI. Once these issues had been addressed, the group stopped functioning;
- The sustainability of the results related to output 4 should be addressed, both on the global and the state level. So far, there does not exist a well elaborated sustainability strategy. Different challenges are to be addressed to ensure that local capacity to continue to accompany the SHoA strengthening process is well embedded in local institutions and mechanisms;
- The Jigawa state program has no TEC and SAP. As such, it lacks a platform for strategic reflection on the strategies and policies followed, and a local forum/institution where the programme staff can account for its performance and get ‘legitimate’ feedback. For obvious reasons, it is not easy to address this lack of institutional embedding. This constitutes an important challenge for SAVI, in particular in view of its aims to promote transparency and accountability. There do not seem to exist easy solutions for this; however, it is worth experimenting with an approach similar to the FGD initiative taken by the PM AP to acquire inputs from the grassroots on the issues considered as a priority;
- SAVI has initiated a reflection on designing an approach to coordinate voice aggregation at the local and LGA level where many project-initiated structures (SBMC, FHC, …) have been set up but seem to work largely disconnected from each other. The idea to establish a forum for cooperation at LGA level that can assume a key function in carrying local voice to a higher level merits being worked out further. Question: is this an issue SAVI can address (considering its mandate to deal with higher-level advocacy and its resource limitations)?
- Question/dilemma: how far should SAVI ‘follow up’ its lobby and advocacy results to check whether they are leading to tangible outcomes that make a difference for the communities? At least there is a need to better document these outcomes in a way that clearly demonstrates how the change can be attributed to SAVI’s work. But how should this be done: is it realistic to ask partner CSOs to provide this information? Or should SAVI engage itself in documenting how change takes place at the local level?
- After initial success of the Gender and Social Inclusion Focus Group in integrating more voice for women, people with disabilities, and other excluded groups into the advocacy of other APs, SAVI is likely to taken on the group as a GSI AP. With the effective work of the FMNCH and School Health APs around access and quality of services to women and girls, and a generally supportive environment for broader reforms around social inclusion, there are opportunities for big gains if the appropriate support provided. SAVI may lack sufficient staff and technical resources to fully develop its potential and address the many opportunities and requests from various groups in Jigawa.

6. Cross-SLP coordination issues
The SLPs exchange information with each other via the monthly SLP meetings; at this occasion monthly implementation diaries are also exchanged. The joint work on the update of the Political Economy Analysis and corresponding SLP engagement strategy has been an opportunity for the SLP partners for dialogue and exchange. Further, ESSPIN and PATHS2 have very much appreciated SAVI’s support in identifying CSOs that cooperate with these two programmes at the local level. Some of these CSO’s are also members of an AP, which provides clear opportunities for better linking short and long route accountability processes. SAVI has also introduced the other SLP programmes to the newly elected House during a two days workshop. SPARC has directly and indirectly provided support to SAVI’s work related to budget analysis and tracking. PATHS and SAVI coordinate efforts to get the F MNCH bill adopted; it is expected that the two programs will intensify in a later stage their cooperation to ensure proper implementation of the bill. SAVI has supported that work of PATHS by associating the State House Committee on Health to the health policy discussions.

Despite these examples of good cooperation and the creation of synergies, cooperation among SLPs mainly occurs on an ad-hoc basis. Question: can/should we expect more? Integrated planning and implementation of all SLP programmes seems not desirable neither feasible; but in a few selected domains (e.g. communication) a better coordinated approach is desirable.

7. Office management
The SAVI-Jigawa team is small, composed of committed and capable staff and hard working. There exists a clear division of task among the three program staff. The team’s approach to remain low profile and pursue its objectives essentially via its APs and other institutions adds to the efficiency of the programme; in addition much informal but highly valuable work is conducted but not well documented and included in the logframe. There is a clear pressure to expand activities and this is also desirable, but difficult to achieve without additional staff.

#### SAVI Mid-Term Review – Kaduna State Report

Context

- Governor Yakowa remains occupied with sustaining a fragile peace following intense post election violence. As Kaduna’s first Christian Governor, he is under great pressure to bring the dividends of democracy to the many competing ethnic, religious, and social interests across the state.
- The State House of Assembly has yet to settle down after the April 2011 elections. There was more than 50% turnover in members. Frequent recesses since elections, lack of experience of new members, capacity issues and lack of clear understanding of SHoA’s roles and responsibilities is delaying work on improving the functioning of the House and addressing key policy and budget reform.
- The new governor has moved the state away from the more centralised management approach of the former governor, opening more space for civic engagement, especially around the planning and budgeting processes at MDA level. However, civil society engagement with SHoA continues to be characterized by mutual distrust and suspicions, limiting effective voice of both civil society and its representatives’ in setting policy and resource priorities.
- The Kaduna SHoA is likely to remain constrained by capacity, its own internal interests, and political alliances that limit its role in balancing the power of the executive on sector planning and budgets, and advancing policy and legislative reforms.

Brief description of the programme
SAVI supports three Advocacy Partnerships in Kaduna. Two of the APs the Free MCH advocacy partnership and the Gender Working Group (GWG) have reached SAVI’s ‘Call Down’ Stage, meaning they are still receiving SAVI support on a request or as needed basis. The third partnership, Know Your Budget (KYB), is well respected for its work on the 2010- 2011 budget process, but is struggling to operate within the SAVI Advocacy Partnership approach.
All three APs seem to be evolving to take advantage of emerging opportunities and as challenges arise. The GWG has evolved from the Gender in Education AP, taking on a broader gender mainstreaming mission and possibly expanding to include increased voice for people with disabilities and other excluded groups. GWG’s work has also expanded gender work beyond the education sector focus of the APs to agriculture, water, and health. Their work with the SHoA is focused more around the MTSS/Budget process than on the stalled passage of the FMCH bill and other policies.

From the PEA Update (August – October 2011) there seems to be scope for advocacy around political appointments given the low number of women elected and appointed as officials following the 2011 elections.

The KYB in its current form appears to be more a group of individuals with technical capacity around budget and planning processes than a coalition of CSOs leveraging capacity and activities to enhance the work of member CSOs.

SAVI continues to face challenges in providing technical support to the staff and members of the State House of Assembly despite the successful induction of new members, well received training on the MDGs and Conditional Grant Scheme, and increased interest and response to civic engagement. However, the House has been reluctant to engage with SAVI on activities aimed at strengthening the House’s accountability functions. Suspicion by the House about the role of SAVI supported CSOs has also complicated relations. Over the past year these issues have presented a major obstacle to SAVI’s work, and large parts of the work programme have stalled. However, at the time of the Mid Term Review visit to the State House of Assembly relations appeared to have improved. Despite the challenges encountered, SAVI and SHoA have been working together around implementation of the new FOI, Public Procurement, Fiscal Responsibility and Public Financial Management and control bills.

SAVI has worked effectively to open space for dialogue and forums where SHoA, CSOs, media, and the general public can better understand the roles and processes of government. The engagement is breaking down some barriers and building more trust and partnership among these key stakeholder groups, especially around health, education, and budget issues.

Assessment of progress against outputs

3.1. Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy & monitoring
The two issue-based APs -- FMCH and the Gender Working Group (formerly Gender in Education) have demonstrated effective advocacy using knowledge and evidence to engage the health and education ministries, and the central MDAs on sector strategies, budget and planning.
The impact of a Free MCH Implementation Survey and a costing exercise for proposed scale up of free maternal health services are good examples of the how the FMCH Advocacy Partnership has matured and become more effective. The Implementation Survey carried out in 2010 resulted in greater awareness by the MDAs, SHoA and the general public of the gaps in implementation of the policy of free MCH services at both secondary and primary health facility levels. The results of the costing exercise has led to more open dialogue with government on a realistic package of services given MCH needs and resources available. This evidence-based engagement has increased the FMCH partnerships credibility with government. The impression of the MTR team is that the Gender Working Group have so far achieved more limited results perhaps because of their much broader focus.

SPARC has stepped up its support to SAVI on tools, reports and TA for use in training and supporting advocacy by CSOs, SHoA, and media. SPARC has also pointed out the need for deeper understanding of budget processing by SAVI and its partners. There is need to engage at all stages of the budget cycle and to use public expenditure and other reports generated by government and available to the public for advocacy and oversight.

3.2. Civil society demonstrates a replicable and sustainable approach to engagement in government budget & planning processes
DFID and other donor support for budget and planning processes have catalyzed civic engagement with government through SAVI partnerships and Kaduna’s civil society more broadly, including the media. SAVI has recognized the value of CSO capacity to engage in these areas to advancing policy reforms and improving service delivery. In response to the assessed needs of civil society and SHoA, SAVI has effectively leveraged support from SPARC, ESSPIN, PATHS II, and the Know Your Budget partnership to integrate more effectively budget and planning in its work with issues-based APs. The MTSS process has been the entry point, providing a structured framework for civic engagement with the health, education, agriculture, and water resources MDAs. The MTSS/MTEF and appropriations processes have also enabled SAVI to promote civil society engagement with SHoA through advocacy and technical support to committee staff and members.

The KYB members have expressed frustration that their membership in the AP prevents them from competing for consultancies for SAVI-supported budget and planning work. The group is planning to register as an organization that can be supported by other donors or through contracts and consultancies with government and other stakeholders. SAVI is not clear how to proceed with the partnership or how to address the central issue of planning and budget engagement by its issues-based advocacy partnerships. SAVI Kaduna are considering forming budget and planning sub-committees within issues-based Advocacy Partnerships.

Civil Society’s engagement in budget and planning is improving steadily; however, the House and the MDAs are still unsure how open they can be in sharing information and inviting interest groups to be part of the process. The Kaduna MDAs seem more open than SHoA, suggesting that SAVI has more work to do in helping SHoA to be more confident in its capacity and understand that civil society brings valuable perspectives and skills to budget and planning processes.

3.3. An enabling environment for policy advocacy & monitoring and engagement in government and budget & planning processes
SAVI has stepped up its work on Output 3 by bringing together SHoA, Media, and civil society to increase public awareness of the roles of the three stakeholder groups and building partnerships for reform of budget and planning processes, and government service delivery programmes. The ‘roundtables’ held most recently in August and September 2011 are creating space for the stakeholder to share their concerns and reduce distrust and suspicion.

SAVI is working to link experienced radio and print journalists to civil society advocacy work. The media partners noted that SAVI and its partners need to move beyond using the media for covering events to capacity building that strengthens and supports media at the journalist, editor, and owner levels. Additionally, SAVI should broaden its media engagement to include more local print and radio outlets. Media needs capacity to balance the negative influences of sponsored reporting, censorship and editors and owners’ fear of political reprisals. SAVI has facilitated media training on health and education issues, and coverage of government events and processes, but there is not yet a fully developed media strategy.

SAVI and the GWG are working to increase awareness and acceptance of Gender and Social Inclusion (GSI) analysis in policy, budget, and planning processes. SAVI carried out a GSI contextual analysis workshop in August 2011 focused on the health and education sectors. The GWG also has plans to carry out GSI work as part of the agriculture and water resource sector strategy process.

The updating of the Governance Baseline survey and other S-DOC documents is taking place August 2011 through early 2012. The findings should better inform a broader, more strategic approach to SAVI Kaduna’s work under Output 3.

3.4. Improved state houses of assembly systems for transparency, public engagement and financial oversight

A number of challenges have arisen since SAVI started to move beyond improving the systems and processes of the House to address capacity issues and reforms around civic engagement, budget and oversight functions,, especially as they related to engaging the MDAs on expenditures, policies, service delivery.

For example, there was significant push back from the House over the past year resulting from a misunderstanding of civil society statements and activities. Despite this and other challenges, SAVI worked with SHoA to developed the induction manual and training of trainers that enabled the House to carry out the induction of the 4th Kaduna State Assembly -- the first time in the state’s history that the House has coordinated the induction independently.

Despite SAVI supported efforts to promote greater budget realism, the House has continued to use its appropriations authority to add projects to the budget. Additionally, SHoA staff and members continue to be much more focused on engagement of the central and line MDAs on implementation of constituency projects than on budget performance issues such as cash releases and expenditure rates.

Progress against outcomes
#### Outcome: Civil society, state houses of assembly and government improve their voice and accountability processes

#### Civil society, SHoA and government have made some progress in improving voice and accountability processes, some of which is attributable to support from SAVI and the other SLPs. On the budget and planning side, all of the SLPs have worked to introduce the MTSS and budget processes which mandate inclusive voice in the expenditure review, sector planning budget review processed at central MDA level where SPARC has the lead. At the sector MDA level ESSPIN and PATHS II have supported both civil society and SHoA with technical support.

Mutual suspicion and distrust of civil society, media has limited members’ outreach to civil society on awareness and input on policies, executive and appropriation bills. The SHoA holds few public hearings and only recently has begun to move beyond carefully staged constituency engagement. SAVI and members report that SHoA participation in SAVI sponsored forums has helped civil society, media, and SHoA to explore ways to build public awareness and support for reforms and better governance.

Civil society pressure supported by SAVI and SPARC have resulted in some progress towards greater budget realism as indicated by the changes brought to the 2010-11 budget. There is also greater civil society engagement in the composition of the budget. The FMCH, Gender in Education, and Know Your Budget partnerships now receive call circulars and invitations to inform policy reviews and MTSS/budget processes. And SHoA members, committees and staff have benefitted from SAVI training and SAVI’s access to specialized TA from SPARC, ESSPIN, and PATHS2. SHoA has also begun to solicit technical inputs and perspectives from interest groups and ordinary citizens to inform policies and programmes implemented by the MDAs.

Key issues

- The SAVI Kaduna team is feeling the pressure to be specialists in many areas. With the demands of internal planning, mentoring of CSOs, coordination of capacity building activities, ongoing support and capacity building of SHoA, time and effort spent on coordination with three other SLPs, and heavy reporting, data collection, meetings schedules, and other internal SAVI responsibilities, the small SAVI state team is overextended. In addition to recruiting another programme officer, there may need for more flexibility and resources to use external TA to support capacity building and mentoring activities;
- The Kaduna state programme is entering a challenging phase. With the issue-based APs active for more than 2 years now, there is a need to invest in mechanisms for capturing replication and sustainability to reflect progress on Outputs 1 and 2. This is particularly important since APs do not submit reports and will be less supported and engaged with SAVI as they move closer to reaching the “Community of Practice” stage;
- SAVI may be too straight-jacketed in its approach to the stages of effective coalition building. The Kaduna experience indicates that varied pathways are possible. The GWG has evolved from being an issue-based coalition with expanding girls school enrolment and retention as the central focus to a network of organizations supporting gender mainstreaming processes across a number of sectors. In establishing the KYB partnership, SAVI brought together skilled professionals needed for the high level planning and budget processes. The partnership has evolved in ways that do not neatly fit SAVI’s approach to advocacy coalitions. There are important questions on how SAVI continues to support the advocacy and other capacity building for the two partnerships;
- Kaduna is exploring the possibility of adding a new AP, possibly around disabilities if broadening the GWG to incorporate social inclusion cannot be accommodated. The decision should be well informed by S-DOC updates, political economy (PE) analysis, organisational capacity (self) assessments (OCAs), stakeholder mapping, risk assessments, etc.) planned for early 2012;
- After more than 2 ½ years the State Advisory Panel (SAP) is still not clear on its role. And the Technical Executive Committee (TEC) has only met twice. The MTR team was concerned that the SAP does not appear to be clear about its role or supportive of SAVI. There is need for SAVI to explore ways to repair the relationship with the current SAP or find an alternative approach to stakeholder engagement of the project;
- There is scope to scale-up media support beyond the engagement of media by advocacy partnerships to report on advocacy issues and activities and increase public awareness of the role of government. Improved coverage and reporting on government activities, processes, and service delivery are important areas for media strengthening. While some SAVI staff and members of the CSOs within the APS are experienced journalists, the level and nature of the media strengthening needs of media houses, SHoA staff and members may require the deployment of more experienced media specialists ensure quality and credible TA;
- Progress in strengthening SHoA’s systems, reforming its approach to oversight of MDA budget and MTSS implementation, and soliciting civil society input in setting policy priorities has been slow and halting. The PEA and other S-DOC updates should provide guidance on the future direction of SHoA support;
- Renewed violence following the 2011 election has heightened tensions in a state with a history of ethnic/religious violence since the end of military rule in 1999. With Governor Yakowa in a delicate position in pushing reforms, SAVI will have to be sensitive to the need to reflect diverse voices in the advocacy partnerships and for advocacy to reflect understanding of the Kaduna political context. SAVI should also step up engagement through the SAP or other mechanisms to ensure understanding of issues that may lead to impasses and conflict with SHoA and other public offices;
- SAVI may want to begin discussions with conflict specialists on integration of conflict analysis, mediation and mitigation strategies for civil society and SHoA. Additionally, SAVI’s media support approach could include training of journalist on conflict reporting. DFID, USAID, EU, and UNDP have all support conflict work nationally and in Kudana. There is a lot of technical expertise to draw upon.

Cross-SLP coordination issues

Despite challenges around conflicting approaches to working with CSOs, the Kaduna SLPs continue to work well together, particularly in two BCIAs - improving access to maternal and child health services to reduce morbidity and mortality and increasing girls child enrolment, retention and completion rates. The extensive collaboration with both PATHS II and ESSPIN has at times been complicated by their more centralised decision making which contrasts with SAVI’s management practices.

The early start of the SLPs in Kaduna and the relatively stability of the state teams over the past 2 years means that Kaduna has had a longer period to work on coordination. The SLPs also have a positive experience base that affirms the need to work together to bring about reforms, strengthens systems, and leverage resources. The SLPs hold regular meetings and are also commited to joint planning and reflection on work around the BCIAs.

ESSPIN and SAVI have collaborated on building advocacy skills of the School-Based Management Committees to aggregate voice and engage more effectively at LGA level. ESSPIN has also established LGA level “Response Roundtables” that have district level education staff, LGA officials and representatives from SBMCs. SAVI could use this mechanism to support work in bridging the gap between short and long route accountability though support to CSOs to move issues identified at LGA level up to state level policy and resource allocation levels.

ESSPIN are keen to work closely with the Gender Working Group. However, ESSPIN may have higher expectations for engagement than the group is currently able to deliver. Compared to Jigawa where there is also an Education (School Health) AP, Kaduna has just begun to understand how the School Census Reports, School Health Policy, and the Teach Development Needs Assessments can provide information for more effective advocacy and oversight at the CSO, LGA, and SHoA levels.

Much attention has focused on problems arising from PATHS II procurement of services from ActionAid to fund civic engagement in the MTSS/budget process and advocacy for the FMNCH Bill through sub-grants. SAVI and PATHS II seem to have moved past this issue and now have agreement on a common approach to supporting CSOs and SHoA. Notable collaboration includes identification of CSO partners to support advocacy activities of health Facility Management Committees using SAVI’s CSO mapping reports. SAVI and PATHS II have also worked closely with the House Committee on Health on understanding the technical aspects of the FMCH bill, legislation on the Drug Management Agency and the establishment of a State Primary Health Care Agency in the state. PATHS II provides support to CSOs and SHoA on engagement of the Ministry of Planning and Budget and the Ministry of Health on health sector budget and planning. Additionally, the FMCH partnership and PATHS II collaborated on the FMCH service delivery survey used to build support for better oversight and expansion of service under the current FMCH policy and the proposed FMCH bill.

SPARC has been increasingly responsive to requests to provide consultants, publicly available information and training tools for engagement of SHoA and civil society on budget and planning processes. SPARC has in the past expressed concern that the advocacy groups do not have the capacity or experience to engage the central and sector MDAs on the MTSS, budget, and PFM and may jeopardize gains in acceptance of hard fought reforms. This view is changing following the experience of the 2010-11 budget process using both KYB and other APs. SPARC expressed the need for civil society to engage government on the full budget cycle, including budget performance reviews, and public finance management. This requires a deeper and more consistent engagement than most advocacy groups have capacity for at present.

Office management

The state team has strong advocacy capacity, knowledge and commitment to the focus issues of the advocacy partnerships – MCH, education, budget, gender and social inclusion, media engagement and governance. However, there are some questions regarding the depth of the expertise of the staff to guide the technical capacity building of legislators, house staff, media, and CSOs, especially on budget and technical issues related to policy.

The APs and SHoA’s expressed appreciation for the technical assistance and capacity of staff, but SAVI may want to consider allocating more resources to using a pool of capable consultants over the remaining project timeframe to reduce the burden and address capacity gaps of staff, and also to strengthen capacity of local consultants and institutions to support CSOs, SHoA, and media in the state.

#### SAVI Mid-Term Review – Report on Mission to Kano

1. Context

- The State has seen dramatic change in the political landscape with a new political party (and governor) coming into power after the elections earlier this year; a majority (60%) of members of SHoA are newly elected;
- The antagonism between present governor (already in power from 1999 to 2003) and previous governor impacts heavily on the development policy context; bold steps have been taken by the newly elected governor during the first 100 days of his government to mark the difference with previous policies, leading to immediate improvements in some areas;
- But the ‘reform mindedness’ of present governor seems often more inspired by his will to act differently from his predecessor than by adequate policy choices. This overall attitude is a serious constraint for the passage and/or implementation of some key reforms (Fiscal Responsibility Bill, Public Procurement Bill, Implementation of House Service Commission Bill) some of which have been initiated via the SLP’s;
- Strong civil society sector and media that have a tradition of cooperation and have built up experience in conducting joint policy advocacy; there is a legacy of cooperation of CSOs and media with SLPs.

Despite a long history of donor support and the central role of Kano in the political economy of the north, the state seems lacking in drive and energy around change and reforms, that will require a more open and engaged society. While there is a general sense that the state is receptive to donor support, historically the relationship has not been smooth with periodic cessation, delays, and refusal of support for cultural, social, and political reasons. (e.g. polio, reproductive health, HIV/AIDS, etc.)

2. Brief description of the programme
SAVi supports three partnerships:
- the PPMNCH (10 member organisations initially, now 20) advocating for free maternal and new-born child healthcare: the partnership is well connected to the SHoA and the media, the MoH and the (new governor-initiated) transition committee;
- Wudil, which is actually a regional water association and not an AP, that is advocating for a new water bill, is also well connected to all relevant key players and liaises with other regional water schemes for further advocacy and replication;
- COBTAK, the Coalition of Budget and Transparency Advocacy (COBTAK) predates the SAVI supported Budget Tracking AP. There have been some tensions as members from the other SAVI supported APs on Free MNCH and Wudil Regional Water Supply AP have joined the Budget Tracking AP. Additionally, the many AP members have been instrumental in creating the Voice and Accountability Platform covering a wider range of civic education areas and broadening participation to include media.

SAVI managed to establish a strong relationship with both the new and the previous SHoA, mostly working on strengthening internal systems of the House.

While the programme in Kano looks similar to that in other states, two specific characteristics can be noted: the cooperation with Wudil, which is not a ‘true’ AP and deals with a sector (water supply) that is hardly addressed elsewhere by SAVI or any other SLP and, more importantly, the existence of a V & A platform bringing together on a monthly basis representatives from CS, the media and the SHoA.
All activities are considered relevant in view of the situation in the State and the outcome of the PE analysis. New activities are essentially meant to further make progress in line with the SAVI theory of change (further promoting self-reliance of partnerships, sustainability and replication). A major problem, the non-inclusion of the youth in key governance processes leading (among others) to post election violence and an overall climate of tension, is however not explicitly addressed.
SAVI has had very limited success with the State Advisory Committee and Technical Executive Committee. There were discussions on merging the two. The SAP has held six quarterly meetings. It was clear that the SAP does not have a deep understanding of SAVI projects. Despite having access to the project documents, the members are not abreast or engaged with the APs or work with media and SHoA. They expressed concern that they were not able to engage the APs directly and did not seem to be aware of the FMNCH AP at all.

3. Assessment of progress against outputs

#### 1. Civil society demonstrates a replicable and sustainable approach to issue based policy advocacy & monitoring
Because of the adequate support provided via SAVI (among others), both PPMNCH and Wudil have grown out to solid structures that are capable to engage in issue based policy advocacy & monitoring. They function predominantly in an independent way and are using their own resources when defining and implementing their plans; SAVI occasionally provides activity-based financial support (e.g. related to townhall meetings, international women’s day, … in the case of PPMNCH, the yearly congress in the case of Wudil). With the support of SAVI, both have established linkages with relevant actors including the media, the SHoA, other SAVI/SLP related structures and MDAs. These institutions recognise their importance, engage them increasingly in key policy and legislative initiatives (e.g. Government has entrusted the review of the Water Bill to Wudil) and are taking increasingly into account the issued raised by the APs.
Both partners also started engaging to exchange their experience and expertise, both with actors in the State and beyond. In particular the Wudil initiative gives hope for replication in the short run at the level of other regional water schemes.
Overall, progress so far corresponds with the targets. Major issues for the future, in view of sustainability, are (1) the capacity of Wudil to share and replicate its approach and get it translated in a comprehensive bill that is accepted by the SHoA and duly implemented, and (2) the pursuit of PPMNCH efforts to get passed the bills related to free MNCH and the set up of a Primary Health Care Development Agency.

#### 2. Civil society demonstrates a replicable and sustainable approach to engagement in government budget & planning processes
The budget tracking partnership is composed of a number of organisations with a varied background, predominantly in social sectors who are not that much interested in government budget & planning processes as such, but rather deal with these because of the key role they play in actually making available the necessary resources for their respective social sector activities. The AP members, hence, were initially focused merely on project monitoring (which they conduct in a professional way) but have gradually shifted to limited (i.e. focused on their sectors) budget analysis and tracking; linkages are also established with the APs working on education and water supply to expand their work to include budget analysis and tracking. The group’s technical capacities were substantially enhanced via various trainings provided via SAVI and other donors. The AP has established relations with the SHoA and the media and with the relevant MDA’s (Ministry of Planning and Budget Ministry of Project Monitoring), but their sectoral capacities are to be further enhanced. The budget tracking process is further hampered by the present political situation (political conflict between present and previous government, see above).

The major strength of the group is situated in the strong linkages of its members with local communities and LGAs, that allow them to bring forward, in their project monitoring and budget-related work, the priority issues of the communities. The group is also closely linked with the V & A forum, and as such plays an important role in civic education. Linkages with other actors in the context of budget-related work (for exchange and replication purposes) are however still limited.

Overall, progress so far corresponds with the targets despite the relative weakness of the group with regard to the technical aspects of budget-related work. Major issues for the future, in view of sustainability and replication, are the further development of the technical capacities of the partnership and the strengthening of its cooperation with the Commissioner of Planning and Budget.

#### 3. An enabling environment for policy advocacy & monitoring and engagement in government and budget & planning processes
All actors concerned consider the readiness and capacity of CS, SHoA and media to relate to each other and undertake collective action to be a major achievement of the project. Cooperation among these institutions has led to the organisation of many important joint initiatives such as an interactive forum on the Freedom of Information Bill, a joint policy and budget analysis workshop, civic education efforts related to the electoral process and efforts (town hall meetings) to increase public understanding of the role of the SHoA. In addition key policy and budget processes have become far more inclusive and transparent. The media from their side have taken more interest in covering governance issues and the activities undertaken by the SAVI partners, and contribute much to awareness raising via their programmes.

The V & A forum that meets on a monthly basis and includes representatives from the CS, the media and SHoA staff is without any doubt the most important achievement in view of improving the environment for policy advocacy & monitoring and engagement in government and budget & planning processes. The forum has managed in strengthening the triangular relationship between the actors and addresses issues that can be considered key in achieving improved voice and accountability processes in the state.

Overall, progress so far corresponds with the targets. Major issues for the future, in view of sustainability and replication, are
- SAVI’s strategy to liaise with CS at large in the State; as CS is relatively well organised and has acquainted experience with cooperation and networking, it seems adequate to consider more structural cooperation with these networks so as to ensure more leverage and better ensure sustainability;
- SAVI’s model of cooperation with the media, where it might be adequate to consider the media as a partner in their own right needing some strategic development support.

#### 4. Improved state houses of assembly systems for transparency, public engagement and financial oversight
Important progress has been made in improving the SHoA’s systems. The proceedings of the House are broadcast via local radios and TV stations; the House disposes of a press directorate, staff that is dedicated to liaise with CS and plans the reactivation of its website. The organisation of public hearings is now included in the rules of the House and the first such initiative is expected to be organised next year. The previous House has approved a House Service Commission Bill which remains however to be implemented by the new government. Most importantly, SAVI has been instrumental in the creation of the Legislative Budget and Research Office (the first in the country) that plays a key role in designing tools and approaches meant to smoothen the functioning of the House. SHoA staff members also take up an active role in the V & A platform and engage in dialogue with their constituents via town hall meetings (see above).

SAVI has equipped the SHoA staff with capacities and tools to conduct policy and budget analysis. Capacities were further enhanced via exchange visits to other states. SAVI has also supported the induction process for new SHoA members (60% of them are newly elected), which has constituted an important entry point to the newly elected house (though there has been initial resistance towards the approach followed for the induction and SAVI’s involvement in it); the process has strengthened the members’ understanding of their roles. On the other side, the increase of the budget (out of political pressure) illustrates the House’s weakness with regard to budget issues and, more in general, its role in ensuring the establishment of adequate financial practices and oversight. SHoA staff members declared however that they are confident that in the future practices and outcomes in this regard will considerably improve.

Major issues for the future relate to the implementation of the House Service Commission Bill, the further improvement of the systems and resources of the House (adequate support staff for the Members), the strengthening of the Members’ capacities in the financial domain, and further training of the SHoA staff.

#### 5. Lessons routinely identified and effectively communicated on SAVI and its state partners’ approaches
In general, SAVI has engaged in various opportunities to present its program and approach to other stakeholders. It participates actively in the monthly SLP exchange and reflection meetings, and supported the other SLP through its substantial contribution to the updating of the political economy analysis and the states’ drivers of change analysis. SAVI has developed synergies with ESPINN (connection in House Committees on Basic Education and Education in relation to MTSS) and PATHS2 (joint work on MNCH bill); its cooperation with SPARC has however just started. It has also established contacts with other actors such as CEDPA, COMPASS, EU SRIP & EU WSSSRP in relation to issues taken up by the advocacy partnerships (health, water, budget tracking). The Wudil initiative seems have progressed most towards replication, as is illustrated by the interest of other actors (SWWWRP) in replicating their approach.

The work of the PPMNCH/Budget tracking AP’s is so far only shared within the SLP context.

4. Progress against outcomes

The major programme outcomes can be summarised as follows:
- The relationships between CSOs, SHoA (members and staff) and the media have considerably improved. Whereas these structures had virtually no contacts in the past and had considerably prejudices against each other, they now better understand their respective interests, perspectives and roles and the importance of cooperation in view of improved democracy and functioning of its constituents. The three structures seem to engage increasingly in cooperation on issues considered relevant for the development of the State, among others via the monthly meetings of the V & A platform;
- More in general, government institutions (in particular technical MDAs) are increasingly recognising the potential added value that can be realised via cooperation with non-state actors and, hence, associate these in key processes such as the definition of MTSS and budgets;
- SHoA has opened up to society by allowing the broadcast, via radio and TV, of its proceedings; its members have shown willingness to engage more explicitly with their constituencies via town hall meetings and linking up with their respective LGAs to monitor progress at the ground. The Commissioner Planning and Budget has declared its support for the passage of the Fiscal Responsibility and Public Procurement Bills which are presently being reviewed in the Ministry of Justice (process retarded because of change of government);
- Through the cooperation with Wudil, there is a clear opportunity to change the policy and practice with regard to water supply in a drastic way that ensures increased empowerment of the water users and contributes to sustainability (by increasing water tariffs), which is a considerable achievement in view of the reluctance of the political class to promote sustainable models. A major component of the proposed Water Bill has already been approved and declared for immediate implementation; Wudil has been requested by the House to draft the new Bill;
- There are clear indications that the approach applied in the Wudil Regional Water Scheme will be replicated to some (if not all) of the 15 Kano State Water Schemes;
- While still rather timid, reflections have started on sharing experiences and broadening the achievements of the partnerships to so-called non-SAVI partners, among others via the incorporation of these CSOs in existing platforms. Already at this moment, these CSOs have benefited to a certain extend from SAVI’s work, e.g. the changes at the level of SHoA made it more easy for them to liaise with the House, the work around the budget cycle has also increased their understanding and analytical capacities related to the budget cycle;
- SAVI has been instrumental in getting passed the Service Commission Bill that has been adopted under the previous government. Actual implementation of the bill (starting with the recruitment of adequate staff for the Commission) is however still pending;
- Through SAVI’s efforts, the Legislative Budget and Research Office has been established. Lagos and Kano are the first two states to join the National Assembly in setting up a Budget and Research Office to review, analyse and respond to budget and policy information provided by the MDAs and generate information needed by SHoA in engaging the public.

5. Key issues

The major achievements of the SAVI-Kano programme include:
- The strong advancement of the work with SHoA towards increased transparency, accountability and inclusiveness, via (among others) the establishment of the LBRO, the set up of a CS desk and recognition of the role of the CSOs and media, the openness of the house towards the public at large, … all point to the change of a paradigm at the level of the House in their relation to CSOs and media and the latters’ efforts to influence policies. A major challenge here is that the present political climate that still is characterised by the tensions between the two major political blocks and the way these related to each other;
- Related to the previous point, the set up and functioning of the V & A platform is another key achievement to further smoothen the relationships between SHoA, media and CSOs, and improve their cooperation around issues considered crucial for the State’s development. The initiatives of the platform in relation to civic education are important to be mentioned, but strategies to broaden the platform (inclusion of other CSOs and actors) are needed to extend its outreach;
- As mentioned earlier, the adoption of the new Water Bill constitutes a radical change as it substantially increased the role and power of local communities (at the expense of the Ministry) in managing their water resources and water supply;
- The composition and work of the budget-tracking group seem to differ from other States. The group prefers not to engage in highly sophisticated budget analysis and tracking work, but rather to focus on these parts of the budget and budgetary process that are relevant for their members. This approach ensures the ownership and sustainability of the AP and guarantees also that the implementation of budget-related decisions will be closely followed up at the local level. The expansion of the Budget Tracking Group to include broader membership and focus via the set-up of the V&A Platform may have implications for work on budget and continued membership of COBTAK. The group has been assured by SAVI that there are no plans to dissolve COBTAK; however, there is still COBTAK sustainability as a key technical budget resource for civil society issues to address;
- The fact that media are not only included as an actor in its own right (SHoA – media – CSO triangle) but also form part of some of the APs, is an interesting approach. There remains however scope for media strengthening in various areas;
- Overall, the work of SAVI is highly appreciated but in view of the magnitude of the task and challenges, it seems to be necessary to increasingly connect with the wider society via the extensive network of CSOs existing in the State and link more explicitly with existing networks and initiatives rather than initiating actions. Such a move seems to be crucial to ensure, on the one hand, a broader level of civic education in relation to the program’s key aims, and, on the other hand, the development of linkages with short route accountability initiatives and the amplification of the voice of women and girls and socially marginalised groups;
- While the TEC and SAP meet on a regular basis, their knowledge and involvement and, hence, their added value, in the program remain limited. Efforts should be undertaken to beef up their role so that they can become at least a platform for strategic reflection on the strategies and policies followed, and – if possible – a local forum where the programme staff can account for its performance. More in general, the lack of institutional embedding and of a true local counterpart poses important challenges for SAVI, in particular in view of its aims to promote transparency and accountability;
- Whereas important issues related to resource allocation and payment still need to be cleared out at a higher level, there exist different views between SAVI-Kano and PRRINN-MNCH on the modalities of SAVI’s involvement in the latter’s program in Katsina State. While SAVI prefers to engage in the State using its usual approach (starting with a comprehensive political economy analysis and actor mapping), PRRINN-MNCH prefers a rather quick approach that will allow SAVI to become truly operational as soon as possible. As the project will end by 2013, it hopes that SAVI will start soon to work on the common results that have been recently defined. The MTR team finds that SAVI could indeed engage relatively quickly in the State, thereby using intelligently the knowledge and experience of PRRINN-MNCH; it could further develop and complete its political economy analysis via its regular work. On the other hand, the team wants to point to the fact that the ‘common results’ all deal with major structural issues that cannot be completely addressed within the lifetime of the PRRINN-MNCH project;
- Ethnic and religious diversity is a key characteristic of Kano State. While many efforts are undertaken to promote harmony among the different communities, maintaining peace and understanding requires a concerted effort of all actors concerned; the security issue is considered as key by the State government that has to devote important resources in this area. SAVI takes this challenge into account via (among others) a varied composition of the APs, its sensitivity towards the different norms and values, civic education (e.g. to address electoral violence). It seems however important to develop and mainstream more explicit ‘work in conflict’ strategies and approaches that allow to make a direct contribution to improved relations among the diverse ethnic and religious groups;
- GSI are claimed to be addressed in a consistent way in all key processes and the list of gender-related initiatives undertaken by SAVI-Kano is impressive. The SAVI gender TA organised a training first for SAVI staff and then CSOs, which has produced immediate effects on how the CSOs (including the AP members) deal with gender in their own organisation and programmes. AP partners have further been supplied specific support (e.g. to celebrate International Women’s Day, a TOT for representatives of all AP members). The team also conducted a review of GSI documents related to Kano state to update their knowledge and assess toe government’s efforts. A governance baseline has also been implemented that also looked at the representation of marginalised groups. The public finance training for SHOA members included a topic on gender responsive budgeting;
- It is not clear that the SAVI team and CSO partners and SHoA have reflected on GSI as it relates to effective voice and accountability frameworks such as the MTSS and budgeting, and policy development.

6. Cross-SLP coordination issues

The monthly SLP meetings have not been organised consistently and one observer also questioned their relevance and effectiveness (lack of agenda setting mechanism, poor meeting chairing, few in-depth discussions among participants, …). This being said, SLPs have been able to cooperate on several occasions and create synergies.

The update of the Political Economy Analysis and corresponding SLP engagement strategy has brought the SLP partners together on several occasions to discuss future planning and strategies. The major contribution of SAVI in this process has been appreciated by the other SLPs and proved valuable to provide direction to their work.

More specifically, the following can be stated with regard to cross-SLP coordination and cooperation:
- The cooperation between SAVI and SPARC has been minimal for a considerable period as SPARC staff were of the opinion that it was not adequate to involve SAVI (c.q. CS) in MTSS processes. Things are however changing and cooperation is now evolving and the understanding of the potential for cooperation increasing, e.g. on the linkage of the work of SPARC on the executive side (system strengthening, technical advice related to planning and budgeting) that eventually has to be endorsed by Government (via pressure of SAVI’s partners and its work at the SHoA). SPARC has in the meanwhile been instrumental in linking up CS representatives with key planning and budgeting processes. Strengthening mechanisms to eventually come to a realistic budget seems to be a major challenge in this regard. This also implies work for SAVI with regard to fundamental issues such as a proper comprehension by the House of its key tasks and duties;
- SAVI has also been instrumental in ensuring that the development plan produced by the previous government (the Kano State Road Map) in close cooperation with SPARC could serve as a usual input for the alternative plan produced by the newly elected governor;
- Cooperation between SAVI and PATHS2 has been shaped in various ways. SAVI has been highly instrumental in identifying and selecting for CSOs that PATHS contracted to conduct training of local health committees and support these committees in assuring the quality of services provided by the health centres. Both programmes are also cooperating in promoting the passage of two Bills (on free MNCH and on the creation of a State Primary Health Agency). In this regard, PATHS2 recognises SAVI’s skills in liaising with the political class and establishing good relations with key actors such as the Ministry of Local Government. CSO involvement in the MTSS process has so far remained rather poor, mainly because of the lack of capacities at CSO level. Finally, SAVI has been instrumental in organising meetings with the transitional committee, with the new Commissioner of health and with SHoA members as part of their induction process;
- As was the case with ESSPIN, SAVI played a role in selecting CSOs that engaged in a partnership with ESSPIN after being trained by SAVI. As no SAVI supported AP is working on education issues, there have been less opportunities for cooperation than in the health sector; in addition ESSPIN considered so far that its staff could deal by itself with the challenges faced. Both programmes have nevertheless worked together to some extent around the MTSS process (including budgeting) and SAVI is requested to follow up in the SHoA the work done by ESSPIN at Ministry level.

7. Office management

The SAVI-Kano team is small, composed of committed and capable staff and hard working. The changes in personnel dealing with the SHoA have slightly affected their work at this level. The team’s approach to remain low profile and pursue its objectives essentially via its APs and other institutions adds to the efficiency of the programme; in addition much informal but highly valuable work is conducted but not well documented and included in the logframe. Expansion of activities seems to be difficult without additional staff.

As with other states, the office appears under resources to provide the assistance needed around cross-cutting issues such as media and GSI. They are doing a good job of leveraging technical support from SPARC, PATHS II and ESPPIN on core suite reform areas, but will need to expand technical resources if they are to scale up technical work on GSI, media, and improving the organizational and advocacy capacity of APs and SHoA around budget, oversight, and advocacy.

#### SAVI Mid-Term Review - Lagos State Report

1. Context
- SAVI Lagos operates in a very different context to the other SAVI state teams. Demand for better governance is more strongly developed in Lagos than elsewhere. This is evident in the existing strengths of civil society, the level of functioning of the State House of Assembly, and the concentration of media organisations in Lagos. The Lagos State Government is showing increasing capability in its ability to deliver services and rehabilitate infrastructure. This has strengthened citizen’s expectations of government and led to a dynamic situation where increased demand for improved government performance is being matched by a level of response from Lagos State Government.
- The political apparatus in Lagos State has long been under the control of the ACN, which has created political tensions between Lagos State and the PDP controlled Federal Government. At times the state has been subject to a federal funding squeeze (for example, funds for local government in Lagos State were withheld during the Obasanjo era), which has compelled the state to develop internal revenue sources. The strong growth in Internally Generated Revenues contributed by Lagos’ vibrant private sector has created an important source pressure on the state government to deliver the services and public goods required for business growth.
- The present Governor of Lagos State, Fashola, has a reputation for being a reform-minded, technocrat who gets things done. There are some tensions within the ruling ACN party between the competing power and patronage structures of Fashola and the previous governor Tinubu, who remains a powerful force behind the scenes. The relationship between Lagos State Government and the Federal Government remains difficult with the EFCC having recently accused the speaker of the Lagos State House of Assembly of financial fraud. In contrast to the improvements in governance experienced at state level, local governments in Lagos state continue to be characterised by corruption, a lack of transparency and a lack of capability.

2. Description of the SAVI Lagos programme
The SAVI programme in Lagos can be summarised as follows:
- Output 1: People with Disabilities Advocacy Partnership focusing on the passage and implementation of the Special People’s Bill; Climate Change Advocacy Partnership working on a state policy framework for climate change adaptation and mitigation;
- Output 2: SAVI has supported the formation of the Lagos State Civil Society Partnership (LACSOP), a large civil society umbrella organisation which engages in MTSS and budget processes, as well as tracking the effectiveness of public policy and service delivery. The Partnership on Good Governance (PaGG) was formed in 2009 to undertake similar work in three pilot LGAs (two of which are part of the Conditional Grant Scheme and one LGA has been selected as a control group.)
- Output 3: This has included actions to improve communication between the State House of Assembly, civil society and the media. Direct work with the media has been limited;
- Output 4: The focus within State House of Assembly has been on strengthening budget oversight, improving planning and management systems for the administration of the house, IT support, induction training for new members, and constituency relations;
- Output 5: This has included communication of SAVI’s approach to other SLPs and development partners, as well as lesson learning within and between advocacy partnerships.

3. Assessment of progress against outputs

#### Output 1:
The major achievement has been the passage of the Special People’s Law that was drafted within the disability advocacy partnership and presented to the State House of Assembly as a private member’s bill (the first ever such bill in Lagos state). The law provides for comprehensive disability rights and was drafted on the basis of international best practice. The disability advocacy partnership is now focussed on maintaining pressure for the implementation of the law and the establishment of the Office for Disability Affairs. The review team judges the Advocacy Partnership to be well organised, highly capacitated, motivated, and likely to be able to continue its activities beyond the duration of the SAVI programme.

The Climate Change Advocacy Partnership has prepared policy documents on the challenge of climate change adaptation and mitigation in Lagos State. It has participated in annual Lagos State Climate Change Summits and has generated media coverage. The group is focussed on getting policy and legislation adopted by Lagos State Government to address climate change comprehensively. In the opinion of the review team the Advocacy Partnership lacks focus and technical capacity. Their policy documents are very broad ranging covering areas of questionable immediate relevance (e.g. reducing carbon emissions in Lagos state), and are not sufficiently focussed on the most pressing challenges (e.g. flood prevention and management). The group appears to be highly dependent on SAVI support, and has absorbed much greater SAVI financial support than the other Advocacy Partnerships.

#### Output 2:
LACSOP engages regularly with MDAs and the State House of Assembly on budget issues. It has completed a survey of the effectiveness of LGAs, a review of state education policy, and has participated in a priority needs assessment for the health sector. It appears to be well organised, includes member organisations with technical skills and strong community connections.
The Partnership on Good Governance (PaGG) is the most recent and weakest of the Advocacy Partnerships. SAVI recently halted all activities for three months while the group addressed internal management issues. The group appears to have limited experience of advocacy at LGA level, and its workplan has not yet developed beyond generalities. Paths2 and ESSPIN have been expecting to partner with PaGG for advocacy work on health and education at LGA level. However, working relationships have not yet developed beyond initial contacts.

#### Output 3:
The main result under this output has been the establishment of a civil society liaison office within the State House of Assembly. LACSOP has also established close working relations with the State House of Assembly.

#### Output 4:
With SAVI and SPARC support the State House of Assembly is establishing a Legislative Budget Research Office. SAVI attributes several other results to its behind the scenes support and advice. These include the passage of the State House of Assembly Service Commission bill (providing the House with financial autonomy), the regular holding of public hearings (including for the first time a public hearing of the budget to take place this year), and the initiation of a system of pre-budget reviews. Training events for House members and staff have usually been provided jointly by SAVI and SPARC.

#### Output 5:
SAVI is working closely with other SLPs in explaining its approach, and in joint programming. LACSOP has also become involved in UNICEF programmes.
4. Progress against outcomes

The strong results of the Disabilities Advocacy Partnership and LACSOP amount to a significant outcome in terms of SAVI’s contribution to the effectiveness of civil society in the state. However, the other two advocacy partnerships have had much more modest results. . The State House of Assembly has also become more effective by virtue of improved systems, new organisational structures and the passage of supporting legislation. SAVI has not had much impact on strengthening the media beyond those media organisations included within the 4 Advocacy Partnerships. However, SAVI has brokered improved relations between civil society, the media and the State House of Assembly through its work with LACSOP and the creation of the State House of Assembly, Civil Society Liaison Office.

The Special People’s Bill stands out as SAVI’s main result in terms of demonstrable changes in policy and implementation. The passage of the bill has been achieved in short period of time and at very modest cost to SAVI. The amount invested in the Advocacy Partnership by SAVI over the past 12 months is about N8mn £32,000 (excluding staff time). Compared to the number of potential beneficiaries in Lagos State, this represents excellent value for money.

5. Cross-SLP coordination issues

- Coordination between SAVI and other SLPs is generally working well in Lagos. The relationship between SAVI and SPARC is particularly close with many activities (MTSS training for CSOs and SHoA etc.) jointly planned and executed. However, SPARC has expressed the view that SAVI is underresourced to the extent that SPARC must often fund and implement activities that ought to be under SAVI’s remit (e.g. training in the State House of Assembly);
- ESSPIN has a close relationship with the LACSOP partnership that has paid dividends in the recent education sector review. Paths2 and ESSPIN are expecting SAVI to become more engaged in advocacy at LGA level through the Partnership on Good Governance (PaGG). However, their plan to link the PaGG to their work with School Based Management Committees and Ward Health Committees may be hampered by the apparent lack of capacity and readiness of PaGG;
- Paths2’s contract with Action Aid for the delivery of training on MTSS has caused friction with SAVI and SPARC. Action Aid’s approach has been heavily consultant-led and has conflicted with the SPARC/SAVI approach of building capacity within the Ministry of Economic Budget and Planning to deliver training. This was also evident in the Priority Health Needs Assessment, where SAVI and LACSOP feel that the Action Aid’s consultant took too much of a leading role without sufficiently engaging LACSOP. However, a satisfactory working relationship was eventually achieved;
- GEMS3 is about to begin work in Lagos state. Based on their proposed activities there would appear to be potential to work together in two main areas of advocacy: (a) land administration and tenancy law, (b) LGA taxation.

6. Office management

1. SAVI Lagos staff are a highly competent and motivated team. However, with just three core staff in programming roles, the office is clearly overstretched. The range of subject areas and activities being worked on appears to be wider in Lagos than in other states. There are some key technical capacities that are lacking in the office, in particular in relation to: a) knowledge of the climate change agenda from a scientific and policy perspective; b) LGA engagement; c) media engagement;
2. Interviews with SAVI Lagos staff point to the time demands imposed by SAVI’s reporting requirements. Between two and three days per month are spent on financial reporting, and around two weeks per quarter on the quarterly progress report.

7. Key issues

SAVI Lagos has developed a very good working relationship with the State House of Assembly, which has already contributed to some important results (see above). So far success has depended on goodwill and behind the scenes advice. The actual activities implemented with the House have been somewhat opportunistic and ad hoc. The challenge now is use the goodwill that has been developed to build a more formal partnership based in a jointly agreed strategy and workplan.

SAVI Lagos is experimenting with some promising models for linking the short and long routes of accountability. For example, LACSOP has been designed in a way that links its member organisations working at the community level to reaches umbrella activities at the state level. The formation of the Partnership for Good Governance (PaGG) is an attempt by SAVI to support more substantial engagement at the LGA level, and to link with the work of Paths2 and ESSPIN in setting up accountability structures at the point of service delivery (the School Based Management Committees and Ward Health Committees). It is evident to the review team that a major effort will be required by SAVI to create sufficient capacity within PaGG to work effectively at LGA level. If successful this could be a promising model for replication in other states.

In contrast to other states, none of the output 1 Advocacy Partnerships is working on issues of health and education. This is partly a reflection of the timing of the establishment of the SLPs in Lagos State where SAVI arrived before Paths2 and ESSPIN. The situation is regrettable as it limits the scope for developing links between SLPs as has occurred in other states. However, SAVI has started to engage in the health and education sectors by supporting LACSOP’s oversight activities in the two sectors, and in establishing the Partnership on Good Governance at LGA level. For the remaining three years of the SAVI programme it is recommended to maintain the focus on existing advocacy partnership, but to step up engagement in the health and education sectors through LACSOP and PaGG and in partnership with Paths2 and ESSPIN.

The review mission has raised questions about the lack of focus of the climate change partnership. It will be worth exploring whether the relevance of the partnership and its political traction could be increased by focussing on the immediate challenge of flood prevention and management (which affects Lagosians every year). This would require a balance between the need for action in the short term and investment and forward planning for the long term taking account of the increased water management challenges that are posed by climate change.

For the second half of the SAVI programme the major challenge will be to ensure that sufficient organisational and technical capacity has been created to continue effective advocacy work after the completion of the project. This will require further investment in training and mentoring on organisational and partnership development. The priority is for the partnerships to find ways to draw most effectively on the resources and capacities of the member organisations rather than formalising new apex structures (several of the Advocacy Partnerships are in the process of registering with the Corporate Affairs Commission, but in the view of the review team this is not a requirement for sustainability and may be a diversion from more important organisational development challenges). Sustainability will also depend on the advocacy partnerships and their members being able to find other sources of funds, whether from grants or member contributions. SAVI has done little to build capacity in this vital area of fundraising. As the partnerships mature it may be appropriate to entrust groups with the management of small funds for specific activities as a means to develop financial management and accounting capacities.

The State Advisory Committee is not functioning in Lagos and needs to be reconstituted with newly appointed and enthusiastic members. There appears to be a major difficulty retaining the members of the SAP without offering payment for the professional advice they provide.

# Annex B –Value for Money Assessment
The terms of reference for the Mid Term Review (MTR) of SAVI require the review team to consider the extent to which SAVI is achieving value for money (VFM) in the delivery of its outputs and principle sub-outputs. They also ask for an assessment of the extent to which the project’s allocation of resources by state, by output, and input type appear to be appropriate.

An assessment of VFM involves making a series of judgements on whether a programme or project is delivering agreed outputs at an optimal level given the resources available and whether these outputs are achieving the desired objectives. It involves an assessment of whether a programme could ‘deliver more for less’ or whether it could ‘achieve given objectives for less’. A VFM review is separate from but complementary to reporting on results and demonstrating good financial management.

DFID’s approach to VFM is based on a balanced assessment across the ‘3 Es’ – economy, efficiency and effectiveness. The approach involves several elements: VFM indicators, modifiers for context and assumptions, attribution, and confidence levels in the data. VFM indicators are ratios, often expressed in monetary terms, which reflect the relationship between different elements in the results chain.[1] They are generally less easy to quantify in the case of governance programmes. The approach is made suitable for interventions that are not easily monetised by allowing VFM indicators to be accompanied by normative judgements about performance and results.
[1] VFM ratios generally focus on the cost to output relationship (e.g. cost per beneficiary, entity or workstream, £ generated or saved per £ spent, etc.) but can also address input relationships (e.g. cost ratios between different types of input or the ratio of technical assistance inputs to overheads) and outcome relationships (e.g. cost per life saved in the case of an immunisation programme).

The focus of the VFM review of SAVI is on efficiency and effectiveness. ‘Economy’ is largely covered by existing processes including: selection of the contractor by competitive procurement, the requirement to use DFID’s procurement agent for large scale purchases, and independent programme audits whose terms of reference include assessing the economy of small scale purchases and efficiency in use of resources. Aspects of efficiency which are of interest to the MTR include:

- Allocative efficiency (is expenditure between states likely to maximise delivery of outputs?)
- Technical efficiency (are the chosen outputs supporting achievement of outcomes?)
- Managerial efficiency (have inputs been combined effectively to deliver outputs?)

Judgements against these criteria, when combined with assessments of context, assumptions and attribution, will help the MTR reach an assessment about the extent to which SAVI has delivered VFM to date. They will also help identify VFM issues and considerations for the programme going forward.

#### SAVI Expenditures
The total budget for SAVI is currently £21.5m. Expenditure to date is shown in the table B1 below.

Table B1	SAVI Total Expenditure
Inception (Aug 08 to Aug 09)	£2,099,835
Implementation (Sept 09 to Sept 11)	£5,578,736
Diff.[2]	(£10,566)
Total	£7,668,005
[2] At the time of the MTR there was a difference of £10,566 between SAVI’s record of total costs to date by phase (i.e. £7.679m for inception & implementation) and its record of total costs to date in other presentations (i.e. £7.668m for total fees & costs). Total expenditure is assumed as £7,668,005 - this figure appears in all other expenditure presentations provided by the programme. The difference is not material to the VFM analysis.

There have been three contract amendments for SAVI. The first amendment, in June 2009, was cost neutral but created additional lower fee bands for more flexibility around use of national consultants. This amendment removed the procurement line item from the contract to enable procurement to be directly managed by Crown Agents. As a result, the contract limit for the contractor was revised from £20.2m to £19.7m.

The second contract amendment, in June 2010, revised the contract limit from £19.7m to £20.7m. The amendments mostly came about as the result of recommendations from the SAVI inception phase review and discussions between SAVI and DFID. In particular, this amendment recommended increased support to State Houses of Assembly so that they should represent 45-50% of programme expenditure, compared with 10-15% during the inception phase, which necessitated some reconfiguration of staffing.

The third contract amendment revised the contract limit from £20.7m to £21.5m to provide for expansion into three more northern states in line with DFID requests. SAVI is initially engaging in two of these states, Yobe and Zamfara, with a technical unit attached to the DFID-funded Partnership for Reviving Routine Immunization in Northern Nigeria – Maternal, New Born and Child Health Initiative (PRRINN-MNCH). This approach has, according to SAVI, enabled much of the additional costs of expansion into the eighth state, Katsina, to be met by savings made in the altered proposals for Yobe and Zamfara. If this initial approach to engagement in northern states proves successful, SAVI has budgeted for a more comprehensive engagement taking place in these states. We understand that at the request of DFID, SAVI is also exploring ways of working in a ninth state, Ekiti.

In summary, SAVI is now programmed to operate in nine states. The programme maintains offices in five states (Lagos, Enugu, Kaduna, Kano and Jigawa) and smaller units in three additional states (Yobe, Zamfara, Katsina). It also operates in Ekiti and maintains a programme office in Abuja. The current level of operations has been managed with an overall increase in the original contract value of 6.3 per cent (to date).[3]
[3] Allowing for rounding, £20,233,323 x 1.06 = £21,504,008.

#### Budget vs. Actual
A comparison of budget versus actual expenditure is important because of the opportunity cost of funds. SAVI expenditure during inception (Aug 08 to Aug 09) was 5 per cent below the amount that was budgeted. Expenditure during the first two years of implementation (Sept 09 to Sept 11) was 19% below the amount that was budgeted. The slower than expected rate of expenditure during implementation is understood to be due to under-estimates of the time required to identify and establish effective working relationships with State Houses of Assembly and with state level accountability partnerships. Budget versus actual expenditure by location is shown in Table B2 below.

Table B2	SAVI Budget vs. Actual Expenditure by location
	Enugu	Kano	Kaduna	Lagos	Jigawa	Abuja	Total
	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000
Inception
Budget	331	375	463	353	176	507	2,205
Actual	349	384	394	395	246	332	2,100
Diff.	6%	2%	-15%	12%	39%	-35%	-5%
Implementation
Budget	1,039	1,246	1,108	1,177	969	1,385	6,923
Actual	876	963	787	925	687	1,341	5,579[4]
Diff. (%)	-16%	-23%	-29%	-21%	-29%	-3%	-19%
[4] See footnote 2

SAVI expenditure to date falls into two main categories; fees and reimbursable costs. Fees are split into long and short term technical assistance, of which the majority is for full time long term advisory staff (LTA). Reimbursable costs are mainly for the operation of programme offices, programme and state activities (i.e. locally incurred costs directly related to delivery of outputs) and related costs. Reimbursable costs include programme management and quality assurance inputs by the main contractor. This would be more accurately described as a component of fees. Budget versus actual expenditure by input is shown in Table B3 below.

Table B3	Budget vs. Actual Expenditure by Input
	Inception			Implementation
	Budget / £’000	Actual / £’000	Diff. / %	Budget / £’000	Actual / £’000	Diff. / %
Fees	1,168	1,032	-9%	3,226	2,859	-11%
LTA	878	820		2,502	2,289
ST Core	138	128		342	280
ST Pool	152	84		382	290
Reimbursable Costs	1,037	1,068	+3%	3,698	2,720	-26%
Programme & state	111	290		2,194	1,067
Office operating	408	493		726	788
Travel	95	87		171	127
Living Costs	255	198		331	297
Procurement	10	0		13	43
Management costs	157	0		262	398
Total	2,205	2,100	-5%	6,923	5,579	-19%

The main observations to be drawn from the comparison of budget versus actual expenditure are:
- Overall expenditure is 36% of the budget at the mid-point of the programme, compared with a planned level of expenditure by SAVI of 42% of the total budget by this stage;
- There is a high ratio of long term to short term technical assistance (TA). Long term TA represents 80% of total fees, short term TA represents 20% of total fees;
- The most significant areas of difference between budgeted and actual expenditure are in the ‘fees’ and ‘state and programme activities’ categories (respectively, 11% and 41% underspent to date). This applies across states and in some states more than others. It is consistent with a pattern of expenditure focussed on establishment of programme infrastructure and working relationships with slower than anticipated roll-out of technical assistance with identified beneficiaries during the first two years of implementation.

The remainder of this section provides an overview of expenditure by location and by output in the first two years of the implementation phase. It excludes inception phase expenditure and expenditure of £568,566 to date for vehicles, office equipment and furniture which has been managed by Crown Agents. It starts by explaining constraints to the VFM analysis.

#### Constraints to the VFM Analysis
The expenditure presentations provided by SAVI are broken down by inception and implementation phases but not by year. This is not a major issue for the VFM analysis at the moment. Our assumption is that, given the cumulative nature of SAVI engagement with stakeholders, expenditure-to-date compared to results is likely to be the more relevant VFM ratio to assess. However, as SAVI develops a clearer understanding of the VFM ratios which apply to its main activities (i.e. how much to spend on particular outputs and sub-outputs per milestone) an understanding of expenditure per year will be required to support an assessment of VFM.

SAVI is currently unable to report expenditure below the level of output without significant additional effort. This is a significant constraint to meaningful VFM analysis which needs to be addressed by the programme. At present it is not possible to identify VFM ratios at a meaningful level (i.e. sub-output) for SAVI. They can be estimated but only with a large margin of error. This was confirmed through a review of SAVI’s state-level accounting and reporting formats and discussions with the programme management team in Abuja. The majority of SAVI expenditure is allocated to (a) supporting state level accountability partnerships (APs) and (b) supporting state houses of assembly (SHoA).[5] However, SAVI cannot report how much was spent on individual APs (i.e. sub-outputs for outputs 1 and 2) although only three or four APs are supported in each state and it cannot report how much was spent on each SHoA workstream (sub-outputs under output 4) although only there are only four main workstreams supported with each SHoA[6].
[5] Outputs 1,2 and 4 respectively.
[6] SAVI currently supports 17 APs in 5 states. SAVI’s work with SHoAs involves supporting the following four main areas – systems of public access, recruitment and retention of support staff, induction and monitoring of compliance with house rules, and scrutiny of public documents.

As a result, comparison of the cost-benefit ratios of SAVI interventions between different sub-outputs within the same state, similar sub-outputs in different states, over time, and with other comparable programmes cannot be made. The SAVI programme management team recognise the issue and understand its significance. It could be addressed relatively easily if staff time and overhead costs were accurately recorded at the sub-output level in each state.[7]
[7] Time recorded to the nearest half day would be sufficient. This would only affect technical staff providing state-specific inputs. For general administrative staff and central-level support, training and dissemination activities, a pro rata allocation would suffice.
A further issue constraining VFM analysis is lack of data on the extent to which the SAVI programme is able to leverage local resources. The SAVI approach involves leveraging additional resources from its advocacy partners which is potentially good VFM practice. However, the programme does not systematically record leveraged resources. Potentially, the effect of leverage could be significant. During fieldwork several examples of cost sharing were readily provided, including the following in Kaduna:

- An advocacy workshop with the National Union of Journalists who contributed the equivalent of N1.1m worth of free media coverage for the workshop compared to SAVI’s costs of N22,000;
- An International Women’s Day Seminar for the Empowering Women in Excellence Initiative where EWIE contribution of N72,300 was identified against a total budget of N283,030.

#### Expenditure by Output and Location
The table below shows total SAVI expenditure to date by output and by location according to the programmes accounts. The allocation of cross-cutting technical inputs and the cost of Abuja and state offices has been estimated retrospectively by the programme.

Table B4	Total Expenditure by Output and Location
	Enugu	Kano	Kaduna	Lagos	Jigawa	Abuja	Total	% share
	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000	£ ‘000
Output 1[8]	104	85	89	121	83	35	518	7%
Output 2	101	81	83	115	79	35	494	6%
Output 3	93	112	96	102	59	69	532	7%
Output 4	280	334	236	294	209	101	1,454	19%
Output 5	73	110	107	151	65	70	575	7%
X-Cutting technical	205	208	235	185	150	163	1,146	15%
Abuja/State Offices	361	399	333	338	274	1,246	2,950	38%
Total	1,216	1,329	1,178	1,306	919	1,718	7,668	100%
% share	16%	17%	15%	17%	12%	22%	100%
[8] Output 1 – civil society issue-based policy advocacy and monitoring; Output 2 – civil society engagement in government planning and budgeting; Output 3 – an enabling environment for civil society advocacy and monitoring; Output 4 – Improved SHoA systems; Output 5 – Communication of lessons learnt.

The main observations are as follows:

53% of total programme expenditure by location is accounted for by Abuja-based fees and costs and cross-cutting technical inputs. The Abuja office manages the overall programmes and acts as a technical and administrative service centre for the state-based programmes, so a significant portion of this expenditure relates directly to output delivery at state level.

Of the 47% of total expenditure which is incurred directly at state level, 40% is allocated to output 4. Outputs 1, 2 and 4 together account for 69% or programme expenditure. As mentioned in the previous section, accurate allocation of this expenditure to sub-outputs – that is, individual APs and SHoA workstreams - is not currently possible.

After the cost of Abuja-based operations, most states have been allocated between 15% and 17% to total programme expenditure. The exception is Jigawa, which has received 12% of total expenditure to date. It is understood that this is due to SAVI activities beginning later in Jigawa than in the other states.

There is considerable variation between states in the level of expenditure per output. For example, the difference in expenditure on output 1 between Jigawa and Lagos is 46% (£83,000 vs. £121,000). Similarly, the difference in expenditure on output 2 between Jigawa and Lagos is 329% (£35,000 vs. £115,000) and the difference in expenditure on output 4 between Jigawa and Kano is 60% (£209,000 vs. £334,000).

#### Expenditure by Sub-Output
The VFM assessment for SAVI at MTR stage will rest largely on the VFM assessment of outputs 1,2 and 4 which together account for 69% of state level expenditure and probably a similar proportion of overall programme expenditure. This assessment should be based on a comparison of (a) results vs. expenditure per AP and (b) results vs. expenditure per SHoA sub-output. The cost-benefit ratios of different sub-outputs could then be determined and comparisons made across the programme. As explained above, it is not possible to calculate expenditure on sub-outputs with any degree of accuracy due to the current nature of programme accounting.

For illustrative purposes, tables 1 and 2 below provide estimates of expenditure per sub-output by state, based on a simple pro-rata allocations. The tables are as follows:

- Table 1 – allocates state level expenditures to sub-outputs on a pro-rata basis, excluding central overheads	;
- Table 2 – as per Table 1, but allocating central overheads to sub-outputs as well on a pro-rata basis as well, to derive a measure of total expenditure per sub-output.

Table 1 shows that, excluding central overheads, total expenditure to date on APs ranges from about £42,000 (average expenditure per AP in Jigawa on outputs 1 and 2) to about £81,000 (Lagos). It also shows that, excluding central overheads, total expenditure to date on SHoA sub-outputs ranges from £52,225 (Jigawa) to £83,456 (Kano). These costs need to be compared to results and with other similar VFM ratios in the programme to reach judgements about VFM. Table 2 shows that, taking all expenditure into account, total expenditure to date on APs ranges from £80,000 (Jigawa) to £188,000 (Lagos) and total expenditure to date on SHoA sub-outputs ranges from £90,626 (Jigawa) to £130,965 (Kano).

Tables 1 and 2 are based on simple averages and provide crude estimates subject to a wide margin of error. However, they give a sense of the magnitude of programme expenditure at sub-output level against which to compare results, and thus derive meaningful measures of VFM.

#### Cost of Inputs
The main cost driver for SAVI is the weighted average cost of long term technical assistance. This comprises the following positions:

- 20 Abuja and state-based advisory positions and 21 state management, administration and support positions (long term technical assistance);
- 7 named short term advisory positions (short term core) and a pool of short term consultants (short term pool) ;and
- 6 named head office management positions.

Weighted average costs for long and short term technical assistance are shown below:

Technical Assistance	Weighted Average Fee Rate per day
Category	Sept 09 – Sept 11
LTA Advisory	£220
LTA Management and Support	£78
LTA Total	£138
STA Core	£551
STA Pool	£357

The weighted average cost of LTA, which represents 80% of total fees expenditure to date, is £138 per day. This is because SAVI employs relatively few international LTA. It indicates that marginal costs of expansion for SAVI will be relatively low. Short term fee rates are higher but represents a lower proportion of total fees expenditure to date.

# Annex C – List of people met
To be completed

# Annex D – Terms of Reference
#### 1. BACKGROUND
The State Accountability and Voice Initiative (SAVI) is one of five interlocking sector and governance State Level Programmes (SLPs) financed by the United Kingdom’s (UK) Department for International Development (DFID).[9]
[9] The other four being: the Education Sector Support Programme in Nigeria (ESSPIN); the State Partnerships for Accountability Responsiveness and Capability (SPARC); the Partnership for Transforming Health Systems (PATHS 2); and Growth and Employment in States (GEMS),

SAVI currently focuses on 5 states, (Enugu, Jigawa, Kaduna, Kano and Lagos) and is planning to expand into 3 additional states.

The overall objective of SAVI is ‘Civil society[10], state houses of assembly & government demonstrate improved voice and accountability processes’.
[10] Meaning: organisations that represent citizens: CSOs, NGOs, CBOs, the media, trade unions, professional, business, advocacy, and voluntary associations, academic/research bodies, women’s organisations, traditional authorities, faith-based groups, coalitions, foundations, development agencies, etc.

The main areas of support provided by SAVI are:
- Support to civil society to improve their capacity and performance in conducting advocacy work around specific policy issues and in influencing and monitoring state government planning and public financial management;
- Strengthening the capacity and performance of the State Houses of Assembly in executing their oversight role in relation to the state executives;
- Supporting the demonstration and replication of the approaches supported by the programme.

#### 2. OBJECTIVE
The objective of the Mid-Term Review (MTR) is to enable programme performance to be maximized over the remaining programme life through a clear and independent in depth review of SAVI’s strategy and performance. It will summarize progress in each of states and at the federal level and highlight good practices and lessons to be learned. Finally, it will set out recommendations to improve SAVI’s effectiveness and impact over the remaining project implementation period (2011-2014). In that context DFID’s expansion into three Northern states and its implications for SAVI, as well as SAVI’s future work with PRRINN MNCH will be addressed in the recommendations.

As SAVI is part of a series of State Level Programmes also known as SLP Suite, the SAVI MTR will also feed directly into the SLP suite MTR that will start immediately after the SPARC MTR.

#### 3. RECIPIENTS
The primary recipients of the findings of the MTR will be DFID-Nigeria, the SAVI team. SAVI’s principal implementing partners in the five focus States (both governmental and non-governmental (Enugu, Kaduna, Kano, Jigawa and Lagos), PRRINN MNCH for lessons and information, other relevant SLPs in the suite as well as other development partners and federal government partners such as NPC.

#### 4. EVALUATION FOCUS AND KEY EVALUATION QUESTIONS
The MTR will assess the project in terms of its continued relevance, its efficiency, effectiveness, likely impact and sustainability. Integrated within this analysis will be an assessment of the extent to which SAVI is providing value for money (VfM). The review will also support the programme to prepare for as assessment of its impact to be conducted at its conclusion in 2014.

The key evaluation questions to be answered are presented below.

#### Relevance
- Is the SAVI intervention logic (as presented in the results chain of its Logframe and any supporting frameworks) coherent and adequate? Are the assumptions upon which this intervention logic rests appropriate and sufficient?
- To what extent are SAVI’s objectives and strategy appropriate in terms of the political economy of improving public sector governance in the focus states? To what extent are they responsive to the different contexts and capacities of the state governments in the different states?
- To what extent are gender and social inclusion aspects sufficiently addressed in SAVI’s work[11]?
  [11] This should include an assessment of the level of awareness of SPARC of DFID-N’s new strategies in this area, and an assessment of the extent to which the programme is addressing them.

#### Effectiveness and Impact
- To what extent has SAVI achieved, or is on course to achieve, its planned outputs (and principal sub-outputs) in both quantitative and qualitative terms?
- On the basis of the assessment of SAVI’s performance in achieving its planned outputs (as well as the relevance and adequacy of these) assess the extent to which SAVI appears to be on course to achieve its purpose within the project life?
- What evidence exists to-date to suggest that SAVI is making a significant contribution towards the achievement of its goal?
- To what extent has SAVI been adapting its’ approach to maximise its’ overall impact? How responsive has the project been in adapting it’s strategies to changes in its understanding of the political economy of public service reform (particularly following the 2011 elections) and to changes in external risk levels? Are there new or additional risks that the programme needs to consider?
- What additional unplanned outcomes can be identified, which have affected (either positively or negatively) either the intended beneficiaries or other groups? How should any negative outcomes be addressed by the programme?
- On the basis of the review’s assessment of the outcomes achieved to date, and the outcomes which are likely to be achieved in the remaining life of the programme, assess the extent to which the project is likely to represent value for money for this type of project.
- What is the likely effect on SAVI’s overall effectiveness and impact of the recent decision for it to expand into new states in the North for the second half of the project?

#### Sustainability
- How sustainable are the outputs, outcome and potential impact likely to be and how should SAVI’s strategy be improved to maximize this?
- To what extent is SAVI implementing appropriate strategies to help ensure sustainability?

#### Efficiency
- What progress has been made to-date in implementing the programme’s agreed strategic plan (activity log)? What are the reasons for the level of progress achieved?
- To what extent is SAVI achieving value for money in the delivery of its outputs and sub-outputs?
- To what extent does the project’s allocation of resources by state, output (and principal sub-output) and input type appear to be appropriate?

#### Programme Oversight and Management
- To what extent is SAVI effectively coordinating its work with that of the other SLPs (SPARC; ESSPIN; PATHS2; GEMS) in order to maximize both its own effectiveness and impact and that of the whole SLP suite? How adequately does SAVI coordinate with other key stakeholders in its intervention areas?
- To what extent does SAVI’s M&E system respond to the needs of the project’s management and oversight bodies and other stakeholders in terms of performance monitoring and continuous learning?
- How adequate and effective is the guidance, support and oversight provided by DFID-N to SAVI at both national and focus state levels?

#### Lessons and recommendations
- What are the overall lessons to be learned from the above analysis in relation to SAVI’s overall and output-level strategies?
- How, if at all, should the overall strategy of SAVI be modified in terms of the type and scale of its outputs, as well as the level of resourcing of the different outputs, in order to maximize its effectiveness?
- What progress has been made responding to the recommendations of the 2011 annual review?
- What are the implications of this mid-term review for the project’s strategy in expanding into its three new states in Northern Nigeria?
- What should SAVI do to increase its overall VFM?

#### 5. METHODOLOGICAL APPROACH
#### Preparation
The review team will conduct the MTR by assessing and further analysing:
- Information provided by SAVI including review of documents and data;
- The annual review of SAVI 2011;
- Information from field visits and interviews undertaken by the review team.

IMEP will outline the details on the information and documents to be provided by SAVI, in discussion with the programme and DFID, at least four weeks before the review mission.(see Annex 1) VFM information is an important part of the inputs to be provided. The SAVI team will also complete a draft ARIES form reflecting SAVI’s perspective prior to the MTR with information provided separately for each state and in summary for the programme as a whole.

On the basis of the information provided by the SAVI team (see Annexe 1) and IMEP core team will develop the approach in more detail. A methodological challenge for a review is to deal with the natural tension between depth and breadth. An option is to select some specific issues for a more detailed analysis for some of the state visits. This might mean that some states will be covered in more depth than others.

The VFM analysis is rather complicated, especially at the start. Therefore, IMEP has developed a gradual approach. A complete VFM analysis requires a mapping of all outputs and sub-outputs and ensuring that all expenditures (including TA inputs) are assigned to a sub-output. Furthermore, a comparison with similar sub-outputs realised elsewhere is needed. On the basis of the VFM information provided by SAVI, the review team will select a number of outputs and sub-outputs for a complete VFM analysis.
Prior to the commencement of the review field work the MTR team will develop one or more simple interview guidelines which will help ensure both that the key information is collected in the state visits and that the different MTR sub-teams follow a harmonized approach.

#### Implementation
The mission will start with a briefing by DFID-Nigeria and an initial meeting between the SAVI team and the MTR team. Additional meetings at the federal level with relevant organisations will be planned, whilst the main focus of the review will be a series of state visits. The intention is to cover all five of the current focus states.

The institutions and individuals to be interviewed will be agreed with the programme and DFID at least three weeks before the mission. The ‘standard’ focus state visit will consist of around two days and will involve interviews with the SAVI state team and project implementing/’beneficiary’ agencies including the state governments as well as other similar development projects and independent informed third parties (e.g. leaders of civil society groups). One or more meetings will also be held with representatives of the other SLPs active in the state. Upon completion of a state visit a short feedback session will be conducted by the MTR sub-team in which some of its main provisional observations are presented for discussion and validation to the SAVI State Team.

Due attention will be paid to avoid ‘interview fatigue’ as a series of mission is planned for the period October-December (Drivers of Change, SPARC MTR, SLP Suite MTR, …). The IMEP Abuja office will be responsible for maintaining an overview of the individuals interviewed by the various review teams and ensuring that information is shared effectively so that interviewees are not questioned (in any depth) on the same topic more than once.

#### Feedback and reporting
A number of feedback and debriefing sessions will be planned to discuss the findings. This will include a short, provisional feedback session in each state and a more extensive feedback session the programme, DFID and other stakeholders at the national level.

The report will be structured around the evaluation criteria. For each assessment sufficient evidence will be provided. The MTR team will also indicate when insufficient evidence is available. In the analysis of each evaluation criterion due attention will be paid to explanatory factors, internal and external to the project. Due attention will be paid to the issue of contribution and attribution. The findings will lead to substantiated conclusions that will be translated into lessons learnt and concrete recommendations for improvement. The recommendations will be targeted to specific stakeholders.

#### 6. ORGANISATION AND COORDINATION
#### IMEP
The schedule for the three week review mission will be developed by the IMEP Abuja team and the SAVI national and state teams. The IMEP Team Leader will develop the initial schedule in close consultation with the MTR Team Leader. All of the logistical arrangements (flights, cars, hotels etc.) will be organized by the IMEP Abuja Finance and Administration Manager. Once the basic programme is established further modifications and updates will be effected directly the MTR Team Leader, who will be in direct contact with the SAVI national or state team leaders, whilst keeping the IMEP Abuja Team Leader informed. The review schedule will be consulted with the relevant DFID staff at least 4 weeks before the mission.

The SAVI independent review team will be made up of the following consultants provided by IMEP:
- Gareth Williams - A governance (including Voice and Accountability) international expert (Team Leader).
- Dirk van Esbroeck - governance Voice and Accountability international expert
- Maisha Strozier - A civil society development national expert.
- Daisi Feyisetan - IMEP Abuja Office M&E expert.

A finance and management systems expert (David Hoole - International – Lead Consultant) - focusing on Value for Money will provide additional support to the MTR team.

The team leader will have overall responsibility for delivery of the outputs of this review and be responsible for the division of tasks. The IMEP Project Director, Anneke Slob, will be responsible for Quality Assurance of the draft and final ARIES and narrative MTR reports.

#### DFID
DFID’s Governance Team Leader (Julius Court), SAVI Lead Adviser (Desmond Woode), and Project Officer will act as resource persons to the MTR team. The review team will also have access to the relevant DFID staff in the DFID regional offices in Kano, Enugu and Lagos and to the State Coordinators

#### 7. REPORTING
The review team will provide:
- Short feedback sessions with preliminary state-specific observations at the end of each state visit[12];
  [12] The date, time, duration and participants will de discussed beforehand and included in the mission schedule.
- Debriefing sessions for key stakeholders at the end of the MTR where preliminary findings, conclusions and recommendations are presented for validation[13];
  [13] The mission schedule will include dates and participants for specific debriefings. In principle, the debriefings will start with a validation session with the SAVI team to be followed by debriefings to DFIDN and other stakeholders.
- A draft DFID ARIES Form Mid-Term Review (using the MS Excel template) including proposed scores[14] (within two weeks of the completion of the mission);
  [14] The scores will be the review team’s recommended scores. It is the responsibility of the DFID Lead Advisor to decide what scores will be entered into the DFID ARIES database. Where the lead advisor proposes a score which is different to that recommended by the MTR team this should be justified in writing and shared with IMEP and within DFID for discussion.
- A draft MTR report including an Executive Summary (max 4 pages) (documents consulted and people met annexes) within two weeks of the completion of the mission;
- A draft final MTR report (including Executive Summary and all annexes) within 2 weeks of receipt of the consolidated comments from SAVI and DFID (and GoN);
- The final report should have a maximum of 40 pages (excluding annexes). The report should include state reports as annexes for each state visited by the team (each one of a maximum of 5 pages).

#### 8. REVIEW TIMING AND TEAM COMPOSITION AND INPUTS
The review will take place from 31st October to 19th November 2011.

The team composition and inputs are as follows:

Name	Category	No of Days for Preparation	No of days in the field	No of days for follow up	Total
Gareth Williams	Subject Leader	4	17	7	28
Dirk van Esbroeck Governance/V&A consultant	Snr International	3	17	4	24
Maisha Strozier	Snr National Consultant (governance/V&A)	3	17	4	24
Daisi Feyisetan[15]	IMEP team member (M&E expert)		17
David Hoole / VfM Expert	Lead Consultant (international)	6	8	0	14
[15] As a permanent member of the IMEP Abuja team Daisi’s input is not costed as part of the review budget.

P.O. Box 4175
3006 AD Rotterdam
The Netherlands

Watermanweg 44
3067 GG Rotterdam
The Netherlands

T +31 (0)10 453 88 00
F +31 (0)10 453 07 68
E netherlands@ecorys.com

 www.ecorys.nl