LOGICAL FRAMEWORK

PROJECT NAME	Tanzania Climate Change Institutional Strengthening Programme
IMPACT	Impact Indicator 1			Baseline 2011					Milestone 2013				Target 2015
Tanzania achieves its MDGs through better management of climate change risks and opportunities.	Tanzania’s progress against MDGs	Planned		3					3.5				4
		Achieved
				Source
				DFID Annual Report. One point for MDGs achieved or on track (“green”) and half a point for MDGs that have showed some progress (“amber”). Baseline to be set once 2010/11 released.
	Impact Indicator 2			Baseline					Milestone 2013				Target 2015
	Number of people better able to cope with the adverse effects of climate change	Planned		0 - no data					To be determined after first year
		Achieved
				Source
				Development partner reports, analysis of government district and national strategies and reports. M&E framework for national CC strategy. Independent project evaluation.
OUTCOME	Outcome Indicator 1			Baseline 2010-11					Milestone 2013					Target 2015		Assumptions
Tanzania accesses climate finance and uses it effectively to support climate change resilience and low carbon sustainable growth	International climate change funds secured ( multi-lateral and bilateral)	Planned		$50m					$150m					$300m		International climate finance and bilateral funds for climate change are forthcoming based on agreements in international negotiations. / Political will and leadership on climate change / On-going macro-economic and political stability. / Fiduciary Risk Assessment is positive
		Achieved
				Source
				Baseline drawn from study for Development Partner Group on Environment and Climate Change: Climate Change Support in Tanzania, Mapping of current and future climate change interventions. To be repeated. Data also checked against www.climatefundsupdate.org
	Outcome Indicator 2			Baseline 2011					Milestone 2012				Target 2015
	Targets set out in National Climate Change strategy are assessed annually and met	Planned		0 - as no strategy in place					Strategy in place with M&E framework				At least 50% of priorities and targets have been met by 2015
		Achieved
				Source
				M&E framework for national CC strategy. Annual reviews of strategy. Independent project evaluation.
INPUTS (£)	DFID (£)			Govt (£)					Other (£)
	£2m			to be determined					£700,000 to £30m
INPUTS (HR)	DFID (FTEs)

OUTPUT 1	Output Indicator 1.1			Baseline 2011					Milestone 2012				Target 2013			Assumption
Comprehensive climate change strategy in place incl. adaptation and low carbon, with budget allocation and being effectively delivered at sector and district level	National Climate Change strategy incl. Zanzibar established and is funded	Planned		NAPA but no comprehensive strategy					Strategy finalised and action plan agreed by 2012				Budgets allocated for implementation of the strategy by 2013			Political will and leadership and momentum in GoT to drive forward climate change agenda. / International climate finance is forthcoming. / International negotiations prioritise allocations to Africa for adaptation. Ministry of Finance is willing and able to play a key role on climate finance. International CC finance system does not further strengthen the position system of gatekeepers constraining the space for engagement across government and at the local level.
		Achieved
		Source
		Reporting on National Climate Change strategy. GoT budget annual budget reports. PER on climate change.
	Output Indicator 1.2				Baseline 2011					Milestone 2012			Target 2014
	Transparent national Climate Change financing mechanism established	Planned			no financing mechanism					Options paper on financing with MoFEA and agreement on preferred option			Establishment of appropriate financing mechanism with engagement of sectors and districts by 2014
		Achieved
		Source
		Reporting on National Climate Change strategy. GoT budget annual budget reports. PER on climate change.
IMPACT WEIGHTING (%)	Output Indicator 1.3				Baseline 2011					Milestone 2013			Target 2015
40%	No of districts with plans and budgets for climate change	Planned			0					At least 2 pilots for performance based payments to district level CC partnerships			At least 5 districts covered. A joint programme identified to provide national coverage working closely with LGRP by 2020
		Achieved
		Source					RISK RATING
		Development Partner Annual Reviews of Decentralised Natural Resource Management and CC partnerships based on M&E framework . Reports from districts and PMO-RALG on progress.					Medium to high
INPUTS (£)	DFID (£)					Govt (£)					Other (£)	DFID SHARE (%)
	£700,000					£200,000- £24m*	80% to 3%
INPUTS (HR)	DFID (FTEs)

* Currently USD 40m is pledged by other development partners for district CC partnerships and decentralised NRM.
OUTPUT 2	Output Indicator 2.1					Baseline 2011				Milestone 2012		Target by 2015				Assumptions
GoT and development partner investments and expenditure is climate smart	Proportion of DFID (and development partner) spend that is climate smart		Planned			DFID portfolio screening excl. budget support - 50% climate risks and 80% opportunities				Methodology of screening PRBS is climate smart is developed		Less than 50% of development spend is at risk from climate change				Macro-economic stability and limited financial and fiscal shocks, which impact of GoT expenditure. / Political will to address climate change at the national and district level. / Leadership from Ministry of Finance on climate financing.
			Achieved
			Source
			Baseline to be drawn from study for Development Partner Group on Environment and Climate Change: Climate Change Support in Tanzania, DFID screening of portfolio in 2010 excl. budget support. To be repeated. Screening undertaken by other development partners.
	Output Indicator 2.2					Baseline 2012				Milestone 2012/2014			Target by 2015
	Proportion of GoT budget that is climate smart		Planned			Public Expenditure Review on climate change. Methodology for screening PRBS/GoT budget developed				Methodology agreed with GoT to screen PRBS and GoT budget. By 2012 and Screening undertaken by 2014			50% of the £640m per annum project aid and concessional borrowing in Tanzania is screened by 2015 ( assess if realistic)
			Achieved
			Source
			Public Expenditure Review on climate change. GoT budgets and expenditure. PETs on climate change funds. Report on climate screening of GoT budget.
IMPACT WEIGHTING (%)	Output Indicator 2.3					Baseline			Milestone 2011			Target by 2015
30%	Climate Change plans developed in key sector ministries and for key sector investments such as SAGCOT		Planned				0 - No sector strategies or action plans on climate change			SAGCOT green growth strategy by 2011			3 key economic sectors have CC strategies and action plans
			Achieved					Medium
			Source					RISK RATING
			SAGCOT Green Growth Strategy. Sector strategies, plans and budgets ( agriculture, water and energy/transport)
INPUTS (£)	DFID (£)					Govt (£)					Other (£)	DFID SHARE (%)
	£700,000					To be determined					£150-200,000
INPUTS (HR)	DFID (FTEs)

OUTPUT 3	Output Indicator 3.1					Baseline 2011			Milestone 2013			Target 2015			Assumptions
Improved aid effectiveness through a comprehensive framework for development partner support in Tanzania on climate change	Increased proportion of development partner spend in line with DP CC framework (and National CC strategy)		Planned				0 - as no framework or strategy in place			25% of climate change funds in support of DP framework by 2013			75% of climate change funds in support of DP framework and national strategy by 2013			Lack of political will and national CC strategy is not developed. / Development Partners continue to prioritise climate change in their bilateral and multi-lateral funding.
			Achieved
			Source
			Development partner reports, analysis of government district and national strategies and reports. M&E framework for national CC strategy. Independent project evaluation.
IMPACT WEIGHTING (%)	Output Indicator 3.2					Baseline 2010		Milestone 2012			Target 2015
25%	Increased proportion of joint DP programmes on climate change		Planned					0		3 by end 2012
			Achieved					Low to Medium
			Source					RISK RATING
			Development partner reports, analysis of government district and national strategies and reports. M&E framework for national CC strategy. Independent project evaluation.
INPUTS (£)	DFID (£)					Govt (£)		Other (£)			DFID SHARE (%)
	£400,000					0		£300,000			57%
INPUTS (HR)	DFID (FTEs)

OUTPUT 4	Output Indicator 4.1					Baseline 2011		Milestone 2012			Target 2015			Assumptions
Establish an effective M&E framework for climate change in Tanzania	M&E framework in place for a CC interventions and monitoring CC as a cross cutting issue in the DFID operational plan (£600m), with work plan for implementation					0 - establish M&E framework in first year building on SPR and logframe		Establish M&E framework with baseline data - identify data sources and needs			M&E framework used for MTR in 2013 and PCR in 2015. / Principles and indicators used by GoT in NCC strategy and by other development partners.			Data and Information is accessible and readily available. Other Development Partners are interested in the findings and ready to learn lessons.
			Achieved
			Source
			DFID Tanzania annual reporting against the Operational Plan. M&E Framework for National Climate Change strategy.
IMPACT WEIGHTING (%)	Output Indicator 4.2					Baseline 2011		Milestone 2011			Target 2015
5%	Independent evaluation undertaken and results shared		Planned					0		Scope of evaluation identified and key questions as part of M&E framework (longitudinal analysis)			Refine questions based on MTR and undertake IE in 2015
			Achieved					Low
			Source					RISK RATING
			DFID Tanzania annual reporting against the Operational Plan.
INPUTS (£)	DFID (£)					Govt (£)		Other (£)			DFID SHARE (%)
	£200,000					0		0
INPUTS (HR)	DFID (FTEs)