IMPACT
PROJECT NAME	Support for Electoral Reform in Pakistan (2012-2014)
IMPACT	Impact Indicator 1		Baseline	Milestone Dec 2012	Milestone Dec 2013	Target / Dec 2014
Stable, inclusive and tolerant democracy in Pakistan	The Economist Intelligence Unit’s Electoral Process and Pluralism category score	Planned	5.17 = Electoral Process and Pluralism category score for 2011	5.5	5.8	6.0
		Achieved
			Source
			The Economist Intelligence Unit Democracy Index 2011 Scale: 0-10 / 1. Full democracies—scores of 8-10. / 2. Flawed democracies—scores of 6 to 7.9. / 3. Hybrid regimes—scores of 4 to 5.9. / 4. Authoritarian regimes—scores below 4.[1]
[1] The ranges represent the overall index of democracy, which is the simple average of the five category indexes, one of which is Electoral Process and Pluralism.

OUTCOME
OUTCOME	Outcome Indicator 1		Baseline	Milestone 1 Dec 2012			Milestone 2Dec 2013				Target / Dec 2014		Assumptions
More credible, inclusive election process	Number of international and domestic observer missions that report that the legal framework provides a sound[2] basis for credible elections	Planned	Legal commentary of observer groups'[3] reports of 2008 elections	90% of observer groups in Pre-election assessments			90% of observer groups in their Preliminary statements				All main observer groups		No major event impactssignificantly on stability. E.g. no major environmental/natural disasters; no constitutional crises (i.e. impeachment of the President or military take-over); no significant events on borders; macro-economic stability. And election held once the voter list is finished. / NB. ECP target for turnout is 63%. This is helpfully ambitious but unlikely to be achieved. ECP target on women is 40% - this is ambitious but could be achieved.
		Achieved
			Source
			International and domestic assessment / observation reports
	Outcome Indicator 2		Baseline	Milestone 1 Dec 2012			Milestone 2Dec 2013			Target / Dec 2014
	Number of international observer and domestic observer missions and political parties report increased confidence in the capacity of the ECP	Planned	Analysis of reports and statements from 2008 elections	90% of observers in Pre-election assessments			90% of observers in their Preliminary statements			All key observers and main political parties
		Achieved
			Source
			Observer reports, media reports, ECP consultative meetings
	Outcome Indicator 3		Baseline	Milestone 1 Dec 2012			Milestone 2Dec 2013		Target / Dec 2014
	Percentage of registered voters participating in the elections is increased	Planned	2008 elections 44% turn-out rate (37 million); women’s turnout 38%[4]	N/A			N/A		50% turn-out for general elections (43.5 million); 40% women voters[5].
		Achieved
			Source
			Polling station data - disaggregated by gender
INPUTS (£)	DFID (£)		Govt (£)		CIDA/EU (£)			Total (£)				DFID SHARE (%)
	5,000,000				7,500,000			12,500,000				40%
INPUTS (HR)	DFID (FTEs)
	A2(L) GA 30% / B2 PO 40% / A2 Economist 5% / A1 SDA/Team Leader 5% / A1 Group Head/SCS HoO 2%
[2] The definition of “sound” for this indicator and “confidence” in the next will be determined by the Election Support Group (made up of donors and civil society) prior to the elections.
[3] Observer groups are likely to include: FAFEN, EU, SAARC, Commonwealth.
[4] There is no reliable data on women voters in previous elections (i.e. the number of women registered to vote who actually voted) . The estimate of 38% comes from FAFEN. A bill has been moved in the Senate by the Women’s Caucus in Parliament proposing separate data for female and male voters. If the bill is approved, the ECP will be obligated to tabulate results accordingly.
[5] IFES’ efforts will be directed at having 40% turnout for women, but this requires that men and women’s votes are calculated separately.

OUTPUTS
OUTPUT 1.1	Output Indicator		Baseline	Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014	Assumptions
Improved legal framework that ensures transparent electoral procedures that promote genuine and competitive elections	Degree to which legal framework meets international standards	Planned	Baseline = 6 = Number of standards met, determined by legal assessment at start of project	+1	+2	Baseline + 5	Parliament passes ECP’s and civil society’s recommendations. / ECP remains willing to engage with stakeholders
		Achieved
			Source
			Electoral laws and amendments
	Output Indicator		Baseline	Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014
	Number of adopted laws or amendments designed to improve credibility of elections that were drafted with IFES assistance	Planned	0	+2	+2	6 (one new unified law adopted and 5 acts repealed)
		Achieved
			Source
			Laws/amendments adopted, IFES drafts
	Output Indicator		Baseline	Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014
	Percentage of recommendations that are relevant to the legal framework and consistent with international standards made by civil society organizations[6] that are incorporated into the legal framework	Planned	N/A	+5%	+15%	25%
		Achieved
			Source
			Record of recommendations of civil society organizations
IMPACT WEIGHTING (%)	15%	RISK RATING	Medium
[6] Consultations with civil society are already in progress; this indicator reflects a combination of existing and new recommendations. The exact number of existing recommendations is difficult to define as there is a whole package of model laws prepared by FAFEN with IFES assistance and presented to all parliamentarians. It is more feasible to measure the percentage of this package being successfully incorporated into the legal framework.

OUTPUT 2.1	Output Indicator		Baseline	Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014	Assumptions
Strengthened institutional capacity of the ECP to manage the electoral process	Number of IFES-supported objectives of the ECP's Strategic Plan achieved	Planned	35 objectives achieved	+5= 40 objectives achieved	+15 = 50 objectives achieved	+25 = 60 objectives achieved	ECP remains committed and able to implement their Strategic Plan.
		Achieved
			Source
			ECP/IFES monitoring matrix, Pildat reports
IMPACT WEIGHTING (%)	15%	RISK RATING	Low

OUTPUT 2.2	Output Indicator		Baseline	Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014	ECP support and funding for large-scale training program.
Increased professionalism and competence of election officials	Degree to which job skills, electoral knowledge, and electoral event trainings supported by IFES result in increased job knowledge of participants	Planned	Baseline for job skills trainings & BRIDGE developed through pre-tests	30 %	60%	100% of targets for all trainings developed by training plan.
		Achieved
			Source
			Post-tests of training participants, training reports, reports by observers[7]
IMPACT WEIGHTING (%)	15%	RISK RATING	Low
[7] While pre-tests or job performance assessments would be ideal to assess this, the ECP is unlikely to allow this. Training monitoring techniques will be clearly defined and will focus on the effective delivery of key points of the training.

OUTPUT 2.3	Output Indicator		Baseline	Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014	Continued ECP-NADRA collaboration. Adequate time given for the update of electoral rolls. / There is no major change in the electoral rolls due to climate change induced migration
Improved and accurate electoral rolls that can be updated and challenged for any inaccuracies	Number of parties and domestic observer groups with increased confidence in the electoral rolls[8]	Planned	Baseline=0	5	15	20 organizations (16 political parties and 4 observer organizations, of which at least 1 is a women’s group)
		Achieved
			Source
			Statements by political parties, observer reports and statements, media reports, ECP reports of consultative meetings, post elections review
IMPACT WEIGHTING (%)	15%	RISK RATING	High
[8] IFES will request both quantitative and qualitative data from all organizations and parties.

OUTPUT 2.4	Output Indicator		Baseline	Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014
Enhanced capacity of ECP to conduct electoral operations	Number of electoral operations systems and procedures amended and strengthened with IFES assistance	Planned	Baseline=0	30% of the target	60% of the target	To be determined
		Achieved
			Source
			From ECP: Procedural notices, announcements, press releases, internal documents, other. From IFES: Project reports
IMPACT WEIGHTING (%)	15%	RISK RATING	Low

OUTPUT 3.1	Output Indicator		Baseline	Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014	Assumptions
Strengthened ECP capacity in the conduct of voter/civic education	ECP successfully implements its voter/civic education plan	Planned	Baseline=0; first time for establishment of plan	20 % of plan achieved	60% of plan achieved	To be determined following review of plan (in process of being developed)	ECP remains committed and able to implement their Strategic Plan.
		Achieved
			Source
			ECP civic/voter education plan, reports of plan implementation, IFES reports
IMPACT WEIGHTING (%)	15%	RISK RATING	Low

OUTPUT 3.2	Output Indicator			Baseline		Milestone 1 Dec 2012	Milestone 2Dec 2013	Target / Dec 2014	ECP able to conduct and fund voter and civic education
Increased CSO capacity for the conduct of voter/civic education	Degree to which the understanding of target citizens of the electoral/voting process is enhanced	Planned		Baseline=37% have enough information on when and where to vote (49% men and 25% women)		20% of the target	60% of the target	To be determined based on outreach strategy
		Achieved
				Source
				Voter education survey (primary source). Reports of CSO partners, findings of focus groups, participant evaluations (validation). Data disaggregated by gender, type of targeted citizen.
IMPACT WEIGHTING (%)	10%		RISK RATING		Low

ACTIVITIES
ACTIVITIES 1.1.1	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Submission of ECP electoral reform proposals to the Ntl Assembly/Senate/ Parl. Committee on Elect. Reforms	Number of proposed laws or amendments to ensure credible elections drafted with IFES assistance[9]	Planned	Number of laws/amendments previously developed by IFES, and not yet adopted = 12			20 laws, amendments and/or articles	Parliament willing to consider reform proposals
		Achieved
		Source
		Laws/amendments proposed, IFES drafts
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of the ECP's electoral reform proposals that meet international standards	Planned	N/A			All
		Achieved
		Source
		ECP's electoral reform proposals
[9] This indicator measures the number of proposals submitted to legislature for their consideration and is different to Output indicator 1.1 which measures the number of amendments passed by parliament.

ACTIVITIES 1.1.2	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Improved ECP regulations	Number of regulations and other implementing guidelines that meet international standards	Planned	Baseline developed through analysis of existing regulations, etc.			All regulations, etc.
		Achieved
		Source
		ECP's regulations, etc
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of regulations, etc. to ensure credible elections drafted with IFES assistance	Planned	Baseline=0			5 e.g. regulations on counting and political finance
		Achieved
		Source
		ECP's regulations, etc; IFES drafts
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of IFES-supported stakeholder consultations on the regulatory framework	Planned	Baseline=0			4	ECP willing to engage with stakeholders
		Achieved
		Source
		ECP reports and press releases, CSO reports, IFES reports. Data collected on participants disaggregated by gender, type of organization.

ACTIVITIES 1.1.3	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Increased interaction with stakeholders to ensure broad public support for reform	Number of CSOs receiving IFES assistance and sub-grants for advocacy for electoral reform	Planned	Baseline=0			3, of which at least 1 is a women’s organization
		Achieved
		Source
		IFES reports, data disaggregated by type of organization
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of CSO campaigns for electoral reform, supported by IFES	Planned	Baseline=0			3	CSOs are able to campaign
		Achieved
		Source
		CSO reports

ACTIVITIES 2.1.1	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Re-structured ECP	Degree to which re-organization plan is implemented, with a focus on the establishment and strengthening of ECP's technical departments	Planned	1 units/institutions created or upgraded			5 units created or upgraded	ECP open to the idea of reorganization
		Achieved
		Source
		ECP re-organization plan, staff structure and records, reports
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Degree to which ECP implements strategy for the competitive recruitment of qualified personnel	Planned	To be determined upon assessment of current process			To be determined upon development of recruitment strategy
		Achieved
		Source
		ECP recruitment strategy, ECP reports, IFES reports, ECP hiring officials and ECP staff

ACTIVITIES 2.1.2	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Improved electoral management procedures and systems	Number of electoral management systems and procedures strengthened with IFES assistance	Planned	Baseline=0			To be determined	Access to ECP’s electoral management practices
		Achieved
		Source
		From ECP: Procedural notices, announcements, press releases, internal documents, other. From IFES: Project reports

ACTIVITIES 2.1.3	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Increased diversification and acceptance of ECP staff	Percentage of women, minorities and persons with disabilities employed by the ECP, as permanent and temporary staff	Planned	Less than 1% staff are women. Baseline data for other groups to be gathered through assessment.			50% of ECP's Strategic Plan targets are met	ECP willing to cooperate on assessment
		Achieved
		Source
		ECP records, ECP-IFES assessment reports. Data also to include type of position.
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Degree of acceptance of staff diversification	Planned	N/A			Implementation of diversification Action Plan	ECP willing to implement Action Plan
		Achieved
		Source
		Action Plan
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Implementation of Gender Policy, establishment of Gender Unit, women’s committees and National Gender Working Group	Planned	Baseline=0			1 Gender Policy / 1 Gender Unit / 4 women’s committees / 1 National Gender Working Group	ECP support for gender issues
		Achieved
		Source
		ECP organizational charts, minutes of meetings

ACTIVITIES 2.1.4	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Increased electoral research and learning outreach capacity	Number of male and female Research Wing staff trainedin research methods with IFES assistance	Planned	1 Research Officer			10 staff trained (at least 1 female), Training materials developed
		Achieved
		Source
		Training reports and pre- and post-evaluations
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Degree to which ECP libraries are updated and allow public access	Planned	150 libraries, 0 with public access			150 libraries updated and improved, 30 allow public access	ECP willing to provide public access to libraries
		Achieved
		Source
		ECP reports, field visits to libraries

ACTIVITIES 2.1.5	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Improved IT infrastructure	Amount of energy efficient IT equipment procured	Planned	To be determined based on pre-intervention assessment			To be determined based on pre-intervention assessment
		Achieved
		Source
		Procurement records, ECP reports
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of staff trained to use new equipment	Planned	Baseline=0			20 IT officers and 80 regular staff trained
		Achieved
		Source
		Training reports, attendance lists

ACTIVITIES 2.1.6	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
ECP’s oversight of political finance improved	Online database for political finance submissions published	Planned	Baseline=0			1 website published	ECP willing to set up database / Database safeguards submission information
		Achieved
		Source
		Online database
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of reform recommendations drafted	Planned	Baseline=0			5 recommendations	Political will for political finance reform exists
		Achieved
		Source
		Report with recommendations for reform
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Support establishment of functioning political finance section	Planned	Baseline=0			1 political finance section	Political will for political finance reform exists
		Achieved
		Source
		ECP organizational charts. Analysis of results achieved by the section by relevant CSOs e.g. PILDAT

ACTIVITIES 2.2.1	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Institutionalized Federal Election Academy (FEA)	Degree to which the ECP's FEA is institutionalized, and has the capacity to conduct technically-sound practices	Planned	Baseline=0			Progress to be measured by the following steps: 1= 4 ECP-funded FEA trainers, 2=4 FEA trainers + Head of Training, 3=Provincial FEAs, 4=Provincially-based FEA teams
		Achieved
		Source
		FEA staffing records, training plans & reports, curriculum, budget
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of training sessions conducted by FEA trainers	Planned	Baseline=0			To be determined by training plan
		Achieved
		Source
		FEA training plan & reports. Disaggregated by those wholly supported by ECP and those receiving IFES/other support.

ACTIVITIES 2.2.2	ACTIVITIES Indicator			Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Trained male and female ECP officials and temporary election staff	Number of (on line where possible) training materials developed and produced, with IFES assistance, including number of training materials translated	Planned		Baseline=0			10
		Achieved
		Source
		Training materials. Distinction made between those that are developed through IFES assistance and those printed/produced by IFES.
	ACTIVITIES Indicator			Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of male and female trainers trained with IFES assistance who are able to conduct effective training of ECP officials[10]. (Indicator also reports on ACTIVITIES 2.2.1, above.)	Planned		43 (30 Master Trainers + 13 BRIDGE), currently no female trainers			An additional 50 trainers – 3 who are female.	Ability to obtain visas for international BRIDGE facilitators and ECP staff
		Achieved
		Source
		ECP training reports, IFES project reports. Disaggregated by type of trainer (BRIDGE facilitator, Master Trainer, etc), and by gender
	ACTIVITIES Indicator			Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of training sessions held with IFES assistance	Planned		Baseline=0			36. Target includes gender and sensitization training.	Elections held in/around May 2013
		Achieved
		Source
		ECP training reports, IFES monitoring reports
	ACTIVITIES Indicator			Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of male and female ECP officials and temporary election staff trained with IFES assistance.	Planned		Baseline=0			50 Lead Trainers / 1,000 Master Trainers	ECP support and co-funding for large-scale training program
		Achieved
		Source
		ECP training reports, IFES monitoring reports. Data disaggregated by gender, type and posting of official
[10] The training will include discussions on how the ECP can minimise its GHG emissions and impact on the environment. Training also needs to specifically include impact of extreme weather events (like floods/drought etc) on election process and electoral rolls and thus aid in effective planning.

ACTIVITIES 2.3.1	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Increased accuracy of electoral rolls	Degree to which electoral rolls meet established targets	Planned	32%			85% accuracy of the surveys of list to voters and voters to list. Average of the two levels of accuracy found, or 85% for each one.	ECP and NADRA agree to audit
		Achieved
		Source
		List-to-voter survey, Voter-to-list survey, electronic audit

ACTIVITIES 2.3.2	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Demonstrated ECP capacity to update and maintain the electoral rolls	Degree to which ECP officials demonstrate the capacity to update and maintain the electoral rolls	Planned	Baseline=0			Capacity to be measured by the following steps:1=Section officer designated for VR, 2=Section officer + IT staff dedicated to VR, 3=VR promoted to a wing of ECP with JS in charge and sections created for different components of VR activity, 4=dedicated VR staff allocated to provinces in charge of VR updates	ECP and NADRA continue to collaborate with each other and IFES on voter registration
		Achieved
		Source
		ECP training and operational reports, IFES training reports and monitoring of electoral roll maintenance. Staff capacity also measured through training under 2.2.2 ACTIVITIES. Voter registration regulations measured through 1.1.2 ACTIVITIES.

ACTIVITIES 2.4.1	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Implementation of new technologies / approaches informed by rigorous testing	Degree to which conduct of the electronic voting machine pilot project follows established legal and operational guidelines, and is transparent	Planned	Baseline=0			To be determined based on guidelines	ECP purchases EVM machines for pilot
		Achieved
		Source
		ECP and IFES reports, reports of observers, survey and focus groups

ACTIVITIES 2.4.2	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Increased transparency of the electoral process	Number and type of electoral stakeholders receiving the final electoral roll from the ECP	Planned	3 political parties			20, including 2 women’s organizations
		Achieved
		Source
		ECP records (including data from website visits), IFES reports
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Degree of the operationalization of a new results management system for the timely and wide dissemination of accurate and complete results	Planned	Current system is not electronic and does not release full (polling-station level) results			To be determined with the design of the system	Access to polling stations/counting centers
		Achieved
		Source
		ECP records and reports, IFES monitoring and project reports, reports from election observers, media reports

ACTIVITIES 2.4.3	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Strengthened outreach to electoral stakeholders	Number of ECP-conducted consultations conducted at the national, provincial, and district levels for civil society and political parties	Planned	National level = 3 per year			National level=4 per year, provincial level=2 per year, district level=to be determined	Continued existence of Political Party Consultative Forum and Civil Society Consultative Forum
		Achieved
		Source
		ECP press statements and reports, List of participants, IFES monitoring
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of electoral stakeholders trained in their roles & responsibilities by the ECP	Planned	Baseline=0			20, including 2 women’s organizations
		Achieved
		Source
		ECP training reports, IFES monitoring reports. Disaggregated by gender and type of stakeholder.
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of male and female ECP staff trained in stakeholder management	Planned	Baseline=0			60, of which at least 6 are women
		Achieved
		Source
		IFES training reports. Disaggregated by gender
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of post-election reviews held	Planned	Baseline=0			4 (local and general, held by the ECP and CSOs)	Local and general elections held during program period
		Achieved
		Source
		IFES, ECP,and CSO reports and post-election review recommendations

ACTIVITIES 2.4.4	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Strengthened outreach to the media	Degree of implementation of the ECP's media outreach policy/strategy	Planned	Baseline=0			To be determined based on policy/strategy
		Achieved
		Source
		ECP press statements, reports of ECP media initiatives, media reports
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Media center established	Planned	Baseline=0			1	ECP dedicates a venue for the Media Center and commits to staffing and maintaining the Center
		Achieved
		Source
		Procurement records, ECP and IFES reports, media coverage

ACTIVITIES 2.4.5	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Improved election policies / procedures	Number of policies / procedures developed and implemented that increase access to marginalized groups to polling	Planned	Baseline=0			To be determined upon policy / procedure review
		Achieved
		Source
		ECP's policies and voting and other procedures. Observer reports.

ACTIVITIES 2.4.6	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Effective and efficient adjudication of complaints	Number of ECP staff and judges trained in election adjudication	Planned	Baseline=0			25, of which 15 judges
		Achieved
		Source
		Training reports, attendance sheets
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Degree to which complaints processes monitored	Planned	Baseline=100%			Target=100%	Access to court and ECP records of complaints
		Achieved
		Source
		Regular reports every month after the election for 4 months

ACTIVITIES 2.4.7	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Increased transparency in constituency delimitation	GIS pilot completed	Planned	N/A			1 GIS pilot in 1 District	ECP willing to move ahead with GIS pilot
		Achieved
		Source
		ECP and IFES reports
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Procurement and training for GIS completed	Planned	Baseline=0			To be determined based on GIS implementation plan
		Achieved
		Source
		Procurement records, training reports
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of constituency delimitations completed	Planned	Baseline=0			To be determined based on GIS implementation plan	ECP willing and able to move ahead with GIS implementation for constituency delimitation
		Achieved
		Source
		Delimitation reports

ACTIVITIES 3.1.1	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Increased staff efforts to conduct voter education	Number of male and female ECP officials trained in voter education outreach	Planned	Baseline=0			150 (one in each district, then additional from provincial-level and from Islamabad)
		Achieved
		Source
		Training reports, attendance lists, training sessions. Data disaggregated by gender, position and location.
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Percentage of voters that have information about when and where to vote	Planned	Baseline=37% have enough information on when and where to vote (49% men and 25% women)				ECP funding of PR campaigns
		Achieved
		Source
		Surveys

ACTIVITIES 3.1.2	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
ECP engagement with civil society organizations and others to expand civic/voter education efforts	Number of civil society organizations and other groups participating in the ECP's civic/voter education working group	Planned	Baseline=0; currently no ECP forum for planning or coordinating civic/voter education			Number to be determined. 10% target for women’s groups and groups representing marginalized populations.
		Achieved
		Source
		Attendance lists, ECP meeting records. Data disaggregated by gender and type of organization
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of schools incorporating democratic awareness into curriculum with ECP/IFES assistance	Planned	Baseline=0			No. of schools to be determined by Ministry of Education	Min. of Education and schools willing to collaborate with ECP/IFES on democracy education
		Achieved
		Source
		ECP records, data disaggregated by type of school

ACTIVITIES 3.2.1	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Increased role for civil society in the conduct of voter/civic education	Number of CSOs receiving IFES assistance and sub-grants for voter/civic education initiatives	Planned	Baseline=0			6, of which at least 1 is a women’s organization
		Achieved
		Source
		IFES reports. Data disaggregated by type of organization.
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of people reached by IFES-assisted voter education	Planned	Baseline=0			To be determined by CSOs project plans (targets will be set for gender, PWDs, minorities, youth)
		Achieved
		Source
		Attendance lists, CSO reports, IFES monitoring. Data disaggregated by gender, PWDs, minority, youth.
	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
	Number of showcase democracy events with youth	Planned	Baseline=0			10
		Achieved
		Source
		CSO reports, event materials

ACTIVITIES 3.2.2	ACTIVITIES Indicator		Baseline	Milestone 1	Milestone 2	Target (Date)	Assumption
Establishment of electoral information web portal	Number of hits (disaggregated by Pakistan, non-Pakistan) to web portal	Planned	Baseline=0			To be determined by project plan
		Achieved
		Source
		Website records