Annual Review – post April 2018

Title: Reducing poverty through Local Economic Development (LED) in the Commonwealth
Programme Value £ (full life): 3,900,000		Review Date: 17/7/2018
Programme Code: / 204043	Start Date: / August 2017	End Date: / July 2020

Summary of Programme Performance
Year	2018
Programme Score	A
Risk Rating	Low

DevTracker Link to Business Case:	https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objId=14416943&objAction=viewheader
DevTracker Link to Log frame:	https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objId=14417850&objAction=viewheader

A. Summary and Overview

Description of programme

The Commonwealth Local Government Forum (CLGF) was established in 1995 and is officially recognised by the Commonwealth Heads of Government. CLGF works to promote and strengthen effective democratic local government across the Commonwealth through local investment opportunities, job creation and improving the environment in which to do business. CLGF facilitate the exchange of good practice in local government through its extensive membership (more than 200 members in 47 Commonwealth countries) at national and local government level.

Under an earlier £4.5 million DFID funded programme (2012–2016), CLGF successfully piloted a Local Economic Development (LED) approach, raised awareness for LED and demonstrated the potential impact of LED. This new £3.9 million programme is expected to further deepen and embed that approach by rolling out local economic development at scale with local government partners and by sharing the lessons learned with other Commonwealth countries. CLGF is an influential knowledge-sharing network and will focus their efforts in this programme on six countries: Botswana, Ghana, Sri Lanka, South Africa, Swaziland (renamed ‘Eswatini’ from April 2018) and Zambia. The expected results will be increased economic opportunities, job creation and improved skills. The programme is, in particular, targeting Sustainable Development Goal 8 (decent work and economic growth) and Goal 11 (sustainable cities and communities).

Summary supporting narrative for the overall score in this review (1/2 page)

The key focus of this programme in the first year has been to build on the pilot programme and deliver at pace to meet the agreed milestones set out at the start of the programme. This Annual Review notes that good progress has been made against outputs and that CLGF has met the expected results with 3 targets moderately exceeding expectations: a) 1.3: target councils demonstrate increased capacity to develop bankable projects and successfully leverage investment; b) 4.1: regional and global policy events highlight the effectiveness of LED as a means of achieving sustainable development and c) 4.4: percentage of funding leveraged against DFID’s contribution. During the Commonwealth Heads of Government Meeting April 2018, CLGF received an award from the Commonwealth Businesswomen’s Network for its work in empowering women. That award has been established to recognise a Commonwealth accredited organisation that has made a significant contribution to support women’s economic empowerment and gender equality through its work, membership and governance.

The programme is on track and has delivered expected results in year one. Lessons learned from the pilot programme have helped with the smooth transition into this phase of embedding and deepening local economic development and its roll out across the Commonwealth.

Recommendations for the year ahead

- CLGF needs to ensure a cross section of staff and leaders are directly engaged in the projects to ensure wide engagement to mitigate the risks around staff turnover and their impact on project deliverables.
- CLGF should continue to prioritise and strengthen institutional relations and linkages with its existing project partners, as well as seek to build new linkages as appropriate with other key stakeholders
- CLGF should continue to look for opportunities to support the informal sector and specific target groups (such as women and youth) in LED pilot work at the local level to ensure national LED rollouts are pro-poor and as inclusive as possible.
- CLGF should continue to involve project stakeholders in guiding the project over the course of implementation to ensure it remains tailored to the local context and it evolves in line with the changing political and social-economic priorities
- CLGF should continue to use LED practitioners from partner countries with experience of LED to share good practice and practitioner know-how
- CLGF should continue to ensure it is present and actively feeding into key Commonwealth and international policy discussions and events on LED, the SDGs and women in development to continue to influence these agendas and build knowledge and awareness of the role of local government in delivering development.
- CLGF should continue to draw on the research outputs of its academic partners to feed into its programme of work both in projects and advocacy.
- the DFID/UNCD Deputy Programme Manager responsible for the CLGF programme should join the CLGF team for a field visit to see programme activity on the ground in advance of the next Annual review (due in July 2019)

## B: DETAILED OUTPUT SCORING

Output Title	National/provincial local economic development (LED) strategies designed and rolled out (Botswana, Zambia and Sri Lanka)
Output number per LF		1	Output Score	A
Impact weighting (%):		50%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of countries that have adopted the CLGF approach to LED and are rolling out national LED strategies which are designed to be (1) pro poor, (2) gender sensitive, (3) enable local participation, (4) locally responsive	At least two LED strategies and/or implementation strategies under development (Dec 2017) / Implementation strategy and Monitoring & Evaluation (M&E) framework being rolled out (July 2018)	Target met: Partners in Sri Lanka, Botswana and Zambia have agreed targeted workplans including the development of LED Strategies and plans for implementation and M&E. In Zambia, LED guidelines were developed and launched with all 104 local authorities in the country. In Sri Lanka a steering committee bringing together the Ministry of LG, the local government association, and the local government training institute is in place and guiding the project implementation and M&E. In Botswana, under the previous DFID funded pilot, the national LED framework was developed. This framework is now being rolled out county wide (in all 16 districts).
1.2 Percent of citizens surveyed in areas implementing LED report improvement with the council’s economic development services (disaggregated by gender)	Mapping of citizen interface/engagement underway in 12 target councils (Nov 2017) / Consultations with local stakeholders (citizen groups, business associations for formal and informal traders etc) undertaken in 12 target councils (March 2018) / Knowledge, Attitude and Practices (KAP) survey developed (July 2018)	Target met: 26 Target councils identified (Sri Lanka 6, Botswana 10, and Zambia 10). Mapping of key institutions for citizen support undertaken in Sri Lanka, Botswana & Zambia. / Consultations have been undertaken with local stakeholders in 4 target councils in Zambia and are ongoing in 4 Sri Lanka and 4 Botswana councils. / Knowledge and Attitude Practices (KAP) surveys developed to target local beneficiaries and measure results.
1.3 Target councils demonstrate increased capacity to develop bankable projects and successfully leverage investment	At least 8 councils (2/3rds) have increased capacity to target potential LED investors (Dec 2017) / LED strategies adopted by at least 8 (2/3rds) of the target councils (March 2018)	Target exceeded: 14 councils are developing targeted LED strategies. / Training on LED has reached +700 local government practitioners (both elected and technical).

Briefly describe the output and provide supporting narrative for the score
Indicator 1.1: Targeted workplans were developed in Sri Lanka, Botswana and Zambia that work towards the development and roll out of the National/Provincial LED Strategies. In each of the three countries these were developed in close partnership with the Ministry of Local Government, the local government association (LGA) and key stakeholders including pilot councils. Key indicative activities undertaken include:
- The launch of a set of LED Guidelines in April 2018 during an event attended by over 650 senior local government officials representing all the 104 local authorities in Zambia.
- Development of learning tools on the different LED services in Sri Lanka to support councils to better understand how their existing work supports (or hinders) local economic development
- Development of local economic assessments in four Botswana districts to inform local development plans
Indicator 1.2: Consultation with stakeholders has been integral in developing the council level workplans and integrated as a key component of the strategies and work plan implementation:
- In Zambia citizens, particularly women and youth, are being targeted through the strengthening of ward development committees. Wards development committees are at the most local level and are made up of Councillors, civil societies, NGOs and community representatives. Wards offer a local space for citizens to take part in the decision-making process by: 1) building the capacity of ward development committees to effectively represent the citizens, 2) establishing complaints and reporting facilities in local government, 3) establishing site offices at ward level using existing infrastructure to bring the council closer to the communities, and 4) using smart technologies and applications to promote citizen participation in local governance and LED.
- In Sri Lanka a mapping of LED stakeholders and programmes at national and provincial levels was undertaken and a report produced to better inform both the steering committee and the provincial and local governments participating in the project of the variety of actors and partners already active in the country. This exercise will ensure the best possible coverage and integration of key actors into subsequent work.
In Botswana, an internal analysis of community views on local government’s economic development services has identified community participation in LED as a priority target area. As such the work on developing and implementing the national LED role out has specifically prioritised increasing community participation and participatory governance through community empowerment on economic activities within LED strategies. This includes the creation of a community-based observatory tool which will strengthen feedback from local people to improve the local council’s economic development services.
Indicator 1.3: 14 councils have are developing targeted LED strategies:
- 10 councils in Zambia are in the process of developing community-led gender responsive LED strategies. These strategies are focusing on internal staff capacity building, targeted services for improved LED (such as project development), and the implementation of community empowerment projects targeting women, youth and the disabled.
- 4 councils in Botswana have developed bankable business plans which have increased the capacity of the councils to attract both private and development funds in the Tourism, Agriculture and Green Economy Sectors.

Lessons identified this year, and recommendations for the year ahead linked to this output
CLGF’s projects are helping demonstrate the value of inclusive approaches both at the national and local level. Whilst inception periods can be lengthy, this is helping to ensure the sustainability of project results and providing the essential political and community buy in needed. LED capacity building with local leaders and technical staff, remains a key priority to underpin the efforts for successful LED strategies at both the local and national levels. With the turnover of staff and democratic renewal of leaders this is a continuous and ongoing process.

Recommendation:
CLGF needs to ensure a cross section of staff and leaders are directly engaged in the projects to ensure wide engagement to mitigate the risks around staff turnover and their impact on project deliverables.

Output Title	Increased capacity to roll out LED in selected countries (Ghana, South Africa and Swaziland)
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of countries embedding the CLGF approach to LED, where appropriate, in national policy, legal, regulatory and capacity development frameworks for LED	Assessment of barriers to successful national roll out of LED policy undertaken in three countries (Oct 2017) / LED implementation strategies developed in at least two countries (March 2018)	Target met: Assessments of national environment (policy, institutional, capacity, political will) undertaken in three focal countries (Swaziland, South Africa and Ghana). LED implementation strategies developed for Swaziland and South Africa, and review of strengths and weaknesses of existing LED policy implementation underway in Ghana.
2.2 Capacity of technical staff and political leaders to deliver LED services increased (councils and ministries)	Detailed assessment of capacity gaps complete in three countries (Oct 2017) / Capacity development activity planning underway (March 2018)	Target met: Assessment of capacity gaps completed and integrated into targeted work plan developed for Swaziland, South Africa, and Ghana. / Extensive briefings, participation in national and regional events have served to increase awareness and capacity of officials and leaders to understand the potential of LED
2.3 Improved economic opportunities for citizens in areas implementing LED	Assessment of data availability and data gaps identified in 6 target councils (Nov 2017) / Consultations with local stakeholders (citizen groups, business associations for formal and informal traders etc) undertaken in 12 target councils (March 2018)	Target met: Assessment of data availability and gaps undertaken for 10 pilot councils in Swaziland, 3 pilot councils in Ghana and 1 district in South Africa. Consultations with local stakeholders undertaken in 14 councils/districts.

Briefly describe the output and provide supporting narrative for the score

Indicator 2.1: CLGF Assessments of national environment (policy, institutional, capacity, political will) have been undertaken in three focal countries and LED implementation strategies have been developed for Swaziland and South Africa:
- In Swaziland, an overview assessment of the socio-economic and governance context was undertaken and analysed to better understand these drivers. Based on this the work to embed LED will work at three levels, (a) continue embedding LED at the national level, (b) build the capacity of technical staff and political leaders, (c) Improve economic opportunities for citizens within local authorities.
- In South Africa a national LED Conference was convened in November 2017, to discuss the state of LED in the country and agree on measures to address barriers to successful national rollout. The conference brought together: the Ministry of Cooperative Governance and Traditional Affairs and the Ministry of Small Business Development, the South African Local Government Association (SALGA) and CLGF with over 500 delegates. The following three focus areas reflect the main resolutions adopted at the summit:
1. Accelerating economic transformation and increase economic opportunities and investment at local level. This results in urban regeneration and improvement and better local services and creates quality living and working environments.
2. Building on the Back to Basics programme by continuing to provide quality services.
3. Collaboration and Leadership: ethical and committed leadership, responsive to needs of local communities, working closely with other spheres of government.
These three areas underpin the LED implementation strategy for South Africa “Supporting Local Government in Promoting Regional Economic Planning and Local Economic Development”.
In Ghana the assessment of the national context highlighted that sound economic empowerment of the citizenry in the various metropolitan, municipal or district assemblies would significantly support the country’s push towards reaching its SDGs targets and would allow for local areas to be developed and decentralised in a sustainable manner as also outlined in the Ghana Growth and Development Agenda II. A review of strengths and weaknesses of existing LED policy, which has been in place since 2013 highlighted that implementation at the local level has been uneven and for the most part local activities are yet not linked to the SDGs. The project is currently working within the framework of the existing national policy with a set of pilot councils to feedback local knowledge into a wider policy review process.
Indicator 2.2: A CLGF assessment of capacity gaps was undertaken in the first months of the project and the results were integrated into targeted work plans developed:
- In Swaziland, the assessment highlighted that while council technical staff have good knowledge and experience in stakeholder, community and business engagement, as well as in strategy development there was limited technical understanding of LED. As such councils have prioritised support to local economic assessments and developing and overseeing PPPs. Following the October 2017 local government elections in the country, it was assessed that the project provided a key opportunity to build capacity of incoming local elected leaders to be LED champions and as such this was integrated as a 1st priority action.
- In South Africa, despite significant achievements in service delivery for water, electricity, sanitation and refuse-removal at a local level since 1994, much needs to be done to support, educate and where needed, enforce implementation of local government’s mandate for wider service delivery. The capacity assessment highlighted that there is a very wide range between the best performing councils, which are delivering services, planning for resilience and sustainability and implementing innovative practices in terms of partnerships and collaboration, and the bottom third of municipalities which in many cases are dysfunctional. To address this situation the Ministry of Cooperative Governance and Traditional Affairs launched the Back to Basics programme (in which CLGF has been identified as a knowledge and best practice partner) with five pillars, namely: (1) Putting people first, (2) Delivering basic services, (3) Good governance, (4) Sound financial management, and (5) Building capacity. Within this framework the project’s capacity building is focused on integrated regional planning across municipal boundaries to enhance economic competitiveness. Support will be given to develop individual, organisational and institutional capacity to effectively implement regional economic planning that promotes spatial integration and inclusive economic development in the Bojanala District municipalities.
- In Ghana, the capacity assessment highlighted that council staff and leadership were familiar with the national LED policy and in many districts LED strategies had been developed however these were often undertaken through consultants and while aligning with the national policy objectives they had a limited reflection of the capacity of the council to implement, as well as the local community to sustain initiatives following a first activity. As such 1st capacity building activities developed for the target pilot councils were focused on building awareness on the linkages between national commitments to LED and the SDGs and local development priorities and potential.
Indicator 2.3: Data gaps at the local level were assessed through both national and local assessments and dialogues with key stakeholders:
- In South Africa, the National LED conference brought together 500 delegates from local councils together with representatives from Central and Provincial government, business, civil society and academia to discuss the challenges and barriers to improving economic opportunities for citizen. CLGF was a core partner in the preparation and delivery of this conference which was hosted by the Ministry of Cooperative Governance and Traditional Affairs and the Ministry of Small Business Development.
- In Swaziland and Ghana, consultations with key stakeholders took place with local stakeholders bringing together community groups, representatives of the business community, decentralised national and sub-national programmes to discuss gaps in existing services for support to citizen economic empowerment. This resulted in a variety of targeted activities being included in pilot council work plans, such as in Tema (in Southern Ghana) where Capacity Building and training will be provided to 500 informal businesses to strengthen their revenue generation, strategic business planning, market segmentation, access to capital and their role in the implementation of SDGs.

Lessons identified this year, and recommendations for the year ahead linked to this output

The projects continue to demonstrate the value of participative and inclusive approaches, building on many of the partnerships established under the earlier project. A clear lesson of the 1st year has been the importance of taking the time to properly understand and align workplans with existing and emerging government goals and objectives to be in a position to provide strategic support to a process that all partners are invested in. The institutional relationships and trust between partners built over multiple project years of joint work, has ensure that CLGF is included in key strategic discussion and activities (such as the national LED Conference in South Africa).

CLGF has a wealth of knowledge and good practice both in LED policy and on practical LED actions and thematic areas. Drawing on this technical and practitioner expertise is a key interest for the project partners at all levels.

Recommendations:
- CLGF should continue to prioritise and strengthen institutional relations and linkages with its existing project partners, as well as seek to build new linkages as appropriate with other key stakeholders
- CLGF should continue to look for opportunities to support the informal sector and specific target groups (such as women and youth) in LED pilot work at the local level to ensure national LED rollouts are pro-poor and as inclusive as possible.

Output Title	Increased awareness of LED potential in selected countries with some fragility (drawn from Bangladesh, Cameroon, Lesotho, India, Pakistan, Sierra Leone, Zimbabwe)
Output number per LF		3	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 National actors (ie Ministry of LG, LGA, business fora) use lessons from demonstration projects and national/regional exchange to inform enabling policy and LED practice to empower local governments to deliver LED	Awareness on potential of LED raised with national actors (Dec 2018)	Target ongoing: Awareness is being raised with technical staff, local leaders, national and state level decision makers on the potential of LED in Madhya Pradesh (India), Cameroon, Sierra Leone and Zimbabwe
3.2 LED demonstrated as an approach to integrated local development	Development of LED strategies initiated in 6 councils (March 2018)	Target met: 9 LED strategies developed/in development
3.3 Improved economic opportunities for citizens in areas implementing LED	Mapping of citizen interface/engagement underway in 12 target councils (Nov 2017) / Consultations with local stakeholders (citizen groups, business associations for formal and informal traders, etc) undertaken in 12 target councils (March 2018)	Target met: / Mapping of citizen interface/ engagement completed in 13 target councils and with the Madhya Pradesh State Rural Livelihoods Project (MPSRLP); / Consultations with local stakeholders undertaken in 12 target councils

Briefly describe the output and provide supporting narrative for the score

Indicator 3.1: CLGF Awareness-raising with key actors and implementers is ongoing. Some key achievements to date include:
- In Madhya Pradesh (India) 70 State government officials directly responsible for the implementation and management of poverty alleviation programmes have been given an orientation training on local economic development. Resulting from this, 10 senior bureaucrats who are the key policy decision makers in the State government are being supported and encouraged to strategically pilot the local economic development approach
- For Cameroon, following the splitting of the Ministry of Territorial Administration and Devolution to create a new Ministry of Decentralisation and Local Development, CLGF had a strategic dialogue with the new Minister Hon George Elanga Oban and his core team. The meetings discussed the potential for LED within the Cameroon system and to look for opportunities to integrate the CLGF programme of work more widely into the Ministry’s support for local development
Indicator 3.2: LED strategy development is underway in 9 local councils:
- In Zimbabwe 5 LED strategies have been developed and are currently being implemented in Makoni Rural District Council, Mutoko Rural District Council, Nyaminyami Rural District Council, Chipinge Town Council and Mbire Rural District Council. These were developed through process which included (1) orientation of Local Authorities and their stakeholders on LED, (2) setting up of multi-stakeholder LED forums in 5 Local Authorities, (3) undertaking local economic analysis, local visioning process and development of LED strategies.
- In Madhya Pradesh the cities of Jabalpur, Bhopal, Ujjain and Sajar are looking to align their Smart cities plans with the CLGF approach to LED with a specific focus on small, medium, micro enterprises (SMME) and wider support to the economic empowerment of their more marginalised communities.

Indicator 3.3: Mapping of citizen interface/ engagement completed in 13 target councils, as well as with the Madhya Pradesh State Rural Livelihoods Project (MPSRLP). Some key outcomes to date have been:
- For the work in Madhya Pradesh (India) in the rural councils the main stakeholders are women from different districts of Madhya Pradesh Self-help group (SHG) federations. To date, more than 250 women have taken part in LED orientation sessions, and in turn these members will be sharing their learning with 500 self-help groups from across the State (a total of +/- 7500 members). These women will be key leaders in guiding the council level work as the project moves forward.
- In Zimbabwe, through the Local Economic Assessment process stakeholder satisfaction was established and identified weaknesses were addressed during the development of the LED strategies.
Lessons identified this year, and recommendations for the year ahead linked to this output

An important lesson that CLGF has taken away from the first year of the project is the importance of tailoring work to each country. Whilst strategies to embedded LED may have been successful in multiple other countries in past projects, developing work programmes in a new country must always draw on local knowledge and expertise, on the current state of local government, the inter-governmental relationships and the socio-economic and cultural appetite for different kinds of interventions. Local partner knowledge is essential and involving a wide range of stakeholders at an early stage is very useful. However, it is also important to ensure this process properly manages partner expectations to align with budget and timeframes.

This project is able to draw on CLGF’s wide expertise and experience in LED, for output area 3 an important quick win has been drawing on regional project partners to share their experience with countries which are at a less advanced stage in institutionalising LED (for example to drawing on Swaziland and South African practitioners in the work in Zimbabwe). Peer to peer exchange is a valuable methodology for effecting change in practitioners and political leaders both at the local, but also at the national level.

Having local staff working in the regions continues to significantly improved CLGF’s ability to be responsive to its members and to respond quickly to issues as they arise.

Recommendations:
- CLGF should continue to involve project stakeholders in guiding the project over the course of implementation to ensure it remains tailored to the local context and it evolves in line with the changing political and social-economic priorities
- CLGF should continue to use LED practitioners from partner countries with experience of LED to share good practice and practitioner know-how

Output Title	CLGF acknowledged as a Commonwealth centre of LED learning and good practice.
Output number per LF		4	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Regional and global policy events highlight the effectiveness of LED as a means of achieving sustainable development	Strategy developed for targeting key policy events (July 2017) / One regional and/or global policy event highlights the effectiveness of LED as a means of achieving sustainable development (March 2018) / Awareness of the role of local government in LED raised at the Commonwealth Summit (April 2018)	Target exceeded: / CLGF developed a strategy targeting and implementing key policy events. / 2 global policy events highlighted the effectiveness of LED as a means of achieving sustainable development / (the 4th LED World Forum in Cabo Verde (Oct17) and the Commonwealth Local Government Conference (Nov17) in Malta). / CLGF was active both through its Secretariat and members at the Commonwealth Summit (CHOGM 2018). Speakers highlighted the importance of local government in LED and good governance in the Women’s Forum, the Business Forum and the People’s Forum, and in high level presentation to Foreign Ministers.
4.2 National actors capitalise on the Commonwealth's shared systems, structures, language and governance to successfully implement LED	CLGF Member survey on use and expected future need for resources and good practice on LED (Dec 2017) / Dedicated knowledge management strategy on resources and good practice on LED (March 2018)	Target met: / Survey developed and circulated to all members and results included into the dedicated knowledge management strategy. / Partnering with a number of Universities on research projects and looking at cities and local government impact on development (for example with Cardiff University On cites and economic development in post conflict communities)
4.3 CLGF’s knowledge hub has a sustained increase of quality LED-focused resources, reviewed on an annual basis with annual increases in the number of visitors to the knowledge hub on the CLGF website.	Visitors to the Knowledge Hub on the CLGF website increased by 10% on previous year (March 2018)	Target met: / 25.5% increase in August 17-July 18 period over the previous year
4.4 % of funding leverage against DFID contribution	10% of the DFID contribution leveraged (March 2018)	Target exceeded: +40% of the DFID contribution leveraged

Briefly describe the output and provide supporting narrative for the score

Indicator 4.1: CLGF’s new strategic plan highlights LED as a core focal area for advocacy and policy influence. A targeted overview of key events has been drawn up and CLGF headquarters and regional staff and members have been/are being mobilised to ensure coverage of key events.

CLGF was a lead member of 2 global policy events highlighting the effectiveness of LED, the 5th LED World Forum in Cabo Verde (Oct 2017) and the Commonwealth Local Government Conference (Nov17) in Malta. CLGF was invited to join the Executive Committee organising the 5th LED World Forum, made up UNDP, UNCDF, Cities Alliance, International Labour Organisation (ILO), United Cities and Local Governments (UCLG) among others. The Forum was attended by 2,800 participants from 85 countries.

At the Commonwealth Summit (CHOGM 2018) CLGF was present in the Women’s Forum, the Business Forum and the People’s Forum increasing awareness of the recognition of the role of local government in LED and good governance. CLGF also briefed Commonwealth Foreign Ministers of the key asks of the Commonwealth Associated Organisations.

Results: Beyond simply raising awareness of LED at the Commonwealth Summit, the outcome statement from the Women’s Forum explicitly calls on heads of government to “to promote and support women in economic development from the local to the national level”.

CLGF received an award from the Commonwealth Businesswomen's Network for its work in empowering women. The Award was been set up to recognise a Commonwealth accredited organisation that has made a significant contribution to supporting women’s economic empowerment and gender equality through its work, membership and governance. CLGF was recognised for its gender strategy, its Commonwealth Women in Local Government Network and its long term focus on women’s economic empowerment through its LED focused work across the regions of the Commonwealth. http://www.clgf.org.uk/whats-new/news/clgf-wins-award-for-womens-empowerment/

Indicator 4.2: CLGF’s member survey highlighted that 70% of respondents highly valued CLGF as a source of good practice, research and knowledge, and 63% of respondents had used CLGF to source knowledge products, good practice or research. More than 50% of respondents highlighted LED as an ongoing thematic priority along with localising the SDGs, decentralisation and development, women in local government, cities and urbanisation and climate change and resilience.

Indicator 4.3: CLGF continues to increase the number of high quality resources on local economic development within CLGF knowledge hub and its online resources. Over the period 1 July 2017 – 30 June 2018, online views of CLGF local economic development knowledge products has increased 25.5% over the previous year. A dedicated knowledge management strategy on resources and good practice on LED is in the process of being finalised.

Indicator 4.4: CLGF has signed a €1.9million project contract with the EU Delegation in Zambia for targeted work with local government aligned to the DFID project objectives giving significant extra resources to role out LED across the country. In Madhya Pradesh (India) 90% of the cost of the LED orientation activities were covered by the State Government (CLGF provided the expertise or programme content and the State provided the travel, accommodation and meeting space and materials). CLGF is in the ongoing process of negotiating co-funding, in-kind support, complementary actions and partner investments across the project work at all levels.

Lessons identified this year, and recommendations for the year ahead linked to this output

CLGF’s global activities and advocacy have had an important impact on the effectiveness of CLGF as a Commonwealth organisation. A strong focus on evidence-based policy making, and drawing on the good practice of its projects and programmes, as well as that its wider membership, has real impact with the Commonwealth and the international community. The results achieved in this first year reflect the benefits of a strategic approach focused on a LED (specifically in this 1st year, LED as a methodology for achieving the SDGs and strengthening women’s economic empowerment) and the recognition of CLGF as leader in this area. CLGF should continue to profile this expertise and the outcomes of the country level work towards Commonwealth and international bodies as the project moves forward to maximise the wider impact of the country and council level successes.

The experience of running the CLGF member survey was a useful input to ensuring the priority focal areas of the organisation are aligned with the needs and interests of the Commonwealth local government community. Both survey feedback and the increased usage of the CLGF knowledge show that the organisation is providing useful and well targeted knowledge products to its members and partners.

A key lesson that CLGF has seen in past projects, and which is again relevant in this project work is how with some base funding to provide strategic support to local government CLGF and its members and partners can leverage significant additional funding to work towards goals at both the local and national level, based largely on CLGF and its partners being able to demonstrate a track record and the value of the work being undertaken on the ground.

Recommendations:
- CLGF should continue to ensure it is present and actively feeding into key Commonwealth and international policy discussions and events on LED, the SDGs and women in development to continue to influence these agendas and build knowledge and awareness of the role of local government in delivering development.
- CLGF should continue to draw on the research outputs of its academic partners to feed into its programme of work both in projects and advocacy.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The theory of change builds on the lessons learned from DFID’s earlier programme of support. The project will provide local government organisations with the skills, capabilities and support needed to design and deliver strategies that provide the environment needed for local economic development and create a series of bankable projects that will leverage additional investment. The project will focus on fewer countries but in greater depth, looking to demonstrate replicability by investing at scale.

CLGF’s Theory of Change

At this stage in the delivery of the project, the theory of change remains valid. There are no plans to make any changes to the expected outcomes or commitments to gender equality.

CLGF remains committed to good practice in the management and delivery of its programmes and projects and has adopted a new gender strategy to guide its work and operations. The organisation has also updated its safeguarding policy.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The project is on track, meeting all of the output milestones set out in the log frame; and in some cases looks set to exceed them.

Explain major changes to the log frame in the past year
There have been no changes to the log frame.

Describe any planned changes to the log frame as a result of this review
The project is currently on track with the milestones within the log frame and these remain realistic. There are no proposals at the current time to change or revise the log frame.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

The Business Case and the report of the previous programme both emphasise the importance which CLGF places on securing value for money across all its activities. In line with the Business Case, the organisation is following an agreed procurement policy based on securing best value for money on all purchases and services. Where appropriate, CLGF members and partners also provide significant in-kind support to the project eg in hosting CLGF regional offices and staff (Southern Africa), by making available meeting space for key project-related events and meetings, eg recent launch of the LED guidelines in Zambia, or by contributing their own funds to the delivery of project activities, such as through alignment with the State Rural Livelihoods Mission in India.

CLGF continues to work to identify ways to leverage DFID’s contribution to strengthening local economic development in the Commonwealth, through identifying opportunities for partnership and cooperation.. In Zambia, CLGF successfully negotiated 1.9million Euros of EU funding for a project that focuses on strengthening decentralisation, including significant additional resources to directly support and strengthen the national roll-out of LED.

CLGF engages in very little direct procurement of goods and services, however, procurement processes are in place throughout the project and include competitive bidding when specialist services are required for any purchases. As a membership organisation with an extensive network of members and partners, CLGF identifies and mobilises technical expertise and capacity at low or no-cost to the project. In addition to ensuring that the project can draw on experienced and skilled expertise with experience of working in the local government sector, this also helps to strengthen Commonwealth links and partnerships at the local level.

CLGF has sought to ensure that wider Commonwealth policy also takes account of the importance of local economic development. At CHOGM, CLGF was able to address Foreign Ministers on behalf of the associated Commonwealth organisations, who are seeking a more strategic partnership with the Commonwealth Secretariat to strengthen policy implementation across the Commonwealth. CLGF was successful in including reference to LED and local government in the outcomes statement of the Women’s Forum.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The programme is delivering VFM and should continue as planned.

CLGF remains committed to the principal of using this programme to leverage funding to expand its impact and value for money and to demonstrate that all alternative sources of funding are available. Over the life of this programme they have committed to leveraging complementary support to the value of 65% of the DFID contribution (approx. £2.5m).

As an associated organisation officially recognised by Commonwealth Heads of Government and with an engaged membership, CLGF remains well-placed to influence policy development and provide a lead on democracy and good governance issues at local level. CLGF continues to demonstrate it has the convening power needed to ensure the buy in and commitment of the political and technical stakeholders and partners that are essential to the success of this programme. It remains extremely well-placed to share the best practice and results being developed under this programme and, in doing so, to influence national policy development.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The overall original risk rating for this project was LOW, and following the 1st year of implementation it remains LOW.

The Business Case reflects that the main major risk to the success of this project is political change in implementing countries, and the resulting potential for change of direction within national and/or local administrations. Other risks included: staff turnover and a lack of delivery capacity in LGAs and pilot councils

To mitigate these risks CLGF has been working to build buy-in to the project across the political spectrum in each country, as well as a wider more general cross-Commonwealth buy-in to LED as a methodology for delivering sustainable development. It has also been taking a flexible approach to the development of workplans in each focal country in close partnership with a range of stakeholders so as to ensure a wide base of support for objectives and activities. These have been effective and CLGFs pro-active engagement and pragmatic approach to adaptive management mean the residual risk remains low.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

The programme builds on a previous pilot programme. CLGF has seamlessly transitioned between the two programmes and is delivering on time with no slippage

Regular meetings and communications between CLGF and the project team in United Nations and Commonwealth Department ensure DFID is kept abreast of developments and day to day project management issues. The teams have collaborated closely on the financial management and quarterly reporting of programme expenditure recognising that the relationship is now governed by an Accountable Grant mechanism rather than a Memorandum of Understanding. The new system has bedded in well and increased the visibility of financial management and the links to project deliverables and outcomes.

Date of last narrative financial report(s)	22/1/18
Date of last audited annual statement (s)	31/3/16 (taken from previous Project Completion Report as annual statement not yet available for 2018)

G: MONITORING, EVIDENCE & LEARNING (

This has been a desk based Annual review drawing on formal project reporting, regular meetings and discussions with the CLGF project team and discussions in the margins of other Commonwealth meetings with other stakeholders. CLGF has provided a full set of documents developed as part of the 1st year of the project (including concept notes and framework documents for national project workplans, meeting report, outcome statements and publications).

The main recommendation for next year is that the UNCD Deputy Programme Manager responsible for the CLGF programme should join the CLGF team for a field visit to see programme activity on the ground in advance of the next Annual review (due in July 2019)

Monitoring

The project log frame is the main instrument for monitoring progress. CLGF has its own in house annual overview tool which is used to track progress against upcoming milestones at a national, sub-national and cross Commonwealth level. This captures both progress to date and upcoming actions, as well as the means of verification and possible issues to address on reporting. CLGF holds monthly meetings, through Skype bringing together its London project team with the regional project coordinators. The overview tool is used as a guide for those coordination calls to share advances and discuss opportunities for cross regional coordination and good practice sharing and learning.

CLGF reports to DFID on a quarterly basis, in the form of quarterly progress reports and an annual report which assess the project’s progress against log frame milestones and objectives. DFID also undertakes an annual review of the work. The annual CLGF Executive Committee meeting (normally held in November in London), provides an important opportunity to review the project achievements and discuss its future direction.

Learning

CLGF’s dissemination strategy provides an overview of the organisation’s approach to knowledge, lessons and good practice sharing within programme partners and stakeholders, as well as to its wider membership, the development community, and academia.

An important learning aim for CLGF over the next two years of the project will be developing tools that support local governments to assess the strengths and economic potential of their local communities so as to more confidently present these to financial institutions and the private sector. The project will also look to draw on the pilot council work in developing bankable projects to produce guidelines and advice for local government more generally to undertake these processes.

Progress on recommendations from previous reviews

This is the 1st annual report. No recommendations were made prior to this report.