Annual Review (AR) - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Somaliland Development Fund (SDF)
Programme Value: Overall £ 52.4 m		Review Date: December 2017
Programme Code: / 202946	Start Date: December 2012	End Date: September 2018

Summary of Programme Performance
Year	2013	2014	2015	2016	2017
Programme Score	A	A	A+	A+	A
Risk Rating	Medium	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review
Strong and stable progress, delivering some impressive results and meeting key milestones that build on Somaliland’s stability and prosperity, despite challenging context (politically and financially). Some useful lessons for SDF 2 such as impressive infrastructure results, delayed social service provision, and value for money being higher and yet do no harm risks being much lower in high population urban areas.

The 2016 SDF AR states that: “The SDF is acknowledged by the Government of Somaliland as one of the best performing multi-donor funds contributing to the Somali New Deal architecture. The year in review (2017) presented a set of predictable challenges – such as the Presidential elections – which were captured and mitigated using DFID’s enhanced risk matrix in close collaboration with the SDF secretariat, Mott MacDonald (MM), and in many cases adapted to challenging contexts. And unpredictable challenges not experienced in previous project years – such as the freezing of Danish funds and significant foreign exchange fluctuations affecting the overall budget.

Presidential elections scheduled for 27 March 2017 were postponed to 13 November (having already been postponed from 2015) ostensibly due to the regional drought. This postponement brought a strong reaction from Denmark who withheld 40% (£2.2m) of its 2017 contribution (£5.5m) in remonstration. This, together with foreign exchange rate losses, reduced the available funds by £3.8m to £34m by December 2017. The election also created considerable political uncertainty, an increase in small pockets of heightened conflict (including in project areas), and a slowdown in day-to-day business. All major decisions were taken with Government before many of the Ministries effectively ground to a halt in August.

Following the Presidential elections in November 2017, Denmark released £1.2M in December 2017 to the SDF. The balance will be used for SDF2 which will start in mid-2018.

However, despite these challenges, the SDF continued to deliver strong results. Infrastructure results were implemented on time and on budget, especially in the roads sector. In addition, this review finds that the government ownership of the SDF remains steadfast and the ‘SDF brand’ is held in high esteem. This includes in the media and in all high level engagement with the Government, such as Minister Stewart’s visit in August 2017. SDF beneficiaries and stakeholders continue to express satisfaction with the governance and operational arrangements of the SDF, including the services provided by the SDF secretariat, Mott MacDonald.

Progress
The majority of projects (all except three) are drawing to a close, and the majority of output milestones for the year were met or exceeded. Results and financial forecasts were met in the roads, agriculture and livestock sectors including enhanced community engagement which has enabled the SDF to realise commendable results. This testifies to the resilience, responsiveness and adaptability of the SDF in such a challenging context. Formal closure of projects is on-going with strong systems around asset management, especially vehicles to be re-used in SDF 2. A testament to its success, SDF donors (including Denmark and Netherlands) have committed to similar levels of financial support for SDF2, which will become active in the last quarter of 2018. Although the newly elected President and his Cabinet have only been in existence since December, early statements from the Government endorse the second National Development Plan and the funding of its priority projects under SDF2.

Areas of slower progress
However, the issues above did cause some challenges, delays and impact on results. The Joint Steering Committee (JSC) spent considerable time in Q.1 analysing the overall portfolio and taking difficult decisions to freeze on-going projects. The following projects were postponed until SDF2:

Ministry	Component	Value (£ m)
Water Resources	Berbera immediate measures	0.4
Water Resources	Borama Civil and Electromechanical works	0.4
Health	Las Anod Hospital - essential drugs and equipment	0.22
Health	Las Anod Hospital – hospital management contract	0.52
Fisheries	Construction of Maydh Jetty	1.9
National Planning	Communications Hub	0.19
Others	Reduction in admin expenses	0.19
	Total	3.82

The most significant of these in terms of impact on results and VfM is the construction of the jetty in Maydh, a key project in the Sanaag region (see output 2). The planning and design of the jetty required intensive technical inputs from several contractors and the freeze will represent a downward trajectory in value for money if the SDF 2 does not pick up this project as recommended by the JSC.

In April 2017, the Netherlands agreed to provide an additional £0.89m towards a wellfield collector needed to enhance the Hargeisa water network. This element, which required significant additional technical design, is unlikely to be fully completed within SDF 1.

The health and education projects in the Sool and Sanaag have proved the most challenging. A key lesson for SDF 2 is that the health and education sectors do not fit neatly into the existing SDF approach and the project management teams struggled to deliver against the original designs. The national planning commission might consider standalone project finance for the health and education sectors in the future rather than the SDF 2.

Given the level of disruption to day-to-day business and the complexity of some of the remaining projects (health, education and HWA), a no cost extension was approved for Mott MacDonald. This approval means that Mott MacDonald’s contract which was to lapse in March 2018 has now been extended to September 2018. This extension will enable Mott MacDonald to complete the three projects mentioned above as well as facilitate a seamless transition from SDF phase 1 to SDF phase 2.

The extension will also allow sufficient progress against previous AR recommendations (where relevant), and lessons from 2017:
1. Engagement with line ministries: the critical factor being perceived delays in SDF implementation, notably planning and governance arrangements. The key lesson over the SDF lifetime has been that once SDF partners are fully orientated with the international standard methods and procedures developed by the SDF, complaints around delays tend to die down.
2. More in depth community engagement: despite undertaking fragility, conflict and social impact analyses across all new projects the Qool Qaday livestock holding ground and the Fiqufiliye water supply projects witnessed localised conflict during implementation. Some of this relates to legal authority and jurisdiction, others to participation and adoption of an integrated approach. In any case, GoSL must allow sufficient time for participatory planning and more in depth consultation. The implementing partner must adopt a conflict sensitive programming approach with regular conflict audits scheduled to monitor the adherence of projects to the framework. The implementing partner must ensure community consultation and acceptance is fully grasped and internalised prior to project proposal development, including buy-in of key local stakeholders.
3. Government and the SDF: the aspirations of the New Deal are to increasingly use country systems. This has not been realised in Somaliland. The SDF was designed to be transferrable to country systems providing adequate safeguards were in place. The reasons for this not taking place – stalled core reform processes – have been discussed elsewhere.
4. Financial Climate: exchange rate movements led to the loss of approximately 10% of the SDF value leading to reprogramming of activities. The conclusion towards the end of the SDF is that there is little the SDF donors, secretariat, or recipient Government can do except to adapt the portfolio to exchange rate losses.

Lessons for SDF 2
- Constant orientation and induction with new Ministers, and better engagement with the national planning commission that sits above individual Ministries. Both can play an important conduit role.
- Develop a realistic strategy for progressive use of country systems in tandem with the need to deliver results. The resuscitation of the public financial management and civil service reforms will be the deciding factor around the pace of greater use of country systems.
- Future SDF roads and urban water projects should require government to deposit agreed maintenance funds in a special account.
- The drought has impacted on project outputs but we have no specific report that collates and analyses the impact across the whole programme. The inception phase of SDF 2 must draw on the research from the Sheikh Vet college and produce recommendations for supporting the resilience of communities and their livestock to persistent drought.
- SDF has demonstrated economy by using a high number of national and regional consultants and suppliers with a focus on building local capacity. 78.5% of SDF contracts were awarded to national consultants and companies creating local jobs and opportunities.
- Feedback from beneficiaries could improve from an inclusion angle – e.g. disability, clan and gender – and mirror the rich feedback from improved roads beneficiaries who responded with “reduced public transport fares by a third as well as ease of access to various destinations – market, schools and hospitals.”

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202946/documents/
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202946/documents/

# Summary of Programme
In December 2012, DFID approved the £20m Somaliland Development Fund (SDF) designed to support the Government of Somaliland to rebuild critical infrastructure, deliver basic social services and build the capacity of Government of Somaliland (GoSL) to implement projects under the 2010 National Development Plan (NDP). Strong ownership and coherence by SDF donors was in line with New Deal principles. The SDF was jointly created by DFID and DANIDA and by 2015 it had also attracted funds from the Norwegian and Dutch Governments.

The NDP was estimated at £900m ($1.2bn), but the SDF only had limited resources of £30 -37m over a 3-year period. Therefore, in February 2013, DFID/DANIDA contracted consultants to help the GoSL identify top priorities from the NDP, eligible for SDF funding. At the same time DFID/DANIDA ran a procurement exercise to identify and contract an international fund manager. The tender was won by Mott MacDonald who mobilized in September 2013. The SDF is directed by the GoSL and donor Joint Steering Committee (JSC) supported by the SDF Fund Manager and staff from the Ministry of National Planning and Development and the Ministry of Finance. Sectoral oversight is provided through GoSL Project Management Boards. Project Management Teams located in line ministries are the loci for project planning, implementation and monitoring activities. A range of national, regional and international contractors have been awarded contracts.

Significance of the SDF to date in the Somaliland context
In addition to the explicit project results reported on in this document, we also note that the SDF has demonstrated that a multi-donor fund supporting service delivery and owned by government could be established, implemented and completed in Somaliland, within four years. Since this is the first time Somaliland has benefited from such a fund, we should not overlook this pioneering initiative and the achievements of the JSC, GoSL ministries and departments, contractors all assisted by the SDF Manager Mott MacDonald (MM). The SDF continues to strengthen the state-citizenship contract and enhance accountability and domestic revenue generation leading to more stability and prosperity in Somaliland. The SDF’s support in enhancing core state capacity strengthens state–building making greater use of government systems and processes. It is worth noting that MM also had to develop and introduce ground-breaking implementation systems and procedures in a country largely unfamiliar with donor-funded programmes and lacking suitably robust country systems for planning, procurement, M&E, accounting and audit. There has been nothing like the scale and depth of the SDF in the history of Somaliland. Although, MM has global experience and depth, they still had to adapt, align and customize their corporate and donor standard systems and processes with the unique Somaliland situation, overcoming among others security, banking, transport and logistics issues.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Despite setbacks causing delays in implementation in 2017, the SDF will achieve most of its remaining results against revised milestones for 2018. The major outlier being the expected overrun of the well field collector project with the Hargeisa Water Authority and social services projects in Sool and Sanaag.
Outcome / Indicator 1	Baseline / (2013)	Milestone / 2017	Achieved 2017	Progress
Number of beneficiaries of services attributable to SDF supported projects	Actual: 0	199,200	113,147	Target not met. Availability of funding affected progress on achieving the 2017 milestone target. Denmark freezing its finance significantly slowed delivery in 2017. Cumulatively, 1,438,321 beneficiaries have been reached exceeding the cumulative target of 1,347,734 by March 2018.
	Cumulative: 0		1,438,321
Outcome Indicator 2	Baseline / (2015)	Milestone / 2017	Achieved 2017	Progress
% of citizens reporting improved service delivery in government sectors supported by SDF.	33%	55%	50%	Target not met. Lower perceptions were registered because the Hargeisa water system is still on-going. Cumulatively, citizens’ perceptions on three services (urban water in Hargeisa, roads and agriculture) have changed from 33% in 2015 to 47% in 2016 to 50% in 2017.
Outcome Indicator 3	Baseline / (2014)	Milestone / 2017	Achieved 2017	Progress
Average effectiveness and efficiency of SDF-supported GoSL Ministries and Agencies (Score 1-6)	4.0/6.0	5.0/6.0	5.2/6	Target met. A limited ex-post survey conducted in November 2017 reported an overall rating of 5.2/6.0 which exceeds the target.

Aggregate Output Score and Description
Output	Score
Improved water and road infrastructure to promote economic and socially equitable development	A
Improved productive sectors enhancing incomes, food security and livelihoods	A
Enhanced citizen perception of Government priorities, activities and expenditure	B
Improved capacity to prioritise development objectives and to plan and budget development activities under the SDF Programme	B
Improved health and education facilities to provide social services (Secondary health care and education	A

Has the log frame been updated since the last review?
The log frame was reviewed in August and approved in October 2017. The log frame includes a new output (Output 5) to cater for the health and education projects. Some indicators were redefined and milestones lowered following the ‘freezing’ of Denmark’s final allocation.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved water and road infrastructure to promote economic and socially equitable development.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Milestone 2017	Achieved 2017	Progress
Output Indicator 1.1: Quantity of water per day available for distribution in urban water systems with SDF support.	N/A	400 m3/day	207 m3/day	Rated C: By the end of 2017, 207 m3/day of water was made available for distribution through the expansion of the Burao water supply system. The expansion included the construction of a 9km water pipeline connecting two boreholes in Burao. Cumulatively, 5,858 m3/day has been reached against an overall target of 8505 m3/day (69%). The delayed Hargeisa Water Agency’s wellfield will enable approximately / 5,000m3/day to be introduced into the system but unlikely by the end of phase 1.
Output Indicator 1.2: Number of rural water points constructed or rehabilitated with SDF support.	N/A	125 points	72 points	Rated C: A total of 72 water points were constructed in 2017. Insecurity in the Sanaag region slowed progress in the construction of additional 53 water points in Figifuliye and Kulaal regions. Cumulatively 141 water points (85%) have been constructed to date.
Output Indicator 1.3: % change in travel time on roads rehabilitated with SDF support.	N/A	25%	35%	Rated A+: A 35% reduction in travel time was achieved against a milestone of 25% following the rehabilitation of Hamas towards Hargeisa road (25 km).
Output Indicator 1.4: Length of roads rehabilitated to all weather condition with SDF support.	N/A	20 km	26.5 km	Rated A+: The rehabilitated Hamas section of the Hargeisa – Berbera road achieved 26.5km against the planned 20km. The cumulative length of roads rehabilitated to date is 146.9km (123%). This includes the Lafaruk – Berbera – Sheikh road (99.3 km) and Kalabaydh – Dila road (21.1 km).

Key Points
The overall rating of this indicator is A. This output achieved mixed results. The output targets were partially met with the two water related outputs scoring C and the two roads outputs scoring A+.

Under output indicator 1.1, an overall cumulative of 5,858 m3/day has been reached against an overall target of 8,505 m3/day. The balance will be met by the completion of the HWA wellfield collector and connection of the Burao eastern and western tanks in 2018. However, during the course of this AR it is becoming clear that i) constant delays caused by unpredictable donor financing, ii) UN-HABITAT estimates for the wellfield collector exceeding available SDF finances, iii) additional validation of designs by MM, and iv) delays agreeing to the procurement process by HWA mean that this project may not be fully completed by the closure of SDF 1. The Burao eastern and western tanks were not connected in 2017 due to importation delays of connection fittings which were in turn due to insurance restrictions associated with Somaliland when importing goods from the UK.

For output indicator 1.2, a cumulative total of 141 water points against a total target of 165 representing 85% of overall target had been constructed. The balance is expected to be completed in 2018 when the Burao and Kulaal and Fiqufiliye – 53 water points expected – are completed. In 2017, a total of 72 water points mainly contributed by MoA – 16, MoWR and 30 and MoL – 26 were completed. These unforeseen delays were reported in a timely manner to the JSC throughout the year, but shines the light back on original designs and the skills within the Ministry of Water’s project management team.

For output indicator 1.3, a 35% reduction in travel time was achieved against a target of 25%. The rehabilitated Hamas section of the Hargeisa – Berbera road achieved 26.5km against the planned 20km. The cumulative length of roads rehabilitated to date is 146.9km against a target of 119.2km representing an increase of 123% against the target. Road safety and maintenance remain key issues for the roads development authority to internalise and will be picked up in SDF2.
Summary of responses to issues raised in previous annual reviews:
1. The well field collector (WFC) needs to be installed on the outskirts of Hargeisa: Procurement of supplies for the WFC is ongoing and will be completed in March 2018. The procurement was split into two lots; Supplies (of pipes and fittings) and Works (installation). Construction of the WFC will commence around April/May 2018. Again, the SDF took on uncompleted works from the EU programme which meant an element of re-design as MM inherited Fitchner designs.
2. The RDA should operationalise the road maintenance policy and roll out the road maintenance guidelines detailed in the Roads Act still pending with Parliament: Marking with white lines and other safety measures of all SDF funded roads commenced in October as part of the maintenance programme and increasing safety on the roads. This is expected to be completed by Feb. 2018.
3. In the final year of the SDF it is important to map the partners who are working in the same urban water locations as the SDF to ensure that hygiene interventions are complementing our mainly infrastructure outputs: Key WATSAN donors meet regularly to report on activities in support of the HWA. This is one of the most constructive donor coordination groups active in Somaliland – including UNICEF WB, KfW and GiZ – and an important structure to engage with during SDF2.

Summary of recommendations for the next year:
1. Urgent attention to completing as much of the WFC works in SDF 1, and agreement on an approach to handover remaining works – especially the liability from the current SDF secretariat to the new SDF 2 secretariat.
2. Donor coordination should improve and consider common WATSAN international standards for equipment and construction.
3. GoSL commitment to planned maintenance of roads has been weak. Any future SDF roads should require government to deposit agreed maintenance funds in a special account.

Output Title	Improved productive sectors enhancing incomes, food security and livelihoods.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revise since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Milestone / 2017	Achieved 2017	Progress
Output Indicator 2.1: Productivity of staple food (Sorghum) in Marodijeex Upper Catchment.	1.0 t/ha	1.0 t/ha	Data not available	Not Rated: A limited yield estimate by the Aburin dryland agriculture research centre found the production of sorghum at a highly impressive 2.5 t/ha in Maroodijeeh catchment area.
Output Indicator 2.2: Number of hectares of land conserved or rehabilitated (for both agricultural and livestock use) with SDF support.	0	11,000 / Hectares	11,000 / Hectares	Rated A: In 2017, the area conserved for agricultural and livestock use through watershed management was 11,000 ha (6,000 ha in Maroodijeh and 5,000 ha in Aroori). Cumulatively 32,783 ha of land have been conserved against a target of 31,688.
Output Indicator 2.3: Number of Animals accessing Aroori Livestock Holding Ground and associated services (monthly).	0	30,000	22,323	Rated B: All infrastructure in the Aroori LHG was completed and started functioning from November 2017. The number of animals (camels and shoats) accessing water and veterinary services over this first month was recorded as 22,323.
Output Indicator 2.4: Quantity of cubic meters of water per annum available in rural areas for Livestock with SDF support.	0	97,876 m3	136,133 m3	Rated A++: 136,133m3 of water has been made available through rehabilitation of 16 small earth dams (balleys) in Maroodijeeh Upper Catchment (16) and Aroori livestock holding ground (7). Cumulatively 217,083 m3 of water has been availed representing 137% above the target of 158,399 m3.
Output Indicator 2.5: Number of cold storage and ice making facilities constructed to improve fisheries supply chain mechanisms	0	3	3	Rated A: Three cold storage facilities were installed in the sites of Maydh, Hiis and Lasurwayn. The tonnage of fish per day processed by the facilities is 1.5 tonnes.

Key points
The overall rating of this indicator is A. The majority of milestones were met, although the results for the Aroori LHG were reported at the year end and should be treated with caution. The indicator on sorghum production will be verified with data from Food Security and Nutrition Analysis Unit (FSNAU), which is yet to be available (expected 1st Q 2018). Key informant interviews during the perception survey indicated that SDF support to Aburin research centre was well received and the farmers’ training and agriculture extension courses have resulted in better farming practices which are likely to increase sorghum yields.
The cumulative indicator on land conserved under the MoE&RD, MoL and MoA is currently at 32,783 hectares, which is 3% above the overall milestone. In 2017, 11,000 ha were conserved mainly through soil and water conservation activities.
The Aroori LHG indicator includes the construction of balleys, fodder production, reseeding of grazing land and access to veterinary services through animal health posts. This is rated B because, despite the infrastructure being completed on time and against all the odds – see the SDF financed RVI Land analysis in 2016 – the LHG only started to function from November 2017 and serviced 22,323 animals. It is important to record that the management of this LHG needs to be taken forwards by the Ministry of Livestock and finance provided from the national budget to manage the LHG as designed.
The cold storage indicator was met through cold storage facilities in Maydh, Hiis and Lasurwayn. This improved fish supply chain management as well improved storage with 1.5 tonnes of fish per day processed through these facilities. This was supported by cooperatives training with participant feedback including improvements in terms of cooperative management skills, better understanding of the fishing sector which has encouraged the acquisition of more boats and expected enhancements to local incomes.
Summary of responses to issues raised in previous annual reviews:
1. The Aburin research centre crop yield production data that was used for Indicator 2.1 needs to be cross checked with FSNAU data for validation. In the 13th QPR, the yield was reported as 0.8 t/ha for validation largely because of the drought experienced in late 2016 and 2017.
2. The conservation and environment restoration projects are quite thinly spread. This makes monitoring and quality assurance a challenge: The MoL, MoA and MoERD reported that they have considered this in relation to the new NDP2, and any subsequent phase will consolidate and scale up successful sites.
3. Retain both a qualitative and quantitative milestone for the Aroori LHG for 2017: Log frame indicator 2.3 was revised and both a qualitative and quantitative milestone retained.

Summary of recommendations for the next year:
1. Include a sustainability indicator for the LHG to cover operating costs, procedures and capacity.
2. All future projects related to land restoration, rangeland and watershed management projects should be at least three years in implementation to allow for full participation and buy-in by the communities.
3. MM to provide a break down in its data on usage of the cold storage facilities usage and qualitative reporting on maintenance protocol operationalised by mid-2018.
4. Ensure the Ministry of Agriculture institutionalises the Aburin research and training centre for future rain fed agriculture activities. Develop an outreach and communication strategy to share knowledge and results in other regions. LAMPS review of the sorghum yield once FSNU data is available.
5. Land selection criteria – consider and adopt the recommendations of the RVI land study for selection of new sites in order to do no harm and reduce the potential for localised conflict.

Output Title	Enhanced citizen perception of Government priorities, activities and expenditure
Output number per LF		3	Output Score	B
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline (2015)	Milestone 2017	Achieved 2017	Overall Target	Progress
Output Indicator 3.1: % of people who report improved access to potable water in Hargeisa	2%	30%	7%	50%	Rated C: The % of residents that reported improved access to water stagnated at 7% during the 3rd indicator survey carried out in October 2017. Residents without access to HWA water do not think that access to water is improving.
Output Indicator 3.2: % of people who report improved journey time on SDF rehabilitated roads	5%	92%	87%	95%	Rated A: 87% of respondents in the SDF supported project areas of Hargeisa, Berbera, and Dila reported reduced travel time during the 3rd indicator survey carried out in October but on the same stretch of road.

Key points
This output is rated as a B. Output 3 indicators focus on water (HWA) and roads (RDA) projects perceptions by users. Under indicator 3.1, the third perception survey, showed that citizens’ opinions on access to adequate water to the residents of Hargeisa had decreased from 20% in 2016 to 7% by the end of 2017. This result is statistically significant. Fewer people who are reliant on private water bowsers, and expect much cheaper HWA water, think that access to water is improving. Qualitative interview data shows that residents of Hargeisa are not happy with the cost, quality and quantity of water supplied in the city. Though HWA sells a cubic metre of water at £1, many residents pay up to £5.2/cubic metre of water from private sellers who truck water from privately owned boreholes. Until the SDF funded projects start to deliver water to households, opinions are likely to remain negative. The SDF has invested heavily in HWA supply improvements, however, the delays that citizens are rightly frustrated by have been caused by: i) two uncompleted EU funded projects, ii) slow progress in the construction of the transmission pipeline by UN-Habitat, and iii) frozen Danish finance at the start of 2017 which lost at least three months of design and procurement time. By contrast, the roads perception survey reported the decrease in travel time improving from a baseline of 5% to a high of 92% in 2016. A slight decline from 92% to 87% was recorded in 2017. This can be attributed to the fact that in 2017 the survey focused on the same road rehabilitation area which did not register to the beneficiaries as new. Positive feedback from roads beneficiaries includes reduced public transport fares by a third as well as ease of access to various destinations – market, schools and hospitals.

Summary of responses to issues raised in previous annual reviews:
1. The perception surveys for the water and agriculture projects should be maintained, and include additional questions relating to the impact of drought on the SDF’s investments: Qualitative questions were incorporated in the survey. During the survey, the effects of the drought were ending with good Deyr rains. However, the impact of drought on crop production and livestock was still evident with most of the families reporting loss of their entire crop and most of their livestock.
2. Increase awareness campaigns on the safe use of the new road infrastructure to mitigate unintended outcomes such as loss of life and livestock because of excessive driving speeds: Communications hub together with RDA developed messages for safety awareness and tips. Development of products for broadcasting via radio and TV is ongoing, as are road markings.
3. Roads signs which have been removed/destroyed should be replaced: No budget was allocated for this recommendation and was thus not implemented. RDA has committed to allocate funds for this activity during the next budget in 2018.
4. The 2017 target for indicator 4.2 on “% of people who report improved journey time on SDF rehabilitated roads” should be revised because no further improvements are expected in SDF 1.

Summary of recommendations for the next year:
1. A comprehensive study on the status of roads in Somaliland (all classifications) should be conducted by the RDA and a road sector development and maintenance strategy developed and financed via the national budget.
2. The (road) materials laboratory earns revenue from a number of private contractors who pay for testing and certification. This should be written up as a case study and finances logged transparently.
3. The drought has impacted on project outputs but we have no specific report that collates and analyses the impact across the whole programme. This should be included in the SDF 1 final report and drawing on the research from the Sheikh Vet College, with recommendations for supporting the resilience of communities and their livestock to persistent drought.
4. More creative effort should go into branding SDF roads. The result of this effort should mean that SDF investments – especially roads – should be known to be an SDF investment, in the same way as the railway in Ethiopia is known to be a Chinese investment.

Output Title	Improved capacity to prioritise development objectives and to plan and budget development activities under the SDF Programme Expenditure
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline / 2014	Milestone / 2017	Achieved 2017	Progress
Output Indicator 4.1: / SDF Programme average aggregate disbursement deviation from forecasts.	5%	9%	11%	Rated A:
Output Indicator 4.2: / SDF Programme average time from approved concept note to approved project proposal.	0	No further concept notes and project proposals expected	No further concept notes and project proposals expected	Not Rated: No new concept notes or project proposals were developed in 2017.
Output Indicator 4.3: Number of SDF projects executed on time and within budget by PMTs.	0	7	3	Rated C: Three projects were completed within expected completion timelines.

Key points
This output is rated as a B. The programme disbursement deviation indicator delivered an 11% deviation against a 9% target. This is still an impressive result in such an unpredictable (politically and donor financing-wise) year. Delayed clearing of goods (construction materials) at Berbera port affected implementation delivery in the field and, despite being an in-year surprise, was caused by the change of management of the Port from the parastatal Ports Authority to Dubai Ports World. This, coupled with the electioneering period, witnessed banks unwilling to extend credit facilities to contractors which affected contractors’ access to liquidity and hence their ability to pre-finance construction activities. Denmark froze 40% of its 2017 funding which led to some activities being postponed until SDF 2. All of which affected planned disbursements significantly. No new concept notes were developed in 2017 so this indicator is not rated. Under the project execution indicator two water (one urban and one rural) and the health and education projects were not completed on time because of procurement, budgeting and security reasons. The delayed projects have been formally granted a time extension by the JSC.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. In July 2016, it was recommended that SDF allocations for 2017 projects be disaggregated and provided directly to the planning and statistics department in the Ministry of Finance: SDF allocations were shared in May 2017. The last SDF figures were shared with MoF in September 2017, but SDF financing remains outside of the government budget and further work to be ‘in budget’ needs to be done, including improved engagement with the national planning commission.
2. Engage with the MoF budget department to ensure that the running costs for the health and education facilities in Sool and Sanaag are included in the 2019 budget: Running costs will be fully covered by the SDF1 up to September 2018. The GoSL will be expected to gradually budget for these running costs from 2019, and fully from 2020 onwards. Pragmatically the JSC has been waiting for a new administration to formalise this.
3. Discuss a way forward with RVI to present the Land analysis to a Ministerial panel and ensure political parties and civil society are aware and inspired to use this analysis to draw up a Land Policy. The Land analysis will be presented to the incoming government.
4. No further work should take place on the incentive fund concept in line with recent IAD recommendation: No further work was undertaken.
5. Any subsequent phase of the SDF should re-design the incentive fund based on political economy analysis and the status of the WB PFM programme: Recommendation does not apply for the current SDF and is for future programming.

Summary of recommendations for the next year:
1. Re-engage with the new Ministers of Finance and Planning to ensure exchange of data and information between SDF secretariat, PMTs and MoF / MNP&D.
2. Prior to the 2019 budget, work with MoF on recurrent cost liabilities and O&M for SDF investments. The indicator of success will be their inclusion in the budget call circular.
3. Present the RVI Land analysis to new President and request nomination of a government champion.

Output Title	Improved health and education facilities to provide social services (secondary health care and education)
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline / 2013	Milestone / 2017	Achieved 2017	Progress
Output Indicator 5.1: Number of School buildings renovated/ constructed and equipped in Sool and Sanaag	0	40	28	Rated C: Construction work for Dayaha and Las Anod secondary schools slowed as insecurity rose around the Presidential elections. 28 school buildings (5 in Las Anod and 23 in Dayaha) in Sool and Sanaag have been completed but not yet equipped.
Output indicator 5.2: Number of Hospital buildings renovated / constructed and equipped in Sool and Sanaag	0	30	41	Rated A+: 41 hospital buildings in Erigavo (16 buildings) and Las Anod (25) have been completed though not fully equipped. The management function in Erigavo is limited because of the delays in procuring drugs and equipment. The management contract for Las Anod delayed because of the freeze in Danish finance.
Output indicator 5.2: % of girls enrolled compared to total enrolment in the two secondary schools of Sool and Sanaag	0	25%	28%	Rated A: The initial girl ratio enrolment was 33% in February 2017 with 209 students (69 females and 140 males). However, enrolment in both the Las Anod and Dayaha schools now stands at 347 students with a girl enrolment ratio of 28%.

Key points
This output is rated as an A. Two secondary schools in Sool and Sanaag have been operational (although operating in temporary facilities while the construction of new facilities takes place) since February 2017 with an initial enrolment of 209 students, with 69 girls. It should be highlighted that enrolment and teaching of these children in temporary facilities is the result of innovative and adaptive programming recommended by MM. The significant construction element has taken longer than expected and working relations with the Ministry of Education have not always been easy – for example months of delay occurred because of a disagreement by the PMT over the quality of internal ceiling tiles and was only resolved after the Minister of Planning visited the site and validated the quality.

Girls enrolment has increased by 42% this year (60% in Sanaag and 12% in Sool) and 347 students are attending the schools – 98 of whom are girls. Some parents have not enrolled their children because of the drought. Overall construction progress of school buildings stands at 80%. Procurement of equipment for the schools is ongoing. The reasonable scores for these indicators masks major difficulties experienced with these projects. Six management experts have been hired and work in Erigavo Hospital; three clinicians, a hospital management expert, a nurse trainer and a pharmacy expert. Several training sessions have been delivered to hospital staff including ICU and basic anaesthesia management, orthopaedic/surgical and trauma management. The UNICEF-designed acquisition of essential drugs was rejected by the MoH in early 2017 requiring an alternative procurement strategy via DPSA. This caused a delay of around one year. There was no clear policy imperative from GoSL to guide the PMTs or the SDF secretariat which has led to well-intentioned adaptation, but receding completion dates.

Summary of responses to issues raised in previous annual reviews (where relevant)
The output was introduced in the revised Log frame.

Summary of recommendations for the next year:
1. Finalise hospital and clinic construction by April 2018 and shift attention to resolving recurrent costs.
2. While the schools in the east target students from disadvantaged families, the running costs of these schools are high and a review of the medium term recurrent costs needs to be agreed by the Ministry of Education and Ministry of Finance.
3. Investments in the health and education sectors should be systematic as part of a sector wide approach or integrated into national programmes and projectised support. This would enable e.g. capacity development of education inspectors for them to be able to improve the quality of education as well as training teachers.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
SDF key cost drivers remains personnel costs (12.5% of total spend to date) and project expenses (4.3%). Personnel costs continue to reduce with a majority of SDF projects reaching closure. The key cost component under project expenses are mainly accommodation which take up 17% of the overall project costs, security (13%), local support staff (11%), travel (7%) and vehicle rentals (5%).

VfM performance compared to the original VfM proposition in the BC
As below, there is robust evidence supporting the VfM proposition in the original BC. SDF has a VFM framework with clear indicators that still remain relevant. However, there is need to evaluate the performance formally as project activities coming to a conclusion. The BC outlined a number of VfM measures by output (efficiency, economy, and effectiveness). While all remain relevant and are used, the fourth ‘E’ Equity was added by DFID in liaison with MM. Equity ensures a fair balance of the distribution of SDF projects across Somaliland.

Economy
The BC sought to ensure value for money by looking at the costs incurred by the fund manager and costs incurred in implementing the projects financed by SDF.

Comparison of SDF Fee rates with DFID Global and Somaliland

	Project Leadership	Project admin/support	Technical experts
DFID Global	£774	£137	602
SDF	£690	£0	690
Somaliland	£696	£175	690

This comparison shows that SDF rates in project management/leadership are lower than DFID’s benchmarks. Technical expert’s rates are higher by £88 compared with DFID’s benchmarks. The high rate is put down to much higher security related costs that increase the cost for consultants in specific technical areas like water engineering and road infrastructure site visits. SDF has demonstrated economy in its utilisation of a high number of national and regional consultants and suppliers with a focus on engaging and building local capacity. Out of 424 total contracts issued, 333 were awarded to consultants/companies with Somaliland nationality, representing 78.5% engagement rate of national consultants and companies.

Efficiency
The BC included plans to assess the cost of TA to the GoSL and outputs delivered through the projects. Efforts to make efficiency savings include:
1. MM conducted a needs assessment and established the required support for the development of quality proposals and programme management arrangements for SDF projects. It resulted in improved capacity in the management of projects by the Programme Management Teams (PMTs) in the ministries and agencies where SDF projects have been implemented.
2. MM shares a backstopping team with another DFID project also managed by MM – Energy Security and Resource Efficiency – reducing redundancies.
3. MM has employed local staff in key positions such as conflict analyst and deputy team leader creating better in-country relationship with the Government ministries and better understanding of the local context and political economy understanding across project sites.
4. QA of equipment procurement processes reduced waste, for example the water pipes for Hora Hadley to Geed Deeble were inspected by the certified engineers before importation and inspected on arrival at the port, ensuring the same quality as purchased.

Effectiveness
The BC identified measures of effectiveness through the spending on the projects financed by SDF, public perception of GoSL as a service provider, and the prioritisation of the projects. To ensure buy-in and ownership of the project activities, the sectors and project activities were selected from the list prioritised by the national planning commission based on the National Development Plan. The programme invested in building capacity of the technical staff at the Ministries implementing SDF projects. This has ensured smooth continuation of activities even with the leadership changes within ministries. The perception survey indicated 47% of citizens reporting improved service delivery in sectors supported by the SDF. This is compared to only 33% that perceived fair Government services at the start of the project.

Equity
The BC did not identify equity as a VfM measure. There has been a significant progress to ensure an equitable distribution of SDF projects across Somaliland including the Eastern regions of Sool and Sanaag. For example, renovation of Erigavo and Las Anod hospitals to provide the provision of secondary health care services to the population of Sool and Sanaag.

Whether the programme continues to represent value for money?
From the evidence above, the SDF continues to represent good value for money. While a number of projects are on track to reaching the log frame milestones, there have been challenges within the context of operation including the review of the scope of some projects, drought, frozen funding by Danida, insecurity in parts of eastern Somaliland and import delays. A more detailed VfM assessment will be conducted in 2018/19 to further ascertain the progress made to date. In particular, this assessment should include a VfM review that includes the impact of the Danish frozen resources – for example this may have reduced SDF VfM by investing in project design for projects that may not end up being implemented. Similarly questions need to be asked around the eventual completion of the well field collector and whether VfM has been affected by delay and implementation probably crossing over into SDF2.

Quality of financial management
SDF is on track to spend as forecasted. Overall, DFID has disbursed over £23M to the SDF programme out of a total of £25M. The balance of approximately £1.5M will be spent in this quarter i.e. January – March 2018. However, there have been challenges experienced in forecasting particularly in the last quarter of 2017 forcing the team to re-profile as necessary. Front loading of the budget in the earlier quarters of 2017 helped mitigate the variances. Being an election year, many government officials were focused on electioneering affecting their attendance of SDF governance meeting and decision making e.g. signing off of contracts. Additionally, the electioneering period affected the monitoring and evaluation of project initiatives hampering approval of payments to suppliers.

Date of last narrative financial report	05/12/2017
Date of last audited annual statement	12/06/2017 (We are expecting the FY2017 financial audit report in January 2018).

E: RISK (½ page)

Overall risk rating: Moderate
The overall risk level rating for the SDF programme has been assessed to be Moderate.

Overview of programme risk
A detailed programme risk register is in place and helps to manage risk. The SDF risk register is updated quarterly; the last update was in October. Many of the risks flagged in the original SDF BC have been substantially mitigated. The following risks were identified as having had an impact on SDF delivery:
1. Political Risks: the Presidential elections set for November 2017, was expected to lead to a significant electioneering period with partners more focused on the election campaign. The electioneering period affected the implementation of SDF projects, especially the signing of crucial project implementation documents including contracts and active participation in the governance of the projects by government officials. This resulted in delayed decision making for some projects. The postponement of the presidential elections from March to November 2017 saw the Danish government withhold part of its SDF funding (GBP 2.2m) until after the holding of the elections.
2. Insecurity: Political manoeuvring and tension impacted SDF programme delivery in the lead up to the elections e.g. insecurity in the Sanaag area prior to the Somaliland national elections in November 2017 slowed progress in the construction of additional water points in Figifuliye and Kulaal regions. In the lead up to the elections, the SDF Secretariat was informed by the Special Protection Unit (SPU) commander that no SPU team would be deployed to accompany SDF field visits until well after the elections. This has had an impact on the project implementation delaying the monitoring of project activities in the field. S/L and PL issue? (I know for the future but worth noting?)
3. Foreign exchange rate fluctuations: The SDF has lost a significant value of its funds available for projects due to exchange rate losses. Further fluctuations remain a threat to the successful implementation of remaining planned activities. The SDF secretariat is regularly monitoring and quantifying the exchange losses/gains. The team is also maintaining an overview of costs by currency type and monitoring the exchange rate to ensure the available SDF budget is adjusted in line with any exchange rate fluctuations. The SDF secretariat reports the fluctuation impact to the quarterly JSC meetings and facilitates a discussion on how to address its impact on SDF projects.
4. Drought: Rainfall is essential for the success of various SDF projects. The prolonged drought has caused significant livestock deaths, depletion of rangelands and availability of water. The success rate of forest reserves rehabilitation in Libaxley, Gacan Libaax and Daalo has been affected by the prolonged drought forcing the rescheduling of related activities.

Annex 2 sets out, in more detail, the major key risks which impacted on the SDF programme in 2017.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Progress on implementation is largely on track. The rate of implementation slowed down between October – December 2017 due to Presidential electioneering period in Somaliland. A number of projects reported importation delays and the slow pace of cargo clearance at the Berbera Port. A number of measures have been undertaken to ensure that the projects are successfully implemented against some revised timelines. MM was granted a no-cost extension extending the SDF end date from March 2018 to September 2018. This no-cost extension will allow MM to effectively manage a number of projects to their conclusion. The projects are under the Hargeisa Water Agency, Ministry of Education and Ministry of Health. These projects will be completed by August 2018.

Performance of partnership
MM has built a good reputation among the SDF donors, GoSL and other stakeholders as an impartial, competent and reliable implementing partner. It continues to maintain a good working relationships and seen as responsive and flexible to partner needs. MM continuously avail themselves to feedback, clarification and maintain mutual respect and trust with the partners, along with strong commitment of completing SDF outputs within stated timelines. Regular interactions at the JSC with government officials has resulted in a focused and coordinated approach to key issues and enhanced implementation. The governmental ministries and agencies involved in the SDF have shown consistently high levels of motivation to lead the implementation of projects. Following the election of the new Somaliland President on 13 November 2017, a new cabinet of 23 Ministers was nominated. The new ministerial changes have affected the SDF projects with nine out of the ten partnering ministries getting new ministers; MM has proactively reached out to build strategic relationships with the new ministers. The secretariat has also scheduled introductory meetings with the new ministers to orient them about the SDF.

Asset monitoring and control
All programme assets are systematically recorded and reported in a comprehensive asset register, maintained by MM. The asset register is reviewed and shared with DFID every six months. MM last updated their register in August 2017. MM has instituted an asset management policy that specifies rules and regulations on asset monitoring and control in line with DFID guidance on asset management. All partner line ministries and government agencies are sensitised on the policy and must commit to and comply with the policy including vehicle use guidelines. Vehicles used by MoERD have been returned to SDF secretariat for storage and handover to SDF2.

G: CONDITIONALITY (½ page)
Update on partnership principles and specific conditions
Not applicable. Although a renewed Somaliland Special Arrangement is likely to include a much stronger emphasis on mutual accountability which will be the cornerstone of the SDF MoU.

H: MONITORING AND EVALUATION (½ page)

Evidence and evaluation
The SDF has developed a strong M&E system. The M&E team is led by an M&E manager and guided by the log frame and M&E manual and framework. The team monitors the implementation of its programmes and conducts a perception survey annually to monitor Somaliland citizens’ opinions and perceptions on the provision of water, improved travel time of resurfaced roads and whether agricultural improvements have impacted on productivity and livelihoods. More specifically, the perception survey review progress made against Outcome 2 “% of citizens reporting improved service delivery in government sectors supported by SDF.” and Output Indicators 4.1 “% of people who report improved access to water in Hargeisa”; and 4.2 “% of people who report improved journey time on SDF rehabilitated roads” (in two areas- Berbera and Dila) in the SDF log frame.

Monitoring progress throughout the review period
Over the review period, the SDF secretariat has submitted quarterly progress reports and fund manager reports covering progress against the log frame milestones. MM facilitates quarterly programme JSCs to monitor progress on activities and in order to make strategic decisions. MM undertakes monitoring visits to project sites to assess implementation progress. The secretariat holds monthly progress meetings with the respective PMTs from the participating ministries and agencies to review overall progress made, share lessons and agree work plans.

DFID has also contracted an independent third party verification provider, LAMPS, to verify SDF results. To date, 29 SDF verifications have been carried out with findings being communicated against five criteria; relevance, effectiveness, inclusivity and gender, efficiency and sustainability. The most common issue arising was the need for a formal sustainability strategy that would incorporate government budgetary support to the operation and maintenance of the initiatives beyond SDF support.

To further mitigate fiduciary risk, the secretariat conducts an independent financial audit annually with the last audit conducted in September 2017 and a final report expected by end of January 2018.

The SDF has developed a conflict sensitive programming framework which includes conflict analysis of each project at the beginning of the project cycle. This is regularly updated through close monitoring including third party monitoring. When specific conflict issues arise, the implementing partner initiates bespoke “conflict audits” which are carried out to monitor adherence of projects to Conflict-Sensitive Programming Framework.

Locations of SDF projects

Risks

	Risk	Potential adverse impacts	Mitigation measures to prevent risks and/or limit potentially adverse impacts
1.	New government in place with different new Ministers in leadership, including-the possibility that their agendas/priorities are less supportive of SDF.	In the last quarter of 2017, various changes were made to the Cabinet members after the Presidential election. Impacts have been felt by the SDF Secretariat due to the slow settling down of the new Ministers. The SDF Secretariat continues to follow up closely to ensure that all new players have the relevant information regarding their projects. Some of the effects include: / Delay in signing of some contracts-pending signature with the former Minister who did not sign these off before he left office.	The SDF Secretariat continues to invest in building relationships with new Ministers, especially the Minister of Planning as the co-chair of SDF Joint Steering Committee; / Maintain strategic relationships with Government.
2.	Security issues. The outbreak of localised inter/intra clan conflict in SDF Project areas/Sool and Sanaag; and tensions between Somaliland, Punt.	The occurrence of security incidents is an ongoing concern for SDF.	The SDF Secretariat continues to conduct detailed security planning which includes daily monitoring of the security situation. Depending on the conflict analysis, certain areas might be avoided until when local partners/individuals are able to continue project implementation. / Adopt a flexible approach to planning and implementation, allowing project activities to be postponed/and funds to be shifted from one project to another.
3.	Contractors/other implementing partners failing to deliver	As SDF 1 programme comes to an end, contractors are increasingly requesting contract time extensions and the limited time available. Thus less risk on fewer results achieved than anticipated and negative reputation of the programme.	Within the overall SDF monitoring and evaluation system, close monitoring supervision of contractors’ performance / Meetings were set up with all major contractors and established realistic work plans in the last quarter to ensure proper tracking of performance and to allow for quick adjustments where required.
4.	The PFM Reform Strategy and related / programmes failing to or being slower / than anticipated to achieve their reforms, / hampering the phased approach of / transferring fund control to the / Government based on meeting / benchmarks and instead using external systems.	The initially intended transfer of Fund responsibilities to the Government of Somaliland has not substantially happened yet. This has been the result of the absence of PFM benchmarks set by the GoSL whose achievement was expected to be the basis of the transfer of responsibilities.	The SDF Fund Manager continues to encourage presence of PFM-stakeholders at Joint Steering Committee meetings, creating leverage over and involvement in the reform process from the SDF side; / As part of the SDF M&E system, closely monitor progress in the PFM programme; / Allowing SDF funding and expertise to be used to support the PFM programme if needed and relevant.
5.	Variations in price and foreign exchange fluctuations	This has affected the amount of funds available for implementation of projects and limited flexibility of making further commitments to projects that were under budgeted.	To address this, the SDF Secretariat is: / Following guidelines for dealing with exchange rate variations where other currency other than GBP is used. which were provided by DFID; / In coordination with the JSC, tracking closely the forex movements in case of further fluctuations.
6.	Prolonged Drought in Somaliland	Rainfall is essential for the success of various projects, such as those at MoERD, MoA, MoL, MoWR etc. A prolonged shortage in rainfall or receiving below average rainfall might result in underachievement of the project targets, directly impacting some of the log frame indicators and overall per capita income of the country. / Drought has had a significant impact on Somaliland’s livestock (loss of livestock, lack of pasture/water, livestock weight, long trekking distances) and the population (internal and external displacement). The international community has been called upon for humanitarian aid as Somalia is on the brink of a famine.	To address this, the SDF Secretariat has: / Communicated on an ongoing basis to the JSC the potential risks for project completion; / Participate in the Inter Cluster Coordination Group meetings and ensure the livelihoods and water projects support response and recovery from drought conditions; / As part of reducing water loss in balleys, the balleys under SDF are being lined with membranes to reduce on water loss through percolation.

Annex 3: Recommendations from last annual review and update on progress made
	Recommendations	Actions	Progress made
1	Engagement with line ministries to avert perceived delays in SDF implementation, notably planning and governance arrangements	Constant orientation and induction with staff and critically new Ministers, and better engagement with the national planning commission	SDF partners are fully orientated to the international standard methods and procedures developed by the SDF, complaints around delays are minimal. Secretariat reaching out to new Ministers for orientation on SDF programme.
2	Revision of logframe indicators on 4.1-people reporting access to clean potable water and 4.2-people reporting improved journey taking on rehabilitated roads.	The indicators have been revised and log frame vaulted.	Log frame revised
2	Need for a well field collector (WFC) to be installed on the outskirts of Hargeisa to enable approximately 5,000m3/day to be introduced into the system, serving an additional 250,000 people in Hargeisa.	Budget Allocation/ Co-financing with Netherlands' additional funds Euro 1m. The SDF took on uncompleted works from the EU programme which meant an element of re-design as Mott MacDonald inherited Fitchner designs. Procurement of supplies for the WFC is ongoing and will be completed in March 2018. The procurement was split into two lots; Supplies (of pipes and fittings) and Works.	Construction of the WFC will commence around April/May 2018.
3	Need for Roads Development Agency (RDA) to operationalise the road maintenance policy as well as rolling out of the road maintenance guidelines detailed in the Roads Act still pending with the Parliament.	Marking with white lines and other safety measures of all SDF funded roads commenced in October 2017 as part of the maintenance programme and increasing safety on the roads. This is expected to be completed by end of February 2018.	On-going implementation of road maintenance policy. Expect the Parliament to approve Roads Act.
4	In the final year of the SDF, important to map the partners (mainly UNICEF) working in the same urban water locations as the SDF to ensure hygiene interventions are complementing mainly the infrastructure outputs	All key WATSAN donors meet regularly to report on activities in support of the Hargeisa water authority. This is one of the most constructive donor coordination groups active in Somaliland – including UNICEF WB, KfW and GiZ	Done and DFID will ensure same engagement with UNICEF and GiZ continue in SDF Phase 2.
	The SDF lost about 10% of its value in 2016 due to currency exchange rate fluctuations. Mechanisms should be put in place to protect the fund against such loses in future. The first JSC meeting of 2017 must focus on finding cost savings and take tough decisions to absorb the 10% financial loss.	The Joint Steering Committee approved reprogramming of activities	The SDF reprogrammed activities, however, there is little the SDF donors, secretariat, or recipient Government can do except to adapt the portfolio to exchange rate losses.
6	The use of country systems is one the aspirations of the New Deal to increasingly use country systems.	The SDF was designed to be transferrable to country systems providing adequate safeguards were in place. However, the use country systems has not been realised in Somaliland.	The use of country systems has not been realized in Somaliland. Reasons for this have been discussed elsewhere.
7	Continue with in depth community engagement and political, social economy analyses in new project areas	SDF undertook fragility, conflict and social impact/political economy analyses across all new projects in Qool Qaday livestock holding ground and the Fiqufiliye water supply projects. Analyses created awareness and reduced intensity of conflict during implementation.	On-going community engagement

Annex 4: Recommendations for next year

	Recommendations	Actions	Comments
1	Urgent attention to completing as much of the well field collector (WFC) works in SDF 1.	Agreement on an approach to handover remaining works – especially the liability from the current SDF secretariat under SDF 1 to the new SDF secretariat under SDF 2 – which in many cases can lead to a revision of designs.	Procurement of supplies for the WFC is ongoing and will be completed in March 2018. Construction of the WFC will commence around April/May 2018. It will be part of the projects for SDF 2 to finalise
2	Donor coordination should improve and consider the common WATSAN international standards for equipment and construction.	DFID and SDF 2 Secretariat to consider this in implementation of SDF Phase 2	To be considered in SDF2
3	GoSL commitment to planned maintenance of roads has been weak. Future SDF roads should require government to deposit agreed maintenance funds in a special account.	Push Government to ensure Roads Act is approved by the Parliament	SDF secretariat will push for the Parliament approval of Roads Act that is still pending
4	Engagement with line ministries	Maintain constant orientation and induction with staff and critically new Ministers, and better engagement with the national planning commission	DFID/SDF secretariat will ensure proper induction and establish good relationship with all the line ministries

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the log frame been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the log frame (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the log frame (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process