Type of Review: Annual Review

Project Title: Universal Elementary Education (Sarva Shiksha Abhiyan)

Date started: 11/03/2008
Date review undertaken: 10/03/2012

## Introduction and Context

What support is the UK providing?
DFID will support the Government of India’s flagship elementary education programme, Sarva Shiksha Abhiyan (SSA), to provide universal access to good quality education for children from 6 to 14 years. Between 2010/11 and 2012/13 DFID will provide £140 million in financial aid, along with £9 million in technical co-operation to help strengthen India’s national learning assessment system and evaluate pilot initiatives to improve the quality of education.

What are the expected results?
By end of project (December 2012), the project proposes: / More children stay at school than would otherwise have been the case and achieve better learning outcomes. The key purpose level targets over the programme period are: / 1. Retention rate at primary level increases from 75% to 80%. / 2. Improvement in learning levels at Grade 3, 5 and 8 (i.e. age 9, 11, 14). / DFID provides around 2% of total SSA funding; and will attribute 2% of the overall programme results. / For the three years of support we will aim to: / (i) Increase the percentage of children who stay in school until Grade 5 from 78% to 82%. / (ii) Increase gross intake to the last grade of primary (Grade 8) by 10,500 (from 350,000 to 360,500). / (iii) Directly support 1.52 million children in elementary education. / (iv) Increase in the percentage of children who after 2 years primary schooling have sufficient reading fluency and comprehension to 'read to learn' from 25.7% to 27.5%. / (v) Build 6,000 new classrooms / (vi) Train 90,000 teachers

What is the context in which UK support is provided?
There has been good progress with increasing access to schooling. India is on track to achieve universal primary education (MDG 2) (for enrolment but not completion) and gender equality in primary education (MDG 3). However, 3.2 million children continue to be out of school[1], mostly from disadvantaged groups. Major challenges remain with ensuring children stay at school (current retention rate is 73%[2]) and receive quality education that ensures they are learning well: recent research shows that slightly less than half of India’s ten year-olds can read a simple paragraph.[3] / DFID’s funding will tackle the challenges of expanding upper primary schooling (11-14 years) and improving the quality of education. In addition to financial aid, DFID’s technical assistance helps strengthen the implementation of SSA overall – for instance, by bringing experience from other countries’ education systems and advising on teaching methods. In particular, DFID’s technical support is helping India to expand and strengthen its student assessment system; so there is better information available on what children learn in school and how government schools are performing. This is essential for improving the performance and accountability of the elementary education system.
[1] 15th Joint Review Mission Aide Memoire
[2] DISE 2010-11 Flash Statistics
[3] Annual Status of Education Report (ASER) 2011

## Section A: Detailed Output Scoring

Output 1: All children in School
Output 1 score and performance description: A+ / Government and independent data sources unequivocally agree that SSA has been successful in bringing children to school. Numbers of out of school children have fallen from over 30 million in 2001 when SSA was launched to just over 3 million in 2012 and more children, regardless of background, are moving through the system to complete 8 years of elementary education. / 1. All sources verify that the number of out of school children has declined across India in the last year. SSA Project Monitoring and Information System reports that 3.2 million children are not enrolled in school in 2011, compared to 5.2 million children in 2010[4]. The reduction is largely due to the efforts of states and injections of funding after the 2010 passing of the Right to Education Act, which constitutionally guarantees every child the right to be enrolled in school for 8 years. There have been concerted efforts to open new schools, construct additional classrooms, upgrade Education Guarantee Scheme (EGS) centres to schools, and provide special interventions to enrol urban, SC/ST/Muslim/girls and Children with Special Needs (CWSN). / The independent Annual Status of Education Report (ASER) also reports an overall decline in the proportion of children in the 6-14 age group that are not enrolled in school from 6.6% in 2006 to 3.3% in 2011. In 2010, this number was 3.4%[5]. They find that 11 to 14 year old girls are the hardest to keep in school, although India has made progress on this front as well: The percentage of out of school girls in the 11-14 age-group has declined from 10.3 % in 2006 to 5.2% in 2011. / However, there is a caveat: The 15th Joint Review analysed and triangulated various sources of data, and suggested that the number of out of school children may be underestimated. The independent PROBE Revisited report, which surveyed communities in Bihar, Madhya Pradesh, Rajasthan, Uttar Pradesh, Uttarakhand, Jharkhand, and Chhattisgarh also finds that while most children are in school, significant disparities persist for rural Scheduled Tribe and Muslim girls in these states.[6] There is acknowledgement that the data will be sharpened in 2012/13 and will likely result in the provision of a more realistic figure. In fact, several states have begun to use more sophisticated methods to identify and track out of school children, including the usage of Global Positioning Systems (GPS) and the development of Child Tracking systems, notably Rajasthan and Assam. The request to incorporate a regular survey of out of school children in all states was made by the government of India in January 2012. The end-line target of 5.1 million out of school children has been achieved. / 2. More children have transitioned from primary to upper primary school. In 2010, 83% of boys and girls were moving from primary onto upper primary school. In 2011, the corresponding number is just under 85% for boys and just over 85% for girls suggesting that more children are moving onto the next cycle of education. All states reflect an improvement with regards to transition barring Sikkim and West Bengal, where one sees a 4% decline from last year. Uttar Pradesh continues to report the lowest transition rate, at 65% with girls transitioning at a higher rate than boys (66% compared with 64%). The end-line target for an 85% transition rate has been achieved. / 3. Student attendance continues to vary considerably among states; data and methodology are inconsistent. The 2011 independent ASER report finds a decline in student attendance over the years, particularly in upper primary schools: On average student attendance declined from 73.4% in 2007 to 70.9% in 2011 in rural primary schools. Last year student attendance was reported at 72.9%. They also found that some states’ had a bigger problem with attendance than others. Bihar, for example, showed a decline from 56% in 2010 to 50% in 2011. Madhya Pradesh also showed a decline from 66% to 54.5% over the same time period. Conversely, Himachal Pradesh had 91% attendance and Gujarat had 85%. / The government of India’s presentation at the 14th Joint Review was largely consistent with ASER: They find an average of 68% attendance across the country. They cite Kerala and Himachal Pradesh as strong on attendance, and add that most of the southern states were above average, but that the rest of the country was cause for concern: Bihar and Uttar Pradesh for example were particularly low (42% and 57% respectively). They added that the problem was particularly acute for girls and for children from SC, ST and Muslim backgrounds. The independent PROBE Revisited report reiterates that student attendance continues to be a problem in their repeat survey: They find 63% student attendance in PROBE states, with striking variations between states. On average in Madhya Pradesh and Rajasthan 75% of students were in attendance, while the figure for Bihar was 53%. The reasons cited were complex – Seasonality, parents’ migratory patterns, ill health, discrimination, social distance and “irrelevant teaching and learning.” / The 14th Joint Review acknowledged that “irregular attendance needs to be viewed as a very different and far more complex challenge than access and enrolment” but cautioned that attendance is not defined or measured consistently across states. The time of the year that attendance surveys are completed can skew results completely if, for instance, they are conducted during the harvest season. Consecutive Joint Reviews have also noted the methodological challenges of defining absenteeism versus drop out. The milestone for 80% student attendance in 2011 has not been achieved.
Progress against expected results: / 2 of 3 output indicators have substantially exceeded their milestone targets, in fact progress has been so dramatic they have achieved their end-line targets (Out of school children and transition from primary to upper primary). / 1 indicator has not achieved its milestone target (student attendance). The decline in attendance requires further analysis. / Recommendations: / 1. DFID will continue to lobby for the development and usage of regular child surveys to track out of school children by ensuring that good practices by States such as Assam and Rajasthan get shared at the upcoming 16th Joint Review (a Delhi based review where states present on their innovations and good practice). / 2. DFID will advocate for the regular measurement and monitoring of student attendance by (i) adding a recommendation in the Joint Review Aide Memoire, which is followed up by the government of India in an official Action Taken Report and, (ii) commissioning a DFID-led multi-faceted time on task study to feed into the third-party end of project (EoP) evaluation (see Section 3.2) / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No
[4] SSA Monitoring Results Framework: 15th Joint Review Mission
[5] ASER (2011)
[6] PROBE Revisited (2011) is a follow up to the original PROBE study conducted in the mid-1990s and replicates the same survey in roughly the same villages that were visited in 1996 to assess the changes in the education landscape in 10+ years.

Output 2: Bridging gender and social gaps
Output 2 score and performance description: A / Through a combination of supply and demand side interventions SSA has been able to close gender and social group gaps, particularly with regards to enrolments and retention. Girls are enrolled in numbers equal to their population as are Scheduled Tribe and Scheduled Caste Children[7]. There has also been a sharp increase in the identification and enrolment of Children with Special Needs. / 1. More schools report having girls’ toilets, with the national average increasing from 58% to 60%[8]. This number, however, masks deep differences across states on the provisioning of girls’ toilets: the troubled north-eastern states (Assam, Arunachal Pradesh, Manipur) and J&K have abysmally low numbers of girls toilets ranging from 26% to 40%. Bihar, Orissa and Madhya Pradesh are also quite low in this regard, all ranging from 37% to 39%. By contrast, Rajasthan shows a great improvement, jumping from 82% to 92% in 2 years. / While this 2% increase in the provisioning of girls’ toilets (as per government data sources) does not meet the milestone target, interestingly this year’s ASER report tells a more optimistic story with a sharp improvement in the proportion of schools with a separate girls’ toilet from 69% in 2010 to 77% in 2011. Moreover, they find that in 2011, 44% of schools had girls’ toilets “available and useable” compared with 33% in 2010. They suggest that this is in part due to the requirements of the Right to Education Act. Regardless, the milestone for 2011 (64% of schools with girls toilets) has not been achieved. / 2. Overall, it appears that the percentage of children that are completing primary school, regardless of social background, has increased significantly from 93.4% in 2010 to 97.6% in 2011[9]. Despite best efforts on the part of DFID, and as recommended in the 13th Joint Review,[10] disaggregated data on completion, transition and retention by gender or social group have not been made available. The analysis of proxy indicators, including numbers of out of school children and attendance, find that though the gap between socially disadvantaged children and others is narrowing it is still palpable[11]. The availability of learning achievement data, raises a significant area for concern: The Class 5 National Achievement Survey (funded by DFID and using internationally-recognized assessment methods) finds that though there is no significant difference in the achievement of girls and boys in reading, maths and environmental studies, Muslim, SC and ST children do score significantly lower than the general population in all 3 subjects. DFID has been active in trying to alleviate this gap, though its support of an innovative low cost private school model that brings quality education to disadvantaged children in the slums of Bihar, and by developing a holistic intervention that combines teacher training, community engagement, and academic support for SC children in Bihar. The latter intervention has been adopted and scaled up by the government of India from 2 to 160 schools. Despite lack of disaggregated data, available evidence suggests this milestone has been achieved. / 3. A sharp improvement in the identification and enrolment of children with special needs (CWSN) has been noted in 2011. The identification of CWSN has improved from 2.5 million in 2010 to 3.02 million in 2011, close to 90% of whom were enrolled in school or provided home-based education. The recent Joint Review commented that this was an area where SSA has made a “dramatic move forward”. They added that SSA staff at all levels appeared to reflect a greater need to identify CWSN and find appropriate strategies to provide schooling. The end-line target for 2.65 million CWSN enrolled has been surpassed.
Progress against expected results: / One milestone has yet to be achieved (provisioning of girls’ toilets) while another has achieved its end-line target (enrolment of children with special needs). There was an expectation that the construction of girls’ toilets would occur with greater urgency given the requirements of the Right to Education Act and this is seen most dramatically in states where gender disparities were traditionally quite stark (Punjab, Haryana and Rajasthan). / Recommendations: / 1. DFID will press for the need for disaggregated data on completion in the 16th Joint Review through a presentation on its work in schools in Bihar (Deshkal Society). / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Low/Medium/High / Revised since last Annual Review? No
[7] The Scheduled Castes (SCs) and the Scheduled Tribes (STs) are two groupings of disadvantaged people that are given express recognition in the Constitution of India. As per data, over 50% SC and 75% ST households account for the lowest 20% income quintile
[8] DISE Flash Statistics 2011
[9] DISE defines gross completion as the Class 5 enrolments as a proportion of the 11 year old child population.
[10] 13th Joint Review Mission Aide Memoire (p10)
[11] 14th Joint Review Mission Aide Memoire (p14)

Output 3: Education of satisfactory quality
Output 3 score and performance description: A / Though quality outputs have largely been achieved, resulting in an output score of “A”, we place on record significant concerns around quality outcomes, i.e. levels of basic learning. Latest results from DFID-supported National Achievement Survey and DFID-supported Programme for International Student Assessment (PISA, which India participated in for the first time) as well as independent assessments confirm that average levels of learning are alarmingly low across much of India. (See Section 1.6 for further discussion) / 1. The percent of teachers receiving in-service training dropped significantly from 78% to 69% from 2010 to 2011, according to an analysis of the SSA Programme Monitoring and Information System. States where low levels of teacher training were reported included Bihar, Haryana, J&K, Jharkhand, Karnataka, Punjab, Rajasthan, Sikkim, Tamil Nadu, Tripura and UP. DISE, which also collects data on the provision of in-service training during the “previous academic year”, reports a national average of 40%. The data confirm low rates of training in Bihar (8%), Manipur (10%), Rajasthan (13%), and UP (18%). Moreover, there are high numbers of untrained teachers – teachers currently in the system without the minimum certification (Bachelors of Education or Diploma in Education) – in all the north-eastern states, Uttar Pradesh, West Bengal and Bihar. In Bihar for example, 45% of all teachers are untrained.[12] / The 14th and 15th Joint Reviews continue to be raise concerns around the quality and effectiveness of the in-service teacher training model. An independent study of teacher practice in 5 states (Tamil Nadu, Maharashtra, Kerala, West Bengal and Rajasthan) finds that in-service training programmes are “rarely need-based, and are viewed as formalities to be completed rather than as important resources to help teachers do their job better. Training methodologies discourage questioning, discussion and analysis by teachers.”[13] / There are, however, pockets of good practice: In Tamil Nadu, ten days’ training is provided by trainers at the sub-district level (at Block Resource Centres) where several of the training themes are needs-based and determined by the teachers themselves. For example, after the recent cyclone Thane in Villupuram district, there was a planned training on stress management for the teachers. In many states, including Tamil Nadu, Gujarat and Chhattisgarh, there continues to be a monthly “cluster” level meeting that focuses on trouble-shooting and classroom practice. / A growing urgency to address the challenges with the current teacher training system is being backed by political commitment in the last year: The government has recently made it mandatory that new teacher appointments are to be made on the basis of a Teacher Eligibility Test (TET). Results from recent TETs confirm the alarmingly low competence of prospective entrants and reiterate the need for a complete overhaul of the existing teacher education system[14].The milestone for 2011 has not been achieved. / 2. Teacher attendance has improved in 2011. ASER 2011 finds an average of 87.2% of appointed primary teachers and 86.7% of upper primary teachers in school compared with 87.1% and 86.4% respectively in 2010. Bihar’s corresponding rates were 85.1% and 85.2% while some states such as Kerala report as high as 92.8% attendance. / The SSA Monitoring Results Framework pegs teacher attendance at 81.7% and 80.5% respectively at primary and upper primary levels, based on a study conducted on behalf of the government of India. The PROBE report also finds teacher attendance hovering at 78%, which is not very different from their finding 10 years prior. They also found considerable variation among states: Bihar had the lowest teacher attendance at 70% and Madhya Pradesh the highest (86%). Schools in Uttar Pradesh had 78% of their teachers present while Rajasthan had 83%. A caveat is that teacher attendance surveys often do not differentiate whether a teacher is absent for official or unofficial reasons. For instance, across the country in 2011, teachers participated in the National Census exercise (as they are every 10 years when the Census is taken), often taking them out of the classroom during school hours. The milestone for 2011 has been achieved. / 3. Most children received teaching learning materials. According to the SSA Programme MIS Quarterly Report, in January 99% of eligible children received free textbooks. The most recent Quarterly Report, which collected data mid-school year reports 88% of eligible children receiving free textbooks, with the remainder set to receive them in January 2012 for the upcoming academic year. / Additionally, ASER reports an increase from 2010 to 2011 in the use of supplementary material being used in Class 2 and 4 classrooms such as charts on the wall, board games, books (other than textbooks). In Class 2 there was an increase from 80.7% to 82.1% and in Class 4 from 76.7% to 78.2%. On average, almost all teachers in Tamil Nadu, Kerala and Gujarat were using materials other than textbooks in their classroom. Overall, the northeastern states such as Manipur, Tripura, and Meghalaya continued to show low usage of supplementary materials. The milestone for 2011 has been achieved.
Progress against expected results: / 2 of 3 output indicators have met their milestone (teacher attendance and availability of teaching-learning materials). / 1 output indicator (teacher receiving in-service training) has not achieved its milestone and continues to be a problem area for the SSA programme. / Recommendations: / 1. DFID to intensify focus on teacher training though consideration of a £10 million grant to the UK Open University to deliver high quality teacher education materials at affordable cost to over 1.5 million teachers.[15] / Impact Weighting (%): 50 / Revised since last Annual Review? No / Risk: Low/Medium/High / Revised since last Annual Review? No
[12] Bordia et al (2010). Sarva Shiksha Abhiyan vis-à-vis The Right of Children to Free and Compulsory Education, Act, 2009 (p61)
[13] Ramachandran, V. Bhattacharjea, S. and Sheshagiri, K.M. (2009) How Teachers’ Practice is Influenced by Ground Realities
[14] At the first TET conducted in June 2011, only 100,000 of nearly 300,000 candidates were found eligible.
[15] The programme will harness ICT technology, build collaborative partnerships with local institutions, and distribute free materials. The programme will build on the OU’s award winning work in Africa (TESSA).

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? / Yes. It was agreed that the Log Frame would be revised for the extension of SSA (2011-2013) and after the 2010 SSA Annual Review (EDRM 3166036) in order to strengthen Output 3 on quality and to replace indicators where targets had been achieved or were near achievement. / 1.2 Overall Output Score and Description: / Overall Output Score: A / Output achievement under SSA continues to meet expectations on most fronts. Children are being brought into school as the number of out of school children falls and more children are staying in school and continuing onto the next level of education. There is growing pressure on states to erase gender and social group disparities, and as a result the provisioning of girls’ toilets has speeded up as has the identification and enrolment of children with special needs. Ensuring that all children receive quality education continues to be the focus, with mixed success: Teachers are coming to school more regularly and children are in regular and timely receipt of textbooks. / Where the programme struggles to keep pace is with student attendance, which seems to have dropped in the last year, and ensuring the coverage and quality of teacher in service training. These are both complex issues to resolve given the scale and complexity of the Indian education system, but the government and its development partners continue to push for long term change. / 1.3 Direct feedback from beneficiaries / The PROBE report finds that parents are articulate about the need for education for their children, however, gendered motivations and aspirations persist. Many parents saw that education empowered their daughters to live better lives: “… nobody will take twenty rupees from her when she owes ten” said a 30 year old lower caste woman from Bihar. “If a girl is educated, she will learn the way to live, speak… because education will light up the way,” said a low caste farmer from Madhya Pradesh. The motivation for education of boys was very strong and was closely tied to improved income and employment opportunities. / PROBE also finds that SSA Village Education Committees (VECs) are more functional than they were in the mid-1990s (when the original PROBE survey took place), playing a larger role in strengthening school accountability: “Education Committees were very active in monitoring the maintenance and construction activities in school, the delivery of incentives and the appointment of contract teachers. Across the board, they appear to have been quite successful in carrying out these activities.” (p26)
1.4 Summary of overall progress / Overall progress within SSA is satisfactory and meets expectations. Children, regardless of background, are enrolling in school in higher numbers. The government is committed to closing the gaps between social groups, particularly for girls. Improving the quality of education, and children's overall school experience, has received much more attention in the recent year, exerting pressure on the government to address issues around teacher training with greater urgency and to focus attention on learning outcomes. However, considerable challenges remain both in retaining children in school and delivering demonstrable improvements in children's learning levels. These are long term, systemic challenges that require prolonged and sustained engagement – and it is unlikely that we will overcome them before the project end date of 2013. / DFID made considerable progress on the effective use of its technical assistance funds in 2011. Specifically, the third cycle of the Class 5 National Achievement Survey was completed; discussions on the need for National assessment strategy for education (and associated budget) were brokered and a government committee has been formed; DFID funded India’s first engagement in the OECD Programme for International Student Assessment (PISA); action research funded by DFID to address issues of discrimination and exclusion in classrooms in Bihar has been adopted and scaled up by the government of India; and DFID India has contributed to global good research in education by supporting an innovative programme which delivers high quality education to children living in urban slums through low cost private schools.
1.5 Key challenges / To build on the success of bringing children into school by addressing learning in the classroom. / Develop a responsible exit strategy, specifically to build institutional sustainability for the activities of the SSA TC Fund, including the National Achievement Survey and programme evaluations.
1.6 Annual Outcome Assessment / The project outcome assumes that increasing retention in primary school (so that a child completes a full cycle of education) and improving learning outcomes will contribute to the programme outcome: Increasing the number of 6 to 14 year old children, especially from special focus groups that are enrolled, regularly attending and completing elementary education and demonstrating basic learning levels. This outcome has been partially achieved. Children are being brought into school, including those from special focus groups, and they are completing school in higher numbers. However, children are not regular in their attendance, may not stay in school for the full cycle of 8 years, and evidence suggests that what they are learning while they are in school is variable. The latest DFID-supported Class 5 National Achievement Survey finds reading and math skills are of particular concern. The bottom 25% of students appear to function at very low levels of literacy and numeracy unable to solve basic mathematical calculations or read with understanding if the context is unclear.[16] These results are confirmed by other independent assessments of learning, including the annual ASER report. Our assessment is that this gap is explained by wider and long-term systemic challenges that should continue to remain the focus in the remainder of DFID support to SSA, such as (i) strengthened national assessment system to inform remedial action (ii) better preparation and deployment of teachers; (iii) location-specific action to address the root causes of student attendance.
[16] NCERT (2011) What do they know: A summary of India’ National Achievement Survey (p7)

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / DFID’s contribution to the current phase of SSA is £149 million over a period of 2 years (2011-12 and 2012-13), through non-budgetary financial aid (£140 m) and technical cooperation (£9 m). DFID’s contribution is reimbursed on an annual basis on receipt of detailed financial management returns from the Government of India along with an audited expenditure statement. Payment is released only against the financial forecasts and agreed capped annual ceiling. / 2.2 Key cost drivers / SSA is a partnership between National and State Governments and three donor partners (DPs): The World Bank, European Union and DFID. The funds are released on the basis of approved annual work plans and budget of the states. / Around 90% of the programme is funded from India’s own resources, with the balance being provided by the donor partners. Donor partner support to SSA is provided through a sector wide approach (SWAp). DFID’s contribution to SSA is approximately 1.6 - 2% of the overall expenditure for SSA in a financial year. Funding is disbursed using a need-based allocation formula (developed with assistance of the donor partners). Currently 72% of SSA funds go to nine most needy States: AP, Bihar, Chhattisgarh, Jharkhand, Rajasthan, MP, Orissa, UP and West Bengal." / The reported expenditure for FY 2010 – 11 was Rs. 31,958 crores; a 50% increase over the previous year. This funding increase results from SSA being selected as the programme through which Right to Education Act (RTE) 2009 will be implemented. The approved outlay for FY 2011 – 12 is Rs. 60,149 crores, which would see SSA receive a further significant increase over FY 10-11. The extent to which this projected increase will be realised is debated given currently reallocation of available funding. / Contract teachers salaries constitute about 30% of the total SSA expenditure incurred in 2010-11. The other significant expenditure items are access and infrastructure (civil works) constituting about 32% of the total expenditure for 2010-11. / The technical cooperation fund under SSA provides technical support for planning, implementation, management and evaluation and capacity building. The main technical support agency (TSA), Cambridge Education, was selected by international competitive tender under OJEU processes. TSA activities and expenditure are monitored against pre-agreed milestone deliverables. / 2.3 Is the project on-track against original timescale: Yes / Yes. The program comes to end on 31st March 2013.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes in evidence are noted and thus, no implications are qualified. Evidence is generated from central government published data sources, project management information system, six-monthly joint review missions with government and donor partners[17], and through independent reports. / 3.2 Where an evaluation is planned what progress has been made? / Four programme evaluations of quality interventions have been completed in 2011: / - Aadhar, in Himachal Pradesh is a state-wide initiative to improve basic literacy and numeracy in primary level students. / - Activity Based Learning, inTamil Nadu is a project piloting the principle of learning through activities in classes 1 to 4. / - Children’s Learning Acceleration Programme (CLAPS) in Andhra Pradesh is an initiative that aims to improve learning levels in all areas of the primary school curriculum. / - and Multilingual Education (MLE) Programme in Orissa is a teaching tribal children in their mother tongue with the aim of improving education equity. / Two further evaluations are planned for 2012/13 on teacher professional development and continuous and comprehensive evaluation; these are in design phase. / A third-party end of project (EoP) evaluation will be initiated to feed into the project completion reporting exercise. This study will be commissioned in May 2012 based on a ToR jointly prepared by DFID, the World Bank and the European Commission (in March/April 2012). / The Independent Commission for Aid Impact (ICAI) conducted an investigation of the impact of DFID India’s programmes in health and education with a focus on 2 education programmes (SSA and Gyanshala) and 3 health programmes in Bihar. The findings will be made available in June 2012.
[17] Colclough (2011) suggests that the Joint Reviews are a powerful example of the strength of the SSA partnership between government and donor partners (p16)

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The "Fiduciary Risk Assessment of DFID's Additional Financial support to the GOI's Sarva Shiksha Abhiyan" report assesses the overall fiduciary risk as "Moderate". / The overall risk of corruption impacting the Public Finance Management and Accountability (PFMA) system is assessed as Substantial. / The table below notes the key highlights of the fiduciary risk rating: / Good Practice Principles & Risk Rating / GPP 1: A clear set of rules governs the budget process. / A Budget Law specifying fiscal management responsibilities is in operation M / Accounting policies and account code classifications are published and applied S / GPP 2: The budget is comprehensive. / All Government activities are included in the budget L / Extra Budgetary expenditure is not material L / GPP3: The budget supports pro-poor strategies. M / Budget allocations are consistent with medium term expenditure plans / GPP 4: The budget is a reliable guide to actual expenditure. / Budget outturn is consistent with the budget S / GPP 5: Expenditure within the year controlled. / In year reporting of actual expenditure S / Systems operating to control virements, commitments and arrears M / GPP 6: Government carries out procurement in line with principles of value for money and transparency. / Appropriate use of competitive tendering rules and decision making is recorded and auditable S / Effective action taken to identify and eliminate corruption S / GPP 7: Reporting of expenditure is timely and accurate. / Reconciliation of fiscal and bank reports is carried out on a routine basis S / Audited accounts are submitted to state legislative Assembly within the statutory period M / GPP 8: There is effective independent scrutiny of government expenditure. / Government accounts are independently audited M / Government agencies are held to account for mismanagement L / Criticisms and recommendations made by auditors are followed up M / Risk Rating Nos. of benchmark / Low Risk (L) 3 / Moderate Risk (M) 6 / Substantial Risk (S) 6 / High Risk (H) 0 / Overall risk rating: M / The reforms undertaken by state and national governments are credible and on a positive trajectory. Some of the achievements/ improvements to strengthen and improve financial management are: / The ministry has established a system of monitoring the pace of expenditure through a system of monthly and quarterly Financial Management Reports (FMRs); / Quarterly review meetings are held by Director, Ministry of Human Resource Development (MHRD) with Financial Controllers (FCs), heads of finance of states, and SSPs to review the issues and challenges faced, status of audit reports, accounting and FM issues, quarterly progress reports, status of Internal Audits; / Concurrent financial review is conducted by IPAI; / Financial Management and Procurement Manual (FM&P manual) , guidelines have been prepared and circulated. These are uploaded on the Ministry’s website. These documents are available in States. Larger states have also prepared hand outs in local language and they are available with Village Education Centres (VECs); / Audit firms have been hired by the centre, there is consolidation of audit though random delays are still there; and / Adequate availability of funds / As we go forward some of the issues and challenges that need to be addressed for ensuring efficient and effective implementation of the programme are: / Human resource capacity constraints in civil and accounts disciplines at state and district level / Inadequate progress in civil works / Weaknesses in accounting and book keeping at sub-district level / Gaps in internal audit systems across the states
Risk of funds not being used as intended: Moderate / All financial contributions from Development Partners (DP) are in the form of reimbursement against the total SSA expenditure (both GOI and states) in the previous financial year. DPs jointly monitor SSA’s financial management systems based on the review of GOI’s Financial Management Reports (FMRs), Audit Reports, JRM documentation, IPAI reports on concurrent reviews, manual and GOI’s external website. / DPs review status of the progress and issues related to programme planning, implementation, monitoring and evaluation, including financial management/procurement capacity of states and districts and agree on actions to support the weaker states. / The GOI provides six monthly financial management reports (FMRs) to DPs in December and June. Eligible expenditure for reimbursement by DPs is calculated based on June FMR covering expenditures in the preceding GOI Financial year (April to March). / DPs examine the FMRs and seek clarification from GOI as necessary. Any disparities between the expenditure statements and audited statements are disqualified from the calculation of eligible expenditure for reimbursement. The World Bank submits a consolidated recommendation of the weaknesses and other observations of the FMR along with the eligible reimbursement by DPs. / As an example, expenditure for the states of Bihar, Chhattisgarh, and West Bengal were excluded from the calculation of eligible expenditure for DP contribution for the financial year 2010-11 payment. / 4.4 Climate and Environment Risk: Low / The climate and environmental issues in the SSA are judged to be low. The main area of environment risk is associated with civil works. Several guidelines have been prepared to ensure better construction management, better learning environment, child friendly elements of schools, and health and hygiene on the school premises.

5. Value for Money
5.1 Performance on VfM measures / The indicators under the Effectiveness parameter of the 3Es (Economy, Efficiency and Effectiveness) of VfM in education have shown a positive trend in the last three years of SSA implementation (2007/08 to 2010/11): / Effectiveness Increase in elementary (grades 1 to 8) enrolment from 185 million to 193 million / Increase in gross completion rate at primary level from 90.2% to 97.5% (target: 95%) / Increase in the transition rate (primary to upper primary) from 81% to 85% (target 85%) / Increase in retention at elementary from: / 38 to 55% in states with elementary stage from grades 1 to 8 (target: 45%) / 56 to 81% in states with elementary stage from grades 1 to 7 (target: 70%) / In addition, the elementary education system in India has grown by close to two-thirds, from 750,000 schools to over 1.30 million schools in just seven years, with one million new classrooms built and close to one million new teachers recruited. This is an unprecedented pace of growth - approximately 6,000 new schools every month (50,000 schools constructed in 2009-10). Innovative methodologies for getting children into school have also been promoted. / Over a million teachers were recruited in the year 2011-12 (1.23 million). Social gaps in terms of enrolment across different social categories are reducing. / DFID’s technical co-operation has helped to develop India’s national assessment programme, providing a much-needed platform for quality monitoring, diagnostic analysis, remedial action, better resource targeting and improved school accountability. DFID’s advice has also enabled the first Indian engagement with international learning assessment - OECD’s Programme for International Student Assessment (PISA) Breakeven analysis suggests that DFID technical cooperation offers ‘excellent returns’ predicting a positive rate of return for every child completing grade 8 for the next 10 years. / 5.2 Commercial Improvement and Value for Money / DFID directly manages the Technical Assistance funds. The Technical Support Agency (TSA) was selected through OJEU competition and an output based contracting arrangement was renegotiated in the year 2011 for better VfM. Specific and measurable milestones with target dates are agreed with TSA and are monitored on a monthly basis. All other low value suppliers/contracts (up to £25,000) are engaged either through nomination or bidding processes for managing short term studies and other related supplementary activities; e.g. The SSA Fiduciary Risk Assessment contract; design and dissemination of the proceeding of the conference on In-Service development of Elementary Teachers etc. DFID team visited the Gyanshala project headquarters and reviewed their procurement and financial management procedures. A proper inventory is maintained for all the items procured from DFID funds. / Procurement under Financial Aid is managed by respective state implementation agencies adhering to the standard GOI procurement standards. Some good practices to facilitate commercial improvement and VfM: Most states have introduced e-procurement system and all procurement plans are uploaded on their official SSA website; Electronic accounting software (TALLY) is used in most states for financial management; Procurement and Financial Management specialists on behalf of the DPs review the procurement plans and ensure that all procurement practices are in compliance with the standard practices set out in the Financial Management and Procurement manual prepared by the GOI with input from DPs. The Ministry of Human Resource Development at the national level has developed online software to monitor progress of procurement contracts in excess of Rupees 1 million. / 5.3 Role of project partners / SSA is a partnership between National and State governments and three donor partners (DPs): The World Bank, European Union and UK’s DFID. Around 90% of the programme is funded from India’s own resources, with the balance being provided by the donor partners. Donor partner support to SSA is provided through a sector wide approach (SWAp). DPs participate in the Joint Review Missions and review status of the progress and issues. DPs actively contribute on activities related to programme planning, implementation, monitoring and evaluation, including financial management/procurement capacity of states and districts and agree on actions to support the weaker states. DFID is the sole provider for technical assistance to government of India’s SSA programme, on behalf of the DPs. / 5.4 Does the project still represent Value for Money : Y/N / DFID’s financial contribution has added value to SSA by: / increasing the rigour with which SSA is supervised; / improving the technical quality of GOI programme management and design and strengthening monitoring and evaluation arrangements; / historically supporting technical improvements in Indian education, particularly pedagogy, teacher development, curriculum development, materials development, research, monitoring and evaluation; / providing policy advice which is sensitive to and understanding of India’s machinery of government in education; / being a ‘mature voice of reason and balance’ among the DPs and strengthening partnership processes; / with other DPs, giving greater credibility to GOI programmes we have supported; / sharing international experience; and helping to boost the confidence and capacity of the GOI and State staff responsible for programme implementation. / See Colclough (2010) for further detail. / 5.5 If not, what action will you take? / Not applicable.

6. Conditionality
Update on specific conditions There are no conditions. / The Memorandum of Understanding signed between DFID and the government of India sets the exit for DFID at 31 March 2013. However, a letter from GOI requests that to align with World Bank’s agreement with GOI, DFID’s support to SSA programme should be restricted up to 30 September 2012. / As per the partnership agreement with GOI, DP’s disbursement of claim is based on FMRs, for eligible expenditure incurred for the prior fiscal year. Any discrepancies between the reported programme expenditures and the consolidated audit reports will be disqualified for the calculation of eligible expenditure. To this effect, expenditure incurred by the states of Bihar, Chhattisgarh and West Bengal were excluded from the calculation of eligible expenditure for DP contribution for the financial year 2010-11 due to persistent and longstanding weaknesses in the financial management systems. A letter was sent to GOI to this effect and appropriate action sought to mitigate the problem.

7. Conclusions and actions
The SSA programme ends in March 2013. Action items for 2012 include: / Clarification on the issue of early exit in September 2012 with GOI; / DFID needs to execute its exit in agreement with GOI and the DPs which includes discussion on the closure of the Technical Cooperation Fund; / Preparation for third-party End of Project (EoP) analytical report with DPs / Planning for project closure within DFID including adequate time and human resource, including planning for the Project Completion Report.

8. Review Process
The annual review was completed by the DFID education team, including members that participated in the 14th and 15th Joint Reviews. The DFID governance advisor also participated in the review. / The 14th and 15th Joint Review Missions (JRM) held in July 2011 and January 2012 respectively informed this review. Representatives from Central and State Governments and a team representing the Development Partners are the members of the review mission. The July mission (14th JRM) was a desk review when the states reported progress against the SSA goals to the mission. The January mission (15th JRM) has conducted field visits in 10 states. / All available government data, independent reports, Joint Review Aide Memoires and Monitoring Results Frameworks were reviewed during the annual review. / Project scoring has been done by the team.