## A1 Goal, Purpose, Risk
Annual Review (reviewed August 2010)
ARIES Project Code | 201601
ARIES Project Description | Interim Support to Education Programme (INSTEP)
A1: Goal, Purpose, Risk
Goal
Goal statement | Kenya on track to meet MDGs 2 & 3
Indicator 1 | Primary School Net Enrolment Rate
Milestone for this review (if any) | Girls: 94%; Boys: 95%
What progress has been made in the period covered by this review? | Girls: 92.3%; Boys:90.6%
Indicator 2 | Primary School Completion Rate
Milestone for this review (if any) | Girls: 80%; Boys: 89%
What progress has been made in the period covered by this review? | Girls: 74.4%; Boys:79.2%
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Information from Kenyan Ministry of Education EMIS indicates slightly off target for net enrolment, significant decline in primary completion rate, particularly for boys.
Goal Recommendation 1 | Renewed emphasis should continue to be applied to improving the quality of education, as well as increasing equitable access, especially in marginalised, hard to reach north-eastern areas and overcrowded urban slums.
Goal Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Improved access, quality and accountability in both state and low-cost private education systems
Indicator 1 | Primary Gross Enrolment Rate in urban slums
Milestone for this review (if any) | 95%
What progress has been made in the period covered by this review?
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Primary Gross Enrolment in arid lands (Eastern, North East and Coast)
Milestone for this review (if any) | Girls: 53%; Boys: 66%
What progress has been made in the period covered by this review?
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Average rates of teacher absenteeism
Milestone for this review (if any) | 10%
What progress has been made in the period covered by this review?
What progress has been made in the period covered by this review? | 13% (UWEZO Kenya 2011 Annual Assessment)
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Purpose assumptions continue to be valid but too early in the project implementation to see any effect.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | With different project components starting in January, February, September and October 2011, limited evidence so far to indicate that the achievement of the Purpose can be attributed to progress made in delivering the Outputs.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | Ditto
Purpose Recommendation 1 | Renewed emphasis should continue to focus on improving access, quality, equity and accountability, particularly in disadvantaged arid areas and urban slums.
Purpose Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 3 | 3
Purpose Justification | Progress limited but satisfactory when different start dates of project components are taken into account.
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | Some of the baseline and milestone data was unavailable when the project was designed.
Logframe Recommendation 1
Logframe Action Point 1 | Give number of schools actually registered other than percentages
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision?
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Improved access and quality in private schools in urban slums
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.6
DFID Share revised/needs revision? | Yes
If Yes, why was/is this? | The target schools were increased from 700 to 1250 in agreement with senior management based on a targeting report filed by the Kenya Independent Schools Association (KISA) and the text books were more expensive than originally estimated due to inflationary effects. | 1
Original or Revised DFID Share | 5314929 | 2
3
Indicator 1 (leave blank if standard indicator) | Children in slum schools benefiting from textbooks | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) |  | 0
Progress made in the period covered by this review, including numbers. | 298,000 children in 1096 private primary schools, grades P1 - P8 in Nairobi, Mombasa, Nakuru and Kisumu received textbooks for 6 core subjects and other supplementary materials.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | In-year dropout rates in slum schools
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Unspecified
Progress made in the period covered by this review, including numbers | Too early to assess and difficult to attribute dropout to lack of textbooks
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Slum schools registered with Ministry of Education
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 70%
Progress made in the period covered by this review, including numbers | Basis for this percentage unclear. The number of low cost private primary schools registered with KISA has risen from 1,250 to over 1,600 during the past year, but this has not yet translated into an increase in the number of these schools registered with the Ministry of Education.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 3 | 0.5
Impact Weighted Score | 15 | 0.15
Justification for the Score | The books were delivered to all the intended low cost private schools in good time; the project turn around period was however very brief resulting in some degree of dissatisfaction among the Kenya Publishers' Association & the Ministry officials.
Output 1 Recommendation 1 | Need numbers of schools actually registered rather than percentages
Output 1 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Improved access and quality in state schools in arid lands
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.5
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 3000000
Indicator 1 (leave blank if standard indicator) | Additional multi-grade school places created
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 5000 girls, 5000 boys
Progress made in the period covered by this review, including numbers | Premature to assess this as programme only started in September
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Teachers trained in multi-grade instruction
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 250
Progress made in the period covered by this review, including numbers | Premature to assess this as programme only started in September
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Number of children benefitting from scholarships
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 650 girls, 450 boys
Progress made in the period covered by this review, including numbers | Additional 399 girls & 200 boys from poor backgrounds benefitting from Equity Group Foundation Youth Education scholarships. When combined with other 500 Equity scholarships, this totals 1,099. (This milestone should be revised to reflect only the scholarships provided by DFID).
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 3 | 0.5
Impact Weighted Score | 12.5 | 0.125
Justification for the Score | The scholarships programme started in the first quarter of 2010 and has benefitted 399 girls and 200 boys. The other innovation projects started in the second quarter of 2011 hence premature to assess their progress.
Output 2 Recommendation 1 | Units costs of scholarships should be compared to ensure maximum VfM
Output 2 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Improved accountability and financial management
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 45%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.9
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 3000000
Indicator 1 (leave blank if standard indicator) | School Management Committees with advance notice of MoE grants
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 95%
Progress made in the period covered by this review, including numbers | Achieved at District level rather than through School Management Committees
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Schools established with Trust Funds
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 500
Progress made in the period covered by this review, including numbers | Too early to have established
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Agreed actions from extended forensic audit implemented
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 50% (tbc)
Progress made in the period covered by this review, including numbers | Final forensic audit reports not yet released, but there has been progress on 4 out of 5 key recommendations from the draft audit (unique reference numbers for schools, advance publication of school grants, entirely electronic transfers of school grants, and implementation of IFMIS).
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 3 | 0.5
Impact Weighted Score | 22.5 | 0.225
Justification for the Score | A website was established for the advance announcement of government grants to schools. But there has been slow progress on implementation of the recommendations from the (still draft) forensic audit.
Output 3 Recommendation 1 | More needs to be done to achieve great accountabilty levels among parents and local communities on school financing and spending. This will be taken forward under the Education Accountability Fund under the Drivers of Accountability Programme.
Output 3 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy)
Impact Weighting (must = 100) | 100%
Total Impact Score | 50 | 0.5
Output Risk | Medium | 2
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners
DFID staff | X
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility. | Consultation between DFID Africa Regional Dept and members of DFID Kenya team
Scoring Recommendation 1 | In future, when there is a serious fraud case that overshadows a programme, more dedicated staff time should be allocated to getting different project components off the ground quickly through non-government channels.
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Finding the right balance between working with the Ministry (rather than in parallel to the Ministry) in the aftermath of serious financial mismanagement, continues to be a challenge
Working with Partners Recommendation 1 | Implementing partners should be encouraged to work to strengthen Governmment capacity centrally and locally, with particular emphasis on building accountability at school and community levels.
Working with Partners Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | Trying to introduce more transparent, accountable processes is a fraught and tortuous process if, as here, there is a lack of strong political leadership in enhancing professional integrity, due diligence and corporate responsibility.
Best Practice / Innovation Recommendation 1 | Significant small steps in establishing greater corporate commitment and accountability should be encouraged incrementally, eg through developing websites where information about resource allocations (teachers and grants) can be easily accessed, and supporting local initiatives to hold officials and school staff to account for the provision of education services.
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Bridging the gap between a 5 year Education programme, that has been seriously undermined by financial irregularities, and a new 4 year investment can be severely undermined when contractual processes (eg OJEU) are very slow to get off the ground.
Project Management Recommendation 1 | DFID monitoring and reporting processes should be more flexible to the need for extended timelines in response to the particular planning and preparation difficulties that can arise from high fiduciary risk in fragile situations.
Project Management Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | If DFID wants to continue to keep communication lines open with Government officials under scrutiny in the aftermath of serious financial malpractice, the likelihood that this will entail working in environments where the Ministry's staff morale and motivation is weak and lacking in commitment, will be very high.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
2883094 | Programme Memorandum: Interim Support to Education Programme (INSTEP) DFID Kenya 13 December 2010
2883094 | INSTEP submission
3248845, 3248845 | MEDIAE Submission & Proposal, and contract & budget
3322460, 3322480 | NAO 2009 & 2010 reports on empowering school communities:text books provision in Kenyan primary schools
3177811 | Aga Khan Foundation Submission and Proposal
2981272 | Equity Group Foundation (EGF) Accountable Grant and Proposal
3248173 | EGF progress reports
2926721 | Kenya Independent Schools Association (KISA) contract & proposal
3168960 | KISA text books distribution project report
3263762 | Charles Kendall Report on text books distribution
2960766, 2965833, 3293824, 2964067 | Media consultant contract, TORs, report and work plan
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause? | No but the project got underway in the aftermath of serious financial malpractice, which continued to dominate the working environment and soured relations with the Ministry of Education.
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | The project is likely to be sustained, because, although it is premature to assess progress against all the indicators, it is an interim programme that will feed into a larger 4 year commitment, with most components being carried over.
Sustainability Recommendation 1 | The logframe should be adapted and expanded into a larger timescale with more realistic baselines and indicators.
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | Renewed emphasis should continue to be applied to improving the quality of education, as well as increasing equitable access, especially in marginalised, hard to reach north-eastern areas and overcrowded urban slums.
R2 | 0
R3 | 0
A1: Purpose
R1 | Renewed emphasis should continue to focus on improving access, quality, equity and accountability, particularly in disadvantaged arid areas and urban slums.
R2 | 0
R3 | 0
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Need numbers of schools actually registered rather than percentages
R1.2 | 0
R1.3 | 0
R2.1 | Units costs of scholarships should be compared to ensure maximum VfM
R2.2 | 0
R2.3 | 0
R3.1 | More needs to be done to achieve great accountabilty levels among parents and local communities on school financing and spending. This will be taken forward under the Education Accountability Fund under the Drivers of Accountability Programme.
R3.2 | 0
R3.3 | 0
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | In future, when there is a serious fraud case that overshadows a programme, more dedicated staff time should be allocated to getting different project components off the ground quickly through non-government channels.
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Implementing partners should be encouraged to work to strengthen Governmment capacity centrally and locally, with particular emphasis on building accountability at school and community levels.
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | Significant small steps in establishing greater corporate commitment and accountability should be encouraged incrementally, eg through developing websites where information about resource allocations (teachers and grants) can be easily accessed, and supporting local initiatives to hold officials and school staff to account for the provision of education services.
R2 | 0
R3 | 0
Project Management
R1 | DFID monitoring and reporting processes should be more flexible to the need for extended timelines in response to the particular planning and preparation difficulties that can arise from high fiduciary risk in fragile situations.
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | The logframe should be adapted and expanded into a larger timescale with more realistic baselines and indicators.
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | Give number of schools actually registered other than percentages
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
AP2.1 | 0
AP2.2 | 0
AP2.3 | 0
AP3.1 | 0
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3