## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 114491
ARIES Project Description | Public Financial Management
A1: Goal, Purpose, Risk
Goal
Goal statement | An effective Public Financial Management system that facilitates the delivery of better public services to improve the lives of the people of Nepal.
Indicator 1 | Extent to which the Government of Nepal budget allocation is consistent with policy planning and Poverty Reduction Strategy (PRS) priorities.
Milestone for this review (if any) | N/A
What progress has been made in the period covered by this review? | The best assessment of the goal statement should come from the planned update of the PEFA 2006 Assessment. It is now scheduled to start in 2012, although it is estimated that it will take 1 year to finalise (the first assessment took 18 months). A proposed 'Independent Impact Assessment' of PEFA implementation is also due to be completed early 2012. This could, give a useful assessment for the next review.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Reduction (by %) of unaccounted funds in health & education sectors including funds transferred to local bodies.
Milestone for this review (if any) | N/A
What progress has been made in the period covered by this review? | At present information against this indicator is not available. The main source for this data was anticipated to be from public expenditure tracker surveys (PETS) or expenditure reviews. The 2011 PETS in local government did provide indiactions as regards unaccounted funds, but by degree of risk, not by specific % of funds. DFID should consider revising this indicator if this data can not be collected. In 2012 PETS are planned for both health and education. This may enable some additional reporting against this indicator in the next review.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | GoN has started the process of rolling out PFM reform to deliver improvements at the sectoral and local level, where services are delivered. PEFA Implementation Units have been established for 3 sectors / line ministries, including Ministry of Local Development, but not yet in health and education. The first District has also set up a PEFA Implementation Unit. Once fully established in each ministry and Dsitrict, these units should play a part in coordination, roll out of activities, building ownership and capacity. PEFA Secretariat are also planning to develop the first PEFA Guideline Manuals for 2 pilot sectors from early next year - Education and Health plus MLD are likely pilot sectors/ministries.Finally, GoN has also announced plans to pilot newly agreed 'Nepal Public Sector Accounting Standards' (NPSAS - meeting international standards) in 2 Ministries next year - including one of education and health.
Goal Recommendation 1 | Revise indicators to ensure they can be measured, when logframe is updated in January into the new format.
Goal Action Point 1 | Update and revise logframe
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | A more efficient Public Financial Management system with increased transparency and accountability to citizens.
Indicator 1 | PEFA scores
Milestone for this review (if any) | 3 of the 6 dimensions increased by at least one step
What progress has been made in the period covered by this review? | We are currently unable to report against this indicator as the repeat PEFA Assessment is planned to start in FY2011/12 for delivery in FY2012/13, supported by the PFM MDTF.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Perception surveys
Milestone for this review (if any) | Key stakeholders perceive the Public Financial Management system to be more transparent, accountable, responsible and effective. (2011 survey)
What progress has been made in the period covered by this review? | We are currently unable to report against this indicator as the project implementation has only just started and perception surveys have not yet been conducted. Perception surveys will be conducted over the next year, allowing for reporting against this indicator at the next review.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | # of reports published by specialised organisations on national and local budgets
Milestone for this review (if any) | Capacity development of specialised organisations
What progress has been made in the period covered by this review? | DFID should consider revising this indicator to better measure impact of demand side activities. Please note that the MDTFs demand side work is scheduled to be delivered through a specific demand side sub-project. This sub-project (PRAN) has only just been submitted to the MDTF for discussion and approval. An impact indicator should be lifted from this sub-project document, to enable monitoring of performance.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Purpose assumptions have not changed. Sections of the bureaucracy, supported by a few political leaders, have prioritized the PFM agenda, as a core principle of development. The fact that the government has initated and paid for TSA and IFMIS reforms with limited international support, due to the slow start of of this programme, is a strong indicator that there is some government ownership and leadership. Some PFM institutions have prepared good quality strategy document related to PFM - the overall PFM Strategy Document driven by the PEFA Secretariat, hosted in the FCGO-Ministry of Finance is one example; the OAG Strategic Plan Document and Procurement Strategy Document are other examples. However, this work is being delivered within a broader reality of high levels of patronage, a lack of political attention (political leaders focused on the peace agreement) and vested interests. The planned political economy analysis of PFM reform, for 2012, is therefore critical. This should enable a details assessment of purpose assumptions and update on these assumptions for the next annual review.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | At present given the early stages of the project evidence is limited. Indicators are that the forthcoming PEFA assessment is expected to show general improvements in the PFM system, which is facilitating the delivery of public services. Data from key sub-sectors, such as health and education, do indicate improvments in service delivery.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | Since the project is only recently starting implimentation, it is too early to make a judgement.Regards Single Treasury System Account (TSA), government has initiated reforms, with an agreement that the cost of the work will be re-embursed by the project. Through this initiative, government has rolled out TSA to 38 districts, 7117 out of 14,000 spending unit bank accounts have been closed and over 30% of the national budget is now going through the TSA.
Purpose Recommendation 1 | The PFM Thematic Donor Group, jointly chaired by WB and EU, has started to operate. This is a good start to begin dialogue on PFM reform with the government. The Group plans to establish linkage with the PEFA Secretariat as well as with the donor heads group (DPG). This needs to be pursued so that we can motivate government to take full ownership of PFM reform.
Purpose Action Point 1 | PFM Thematic Group meeting will take place regularly (now planned for every two months or earlier as required).
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 3 | 2.8
Purpose Justification | The PFM MDTF has only just started implimentation.There is therefore no data yet against which to score the purpose. Progress was delayed by slow World Bank procedures and the length of time taken to receive internal Bank and Government of Nepal (GoN) approvals of the various 'sub-project's under the MDTF. Currently there are 3 sub-projects. The first 'Strengthenign PFM Systems' has just been signed off by the World Bank and GoN and has been effective since October 31, 2011. The WB fielded an implementation support mission in November to accelerate implementation. Progress has also been made (as cited above) due to the agreement to re-emburse government costs for TSA implimentation. The second sub-project 'Strengthening the Office of the Auditor General' has just been submitted to the MDTF for approval and should be signed off by the MDTF, WB and GoN by end 2011. The third sub-project 'Promoting Accountability in Nepal' (PRAN) has also been submitted to the MDTF for approval and should be signed off by the MDTF, WB and GoN by end 2011.
Risk
Project Risk Rating or latest Overall Risk Score. | Medium
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | New logframe format is required. Also some indicators need to be updated and / or improved, reflecting new sub-projects / scope of work supported by the MDTF, available data and the indicators that will be measured in the sub-project documents.
Logframe Recommendation 1 | Update logframe
Logframe Action Point 1 | Update logframe
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1 | N/A
DSO Action Point 1 | N/A
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1 | N/A
CCM Action Point 1 | N/A
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Treasury Single Account (TSA) implemented at District Treasury Comptroller’s Office (DTCO)
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share | 47% | 2
3
Indicator 1 (leave blank if standard indicator) | Number of DTCOs where the TSA has been implemented | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 12 or more | 0
Progress made in the period covered by this review, including numbers. | Whilst the sub-project to be supported through MDTF (SPFMS) only became effective on October 31, 2011, due to the retroactive financing agrement with the GoN TSA has now been implemented in 38 districts, covering 38 DTCOs. 7117 GoN spending unit bank accounts have been closed. 60 DTCOs should be under TSA by July 15, 2012.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Cash flow management and payment/receipt settlement through DTCO
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 12 or more
Progress made in the period covered by this review, including numbers | As above, this has reached to 38 districts, covering 38 DTCOs.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 1 | 1
Impact Weighted Score | 20 | 0.2
Justification for the Score | Significant progress has been made, far more than anticipated in the results framework.
Output 1 Recommendation 1 | Progress needs to be maintained. A proposal to spread the TSA in 2012, to include the Kathmandu DTCO, will mean about 60% of public expenditures are under TSA. If implimented, this would be a major achievement. Given the scale of this work, progress should be monitored and supported. There are major challenges and risks in managing the Kathmandu roll-out: the 2 major risks are i) technical (the GoN, supported by the MDTF, must install a larger server and more work stations before Kathmandu is brought on line, to manage the work-load) and ii) staff numbers - the Kathmandu DTCO will need to increase its staff from 40 to 70 or 80. As appointing new staff is often a slow process, GoN may need to take a flexible approach to transfers-in of existing staff to manage this process sucessfully.
Output 1 Action Point 1 | Monitor the risks and support mitigating measures for the Kathmandu DTCO roll-out in 2012
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 | There is a risk that corruption/patronage can creep into the new TSA system, as the DTCO become the key official for managing all GoN payments in a District: however the risks may be lower then in other countries as the main source of corruption / rent seeking is often when the DTCO also does the pre-audit of the transaction. In Nepal they do not. Risks can be further mitigated through i) the introduction of a module for bill tracking (tracks the progress of payment requests and signals those that are delayed beyond the normal time) and ii) payments to be made directly through transfers (not cheques) to the suppliers Bank account.
Output 1 Recommendation 3 | The final major risks to TSA roll out is from push-back from those loosing power (loosing control of finances) and the risks that a new federal government structure will undermine the ability to roll this out in the longer run to local levels. It is understood that the risk of push-back was highest when the TSA system was first proposed and introduced. Now that ministries have accepted the system and are used to the new system, the risk is reducing. In future, to help mitigate this risk, line ministry staff can be given direct access to view the TSA system, so they can track transactions - to reduce confusion/conflict/incentivise speedy payments. Future decisions as to whether sub-national governments adopt the same TSA systems are very political. There is a risk that sub-national governments reject the TSA system. There is no barrier to sub-national governments using the same systems (retaining central fiscal controls), with some of the decision making power over spend decentralised to these sub-national bodies and some of the processing to below the current DTCOs (a new lower level). It is understood from international experience that if the TSA system is already operational, it is less likely that sub-national governments will try and adopt completely different systems.
Output 1 Action Point 2 | Monitor the risk, apply identified mitigating actions and report any concerns that arise. The 2 additional risk mitigation actions identified above, should be implemented, if appropriate.
Output 1 Action Point 3 | Monitor the various risk, through a risk-matrix, apply identified mitigating actions and report regularly (note other risks include, risks around poor connectivity; load shedding; and staff turnover.
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | TSA implemented at the FCGO
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 10%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.2
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 47%
Indicator 1 (leave blank if standard indicator) | Status of implementation of TSA at the FCGO
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Procurement process started and company starts work (2011)
Progress made in the period covered by this review, including numbers | Procurement for this work is an ongoing process over the lifespan of the MDTF. Procurement of necessary equipment for initial stages was completed in 2011. Other procurement (mainly the servers for upgrade of IFMIS) will be procured in the second half of 2012. For maintenance and support of the IFMIS, WB has not procured the delivery agent as yet (due to the slow approval of the project - as above). To address this delay, 2 national consultants were provided 6 months extensions on government request through the DFID ESP. Their further extension will now be supported through the MDTF, as the sub-project (Stengthening PFM Systems - SPFMS) is now operational.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Network system established
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | System analysis (2011)
Progress made in the period covered by this review, including numbers | Not yet started - delayed due to slow start of the sub-project - as above.
Indicator 3 (leave blank if standard indicator) | Network reporting and FMIS
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Preparation and development (2011)
Progress made in the period covered by this review, including numbers | Not yet started - delayed due to slow start of the sub-project - as above.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 3 | 0.5
Impact Weighted Score | 5 | 0.05
Justification for the Score | Limited progress has been made through the procrement processes, but other indicators are lagging due to slow project implimentation cited against the purpose statement. However, progess has started to pick up and with the sub-project now approved, this work is expected to be delivered as planned in the next year (2012).
Output 2 Recommendation 1 | Ensure delivery pace improves now sub-project is approved.
Output 2 Action Point 1 | Ensure delivery pace improves now sub-project is approved.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Cash Receipts and Payments (CR&P) Statement and Budget/Actual Comparative Statement for budgetary and non budgetary entities in accordance with Part 1, Cash IPSAS
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 15%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.15
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 47%
Indicator 1 (leave blank if standard indicator) | Extent to which CR&P and Budget/Actual Comparative Statements are prepared
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Selected entities trained in the preparation of CR&P and Budget/Actual Comparative Statements in IPSAS format by 2011
Progress made in the period covered by this review, including numbers | Not yet started - delayed due to slow start of the project - as above.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Preparation of CR&P Statement by all budgetary and non-budgetary controlled entities
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | All entities trained in the preparation of CR&P and Budget/Actual Comparative Statements in IPSAS format by 2010
Progress made in the period covered by this review, including numbers | The World Bank and the Government of Nepal (GON) has approved the project in October. Good progress has been made in the past 2 months and we are fairly confident that the programme will pick up speed in the coming year
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 3 | 0.5
Impact Weighted Score | 7.5 | 0.075
Justification for the Score | The World Bank and the Government of Nepal (GON) has approved the project in October. Good progress has been made in the past 2 months and we are fairly confident that the programme will pick up speed in the coming year
Output 3 Recommendation 1 | Ensure work starts now sub-project is approved.
Output 3 Action Point 1 | Ensure work starts now sub-project is approved.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | State Owned Enterprises (SOEs) produce Accrual financial statements in accordance with IAS/IFRS.
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 5%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.05
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 47%
Indicator 1 (leave blank if standard indicator) | Preparation of accrual statements by SOEs selected to pilot procedures
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Selected SOEs trained in the preparation of accrual statements in IAS/IFRS format and published the statements in the new format by 2011
Progress made in the period covered by this review, including numbers | The World Bank and the Government of Nepal (GON) has approved the project in October. Good progress has been made in the past 2 months and we are fairly confident that the programme will pick up speed in the coming year
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 3 | 0.5
Impact Weighted Score | 2.5 | 0.025
Justification for the Score | The World Bank and the Government of Nepal (GON) has approved the project in October. Good progress has been made in the past 2 months and we are fairly confident that the programme will pick up speed in the coming year
Output 4 Recommendation 1 | Ensure work starts now sub-project is approved.
Output 4 Action Point 1 | Ensure work starts now sub-project is approved.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5 | Government of Nepal produce consolidated Cash Receipts and Payments (CR&P) Statement
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 5%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.05
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 47%
Indicator 1 (leave blank if standard indicator) | # of consolidated financial statements tested produced
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Train appropriate accounting personnel on consolidation procedures and commitment accounting by 2011
Progress made in the period covered by this review, including numbers | The World Bank and the Government of Nepal (GON) has approved the project in October. Good progress has been made in the past 2 months and we are fairly confident that the programme will pick up speed in the coming year
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | # of consolidated financial statements tested and produced.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Test consolidation procedures on financial statements for all controlled governmental entities (within central government) to include budgetary, non-budgetary, and SOEs by 2011
Progress made in the period covered by this review, including numbers | Not yet started - delayed due to slow start of the project - as above.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 | 3 | 0.5
Impact Weighted Score | 2.5 | 0.025
Justification for the Score | The World Bank and the Government of Nepal (GON) has approved the project in October. Good progress has been made in the past 2 months and we are fairly confident that the programme will pick up speed in the coming year
Output 5 Recommendation 1 | Ensure work starts now sub-project is approved.
Output 5 Action Point 1 | Ensure work starts now sub-project is approved.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6 | Well functioning PEFA secretariat established
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 25%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.25
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 47%
Indicator 1 (leave blank if standard indicator) | PEFA secretariat plays catalytic role in PFM reform process
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Employees allocated to PEFA secretariat. External consultants appointed, manuals, directives prepared for PFM assessments and in house PEFA assessment (2011)
Progress made in the period covered by this review, including numbers | The PEFA Secretariat has been established and is increasingly active, with government staff deployed. Other milestones are yet to be implemented, but indications are that they will be delivered within a short period.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Develop implementation mechanism of overall PFMRP strategy
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Work with all line ministries to prepare an overall strategy (2011)
Progress made in the period covered by this review, including numbers | PEFA Units have been established in a few, but not all, line ministries and Districts. These have started to coordinate with the PEFA Secretariat, but more units need to be established and work completed before an overall strategy can be developed and finalised.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | Reinforce PEFA Implementation Units (PIU) in line ministries
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Establish PEFA Implementation Units (PIU) in 50% of line ministries and provide training to key staff (2011)
Progress made in the period covered by this review, including numbers | PEFA Implementation Units (PIU) have been, or are currently being, established in 3 of line ministries - health, education and local government. The GoN PFM Steering Committee has decided to complete implementation in early 2012.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | Capacity of accounting professionals in financial planning and programming
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Training Needs Assessment Undertaken (2010-11)
Progress made in the period covered by this review, including numbers | The World Bank and the Government of Nepal (GON) has approved the project in October. Good progress has been made in the past 2 months and we are fairly confident that the programme will pick up speed in the coming year
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 | 3 | 0.5
Impact Weighted Score | 12.5 | 0.125
Justification for the Score | Whilst the MDTF has been slow to provide supoort, GoN actors, particularly the FCGO have kick started this work, establishing and staffing the PEFA Secretariat, managing the roll-out of Implimentation Units into line ministries and Districts. Whilst implimentation is behind anticipated schedule, it has been driven by national partners and further progress is expected to be made in 2012.
Output 6 Recommendation 1 | Monitor and ensure delivery pace improves in 2012
Output 6 Action Point 1 | Monitor and ensure delivery pace improves in 2012
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7 | Nepali CSOs use Social Accountability Tools and Techniques
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.4
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share | 47%
Indicator 1 (leave blank if standard indicator) | # of CSOs using SA tools by trained practitioners to promote transparency, efficiency and equity in PFM
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Design training modules on SA tools and techniques (NCBI/ICBP) (2010)
Progress made in the period covered by this review, including numbers | Not yet started: relevant sub-project only just circulated for comments and not yet approved.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | # of grants awarded to NGOs for adaptation and application of best practice SA approaches and tools by practitioners to influence PFM
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Award 4 grants to pilot and develop SA techniques and tools in PFM (GMA) (2010)
Progress made in the period covered by this review, including numbers | Not yet started: relevant sub-project only just circulated for comments and not yet approved.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | # of NGOs using SA approaches to improve PEM
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Design and initiate web-based platform for capturing and sharing knowledge linked to other knowledge centres (NSAC/PCU) (2010)
Progress made in the period covered by this review, including numbers | Not yet started: relevant sub-project only just circulated for comments and not yet approved.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | Monitoring and evaluation of funded activities
Is this a Standard Indicator? | No
Select standard indicator from drop down list
Milestone for this review (including number, if any) | Design tools for monitoring and evaluation (NRI) (2010)
Progress made in the period covered by this review, including numbers | Not yet started: relevant sub-project only just circulated for comments and not yet approved.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 | 4 | 0.25
Impact Weighted Score | 5 | 0.05
Justification for the Score | Unable to score this output at this stage.
Output 7 Recommendation 1 | Monitor progress to ensure speedy approval of sub-project and fast pace for implimentation.
Output 7 Action Point 1 | Monitor progress to ensure speedy approval of sub-project and fast pace for implimentation.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-12-10
Impact Weighting (must = 100) | 100%
Total Impact Score | 55 | 0.55
Output Risk | High | 1.5
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment | X
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner | X
Independent consultant
Donor partners
DFID staff | X
Donor partners | AUSAID
DANIDA
NORAD
Comment here on the Method of Scoring and Scoring Responsibility. | Due to the limited progress of the programme, it was decided to complete a very light touch review, led by DFID staff, and completed in consultation with World Bank colleagues.
Scoring Recommendation 1 | The next annual review should be after a period of significant implimentation and should ideally be a multi-donor review, including GoN and with external support.
Scoring Action Point 1 | Next annual review to be a multi-donor review, including GoN and with external support
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | There is now a coordinated and harmonized approach amongst development partners to address the PFM agenda and increased dialogue with the government on PFM. This is critical and should have been started at an earlier stage.
Working with Partners Recommendation 1 | DFID continues to invest in the set up and activities of the PFM Donor Group - encouraging strong links to GoN (and GoN leadership if possible) and to the DPG, to ensure high level police messages are delivered.
Working with Partners Action Point 1 | DFID continues to invest in the set up and activities of the PFM Donor Group
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | The decision and flexibility shown in agreeing with the GoN to reimburse TSA activities, to enable work to start, before the programme received final approvals, has allowed progress to be made.
Best Practice / Innovation Recommendation 1 | Continue to deliver with such flexibility where necessary.
Best Practice / Innovation Action Point 1 | Encourage flexibility where necessary.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | A decision was made to not seek approval for the MDTF as a whole, but to seek GoN approval for each sub-project. In part because this has required each sub-project to go through lengthly internal WB approval processes and then GoN approval, overall implimentation has been significantly delayed.
Project Management Recommendation 1 | Consider ways to speed up approval of future sub-projects.
Project Management Action Point 1 | Consider ways to speed up approval of future sub-projects.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | The planned PEA analysis of PFM to be carried out by the WB (with inputs from us and other donors) should also help to identify where there have been blockages to date and where there may be likely blockages in future implementation We (DFID) are and will continue to push for stronger Government ownership of the PFM agenda. In this respect, it will be important that the PEFA Secretariat is not considered as a kind of project implementation unit for this programme, but more a Government-led and managed unit to help them to coordinate and implement PFM reform
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
3324199 | Logframe
3324175 | Project Memorandum
114491 | Reports and emails saved in project QUEST folder
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1 | N/A
Conditionality Action Point 1 | N/A
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | Since the Project is supporting the government's PFM agenda, the interventions on TSA, IPSAS and PEFA Secretariat are fully owned by the government. Hence, there is a high chance of the work suppoted being sustainable.
Sustainability Recommendation 1 | Continue to press for GoN leadership and ownership of the PFM agenda, at version levels, including through the DPG and PFM donor working group.
Sustainability Action Point 1 | Continue to press for GoN leadership and ownership of the PFM agenda, at version levels, including through the DPG and PFM donor working group.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | Revise indicators to ensure they can be measured, when logframe is updated in January into the new format. | Bandhu Ranjan
R2 | 0
R3 | 0
A1: Purpose
R1 | The PFM Thematic Donor Group, jointly chaired by WB and EU, has started to operate. This is a good start to begin dialogue on PFM reform with the government. The Group plans to establish linkage with the PEFA Secretariat as well as with the donor heads group (DPG). This needs to be pursued so that we can motivate government to take full ownership of PFM reform. | David Osborne
R2 | 0
R3 | 0
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | Update logframe | Bandhu Ranjan
R2 | 0
R3 | 0
A1: DSOs
R1 | N/A
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | N/A
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Progress needs to be maintained. A proposal to spread the TSA in 2012, to include the Kathmandu DTCO, will mean about 60% of public expenditures are under TSA. If implimented, this would be a major achievement. Given the scale of this work, progress should be monitored and supported. There are major challenges and risks in managing the Kathmandu roll-out: the 2 major risks are i) technical (the GoN, supported by the MDTF, must install a larger server and more work stations before Kathmandu is brought on line, to manage the work-load) and ii) staff numbers - the Kathmandu DTCO will need to increase its staff from 40 to 70 or 80. As appointing new staff is often a slow process, GoN may need to take a flexible approach to transfers-in of existing staff to manage this process sucessfully. | David Osborne
R1.2 | There is a risk that corruption/patronage can creep into the new TSA system, as the DTCO become the key official for managing all GoN payments in a District: however the risks may be lower then in other countries as the main source of corruption / rent seeking is often when the DTCO also does the pre-audit of the transaction. In Nepal they do not. Risks can be further mitigated through i) the introduction of a module for bill tracking (tracks the progress of payment requests and signals those that are delayed beyond the normal time) and ii) payments to be made directly through transfers (not cheques) to the suppliers Bank account. | David Osborne
R1.3 | The final major risks to TSA roll out is from push-back from those loosing power (loosing control of finances) and the risks that a new federal government structure will undermine the ability to roll this out in the longer run to local levels. It is understood that the risk of push-back was highest when the TSA system was first proposed and introduced. Now that ministries have accepted the system and are used to the new system, the risk is reducing. In future, to help mitigate this risk, line ministry staff can be given direct access to view the TSA system, so they can track transactions - to reduce confusion/conflict/incentivise speedy payments. Future decisions as to whether sub-national governments adopt the same TSA systems are very political. There is a risk that sub-national governments reject the TSA system. There is no barrier to sub-national governments using the same systems (retaining central fiscal controls), with some of the decision making power over spend decentralised to these sub-national bodies and some of the processing to below the current DTCOs (a new lower level). It is understood from international experience that if the TSA system is already operational, it is less likely that sub-national governments will try and adopt completely different systems. | David Osborne
R2.1 | Ensure delivery pace improves now sub-project is approved. | David Osborne
R2.2 | 0
R2.3 | 0
R3.1 | Ensure work starts now sub-project is approved. | David Osborne
R3.2 | 0
R3.3 | 0
R4.1 | Ensure work starts now sub-project is approved. | David Osborne
R4.2 | 0
R4.3 | 0
R5.1 | Ensure work starts now sub-project is approved. | David Osborne
R5.2 | 0
R5.3 | 0
R6.1 | Monitor and ensure delivery pace improves in 2012 | David Osborne
R6.2 | 0
R6.3 | 0
R7.1 | Monitor progress to ensure speedy approval of sub-project and fast pace for implimentation. | David Osborne
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | The next annual review should be after a period of significant implimentation and should ideally be a multi-donor review, including GoN and with external support. | Bandhu Ranjan
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | DFID continues to invest in the set up and activities of the PFM Donor Group - encouraging strong links to GoN (and GoN leadership if possible) and to the DPG, to ensure high level police messages are delivered. | David Osborne
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | Continue to deliver with such flexibility where necessary. | Bandhu Ranjan
R2 | 0
R3 | 0
Project Management
R1 | Consider ways to speed up approval of future sub-projects. | Bandhu Ranjan
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | N/A
R2 | 0
R3 | 0
D: Sustainability
R1 | Continue to press for GoN leadership and ownership of the PFM agenda, at version levels, including through the DPG and PFM donor working group. | David Osborne
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | Update and revise logframe | Bandhu Ranjan
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | PFM Thematic Group meeting will take place regularly (now planned for every two months or earlier as required). | David Osborne
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | Update logframe | Bandhu Ranjan
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | N/A
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | N/A
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Monitor the risks and support mitigating measures for the Kathmandu DTCO roll-out in 2012 | Bandhu Ranjan
AP1.2 | Monitor the risk, apply identified mitigating actions and report any concerns that arise. The 2 additional risk mitigation actions identified above, should be implemented, if appropriate. | Bandhu Ranjan
AP1.3 | Monitor the various risk, through a risk-matrix, apply identified mitigating actions and report regularly (note other risks include, risks around poor connectivity; load shedding; and staff turnover. | Bandhu Ranjan
AP2.1 | Ensure delivery pace improves now sub-project is approved. | David Osborne
AP2.2 | 0
AP2.3 | 0
AP3.1 | Ensure work starts now sub-project is approved. | David Osborne
AP3.2 | 0
AP3.3 | 0
AP4.1 | Ensure work starts now sub-project is approved. | David Osborne
AP4.2 | 0
AP4.3 | 0
AP5.1 | Ensure work starts now sub-project is approved. | David Osborne
AP5.2 | 0
AP5.3 | 0
AP6.1 | Monitor and ensure delivery pace improves in 2012 | David Osborne
AP6.2 | 0
AP6.3 | 0
AP7.1 | Monitor progress to ensure speedy approval of sub-project and fast pace for implimentation. | David Osborne
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | Next annual review to be a multi-donor review, including GoN and with external support | Bandhu Ranjan
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | DFID continues to invest in the set up and activities of the PFM Donor Group | David Osborne
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | Encourage flexibility where necessary. | Bandhu Ranjan
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | Consider ways to speed up approval of future sub-projects. | Bandhu Ranjan
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | N/A
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | Continue to press for GoN leadership and ownership of the PFM agenda, at version levels, including through the DPG and PFM donor working group. | David Osborne
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3