Annual Review 2018

Title: Health Partnership Scheme (HPS) – Accountable Grant (AG) 2017-19
Programme Value £ (full life): £32.3m / (including extension via Accountable Grant of £2.1m)		Review Date: July 2018
Programme Code: 202208	Start Date: July 2011	End Date: February 2019

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017	2018	2019
Programme Score	A	A+	A++	A	A	A+	A
Risk Rating	L	L	L	L	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case Addendum
DevTracker Link to Log frame:	Logframe

A. Summary and Overview

Description of programme
The Health Partnership Scheme (HPS) funds health partnerships to develop and improve health services in low- and lower-middle income countries (hereafter shortened to LMIC). It harnesses the experience and expertise of UK health institutions and professionals to work with their LMIC counterparts to strengthen health systems and improve essential services through skills transfer, capacity development, and other collaborative work. The Tropical Health and Education Trust (THET) manage the programme.

Originally planned to run from July 2011 to June 2017, DFID extended the HPS until February 2019. An independent evaluation in November 2016[1] concluded that that the scheme, “overwhelmingly demonstrated the effectiveness of the partnership and volunteering approach in supporting health worker capacity strengthening” and that “projects have contributed to health system strengthening by strengthening health worker capacity in terms of their skills, knowledge and confidence.”
[1] Health Partnership Scheme Evaluation Report

The programme extension is funding 20 projects in six countries in Sub-Saharan Africa and Asia. These are delivered by 13 previous HPS partnerships and 7 partnerships that have successfully implemented projects together. Activities started in December 2017. These projects are facilitating 74 health institutions to sustain and scale up the impact of partnerships and improve access to health services.

Country		No. of projects	Focus of projects
Burma		3	Improving children’s cancer services; general practitioner (GP) quality improvement; trauma and orthopaedic training.
Ghana		2	Multi-disciplinary stroke training; primary trauma care training.
Tanzania		1	Mental health and substance use training.
Uganda		9	Palliative care leadership training; community health workers (CHWs) training; medical equipment management for blood transfusion; peer support worker (PSW) training on mental health; emergency obstetric skills; biomedical engineering skills; essential pain management; prevention of infant developmental disability; community eye health services.
Zambia		3	Anaesthesia services development; diabetic retinopathy screening services; critical care nursing education.
Multi-country	Uganda, Tanzania	1	Clinical audits for midwives.
	Ghana, Uganda, Kenya and Tanzania	1	Children’s epilepsy care.

For a detailed breakdown of projects supported by the extension, see Annex 1.

Summary supporting narrative for the overall score in this review
The programme is meeting expectations and is scored at an A. The programme extension has seen good progress on the number of health workers trained. Development and implementation of policies and protocols is proceeding well, with curriculum development also showing progress. There have been some barriers to progress, such as delayed approval for curriculums and the need to reassess local capacity to independently deliver courses integrated into curriculums. While there is encouraging evidence of development for UK volunteers and the strengthening of partnerships, the sample size for this evidence remains small. Similarly, there is progress on improving data collection on health workers but the evidence on improving access to health partnership benefits for service users, a key focus of this programme extension, remains limited. It remains early in the programme extension to robustly assess the effectiveness and sustainability of partnership activities.

The principal achievements of the programme extension are the training of 3,220 health workers (including 1,824 women) and the six institutions that are already implementing new or improved policies and protocols. These figures build on those for the programme between 2011 – 2017 that trained 83,973 health workers (+54 Uganda office[2]), including 41,401 women; supported 135 health institutions such as clinics and hospitals in 32 countries in Africa, Asia and the Middle East; and enabled 37 health institutions to evidence improved health outcomes for patients.
[2] THET’s Uganda Country Office, previously funded by the HPS, has also delivered training to Ugandan health workers.

The programme has continued to facilitate strong engagement from UK volunteers for health partnerships. 1,681 volunteering days were spent overseas and 537 volunteering days were undertaken in the UK in this reporting period. There is some further evidence that UK volunteers benefit from increased clinical and leadership skills, contributing to health workforce development back in the UK.

Recommendations for the year ahead
There are specific recommendations in this annual review to adjust logframe targets for the second half of the programme extension to reflect progress and issues.

This is the final annual review before programme closure in February 2019. The focus of the recommendations are therefore on effective programme closure and facilitating partnerships to focus on ensuring the outputs and outcomes being delivered are sustained beyond programme closure.

To ensure that the programme has a robust evidence base at programme closure, it is recommended that THET continue to develop their offer of assistance to strengthen health partnerships’ ability to: monitor and measure Value for Money (VfM); increase and measure access to women, girls and people with disabilities and collect relevant data on their inclusion; and measure how the HPS has supported the strengthening of participating health partnerships.

To develop evidence on the longer-term outcomes and impact from HPS projects, it is recommended that THET use all available opportunities to meet with previous LIC and LMIC partners and project stakeholders to collect qualitative evidence and data on sustainability and long-term impact for the Project Completion Review (PCR).

To support partnerships to sustain the outputs and outcomes of projects, it is recommended that THET continue to monitor partnership progress against project plans and ensure that all funded activities can be delivered within the remaining programme timeframe. THET should ensure that all partnerships are clear that no further funds will be available through the HPS and that independent plans and resources will be required to continue or exit partnership activities after HPS closure.
## B: DETAILED OUTPUT SCORING

Output 1	Improved and strengthened knowledge and capability in participating health institutions
Output number per LF		1	Output Score	A
Impact weighting (%):		50	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of training course places or other educational opportunities provided to developing country health workers (directly by project or by trainers trained in project), including % of female health workers	85,313 (cumulative) / > 49% female	87, 247 (cumulative) / 49.5% female / (3,220 trained in reporting period / 1,824 women, 56.6%)
1.2 Percentage of tested trainees showing improved skills or performance immediately after training or education.	92% (cumulative) / (96% (1147) in reporting period out of 1,195 assessed)	92% (cumulative), 36,154 of the 39,302 assessed / (94.5% (1113) in reporting period/ of 1178 assessed)

Briefly describe the output and provide supporting narrative for the score
The HPS aims to strengthen the capabilities of health workers. This output measures those projects that seek to do this directly through training and support on clinical and other skills. There has been strong progress on the number of health workers trained in this reporting period, with the partnerships exceeding the target by 1,934. The milestone for this reporting period of 96% of tested trainees showing improved skills or performance immediately after training was missed by 1.5%. Although below target, this reflects a high proportion of those tested demonstrating improved skills or performance, suggesting that the training is effective and well-targeted. However, this represents a minority of health workers trained, which makes it more difficult to assess the quality of training provided overall. An A has been awarded to reflect the over-delivery on training. More evidence of the impact of this training is required to have scored an A+. The programme should adapt milestones in the next phase to proportionally increase the number tested, where appropriate, if there is continued over-performance on the delivery of training.

Output 1.1 Number of training course places or other educational opportunities provided to developing country health workers (directly by project or by trainers trained in project), including % of female health workers
- Some projects significantly exceeded their training targets due to greater than expected demand for training. For example, the Burma project on quality improvement for GPs trained 60 GP quality appraisers rather than the target of 25 – 30. The Community Health Worker (CHW) Programme in Wakiso District, Uganda trained 58 CHW supervisors rather than 34. The Peer Support Workers project in Uganda trained 250 hospital and community staff in adolescent and child mental health rather than the 100 expected.
- Since 2011, the gender is unknown of 12,209 of the health workers trained. Data disaggregation has improved under the programme extension. In this reporting period, partnerships have collected gender disaggregated data for all 3,220 health workers trained, with 1,824 of them being women (56.6%). This increase reflects the health cadres involved in training and that women make up a higher proportion of health workforces, rather than clear evidence that this is due to the extension’s greater focus on access for women, girls and people with disabilities.
- THET, through high quality guidance documents, have supported grant holders to expand their data collection to include whether any of their trainees had disabilities. 123 people trained through 7 projects self- identified as having a disability of some form. This data collection will help our understanding of the extent to which partnerships interact with health workers with disabilities but, given that there is no baseline, it is not possible to comment on whether access to training has increased.

Developing palliative care leaders in Uganda: A partnership between Global Health Academy, University of Edinburgh, and Makerere University, Uganda, developing leadership skills in palliative care, has tried to combat the traditional belief that leadership in Uganda sits with men. Throughout their project they have specifically modelled and showcased the significance of women’s leadership by having the training delivered by expert senior women. 71% of the leadership fellows trained were women. (4/9 clinical officers and 21/26 nurses trained in leadership were women).

1.2 Percentage of tested trainees showing improved skills or performance immediately after training or education
- 94.5% showed an increase in skills or performance reflecting that a high percentage of tested trainees showing increased skills or performance.
- 1,178 trainees were tested. This is fewer than expected. Moreover, the number of health workers trained exceeded expectations. The number tested is therefore a much lower proportion of those trained than expected (36% rather than 62%). This reflects the low testing rates of two projects (10% and 5%). When these projects are removed, the proportion tested increases to 59%.
- The two projects that tested a small proportion of trainees were the community health worker (CHW) (10%) and the peer support worker (PSW) (5%) training projects in Uganda. In the former, all 58 CHW supervisors have been tested. While the 510 CHWs have not been immediately tested due to the available capacity and funding, supervisors will monitor the skills and knowledge they demonstrate over time when interacting when interacting with community members and visiting households. In the PSW project, only staff who received teaching and research training in child and adolescent mental health were formally assessed.
- For those trainees who did not show an increase in skills or performance, reasons stated included a high level of knowledge prior to the training or a poor level of basic knowledge meaning that the training was too advanced for them. Some projects offered them extra support or training to bring them up to the required level.

Sustaining and scaling up clinical audit in Uganda and Tanzania: The partnership between the University of Manchester, Lugina Africa Midwives Research Network (LAMRN) Uganda c/o Uganda Nurses and Midwives Union, and LAMRN Tanzania c/o Catholic University of Health and Allied Health Sciences, which trains nurses and midwives to identify and strengthen audit processes, had a 100% success rate in the number of trainees who were tested that showed an increase in skills and knowledge immediately following the training. Trainees were assessed on their ability to identify and articulate clear auditable problems, their input during the training sessions was observed, they had to present on different protocols, and complete self-assessment evaluation forms. The training included a buddying and mentoring element, which meant that trainees had a solid base of support throughout their training, likely contributing to the high success rate.

Lessons identified this year, and recommendations for the year ahead linked to this output
- THET should work with partnerships to improve the proportion of those tested immediately after training in the next reporting period of those trained or offered other educational opportunities. THET should share learning across partnerships to increase assessment of the impact of training, such as the example of some projects using completion of a pre-training questionnaire as a pre-requisite to join the training.
- It is difficult to assess cumulative percentage of women trained by funded health partnerships as this information has not been recorded for a large number (12,209). While the current cumulative data is that 49.5% of those trained are female, the actual figures for those health workers whose gender is known show that 43,225 women have been trained as opposed to 31,813 men. This accounts for 57.6% of trainees being female. In the year ahead, THET will continue to assist partnerships to collect gender data on those that they train.
- One partnership raised ethical concerns about collecting disability data. THET should continue to gather information and evidence on how to integrate disability and data disaggregation to inform future technical assistance and DFID programmes.

Output 2	Improved and strengthened policies, protocols and curricula in participating health and health education institutions or across health systems
Output number per LF		2	Output Score	A
Impact weighting (%):		25	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of national and institutional health strategies and professional standards / protocols to which projects have contributed for development, review or update	522 (6 in reporting period)	525 (9 in reporting period)
2.2 Number of new or improved policies and professional standards approved and signed off, by end of programme: at national government, subnational government, and institutional level	355 (5 in reporting period)	357 (7 in reporting period)
2.3 Number of medical education curricula to which projects have explicitly contributed for development, review or update.	116 (2 in reporting period)	115 (1 in reporting period)
2.4 Number of new and or improved medical education curricula explicitly approved for teaching.	59 (2 in reporting period)	57 (0 in reporting period)

Briefly describe the output and provide supporting narrative for the score
The HPS aims to strengthen the policies and frameworks that support the development of a strong health workforce. There has been continued progress on strengthening policies, protocols and curricula under the programme extension, with the milestones relating to professional standards, policies and protocols exceeded. However, an A has been awarded to reflect that the milestones for curricula development have not been reached, demonstrating that planning assumptions have not held, with one underestimating the time to negotiate with stakeholders and another over-estimating the capacity of a local faculty to run the training course. This suggests that there is continued need for technical assistance from THET to support projects working on curriculum development with multiple stakeholders to develop realistic project plans.

2.1 and 2.2 National and institutional health strategies and professional standards/protocols
- During this reporting period, three more protocols have been developed, reviewed or updated by projects than anticipated, demonstrating good progress on strengthening policies and standards to support health workers and improve health services.
- This project in Burma that is scaling up and improving access to child cancer services delivered two additional policies and professional standards signed off at institutional level earlier than anticipated.
- Partnerships are also engaging with wider stakeholders to influence national partners on health services development. For example, the Cambridge Yangon Trauma Intervention Project carried out a national survey of intensive care along with a series of workshops to develop a 10 year plan for intensive care delivery in Burma, presenting this to the Ministry of Health to inform policy development. This will be followed up during the Project Completion Review to assess impact.

2.3 and 2.4 Medical education curricula: contributed/approved
- One curriculum out of the expected two has been developed. None have been explicitly approved for teaching yet. This demonstrates that the assumption that having approving authorities in the partnership projects delivering these would allow faster approval at institutional level has not been realised. The Burma child cancer services project has extended the development of the curriculum to consult with stakeholders, including the relevant professional body and government ministry.
- The main aim of the Burma project on trauma care is to ensure that the local faculty can run it from project end, taking over from UK faculty delivery. However, this does not look possible. This suggests that the course is too challenging for the local context and should be initially adapted to suit existing local faculty capacity, with plans to scale up capability over time.
- An additional project in Zambia has made excellent progress in its first six months to develop a framework for developing a higher level curriculum in Critical Nursing Care (from diploma to degree level).

Scaling up and improving access to cancer services for children in Burma: A partnership between Yangon Children’s Hospital (YCH) and Guy’s and St Thomas’s NHS Foundation Trust aims to scale up and improve access to childhood cancer services for children in Myanmar. They have developed a Childhood Cancer Early Warning Signs training curriculum for GPs in collaboration with key stakeholders including the Myanmar Medical Association (MMA) and the Technical Advisory Group to the Ministry of Health and Sports, and the former Minister of Health. The curriculum was piloted among 47 GPs in the first six months, with the training carried out by paediatric oncology experts from YCH. After further pilot training, the curriculum will be reviewed in the next quarter with the aim of being formally approved by the MMA for official roll-out in the future by the end of the project. This process enables the development of a robust curriculum that is adapted to the local context and for the partnership to build strong relationships with the MMA, the umbrella organisation that encompasses the Myanmar GP society and supports GP education, continuous professional development and quality assurance.

Lessons identified this year, and recommendations for the year ahead linked to this output
- THET should work with the Burma project on trauma care to revise their project plan and define what can be realistically achieved in the programme extension and develop their plans for any post-HPS funding support required to deliver the intended project outcome.
- Quantitative indicators are limited in assessing actual impact of policy or curricula uptake and use, as well as the quality and extent of contributions to curricula. DFID and THET should consider ways to capture qualitative data on this for the PCR and future health partnership work.
- THET should continue to scrutinise project timeframes and possible barriers for development and approval at national and institutional level during inception and design of grants. THET should incorporate this learning point into their grants management manual and MEL systems and processes.

Output 3	Stronger and more institutional and country health partnerships that promote and enable mutual learning and skills and technology transfer
Output number per LF		3	Output Score	A
Impact weighting (%):		15	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of new institutional health partnership Memoranda of Understanding or other formal written commitments	100 (2 in reporting period)	100 (2 in reporting period)
3.2 Number of institutional health partnerships strengthened	135 (n/a in reporting period)	135 (n/a in reporting period)
3.3 Number of UK health professional days spent volunteering overseas (OS) + in the UK	86,147 OS + / 11,779 in the UK / (2,094 OS + 483 UK in reporting period)	85,734 OS + / 11,833.5 in the UK / (1,681 OS + 537.5 in the UK in reporting period)

Briefly describe the output and provide supporting narrative for the score

The HPS seeks to ensure that funded projects strengthen the partnerships that deliver them, and the links between the UK and other countries, so that health partnerships and their benefits can continue after the programme ends. The programme has demonstrated continued progress on strengthening partnerships, such as further formal written commitments to institutionalise health partnerships. Partnerships are making good initial progress on objectives to strengthen their learning, communications and joint working and will report on this at the end of the extension phase. On volunteer engagement, while the target number of UK health professional days spent overseas has not quite been reached, the number of volunteering days that were spent in the UK is higher than expected, reflecting greater investment in the inception of partnerships and preparation for partnership activities.

3.1 New institutional formal written commitments for institutional health partnerships:
- The project extension has demonstrated continued formal strengthening of partnerships. Two health partnerships in Uganda that are receiving HPS funding for the first time signed Memorandums of Understanding (MoUs) to formalise their partnerships following the partnership assessment and due diligence process carried out by THET.
- Three other health partnerships have renewed their MoUs to reflect changes. This includes a 5-year university-wide MoU between Nottingham Trent University and Makerere University and the extension of the MoU between the British Paediatric Neurology Association and the Paediatric Neurology Development Association of Southern Africa to include each of the paediatric associations participating in the multi-country project.

3.2 Health partnerships strengthened:
Progress will be fully assessed against this output at the end of the programme, but each health partnership identified partnership development objectives (three expected for large grants, two for small grants) to improve:
- Communication (11 partnerships), including between partners and using appropriate technology
- Joint Working (8 partnerships), including making the partnership a team effort (not solely reliant on two key individuals) and defining clear roles and shared responsibility
- Learning (6 partnerships), including regular lessons learning for continuous evaluation and sharing these outputs with external stakeholders and the wider health partnership community
- Effectiveness (5 partnerships) including raising awareness of the partnership among other staff at the institutions and obtaining the support of senior management
- A few partnerships are widening their recruitment of volunteers and developing better support through a Volunteer Training and Information pack and a Volunteer Handbook
Good initial progress has been made against partnership development objectives. Projects have, for example, reported working on communications by establishing regular teleconferences to improve communications with the local partner, setting up regular meetings with district health officials to improve collaboration and local government awareness of the project, and developing repair and maintenance forms for biomedical engineers and users to collect frequent data on performance for the duration of the project and beyond.

3.3 UK health professional days spent volunteering:
- The overseas target in the reporting period was missed by 413 (20%) and the UK target exceeded by 54.5 (11%). This reflects that projects started one month later than anticipated and more activity happened in the UK to mobilise the projects and prepare for visits and training. This is expected to translate into greater project efficiency and effectiveness. A number of health partnerships are providing remote mentoring to LMIC health workers, increasing support from UK-based activity.
- The overseas volunteering is expected to increase in the second half of the extension phase as projects undertake more activity in country and resolve practical issues for volunteers. The scheme continues to see a significant investment of volunteering time in health partnerships, with the cumulative overseas and UK targets missed by just 0.5%.

Lessons identified this year, and recommendations for the year ahead linked to this output
- Two large health partnerships identified two rather than three development objectives. THET will provide further support in the next quarter for them to assess gaps and identify clear objectives.
- THET will improve assessment of health partnership strengthening by integrating progress reviews against development objectives in quarterly progress meetings and requiring evidence in final partnership reports.
- THET should continue to work with partnerships to overcome barriers to volunteer participation and collect and present evidence of systemic barriers to DFID.
Output 4	Effective and efficient grant funding and strategic management support to projects and health partnership community by the managing agent
Output number per LF		4	Output Score	A
Impact weighting (%):		10	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Amount and % of grant funding disbursed, within agreed timeframes	£21,686,996.30 (100%) / (£855,269.30, 100% in reporting period)	£21,686,996.30 (100%) / (£855,269.30, 100% in reporting period)
4.2 % of timely and appropriate provision of technical assistance to grant holders and other eligible stakeholders, in a 12 month period	95%	100% / [Sample size: 10] / In six month period of AG grants, (1 December 2017 to 31 May 2018)

Briefly describe the output and provide supporting narrative for the score
Given the shorter timeframe for delivery of projects under the Accountable Grant, the timely and effective delivery of grant funding and technical assistance by THET is important to deliver the expected results. An A has been awarded as THET have met expectations in their grant management and technical assistance, disbursing 100% of funding to contract holders within the first quarter of their projects. While 100% of grant holders that responded to an anonymous survey reported satisfaction with the timeliness and quality of technical assistance provided by THET, this only reflects a sample of 10. This is not judged to provide sufficient evidence that THET are exceeding expectations in their technical assistance.

4.1: Amount of grant funding disbursed, within agreed timeframes
- THET has dispersed 100% of the expected funds (£855,269.30 in this period). There were some delays with initial disbursements due to delays in finalising grant contracts. This delayed activities for a small number of projects but has not affected the anticipated project delivery of outputs.
- THET, in consultation with DFID, has developed a robust strategy to manage any grant holder underspends reported. THET will provide additional support where required and will agree with grant holders on how anticipated underspend can be reallocated to activities to further strengthen the project and its impact. Where appropriate, THET will also recommend grant holders allocate further resources to monitoring and evaluation to strengthen the programme’s evidence base.

4.2: % of timely and appropriate provision of technical assistance to grant holders and other eligible stakeholders, in a 12 month period.
- 10 health partnerships completed a short survey on THET’s technical assistance to grant holders. 70% were very satisfied with the quality of the technical assistance and 80% very satisfied with the timeliness of the assistance. This indicates that THET’s technical assistance is meeting partnership needs, although we would like to see greater uptake on future surveys to provide a more comprehensive view of technical assistance provided.
- A selection of comments from health partners are included below:

‘We have worked closely with the grant team to identify and revise project indicators and have received support in addressing challenges in the implementation. The early dissemination of the report templates and guidelines and the Webinar were also useful.’

‘Great technical assistance and always extremely responsive on ema.

‘Impressed by the attention to detail and understanding of the projects - activities and finances.’

Lessons identified this year, and recommendations for the year ahead linked to this output
- THET should continue to respond to technical assistance needs in a timely and effective way, sharing lessons and evidence across partnerships.
- THET should seek to increase volunteer responses to surveys and other forms of data collection at the close of the programme.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The expected impact is more effective and efficient health service provision. Health partnerships contribute by strengthening human resource capacity. The quality and efficiency of health service provision depends on many factors, including governance and leadership, financing, infrastructure, technology and information systems, the supply of health workers, and engagement with communities.

The planned outcome from the project’s health partnerships is more effective and efficient health systems, with an emphasis on strengthening the health workforce. This is primarily through support to education and learning, policies and standards, and management and supervision. Health partnerships may also intervene elsewhere in the health system, such as providing medical equipment.

The 2016 independent evaluation of the HPS found that:
- HPS projects have contributed to health system strengthening by building up health worker capacity in terms of their skills, knowledge and confidence;
- Partnerships that are able to make linkages with other initiatives, establish synergies and be more strategic are more effective;
- HPS benefits both volunteers and the UK health system.

The evaluation updated the Theory of Change (ToC) for the programme (see Figure 1 below) with widespread stakeholder consultation, including THET and UK and LMIC stakeholders. The illustrated ToC comprises three interconnecting change pathways where the HPS is expected to effect change:

Change pathway	Expectation and assumptions
Partnership change	Over time partnerships will develop their relationships and alignment with national health systems, adapting to address different elements of the health system and creating networks to have scalable and sustainable impact. / This assumes that as health partnerships mature, they have a better understanding of health system needs, other partnerships and how to deliver sustainable change.
Volunteer and UK health system change	Volunteering opportunities enhance UK health workers skills and behaviours, benefiting the UK health system on their return, improving retention and encouraging further volunteers. / This assumes that volunteers are able to take up volunteering opportunities, have enriching experiences and share their learning on their return.
Host country health system change	Health partnership projects strengthen the health workforce, delivering higher quality services. Training curricula and certification, system inputs such as better equipment management and infection prevention and control, leadership and human resources management lead to sustainable changes in the partnering institution and the health system that the institution is part of. / This assumes that partnership outcomes are sustainable, supported by government strategies addressing barriers to health system strengthening, and lead to equitable and inclusive human resource management in health institutions.

[3]
[3] https://www.gov.uk/government/publications/evaluation-of-health-partnership-scheme
The HPS extension is designed to support DFID’s focus on health systems strengthening and respond to evaluation recommendations to strengthen some of the weaker links in the ToC, which are:

- Expanding health partnership initiatives to whole health facilities and communities, engaging more with leadership and making sure the approach is more institutionalised;
- Promoting learning, synergies and country coordination by providing platforms and facilitating connections between existing partners and other actors in the health sector;
- Strengthening health partnership impact, outcome and value for money performance and evidence-base;
- Integrating gender equality and social inclusion into project design, implementation and monitoring, evaluation and learning.

The HPS extension is focused on sustainability, scale-up and access. Grants are restricted to 5 main countries (Ghana, Burma, Tanzania, Uganda and Zambia), selected on the basis of existing health partnership work and THET’s capacity to support new projects. The projects because they could meet at least one of three objectives:

- Sustain health system improvements: they have previously achieved across LMIC health institutions at district, national or regional level, without further UK partner input at project end.
- Scale up improvements: they have previously achieved, by supporting other institutions to adopt them or by embedding them at a higher level of health system decision-making (e.g. getting an institutional improvement included in national policy).
- Make improvements accessible: to make the health system improvements they have previously achieved accessible to poor and socially excluded groups among the health workforce or health service users across LMIC health institutions at district, national or regional level, including (where possible) to women, girls and people with disabilities.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The programme extension is starting to demonstrate delivery against expected outcomes and impact, particularly on improving health services and implementation of improved policies and curricula. There is some limited evidence that UK volunteers are improving clinical and leadership skills. However, it is either too early in the extension phase or more evidence is needed to demonstrate increased access for vulnerable and marginalised groups to improved health services. Challenges remain in collecting robust evidence of improved health outcomes for patients from partnership activities.

Progress at impact level has exceeded expectations for the reporting period
The programme’s impact indicators focus on institutions demonstrating delivery of high quality specified health services, women, girls and people with disabilities using a new or improved health service, and institutions demonstrating improved health outcomes for patients.

Impact level progress was not expected for the Annual Review, but two health partnership projects in Ghana and Uganda, working with six institutions, are demonstrating delivery of higher quality health services. The programme is not yet demonstrating an increased number of women, girls and people with disabilities using a new or improved health service provided by participating institutions. While some projects are directly targeting these groups, evidence that all projects are taking opportunities to expand access to these groups remains limited. This should be a key focus for the remainder of the extension phase. It is too early in the extension phase for institutions to demonstrate improved health outcomes. We expect this will be challenging to demonstrate due to the shorter timeframe of the extension phase.

Scaling up multi-disciplinary stroke training in Ghana: The Wessex Ghana Stroke Partnership has strengthened existing stroke care services at Korle Bu Teaching Hospital (where a dedicated stroke unit was established by the partnership through a previous HPS grant) and have developed new stroke care services at two other hospitals in Accra. Multi-disciplinary teams at each institution have received specialised training in stroke care, dedicated stroke wards have been created and specialised equipment for managing stroke patients (such as chairs and ridge mattresses) is on its way to these new units. Having teams who are specifically dedicated to stroke care means that patients have more specialised care focussing on addressing their needs in a targeted way.

There are initial signs of progress against outcomes but further evidence is required
The programme’s outcomes focus on health workers demonstrating improved performance at least three months after training, institutions demonstrating implementation of improved policies and curricula, UK volunteers demonstrating improved clinical and leadership skills and evidence of LMIC health facilities and governments committing resources to sustain health partnership improvements in the health system.

Health partnerships projects have contributed to the implementation of improved or new policies and protocols in 6 LMIC health institutions, exceeding the target of 3 for this reporting period. Two health partnerships implemented newly developed protocols earlier than expected, with one an integral part of training and another an audit protocol immediately implemented after development.

Early detection, prevention and intervention for infants at high-risk of developmental disability in Western Uganda: A partnership between University College London Hospitals and Kyaninga Child Development Centre (KCDC) aims to improve services for infants at high-risk of developmental disability in Western Uganda. The partnership has developed protocols for Helping Babies Breathe and Kangaroo Mother Care[4] in the first six months of the project which are now in use in each of the units of the three neonatal care facilities where staff have received training. As a result staff are better able to treat patients in these neonatal facilities, and there is a greater level of consistency around care.
[4] Kangaroo mother care is a method of care for pre-term infants. The method involves infants being carried, usually by the mother, with skin to skin contact.

The development of UK volunteers is an important objective of the programme. THET undertook a survey with UK volunteers to assess volunteer development during the programme extension. However, the survey response rate was low, with only 26 out of 116 volunteers responding and not to all questions. Survey responses therefore only provide a partial indication of volunteer benefit at this stage. To measure progress against the programme extension target of 20 UK volunteers demonstrating improved clinical and leadership skills, data collection will need to be more extensive.

However, there are some encouraging examples. Of the 16 who responded to questions on improved capabilities, 10 felt that they had either developed new capabilities themselves, or had brought back new skills or ways or working that would benefit the NHS. Of this group, five reported improvements in both their clinical and leadership capabilities. Examples of these reported improvements are:

‘Having developed my educational skills over my career as a consultant, the volunteering activities with Ghana have necessitated and contributed to strengthening my leadership/strategy skills by providing real-time experience in a domain that I had, hitherto, not felt confident in. Being the principal project lead over the past few years, I felt that I had to succeed in steering projects despite challenges, and in doing so, learnt how to overcome obstacles and also the fact that I possessed skills to do so. This was, however, very much dependent upon the impressive support, understanding and guidance from my overseas partners’.

‘I am much more aware of MDT [Multi-disciplinary team] working and the roles / responsibilities of the members of my MDT. I am more able to 'tap into' their skills and strengths and I feel that they are more empowered as a result of this. We recently held 2 service development sessions at my workplace, largely inspired by my work and experiences with [institution deleted to maintain anonymity]. Through this several MDT-led service development projects are now underway to improve my UK service’

On sustaining health worker performance, it was not possible to assess the target for health workers demonstrating improved performance at least 3 months after education or training, as not enough time had elapsed before the reporting was requested by partnerships. All partnerships plan to collect this data. Projects are expected to disaggregate data by gender and disability.

Development of Palliative Care Leaders in Uganda: This partnership between Global Health Academy University of Edinburgh and Makerere University has an innovative and multi-dimensional approach to measuring change in trainee after taking part in the programme. As well as having a facilitator/mentor assessment scheme where facilitators/mentors carry out site visits to assess trainee performance, the trainees themselves are asked to do a self-assessment mapping exercise, identifying the skills that they have learnt, how they’ve used them, and how their leadership skills have developed throughout the course of the programme. Having a multi-faceted assessment strategy will allow for a more broad and informative set of data around performance, allowing assessment of skills improvement through both external assessment and the self-assessment and confidence of the trainees.

New health partnership activities are not yet able to show, in the first six months of their projects, LMIC health facilities or government commitment to resources to sustain health system changes generated. However, there are some signs of MoH and institution leadership level engagement that could lead to LMIC institutional resources by the end of the extension phase to sustain project outcomes.

Describe any planned changes to the logframe as a result of this review
At the start of the HPS extension, DFID and THET revised existing indicators and developed new indicators specifically for the extension phase. Given the amount of time remaining in the programme extension, further significant revisions are not recommended. Some minor changes to targets are recommended to reflect progress reported in this Annual Review:

- The cumulative programme target for Output 1.1 should be increased to 88,898 training courses and educational opportunities provided to reflect the greater progress than expected in this reporting period.
- The target for the next reporting period for Output 1.2 should be increased to 92%.
- The cumulative programme target for Outputs 2.3 and 2.4 should be revised down by one respectively to reflect that the Burma project on trauma care is seeking to increase local faculty capacity to run the course and that it is already integrated into the national curriculum.

## D: VALUE FOR MONEY
Assess VfM compared to the proposition in the Business Case, based on the past year

The agreed budget for the HPS extension is £2,100,000. Up to July 2018, the programme has spent £1,791,265 (85% of the budget). This reflects the disbursement of grant funding totalling £1,469,438. Projects received 50% of grant funding when grant contracts and due diligence assessments were completed. This enabled partnership activities as few partnerships have independent access to other sources of funding. A further 45% of funding to enable further partnership activity has now been released after six monthly performance and financial reports were reviewed and verified by THET. Projects will receive the final 5% of funding at the end of the extension period when partnerships have provided satisfactory evidence that all project activities and spend has been completed.

THET continue to demonstrate VfM in their management of the programme
THET’s management costs are 18% of the programme extension spend to date. Key cost drivers include THET salary rates, office and travel costs. As in the business case addendum, this reflects more support to partnerships due to the introduction of larger grants and the shortened implementation period than previous phases of the programme. Savings have been made in salary rates due to staffing changes, allowing additional budget for monitoring and evaluation (M&E) of the programme.

Costs have been managed by benchmarking salaries against the sector, remote working, and maintaining advance travel booking and economy fare policies for international travel. One recent example of this is the sharing of travel costs across the HPS and another project (funded by another partner) during recent M&E country visits. Economy has also been ensured through ongoing support to grant holders through the use of webinars and remote communications with grant holders.

The 2016 evaluation found that HPS projects are missing opportunities to create added value from coordination and integration with the other HPS projects and other aid programmes. During this grant period, THET have made efforts to strengthen the links between country offices and HPS projects so that country directors can facilitate links between the projects and other key stakeholders, including the MoH and any other significant programmes or projects. DFID Zambia reported the value of complementary activity between the HPS and bilateral programme efforts to support anaesthesia development, with the depth of support offered meaning that the number anaesthetists in Zambia has doubled from 22 to 45 in seven years. Four specialists now run provincial hospitals.

Health partnerships and projects continue to demonstrate economy and efficiency but need to do continue to focus on evidencing effectiveness, equity and sustainability
The 2016 independent evaluation identified that projects were aware of economy (in particular), efficiency and effectiveness as well as sustainability.

The greatest focus continues to be on economy and efficiency. Good evidence of this is provided in partnership six monthly reports. Partnerships also demonstrate some awareness of effectiveness and equity. There is some emerging evidence on this but projects require further support to better understand and provide robust evidence of effectiveness and equity at the end of the programme extension. THET will offer guidance and worked examples to partnerships in the remaining six months to strengthen partnerships’ understanding of VfM and how they can monitor and measure this in their projects.

Economy: The 2016 HPS evaluation found that the use of expert volunteers enables low cost provision of specialist expertise to LMIC partners. Analysis found that most training costs assessed were very low, around the £30 to £200 per person per day range, with one partner estimating that if they had conducted the same training with paid professionals the whole training would have cost them £202,404.[5]
[5] Accident and emergency health partnership between Cambridge University Hospitals and Yangon General Hospital, Myanmar (AGL29).

The most substantial evidence of VfM is on economy. The majority of projects continue to demonstrate evidence that they are minimising the main cost drivers of travel, accommodation and subsistence through advanced planning, using remote communication to deliver assistance where appropriate and extending volunteer time in country to maximise outputs from visits. Three projects have provided evidence of pooling costs on travel, materials, website support and other materials with other partnerships or wider networks to which they have links. Two projects have succeeded in securing high-value software inputs for discounted or zero cost (see example below). Projects are undertaking local procurement where possible, from basic services such as catering to more sophisticated requirements such as pathology equipment being purchased from local rather than international suppliers.

Increasing access to eye healthcare in two Ugandan health regions through an innovative outreach clinic training programme: “We were able to use a retinal abnormality detection software provided for free and teaching was provided by the company. The Arclights were given to us for free and the fundus cameras and ICare intraocular pressure measurer given at near cost price. This was because of energetic presentation to the companies of the value of this project.”

Efficiency: The 2016 evaluation found that the efficiency of technical assistance using a partnership and volunteering approach is high. Projects are demonstrating efficiency through a range of practices:

- Using specialist volunteers to deliver targeted training and technical assistance;
- Exceeding expectations in the numbers trained and educational opportunities offered;
- At least four projects are creating training materials, including online and e-learning materials, which reach a greater number of health workers for the expertise input of their volunteers. This is also effective in sustaining the training outputs beyond the project lifetime;
- Using a “training of trainers” approach to maximise outputs from expert volunteer inputs. In addition, it builds local capacity and knowledge, reducing the need for UK partner input and scaling up of impact as training is cascaded;
- Integrating partnership activities with existing LMIC partner and other project outreach activities.

Developing capacity and capability in biomedical engineering in greater north and eastern Uganda: “Our project has been designed to continue to achieve an output after the project has finished. Those who have attended training have much improved knowledge around the equipment they are using and have reported increased confidence – we anticipate that this will enable the participants to use and share their knowledge of the proper use and maintenance of the equipment for themselves but also in a cascade approach to others.”

Sustaining and scaling up clinical audit in Uganda and Tanzania: The start-up and initial workshops were completed at the same time as visits were taking place for another partnership project (NIHR 16/137/53), thus saving travel and accommodation costs

Effectiveness: Since 2011, the HPS has helped strengthen the capacity of 137 LMIC health institutions. Partnerships draw on appropriate expertise and co-development to build lasting institutional partnerships. Approaches such as training of trainers standardise training and extend the sustainability and reach of skills transfer. As projects are half way through project activities, concrete evidence of effectiveness is limited. The majority of partnership reporting to date is dependent on the project design assumptions that the outputs being delivered will lead to the anticipated outcomes. It is expected that partnerships will demonstrate stronger evidence of effectiveness by the end of the extension phase.

There are some initial signs of effectiveness, with evidence that projects are starting to demonstrate sustained skill and knowledge development. Projects are focusing on quality of outputs by, for example, ensuring independent mentoring and review to quality assure project activities and training delivery. Some projects are also sharing their materials and strategies with other partnerships outside of the HPS, scaling up their impact and beginning to evidence scale up towards national level. Other partnerships demonstrate further adaptation of their project design to the local context to increase effectiveness.

Sustainable training of general practitioners on quality improvement in Burma: Following the two Royal College of General Practitioners’ trips to Myanmar visits in the first quarter, it was felt that appointing Quality Appraisers from the group of local GPs would be inappropriate in this cultural setting and it was decided that higher Quality Training would be provided to all 32 GPs in Mandalay and all 32 GPs in Meiktila who had attended the training. This has instead meant that all of the GPs are taking part in ‘Quality Circles’ that are run as peer group learning and has improved the uptake of higher level training above that in the initial target.

Advancing access to critical care education in Zambia: Review and accreditation has already led to a national change in critical care provision at minimal cost as the partners and expert panel were able to provide the appropriate advice and information for the MoH and the General Nursing Council.

Scale-up of diabetic retinopathy screening and treatment services across Zambia: Frimley Health NHS Foundation Trust and the University Teaching Hospital in Lusaka are working closely with the Zambian Ministry of Health through the newly established national diabetic retinopathy steering group and through jointly delivering training in this project to achieve their goals in the health care system and the prevention of unnecessary blindness in the population. The growing burden of diabetes and its side-effects, including diabetic retinopathy, will require increased country’s health care funding as the number of people with diabetes grows and the number being diagnosed and seeking treatment grows. Unnecessary loss of sight in adults of working age has an economic cost to the country and the project is helping Zambia to prepare for the expected growth in diabetes in its population.

Equity: The evaluation found that projects reviewed tended to have limited understanding or analysis of how gender inequality and social exclusion can affect efforts to enhance human resource capacity and improve people’s access to and use of health services. The programme extension has focused more on ensuring increased equity, supported by two studies on health equity commissioned by THET and a step up in technical assistance on data collection and targeting activities. Overall, at this stage of the programme extension there remains limited evidence that partnerships are ensuring access for vulnerable and marginalised groups, with many assuming rather than explicitly measuring access. This reflects limited experience of partnerships in considering equity in programme design and with 12 projects seeking to deliver improved access, this measurement needs to be improved for the Project Completion Review.

However, there is some evidence that projects are more explicitly seeking to address equity. One project is contributing to improved access through expanding its networks and care provision beyond urban hubs, providing patients from other regions with access to care closer to home. Another project has explicitly taken equity into account in its project design. Recognising that its training inputs are limited, it is focused on training supervisors on child epilepsy so that this can be cascaded through the health system to rural health workers and the first point of care in primary care health facilities, in combination with plans to extend training directly to all health workers in over time through continuing partnership activity. Some projects are putting in place measures to directly improve access for women, children and those with disabilities, for example:

Strengthening the community health worker programme for health improvement in Wakiso District, Uganda: The project is supporting community health workers (CHWs) in targeting women’s groups and disability groups in the communities. They are currently in the process of identifying these groups, and in the next quarter they will be supporting CHWs in health promotion and education among women and people with disabilities on key health issues such as communicable diseases, non-communicable diseases, maternal health, child health, reproductive health, water, sanitation, hygiene, vector control, food safety and safe housing. It is anticipated that with this particular activity, women and people with disabilities will acquire more knowledge and skills to to improve their health and that of their families.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
The evidence from this reporting period builds on the 2016 evaluation’s assessment that the HPS offers value for money. In this reporting period, projects have been able to provide further evidence of value for money in terms of economy and efficiency. It is encouraging that there is emerging evidence of effectiveness, sustainability and equity, however further evidence is required to demonstrate comprehensive VfM. It is expected that further evidence across these components of VfM will emerge in the next reporting period when partnerships enter the latter stage of the project cycle.

In line with the evaluation recommendation, THET should continue to promote synergies between partnerships and other aid programmes by strengthening international development expertise, simplifying its Principles of Partnership[6] and developing guidance on institutional capacity strengthening approaches.
[6] THET Principles of Partnership: http://www.thet.org/pops/principles-of-partnership

E: RISK

Residual Risk Matrix
The circles indicate the residual risks for the programme after mitigation activities. The trails indicate the gross risk rating before mitigation.
Overall risk rating: Moderate
The programme was approved with a risk rating of moderate. This was subsequently reassessed as minor until the introduction of DFID’s revised risk framework in March 2016, when it returned to moderate.

## Overview of programme risk
Programme risks are regularly monitored and overall remain the same as in the previous Annual Review. The risks around ensuring safeguarding have received particular emphasis in 2018. Other key risks that need to be managed relate to potential weak financial and programme management capacity of grant holders, security issues in some contexts and lack of ownership over the programmes.

Additional risks identified for the extension period are the following:
- The need for DFID and THET to ensure more intensive inputs throughout, given the shorter implementation period, and the risk that this might not be possible;
- The risk of unrealistic partnership expectations for the extension period, and of dissatisfaction around the lack of continued funding for some, and;
- UK or LMIC staff from a project abuses or mistreats a project beneficiary, staff member or other stakeholder.

The delivery and expectation risks have been mitigated through regular monitoring of progress against plans, agreeing clear criteria and transparency and an open competitive process for how grants will be allocated and ensuring grant holders are notified of expectations in advance (both at the selection stage and in management of the grants e.g. for reporting).

THET have comprehensively responded to the safeguarding risks identified. They have reviewed all partner safeguarding policies shared as part of due diligence processes and followed up where improvements were required. THET clearly outlined expectations both through grant holder contracts and through webinars with partnerships. THET’s website has been updated with information about how confidential contact can be made to raise any concerns or issues within partnerships.

Management of financial risks: THET has applied robust grant award and grant management processes, including risk management procedures. These include due diligence assessment of health partnerships before grant award followed by guidance and ongoing support on project design, budgeting, governance, financial controls, fraud management and duty of care. Grant holders provide regular detailed financial and narrative reports, with payments contingent on verification of expenditure, performance and evidence-based results. Review of programme and grants-level risk is a standing item at THET’s monthly Grant Management Group (GMG) meeting. There has been no incidence of fraud or corruption in this reporting period.

The risk matrix is continuously reviewed and updated and DFID remain confident that THET’s risk management is proportionate and effective.

Outstanding actions from risk assessment/due diligence
There are no outstanding actions.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
THET has effectively delivered the programme and grant management and technical assistance required in this reporting period.

On programme management, THET and DFID have worked closely to update the logframe to reflect changes in grant designs for the programme extension, particularly focusing on data disaggregation for marginalised groups. The delivery chain map has been updated to record financial flows to and within partnerships. THET has submitted timely quarterly narrative reports detailing programme activities and developments. DFID and THET meet bi-monthly to review programme progress and documents, discuss and resolve issues and review workplans.

THET responded comprehensively to DFID requests for assurance on safeguarding and have taken forward steps to further strengthen partnerships understanding and processes for safeguarding.

THET have also taken steps to promote health partnerships in the UK, working with DFID Communications to release a video for the NHS 70th anniversary where volunteers described their experiences overseas.

On technical assistance, THET has delivered more intensive inputs to support projects during the programme extension. These have included an in-country event in Uganda (February 2018), where 11 of the 20 projects are located, to support them on with guidance on progress reporting, M&E, financial management and general project management. Attendees indicated that they would change their practice as a result of the event, including collection of gender and disability disaggregated data, more engagement with the THET Uganda Office, the Uganda Ministry of Health and other partnerships working on similar themes, and an improved understanding of the collective responsibility between partners on a project.

THET has consistently sought to deliver accessible technical assistance to all partnerships on a range of topics, including through quarterly monitoring meetings and a series of webinars. This includes a Partnership Support webinar on monitoring and evaluation, partnership management, financial management and reporting, and a Volunteering Management Webinar to provide guidance on good practice in volunteer management. THET also plan to organise a webinar on Shared Ownership in the next quarter. THET has also developed the resources available to support partnerships, including a Finance Toolkit for Grant Holders in response to requests for additional support. The guide on collecting data disaggregated by disability in particular was high quality and demonstrated THET’s responsiveness to the recommendations from the evaluation on how partnerships can better consider equity.

On financial management, THET has provided timely and accurate forecasting on a resource accounting basis. THET has competently administered monitoring and management of budgets for the 20 grants. This has included conducting an audit of the one grant holder (on financial, asset and fraud management) overseas and making/following up on recommendations for improvements. In consultation with DFID, THET has developed a robust strategy to manage any forecasted underspend.

An independent audit report of THET’s 2016 accounts clearly accounts for DFID funds and expenditure, including grants, and found THET’s financial systems to be true and fair. Audited accounts and an updated asset register, which will be physically checked by DFID, are expected by the end of July 2018
.
Date of last narrative financial report(s)	13/07/2018
Date of last audited annual statement (s)	2016

THET and DFID will update the delivery plan to set out the activities required to deliver the final stage of project activities, ensure a sound Project Completion Review and close the programme by March 2019.

G: MONITORING, EVIDENCE & LEARNING

Monitoring
In addition to progress and results reported to THET by grant holders on activities from December 2017 to 31 May 2018, THET carried out a number of monitoring and support activities for health partnerships:

Quarterly progress meetings with grant holders: to maximise outputs from the short implementation timeframe (13 months), THET held quarterly review meetings with all grant holders in March 2018 to ensure that activities were progressing as expected and to discuss challenges and delays early on. Most partnership projects were on track. Engaging early enabled THET to discuss solutions to problems and mitigate any delays through guidance and additional support from the partnership network.

Monitoring visits to funded projects: THET have carried out two monitoring visits in Ghana and Myanmar to grants funded under the HPS extension programme. This allowed THET to ensure that project activities were taking place as planned, that M&E systems were being implemented and relevant data collection and analysis being carried out at each of the project sites. THET also carried out financial audits where appropriate, triangulated information from different stakeholders/sources to verify progress, and gathered individual stories of impact (including interviews for communication purposes). These visits enabled direct engagement with LMIC partners and stakeholders and supported identification of areas for improvement within the partnership working and project management. THET provided a feedback report with recommendations and follow up actions to each partnership.

Evidence

Sustainability and scale of health partnership and project outputs and outcomes
Projects cannot provide concrete evidence at this stage that outputs and outcomes will be sustained. There is no data yet for outcome indicator on improved performance or skills at least three months after training. Projects are reporting good progress on output indicators on improving policies, professional standards and curriculum, outperforming on the number of health workers trained and maintaining strong performance on those health workers demonstrating improvement when immediately tested after training. This should lead to sustainable impact.

As partnerships are building on previous projects, there is some indicative evidence that partnerships can deliver sustainability. Some projects report sustained performance in those previously trained, with these professionals contributing to sustaining and scaling up training for other health workers in more health facilities. Others are scaling up their work with institutions and facilities, for example working with the Ministry of Health and General Nursing Council in Zambia to bring in a second education and training centre to ensure more than one long-term provider for certification and basing trainers for emergency obstetric skills in the two largest regional facilities to expand partnership reach. Projects are taking steps to enable activities to continue beyond the project by increasing the capability of partners to deliver more partnership activities such as project management and training.

DFID and THET will work together to establish how qualitative data can be gathered for the Project Completion Review to assess programme impact and sustainability beyond the HPS, particularly for institutional and government commitment to sustaining partnership impact. THET and DFID will seek to supplement the evidence base for the programme by meeting previously funded health partners and stakeholders through the HPS as part of their monitoring visits. This is to gather additional evidence on sustainability and long-term impact beyond their grant timeframe and whether partnerships were strengthened and able to continue activities with alternative support.

Leaving no one behind: improving access for women, girls and people with disabilities
THET asked health partnerships specific questions on how their projects are benefitting women, girls and people with disabilities as part of their six monthly reporting.

For health workers, at least 14 health partnerships have demonstrated that they are collecting data on disability on those trained, seven of which have reported health workers who have declared a disability. Two mental health projects are training peer support workers – former and current patients with mental health issues who are categorised as having a form of disability. Another project has reported that 34 of the Community Health Workers they trained have a declared disability. One health partnership was not permitted to ask for disability under their ethics agreement; THET and DFID will consider how to work on these data collection challenges.

On gender, some partnerships are encouraging female health workers in certain professions to attend training, others are also supporting women in leadership roles. Some partnerships have explicit gender inclusivity recruitment policies for their training. At the partnership level, many health partnerships have indicated that the involvement of female UK health professionals as volunteers or partner members can encourage more inclusivity among health workers and LMIC partner teams. However it appears that partnerships that have a majority of female volunteers or team members is coincidental rather than a deliberate effort to include women.

While data disaggregation for partnership activities with health workers has improved, further work is required to improve data collection on service users to demonstrate impact on improving access. For service users, five health partnerships specifically target people who are perceived as having a form of disability either from birth or from underlying conditions including children with learning disabilities, people with serious mental health conditions, stroke patients, and children with epilepsy who have disability co-morbidities. Two health partnerships are specifically providing services for women (maternal health). Beyond those specifically targeting these groups, other projects are seeking to ensure women, girls and those with disabilities have access to mainstream health services (see example below), but there is a need to strengthen evidence on access across those projects that are not specifically targeting these groups.

THET has reflected this in their feedback to grant holders and will continue to assist on how to collect data on disability. For a majority of health partnerships this is a new area for consideration, which requires integration into their work, further evidence gathering and a shift in mind set. THET and DFID will consider the best strategies for demonstrating this in the remainder of the programme extension and lessons to take forward for future health partnership programming.

Strengthening the community health worker programme for health improvement in Wakiso District, Uganda: A partnership between Nottingham Trent University and Makerere University is scaling up their previous Community Health Worker project to an additional three new sub-counties in Wakiso district, Uganda. One sub county in particular is made of small islands on Lake Victoria with limited access to health facilities and have worse health indicators than the mainland. The partnership has developed new activities specifically targeting women, girls and people with disabilities including health promotion and education to women’s groups and people with disabilities’ groups in the community on key health issues such as communicable and non-communicable diseases, maternal and child health, reproductive health, hygiene and sanitation. It is anticipated that such achievements will help women improve their health and that of their families. They plan to reach 20 women’s groups and 15 groups of people with disabilities and this has been built into their objectives.

Learning
Key lessons learnt from the external evaluation of the HPS in 2016 have been taken into account in both the design and the implementation of the grants scheme as explained above.

THET held an internal Knowledge Management and Learning workshop in July 2017 to capture experience and learning from the HPS team. The workshop was structured into 5 sessions: (1) Sharing and Learning within the health partnership community, (2) Programme design, (3) Programme implementation (4) Data collection, M&E and reporting (5) THET project management. Although this session was carried out before the programme extension was decided, it has led to concrete changes in the way THET manages the programme in this Accountable Grant, as summarised in the table below:

Recommendation based on workshop feedback	Related activity under HPS extension phase
Organise more events especially overseas and also spread out across the UK	Ugandan Health Partnerships event at the start of the AG projects
Establish systematic, regular catch ups with HPs irrespective of whether there are issues or not.	Established quarterly progress meetings with all AG grant holders.
Reporting webinar at the beginning and clearer expectations	In March 2018, THET organised a webinar to take current grant holders through the reporting template and giving them the opportunity to ask any questions.
Ensure organisations have good financial management systems in place and assess this as part of the application process	A thorough due diligence form was completed by partnerships at the start of the AG grants.
Emphasise value of M&E for both partners, highlighting DFID’s requirements and case studies of health partnerships that have benefitted from M&E.	THET have been much clearer on reporting and disaggregation requirements and increased transparency on how the information is used.

THET has monthly Partnership Support Working meetings and weekly grant management meetings to identify areas of support for health partnerships. THET analyse submitted progress reports to identify impact, challenges and good practice to develop into knowledge materials or learning and sharing sessions for current grant holders and the wider health partnership community.

The annual THET conference will provide a platform for health partnerships to present their findings through presentations or poster displays. Presenting partnerships were selected through an abstracts review process.

Progress on recommendations from previous reviews
The programme extension has responded to the recommendations from the 2017 annual review by:

- The programme should focus on sustaining momentum but start to shift towards a more strategic approach, focussing partnerships on fewer countries and, within those countries, on areas identified by the Government as part of their overall health approach.
  - DFID and THET designed the programme extension to focus on supporting fewer partnerships in fewer DFID priority countries (Uganda, Zambia, Tanzania, Myanmar and Ghana) where there have been successful former partnerships and where THET can effectively provide in-country support.
- Identify which partnerships have been most successful in terms of institutional impact, to aid a more strategic selection of partnerships during the extension period.
  - THET considered the previous performance of HPS partnerships and their institutional impact in the selection of partnerships for the Accountable Grant.
- The logframe needs to be revised by September 2017 to agree 2018 milestones and end of programme targets for indicators at impact, outcome and output levels. Where possible, more qualitative indicators should be identified.
  - The logframe was revised by September 2017 with new and adapted indicators to respond to the independent evaluation findings (including gender and disability data disaggregation), with further revisions to milestones and targets based on the monitoring and evaluation plans of each project.
- Continue the positive progress on implementing the remaining relevant recommendations from the management response to the evaluation and consider how best to take forward recommendations from the two health equity studies (gender and populations served).
  - THET is responding or is preparing to respond to most of the recommendations from the management response to the evaluation, in collaboration with DFID. Selection and management processes more rigorously consider gender and populations served.
- Introduce data disaggregation on disability, where possible, for both participants and beneficiaries.
  - THET has included more on disability data disaggregation in narrative report templates for grant holders. This has been captured in logframe indicators. THET has also developed a How to Capture Disability Data in Health Projects Guidance and shared with all grant holders.
- Identify what factors enable or hinder the success of improvement/adoption of health policies and ways to assess quality and impact for future grants including identifying logframe indicators.
  - To assess the factors that influence the adoption and improvement of health policies, THET have continued to offer support to partnerships to engage in some of the key decision making spaces related to their work. This has included facilitating the engagement between the Ministry of Health and Sport and health partnerships in Myanmar. This evidence will be analysed in the Project Completion Review.
- DFID and THET should continue frequent reviews of workplans, budgets and activities to maximise programme grant spent and results achieved.
  - DFID and THET undertake reviews of workplans, budgets and activities every two months to maximise programme grant spent and results achieved.

One recommendation has not been taken forward:
In line with DFID’s environment and climate safeguards, start to address environmental measures and opportunities to among other, contribute towards adequate waste management and improved water and sanitation at health facility level.
  - The recommendation on considering environmental and climate safeguards has not yet been taken forward. A number of current grant holders do undertake a substantial amount of remote support volunteering within their projects, which reduces the volume of air travel required. It is recommended that THET and DFID assess these opportunities as part of the Project Completion Review. DFID should incorporate this evidence into the design of future health partnerships programmes.