Project Completion Review – post April 2018

Title: AAWAZ (Voice and Accountability) Programme
Final Programme Value £ (full life): 39.1 million	Review Date: / 18 June 2018
Programme Code: / 114433	Start Date / 20 May 2012	Final End Date: / 20 May 2018

Summary of Programme Performance

Year	2013	2014	2015	2016	2017	2018
Programme Score	B	A	A	A+	A++	A+
Risk Rating	Moderate	Minor	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-114433/documents
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5771140.xlsx

A. Summary and Overview

Description of programme and what it has achieved

The AAWAZ Voice and Accountability (V&A) Programme was a six year, £39.1 million programme[1] (May 2012 – May 2018, including the 12 month costed extension). AAWAZ was implemented through Development Alternative Inc. (DAI) as the management organisation (MO) and contract supplier with 4 leading Pakistani civil society organisations: South Asia Partnership (SAP PK); the Aurat Foundation (AF); Strengthening Participatory Organisation (SPO); and Sungi Development Foundation. It was DFID Pakistan’s largest demand side voice and accountability programme and it was implemented directly across 4,500 villages in 45 districts (26 in Punjab and 19 in Khyber Pakhtunkhwa (KP)). The programme aimed to ensure that democratic processes were more open, inclusive and accountable to citizens in Pakistan. The programme focused on women’s and minority rights, their political participation and decision making; identity-based discrimination and prevention of violence; and increasing the accountability and responsiveness of the state to citizens’ demands for improved service delivery.
[1] £37,329,966.32 DAI Supplier contract; £1,261,950.51 procurement of programme equipment (cars, desks, etc.) through Crown Agents; £235,613 given to UN Women for work on prevention of Violence Against Women and Girls legislation; £98,100 for M&E activities and £174,369.20 for programme design activities.

AAWAZ contributed towards good governance by consistently and systematically protecting and expanding public spaces for poor and excluded people especially women, minorities, and transgendered. The programme reached 8.316 million (3,478,608 KP, 4,838,344 Punjab) citizens in the two provinces solely in relation to programme outputs 2 and 3 (pre-emption of religion-based conflict and demands for improved education and health services, respectively). As a result, democratic processes became significantly more inclusive. When the programme began operating, many women were confined to their houses, and had almost no contact with the outside world. During the course of the programme, transformations in attitudes and behaviours were recorded by internal M&E assessments and external evaluations. 91,621 (38,209 KP, 53,412 Punjab) women actively participated in community meetings and 89,076 (36,490 KP, 52,586 Punjab) in citizen town hall meetings. Now, 31,431 (12,540 KP, 18,891 Punjab) women hold leadership and decision-making positions – in citizen groups and networks, as members of local women’s assemblies, change makers, women peace connectors and youth leaders, and Aagahi Centre Resource Persons (ACRPs).

2,243 (964 KP, 1,279 Punjab) khuli katcheries (open town hall meetings) were held where citizens, including women members, met with district and provincial government officials on service delivery issues for water, health and education. They provided a robust citizen-state interface where government officials and elected representatives were held accountable to women and the socially excluded. The programme also supported 31,968 (17,822 KP, 14,146 Punjab) individual citizens and citizens’ groups to establish direct contact with high-level, public sector officials working at union council and district levels of government. In addition, some district forums and women assemblies engaged with the relevant government stakeholders in the shape of formal monthly meetings or District Coordination Committees (DCC) for demand articulation, pre-budget consultation, expenditure tracking and monitoring. There is strong evidence that these district forums and women assemblies have deepened their relationships with government authorities and that some village and union council forums have become increasingly sophisticated in their use of advocacy methods as well as in their analysis of the steps needed to achieve change. The programme district forums successfully lobbied in recent years for 159 (45 KP, 114 Punjab) policy and service implementation reforms that benefited women and the socially excluded. All such interactions provided an opportunity to build mutual understanding between the state and citizens and inculcate a culture of accountability on local development issues.

Over the life of the programme, AAWAZ adapted to take account of lessons learned and changes in the context through its annual reviews and in particular through its 2014 midterm-review. The 2014 review recommended changes that included refocusing of output 2 away from conflict mediation to pre-emption, the reincorporation of Programme, Analysis Research Results, into the MO and a greater focus on diversity (religious, disabled, transgender) within AAWAZ forums at all levels. The implementation of a robust monitoring, evaluation and results management system underpinned the shift programming from 2014 and enabled the MO to track results in great detail until the programme end in May 2018. The outputs 2 and 4 were reweighted last year based on the recommendation of the 2017 Annual review.[2] This was done to capture the significant results being achieved (progressively) under output 2 since the shift to pre-emption of conflict. The last amendment to the logframe was made in July 2017.
[2] Output 2 increased from 20% to 25 % and output 4 reduced by 5%.

The AAWAZ programme made significant progress against its outcome statement by involving women, men and minority groups in new watchdog roles in state oversight functions (e.g. spending against village development plans) and in demanding the implementation and adherence to the law in areas like early marriage, forced/bonded labour and domestic violence, thereby making government processes more accountable to all citizens.

At the impact level the programme contributed to improvements in Pakistan’s World Governance Indicators’ voice and accountability rating from -0.88 to -0.69. The programme also contributed towards increasing the percentage of Pakistanis who felt ‘quite safe’ or ‘very safe’ from 38% to 69% in line with its intended impact, as evidenced by the 2017 Gallup and Gilani polls. The World Economic Forum Gender Gap Index has ranked Pakistan 143rd out of 144 countries for the last two years. This does not necessarily mean that the situation for women and girls in Pakistan has deteriorated, but that its position vis a vis other countries is still poor. We know that the AAWAZ programme contributed significantly to women’s interest and participation in both formal and informal decision making.

The ability of the programme to shift and adapt to midterm and annual review findings helped the programme to maintain relevance and grow in influence. Provincial government officials were initially sceptical of AAWAZ activities during the first half of the programme’s implementation, due in part to the sensitive issues that were tackled including prevention of violence against women, conflict pre-emption, rights of religious minorities and pro-women legislation. The signing of an MOU[3]with KP government and exchange of letters with Punjab government in 2015 created greater transparency between the work of forums and government at all levels. This helped to break down mistrust and develop allies within the government for the implementation of AAWAZ in the field.
[3] MOU / Exchange of letters established district coordinating committees under the auspices of the government District Coordination Officer (DCO) in each AAWAZ programme district in both provinces. This allowed CSO to demonstrate that they are there to work with the state in the delivery of local integrated delivery plans.

In spite of its successes, AAWAZ faced constraints and challenges. These related mostly to the political external context and fluctuating security concerns, as well as some management issues with the consortium.

DAI addressed these risks by, respectively, adapting the direction and visibility of the programme’s work in particularly sensitive areas (interfaith harmony), building close relationships with government at district and provincial levels and maintaining its rigour with regard to compliance and financial management.

The outcome: Democratic processes in Pakistan are more open, inclusive and accountable to citizens:

The AAWAZ programme made significant progress to contribute to a more open, stable, inclusive and tolerant democratic society in Pakistan, and in particular to making democratic processes more open, inclusive and accountable to citizens.

The programme laid the foundation of “diagonal accountability” in the country by taking women and socially excluded groups (traditionally at the base of ‘vertical’ accountability relationships) and enabling them to be included in – or in some cases creating – more ‘horizontal’ accountability mechanisms (e.g. Khuli Katcheries, peace committees, district education and health monitoring committees and others). Thus, the programme brought a shift by involving women and minority groups in new watchdog roles in state oversight functions, breaking state monopoly of ‘official executive oversight’. This was vital if the programme was to realise the higher level outcome of a Pakistan more accountable to its citizens.

Some key achievements of the programme are:
- More than 90% of men and women in programme areas are aware of violence against women and pro-women legislation in Pakistan.
- 93% of respondents believe that domestic violence is a crime (compared to 61% in 2016).
- Around 86% of men and women in programme areas believe that women’s vote and candidature in elections is important for strengthening democracy in Pakistan.
- Over 89% of women cast their votes in 450 programme supported union council elections across KP and Punjab. Women and socially excluded members contested general seats in 30% of the programme areas.
- Nearly 53% of men and women claimed ‘stopping’ a member of their family/community from physical or verbal abuse of women and 40% of survey respondents have themselves stopped child marriages from taking place in AAWAZ intervention areas.

The key lessons from the programme are:
- Demand side programming is challenging, therefore invest in monitoring and learning mechanisms. The investment will contribute to programme adaptability and respond to challenges. It will also contribute to maximising opportunities.
- Boys and men’s involvement, improved communication and relationship messaging and confidence building in women has helped to establish that change does not mean taking power from men, but rather empowering women to become active citizens who contribute at household and community levels.
- Positively influencing service delivery has a multiplier effect. It increases communities’ confidence in the programme and its way of working; it gives credibility to the involvement of women, youth and minorities and can be catalytic in opening opportunities to pursue other programme goals.
- Transformative social change takes long-term and sustained investment. Where changing social norms is essential to right-based development programming, it is important for the programme and its partners in civil society and government to have confidence in the programme and donor’s commitment to change.
- The intended result of all AAWAZ interventions is to build social capital[4] - alliances and networks to build common ground, solidarity, mutual understanding and support for collective action and positive change. It also builds an alternative to patron-client relationships, acts as a social safety net and can resist the trend towards an ever more unequal, divided and intolerant society.
  [4] Organisation for Economic Co-operation and Development (OECD) defines social capital as “networks together with shared norms, values and understandings that facilitate co-operation among groups”.
- Investing in targeted, good quality capacity building can result in real changes and pay huge dividends.
- Having first class specialists and a strong leadership team in the MO to provide quality technical support and guidance makes a big difference to the quality, scope and impact of the programme.
- For government to respond to demands for better services, to create new policies/laws (Domestic Violence Act Punjab) and to allocate resources for law enforcement (prevention of child labour) requires a government system that is capacitated to meet the demands of the public. The successor programme (AAWAZ II) will work with key line ministries and statutory bodies to address the capacity gap within government and enhance their responsiveness to citizen demands.
- Where changing social norms is a necessary precursor to overcoming obstacles to genuine, inclusive development and democracy, it is unrealistic to expect quick fixes.
- The benefits of successful influencing on service delivery go beyond improving local governance and impact of having better services. This work also increases the community’s confidence in the state to deliver and it gives credibility to the involvement of women and minorities.
- A key lesson for any successor programme is to understand the cultural governance differences between both provinces in order to engage early with the main provincial line departments and officials.
- AAWAZ Aagahi Centres (AAC) (citizen advice bureaus and community meeting places) and their female Resource Persons are becoming key places for ordinary poor people to connect to state services.[5] They also continue to be as a safe meeting place for women outside of the family to network, learn and study. Local government line agencies continue to publicise their special events (polio vaccination, health camps, etc.) and programmes displaying their materials and posters, bringing government services closer to communities. AAWAZ II will use AAC as an entry point in reaching the most excluded at the village level.
  [5] In this context, state citizen engagement enables poor women, men and the excluded to speak for themselves about their needs and priorities for services directly to government. In addition, it enables government to understand, budget and plan for the needs of all their citizens to provide inclusive, effective and efficient services.

Acronyms

AAC	AAWAZ Aagahi Centre
AAWAZ	Urdu word for voice
ACRP	Aagahi Centre Resource Person
ADF	AAWAZ District Forum
AF	Aurat Foundation
AR	Annual Review
ARAP	Annual Review Action Plan
ASC	AAWAZ Steering Committee
AUF	AAWAZ Union Council Forum
AVF	AAWAZ Village Forum
BPA	Blanket Purchase Agreement
CBA	Cost-Benefit Analysis
CBO	Community-Based Organisation
CDIP	Consolidating Democracy In Pakistan
CNIC	Computerised National Identity Card
CSO	Civil Society Organisation
CWP	Costed Work Plan
DAI	Development Alternatives, Inc.
DCC	District Coordination Committee
DFID	Department for International Development
DQA	Data Quality Assessment
DWLA	District Women's Leader Assemblies
ECP	Election Commission of Pakistan
EWSs	Early Warning Systems
GoKP	Government of Khyber Pakhtunkhwa
GoPb	Government of Punjab
GRM	Gender Road Map
HMG	Her Majesty’s Government
IRR	Internal Rate of Return
JASAT	Jamhoryiat Angan Se Aiwan Tak
KP	Khyber Pakhtunkhwa
LF	Log Frame
M&E	Monitoring and Evaluation
MAISP	Multi-Agency Information Sharing Protocol
MIS	Management Information System
MO	Management Organisation
MOU	Memorandum of Understanding
NPV	Net Present Value
NVC	Non-Violent Communication
OECD	Organisation for Economic Co-operation and Development
P&D	Planning and Development
PAAP	Policy Advocacy Action Plan
PARR	Policy, Advocacy, Research and Results
PCMR	Provincial Commission on Minority Rights
PCR	Project Completion Review
PKR	Pakistan Rupees
PMC	Programme Management Committee
PSOA	Project Schedule of Authorities
PTV	Pakistan Television
PWD	People with disabilities
RP	Resource Person
SAARC	South Asian Association for Regional Cooperation
SAP-PK	South Asia Partnership Pakistan
SAWA	South Asian Women Alliance
SAWACL	South Asian Women Alliance of Community Leaders
SDF	Sungi Development Foundation
SDG	Sustainable Development Goal
SLU	Strategic Learning Unit
SMT	Senior Management Team
SPO	Strengthening Participatory Organisation
TOC	Theory of Change
TA	Technical Assistance
UC	Union Council
V&A	Voice and Accountability
VAWG	Violence Against Women and Girls
VDP	Village Development Plan
VfM	Value for Money
WGI	Worldwide Governance Indicators
WL	Women Leader
YCI	Youth Circle of Influence

## B: DETAILED OUTPUT SCORING

Output Title	Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab
Output number per LF		1	Output Score	A+
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	N

Under this output, the programme was expected to increase the participation of women and excluded groups (transgender/PWD[6]/religious minorities) in community and other decision making processes at local, provincial and national levels. It was also expected to decrease the number of men and women reporting acceptance of gender based violence (GBV). AAWAZ exceeded expectations in the implementation of this output achieving an A+ score overall.
[6] People with disabilities (PWD)

Indicator(s)	Milestones	Progress
Number of women and girls participating in awareness raising sessions and change maker training on participation in public spaces and political processes and women's right to freedom from violence and receiving change-agent training (data disaggregated by location/exclusion).	104 women master trainers trained on additional modules. / 100,000 women and girls (100% of the total women forum members) made aware on pro-women laws, early marriages, modern slavery, and customary practices and women rights of political participation. / 80% women in AAWAZ forums demonstrate positive change in knowledge (pre/post evaluation). / 8,652 women trained as change makers and at least 80% of them are able to establish circle of influence in AAWAZ forums where all 4 issues (gender, discriminatory practices, exclusion and right to information) are discussed and regular follow-up is maintained.	104 (37 KP, 67 Punjab) women lead trainers trained. / 113,916 (44,912 KP, 69,004 Punjab) women and girls (100% forum members) made aware. / 90% women in AAWAZ forums demonstrate positive change in knowledge (pre/post evaluation). / 8,652 (4,137 KP, 4,515 Punjab) women trained as ‘master trainer/change makers’. 92% of change makers have established circle of influence. / Around 84% of women have better understanding about gender, gender roles and issues of social cohesion. / More than 98% women are now aware of gender-based legislation and discriminatory practices. / 71% of women know about social cohesion. Around 62% of women know about social accountability mechanisms.
Number of men and boys participating in awareness raising sessions and change maker training on the role of male socialisation as root causes of gender inequality, women's right to freedom from violence and participation in public spaces and political processes and receiving change-agent training.	97 men master trainers trained on additional modules. / 100,000 men and boys (100% of the total men forum members) made aware on masculinity, pro-women laws, early marriages, customary practices and women rights of political participation. / 8,122 men trained as change makers and at least 80% of them are able to establish circle of influence in AAWAZ forums where all 4 issues (gender, discriminatory practices, exclusion and right to information) are discussed and regular follow-up is maintained.	97 (34 KP, 63 Punjab) men lead trainers (100% forum members) trained. / 112,985 men and boys (47,672 KP, 65,313 Punjab) made aware. / 85% men in AAWAZ forums demonstrate positive change in knowledge (pre/post evaluation). / 8,122 (3,789 KP, 4,333 Punjab) men trained as ‘master trainers/change agents’.
Number of men and boys who are in AAWAZ forums demonstrating: / a. Knowledge on the role of male socialisation, masculinity, power, modern slavery, privilege and control as root causes of gender inequality; / b. Communication skills – to listen to girls and women with attention and compassion, and without judgment, advice or interruptions; and / c. Improved relationship skills - involving girls and women in decision making.	80% sample size with at least 2/3 skills.	Around 86% of men possess 2/3 skills. / 80% of the respondents understand male socialization and masculinity. / 92% of men & boys claimed improvement in communication skills and 3/4 of them claimed improvement in their relationship skills.
Number of women actively participating in AAWAZ forums and public events and in leadership positions.	80,000 women (80% of total women forum members) actively participating in forum meetings / 80,000 women actively participating in women assemblies/khuli katcheries. / 25,000 women in leadership positions and 75% of them demonstrating at least 4/6 skills: / Knowledge and women rights and legislative agenda. / Communication, influencing and relationship skills. / Play effective role in campaigning/contesting for local government election and/or women assemblies. / Possess budget literacy and carrying out advocacy at local level. / Take initiatives to voice and address VAW/G and promote women political participation in their communities. / Take affirmative actions to end modern slavery.	91,133 women (80% of total women forum members) actively participated in forum meetings. / 89,138 (37,201 KP, 51,937 Punjab) women actively participated in women assemblies/Khuli Katcheries and youth conventions. / 31,431 (12,540 KP, 18,891 Punjab) women have assumed leadership roles, comprising 10,370 office bearers, 416 resource persons, 1,481 women assembly members, 6,628 change agents, 2,734 peace connectors, 3,557 women in sub-committees and 6,245 youth leaders. / Over 87% of them demonstrating 4/6 skills including. / 87% are aware of women's’ rights and pro-women legislation. / 92% have taken steps in local government campaigning. / 86% have undertaken advocacy actions. / 83% have proactively taken initiatives on VAW/G. / 55% of Women Leaders (WLs) have held sessions on modern slavery and 57% claimed to have taken actions to end modern slavery.
Number of youth leaders with improved skills and supported to challenge discriminatory social norms in AAWAZ communities.	425 youth circles of influence established in 45 districts. / 8,856 youth leaders (63% men and 37% women) trained on seven themes and 75% of them demonstrate positive change in knowledge (pre/post evaluation). / At least 60% of the youth leaders taking affirmative actions (end modern slavery, gender discriminatory practices, promoting women political participation, Non-Violent Communication (NVC) and multiple identities) to further support youth within their constituencies. / At least 50% of the youth leaders are aware of Youth Parliament of Pakistan and 25% are connected (offline/online) with them.	440 (184 KP, 256 Punjab) youth circles of influence established across 45 districts. / 12,180 (4,930 KP, 7,250 Punjab) youth leaders (6,245 girls, 5,933 boys, two transgender) trained on seven themes. 86% of youth leaders demonstrate 34% improvement in their knowledge (pre/post evaluation). / 95% youth leaders have developed action plans and have held detailed sessions. / At practical level, 72% youth leaders reported that they have taken steps to eliminate violence against women. 47% of the youth leaders are connected through online activities.

Provide supporting narrative for the score

The output was designed to meaningfully educate the communities in general and women in particular to understand and participate in local, provincial and national politics. The objective was to support socially excluded citizens to engage with informal and formal political structures, without fear of discrimination or retribution. The programme created a cadre of women and men change makers to become role models in their communities. The change makers were to influence the programmes, policies on women’s rights, gender based violence, inclusion and contribute to conflict prevention. The trainings supported women community leaders from village and union council to be elected to District Women's Leader Assemblies (DWLAs). Through the assemblies, women gained experience of the public sphere and were able to better articulate their views as an elected leader.

The output slightly overachieved all of its targets. The output focused to reach out beyond the AAWAZ programme forum membership to build the leadership skills of 1,481 (633 KP, 848 Punjab) women assembly members in 45 districts of KP and Punjab. 31,431 (12,540 KP, 18,891 Punjab) AAWAZ women held leadership positions. These included roles as office bearers in AAWAZ Village Forums (AVFs), membership of the Women Assemblies, Aagahi Centre Resource Persons (ACRPs), and sub-committee members.

AAWAZ programme trained 227,491 (92,623 KP, 134,868 Punjab) women, men and transgender people on gender, masculinity, leadership, prevention of violence and inclusion in 45 programme districts. Participants demonstrated the depth of knowledge and positive attitudes as a result of a series of ‘Jamhoryiat Angan Se Aiwan Tak’[7] (JASAT) trainings. The M&E assessments show that 80% of the women demonstrated improvements in knowledge of basic human rights and women’s rights, participation in public events and AAWAZ initiatives, communication and negotiating skills and decision making. These women were not only actively involved in decision making, giving them increased voice, choice and control over their lives: they also support others to gain confidence and rights through their work, and act as role models in their communities. Eighty five per cent of the target community was sensitised and supported to vote in the local government elections. 87% of women received their national identity cards (against the target of 86%) while 87% or 290,385 (72,004 KP, 218,381 Punjab) women voters registered against the target of 80%. 1,253 (669 KP, 584 Punjab) women and 1,567 (942 KP, 625 Punjab) socially excluded men were supported to stand for positions in the local government elections. 649 (421 KP, 228 Punjab) women candidates and 894 (572 KP, 322 Punjab) men won council seats. The benefits of this training approach is not only limited to women as 76%[8] of men and boys from programme areas possessed knowledge of basic human and women rights, on how to participate inclusively with women in public events and how to provide a safe environment for women to make their views known through using an inclusive listening style. This training helped to make men active gender champions supporting positive change for women at the local level.
[7] Democracy from courtyard to people
[8] Taken from annual review 2016 actual result is higher.

The programme established 440 (184 KP, 256 Punjab) youth circles of influence in 45 programme districts. The youth circles of influence included 6,245 (2,469 KP, 3,776 Punjab) girls, 5,933 (2,459 KP, 3,474 Punjab) boys, and two transgender people, at Union Council (UC) and district levels. AAWAZ conducted intensive, participative training on gender and masculinity, Violence Against Women and Girls (VAWG), violent extremism, non-violent communication and political participation of women. The pre and post session evaluation showed that 86% youth leaders demonstrated positive change in their knowledge. 72% of youth leaders reported that they have taken steps to eliminate VAWG, 45% took initiatives to spread the message on non-violent communication while 41% youth leaders took steps for promoting gender equality in their area. As a result of sessions conducted by the youth, 77% of community respondents were found more knowledgeable on gender concepts and non-violent communication and 55% of them claimed taking actions against VAWG.
The programme worked with men and boys

Towards the end of 2017, AAWAZ held awareness raising sessions on modern slavery with members of the AAWAZ District Forums (ADFs), youth leaders and Resource Persons (RPs) of the AAWAZ Aagahi Centres (AACs). The issues of the domestic workers, home based workers, brick kiln workers and factory workers were shared with the public. Discussions with the labour departments and local government departments in both provinces on modern slavery emphasised the need to implement the national laws.

The AAWAZ programme took its focus on women’s community leadership development to the regional level in 2016, by setting up the South Asian Women Alliance (SAWA). In January 2017, AAWAZ organised a Regional Conference for the South Asian Women Alliance of Community Leaders (SAWACL). Women from eight SAARC (South Asian Association for Regional Cooperation) countries participated in the event. SAWACL is registered with the SAARC Secretariat in Nepal as an alliance. The Alliance will support the monitoring desk of SDG Goal 5 (women empowerment). At the AAWAZ supported Annual Strategic Planning Meeting of the National (read Pakistan) Chapter of South Asian Women’s Alliance in October 2017 the programme ‘Women’s Participation in Upcoming General Elections’ in Pakistan was launched, independent of the AAWAZ programme. The alliance will work with the Election Commission of Pakistan (ECP) to ensure the 5% quota of women’s seats are fully allocated.

Lessons identified this year linked to this output and recommendations for future programmes
- Enabling women to participate in the public sphere is challenging in conservative societies. Structured interventions based on in-depth contextual knowledge and consultation with the women and men of the community are critical for women’s ability to negotiate her space at home, within the community and society at large.
- Sixty per cent of Pakistan’s population is under the age of thirty. Creating a safe environment for positive youth engagement is critical for the future of Pakistan. The programme provided leadership opportunities to the young people to build their confidence and to help create a pluralistic society.
- Women’s political participation is difficult without engaging men and boys. The engagement of men and boys in the programme positively contributed to the women gaining increased mobility, decision making at both household and community levels and effective participation in politics.

Output Title	Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa and Punjab
Output number per LF		2	Output Score	A+
Impact weighting (%)?		25%	Impact weighting % revised since last AR?	Y (20% to 25%)

Output 2 aimed to promote greater community cohesion and tolerance in order to create an environment in which women and other excluded groups (transgender/PWD[9]/religious minorities) could participate fully in political and public life. The output design emphasised developing the capacity of citizens to be able to work together to identify and prevent disputes peacefully without recourse to violence. Previously the output focused on conflict mediation and this shifted to conflict pre-emption in 2014. The scoring of A+ not only reflects the attainment of the miletstones, but also the success of the prevention approach as evidenced below. The weighting of this output incresed to 25% from 20% after the 2017 annual review.
[9] People with disabilities (PWD)

Indicator(s)	Milestones	Progress
Number of women and men informed about support mechanisms and provided with awareness on non-violent communication and valuing diversity, particularly religious minorities (data disaggregated by location/youth/exclusion).	5 key messages developed and disseminated on non-violence and tolerance (continually reinforced).	Key messaging developed and disseminated on non-violence and tolerance. / In 2015, AAWAZ developed five messages on non-violence and tolerance. / All forms of hate speech – written, verbal and actions – is against the law. / Under 153-A of the penal code of Pakistan hate speech is a crime and punishable. / We need to stop all speeches that incite discrimination, hostility or violence. / Words can hurt and words can heal, make sure our words heal. / Respect the Constitution of Pakistan maintains equality of men and women without any discrimination based on religion, sex, caste, sect and ethnicity / (Validated by DFID’s Annual Review 2016)
	200,000 citizens including 50% women made aware of techniques for non-violent communication and valuing diversity and multiple identities. / 80% men and women in AAWAZ forums demonstrate positive change in knowledge (pre/post evaluation).	227,491 citizens (92,623 KP, 134,868 Punjab) citizens made aware through awareness raising sessions. / This year, the master trainers rolled out 469 trainings on Multiple Identities at UC level with 3,714 men and 3,725 women resulted in 77% improvement in their knowledge. / 89% men and women found knowledgeable about non-violent communication.
Number of women, men and socially excluded citizens positively impacted by AAWAZ forum interventions/ members' actions to protect them from discrimination, harmful cultural practices & violence (sectarian, gender, religious etc.).	7.5 million people in 45 districts. / Early response mechanism for dispute pre-emption in place in all village forums. / Early warning system in place for all 21 district conflict prone districts across two provinces.	8.484 million (2.782 KP, 5.702 Punjab) people positively impacted. Details are as follows: / 2.90 million (0.49 KP, 2.41 Punjab) people positively impacted in 21 conflict sensitive districts and 5.584 million people (2.292 KP, 3.292 Punjab) positively impacted by the pre-emption of 41,390 conflicts at village level. / Early response mechanism in place in 100% village forums. VAW existed in almost every village, while 18% of them had sectarian and 7% had interfaith conflicts. / Early warning system in place for all 21 districts (7 KP, 14 Punjab). / VAW existed in all union councils of each district, while 43% had sectarian and 21% had interfaith conflicts.
% of people in programme areas who consider community pre-emption and cohesion mechanisms to be credible and effective.	Based on the Annual Follow-on Survey 2017, 95% of the village respondents who are aware of the conflict pre-emption mechanisms in their respective areas, considered these mechanisms credible and effective.	95% of the community members were satisfied with the process and effectiveness of the early response mechanism at village and district levels.
Number of women and excluded group members participating in AAWAZ Forums’ local level peace building initiatives (data disaggregated by gender, youth and religion)	350,000 women and excluded groups participating in events and 75% reporting (post event feedback) improvement in social cohesion knowledge and attitude.	373,169 (193,803 women, 179,326 men, 40 transgender people), (152, 982 KP, 220,187 Punjab) participated in events. / 89% reported improvement in knowledge. 98% respondents rated their experience of participation in these events as strongly valuable. / 94% think that religious minorities in our country should celebrate their days / events with liberty and 56% of them reported claimed participation in the social events of minorities.

Provide supporting narrative for the score

The output was significantly changed after the 2014 mid-term review. The earlier output focused on conflict mitigation. The current output focuses on conflict prevention. The output weighting was increased to 25% from 20% with output 4 being reduced by 5% as recommended by the 2017 annual review to capture and give more weight to the extraordinary success of the output. The programme endorses the plural nature of the communities and builds on diversity. The output emphasised developing the capacity of citizens to be able to work together to identify and prevent disputes peacefully without recourse to violence. Focusing on resolving the inter-faith / sectarian violence, VAWG, land disputes and community conflict. 8.484 (2.782 KP, 5.702 Punjab) million citizens benefitted through the prevention of 41,390 (15,917 KP, 25,473 Punjab) conflicts including 29,241 domestic violence and 1,130 interfaith / sectarian conflicts.

One of the key elements of the programme was to introduce Early Warning Systems (EWSs) to help prevent violence and conflict in the communities. The programme learned that inter-faith and sectarian conflict is often triggered by social events e.g. music, public processions, the timing of religious rituals or driven by personal grievances. AAWAZ identified the 21 (seven in KP, 14 Punjab) most conflict prone districts for special attention. EWSs were then developed in all districts, AAWAZ provided support to bring together multi-stakeholder groups to create peace maps. The mapping exercise included district government officials, the law enforcement agencies, influential religious scholars, the media, local influential people, members of official peace committees, Civil Society Organisations (CSOs) and local businesses. The EWS involved an iterative monitoring of the triggers of violent conflict and a commitment to collaborative responses from all those party to the development of the system.

The programme trained 227,491 (92,623 KP, 134,868 Punjab) women and men on citizenship; the positive values of compassion; human rights and mutual respect; identification of the causes of conflict. The programme invested in existing structures to build consensus for peace in the area. The participants were particularly sensitised about hate speech and other triggers of conflict, and the direct links between hate speech and harmful impacts on marginalised groups. The programme focused on creating an understanding among different faith groups. The exposure was helpful to understand and dismiss the taboos set against each other’s religions. The programme invested in sensitising men and women on multiple identities and stereotypes. Multiple identities allowed people to connect with each other meaningfully. Beneficiary feedback exercise noted that participants felt the collective cultural events had stimulated a culture of peace and harmony amongst community members and inspired official peace committee members to remain active throughout the year instead of specific occasions. Respondents’ knowledge of non-violent communication themes stood at 76%, while 32% of respondents stated that they had personally facilitated a session on similar themes. In a major shift in attitudes, translating into behaviour, 94% respondents thought that religious minorities should celebrate their events with full liberty and 64% of them reported that they themselves have participated in the social events of religious minorities.
Lessons identified this year linked to this output and recommendations for future programmes
- One of the key lessons from the programme is to constantly learn and adapt. While AAWAZ was not an adaptive programme, it clearly demonstrated the effective use of learning mechanisms. The programme transition from conflict mitigation to conflict prevention was critical to the success of the programme.
- The programme embraced pluralism instead of inclusion. This is critical in the context of Pakistan and if seen through the lens of multiple identities. The approach supported the people to connect with each other at multiple levels. This was only possible through the support and decades of civil society work prior to AAWAZ. It is important to learn, AAWAZ and programmes like AAWAZ are building blocks for a generational change process. The knowledge of the context and positive internal and external networks of civil society organisations are critical to the success of the programme.
- Enabling women to participate in the public sphere is particularly challenging in conservative areas. Structured interventions based on in-depth contextual knowledge and consultation with the women and men of the community can provide women with the space to start engaging with other women publicly.

Output Title	Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa and Punjab
Output number per LF		3	Output Score	A+
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	N

This output enabled forum members especially women, transgedner, religious minorities and their communities with skills and tools to connect constructively with government to improve their daily lives and strengthen mutual accountability. This helped to break the traditional patron-client relationships through which deals are done and services delivered that exclude the poor. This state citizen engagement enabled poor women, men and the excluded to speak out about their needs and priorities for services and to hold government to account. In addition, it enabled government to understand, budget and plan for the needs of all citizens for effective and efficient services. Progress exceeded expectations across this output scoring an A+ overall.

Indicator(s)	Milestones	Progress
Number of women and socially excluded citizens informed of rights, procedures and hotlines for accessing and demanding improved delivery of services from public officials and political representatives.	Messaging developed and disseminated (continually reinforced). / 400+ AAWAZ Aagahi Centres (AAC) continued to operate in programme areas. / 100,000 females accessing AAWAZ Aagahi Centres (Continued).	227,491 (92,623 KP, 134,868 Punjab) citizens informed on the basics of citizenship, advocacy for social services, Right to Information and procedures to access public services. / 409 (168 KP, 241 Punjab) AAWAZ Aagahi Centres actively used to connect citizens to state services and information. / The coverage of an AAC remained eight villages. / 56% respondents reported that they visit centres for women to women engagement while the remaining respondents approach these centres for information sharing and improved access to services. / Over 100,000 (42,171 KP, 58,611 Punjab) women and girls accessed AAC.
Number and types of demands raised with public officials and political representatives in education, health and other priority areas benefiting women, girls and other excluded groups (data disaggregated by location/gender/nature of issues).	25,000 demands raised. / 14,000 engagements with district and provincial government duty-bearers on policy or implementation issues impacting improved service delivery,	28,905 (10,922 KP, 17,983 Punjab) demands raised, / 35,111 (19,686 KP, 15,425 Punjab) engagements were made in 489 District Coordination Committees meetings, 2,243 (964 KP, 1,279 Punjab) Khuli Katcheries (open town hall meetings) and 31,968 (17,822 KP, 14,146 Punjab) one-on-one meetings between citizens including women members with district and provincial government officials on policy or implementation issues. / The District Coordination Committees (DCCs) established in 19 districts of KP. / The Government of Punjab sent notification to all 26 districts for support and coordination.
Cumulative number of demonstrable changes in policy and implementation by local/provincial government in response to public demands where there is attribution to AAWAZ, a proportion of which reflect the voice of women and other socially excluded groups.	At least 48 examples from across the programme.	The Data Quality Assessment carried out by DAI’s M&E team indicated that AAWAZ District Forums (ADFs) have deepened their relationships with government authorities and that some AVFs have become adept and sophisticated in their use of advocacy methods as well as in their analysis of the steps needed to achieve change. In two years, ADFs have successfully obtained reforms in 159 (45 KP, 114 Punjab) policy and service implementation areas for the benefit of women and the socially excluded. For further details, please see the attachment.

Provide supporting narrative for the score

The output’s focus was to connect the demand side interventions with the supply of state services. The focus was to ensure socially marginalised and vulnerable people are able to demand for better services. The programme helped developed state citizen engagement enabling poor women, men and the excluded to speak out about their needs and priorities for services and to hold the government to account. It enabled the service providers, provincial, district and local governments to understand, budget and plan for the needs of all citizens for effective and efficient services.

The programme held sessions for over 227,000 women and men on understanding the basics of citizenship; advocacy for social services; the right to information; and information on procedures to access public services. The 450 (190 KP, 260 Punjab) AAWAZ Aagahi Centres (AACs) evolved from women-friendly spaces to a citizen advice bureau function in many places. The final qualitative survey confirmed that, on average, the outreach of AACs increased from five to eight villages. Fifty women per month visit the centres. More than 85% of the respondents visit the centres on a monthly basis. The over 2,243 Khuli Katcheries (open town hall meetings) with government line departments were key in fostering citizen-state engagement to raise communities’ concerns with district and provincial government officials. The programme conducted social audits with the women, men and transgender community members to assess the status of health and education sectors in eight districts and key informant interviews with select government officials. Community scorecards were developed and findings were shared during provincial workshops, leading to recommendations for improvements. These interventions resulted in increased demand for services with 28,905 (10,922 KP, 17,983 Punjab) demands being raised in both KP and Punjab. This resulted in 27,467 (14,600 KP, 12,867 Punjab) improvements in services of which 7,923 related to education and 5,752 to health. The 2017 annual review highlighted an example of a demand being raised and met in Haripur, KP, where AAWAZ provided support to people with disabilities (PWD) to demand their rights from the government of KP. The programme supported participation in a peaceful protest, after which the administration arranged an in-house meeting with members of the AAWAZ forum and senior representatives from government. The government officials agreed to all 5 of the demands 20 (including, for example, provision of free medical aid to PWD[10] and an increase in the quota for government jobs for PWD).[11]
[10] People with disabilities (PWD)
[11] The government of KP employed 17 disabled people within the bureaucracy since this agreement.

Over eight million people directly benefitted from the improved service delivery of the state. District Coordination Committees (DCCs) were formally developed for the citizens to continue to engage with the service providers on regular basis beyond the life of the programme.

Lessons identified this year linked to this output and recommendations for future programmes
- Connecting demand side interventions with service delivery structures is critical for the success of programmes. The programme built strategic relationships with officials in government (at all levels) and parliamentarians to strengthen the citizen-state engagement. It increased the acceptability of the programme and enabled the achievement of substantial legislative reforms. It also reduced operational and programmatic risks.
- The programme created strategic links with the media, civil society and other development programmes. The synergies were critical to build collective action and to amplify the voices.
- Provincial Forums are an important forum to trigger change at the macro level and to forge strategic partnerships with provincial ministries and key decision makers to tangibly influence legislation.

Output Title	Improved evidence generated, synthesized and communicated/ championed to political leadership in Khyber Pakhtunkhwa and Punjab
Output number per LF		4	Output Score	A
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	Y (20% to 15%)

Output 4 was comprised of programme analysis, research and results commonly referred to by its acronym as PARR. It was designed to be AAWAZ’s engine room for knowledge and research, to leverage reforms in practice and policy through the development and use of credible evidence. Its work involved analysis and synthesis of monitoring information collected by the consortium partners responsible for outputs 1, 2 & 3; follow-up activities to confirm, deepen and add value to partners’ monitoring information, including the identification of lessons and best practice; research to strengthen contextual information and/or fill out gaps; research and policy briefs that can be used to influence decision-makers ; and activities to generate local, national and global debate on empowerment and accountability. The weighting of this output decreased to 15% from 20% after the 2017 annual review.

AAWAZ met expectations in the implementation of this output and scored an A.

Indicator(s)	Milestones	Progress
Effective evidence-based (qualitative/quantitative) M&E systems established.	A fully functional M&E system in place across Management Organisation (MO) and partner organizations. / Management Information System (MIS) used to produce final analyses of results.	Log frame revised and approved by DFID. M&E plan developed, approved and being implemented. / 10 quantitative and qualitative assessments completed on a quarterly basis. / Data quality assessment (DQA) carried out across 45 districts. / MIS system developed and used by all programme and district staff across all 45 districts for data analyses. / Two additional M&E working groups established. One with Government of KP and one with coalition partners.
Number of quality evidence-based research commissioned on select thematic issues and disseminated for policy and practice.	20 research studies conducted on selected AAWAZ related themes and widely disseminated and used to inform women and exclusion related policy reforms. / 8 evidence-informed policy briefs for AAWAZ initiatives produced and used by CSO network and research organizations. / Cumulatively, 38 innovative projects implemented. / 33% of innovations funded by AAWAZ receive subsequent scale-up funding (by AAWAZ or others). / Knowledge base institutionalised for information sharing between partners.	19 studies completed and published. / 8 policy briefs completed and used by CSO networks. / 37 projects implemented and completed under Response Fund in four phases. / 33% i.e. 7 partners received scale-up funding. Four of them got it from AAWAZ and five from other sources. / Knowledge management strategy and plan developed and implemented to leverage knowledge products through seminars, lobbying meetings and media interventions for advocacy.
Cumulative number and types of quality advocacy campaigns initiated by AAWAZ, consolidated, synthesized and analysed by PARR.	3 campaigns implemented. / 9.17 million people reached on key issues such as VAWG, hate speech and improved local governance.	Policy Advocacy Action Plan (PAAP) prepared and monitored. 3 Campaigns (VAWG, anti-hate speech and local government) implemented. / 9,171,782 (4,101,924 KP, 5,069,858 Punjab) people reached on women rights through PTV, radio and social media.
Number of women and men who are in AAWAZ forums demonstrating knowledge on the AAWAZ’s research and communication products and campaign themes. / Cumulative number of adaptations in implementation and policy, and demonstration of good practice attributable to AAWAZ products.	Field studies endorse that the material is being used. More than 76% of the sample size across 39 districts are aware of the 7/15 research studies. / 10 response fund projects demonstrating change in implementation and policy level.	76% of the 687 total respondents across 39 districts are aware of the 7/15 research studies / 11 response fund projects demonstrating change in implementation and policy level

Provide supporting narrative for the score

The output was designed to provide high quality independent monitoring and evaluation, knowledge and research to leverage reforms. The AAWAZ programme developed evidence-based monitoring and evaluation systems – with a focus on clearly articulated programme theory of change, logical framework, and M&E plan that entailed quantitative and qualitative data collection, collation, analyses, report and ensuring all data had quality parameters. The AAWAZ programme invested time in engaging with both of the relevant provincial governments. In response to demand from Government of Khyber Pakhtunkhwa (GoKP), AAWAZ set up an AAWAZ-GoKP monitoring and evaluation working group and conducted joint field visits using a mutually agreed and standardised evaluation framework and survey instrument. A cross programme M&E group was also developed to help leverage learnings across different DFID programmes. This group was instrumental in improving the programmes’ outreach, avoid duplication of efforts, and thus increased value for money (VfM). A Multi-Agency Information Sharing Protocol (MAISP) was signed by all partner projects to provide a framework of working relationships, establish a comprehensive and consistent knowledge sharing link, and guide the sharing of thematic and geographic information. The M&E team hosted all external evaluations including all DFID’s Annual Reviews, baseline and annual follow-on survey in selected programme and control areas, and third-party VfM assessments using case study approach and desk analysis to validate, refine and calibrate its VfM framework. A number of case studies were developed to highlight the VfM aspects of a range on interventions. The weighting of this output was reduced by 5% after 2017 annual review with output 2 increased by 5%. This was done to give more visibility to the great results being achieved under output 2 and given that most of output 4 was completed in 2017.

AAWAZ’ s Strategic Learning Unit (SLU) produced cutting-edge, innovative and revolutionary research capturing voices of marginalised and excluded groups and providing critical evidence for more inclusive and gender sensitive policies. Cumulatively, it produced 19 research papers, eight policy briefs and a report on the latest perception survey covering a range of sensitive topics relating to minorities, conflicts, honour killing and rape legislations, disenfranchisement of women, state accountability and public policy.

AAWAZ also ran three campaigns in parallel over the last three years: ending violence against women; anti-hate speech; and local government reforms. AAWAZ estimates that more than nine million people were reached through these campaigns using press, television, radio and social media.

The VAW campaign generated for the first time ever, nationwide public debate on the issue. The campaign provided a platform to women community leaders where they could share the challenges they face and success they have achieved at the community level. A resolution was presented by the AAWAZ partners demanding gender equality, violence free environment and education for women, education, implementation of laws, role of media towards women empowerment and end to anti women practices. More than 50,000 people participated in the signature campaign to stop violence against women.

AAWAZ anti-hate speech campaign reached over 1.5 million people through local media across 45 districts of Punjab and KP. Eight radio programmes were aired highlighting true stories of conflict pre-emption in 16 districts of Punjab. Similarly, radio talk shows on ‘bolo zimadari se’ were recorded and aired with coverage across 14 districts of KP. For greater outreach and public support AAWAZ held seminars on anti-hate speech and promotion of peace and harmony in programme districts of KP and Punjab. A brochure on anti-hate speech was disseminated to all consortium partners with wider distribution to the change agents in AAWAZ villages. A critique of the law of Anti-Hate Speech was shared with Ms. Mary Gill, a Punjab provincial parliamentarian. She committed to present the key recommendations with the Advisor to Law and Justice Department, Government of Punjab. In 2017, all policy recommendations were shared with the Provincial Commission on Minority Rights established in Punjab.

The programme provided small grants to organisations working on similar programme issues, to encourage innovation, address issues as they arose in the programme, and support improved evidence. Four rounds of grants were implemented. Cumulatively, the programme awarded 37 projects among 29 partners, covering a number of non-traditional themes using a variety of vehicles including documentaries, mapping, songs and training packages. These projects were implemented in 25 districts (15 Punjab, 10 KP). These initiatives exposed smaller scale CBOs to the national development agenda whilst linking their localised interventions to the higher-level norm-breaking agenda.

Lessons identified this year linked to this output and recommendations for future programmes
- Robust monitoring, evaluation and results management in voice and accountability programme increases visibility. It ensures that attention is paid to otherwise marginalised issues and helps communities, government and other development partners to understand the impact of the programme.
- The concept of embedding a learning mechanism is not new. It needs special efforts to differentiate between monitoring and ensuring learning takes place across the programme. The programme initially struggled with the concept but over the years it managed to build relationships and trust among different tiers of the programmes.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

AAWAZ aimed to ensure that democratic processes were more open, inclusive and accountable to citizens in Pakistan at the outcome level, which contributed in turn to a stable, inclusive and tolerant democracy in Pakistan at the impact level.

IMPACT: Stable, inclusive and tolerant democracy in Pakistan / OUTCOME: Democratic processes in Pakistan are more open, inclusive and accountable to citizens / OUTPUTS: / Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa (KP) and Punjab. / Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa (KP) and Punjab. / Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa (KP) and Punjab. / Improved evidence generated, synthesised and communicated/ championed to political leaders/ elites in Khyber Pakhtunkhwa (KP) and Punjab.

At the impact level, AAWAZ contributed to improvements in Pakistan’s World Governance Indicators’ voice and accountability rating from -0.88 to -0.69. The programme also contributed towards increasing the percentage of Pakistanis who felt ‘quite safe’ or ‘very safe’ from 38% to 69% as its intended impact, as evidenced by the 2017 Gallup and Gilani polls. The World Economic Forum Gender Gap Index ranks Pakistan 143rd out of 144 countries for the last couple of years. This does not necessarily mean that the situation for women and girls in Pakistan has deteriorated, but that its position vis a vis other countries is still poor. We do know that the programme contributed significantly to women’s interest and participation in both formal and informal decision making. This has all resulted in building a notable increase in the volume of social capital of a kind that resists the trend towards an ever more conservative and intolerant society.

At the outcome level AAWAZ managed to strengthen democratic and inclusive processes by protecting and expanding existing public spaces for poor and excluded people especially women, minorities, and transgendered to express their views, needs and priorities without discrimination or retribution. This critical engagement between people and state gave the government a better understanding of community needs whilst citizens were able to hold government to account to improve their performance. This in turn helped reduce service gaps, empower women and men to play an active role in their own development and contributed towards the achievement of results.

Outcome Results by indicator
Indicator	Milestone	Progress	Overall Analysis and Reflections
Number of laws on which progress is made in preparation, negotiation, passage and enactment for supporting the rights of women and excluded groups	1 legislation at stage-2 (KP) / 1 at stage-3 (1 KP) / 1 at stage-4 1 (1 KP) / 1 at stage 10 (VAW Policy / National level) / 3 at stage-10 (Three laws passed in Punjab) / 3 at stage-16 (Three laws passed at National level) / 1 national bill withdrawn	Anti-Honour Killing (Criminal Amendment) Act 2015[12] / Anti-Rape (Criminal Amendment) Act 2015 Law[13] / Hindu-Marriage Act 2017[14] / Child Marriage Restraint Act [15] / Muslim Family Laws Amendment [16] / Punjab Protection of Women against Violence Act 2016[17]	AAWAZ supported national and provincial legislation on women, girls and religious minorities through direct drafting, lobbying on the contents of legislation and advocating with legislators to get the Bills passed in the provincial or federal assembly.
Proportion of men and women who report change in knowledge, attitude and practices regarding participation of women in political and public spheres and VAWG	80% women and 80% men in AAWAZ forums demonstrate positive change in knowledge and attitude / 30% men and 30% women who have taken some action against GBV and for participation of women in public and political spheres	Around 90% of men and women in programme areas are aware of AAWAZ themes / 86% of men and women in programme areas believe that women’s vote and candidature in elections is important for strengthening democracy. / More than 89% of women cast their votes in 450 AAWAZ’s union councils across KP and Punjab / 53% of men and women reported change in their practices regarding VAW/G as they claimed ‘stopping’ a member of their family/community from physical or verbal abuse of women in case of such incident.	Social norm change is expected to result from the combination of work across outputs. Change in attitude is measured by women and men’s preparedness to take personal action to counter GBV or to promote women’s participation. / This year, increasing number of women in AAWAZ working areas have promoted women political participation as voters and candidates. / Strong evidences exist in the programme areas where both men and women claimed to have ‘broken’ the cycle of gender-based violence.
Percent of girls, women and excluded groups who report use of and satisfaction with key public services	70% using public services (overall 14% increase from baseline) / 75% of them satisfied with public services (overall 9% increase from baseline)	The annual follow-on survey 2017 reveals that 67% of target group are using public services (overall 11% increase from baseline) / And / 73% satisfied with public services (overall 7% increase from baseline).	As communities become better able to engage with service providers, services are likely to improve; satisfaction and take-up is likely to be greater. / 66 percent of respondents had been to some form of a public health facility (BHU, RHC, THQ, DHQ etc). About 68 percent of those in project areas who had children in school had at least one child in a government facility.
Number of people supported to have choice and control over their own development and to hold decision-makers to account	5,125 Forums / 200,000 Direct Members / 7.5 million Indirect People	5,004 forums (Over 95% Restructured) / 227,491 Direct Members (113,916 women, 112,985 men and 590 transgender) (92,623KP, 134,868 Punjab) / 8.316 million people potentially benefitting within 4,532 settlements owing to demands addressed in education and health sectors and pre-emption of sectarian and inter-faith disputes across 45 districts of KP and Punjab	The AAWAZ Forums and Aagahi Centres continue to show results of improved women’s utilisation and social acceptance of women in public life. / Increase in membership is owing to concerted efforts of change agents and capacity building of AAWAZ forums
[12] The legislation introduces strict punishment for honour killings and removes the loophole whereby perpetrators could escape punishment by agreement with the victim’s family.
[13] The Anti-Rape law provides that the suspect may be subjected to medical examination and DNA testing, that cases must be resolved within three months and imposes greater sentences for rape of a minor or a person with disabilities.
[14] This legislation gives Hindus the right to marry by providing a mechanism and conditions for registration of Hindu marriage and the grounds and procedure for dissolution of the marriage.
[15] According to this law, any girl under the age of 16 and a boy under the age of 18 is considered a child. An adult person who contracts child marriage will be liable to punishment of up to six months’ imprisonment and a fine of Rs 50,000. The penalty also applies to Nikah (marriage) registrars.
[16] Under this legislation, Muslim Family Law Act, it is now mandatory for Nikah registrar to fill all the entries of Nikahnama (marriage contract) to avoid violation of the rights of the bride or face a penalty.
[17] This legislation contains remedies for victims of violence, criminalise all forms of violence against women and also provides them with special centres which remove the usual red tape hurdles that complicate a woman’s quest for justice.

The programme laid the foundation of “diagonal accountability” in the country by taking women and socially excluded groups (traditionally at the base of ‘vertical’ accountability relationships) and enabling them to be included in – or in some cases creating – more ‘horizontal’ accountability mechanisms (e.g. Khuli Katcheries, peace committees, district education and health monitoring committees and others). Thus, the programme brought a shift by involving women and minority groups in new watchdog roles in state oversight functions, breaking state monopoly of ‘official executive oversight’. This was vital for if the programme was to achieve the outcome of a Pakistan accountable to all its citizens especially the most excluded.

Summarise the programme’s theory of change and major changes to it in the past year
AWWAZ articulated its theory of change at two levels: an overarching theory for the programme and a theory of change for each programme output.

Need
Exclusion on the basis of gender, religion, class and caste manifested in unequal power relations, especially between men and women, leads to lack of voice, choice and control for women, and socially excluded groups from household to the national level, in public and in private spaces, increasing vulnerability to violence and limiting their freedoms and opportunities as full and equal citizens of Pakistan
Barriers to Change
Individual Level	Low social status / Exclusion from engagement, decision making, public spaces, and access to resources / Lack of self-esteem, confidence, opportunities and freedoms / Lack of skills, knowledge, information and networks to exercise citizenship rights / Limited access to basic social services / Violence or threat of violence
Social Level	Patriarchal beliefs, attitudes and cultural practices / Stereotypes, prejudices, and discrimination based on class, caste, religious and sectarian differences / Exclusion from public spaces, decision making processes and access to resources / Violence – sectarian / religious and gender-based / Lack of social cohesion
Political Level	Elite capture of power and resources resulting in patronage-based and weak governance / Authoritarian political culture blocking citizen’s participation and voice in policies, laws and decisions that affect their lives / Discrimination against women and excluded groups in laws, policies, institutions, systems and processes / Weak enforcement of laws and policies for women and excluded groups / Poor delivery of social services for women and excluded groups
Generating evidence on key AAWAZ themes through research and dissemination will influence politicians and decision makers to undertake the policy reform required to safeguard the rights of women and socially excluded groups and promote their participation as equal citizens of the State. / Raising awareness on women’s rights and the rights of socially excluded groups and build their skills to challenge discriminatory social norms, attitudes and practices; and information dissemination to citizens on laws, government processes and procedures for delivery of services, will lead to positive changes in perceptions, attitudes and practices. These changes will increase women and socially excluded citizens’ confidence, space to access rights and capacity to take action for equality. / Creating coalitions for action and inclusion– Working directly and intensively with a critical mass of women and men, through forums and coalitions, (1) raising awareness on root causes and key issues of exclusion and conflict , (2) providing knowledge on rights, government processes for delivering basic social services and advocacy tools for raising demands and (3) facilitating their access to government officers and political representatives will create communities of practice at the local level and amplify the voices of women and socially excluded groups in and across districts to the national level. These coalitions will drive change by ,challenge discriminatory norms and harmful practices and foster inclusion at the individual, household, community and national levels, with a special focus on influencing the State and holding it accountable. / Advocating for Legislation/Policy - Advocacy with key policy makers, assistance in drafting laws, conducting dialogues and raising demands for new laws from grass-roots to provincial and national levels, to safeguard the rights of women and socially excluded groups will create an enabling environment for women and socially excluded groups to participate in public spaces/politics and occupy leadership positions.
Outputs
Improved evidence generated, synthesised and communicated/championed to political leaders/elites in Khyber Pakhtunkhwa and Punjab. / Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa and Punjab. / Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa and Punjab. / Women better able to participate safely in politics and public spaces at federal, provincial local levels in Khyber Pakhtunkhwa and Punjab.
Outcomes
Democratic processes in Pakistan are more open, inclusive and accountable to citizens
Impact
Stable, inclusive and tolerant democracy in Pakistan

Theories of change (TOC) are particularly important for governance of programmes as they provide the basis for interrogating assumptions about the relationship between "voice" and "accountability".
Many programmes make a leap of faith by assuming that building awareness of rights of groups and equipping them with advocacy skills, there will be automatic changes in power relations and behaviours that will lead effortlessly to an improved set of outcomes.

Reality is more complicated. Relationships between governments and citizens are influenced not only by the power and interests of a variety of stakeholders but by institutional and financial constraints. Relationships between women and excluded groups and the outside world are influenced not only by custom, emotion and social norms but also economic power and control over labour.

AAWAZ re-examined some of its initial assumptions on the type of changes expected from its activities (awareness raising/community capacity development/empowerment trainings/etc) after the mid-term review of the programme in 2014. The TOC did not change in essence; however it was refined to more accurately reflect the partners' combined understanding of shifts that can take place through realising programme outputs. This in turn led to the development of a new logframe with qualitative and quantitative indicators and to the revision of the VfM framework. This reality check on the level of change that is possible from engaging with communities helped AAWAZ adopt a ‘walking with approach’[18] in working with communities in order to embed knowledge and facilitate change.
[18] This is a continuous learning approach, where by the CSO works through CBO with the community over a period of time to ensure knowledge is translated into action.

The programme worked at multiple governance levels, from villages to districts to the provinces, working with the national and provincial legislators, service providers. It explored and successfully managed the avenues to work at South Asia level through the SAARC. Therefore the programme outputs are not just confined to its quantitative results on the ground. It contributed to national and provincial legislation – thus expanding its scope beyond it immediate programme beneficiaries. The strategic use of the opportunities led the programme to have an impact at the South Asian level. The baseline survey conducted in 2014/15 provided the necessary evidence on targeting performance against logframe indicators. This evidence also provided the basis to track results that were monitored by an independent third party monitor, managed by the implementer on the annual follow-on surveys. The programme logframe was revised, new indicators were added and the milestones were re-aligned for some indicators. Data collection and management tools were updated complying with data quality parameters. The programme constantly used adaptive programming techniques to ensure the outcomes were achieved and directly contributed to the impact.

Explain major changes to the logframe in the past year

The key changes made in the final logframe in November 2017 are as follows:
- At the impact level, we updated the actual scoring on two impact indicators. For instance the voice and accountability score and the international gender gap rank.
- No major change in outcome statement and indicators.
- Under output 1, we revised targets of reaching and training at least 50% young women. The figures for 2017 were 8,856 youth leaders (63% men and 37% women) trained. This was in consistent with the Annual Review finding.
- No changes were suggested under outputs 2 and 3.
- One action research on bonded labour (modern slavery) was added under indicator 4.2.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

Originally AAWAZ had an overall Management Organisation (MO) budget of £33.85 million to cover fees, operations and programme activities during inception and implementation. Through the contract amendment on 12 May 2017 for extension to 20 May 2018, DAI (the MO) was provided with an additional £4.75 million which increased the overall MO budget to £37.3 million. There was a budget of £1.3 million allocated to supplies at the inception stage of the programme – bringing the total to £38.6 million.
The key driver of costs in AAWAZ was technical assistance. Due to the large scale targeted outreach of this programme, technical staff salaries consistently remained the major cost driver of this programme at 50% (including the MO and partner organisations). Operational expenses represented 18% of the budget and programme activities - 32%. Of the latter, support to AAWAZ Aagahi Centres (AACs) remained the major cost driver under this category. Please see section F below for details.

Value for Money was integrated into the programme design in 2015. This was done by developing a VfM framework which helped identify some of the key metrics on which information was collected to yield a cost-benefit analysis (CBA) of the programme. In the following years, the key assumptions were replaced and further refined to track a relevant set of indicators which were linked directly to the approved logframe indicators and implemented interventions, compared to the indicators proposed at the business case stage. Furthermore, third-party Value for Money assessments using case study approaches and desk analyses to validate some of the benefit streams and capture effectiveness of the programme through live examples.

Analysis in 2018 which captured and monetised all the potential benefits and included all the costs of the programme, AAWAZ showed an Internal Rate of return (IRR) of 97% for the programme and £210 million, as a positive Net Present Value (NPV)[19], incurred over 15 years (discounted at 10%). In this manner, the analyses demonstrate ‘five times higher benefits’ compared to the original business case. Furthermore, the third party VfM analysis concluded that for every £10 spent by the programme has resulted in: 16+ citizens safer, 7+ additional citizens using public services, 8+ citizens more satisfied with use of public services and 2+ citizens to have choice and control over their own development and to hold decision-makers accountable.
[19] The Net Present Value compares the value of a dollar today to the value of that same dollar in the future, taking inflation and returns into account. If the NPV of a prospective project is positive, it should generally be accepted.

Economy: AAWAZ's detailed competitive procurement policies and financial and operational guidelines, including an annual costed work plan, plus a rigorous approach to compliance indicates that the programme operated with the right tools to achieve economy. In addition to DFID policies and procedures, DAI deployed its own Governing Policy on Procurement and Inventory Management; it used Blanket Purchase Agreement (BPA) or Vendor Ordering Agreement to reduce cost and time delay related to procurement; enforced Operational and Financial Guidelines for Partners - Mandatory for downstream partners; and use of a procurement agent appointed by DFID for any procurement above £3000. There have been five audits of AAWAZ since its inception and no procurement related issues have been highlighted.

Selected unit costs of outputs
- 1,481 (633 KP, 848 Punjab) women assembly members were engaged at a cost of £7 per woman across 45 districts and were equipped with necessary leadership skills to act as mentors and role models to guide their respective communities;
- Unit cost of a Khuli Katcheri (open town hall meeting) at a union council was estimated at £73;
- Cost per village development plan (4,500) estimated at £9
- Aagahi Centres (450) were upgraded and converted into advisory bureaus and safe spaces at a cost of £99 per centre to generate constructive dialogue among communities on issues related to inclusion, gender, gender based violence, conflicts and accountability.
- 227,491 citizens mobilised at a cost of under £170 over the life of the programme (£30 p.a.) per citizen
- 8.31 million direct beneficiaries at a cost of under £50 over the life of the programme (<£0.8 p.a.) per citizen
- Approximately 10 million citizens reached by the programme at a total cost of £3.80 (<£0.7 p.a.) per citizen
- Programme spend = approximately £150,000 per district p.a.

Efficiency: AAWAZ exceeded the output objectives of its year 4, 5 and 6 work plans, in line with the allocated budget. Key to the efficiency of the TA team was them achieving their outputs by influencing and improving the way both demand and supply side interacts and delivers better.

The Punjab Provincial Government 2017-18 budget for service delivery is £4.5[20] billion; for KP it is £2.66 billion[21]. DFID’s investment of £38.6 million (representing under 0.1% of Punjab and KP budgets) will help deliver better results and use of both provinces’ service delivery budgets – through improved accountability and increased communication with citizens.
[20] Punjab Citizens Budget 2017-18: PKR 263.1 billion for health; PKR 345.2 billion for education; and PKR 72.6 billion for local government and community development
[21] Khyber Pakhtunkhwa Citizens Budget 2017-18: PKR 56.2 billion for health; PKR 168.08 billion for education; and PKR 175.58 billion for local government and community development

From a programmatic perspective, all expenses were classified into three primary heads – fees, operations or programme expenses; and programme activities. In particular, the review looked at management office cost as well as operations cost as percentage of total budget and both were found to be well within 20% range. The total MO cost was 16.51% of the total project expense.

Effectiveness: AAWAZ programme effectiveness was assessed both through a cost benefit analysis and case study approaches. The latest updated CBA demonstrated a rate of return of 97% while the net present value of benefits was estimated at £210 million over 15 years. To bring these numbers alive, a case study approach was also adopted and two selected examples are shared below:

Women’s Empowerment & Leadership – AAWAZ established women assemblies in all 45 districts across the two provinces. These women assemblies provided a one of a kind model to organize marginalized women, build their capacity, mobilize their advocacy efforts and channel them towards locally identified development needs. AAWAZ conducted a series of six training sessions in Swat district at a cost of PKR 199,500 (£1,550), while the total cost of the initiative stood at PKR 9,450,000 (£73,426) across 45 districts.
- AAWAZ Women Assemblies were established at a cost of £1,600-1,700 per district. Each £1 of DFID investment helped create a women-centric platform for almost 236 women.
- Through women assemblies, 1,403 women were trained in pro-women laws/rights, budget knowledge and tracking, gender and political participation, at a cost of £1 per woman through six training sessions and were equipped with necessary leadership skills to act as mentors and role models to guide their respective communities. Every £100 of programme investment in women assemblies resulted in training 2 women in special laws/rights, budget knowledge, gender and political participation so that they can act as champions in their respective communities as well as making 130 women aware of women’s rights.
- In Swat, the investment of £1,550 in women assemblies resulted in additional allocation of £21,756 of public funds for women-specific schemes, reflecting a fourteen fold return.

Better Service Delivery through Greater Accountability – More than 160,000 women and 80,000 socially excluded men participated in 2,243 (964 KP, 1,279 Punjab) Khuli Katcheries at a total cost of £254,600 for the events and the follow up of the issues identified and a total of £840,000 for the formulation of village development plans (VDPs). Costs are as follows:
- Each VDP: £186
- Each Khuli Katcheri: £135
- Cost of directly engaging one citizen in participatory planning and developing the VDP: £4.
- Cost of one citizen participating in a Khuli Katcheri: £2.
- Raising a demand through a Khuli Katcheri: £12; Resolving the issue: £21.
- In total every £100 spent on VDP and Khuli Katcheri resulted in benefitting 109 households and approximately 639 citizens.

At impact level, AAWAZ contributed towards increasing the percentage of Pakistanis who felt ‘quite safe’ or ‘very safe’ from 38% to 69% with an overall implementation cost of £38.6 million – a programme cost of £1.24 million per percentage point of population, given a population of 206 million. [22] Additionally, the programme contributed towards improving Pakistan’s V&A score in Worldwide Governance Indicators (WGI) from -0.88 to -0.69 and improving the international Gender Gap Rank of Pakistan by two positions.
[22] GBP 1.24 million for 1% of 206 million (2.06 million)

Equity: AAWAZ is an equity-based programme, focusing on women’s empowerment and participation, improved service delivery for marginalised communities, reduced persecution of minorities and improved rights of people with disabilities and transgender people. The results of the programme are monitored against their impact on these marginalised groups. A case study highlights the following benefits for the Christian community.
A Christian community was deprived of their land entitlements, despite living on that tract of land since 1919. Without proof of residence, they could not register their CNICs, nor could they build a church on the land, isolating them from the networks of Christians across Pakistan. AAWAZ helped the representatives of the community engage with decision-makers at the local, provincial – even federal levels for seeking a solution. Three Khuli Katcheries – at a total cost of £220 - were held coupled with a series of meetings. After months of persistent advocacy and follow-up with concerned officials, eight acres were approved with 100 plots for housing including 1 kanal[23] of land reserved for a centrally located Church. By February 2018, 74 houses had been constructed and land rights handed over to 33 families who were living there. A functioning water supply was established and the church nearly built. Each housing plot is valued at roughly £1,000, likely to increase with a major road by-pass being constructed nearby. The whole community now owns property worth £100,000, lifting them out of poverty.
[23] A unit of measuring land in Pakistan and India. A Kanal is generally equivalent to one eight of an acre or 4500 square feet.

E: RISK

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

The programme risk remained moderate throughout the course of the programme. It was primarily due to the robust risk identification and risk management. It is important to note here, while the country had several high level violent incidents, the programme continued to work on these sensitive issues. The primary reason was higher levels of trust between the local organisations and their approach to conflict pre-emption (prevention) instead of conflict mediation. The programme also focused on diversity as a positive given, instead of a linear, narrow definition of inclusion. Furthermore, DAI developed and implemented a management information system (MIS) system for data analysis of the programme activities. Presentations on the MIS system were also made to provincial governments in a move to ensure complete transparency regarding AAWAZ operations, reduce some risks and to build and maintain good institutional relations.

Overall risk rating: moderate.
The risk is moderate overall.

Overview of programme risk
AAWAZ divides its risks into four different categories. These are: (i) External risks (ii) Activity risks (iii) Financial risks and (iv) Human resources risks. The programme team have documented all their risks in a risk register which is regularly reviewed and updated by the programme team.

External Risks: Since AAWAZ works on raising awareness about sensitive social issues, including the rights of women and minorities, there is a constant threat of backlash from extremist segments. In many areas, the operations are conducted with a low profile to avoid harmful attention, whilst in other areas, extensive procedures have to be followed to gain government permission to conduct activities. This has caused delays in implementation and at times reduced the effectiveness of activities. The programme also faces access risks from time to time, due to the shrinking operating space for civil society organisations, particularly in southern parts of Punjab and KP.

To mitigate these risks, the programme has adopted a three pronged approach to ensure buy-in and raise awareness about the objectives of the programme at all levels. First, it has brought on board a consortium of partners with strong local links, who are able to provide an early warning system of their own for any signs of backlash. Second, the team has ensured effective coordination with government at multiple levels. Third, it has engaged highly socially credible platforms like mosques to raise awareness about the programme.

Delivery Risk: The risk of ineffective implementation was reduced after the 2014 midterm review. The changes made included ensuring that (a) the programme was technically robust and strategic; (b) the monitoring and evaluation (M&E) function contributed to the delivery of the programme; (c) a revision of the approach to output 2; (d) improved risk management and (e) increased involvement of DAI headquarters. In September 2014, to track compliance with the recommendations, DAI initiated an Annual Review Action Plan (ARAP). By March 2015, DAI had changed the structure of the MO to include two Deputy Team Leaders – one technical and one for finance and operations and recruited a cadre of technical experts into the MO. The M&E manager was replaced. Contractual terms between DAI and the implementing partners were tightened up and a new Project Director, Technical Director and Programme Manager brought in to work intensively from DAI Headquarters. This laid the foundations for the successful implementation of the programme and led to its progressive achievement moving from a B in 2013 to an A++ in 2017.

The programme has completed its last year and there is a risk that many AAWAZ-created networks will not be able to operate effectively once the programme ends in 2018. To ensure that these networks are able to continue without DFID’s support, AAWAZ has focused on forming a strong network of trained volunteers who will be able to continue the work with minimal supervision. Moreover, women assemblies have been established at district levels, and it is expected that these networks will continue with the advocacy campaigns. Some members of ADFs have secured roles in local governments and this is also an avenue to sustainability. It is expected that members will be able to use these new platforms to build support for inclusive democracy and sustainable development. The Consolidating Democracy in Pakistan programme is directly working with ADF and AAC to maintain outreach to women and the most excluded for voter registration in advance of the general election 2018 with 256 out of 450 AAC being transferred to CDIP for their use.

Financial Risk: AAWAZ has managed its financial risk by putting in place a strong financial management system. They have also ensured well defined procurement polices along with strong internal controls and accounting systems as summarised above. All audit reports were unqualified to date.

Human Resources risk: It was critical that the AAWAZ programme retained high quality human resources to deliver work in the final year of the programme. DAI managed this well with a phased approach to letting staff go as the major final year results were achieved.

Outstanding actions from risk assessment: none.

Safe guarding of Beneficiaries:

AAWAZ deliberately decided not to work with persons under the age of 18 recognising that working with children would require the upskilling of downstream CSO partners to ensure that children are protected from abuse and exploitation.

AAWAZ used the Aagahi centres as safe places for women to meet and ensured from 2014 that female resource people worked at the centres. This mitigated against the risk of harassment of women.

AAWAZ adhered to the do no harm principle and sought to ensure that no person engaged in the programme was put at risk. A number of actions were taken in this regard, such as minimising UKaid branding at the village level and working with existing community based organisations to sensitively roll out training on gender, conflict, community harmony etc.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

AAWAZ was designed to be implemented through national civil society organisations (CSOs), with DAI as the Management Organisation (MO). For the first two years, there were two consortia; Consortium A was comprised of four CSOs (Sungi Foundation, Aurat Foundation, SAP-PK and Strengthening Participatory Organisation (SPO)) and was responsible for the implementation of programme activities in the field. Consortium B was comprised of one CSO (Sustainable Development Policy Institute (SDPI)) and was responsible for the Policy, Advocacy, Research and Results (PARR) facility, which aimed to synthesise information and findings from AAWAZ and to build a robust evidence base around community voice and empowerment, social change, policy influence and government reform.

The 2013 Annual Review found that the design of two consortia was not working and recommended that the PARR function be brought under the guidance of the MO. This was implemented by the forming of a Strategic Learning Unit within the MO and strengthening its M&E function.

The 2014 Annual Review recommended a number of changes. These included ensuring that (a) the programme was technically robust and strategic; (b) the monitoring and evaluation (M&E) function contributed to the delivery of the programme; (c) a revision of the approach to output 2; (d) improved risk management and (e) increased involvement of DAI headquarters. In September 2014, to track compliance with the recommendations, DAI initiated an Annual Review Action Plan (ARAP). By March 2015, DAI had changed the structure of the MO to include two Deputy Team Leaders – one technical and one for finance and operations and recruited a cadre of technical experts into the MO. The M&E manager was replaced. Contractual terms between DAI and the implementing partners were tightened up and a new Project Director, Technical Director and Programme Manager brought in to work intensively from DAI Headquarters.

Output 2 was significantly revised to shift from conflict mitigation or conflict resolution to ‘pre-emption’ (prevention) of violent conflict, not least to protect the human rights of women who were involved with AAWAZ at the village level.

The programme’s theory of change was revised to ensure a clear pathway from output to outcome and to give greater guidance to the delivery teams.

DFID and DAI also recognised the need to improve the attendance by women and minorities in the AAWAZ Aagahi Centres (AACs). A comprehensive overhaul resulted in mass replacement of the male ‘Resource Persons’ with local women and re-location of the AACs to locations where women and minorities were more likely to attend.

The programme logical framework was revised at several points. AAWAZ conducted a baseline across all programme districts and created a results framework that allowed evidence to be created and used by the programme as well as to track qualitative and quantitative changes over time.

Value for Money was integrated into the programme design in 2015 and has since become a prominent feature of reporting, evidence-gathering and learning for both AAWAZ and DFID.

From the start, AAWAZ put learning and adaptation at the centre of all decision-making. In relation to management and staffing, the Programme had a Steering Committee, which included DAI, the four lead implementing partners and DFID representatives to provide technical leadership and oversight. This committee was complemented by a programme management committee. Learning and adaptation took place in AAWAZ at three levels: the work of implementing partners, the work of AAWAZ programme team; and the enabling environment of the programme as a whole. Achieving this involved:
- Removing the obstacles to adaptation such as delivery against a pre-set costed work plan during programme review and quarterly review meetings;
- Creating and investing in space for structured reflection and learning. Meetings of AAWAZ Steering Committee, Programme Management Committee and Working Groups provided opportunities to use lessons for planning and strategic direction.
- Developing systems for quality assurance of decision making and reporting in ways that reinforce good practice internally and met DFID requirements.
- Developing systems at all levels for effective interaction with government in order that demands raised for better service delivery are met.

Programme budgeting: The programme budget for each phase (inception, implementation and extension) was agreed separately with DFID. This budget was divided into the following 3 components: Fee, Operations and Programme.

A detailed annual Costed Work Plan (CWP) was prepared by MO for the three outputs of the programme component in consultation with the programme leads of implementing partners. The CWP provides activity level targets, unit cost and budget estimates for each implementing partner. Notes providing explanations of unit cost and detail of the proportional costs for each tier of intervention (village, union council, tehsil etc.) are also provided as part of the CWP. At the start of each year, the CWP was shared with DFID representatives for approval. Once the CWP was approved, it was shared with implementing partners for execution of activities as per the plan.

Originally AAWAZ had an overall budget of £33,850,000 to cover fees, operations and programme activities during inception and implementation. Through the contract amendment on 12 May 2017 for extension, DAI was provided with additional £4,751,899 which increased the overall budget to £37,331,040 (£4,600,000 for extension and £151,899 transfer from M&E component to the implementation component, with the removal of £1,270,859 from procurement funds).

At the time of this PCR, AAWAZ’s total spend rate is 99.5% including a spend rate of 99% on programme activities. The breakdown of budgets in details is as below:

AAWAZ Total Budget Spend
	Budget	Total Spend	% Spend
Fee	£19,398,740	£19,311,500	100%
Operations	£5,598,089	£5,429,008	97%
Programme	£10,787,691	£10,652,547	99%
Response Fund	£1,546,520	£1,546,520	100%
Sub Total	£37,331,040	£36,939,575	99%
Procurement	£1,270,859	£1,270,859	100%
Sub Total	£1,270,859	£1,270,859	100%
Total	£38,601,899	£38,210,434	99%

AAWAZ Total Budget Spend per Implementing Partner
	Management Organisation			Implementing Partners			Programme Analysis, Research & Results (PARR)
	Budget	Total Spend	% Spend	Budget	Total Spend	% Spend	Budget	Total Spend	% Spend
Fee	£4,715,173	£4,650,083	99%	£11,904,539	£11,894,238	100%	£2,779,028	£2,767,179	100%
Operations	£1,601,018	£1,469,622	92%	£3,564,799	£3,561,740	100%	£432,272	£397,646	92%
Programme	£0	£0	-	£9,840,927	£9,709,079	99%	£946,764	£943,468	100%
Response Fund	£0	£0	-	£0	£0	-	£1,546,520	£1,546,520	100%
Sub Total	£6,316,191	£6,119,705	97%	£25,310,265	£25,165,057	99%	£5,704,584	£5,654,813	99%
Procurement	£35,154	£35,154	100%	£1,056,583	£1,056,583	100%	£179,122	£179,122	100%
Sub Total	£35,154	£35,154	100%	£1,056,583	£1,056,583	100%	£179,122	£179,122	100%
Total	£6,351,345	£6,154,859	97%	£26,366,848	£26,221,640	99%	£5,883,706	£5,833,935	99%

Budget monitoring: Each partner submitted monthly field expense reports (detailing transaction-level expenses incurred against each budget head) by 20th of each month, against the advance received from MO. The Compliance and Agreement Officer prepared financial details (including partner level budget vs actual analysis) which were reviewed by the Senior Manager of Finance and Operations including variances from budgeted expenditure.

Due to the large scale targeted outreach of this programme, staff salaries consistently remained the major cost driver of this programme at 50% (including the MO and partner organisations). Operational expenses represented 18% of the budget and programme activities - 32%. Support to AAWAZ Aagahi Centres (AACs) remained the major cost driver under programme activities.

AAWAZ programme demonstrated strong financial management both at the Management Organisation and downstream partner level. A multi-level control system including due diligence, external audits, compliance and spot checks was put in place to identify any deviations from contractual agreements, other irregularities and to suggest measures to reduce financial risk. AAWAZ produced a wide range of detailed financial data and analysis that meant the Senior Management Team (SMT), Programme Management Committee (PMC), AAWAZ Steering Committee (ASC) and DFID were able to relate finances to the programme results in order to improve programme delivery and value for money (VfM).

Organisation structure: The overall responsibility of the finance function is with the Deputy Team Leader/Head of Finance and Operations who is assisted by the Senior Finance and Operations Manager. There were 3 other staff who work under the supervision of the Senior Finance and Operations Manager. The key responsibilities of each position are stated in the Finance Manual and are made part of their respective job descriptions.

The Project Manager at the DAI UK Office provides guidance and oversight to the Pakistan team and is also responsible for the financial reporting of the AWAAZ programme to DFID in liaison with the Pakistan Team. DAI implementing partners are responsible for managing their accounting and share a monthly field expense report to DAI against any advances received.

Policy framework: The finance and accounting Manual (July 11, 2012) serves as a policy framework for steering the financial matters of DAI. Project Schedule of Authorities (PSOA) are defined for the AWAAZ programme which provide authorities for initiating, reviewing and approving different types of transactions including procurement, treasury, payroll, field expenses etc.

DAI strengthened the capacity of the MO and all downstream partners to identify, tackle and report fraud. This necessitated the appointment of a qualified, full time finance team for the AAWAZ programme and all implementing partners. In line with DAI’s own ethical policies and practices, the MO worked with all partners to revise their whistle-blower policies and improve their reporting / response to fraud issues. Selection of all Response Fund grantees was made in accordance with DFID’s procurement policies. DAI also mitigated the fiduciary risk by ensuring payments upon completion of pre-agreed milestones, and conducted delivery chain mapping at DFID’s request. DAI strengthened the quality and performance of financial management on the basis of recommendations from annual reviews, external audit observations and internal compliance audit findings. For example, financial managers at DAI were empowered to continue rigour on compliance and financial management. As a result, partners’ risk rating in the recent external audits improved from high/medium to medium/low.

DFID only allows for the procurement of services by AWAAZ Pakistan, with the procurement of goods for the programme being made directly by DFID Pakistan via Crown Agents. The Governing Policy on Procurement and Inventory Management provides the necessary framework with respect to procurement. There are Procurement Guidelines in place which provide procedural details on procurement planning, requisitioning, procurement methodologies for goods and related services (open tendering method, quotation method and direct purchase method), enlistment of suppliers, post tender negotiations, procurement methodologies for consulting services, basis of selection, single source selection and a conflict of interest declaration.

DAI and all CSO partners managed their assets using system based asset registers where the assets were recorded and updated regularly. The register recorded complete information of all the assets including their quantity and the users. Asset codes were allocated to each asset to be used as the unique identifier. Internal and external spot checks and assessments validated that all of these assets were found present, well maintained and properly tagged.

DAI entity audit: An external audit for financial year ended 30 June 2016 was conducted by Rafqat Mansha Mohsin Dossani Masoom & Co., a Chartered Accountancy firm. The latest external audit report was issued on the financial statements for the year ended June 30 June 2016 where an unqualified (“clean”) audit opinion was given.

Programme audit: An external audit of the financial statements of DAI – Pakistan (AWAAZ programme) has been conducted by Ernst & Young Ford Rhodes Sidat Hyder, a Chartered Accountancy firm. An engagement letter is signed setting out the terms and conditions for the external audit engagement. The last external audit report was issued on the programme financial statements for the year ended 30 June 2016 and an unqualified (“clean”) audit opinion was issued.

Date of last narrative financial report	20 May 2017
Date of last audited annual statement	20 May 2017

G: MONITORING, EVIDENCE & LEARNING

The review team met with the M&E team of the MO and discussed the details of the MIS system it put in place to manage the data analysis of programme activities. In their meetings with various stakeholders (beneficiaries, consortium partners and government counterparts) the review team verified the evidence projected by the MIS system.

Monitoring

AAWAZ was an adaptive programme with monitoring, learning and adaptation at its centre. DAI developed a comprehensive and adaptive Monitoring and Evaluation (M&E) framework which supported timely decision-making, ensured project accountability, and provided a robust foundation for evaluation and learning through the lifetime of the project. Underpinned by the hiring of an M&E specialist by DAI the multi-layered M&E approach included direct process and results-based monitoring, independent and third-party monitoring and evaluation; value for money framework at outcome and outputs levels; M&E with DFID-funded partner projects implemented by DAI; joint M&E with Government of KP and engaging with partners’ own M&E systems. A number of M&E initiatives, innovations and adaptations to the programme were key success factors for the programme.

At the outset, the programme established a theory of change, a programme logframe and an M&E Plan. The baseline survey conducted in 2014/15 provided solid evidence on targeting performance against logframe indicators. This evidence also provided the basis to track results that were monitored by a third-part consultancy firm helping DAI on the annual follow-on surveys. Subsequent to the DFID Annual Reviews, the programme logframe was revised, some new indicators were added and the milestones were re-aligned for some indicators. Data collection and management tools were updated complying with data quality parameters.

DAI developed and implemented a management information system (MIS) system for data analysis of the programme activities. Presentations on the MIS system were also made to provincial governments in a move to ensure complete transparency regarding AAWAZ operations, reduce some risks and to build and maintain good institutional relations.

Throughout the programme implementation period, independent monitoring played a key role in delivering better impact and raising capability of implementing partners to monitor. Beneficiary monitoring and qualitative assessment remained the centrepiece of the AAWAZ M&E framework. The M&E team also conducted spot checks and support visits with a special emphasis on qualitative issues. All visits included a debrief to the programme and field team including suggestions for solving problems. Visit reports were shared with the appropriate member of the M&E working group, district coordinators, national programme managers and sometimes programme directors shared findings from visits and lessons learned included in the quarterly review meetings.

DAI directly engaged with all partners through quarterly reviews, ad-hoc, coordination and M&E working group meetings. This resulted in new levels of analytical and critical thinking across the consortium partners M&E specialists and enabled honest discussion on challenges, lessons and limitations and opportunities for innovation and adaptation.

In 2016, DAI established a monitoring and evaluation working group of all DFID’s governance programmes managed by DAI, to build synergies, coordinate and establish an information sharing protocol. This working group helped to improve the overall outreach of programmes and avoided duplication of efforts.

The AAWAZ monitoring and evaluation team also worked closely with the KP government to develop a standardised evaluation framework in 2017. The team was made part of the AAWAZ-GoKP monitoring and evaluation working group, in which some members were representatives of KP Planning & Development (P&D) Department and Monitoring and Evaluation Directorate. This group not only helped in building a shared understanding about the programme but also contributed for course correction as a result of joint M&E visits and surveys.

Provincial government was sceptical, of AAWAZ activities during the first half of the programme’s implementation. This was due in part to the sensitive issues that the programme tackled including prevention of violence against women, conflict pre-emption, rights of religious minorities and pro-women legislation. This was overcome in KP through regular meetings by the MO with government officials including the provincial M&E department and through the establishment of a project steering committee for the province with an MOU. In Punjab, high level consultations with the provincial Home Department helped to explain the rationale for the programme and assure the government that it was acting in line with their priorities (namely the national action plan on the prevention of terrorism). This engagement led to a government letter of support being issued to all districts and the sharing of information by AAWAZ partners at local level. This helped to break down mistrust and develop allies within the government for the programme.

A key lesson for any successor programme is to understand the cultural governance differences between both provinces in order to engage early with the main provincial line departments and officials.

Evidence

The M&E team carried out Data Quality Assessment (DQA) across all 45 districts. This tool enabled the M&E team, male and female forum members, women assembly members and field teams to assess whether the data collected met the standards defined in the monitoring and evaluation framework of AAWAZ in terms of reliability, validity, integrity, precision and timeliness. As a result, an evidence-based quantitative data collection system was put in place across all districts.

To triangulate results and better verify progress, a system of qualitative and quantitative assessments of specific aspects of the programme was developed and implemented. The M&E group completed ten qualitative assessments in all programme districts. Key findings were shared with the programme and district staff during the programme review meetings for necessary follow-up and course correction.

Learning
- A clear theory of change is needed at the outset of programming;
- Robust monitoring, evaluation and results management in voice and accountability programmes increases visibility, ensures that attention is paid to otherwise marginalised issues, and helps communities, government and other development partners to understand the impact of the programme;
- Evaluations and reviews should include assessment of the relationship and process of a management organisation working with implementing partners, including coordination, contribution and compliance;
- DFID’s investment in the 45 programme districts should form the basis of future programming, to build on the human capital and networks, particularly to address emerging priorities such as modern slavery;
- DAI should ensure that learning from AAWAZ feeds directly into the other HMG programmes e.g. Consolidating Democracy in Pakistan programme (CDIP);
- Such future voice and accountability programmes should include a focus on building the role of women in peace building – as peace connectors and in conflict prevention roles;
- The Aagahi Centres should continue to be supported to use their strong networks and experience to provide support to their communities. They should be supported and encouraged explicitly to include disability both as a factor of exclusion and to strengthening the capacity of people with disabilities;
- Increased focus on disability across the whole portfolio, including future voice and accountability programmes should be considered;
- Focussing on a number of priority districts, particularly those that are vulnerable to violent conflict, building on the groundwork laid in the final years of the AAWAZ programme should be considered;
- Adequate resources should be allocated by development partners and government for building the evidence base and knowledge on working with youth, on modern slavery, minority communities and violent conflict;
- The wealth of knowledge from the AAWAZ Strategic Learning Unit (research and the Response Fund project results) should be made publicly available for future programming, particularly in the areas of modern slavery, religious minorities, transgender and youth;
- Under future voice and accountability programmes, the management of knowledge and integration of research should be structured across the programme, coupled with a clear and robust communications strategy and plan;
- Lessons and good practice from AAWAZ’s interactions with government at provincial and district levels should be harvested and applied to work with other district and provincial governments;
- More investment in the capacity of CSOs to work at grass-roots level with communities, would ensure conflict sensitivity, gender equality programming and social inclusion approaches are addressed;
- Future voice and accountability programmes should be able to support provincial or national CSOs to capitalise on their knowledge and networks, while supporting their increased organisational management capacity.
- Invest in young people. Build on the gains made in AAWAZ, particularly with the Youth Circles of Influence and the young women and men who participate in the AAWAZ Forums or who are resource persons in the Aagahi Centres;
- In future programming with youth, ensure a 50/50 gender balance for youth leaders, as well as equitable representation in youth-led organisations or events;
- Invest in innovation through digital tools and social media, as well as person-to-person engagement, training, youth conventions to allow for networking and mutual learning. Ensure that young people understand and are able to manage risks to do with advocating for tolerance, whether in educational settings or communities;
- All future programmes should support district governments to take on and embed the Early Warning Systems;

We now have an approval for a £39.5 million AAWAZ II programme for five years (2017 – 2022). The AAWAZ II programme will work with government and local communities to promote the rights of children, women, youth, religious minorities and excluded groups to strengthen their control over their own development. The programme has a particular focus on the issue of modern slavery, to which marginalised groups are extremely vulnerable. The programme aims to reach 7 million beneficiaries across the provinces of Khyber Pakhtunkhwa (KP) and Punjab. Leaning from the AAWAZ programme will be carried forward in the AAWAZ II programme.

Progress on recommendations from annual reviews for this programme

Sr	Key Recommendations	Success Criteria	Update on Progress / (21-Mar-18)
i	Ensure sustainability and build beyond this foundation	Sustain engagement in all 45 districts till January 2018.	Done
		Develop a brief about different options for AACs institutionalization and sustainability beyond AAWAZ	Done
		Build alliance with government(s) and other projects/institutions for the use and sustainability of AAWAZ Aagahi centres:	Done
		Pilot testing different institutionalization models as per local opportunities for 20% of AAC in intensified districts and documenting and sharing learning across AAWAZ and others.	Done
		Continue supporting local civil society actors to pursue local development agenda through ADF to continue engaging with communities.	Done
ii	Deepen the change: inclusive development	Develop and focus on the three emerging thematic areas this year: Modern Slavery, Women Participation in Electoral Political and Youth Engagement.	Done - Developed and rolled out at field level
		Develop one page briefs on modern slavery approach as well as on other prioritized interventions including youth engagement, women leadership in political processes.	Done - Developed and rolled out at field level
		Deepen engagement in specific priority communities in 21 intensified districts (like those that are conflict affected) and capture learning for wider sharing.	Done - Peer Learning- completed
iii	Build the evidence base and maximise learning: youth, modern slavery, violence and religious minorities.	Learning from AAWAZ feeds into the new Consolidating Democracy in Pakistan Programme.	Done - Process completed MoU signed with CDIP
		Support Aagahi centre resource persons to build a strong network and share learning on providing consistent support to their communities (including disability).	Done
		Ensure deeper and more regular sharing of lessons across the consortium through ASC and PMC to further improve quality in delivery during the extension year.	Done
		Share one pagers on MS, EWS, YCI, WL with district teams	Done - One pager shared with PMC
		Action research on multiple identity	Done
		Analysis of Gender Road Map (GRM) to understand power dynamics at household level and has it brought an shift in power relations	Done
iv	Capitalise in investment in young people.	Ensure 50/50 gender balance for youth leaders in the extension phase.	Done
		Deepen work with youth leaders and youth circles of influence through face-to-face meetings and youth conventions for networking and sharing lessons learnt.	Done
		Training for youth leaders on managing risk around speaking out for tolerant and inclusive societies as their role grows (esp. religious minorities)	Done
		Maximise use of digital tools (e.g. WhatsApp, Facebook)	Done
v	Deepen connections with other programmes and government.	Deepen connections with line departments in AAWAZ districts to help making early warning system more embedded.	Done
		Build on discussion with DFID’s Sub-National Governance Programme and CDIP to explore synergies and maximise on DFID’s investment in supporting the people and government of both provinces to form inclusive budgets.	Done
		Ensure communication with the district level and provincial government of Punjab and KP.	Done
vi	Strategic questions & efficiency	Impact weighting for output 2 to be increased in light of its increased work; Log-frame to be revised accordingly.	Done - Log-frame revised and approved.
		Continue to conduct joint monitoring exercise in partnership with consortium members and government departments (if asked for) across the programme.	Done
		MoU to be signed with KP Government.	Done - MoU with KP government signed
		Asset disposal plan to be implemented.	Done